Programme Completion Review

Title: India Infrastructure Policy Fund (IPF) / Infrastructure Technical Cooperation Facility (ITCF)
Final Programme Spend £ (full life): £5.34 Million	Review Date:	30/05/2024
Programme Code: 203908	Start Date: / 18/07/2013	End Date: / 31/03/2024

Summary of Programme Performance

Review Period	2013-14	2014-15	2015-16	2016-17	2017-18	2018-19	2019-20	2020-21	2021-22	2022-23	2024 PCR
Programme Score	A	A	A	A	A	B	A	A+	B	B	A
Residual Risk Exposure Rating	Low	Low	Low	Low	Mod-erate	Mod-erate	Mod-erate	Mod-erate	Mod-erate	Mod-erate	Mod-erate

DevTracker Link to Business Case (and any addendum):	http://iati.dfid.gov.uk/iati_documents/4941197.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.dfid.gov.uk/iati_documents/5043205.xls

List of Abbreviations
ADB	Asian Development Bank
AR	Annual Review
BII	British International Investments
BIM	Building Information Modelling
BIP	British International Partnerships
CoE	Centre of Expertise
CPSE	Central Public Sector Enterprises
DEA	Department for Economic Affairs
ECoP	Economic Cooperation Programme
FCDO	Foreign Commonwealth and Development Office
GoI	Government of India
ICE	India Challenge Enabling Fund
IDS	International Development Strategy
IFS	Infrastructure Finance Secretariat
IIPDF	India Infrastructure Project Development Fund
IMSC	Inter- Ministerial Steering Committee
IPA	Infrastructure and Projects Authority
IPF	Infrastructure Policy Fund
IPP	Infrastructure Policy and Planning Division
ISD	Infrastructure Support and Development
ITCF	Infrastructure Technical Cooperation Facility
IWG	Infrastructure Working Group
KPMG	KPMG India Private Limited
MoF	Ministry of Finance
NIP	National Infrastructure Pipeline
NMP	National Monetisation Pipeline
ODA	Official Development Assistance
PDC	Project Development cells
PPP	Public-Private Partnership
PPPAC	Public-Private Partnership Appraisal Committee
PRO	Programme Responsible Owner
PSA	Project Sponsoring Authorities’
PwC	Pricewaterhouse Coopers
QII	Quality Infrastructure Indicators
RFP	Request for proposals
SGB	Sovereign Green Bond
SoPs	Standard Operating Procedures
SP	Service Provider
SRO	Senior Responsible Owner
TA	Technical Assistance
UKEF	UK Export Finance
VfM	Value for money
VGF	Viability Gap Funding
WB	World Bank Group

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved.

The Infrastructure Policy Fund programme was created in 2013 to support the Government of India (GoI) to improve the policy and regulatory framework, to create financing solutions for infrastructure projects, including by using foreign investment in infrastructure. The programme provided technical assistance (TA) to the Department for Economic Affairs (DEA) of the Indian Ministry of Finance (MoF), focussing on the divisions that deal with infrastructure and PPP (Public-Private Partnership) policy, i.e., Infrastructure Support and Development (ISD) and Infrastructure Policy and Planning (IPP) Divisions, which together constitute the Infrastructure Finance Secretariat (IFS). IPF became known as the Infrastructure Technical Cooperation Facility (ITCF), to avoid confusion with the division of Department of Economic Affairs (DEA) called the Infrastructure Policy and Finance Division. This programme was the UK’s primary programme for delivering technical assistance to the Indian government in infrastructure sector and covers all these requirements from policy, institutional process, and capacity perspectives.

The aim of the programme was to enable access to global expertise in private sector approaches for infrastructure delivery and financing by DEA. The UK partnered with DEA to resolve key challenges, mutually identified in 2013, in the infrastructure development and financing market in India. These included significant gaps in infrastructure, limited financing appetite in the domestic banking system, absence of debt with sufficiently long tenors, administrative bottlenecks, gaps in institutional capacity and regulatory framework, and slow offtake of Public-Private Partnerships (PPPs) with the exception in a few sectors. The programme was set to conclude in March 2020 but was extended twice until March 2025. In 2023-24, a decision was taken to offer a consolidated UK offer to the Ministry of Finance; all streams of support, including ITCF were brought under a new Economic Cooperation Programme (ECoP). ITCF, as a standalone intervention, was concluded. The cumulative spend at the programme closure was £5.34 Million out of the total value of the programme £10 Million.

The expected impact of the programme, as defined in the business case was to increase private sector investment and confidence in the infrastructure sector. This was sought to be measured through the growth rate of infrastructure PPPs in the country. The target was to increase the growth rate by two percentage points over the life of the programme. The impact was achieved ahead of time in 2015-2016, but then the growth rate plateaued and then slowed down due to various macro-economic and financial market influences. However, the focus of Government of India on infrastructure investments is evidenced by the £1.4 Trillion National Infrastructure Pipeline, 17% of which is expected to be delivered through PPP and other forms of leveraging private investment, the number and value of PPPs is expected to increase significantly. The increased confidence of private investors in the infrastructure sector was expected to be measured using the Doing Business Ranking by the World Bank Group. Due to the discontinuance of this index, the KPI was amended to be measured using the infrastructure pillar of the Global Competitiveness Index. India’s ranking has improved, as measured through this index, from 84 in 2013-14 to 70 in 2019-20.

The key achievements of the programme during its implementation include the following:
1. Strengthened policy and knowledge framework for Public Private Partnerships (PPPs) in India.
2. Effective Contribution to the development, management, and supervision of the key infrastructure investment platforms of Government of India, i.e. National Infrastructure Pipeline and National Monetisation Pipeline.
3. Demonstrated and facilitated PPPs in nascent sectors like solid waste management, wastewater management, ropeways, grain storage, schools, and hospitals.
4. Enhancement of institutional knowledge in infrastructure ministries through development, dissemination, and training on guidance for management of various aspects of the PPP lifecycle.
5. Contribution to enhancing the flow of private investment in infrastructure sector through development of a range of instruments including revised Viability Gap Funding scheme, revised Project Development Funding scheme and inputs for the development of the Sovereign Green Bond Framework of India. During the programme tenure, the department was supported for 201 PPP project proposals, approved by the PPP Appraisal Committee, aggregating to approximately GBP 40 billion. At the same time, during the programme tenure, VGF was approved for 56 projects, with total cost of GBP 4.3 billion and approved VGF amount of GBP 1.1 billion.
6. Enhancing private sector interest in PPPs in infrastructure, especially in nascent sectors mentioned above.

Major lessons learned, evidence generated and recommendations.

Major lessons learnt and evidence generated for future programmes:
A flexible and responsive approach is useful in efficient programme and relationship management. The programme team was able to reprioritise its focus based on the evolving nature of the Indian infrastructure sector. In the initial years of the programme delivery, focus was on scaling up of investments in economic infrastructure sectors including roads and bridges, airports, and ports. However, as the PPP programmes in these sectors matured, the focus in the programme shifted to enhancing the quality of contract management and showing use of PPPs in social infrastructure sectors. Further, during the last three years of the programme, the focus expanded beyond PPPs to broader financing approaches in the infrastructure sectors, especially climate finance. This shows the importance of keeping track of the context in which a programme operates and being open to reprioritise as the target sectors evolve and the original problem statement shifts.
In addition, multiple dialogues among different stakeholders of the PPP ecosystem, including government sponsors (central, state, and local), financiers, developers, and professional delivery partners were facilitated through the ITCF support to seek suggestions and feedback on policies enabling private investment into infrastructure sectors. These helped DEA develop new policies, standard documentation, and guidance to help facilitate private investment in infrastructure sectors.
1. Programmes with long-term strategic outcomes benefit from visibility of resources covering their intended tenure. The latter years suffered significant budget uncertainty. This absence of budget certainty caused the design of annual interventions, with short term, at times disjointed focus limiting outcomes.
2. Programmes in the same areas as active multilateral or bilateral programmes are strengthened by a formal coordination mechanism. Absence of consistent coordination mechanisms lead to disjointed or overlapping interventions being delivered with the same counterpart institution, also leading to opportunities for collaboration being missed. Partner Governments in this case, Government of India could assume an active role in coordination among the development partners or alternatively the donors should invest more in coordination ourselves.
3. The programme has shown that it is possible to inform and support key economic and infrastructure related policies with limited technical assistance by using available resources in a focussed manner. It was made possible due to close working relationship with the partners and clearly defined interventions with specific outputs.
4. Often There was limited visibility of the UK support in some significant achievements supported by the programme. This was largely because the delivery partner and counterpart department were the interface for all external communications. As a result, some of the direct outcomes of the ITCF programme were not attributed to UK support which led to lower-than-expected recognition of UK as a partner among key stakeholders. There was scope for the UK Team to require the delivery partners to better acknowledge UK visibility in all products, deliverables, and outreach communications.
5. The business case of ITCF had included focus on low carbon development and climate resilience. Most of ITCF’s interventions focussed on low carbon development and climate finance, with almost no focus on climate resilience, until the last two years of the programmes. This was in line with the priorities of the Government of India and the demand for specific areas of support under the programme. The growing exposure of infrastructure investments on climate events, amidst the increasing frequency and intensity of climate events makes it critical for all future programmes in the infrastructure sector to focus on resilient infrastructure.
Recommendations:
1. ITCF evolved over a decade – this allowed the programme to transition out of the mature areas of PPP policy and intervene in emerging areas like PPPs in social sector. It is recommended that while delivering policy support programmes like ITCF, the programme design should try out an adaptive approach that allows a dynamic response to build on successes and trial innovation which covers areas beyond the conventional solutions to the need of the counterpart.
2. ITCF has laid down the preparatory work for a few areas related to infrastructure finance in India. The Economic Cooperation Programme and other future programmes can build upon the preparatory work and foundations laid down already, especially in the following areas:
  1. Climate finance: ITCF has supported the development of the Sovereign Green Bond Framework and integration of climate considerations into the PPP model documents and guidelines. Future programmes can strengthen the climate finance framework through development of other instruments (e.g. credit enhancement, blended finance, carbon, and green credits) and help make a library of standard clauses for embedding climate considerations in PPP contracts.
  2. Information on infrastructure finance market: ITCF had supported the development and maintenance of a database of infrastructure PPPs in India. Future programmes may extend the scope of the database to all infrastructure finance deals or develop a new information repository that might ensure information transparency and fair access across the sector.
  3. Social impacts of infrastructure projects: ITCF had supported interventions to increase private investment in infrastructure sectors. Future programmes, including the Economic Cooperation Programme can build into the initial work and (1) create enabling and guiding frameworks for private investment specifically for social sectors (2) integrate social considerations in PPP contracts across all sectors (3) develop social KPIs for reporting on infrastructure PPPs (4) disseminate standards on universal access.
3. It is recommended that the delivery partners and counterpart departments ensure comprehensive documentation and reporting process laying down protocols to record each key decision and development in the programme, to ensure institutional memory is retained over the tenure of the programme. This is especially crucial as UK in India develops a comprehensive offer across the mission to the MoF/DEA.
4. The mandatory practices by the FCDO on GDPR, SEAH and Visibility should be reviewed at intervals and supported by a communication plan, esp. with the delivery partners. Protocol set up at the start of the programme to ensure balanced and proportionate representation of UK’s role in the programme can help. This is especially recommended for programmes that interface with a single department for policy support, i.e. where there are limited opportunities for the UK to interface with external stakeholders.
5. While working with limited resources for programme implementation, programme teams were dependent on short term interventions. It is important to ensure that such short-term interventions were integrated and consistent with preceding and later interventions.
6. It is recommended that future FCDO programmes work with a complementary basket of interventions, ideally working with more than one department or institution. This will ensure that the programme’s delivery is not solely reliant on a single department or secretariat. In addition, programme delivery through a complementary basket of interventions will ensure that the programme delivery is diversified across multiple streams, and the programme can adjust to focus on the stream that is working best.
7. In addition, future programmes could focus more on embedding and institutionalising policies, knowledge, and systems in such a manner that the sustainability of these do not depend on any single decision maker or department. That will ensure that long term programmes are able to sustain their results over their tenure.
8. Future programmes in the infrastructure sector should necessarily include a resilience component. This not only aligns with the International Development Strategy of the UK, but also allows the UK Team to share knowledge, expertise and programme elements across the infrastructure programmes and its collaboration with the Coalition for Disaster Resilient Infrastructure.

How this report was conducted
This report was conducted by the FCDO staff with key inputs from DEA, Ministry of Finance, PWC and KPMG, drawing from the lessons documented in the earlier Annual Reviews and learning from the last year of implementation. Regular interactions with DEA and the delivery partners, conferences and dialogues organised around PPP themes also provided opportunities to seek updates and feedback. Feedback and suggestions have been separately asked for from DEA and the delivery partners specifically for this Project Completion Review.
In addition, an independent Lessons Learnt Review of the India Infrastructure Technical Assistance Portfolio was undertaken which has generated a few observations relevant to the ITCF programme. This review included extensive consultation with DEA and the delivery partners. These have been included in this Project Completion Review.

Actions following approval of this report.
All deliverables have been received and there were no invoices outstanding or funds to be recovered from the delivery partner. There were no assets held under the programme.
The results of the Project Completion Review will be integrated into the Economic Cooperation Programme (ECoP), especially on the importance of responsiveness, diverse portfolio of complementary interventions and acknowledging UK support.
A brief lesson learnt session will be organised for all colleagues at the post who are working in infrastructure sector highlighting the evolving nature of the programme in alignment with the changes in the infrastructure sector in India. The lessons learnt session will be planned during the second half of 2024-25 and will be led by the SRO of the programme.

## B: Theory of Change and Outcome Assessment

	Starting point	Result
Budget	£10,000,000	£5,340,000
Timeframe	Approved in 2013-14 / Full implementation started in 2014-15	Concluded in 2023-24
Outcomes	Enhanced capacity to further improve investment climate for infrastructure investments in India	The programme has met the log frame expectation on the outcome. However, there were challenges faced in exact measurement due to discontinuance of the index which was being used as the indicator for the outcome. / The following section provides more details on the achievement of the impact and the outcome, and the challenges in measurement of the same.

Overall assessment of programme outcomes, sustainability and VfM
Outcome indicators	Milestones	Progress
Perception index measuring confidence of private sector and other key stakeholders in infrastructure sector in India	Improve or maintain based on the baseline	Achieved / The indicator defined for measurement of the progress of this outcome was the World Bank Doing Business Indicator. However, that was discontinued in 2021 based on internal findings of reported data irregularities and inconsistencies in the 2018 and 2019 versions of the rankings. / The Ease of Doing Business Indicator improved to 63 in 2020 from 132 in 2013. This was primarily driven by the regulatory reforms implemented by the Government of India focussing on making processes simpler for investors and entrepreneurs. / To validate the improvement in Ease of Doing Business, the programme team referred to other global indicators (esp. due to the data inconsistencies reported by the World Bank for 2018 and 2019). The other indicators also indicate improvement in the perception of investors. For instance, the Competitiveness Ranking by IMD World Competitiveness Ranking (which measures India’s attractiveness for business) shows an improvement from 43 in 2018 to 40 in 2023.
[note] Source: World Bank Group to Discontinue Doing Business Report

At the start of the programme, the PPP market in India had gained significant momentum, but was concentrated around key economic sectors of highways, ports, airports, and power generation. In 2011, other sectors of infrastructure like water, wastewater management, solid waste management, public health and education had experienced sporadic PPP investments but had not experienced the same momentum as the economic sectors.
A significant outcome of the programme has been to help the enabling PPP framework in India evolve in response to the changes in the macro-economic environment and the state of the financial markets. The programme helped restructure PPP models to mitigate the risk perception of financial institutions and banks in response to an increase in infrastructure loans turning into non-performing assets. For example, the annuity and hybrid annuity models were developed and rolled out in many sectors where the investors and banks did not have any appetite to be exposed to traffic / demand risks. The programme also helped revise the viability gap funding scheme for sectors that had a larger viability gap due to higher costs and lower tariffs.
The other most important outcome of the programme has been to facilitate an increased momentum of PPPs in sectors other than the large economic sectors like highways, ports, and airports. The programme contributed to design the enabling policy environment for PPPs in nascent sectors through revising the viability gap funding and project development funding schemes, developing model contracts for PPPs in such sectors, providing transaction advise for pilot projects and supporting project pipelines. Some of the nascent sectors supported through the programme were solid waste management, grain storage, hospitals, wastewater treatment, and ropeways (public transport for mountainous terrain).
In addition, some of the achievements at the outcome level, in line with the theory of change, demonstrate that its influence has been significant.
1. ITCF contributed to the content, design, and implementation of the National Infrastructure Pipeline (NIP) and the National Monetisation Pipeline (NMP). The NIP and NMP represented significant opportunities for levering private sector and financial markets for infrastructure investments and were the primary platforms of the Government of India for such investments.
2. ITCF helped make public-private partnership (PPP) contracts in infrastructure sectors consistent and predictable through development and dissemination of model contracts and model bid documents. This strengthened the confidence of private investors and financiers in the PPP contracts and contributed to increasing and sustaining their interest.
3. ITCF contributed to the design of the Sovereign Green Bond Framework which promises to be a significant platform for leveraging investments from institutional investors and financial markets into clean and green infrastructure development. The first issue of the Sovereign Green Bond was in 2023 – it demonstrated the interest from investors and validated green bonds as a significant instrument for infrastructure development. This contribution of the programme creates a platform for UK engagement in further building the climate finance ecosystem in India, both sovereign and non-sovereign. This further engagement is expected to be driven through the Economic Cooperation programme.
4. ITCF organised multiple dialogues among different stakeholders of the PPP ecosystem, including government sponsors (central, state, and local), financiers, developers, and professional delivery partners to solicit suggestions and feedback on policies enabling private investment into infrastructure sectors. These provided inputs and supported DEA develop new policies, standard documentation, and guidance to help facilitate private investment in infrastructure sectors.
Sustainability: UK priorities in the Indian infrastructure sector remain similar even after the conclusion of ITCF. Interventions progressing the UK priorities and objectives, as defined in the 2030 Roadmap and the Country Business Plan are expected to be delivered through the Economic Cooperation Programme for India (EcoP). To ensure sustainability of the work delivered through ITCF and continuity of the broad themes in the new programme, following actions have been undertaken / are planned:
1. An independent review of the infrastructure programme portfolio of FCDO, including ITCF, has been undertaken, with a view to presenting best practices of implementation that can make future infrastructure programmes more effective. The review identified lessons, themes and types of interventions that have been successful in past programmes, and which are likely to be good examples for the future. Some of the key lessons from the review include:
  1. Flexible, responsive & demand-driven approach to programme implementation helped drive success in contributing to the intended outcomes.
  2. The programme was successful in creating a knowledge ecosystem around infrastructure investments through the facilitation of investor engagements, digital platforms, compendiums, model documents, manuals, and reference guides.
  3. There was limited cross HMG collaboration in the programme.
2. The repository of documents, reviews, deliverables, and discussion notes from ITCF will be passed on to the EcoP Team to ensure continuity of priority themes in delivering interventions under the new programme.
3. The current FCDO programme team of ITCF will be actively involved in the design and delivery of infrastructure programmes in EcoP delivery as well. This will ensure continuity in approaches and help maintain the organisational relationships carried over from ITCF.
4. The FCDO programme team-maintained transparency with DEA and other key stakeholders, about the delivery of infrastructure interventions being shifted to ECoP from ITCF and has emphasised the continuity of focus on infrastructure in UK programmes in India. The consistent communications by the UK team have ensured that the existing relationships with counterparts and stakeholders will be continued through ECoP.
Value for Money (vfm): The overall assessment for VfM in the business case was undertaken based on operational delivery of the programme. The measures that were proposed for the assessment of VfM were:
1. Cost of technical assistance (input level),
2. Number of people reached with improved infrastructure services,
3. Amount of additional capital mobilised from the private sector,
4. Feedback by government partners suggesting high quality of support and analytical work, and
5. Partner inputs into developing and monitoring ITCF plans and work streams.
The overall assessment is indicated in Section D.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The following figure represents the summarised theory of change for ITCF:

The intended impact of ITCF – Private sector investments and confidence increased in the infrastructure sector remained unchanged during the tenure of the programme. An Annual Review midway through the implementation of the programme highlighted that impact of the programme is dependent on multiple external factors and influences including the priorities of the Government of India, policy support for private sector investments, approach of the government for infrastructure finance, financial market conditions, banking sector regulations, global economic trends, and economic conditions of the country. The broad strategic nature of the impact makes us cautious about attribution of programme results, but complementary externalities and relevant government priorities have augmented UK impact in the sector.
The indicator(s) selected for measuring the impact of the programme shows substantial increase from the baseline. Further, given the significant outcomes and outputs of the programme it is highly likely that the programme contributed to increase in private sector investments and investor confidence in the infrastructure sector.
Outcomes and Outputs: ITCF has performed well in terms of achievements of the targeted outcomes and outputs. The following figure provides a summary of the outcomes and outputs against the logframe indicators:

The overall theory of change has not changed during the life of the programme as the broad requirements for the infrastructure sector in India remains the same. At the same time, the priorities within the broader objective of infrastructure development have evolved since the inception of the programme. The theory of change was reviewed at the time of extending the programme and it was established that the overall impact and outcomes were still valid. The logframe was reviewed every year, revising the assumptions, the current context and the programme’s approach. As a result, the weightings of the different outputs were changed – the weighting for Output 1 was increased from 20% to 40%, while the weightings for the Outputs 2 and 3 were each reduced from 40% to 30%. This was done to recognise the higher priority accorded to PPP investments and easing of the regulatory framework to encourage private investment across various sectors as compared to knowledge development and capacity building. This also recognised the fact that some of the Indian infrastructure ministries were able to develop institutional capacities for PPP during the programme.
In addition, due to changes in the broader infrastructure finance ecosystem and more specifically in the PPP ecosystem, one output indicator was added (for Output 2) and some of the sources for other outcome and output indicators were redefined.

## C: Detailed Output Assessment

Output Number and Title	1. Improved business environment for private sector participation in infrastructure, including a focus on providing international experience and perspectives on regulations and policies, particularly in sectors with limited PPP experience
Output Score	A
Impact weighting (%)	40%		Impact weighting revised since last AR?	No

Output Indicator		Starting Position	Final Logframe Target	Result Achieved
1.1 Number of significant analytical products for improved policy making, regulations and guidelines developed and supported		0	18	24
1.2 PPP market studies, feasibility studies or transactions supported and / or advanced to next stage of development and implementation		0	14	17
1.3 Innovative financial instruments for the infrastructure sector / Developed / Implemented		0 developed / 0 implemented	4 developed / 2 implemented	6 developed / 2 implemented

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output focussed on strengthening the policy and knowledge frameworks covering private investment in infrastructure including through PPPs. The output included specific types of deliverables that improve the predictability, consistency and quality of transactions involving private investment in infrastructure. The overall output was delivered through the following components.
Output 1.1: This output provided government sponsors of PPPs and other projects involving private investment the tools, knowledge, and policies that they need to deliver successful transactions. These deliverables helped sponsors by standardising transaction structures, providing policies that ensured predictability in transaction structures and guidelines that helped decision making. Higher quality and predictable transactions enhanced the confidence of private investors and financial institutions in PPP transactions and thereby contributed towards increasing the project pipeline. Some of the deliverables included in this output were as follows:
1. Revisions in the Viability Gap Funding (VGF) Scheme and the India Infrastructure Project Development Fund (IIPDF) Scheme: ITCF supported reviews of the schemes, including eligible projects / sponsors, extent of support available, sectoral composition of supported projects, difference in requirements for projects of different sectors, and changes in context. The outcomes of the review were then fed into revised versions of these schemes. Some of the significant changes in the VGF included enhancement of the maximum VGF allowed to 60% (30% from Central Government and 30% from Government Sponsor) for social sector projects and provisions for operations and maintenance support (in addition to capital grant) for PPPs in health and education sectors, up from the earlier limit of 40% capital grant. The IIPDF Scheme was eased for social infrastructure sectors like health and education by not obliging the project sponsors to return the grant under the scheme and increasing the amount available for project development.
2. Contingent Liability Estimation Tool: ITCF supported the development of an interactive tool to estimate the contingent liabilities for government sponsors arising out of individual PPP contracts. The tool helped the user quantify significant liabilities from the compensation payable at termination or for force majeure events as defined in the key terms and conditions of the contract. Globally there is a push for identification of such contingent liabilities and the most likely / maximum fiscal impact of such liabilities. Government sponsors can use the estimate to make provisions to meet the liabilities in case they are triggered and are an essential element of organisational risk management systems.
3. Support for development of organisational policies of National Infrastructure and Investment Fund (NIIF): ITCF supported the development and rollout of fifteen organisational policies of NIIF including policies on investments, valuation, human resource management and risk management during 2016-17. ITCF funded technical experts to advise on structuring equity funds of NIIF.
4. Formulated guidelines and standard operating procedures for empanelment and use of transaction advisors for PPPs: ITCF supported the development and implementation of a panel of prequalified transaction advisors for supporting PPP project development, structuring, and procurement. ITCF supported the establishment of the panel by shortlisting qualified consulting firms. In addition, ITCF supported the development of guidelines to help Central Ministries and State Governments to access the empanelled transaction advisors. These helped shorten the time and cost required by government project sponsors to get transaction advisors separately and thereby also shortened the project development process for PPPs.
Output 1.2: This output provided specialised transaction advice on behalf of the IFS to the government project sponsors for complex PPPs or new sectors / sub-sectors with low PPP experience. This output demonstrated PPPs as transaction structures and PPP models to potential sponsors, bidders, and financial institutions. The idea was also to socialise these structures and lessons learnt during their operationalisation in the form of model contract documents and guidance on PPP structuring. Some of the notable examples of projects supported by ITCF includes the following:
1. Project development support for Sewage Treatment Plants (STPs) in Himachal Pradesh: 49 plants were upgraded, connecting left out and peri-urban areas of the municipalities. The wastewater / sewage sector had experienced limited PPPs in India, especially at the state level, hence an essential part of the urban development of the state.
2. Project Development Support for Development of Skywalk at Bhaleydunga, Sikkim: The project was expected to lead to economic growth of the state by promotion of tourism which is identified as one of the key sectors for creating jobs. Activities undertaken include collection of data, assessment of present status, availability of supporting infrastructure at the site and other infrastructure components proposed as a part of the project.
3. Advisory support to PPPs in grain storage: The Food Corporation of India (FCI) handles developing and managing public storage for foodgrains. The grain storage capacity and facilities were inadequate. The Department of Food and Public Distribution and FCI put forward a plan to increase capacity through a hub and spoke model of silos at 249 locations across the country. Specialised support through ITCF helped strengthen project reports, techno-economic feasibility study undertaken by FCI, and the contract documents drafted for the projects.
Output 1.3: This output supported the DEA and IFS develop instruments and platforms that offer investment and financing opportunities for different classes of investors, thereby bringing in new sources of capital into the infrastructure sector. ITCF supported:
1. The development and monitoring of the National Monetisation Pipeline working with the DEA to estimate the potential revenues available from monetising assets in key infrastructure sectors. ITCF supported DEA design inputs for the NMP, launched in 2021-22, and then in developing a detailed mechanism for utilisation of proceeds generated by monetising assets under the NMP.
2. The development of the Sovereign Green Bond Framework, working with IFS in the development of the concept, detailing the same and planning for its implementation. The Framework was launched as part of the Union Budget for 2022-23. The Government of India has mobilised INR 160 billion in two tranches – with 5- and 10-year tenure.
Lessons learned through this output, and recommendations for future programming. Some of the significant lessons from delivery of Output 1 have been as follows.
1. The outputs from programme delivery are not sufficient to have the confidence that the outcomes will be achieved. For effective delivery, a mix of technical outputs, dissemination to a wide section of stakeholders and capacity building for implementation are essential. A few outputs had limited impact as they were not supported by dissemination and capacity building activities.
2. Using programme resources to deliver routine functions of the counterpart departments is not sustainable or an effective use of the resources however, outputs that are strategic in nature and contribute to the enabling frameworks for investment in infrastructure may have lower immediate benefits for the counterpart team, but they have more long term and sustained impact on the sector.
3. The programme was limited in delivering some of the longer term, strategic priorities. For example, integrating climate action in infrastructure PPPs was one of the proposed tasks that was aligned with the UK focus on clean and green infrastructure. However, the counterpart team did not have climate as one of the immediate priorities and instead focussed on increasing private investment in infrastructure. In the final two years of the programme, the team was able to work with the DEA to include climate considerations in some of the interventions, as a start. But given focused inputs, the scope of such interventions was limited. The demand responsive nature of the programme meant that the programme largely delivered on the private investment theme but not on integrating climate action with infrastructure investments.
4. External stakeholders beyond the immediate counterparts have limited awareness of the UK’s contribution in development of the policy and knowledge framework for infrastructure investments. For example, there is no recognition of the UK’s contribution to the Sovereign Green Bond Framework in any public document or media. Further, due to gaps in documentation of the UK’s work in the counterpart institutions, the institutional memory of the programme is getting lost.
5. The counterpart institutions and teams did not share many of the policy outputs that were being supported under the programme given confidentiality concerns of Government of India. This meant that the UK Team was not able to review the quality of such deliverables and outputs effectively. Post discussions with the partners, in the last three years of the programme, the team was able to review and provide international best practice before these were approved for publication.
Recommendations for future programmes
1. It should be emphasised that policy driven programmes will have long term ambitions and should focus on strategic changes, and not just the immediate needs of the counterpart. Mutual priorities must be agreed at the outset. Ideally, routine processes of the counterpart organisation should not be supported under policy support programmes.
2. It is recommended that comprehensive documentation and a reporting process is agreed with the delivery partners and counterpart departments. The documentation process must lay down protocols to record each key decision and development in the programme to ensure institutional memory is kept over the tenure of the programme.
3. It is recommended that a communication plan and protocol is set up at the start of the programme to ensure balanced and proportionate representation of UK's role in the programme. This is important for programmes that interface with a single department for policy support, i.e. where there are limited opportunities for the UK to interface with external stakeholders. This is with a view to bring the best practices available internationally, including that from the UK.
4. It is recommended that as part of the formal arrangement with the counterpart institution, confidentiality provisions are incorporated, addressing the counterpart institution’s concerns. This will ensure that the implementation and monitoring of the delivery by the UK Team is not affected by confidentiality concerns, later during the implementation of the programme.

Output Number and Title	2. Increased capability to formulate development-oriented infrastructure projects and to address implementation barriers
Output Score	B
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Position	Final Logframe Target	Result Achieved
2.1 Specialised support provided to enhance capacity in designated line ministries/state governments to design, develop, structure, appraise and begin PPP projects		0	10	15
2.2 Development of new / improved frameworks, approaches, tools, instruments, and standard / model documents supported to enhance capacity of Ministry of Finance / selected line ministries / state governments		0	5	2

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output was targeted towards enhancing the institutional abilities of government project sponsors at national and sub-national levels for identifying, developing, and implementing infrastructure projects with private sector participation. The idea behind this output was to provide active support to such institutions and equip them with standardised tools, instruments, and approaches for structuring projects. This output was delivered through the following components:
Output 2.1: This output provided advisory and operational support to select central ministries and state governments. The support was focussed on the PPP project development process and proven best practices and standard approaches that could be used by the government sponsors when implementing PPPs in the sector, including:
1. Capacity building training for senior government officials on infrastructure PPPs - Based on the Kelkar committee report which recommends improved knowledge for national and state officials on designing and structuring PPPs, a training Programme was developed by the Ministry of Finance. Infrastructure Development Corporation Karnataka Limited (iDECK) conducted basic as well as advanced training on PPP concepts like project life cycle, structuring of projects, risk management, post governance issues and monitoring.
2. Specialised support to State Government of Assam – to meet the infrastructure gaps and low penetration of PPPs in northeastern states, the Government of Assam had requested the Department of Economic Affairs (DEA) for a PPP capacity building workshop addressing specific challenges related to PPPs in the region. In May 2018 ITCF supported a 5-day training on PPPs for officials of Government of Assam.
3. Sharing UK frameworks and best practices - In 2022 a series of workshops were delivered through the Infrastructure and Projects Authority (IPA) targeted towards officials from key infrastructure ministries of the Government at both the state and central level.
Output 2.2: This output was focussed on development of standardised guidance, tools, approaches, and model documents that could make the PPP project development, procurement, contracting, and procurement processes more time and cost efficient. The idea was to learn from successful projects in specific sectors and then institutionalise the approaches used in such projects in the form of model documents, tools, and instruments. This part of the output was added in the logframe in 2022.
Some of the significant deliverables contributing to this output were as follows:
Model Request for Proposal: The programme supported the review and revision of the model Request for Proposal for PPP Projects (RFP). The earlier version of the model RFP was issued in 2009 and since then become an indispensable standard document for procurement of concessionaires / developers for PPP transactions. However, since then PPP approaches have evolved in most key sectors and the private sector infrastructure industry has matured. Hence there was an urgent need to review and revise the earlier version. The programme supported the review, revision, and publication of the revised model RFP to be used by government project sponsors for PPP projects.

Model Concession Agreement for Integrated Solid Waste Management Projects: The programme supported the development of the Model Concession Agreement for integrated solid waste management projects. Integrated solid waste management projects are where the urban local body contracts a private concessionaire for the construction, operations, and maintenance of the complete solid waste management process in a city or a group of cities including the collection, transportation, treatment, and disposal processes.

PPP Procurement Manual: To ensure that PPP procurements are made by following a uniform, systematic, efficient, and cost-effective procedure and to ensure fair and equitable treatment of bidders/ contractors, this procurement manual has been prepared as a guidance document. This manual aims to bring together at one place in a whereat and logical step by step procedural manner, the information related to procurement of PPP’s, which is hereto collected.

PPP Appraisal Manual: This Manual brings together the best practices for formulation and appraisal of PPP projects. It is expected that this Manual will be an important reference document for the Project Sponsoring Authorities while structuring their PPP projects. This Manual may be referred to by Central/State Government Ministries/Departments, Central Public Sector Enterprises (CPSEs), Statutory Authorities or other entities under their administrative control, hereinafter referred as Project Sponsoring Authorities or PSAs, as a reference or guiding document for the purpose of appraisal of PPP projects.

Contingent liability estimation tool- The programme supported the development of a tool for assessing and managing contingent liabilities for the Government arising from the PPP projects. After extensive testing and consultations, the tool has been finalised and has been made available for use of the project authorities as a knowledge product under www.pppinindia.gov.in website.

Lessons learned through this output, and recommendations for future programming.
Some of the significant lessons learnt from the delivery of activities contributing to Output 2 are as follows:
1. The tasks under this output were not always internally integrated – some components were delivered for a particular sector / department while the others were delivered for other departments. E.g. a model concession agreement was developed for integrated solid waste management sector, but the capacity building sessions were not delivered to the stakeholders in that sector. This leads to limited value of the tasks under this output, given the limited scope of an individual part. This was exacerbated by the latter years' short-term programming necessitated by budget uncertainty.
2. The approach for capacity building should be reviewed for future programmes. Classroom training of government officials saw limited demand and impact during the delivery of ITCF. The key reasons for the limited impact were as follows:
  1. The relevant people might not always be nominated by their organisations. There are several considerations for nominations including nomination as reward, turn-by-turn choice, based on existing workload etc. While relevance might be a parameter for nomination, it is usually not the only one. Hence a significant part of the trainee cohort may not have the context or be able to apply the knowledge in their official functions.
  2. There is no mandate or incentive for the trainees to disseminate the knowledge gained from the capacity building initiatives, within their organisations. Hence the knowledge is limited to only the participants of the workshop, and not socialised within their organisation. When the officials trained under the programme get transferred or retire, then the knowledge is also lost.
  3. There was no follow up (say after six months or a year) with the participants in terms of building on the capacity building with follow on sessions building upon preceding sessions or reviewing the extent to which the knowledge is being applied and the impact that has created.
3. The DEA handled dissemination and institutionalisation of the knowledge generated under this output. Going forward, attempts should be towards strengthening dissemination, such that it sustains the impact of the output.
Recommendations for future programmes
1. Both partners, India and the UK should be able to use the knowledge material, model documents and training content developed through its programme with other counterparts and in other countries. The DEA suggested this kind of mutual learning as well. This would generate added value for money as at least a part of the knowledge developed in such programmes in India would have utility in similar development contexts, where both India and UK can partner.
2. Explore alternative mechanisms for capacity building components of future programmes. An approach focussing on working over a longer term in a single sector and / or with a single ministry to deliver an integrated programme of capacity building including training, knowledge development, preparation of model documents and guidance, might generate better and sustained impact as compared to standalone activities spread across multiple sectors and ministries.
3. Dissemination plan and follow-up tasks should be essential components for all programmes that have a capacity building or institutional development part. The dissemination plan should be driven by the UK team with the support of relevant experts deployed by the delivery partners. The follow-on steps should focus on the extent to which the ability and knowledge gained through UK support has been sustained, used, and socialised in the organisation.

Output Number and Title	3. Policy-relevant knowledge generated and disseminated
Output Score	A
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Position	Final Logframe Target	Result Achieved
3.1 Number of analytical pieces, evaluations & knowledge products developed		0	18	18
3.2 Number of effective dialogue mechanisms and forums conducted to facilitate information sharing, dissemination, and exchange		0	16	20

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output was directed towards knowledge generation and dissemination with a focus on PPP project development and implementation aspects. The idea was to capture the experiences, lessons, and best practices in the PPP development lifecycle within India and from other countries and disseminate them among the government project sponsors. This will allow project sponsors to strengthen the projects under development and learn from experiences of others. The output was delivered through the following components:
Output 3.1: This component focused on knowledge products that synthesise the experiences and lessons from PPPs in similar development contexts as India. Some of the significant knowledge products produced under this component are as follows:
1. Database of PPPs in India: - The Programme provided technical support to create and populate information on the infrastructure database (www.infrastructureindia.gov.in), which is live and has physical and financial information on 8,735 infrastructure projects (including 1,575 PPP projects) in India with 3,433 projects added in the last year. The website provides state, sector, status and year wise information on PPP, Non-PPP, and private sector projects. The information is now being used by the Government to take informed policy decisions.
2. Compendium of case studies in key economic sectors: The programme supported in preparation of PPP case studies highlighting challenges, drawbacks, and success across implementation of projects in three key sectors i.e. Airports, Urban Public Transport and Roads:
  1. The Airport sector case study discussed the successful leasing of six airports on Operations, Management, Development and Transfer basis under PPP mode.
  2. The Urban Public Transport sector case study discussed the implementation and intended outcomes of the Pune Metro Rail Line-III project under Design, Build, Finance, Operate and Transfer (DBFOT) basis under PPP mode.
  3. The Road sector case study discussed implementation of the first toll bridge of India i.e., Delhi-Noida-Delhi (DND) on Build, Own, Operate and Transfer model under PPP mode.
3. Aspects of technology and innovation in brownfield investments in infrastructure: A study to review evaluation of the role of improvements in technology (such as construction technology in roads or signalling technology in railways) in enhancing returns from private investment in existing infrastructure assets and identification of measures on how technology can be leveraged to attract institutional investment by creating a pipeline of “bankable quality brownfield infrastructure projects.”
4. Impact of COVID-19 on the Indian Infrastructure Sector: An impact assessment report of COVID-19 on the Indian Infrastructure Sector was developed to understand the short, medium and long-term impact of COVID-19 on key infrastructure services (direct or indirect) including Power, Oil & Gas, Roads, Railways, Ports, Airports, Urban Infrastructure, Telecom, Agriculture, etc. The study provided ten focus areas to improve COVID-19 preparations specifically for the infrastructure sector which can be considered for designing and implementation of infrastructure projects.
5. Model for capital market financing of urban infrastructure (Municipal Bond). The study undertook the readiness assessment of four municipalities: Chennai, Indore, Rajkot, and Bhubaneshwar. The report was jointly submitted to the Ministry of Finance and the Ministry of Urban Development. In the joint meeting it was agreed that the Ministry of Urban Development would undertake the issuance of bonds. Announcement of issuance of infrastructure bonds by Pune was made in June 2017.
Output 3.2: This component was focussed on helping dialogues among the key stakeholders from the PPP ecosystem in India including government project sponsors. The idea was to set up two-way communication – feeding private sector concerns into development of new policies / strengthening of existing policies of DEA and providing information on these to the private sector. Further, the component also helped dialogue between India and other countries, sharing the experiences from India and other countries, and influencing global principles on infrastructure financing. Some of the significant dialogues organised included the following:
1. Dialogue with private investors in infrastructure sector: The programme supported a national workshop convening key government stakeholders including the Chief Economic Adviser and other officials from Ministry of Finance with approximately 50 key private sector infrastructure players in India. The objective was to ask for feedback, concerns, suggestions from the private sector stakeholders for improving the policy landscape for PPPs in infrastructure.
2. Dialogue with stakeholders for estimation of contingent liabilities for the government from PPP contracts: Stakeholder consultations carried out with key large infrastructure players (such as L&T, IL&FS etc.) and government agencies (such as National Highway Authority of India, National Disaster management Authority, Ministry of Road Transportation and Highways) for assessing government liabilities under PPP projects in case of termination of contracts.
3. Market consultations as a precursor to PPPs in wastewater treatment sector: Information and learning session was conducted with various Government Departments and potential private sector players on prospective technologies, market sounding and financial modelling for sewerage treatment plants.
4. Infrastructure Working Group of G20 India Presidency: The programme supported the Infrastructure Working Group proceedings as part of the G20 India Presidency. There were 3 working group meetings. The programme helped provide strategic inputs for representatives of India, chairing the proceedings. The priorities discussed during the sessions included financing of resilient cities, capacity building of cities, Quality Infrastructure Investment principles and criteria.
5. Review and monitoring of National Infrastructure Pipeline progress: The Programme supported DEA in conducting periodic review meetings chaired by Union Finance Minister and Secretary (DEA) to monitor projects under National Infrastructure Pipeline and capex spending of key infrastructure ministries. In these review meetings, ministries/ departments were encouraged to front-load their capital expenditure, actively work on getting projects funded through innovative structuring and financing and provide all support to private sector for enhancing infrastructure spending apart from exploring PPP mode for viable projects.
Lessons learned through this output, and recommendations for future programming.
The key lessons from the delivery of Output 3 are as follows:
The PPP in India database was developed, operationalised, maintained, and updated under the programme. In 2019, the programme moved on to the delivery of other components, handing the PPP database over to DEA for updating and maintenance. The PPP Database is a credible compendium of all major PPP projects in India from 2002 onwards, including data on project sponsors, project cost, developers, stage of implementation etc. for PPPs across major infrastructure sector. The PPP ecosystem in India, including regulators, government, private investors, and financial institutions are users of the database. For instance, inclusion in the database was taken as official recognition of any given project as a PPP for application of specific RBI provisions applicable on the provisioning for loans to PPP projects.
However, due to other urgent priorities of the partner, the database has not been updated since 2019. This has led to the database being outdated and has caused reputational damage to the UK as it was widely known to have been supported by the UK. In the absence of a sustainability mechanism such platforms will have temporary impact and generate negative perception. FCDO should have also put in place mechanisms for sustainability.
1. The programme supported the publication of a few sets of PPP case studies as demonstration of both success and failures in such transactions. These were based on specific requests by the counterpart department to go with key national events. However, these case studies were standalone publications, and not integrated with other components like capacity building, investor-investee platforms etc. The standalone nature of these publications limited their impact, as the opportunity to link them with the understanding of the PPP development process was missed.
2. The programme supported the monitoring and supervision of the National Infrastructure Pipeline (NIP) and the National Monetisation Pipeline (NMP). The monitoring activities included collating of data from various ministries and providing a summary of progress to high level committees. The activities also included strengthening and streamlining the data capture and reporting processes of various ministries. The impact of this activity is expected to be long lasting and will be sustained over several years for infrastructure plans following the NIP. The experience from this activity can be especially useful across the UK network for supporting infrastructure pipelines in similar development contexts.
3. The UK Team had limited interfacing with stakeholders as part of some of the activities in this output. Some activities included reporting on progress of infrastructure programmes to high level Government of India committees or supporting Government of India representatives in global forums. The UK Team could not be part of such conversations and discussions. The main interface for key stakeholders were the DEA. This might have led to limited recognition of UK’s role as a trusted partner, especially in supporting the monitoring of NIP and NMP, and the analytical support provided for the Infrastructure Working Group under India’s Presidency of the G20 in 2023.
Recommendations for future programmes
1. Programme elements that are expected to be operational beyond the tenure of the programme should have clear and viable sustainability mechanism, including financial and human resource commitments from the counterpart (if applicable). Unless sustainability mechanisms for long term components are agreed upon during the programme design phase, it is recommended that the programme team do not support such components.
2. Standalone knowledge products without being integrated with either capacity building, dissemination activities and future actions should be avoided as they are likely to have limited application.
3. Programme arrangements should include clear commitments from the counterpart department on recognising the support provided by the UK Government. Based on the circumstances, it might range from mentioning the support in all project documents to ensuring presence of representatives of the UK Government in key events. In addition, the management of service delivery partners must be made stricter and robust, e.g. where applicable payments being linked to visibility and communication.
4. Future programmes could benefit further (apart from the PCR) from the documentation of key lessons and best practices from the delivery of the programme, targeted across HMG departments engaged in development or delivery of similar programmes. For instance, a paper on the lessons from the implementation of the NIP, including a description of the support provided by the UK would have been especially useful as a knowledge resource.

D: Value for Money

The Business Case specified that the assessment of value for money (VfM) will focus on the efficiency and economy of the selected management agency’s operations. The delivery partner was selected based on its capacity to undertake the work and promote its adherence to good management practices e.g. the quality of its proposed procurement, quality assurance and risk management procedures. Emphasis was placed on the ratio of the management costs to total programme value; expected and actual number of days worked, daily fee rates in relation to the market etc.
The Business Case defined the following measures for assessment of:
1. Cost of technical assistance (input level)
2. Number of people reached with improved infrastructure services.
3. Amount of additional capital mobilised from the private sector.
4. Feedback by government partners suggests support and analytical work is of high quality and relevant.
5. Partner inputs into developing and monitoring ITCF plans and work streams.
Over the lifetime of the intervention, the delivery approach for ITCF was changed from the activities being managed by a management agency to delivery partners being directly appointed by FCDO. This was necessary due to HMG budget uncertainty, both in timeframe and amount. These limitations led to the programme being delivered through short term interventions, directed at specific deliverables and the payment being made to delivery partners on submission or approval of specific deliverables.
The VfM of the programme is assessed in the following sections based on aspects of economy, efficiency, effectiveness, and equity.
Economy
The major input cost for ITCF was the fee paid to delivery partners. The delivery partners were appointed based on competitive procurement processes with 70-80% weightage to technical parameters such as experience, understanding of the terms of reference, quality of methodology and adequacy of work plan. The remaining weightage was applied on the total cost of predefined deliverables.
Except in the first contract the fee payable to the delivery partners was not based on person days deployed for deliverables, the proposals submitted for the procurement processes did indicate the estimated number of days of deployment as a basis for the calculation of the total fee quoted. Based on such estimated number of days, the average person day cost paid to the delivery partners is approximately GBP 241 which is lower than that of comparable programmes during the same period (over GBP 325). Later interventions were based on deliverables approved by the SRO.
Efficiency
The efficiency aspect of the programme has been measured against the value of private investment that the programme helped mobilise in the Indian infrastructure sector. The programme helped facilitate the implementation of the GBP 1.4 trillion National Infrastructure Pipeline to be completed by 2025, of which private investment is expected to contribute about 21% (GBP 0.29 trillion) as per Government of India estimates. In addition, the project has helped mobilise private investment in other sectors including grain storage, wastewater treatment, public health facilities, ropeways, and solid waste management. These projects may or may not be included in the National Infrastructure Pipeline. The programme has contributed to design and monitoring of the Government of India’s National Monetisation Pipeline for monetisation of existing infrastructure assets to unlock value of approximately GBP 9.7 billion in 2021-22 and GBP 13 billion in 2022-23 for investment in other infrastructure assets, according to figures published by the Government of India. However, the value of private investment in infrastructure and the value unlocked through monetisation of the existing assets cannot be solely attributed to the programme as there were other factors and institutions beyond the scope of the programme that contributed to these achievements.
In addition to the advisory inputs, the programme had provided technical inputs to the DEA for (1) technical appraisal of project proposals presented to the PPP Appraisal Committee for approval and (2) technical appraisal of requests for viability gap funding.
During the programme tenure, partners were supported for approval for 201 PPP project proposals by the PPP Appraisal Committee, aggregating to approximately GBP 40 billion. At the same time, during the programme tenure, Viability Gap Funding (VGF) was approved for 56 projects, with total cost of GBP 4.3 billion and approved VGF amount of GBP 1.1 billion.
Given the policy support nature of the programme, the efficiency of the programme must not only be measured in terms of quantitative parameters but may also be measured in terms of anecdotal evidence of the strategic impact of the programme. For example, the private investment in development of the grain storage infrastructure is estimated to be approximately GBP 0.84 billion by 2025-26. The programme provided advisory inputs to the Food Corporation of India and the Ministry of Consumer Affairs, Food, and Public Distribution to develop the transaction structure for the PPPs and helped develop the contract document to be used for development of the grain storage capacity.
Effectiveness
The dedicated support of the programme to DEA meant that the programme was able to provide transaction advisory to 17 PPP projects for which the respective government sponsors had requested help. Many of these projects were in sectors with nascent pace of PPPs (like grain storage and ropeways) or had a government sponsor that was undertaking PPPs for the first time. The project has also been able to develop multiple policy and knowledge documents that have been widely adopted by all key infrastructure ministries in the Government of India.
A negative on effectiveness has been on account of the PPP Database not being maintained and updated by the DEA after the component was handed over from the programme, during its operational period, when the database was supported through the programme, it had been recognised as a useful and credible source of information. During this period, potential investors (among other stakeholders) were using the database to assess risk in the Indian infrastructure sector, thus helping mobilise investments.
The counterpart officials in DEA have expressed their appreciation on the quality of support provided through the programme, which is also shown by the fact that the programme was extended twice beyond its original tenure. The feedback on relevance and quality of outputs have also been reported as part of the independent study – Lessons Learnt from the Implementation of UK-supported Infrastructure and Urban Programmes (2013-22) in India.
Given the policy support nature of the programme and the fact that the DEA had collaborated with other development partners, including the World Bank and Asian Development Bank makes the attribution of the programme activities to the programme challenging.
Equity
The programme supported development of infrastructure facilities in sectors such as roads, highways, ports, airports, water treatment, wastewater treatment, solid waste management, grain storage and public transportation. The projects supported by the programme improved access to infrastructure services for all sections of the society. Though not directly targeting women or vulnerable sections, the assumption is that the projects in sectors such as water treatment, grain storage and public transportation may have disproportionately higher impact on the economic weaker sections of the society, women, youth, and disabled persons. For instance, grain storage reduces the wastage of food grains and allows the government to time the supply of stored grains to keep the prices low in food markets. Similarly, wastewater treatment projects supported through the programme helped keep the water bodies less polluted and improved the resilience of the community against droughts.
[note] Source: Progress on household drinking water, sanitation, and hygiene 2000–2022: special focus on gender. New York: United Nations Children’s Fund (UNICEF) and World Health Organization (WHO): 2023. https://www.who.int/publications/m/item/progress-on-household-drinking-water--sanitation-and-hygiene-2000-2022---special-focus-on-gender
[note] Source: Borker, Girija. Constraints to Women’s Use of Public Transport in Developing Countries, Part I: High Costs, Limited Access, and Lack of Comfort (English). Global Indicators Briefs; no. 9 Washington, D.C. : World Bank Group ; https://documents.worldbank.org/en/publication/documents-reports/documentdetail/099550408012242045/idu05986e9020f68504b680bc3709f90291733e9
Recommendation on Measurement for future programmes
The detailed indicators were not effectively defined at earlier stages of the programme, only limited year-on-year comparison is available in respective annual reviews. As a result of this learning, the programme team has found a few steps that could assist the future FCDO programmes to strengthen the measurement and delivery of VfM. They include setting up early on a standard set of qualitative and quantitative VfM indicators that can be updated to the specifics of any FCDO programme, as well as enabling comparison and benchmarking between programmes.
The measures for policy support programme must be clearly thought out, given the challenge of attribution, especially when the target aspect is a wide policy area (like infrastructure finance) with multiple development partners working with the same counterpart institution.
In addition, for a demand responsive programme such as ITCF which had to evolve with the changing context of infrastructure investments in the country, the measurement should have evolved through the programme tenure.

E: Risk [½ - 2 pages]

The overall risk of the programme trended from low to moderate during its lifecycle. In the initial years of the programme, the risk was rated as low. The risk rating increased to moderate due to concerns on quality of delivery by the delivery partners and thereafter due to disruptions caused by the COVID19 pandemic. In the last three years of the programme, the risk was rated as moderate due to the risk of underspending on the budget and disruptions in delivery due to ODA cuts. The programme ended with an overall risk rating of moderate. Hence, over the life of the programme, the main risks that materialised where the delivery risk, risk of not using the approved budget and the disruptions caused due to the pandemic. The programme managed to control the impact of COVID 19, ODA prioritisation on the quality of delivery and contribution to intended impacts of the programme by deprioritising resource intensive, long-term activities and through focussed short term, targeted support. The pivot to short term, targeted support helped in maintaining the relationship with the partners (DEA), the impact was limited due to restricted funds.

The Annex 1 provides a list of the risks identified in the Business Case for the programme, whether the identified risks materialised and the impact they had on the outcomes of the programme.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including measures of economy and efficiency.
FCDO’s support to the DEA was a technical assistance programme without any financial assistance. The programme was demand driven and the outputs under the programme were largely based on specific requests from DEA. The ITCF Steering Committee was the formal platform for jointly finding areas of support and future trajectory agreed by DEA & FCDO under the programme. However, during the last 3 years, there was no Annual Steering Committee Meeting. Though regular meetings were held with the Joint Secretary along with ongoing periodic meetings among the DEA, FCDO and delivery partner teams. FCDO managed the contract for the SP and monitored delivery of the programme milestones.
The following schematic provides an overview of the key partners and other stakeholders of ITCF:

The governance structure represented above was discontinued during the COVID19 pandemic, due to the disruptions in delivery of the programme itself. Post the pandemic, given the limited funds available for the delivery of the programme, a strategic steering committee was not good use of resources and was discontinued to keep the programme management cost low. During the period after 2020-21, the programme interventions were largely designed based on direct interactions between FCDO and DEA teams including the senior officials.
The programme was delivered through various partners, as shown in the following table:
Year	Delivery Partner	Role
2013-2019	PWC led consortium	Main programme delivery partner, managing all outputs under the programme
2019-2020	KPMG	Main programme delivery partner, managing all outputs under the programme
2021-22	KPMG	Main programme delivery partner, managing all outputs under the programme
	PWC	Delivery of specific technical outputs on integrating climate aims with PPPs, identification of strategic gaps and recommendations
2022-23	KPMG	Main programme delivery partner, managing all outputs under the programme
2023-24	KPMG	Main programme delivery partner, managing all outputs under the programme.

The cost of personnel deployed through the contracts was the main cost driver of ITCF. These were kept as low as possible by benchmarking using competitive rates and following compliance requirements set out under [the then] Smart Rules and now PrOF. Payments were made on realisation of outputs and against invoices and financial reports (with necessary documentation) and SRO approval. The delivery partners worked closely with the DEA officials with an ongoing interaction and regular technical vetting of the deliverables and systematic review meetings. FCDO and DEA have also conducted regular joint review meetings with the delivery partners on deliverables ensuring prompt and quality outputs. The FCDO task team developed robust monitoring mechanisms including periodical meetings, weekly and quarterly progress reports from the delivery partners. The quality and periodicity of these have been diverse through the life of the programme.

The performance of the programme delivery partners was satisfactory as shown by the feedback received from the counterpart institution and other key stakeholders. There were issues raised with the performance of the delivery partners in a few instances, which were resolved to the satisfaction of DEA, with close monitoring by the FCDO programme team. DEA had concerns about sharing of information and project documents by the delivery partners with the FCDO Team, which were raised with DEA for the required resolution. Additionally, lessons for an appropriate and adequate recognition of the UK support through this programme, especially in communications and documents directed towards external stakeholders were agreed for future interventions. This has been reflected in the recommendations for future programmes.
Financial Performance
Initial years of the programme took some time in being embedded. The later years, due to the uncertainty about availability of resources and the time available for implementation of ITCF necessitated use of limited tenders for short-term annual interventions. This approach limited the efficiency and effectiveness of delivery. In addition, it was difficult to attract much enthusiasm from the market – though the team and the DPO ensured that rules and regulations for the tendering process were adhered to. It was also one of the first interventions that saw an active involvement of the GoI officials in the tendering process from the TORs to the evaluation of the bids. However, the dependence on short term contracts increased the number of procurement and contracting processes, increasing the administration effort and cost needed for delivering the programme. The administration effort and cost spent was even higher in one instance where the procurement process had to be repeated due to the delays (ODA and GoI prioritisation) and consequent changes in the scope driven by emerging priorities of DEA. Given that the same service provider repeatedly won these tenders, the team in collaboration with the commercial specialist undertook an audit to confirm adherence to the procurement rules.
Programme-level approach to monitoring and evaluation.
For most of the programme duration, the programme activities were monitored at monthly intervals through face-to-face meetings with delivery partners and Ministry officials, and beneficiaries. These meetings reviewed progress against targets; share deliverables; address challenges in execution; and agree on the next steps. There was an intra-team shuffle of the programme post the DFID-FCDO merger.
Regular meetings of the Senior officials within DEA and FCDO were held throughout the life of the programme. During 2019-2022, face to face engagement with delivery partners and stakeholders was limited due to Covid-19 related restrictions. However, the FCDO and PwC / KPMG teams adapted quickly to new ways of working and ensured that all monitoring activities which would normally have taken place in person was conducted virtually instead, with monthly progress reports from delivery partners for a documented update on the progress of the implementation.
The monitoring of the programme was also based on the logframe that was jointly agreed with the delivery partners. The partners presented their delivery plans and feedback on the results framework, and these were reviewed during the periodic monitoring meetings. The logframe was reviewed every year, revising the assumptions, the current context and the programme’s approach. As a result, the weightings of the different outputs were changed.
In addition, due to changes in the broader infrastructure finance ecosystem and more specifically in the PPP ecosystem, one output indicator was added (for Output 2) and some of the sources for other outcome and output indicators were redefined.
From a technical perspective, contracts and inputs were managed by the SRO bringing in ability as required from the wider FCDO team. From a commercial perspective, contracts were managed by the Programme Officers who ensured efficient financial management and monitoring. All partnerships during the review period were continually monitored.
Recommendation:
Given the uncertainty by COVID 19, some of these systems had to be redesigned or repurposed. Lessons learnt from these will be incorporated in the future support e.g. stringent adherence to agreed timelines and meeting reports. This is to ensure that regular reporting and progress meetings were held to support consistent engagement with suppliers and resolve any issues early on.

Date of last narrative financial report		Date of last audited annual statement

Annex I

The Business Case had listed down the following risks. The following table also shows whether the identified risks materialised and the impact that they had on the outcomes of the programme.
Risk	How did the risk materialise?	What was the impact on the intended outcomes?
ITCF outputs not used by GoI when designing new policies and programmes.	This risk did not materialise, as GoI and governments at other levels (state and local) did use most of the outputs (e.g. model concession agreements, model procurement documents etc.) widely.	The use of most of the outputs strengthened the contractual arrangements of PPP projects and led them to commercially viable and sustainable over a long term. In addition, high level policy outputs like the contribution to the Sovereign Green Bond Framework, inputs to the design of NMP and NIP were used by the GoI, amplifying the impact of the programme on infrastructure investments.
Difficulty in attributing outcomes to FCDO activities and demonstrating VfM	This risk materialised as multilateral institutions like the World Bank and Asian Development Bank were working with the same counterpart institution on infrastructure finance. While not entirely overlapping with the programme, the TA support from these institutions strengthened the policy framework for infrastructure finance and helped mobilise private investment for the sector.	The outcomes and the impact of the programme could not be directly or solely attributed to the programme due to the TA support provided by the World Bank and the Asian Development Bank to DEA. Based on stakeholder feedback while the programme contributed to the achievement of the outcomes and generated, it might not be clearly demonstrated through empirical evidence.
Government does not follow through with reforms and infrastructure does not remain a priority sector	This risk did not materialise as infrastructure and private investment in infrastructure remained the priority of government of India and continue to remain so.	Due to the high priority of infrastructure and private investment in infrastructure, the programme always had top level administrative support within the government and was allowed the opportunity to provide inputs to high level policies, enhancing the impact of the programme.
FCDO is not able to contract a Programme Manager with the right range of policy, financial and management skills	This risk did not materialise as (1) FCDO was able to contract delivery partners with right expertise and skills (2) the delivery approach of the programme was changed during the latter part of its tenure, pre-empting the need for Programme Manager	Since the risk did not materialise, the outcome and impact of the programme were not affected
Analysis and outputs produced under the ITCF, is not high quality, undermining reach, and impact	This risk did not materialise as the FCDO Team had an active role in monitoring and reviewing the analysis and outputs produced under the programme	Since the risk did not materialise, the outcome and impact of the programme were not affected
ITCF is not able to utilise its budget of £10 m	This risk materialised as due to lower-than-expected annual funds being given to the programme during the period 2021-2024 due to ODA cuts by the Government of UK	The limited allocation of funds due to the existing context of support, to the programme limited the outcomes and the impact that the programme could have delivered. Since there was demand from counterparts to provide support, funds were the only limiting factor on the activities of the programme and therefore its impact.
Specifics needs and interests of socially excluded groups get low priority	This risk materialised as the programme covered infrastructure services for the entire population including socially excluded groups and did not have components specifically targeted towards socially excluded groups.	Given that the programme was targeted at infrastructure development for the whole cross-section of population and did not exclude any group, the impact was on the entire population. In fact, some of the outputs like the model concession agreement for solid waste management projects and for grain storage would have provided higher level of economic and social benefits to economically weaker sections, women, youth, and disabled people.