Annual Review Template – from April 2020

Title: UK Trade Partnerships Programme (UKTP)
Programme Value £ (full life): 20 million		Review date: 31/03/2020
Programme Code: 300602-101	AMP start date: 01/04/2019	AMP end date: 31/03/2022

Summary of Programme Performance
Year	2019/2020
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/47875848.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/53216242.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The UK Trade Partnerships (UKTP) programme will deliver technical assistance and capacity building to the countries party to Economic Partnership Agreements (EPAs), trade agreements between African, Caribbean and Pacific (ACP) countries and the UK/EU. The UKTP programme contributes to fulfilling the UK’s development cooperation commitments in the Economic Partnership Agreements (EPAs). UKTP will support our ACP partners to effectively implement and maximise the benefits of the EPAs, both under the EU EPAs and in anticipation of the implementation of the replicated UK EPAs when they come into effect after the Transition Period.

Over three years (from May 2019 to March 2022), the programme aims to increase export flows from African, Caribbean and Pacific (ACP) countries to the UK and the EU, creating quality jobs in those countries in the long-term. The programme will:
- Provide technical assistance to our partners to enable the effective implementation of the UK EPAs when they come into effect. We intend to undertake scoping in our target countries this year (2020), but activities will only be implemented when UK EPAs have come into effect (or shortly beforehand), i.e. after the Transition period (after December 2020 at the earliest). This component will initially be implemented through existing DFID programmes (TAF2+) and the CARICOM Secretariat.
- Increase awareness of firms and institutions on how to access the UK/EU markets and its potential benefits as well as a more transparent business environment. The approach will involve: (1) centralising data on export procedures, entry requirements and trade trends among different markets; (2) communication and capacity building of trade support institutions on issues related to standards, compliance, performing analysis of recent trends and identify diversification possibilities; and (3) conducting business surveys on non-tariff barriers to identify bottlenecks faced by exporters to the EU and UK markets.
- Implement export promotion projects in 10 ODA-eligible countries, targeting firms, sector organisations and export promotion agencies in sectors with high potential to increase exports to the UK and EU markets. Targeted firms will benefit from support tailored to the local context that will cover some or all of: logistics and supply chain; meeting quality requirements; marketing; and fostering market linkages.
  [note] Cameroon, Côte d'Ivoire, Ghana, Madagascar, Zimbabwe, Comoros, Fiji, Dominican Republic, Jamaica and Saint Lucia.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, the UK Trade Partnerships Programme has met or exceeded expectations for the outputs delivered during the inception phase of the programme. Our key implementing partner the International Trade Centre (ITC) has commenced the programme quickly, been flexible and decisive in responding to any issues. This is despite the challenge of a large spread of countries for which data collection needed to be completed during the inception phase and changing demands from DFID to respond to live issues. DFID will work with the ITC’s and Global Trade Programme’s monitoring, evaluation and learning units which will provide advice and quality assurance on the effectiveness of the programme’s activities and outcomes at subsequent reviews, including progress against the log-frame, theory of change, and Value for Money (VfM).

Major lessons and recommendations for the year ahead [1/2 page]

- ITC will revert to DFID with further evidence where it was weak on the sector selection in certain markets including Fiji (spices) and Ghana (cocoa), where proposed interventions need refining or where political economy concerns were raised. These results will be revisited at a six-month check in. On component two -trade intelligence, the selection of priority countries in which the Trade Obstacles Monitoring System will be implemented will need to be confirmed.
- On the expected impact of the programme, the expected results are high in certain countries and lower in others. For example, initial VfM calculations were highly positive for Ghana based on the evidence gathered at country level, and in comparison low in more geographically distant markets or where ITC will be working in niche/new sectors in the Caribbean and Pacific. These markers will need to be revisited at the six-month stage to ensure they are achievable and reliable.
- The programme’s inception period originally was foreseen to be completed by December 2019. However, due to changes in our requirements and delays in scoping missions (including some delays requested by us due to sensitivities relating to parallel discussions with partner countries) the draft inception report was reviewed in December and finalised and approved in February 2020. Implementation phase activities have commenced incorporating the delayed start up and workplans had been adjusted accordingly, however a 12 month extension to the original programme timeline should be considered to ensure the maximum results can be achieved. The recent C-19 impacts are under consideration and will result in further adaptations and flexing of the programme.
- ITC has an extensive multimedia communications strategy to communicate with key stakeholders about the programme. This will be fully rolled out once the programme is formally launched by DFID. Following this, ITC should engage with DFID, FCO and DIT’s communications teams to communicate information, results and lessons from the programme.
- Annual Steering Group meetings should be established with project stakeholders/beneficiaries, partners countries’ representatives, ITC team and HMG officials as appropriate.
- Reporting mechanisms have been agreed. Each pilot export country’s national coordinator will have regular check-in meetings throughout the year with DFID’s Regional Trade Advisors on progress against the log-frame. To minimise duplicate reporting, only major changes in budget or project structure should be escalated to DFID’s central team.
- ITC produced a rapid Gender Sensitive Value Chain Assessment and climate change risk case study for Zimbabwe’s horticultural sector that identified opportunities to address constraints at all levels of interventions. The gender and environmental reports will be published as self-standing documents to inform policymakers and leveraging these reports, ITC will draft gender and environmental action plans for all pilot projects addressing project-specific constraints and opportunities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Figure 1: Theory of Change

Explain major changes to the logframe in the past year [1/2 page]

The logframe was finalised in the inception period and further changes will be tracked here.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme overall has workplans and activities in place to achieve the outputs that were set out. However, it will be extremely hard to isolate the impact of the UKTP on trade aggregates and overall performance because many other determinants come into play. This has become even more obviously true in the Covid-19 pandemic which is strongly affecting global trade and UK/EU demand for the products supported by UKTP.

ITC has proposed metrics to adapt and flex the programme and track cost-effectiveness at an aggregate programme level (return on investment of total funds to creating jobs, increasing the value of exports, and beneficiaries using UKTP tools). These outcomes will be difficult to measure and attribute to ITC activities, and programme may take time to deliver results, meaning this can be the most challenging area of the VfM assessment, but also the most important.

DFID and the Prosperity Fund’s Global Trade Programme (which funds UKTP) are considering an extension of the programme (until 2023) to achieve more mature results after initial feedback from ITC indicated that an implementation phase of less than three years limited the results we could expect to see for our investment within the timeframe of the programme given the nature of the interventions and the sectors in which we are working. We hope that this extension will be formally endorsed following the relevant internal approvals process. This will also entail determining how spend will be re-distributed over the extended period. It is anticipated that an extension will allow beneficiary companies to leverage their presence in more trade fairs to secure more orders and to see the impact of interventions that may take a while to show results, for example additional harvests during the term of the programme may enable us to observe an increase in volume of exports of agricultural produce as a result of programme activities. With an extension, more lessons-learned will be captured in areas where ITC will be testing innovative approaches, such as in services sectors in the Caribbean.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

While there are risks in effectiveness of some of the activities, the programme should go ahead while strengthening its approach to monitoring VFM and testing the Theory of Change. On the expected impact of the programme, the current VfM calculations in the inception report are now positive based on the evidence gathered at country level.
DFID will work with the ITC’s and Global Trade Programme’s monitoring, evaluation and learning units which will provide advice and quality assurance on the effectiveness of the programme’s activities and outcomes at subsequent reviews, including progress against the log-frame, theory of change, and Value for Money (VfM).

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Validated consolidated report for component 1 – transitional support to EPA partner country governments
Output number:		1	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
UK-ACP EPA agreements implemented by partner countries	Country scoping missions and reports completed via TAF2+	Ongoing
	MOU signed with CARICOM Secretariat with accompanying workplan	Ongoing

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]

Transitioning from trading with the UK under the EU EPA agreement to trading under a new UK EPA agreement and managing the implementation of a new trade agreement places demands on the UK’s partner country governments. Component 1 of the UKTP programme is designed to support our partner country governments to meet those demands through the provision of technical assistance and other support to implement the agreements.

This component of the UKTP programme is closely linked with the entry into force of UK EPAs because it relates to support for the implementation of those agreements. If the agreements are not in force, there is nothing to implement. Our timelines for this work was therefore dependent on the UK’s departure from the EU which were influenced by the political context, including the UK general election and the UK’s negotiations with the EU.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

As mentioned above, negotiating and implementing a new trade agreement places significant additional burden on our partner country governments and regional secretariats even though the EPAs between the UK and ACP countries replicate the equivalent EU-ACP EPAs. Multi-country surveys have found that developing countries often lack trained and experienced trade policy analysts and negotiators, have weak institutions that fail to build collective memory; and are frequently unable to access and assimilate relevant external expertise, limiting their ability to address transition issues at short notice. Support for implementation of agreements will commence when agreements come into effect (or shortly beforehand), however, during this period desk-based assessments and scoping work will continue. A due diligence assessment will also be carried out for CARICOM Secretariat in preparation.

Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]

In light of a number of extensions to the timeline for concluding a withdrawal agreement with the EU, and then the conclusion of a withdrawal agreement which is in effect until December 2020, the activities under this component were postponed for most of the review period. Preparatory work still took place, including receiving an initial proposal from the CARICOM Secretariat of a workplan and budget and a proposal from TAF2+ for carrying out scoping for support in the non-CARICOM EPA partner countries.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

It was agreed during this review period that the scoping work under TAF2+ would also cover the SACU+M region, at the request of the Global Trade Programme SACU+M programme manager. This was agreed by the TAF2+ team within the current envelope of TAF2+ funding.

Output Title	Memorandum of Understanding (MoU) between the Government of the United Kingdom and Northern Ireland acting through the Department for International Development (“DFID”) and the International Trade Centre (“The Partner”)
Output number per LF		2	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Business case agreed	Submission and approval of Business case	Completed and Published
Terms of Reference agreed	Approval of Terms of Reference	Completed
Partner has cooperated with the rules around disbursement of funds, ongoing audit and assistance, due diligence, communication and branding	Completion of due diligence / Release of payments of two prepayment amounts as per the MoU.	Completed

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]

A Memorandum of Understanding (“MoU”) was agreed between the Government of the United Kingdom and Northern Ireland acting through DFID and the International Trade Centre. The MoU sets out the terms of DFID’s grant to ITC and governs our arrangements for delivery of the UKTP programme. A sum of £17m of the total UKTP budget was allocated to ITC with disbursement tranches assigned to milestones. During the drawing up of the MoU between DFID and ITC, two prepayments were negotiated for the first year to enable ITC to carry out scoping missions and activities in countries and regions to help with design of the programme. The first tranche of funding of £1.55m was released upon signature of the MoU. The second tranche of £2.7m was released upon receipt of the draft of the inception report including the work plan.

Prior to the MoU agreement and in line with DFID governance rules and standard practice for DFID, an enhanced due diligence (EDD) assessment was carried out to confirm that ITC’s corporate policies and processes, audit, anti-fraud, safeguarding controls are in keeping with DFID’s normal rules and expectations. The EDD also focused on ITC’s governance structures, financial management, audit processes, risk management, procurement and the monitoring and managing of downstream partners. The EDD was completed in October 2019 concluding that (ITC), as an implementing partner, had the capacity and capability to deliver DFID trade-related programmes to promote increased trade and sustainability.

As part of the EDD process, a desk-based review and face to face meeting also took place when the DFID team visited ITC HQ in Geneva on 21st August 2019 to in particular, discuss how ITC manages risks, fraud, audit, safeguarding issues and programme governance and management. These discussions were open, honest and challenging with helpful contributions from subject specialists. The DFID Programme Manager posed specific questions to extract specific information and also to provide ITC with an opportunity to present further evidence.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

During the inception period, the EDD assessment reaffirmed that ITC have developed a set of metrics to track VFM along the 4 E dimensions (economy, efficiency, effectiveness, equity) of DFID’s framework in each country and over the duration of the programme. The ITC employs a range of approaches designed to achieve VFM. On Economy, ITC aims to reduce costs by sharing costs with/ seeking contributions in kind from partners. ITC aims to maximise efficiency and effectiveness through partnerships, technology and cost-sharing. ITC will continue its model of working with partners in this project. ITC’s established networks, presence in country and experience in delivering similar projects to UKTP programme also added to VFM in selecting ITC as an implementing partner.

Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]

The DFID Programme Manager recommended that ITC further strengthen its downstream partner mapping. DFID has asked ITC to consider gathering more assurance and due diligence on their downstream partners particularly around performance assessments and their tracking of payments to beneficiaries. Although no fiduciary risk is envisaged in these partnerships there could be reputational risks to DFID as a donor and ITC as an implementor. A CUBED assessment was carried out by ITC to assess partner organisations’ capability and capacity. The CUBED assessment approach was used to mitigate and avoid delays in selection of partners and procurements if needed. The methodology adopted was effective as it assessed organisations in a uniform and fair manner, the process was transparent and evidence based, the selection of an institution had to justified when presented for approval. The validation process provided the opportunity to approve or challenge any findings or present recommendations to further assess the results. ITC is presently considering extending mandatory training on safeguarding, including a zero-tolerance statement on bullying, harassment and sexual exploitation and abuse to non-staff including consultants, independent contractors and volunteers. Progress on this initiative will be reviewed during the implementation stage.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

ITC has strong overall governance and control arrangements, with good oversight as part of the UN system. ITC has the capacity to carry out the scope of UKTP work and ITC’s systems offer adequate protection to DFID’s resources and reputation. During the inception phase of the UK Trade Partnerships programme, we found ITC to be co-operative, flexible and open to changes in scope of activities and sectors to achieve greater value for money and impact.
- It has strong delivery systems, procedures and good staff capacity in these areas. Its processes and performance appear strong across the project cycle from project initiation to evaluation, as evidenced both by formal evaluations and audits and by feedback from another DFID departments funding ITC.
- No significant concerns over ITC’s financial viability, which are effectively underwritten by WTO and UNCTAD. Its ability to properly account for funds in an open and transparent manner is also strong and evidenced by both UN internal audits and external assessments including by the UK Audit Office.
- The MoU template requires the ITC approver of payments to view evidence of payments receipts, certificates etc. ITC’s approval levels are set to ensure payments are made with scrutiny. For higher payments the request is followed through the Grants Committee that require more detailed evidence and justification prior to approving disbursement of funds.
- ITC requires its consultants and individual contractors to abide by ITC’s policies addressing bullying, harassment, sexual exploitation, and abuse. This is also addressed in MOUs with grantees/implementing partners. ITC have agreed to take all appropriate measures to prevent sexual exploitation or abuse of vulnerable people.

Output Title	Validated consolidated report for components 2 and 3 as well as individual inception reports for pilot export promotion projects in 10 ACP EPA countries
Output number per LF		3	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Field data collection and analysis missions completed	Scoping mission reports	Complete
Reports contain trade facilitation issues; sector/product choice; gender and environment mainstreaming; risk register; preliminary results framework and workplan.	Scoping mission reports and Final consolidated Inception report	Complete
Validation workshop with stakeholders	Final consolidated Inception report	Complete

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]

Since May 2019, research, field data collection and analysis missions were the focus of ITC’s activity. Their finalised consolidated inception report is in good shape covering theory of change, results, VFM and risks, as well as an overview of the trade intelligence component and a summary of each country project, including product/institution selection, strategy, governance and expected results. It is supported by eight detailed individual country reports as well as two reports with risks and recommendations on gender and environment mainstreaming in the Zimbabwe project.

Producing and reviewing many reports simultaneously has been a challenge for both ITC and DFID teams. ITC has accommodated DFID’s interest in its role extending beyond quality assurance to an advisory one. ITC teams have worked hard to revise the draft reports based on DFID’s comments.

There were weaknesses in the initial draft inception reports received from ITC. In particular there was a lack of clarity on the linkages between the evidence and analysis and ITC’s conclusions and recommendations. For example, there were some evidence gaps in relation to the sector selection in the ten pilot export promotion countries. Strengthening the justifications for decisions on sector selection has been a valuable process, allowing DFID/ITC to better understand challenges and needs in each target country. ITC presented evidence about the static and untapped demand for exports from a range of sectors per country. This led ITC to look at some more niche sectors in some countries, such as herbs and spices in Fiji and Penja pepper in Cameroon. There was also a lack in clarity on the link between the challenges identified and the interventions recommended to address those challenges. Through a process of detailed review and discussion of the draft inception reports ITC addressed the weaknesses in the reports, which, in turn, has strengthened our confidence in their proposals.

Since approving the final versions of the country reports, ITC have started to plan for launch events and workshops in country, to raise awareness, determine target firms training needs and assist firms to increase capacity to export to the UK/EU markets (output 4). The first launch workshop took place in Madagascar in January 2020 which was well attended. The second took place in Cameroon in early March. ITC is now evaluating whether and how project activities can go ahead in light of the current C-19 pandemic.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

VfM was not formally tracked by ITC or reported to DFID during the inception phase of the programme. There was no formal framework for the monitoring it, so it was not part of the regular reporting cycle between ITC and DFID. However, we note that the final consolidated inception report was delivered to the expected quality after a few iterations. The effort put into the process by both ITC and DFID teams was invaluable as the document will form a solid base for the implementation phase of the programme.

Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]

This output is now completed. However, through review and discussion of ITC’s inception reports we have identified some areas to monitor during the implementation phase of the programme. These are set out in the lessons learned and recommendations section below.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Areas to monitor in the year ahead include:

Sector selection
In Ghana, strong market growth is predicted for cocoa derivatives, however, it is clear that the project will need to complete an in-depth analysis of UK/EU market trends and requirements as a first activity of the implementation phase. This will be realized through consultation of multiple data sources available and meetings with the industry. This will include structured interviews with buyers in EU/UK as well as local processors of cocoa derivatives to address concerns of supply and volume of beans. ITC will undertake further analysis of UK/EU market trends to determine whether there is enough demand for the cocoa sector.

Interventions
Proposed interventions were refined over the course of the inception phase. In Zimbabwe, there were concerns around which business model would be best suited to supporting small-holder farmers given the challenge of contested land ownership. ITC undertook business engagement and narrowed this down to promising models, lead farms and lease models, plus an irrigation scheme model.

Political economy risks
- The ITC is also identifying which non-tariff barriers and enterprise-level challenges are outside the scope of UKTP but which still need to be monitored, such as corruption within the textiles supply chain in Madagascar. To mitigate against the non-tariff barriers and enterprise-level challenges ITC will ensure only those enterprises willing to innovate are selected to make the textiles and clothing sector more competitive
- Political economy risks were identified in Comoros and ITC will need to monitor the risk of exporting companies increasing their market dominance to the exclusion of cooperatives and other small players.
- In Ghana, ITC will also undertake further political economy analysis to identify whether there could be risks of resistance within the value chain for moving from the export of raw cocoa beans to the export of semi-processed products and identify potential benefits for these businesses.

VFM and results
- In Côte d'Ivoire, DFID has asked ITC to demonstrate the cost effectiveness of the proposed skills training activities and explore standardising training on complying with sanitary and phytosanitary certification.
- In the Caribbean region, further clarity is sought around a coherent export potential strategy to overcome the small-scale results predicted for the Eastern Caribbean islands.
- There remains a need in Fiji to look at the potential demand for regional exports within the Pacific region to justify the cost-effectiveness of the proposed interventions.
- In terms of expected results, in the Caribbean region, ITC modified job-creation targets to make them more ambitious over 10 years given that the services sector needs more time to mature.
- For Cameroon, DFID has also asked for ITC to re-assess the ambition of the job-creation results.
Lessons learnt from UKTP launch workshop in Madagascar:
- During the inception workshop in Madagascar, some challenges were identified which ITC will address relating to company inclusion such as integrating appropriate training for smaller company participants within the cluster of larger companies given different knowledge levels. There is also a need to manage training for geographically dispersed clusters of firms located away from main production hubs.
- The workshop also reaffirmed the importance of donor coordination with beneficiaries mentioning other donors with legacy projects in the textiles and clothing sector. ITC is aware of the need to ensure synergies with other programmes across the pilot export promotion projects such as complimenting activities with ITC’s existing SheTrades programme in Ghana in the cocoa sector.

Output Title	An inception report on improving market information and systems in EPA countries
Output number per LF		4	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Assessment of market information availability, mapping of web-portals and reporting systems in EPA countries	Spreadsheet mapping web-portals and their capability	Complete
Report containing project strategy including intervention logic	Final Consolidated Inception Report	Complete

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]

Component 2 of the UKTP programme seeks to build awareness and transparency of timely trade and market information and the EPAs to create an enabling environment for EPA country exporters. ITC produced a comprehensive inception report outlining their project strategy for this component. This followed an assessment of market information availability, mapping of web-portals and reporting systems in EPA countries. This component has four interrelated interventions: centralising trade data and information; communications and capacity building; trade alerts helpdesk services; and business environment surveys. ITC has set out the reasoning for this component noting the importance to small-medium sized enterprises (SMEs) of understanding the regulatory and business environment in the countries of origin and destination of exports and improving exporters' ability to report potential trade constraints.

ITC found that only 6 out of around 24 EPA countries (Bahamas, Jamaica, Fiji, Ghana, Mauritius and Zimbabwe) have a good coverage of trade-related data required to raise awareness on the use and benefit of the Economic Partnership Agreements (EPAs). They also found weakness in 9 out of 24 countries’ national capacities to collect or maintain the necessary data to build their capacity on data quality. Whilst in 10 other countries, activities to consolidate available information are needed. Given the granularity of this analysis and detailed intervention logic, ITC has scored an A.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

VfM was not formally tracked by ITC or reported to DFID during the inception phase of the programme. There was no formal framework for the monitoring it, so it was not part of the regular reporting cycle between ITC and DFID.

Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]

This output is now completed as the inception report has been finalised and approved. Lessons learned and recommendations relating to this component of the programme are set in the section below.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The UKTP inception period coincided with high activity on the development of other trade-related HMG digital initiatives in the run up to Brexit. We are grateful to ITC for its flexibility in adapting its initial proposals to accommodate changes made necessary to avoid duplication with other initiatives. Our key recommendation for the year ahead is to ensure there is regular collaboration between ITC and the relevant HMG digital teams.

DFID had some reservations about the effectiveness and sustainability of output 2 concerning setting up or strengthening country-specific mechanisms to monitor the business environment given the need for partner government buy-in and capacity for them to succeed. This online mechanism will allow companies to report non-tariff barriers (NTBs) in exporting goods to the UK/EU markets with designated national focal points in identified institutions tasked with processing queries. ITC provided additional evidence and case studies and we have agreed with ITC that the monitoring system will only be implemented if the partner country endorses it and integrates it in its trade facilitation strategy.

ITC also clarified that the aim of the monitoring system is to act as a ticketing system for businesses to raise their concerns and create public-private dialogue rather than to resolve NTBs directly. The constraints captured during the business surveys in 2021 will also feed into the monitoring system from 2022. Given that results measurement on output 2 (making the business environment more transparent) is difficult to capture, it will be valuable to see the feedback of exporters on whether their experiences with regulatory and procedural trade obstacles are successfully brought to the attention of policy makers.

The need for a regional approach in the Caribbean was clarified by ITC in the finalised inception report. Despite varying information gaps, the existence of regional initiatives and regulations will create synergies with national work plans and increase the overall sustainability of trade information. This will include regional organisations facilitating access to trade information in partnership with national organisations; capacity building of trainers on advanced market analysis and a lighter touch business surveys to make the best use of resources. To ensure skills sustainability at the national level, the basic market analysis training will still take place nationally.

A miscommunication about countries within scope for this component was realised and clarified with ITC quickly. DFID and ITC must take care to be clear on the agreed scope given the large number of target countries. It is potentially confusing to stakeholders that UKTP covers all EPA countries except the Southern African Customs Union and Mozambique, which is covered in a separate programme, and we will have to keep this under review. Regular face-to-face/teleconference meetings with ITC are valuable to flush out issues that might not come up in written correspondence. These lessons are important to remember as and when the scope of the programme changes in future with the potential accession of additional countries to the UK EPAs (e.g. Samoa, Solomon Islands, East African Community).

DFID and ITC had early discussions regarding the constraints on activities in non-ODA countries (e.g. Seychelles and some CARIFORUM countries) given that UKTP is ODA funded. Non-ODA eligible countries will still be able to take advantage of some aspects of the trade intelligence component. For example, ITC will be organising project activities at the regional level and enabling self-funded attendance by representatives of non-ODA eligible countries. However, some confusion about ODA rules amongst ITC’s country teams has demonstrated the importance of ensuring that guidance on the rules and restrictions on the use of ODA funds are filtering down from ITC’s central team to ITC’s country teams.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The UKTP risk register includes risks on key areas such as operational, reputational, fiduciary, safeguarding and external context risks. The risk register is regularly updated by the DFID programme management team. The overall UKTP programme risk is assessed as moderate but will be reassessed regularly to determine the severity of risks related Covid-19 pandemic.

DFID maintains a comprehensive risk register for the UKTP programme that is updated at the end of each quarterly reporting period or sooner as risks arise. In the register, all identified risks include probability and impact ratings as well as mitigating actions planned or completed. DFID conducted a due diligence assessment of ITC in October 2019 in which risk management was discussed in depth. Risk management is a standing agenda in regular catch-ups with implementing partners.

Component 1
The risk of delay of activities due to external context of Brexit negotiations materialised during the period under review. The postponements of the date of the UK’s exit from the EU and the negotiation of a transition period affected the timelines of activities under this component because technical support for the implementation of the EPAs is not needed until those agreements come into effect. However, during the inception period, DFID and implementing partners identified scoping activities that can be done in preparation for when the UK EPAs come into effect after the transition period.

Components 2 and 3
The risk register worked well in capturing the nature of the risk, risk category, risk level and mitigation actions. ITC’s risk register was made available to us on a shared drive. ITC could add country specific risks to their risk register, enabling us to monitor them centrally. Some operational and fiduciary risks were the same and relevant across countries and regions, but the reputational risks and market risks were different and specific to the particular country/region. ITC teams members were encouraged to log risks even if it was considered unlikely or the impact would be limited. This allowed the ITC lead in the centre to have a full insight of risks at all levels.

The ITC’s risk register will be reviewed periodically by DFID programme team management to ensure there is a cohesive and sensible approach being taken across the organisation. Through regular programme check-in meetings and quarterly reports, ITC will share with DFID all project related risks pulled from the database. Subsequent reviews of these risks will be updated on the central database.

A few key risks of the UKTP are as follows:
External context:
The highest quality and best targeted technical assistance will fail to produce results without the commitment of key domestic stakeholders. A lack or loss of political will in target countries (which can result from change in a key member of staff as much as a change of Government) is therefore a key programme risk. Ongoing engagement with key figures within public authorities, and a flexible response to evolving circumstances is key to mitigating this risk.
Operational risk
Although Sector and product choice is appropriately tailored to local political and economic context, there is a risk that regulatory institutions in target countries simply lack the capacity to absorb the amount of technical assistance provided, or that staff who have absorbed it subsequently move on. UKTP programme includes diagnostic and design phases to understand the absorptive capacity of partners to take on activities.
Finance related risk:
Sector interventions are not supportive of real economic growth that benefits the poor. There is a danger that increased activity does not drive productive growth in the real economy, and/or that increased integration into wider markets creates a vulnerability. Strengthening regulatory and supervisory capacity to enhance growth and stability is a vital complement of the programme outcomes to mitigate potential adverse effects.
The delivery model of the programme represents a very low risk of fraud or financial mismanagement. DFID manages the programme through close collaboration with implementing partners and Overseas Trade Policy advisors. ITC is recognised as an agency with good systems and processes that deliver programmes successfully.
 Additional risks identified through recent discussions:

Country teams are anticipating the further dissemination of materials and a toolkit via the digital portal. Delays in the portal launch may hamper engagement and reduce momentum.

As the UKTP programme ends, partners and beneficiary organisations may lose motivation to cooperate and/or begin to disengage prematurely. A sustainability strategy is ongoing throughout the lifecycle of the programme and interventions are designed to sustain the activities going forward.

International experts might not be available to travel due to Covid-19 and this leads to delays in programme activities. To mitigate this local teams and consultants are being trained remotely to deliver interventions.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

Component 1 will initially be delivered by existing DFID programmes, i.e. through the Trade and Investment Advocacy Fund (TAF2+) and the CARICOM Secretariat (in the Caribbean region). The transition period has affected the timelines of activities under this component. However, during the inception period, DFID and implementing partners identified scoping activities that can be done in preparation for when the UK EPAs come into effect after the transition period.

Components 2 and 3
DFID and ITC programme management teams developed a good working relationship from the outset of the programme this in turn helped to build a productive, open and flexible approach in designing the intended interventions of the programme. Both teams made concerted efforts to support each other in meeting set targets and deliverables.

In the beginning of the inception phase, ITC faced internal programme management capacity issues and recruitment of local office staff also took longer than expected. To mitigate this ITC lead team members took onboard additional tasks whilst continuing to recruit the team. The ITC programme management team is now well placed and getting up to speed.

The programme aimed to complete the inception phase by end of November 2019. However, due to delays in scoping missions going ahead (including some delays requested by us due to sensitivities relating to parallel discussions with partner countries), changes to the programme design requested by DFID, in particular in developing digital platforms and tools, and reiterations of the inception reports, the inception phase could not fully conclude until February 2020 in some regions. However, we gave approval of the draft consolidated inception report in December 2019, allowing activities to move forward in some countries in early 2020.

In a few countries there has also been limited implementation activities due to lack of collaboration of partner country ministries or where the UK’s EPA negotiations have not progressed. These factors are being carefully monitored and mitigating actions are being set out.

ITC kept DFID updated on progress, impending risks, and expected delays. However, in some instances they underestimated the length and expenditure of the scoping missions resulting in a significant underspend of the allocated budget.

ITC provided quarterly reports in a timely manner with narrative on actions taken. However, it would be useful to ensure closer management on reporting against forecasts to be more transparent, with reasons for delays clearly signposted.

It is expected that the programme will ramp up activities significantly and work efficiently over the next financial year. Throughout the inception phase, there was a consistent delay in projected expenditure. The budget at the beginning of FY19/20 was £4.25m; however, expenditures totalled just £2.956m resulting in a significant underspend.

 UKTP Budget Status - AR 2020

Year 1 (2019-2020)	Apr - Jun 19	Jul - Sep 19	Oct - Dec 19	Jan - Mar 20	Total
Original budget	£258,333.00	£770,501.00	£1,196,166.00	£2,025,000.00	£4,250,000
Actual spend	£159,355.20	£739,339.73	£744,039.60	£1,313,631.15	£2,956.3365.69
Variance	-£98,977.80	-£31,161.27	-£452,126.40	-£711,368.85	£1,293.634.30

For this financial year the key cost drivers have been professional fees, administration costs, non-operating costs and management overheads. With a full ITC team in place it is envisaged that programme intervention activities will be costed and forecasted more accurately going forward. The underspend caused significant budget and forecast variances and as a result the underspend amounts had to be returned back to Prosperity Fund. As a consequence, a significant budgetary reduction was applied to the allocation of FY 20/21.

The importance of accurate forecasts has been clearly communicated to all teams involved, regular catchup meetings have also been set up to keep on track of the expected spend. This has become increasingly important in the current volatile environment due to Covid-19 spread and its potential impact on activities and milestones.

Financial matters are discussed and agreed in monthly catch-ups and submissions, impact in terms of value for money is always considered in decisions made. During the ITC due diligence assessment exercise, it was evident that ITC has a clear process for managing procurement and contracts. The procurement manuals set out clear processes that prospective suppliers and partners must meet.

It was agreed that monthly financial forecast & expenditures would be submitted by ITC by 20th of each month and will provide an effective means to improving financial and risk management.

Recommendations

1. ITC to ensure that DFID can compare the budget set at the beginning of the year against monthly forecast updates and actuals. Ensure that the report incorporates a narrative to justify the variances.
2. ITC should use the RAG rating in order to determine realistic forecast. The overall forecast figure should be risk adjusted.
3. Given the demand-led nature of the programme, ITC should by using the RAG rating to manage in-year expenditure.
4. DFID and ITC should work together to ensure that the timing of forecasted expenditure takes ODA (calendar year) and financial year (Apr-Mar) targets into account i.e. not forecasting fund disbursements with a high risk of failure in December and March.