Project Completion Review – post April 2019
Title: Bihar Agriculture Growth and Reforms Initiative (BAGRI)
Final Programme Value £ (full life): £10 Million	Review Date: September 2020
Programme Code: 204135	Start Date: 29/06/2015	Final End Date: 28/06/2020

Summary of Programme Performance

Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4158341.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/46430093.xlsx

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

Bihar Agriculture Growth and Reforms Initiative (BAGRI) provided a range of technical assistance support for the reform of agriculture sector in the state of Bihar in collaboration with the Department of Agriculture (DoA), Government of Bihar (GoB) over a period of five years from July 2015 to June 2020.

At the state level the programme provided support for governance and policy reforms for strengthening agriculture marketing, warehousing and storage, farm mechanization, seed production promotion, agriculture research and other allied areas. Overall 35 reforms were supported of which 20 were adopted by the state government and 8 are now under implementation. At the field level it helped aggregation of small and marginal farmers into Farmer Producer Companies and their strengthening. Supporting GoB in the implementation of its Agricultural Road Map 2017-22, BAGRI focused on fruits and vegetables growers across 11 districts of Bihar. The overall objective of the programme was to help impro,ve performance of the agriculture sector in Bihar by catalysing private sector investment, higher production and price realisation by farmers. Activities towards these objectives included facilitating collectivization of farmers into Farmer Producer Groups (PGs) and subsequently into Farmer Producer Companies (FPCs) create forward and backward linkages, assist in developing market value chains and contribute to key agriculture sector reforms in the state.

Over past five years, BAGRI piloted community led collectivization of agricultural activities to infuse viability for small and marginal landholding farmers and increase their income. Through project interventions, over 75000 farmers have been mobilised into about 3400 Producer Groups and finally registered into 20 Farmer Producer Companies To catalyze agricultural transformation through community led approach, BAGRI facilitated backward, forward and financial linkages thereby enabling FPCs to move up the supply/value chain in order to capture better value/margins.

Major companies with which innovative and pertinent forward linkages were forged are ITC, Mother Dairy, Big Basket, Arya Collateral, Dehaat, Ergos, Milk Basket, Britannia, and NeML etc. Through these collaborations, BAGRI tried to circumvent at least two level of intermediation and enabled FPCs to sell farmers’ agri-produce directly to institutional buyers, resulting in better price realization. BAGRI has also facilitated critical backward linkages with companies like IFFCO, BRBN, S. V. Agri, Harvest Plus, BigHaat, AgroStar, Bayer, DeHaat etc. thereby enabling FPCs to provide quality agri-inputs at competitive prices to its member farmers in timely manners. The FPCs were facilitated in acquiring necessary licenses to open their agri-input shops as well. These linkages and collaborations for the FPCs helped improve the realization from agri ouputs, reduce the cost of the agri input, thus helping farmers improve their incomes.

BAGRI Promoted FPCs have on an average share capital base of about Rs 5 lacs per FPC with a range between INR 130,000 to INR 1.2million. Though, this corpus amount has grown over a period of time; for many FPCs it is not enough for meeting the working capital and funding requirements. Keeping this in mind, BAGRI facilitated multiple financial linkages for FPCs with institutions like Samunnati, FWWB, Aryadhan, etc. for working capital related requirements. BAGRI also facilitated convergence of Small Farmers’ Agri-Business Consortium (SFAC) equity grant schemes with the FPCs. Working capital loans ranging from INR 300,000 to INR 1.5 million were facilitated for the FPCs.

Additionally, BAGRI facilitated piloting of multiple innovative business propositions like farmgate level warehouse receipt financing in collaboration with Aryadhan, minimum price guarantee based contract farming of potato cultivation in collaboration with S.V. Agri, promotion of women entrepreneurship for creation of FPC led rural to rural supply/value chain of processed food products, e-commerce based agri-input procurement model, promotion of niche agri-produce (Shahi Litchi) supply chain optimization in collaboration of Department of Horticulture (DoH) and Indian Post, farmer to farmer based radio taxi model of custom hiring centres in collaboration with Jfarm and ensuring nutritional security through seed production of zinc fortified wheat seed in collaboration with Harvest Plus etc. Through these pilots, BAGRI has opened up opportunities for the FPCs and has captured numerous ground level wisdom, knowledge and insights that can be carried forward.
At the State level, BAGRI facilitated Government of Bihar in policy formulation and providing institutional strengthening support to its functionaries like Bihar Agricultural Management Extension and Training Institute (BAMETI), eKisan Bhawans, Bihar Rajya Beej Nigam (BRBN) etc. The important policy initiatives include introducing an alternate Agri-marketing system in the state, an in-house seed production framework, streamlining state schemes for effective implementation, introducing capital subsidies in Agri-business investments and many more. BAGRI also provided capacity building support to Bihar Agriculture University (BAU) through linkages with University of Greenwich, UK and Cornell University, UK in agricultural research. Apart from these, BAGRI has also facilitated micro food enterprise promotion in post-harvest management of more than £40m in the state.
The aforementioned stream of activities undertaken in the BAGRI programme have been structured into 4 outputs and the same reflect the importance of activities and their correlation with the theory of change. The outputs have been elaborated in the subsequent sections.

Progress against recommendations of last AR

In its final year, the programme will focus on sustainability of its interventions and preparing an exit strategy with GoB. The strategy will be prepared jointly with GoB and disseminated to widely to key stakeholders – by October 2019	A concerted handover strategy and activities have been conducted, not only with GoB officials but also with the community level participants in FPCs. The sustainability strategies and activities have been well disseminated and reached to different stakeholders. Date of handover meeting 25th June 2020 (vault id: 56875068)
The programme will prepare Standard Operating Procedures (SoPs) for all its key operations (forming farmer collectives, operating manuals for FPCs, key terms of negotiations with market players, training modules etc.) and hand them over to BoD of FPCs and GoB officials – by October 2019.	Detailed standard operating procedure for activities involved in formation and promotion of FPCs in Bihar have been prepared and shared. It involved SOPs for farmer mobilisation, FPC registration as a company, Training and capacity building, compliance management, various business and governance activities as well as financial components like working capital loan application , books of account management etc.
The Implementing Partners will systematically document lessons learnt and prepare best practice case studies throughout next year, in close consultation with DFID’s Results and Communications Advisers.	BAGRI compiled a comprehensive document with case studies that capture key activities and lessons learnt across project life cycle including community mobilisation, FPO formation, establishing marketing and financial linkages, various policy formulations and digital interventions like JFarm among others.
DFID programme team to prepare an effective communications strategy that assures GoB of UK’s continued presence and support to Bihar through other multi-state programmes over the next year.	An official communication in this regard has gone from the HoO, DFID India to the Agriculture Minister, Government of Bihar (vault id: 5836142)
The Implementing Partners to support the Post Completion Review of the programme by developing capacity to monitor the programme’s overall impact and sustainability parameters – by May 2020.	The project has enabled formation of working groups for all key initiatives with Department of Agriculture, GoB to help keep track and monitor progress of various policy reforms and FPC formation and promotion initiatives. / Handover meetings and consultation workshops were also held to capacitate the Department of Agriculture to carry out the activities themselves post project closure.
DFID India to actively engage with BAGRI programme team to identify potential future investment opportunities – either in mature FPCs or the private sector investee companies (food processing, cold storage etc.) facilitated through BAGRI programme. Moreover, the lessons that have emerged through the programme can be used to inform DFID’s engagement in the sector in other states of India.	As stated above, a compendium of successful case studies and lessons learnt document exists for easy reference of DFID. The same may be used and leveraged in the sector as well as other parts of the country. (vault id 57179429) / The compendium may be referred to for exploring potential future investments in food processing units, farmer producer companies and Agri input organizations.
[note] ( see vault id : 55836038, 55836478, 55836477, 55836034, 55836363, 55836586 for documents pertaining to project closure including SoP for FPC management, 4-model business plans, Facilitating adoption of 5 FPCs by BHDS, GTM for accessing credit, Strategy action plan for Bihar Organic Mission, Implementation of seed sector initiative & BRBN, e-NAM related activities and Standard bidding document for e-Kisan Bhavan and MSTL)

Acronym	Full form
AMP	Aid Management Platform
AR	Annual Review
ATMA	Agriculture Technology Management Agency
BAGRI	Bihar Agriculture Growth and Reforms Initiative
BAMETI	Bihar Agricultural Management Extension and Training Institute
BAMIIS	Bihar Agriculture Market Information and Intelligence System
BAU	Bihar Agriculture University, Sabour, Bhagalpur
BHDS	Bihar Horticulture Development Society
BISA	Borlaug Institute for South Asia
BKB	BAGRI Kisan Bazar
BKSK	BAGRI Kisan Sewa Kendra
BoDs	Board of Directors
BRBN	Bihar Rajya Beej Nigam
CRPs	Community Resource Person
DFID	UK Department For International Development
DoA	Department of Agriculture
DoH	Directorate of Horticulture
eKB	e-Kisan Bhavan
FPCs	Farmer Producer Companies
FPCs	Farmer Producer Organisations
FWWB	Friends of Women's World Banking
GBP	Great Britain Pound
GoB	Government of Bihar
IAD	Internal Audit Department
ICT	Information & Communication Technology
IFFCO	Indian Farmers Fertiliser Cooperative Limited
ITC	India Tobacco Company
JFS	J-Farm Services
KANCHI	KISAN'S ADVANCEMENT THROUGH CASHLESS INNOVATIONS
KPIs	Key Performance Indicators
KVK	Krishi Vigyan Kendra
LF	Log Frame
M&E	Monitoring & Evaluation
MFIs	Micro-Finance Institutions
MSTL	Mobile Soil Testing Laboratories
MTR	Mid-Term Review
NABARD	National Bank for Agriculture and Rural Development
NBFCs	Non-Banking Financial Corporations
NRI	Natural Resources Institute
NRI	Natural Resources Institute
OBCs	Other Backward Classes
PCR	Project Completion Review
PGs	Producer Groups
PPCs	Plant Protection Centres
PPP	Public-Private-Partnership
PPPIAD	Public Private Partnership Initiatives for Integrated Agriculture Development
PPs	Partnership Principles
R&D	Research & Development
SAP	Strengthening Action Plan
SFAC	Small Farmers’ Agribusiness Consortium
SHGs	Self Help Groups
SRO	Senior Responsibility Officer
SV Agri	SiddhiVinayak Agri Processing Pvt Ltd
TA	Technical Assistance
TAFE	Tractor and Farm Equipment Ltd
TAST	Technical Assistance Support Team
ToC	Theory of Change
UK	United Kingdom
VfM	Value for Money

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Enabling Formation of sustainable farmer collectives ( Producer Group / Co-operatives) for Maximizing Profits to Farmers and Strengthening their Bargaining Power)
Output number per LF		1	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
1.1 No. of farmers mobilised into Producer Groups (PG)’ groups	75,000	75,793 (Exceeded)
1.2 No. of Producers Groups (PG) formed	3,750	3,451 (Met)
1.3 No. of women farmers mobilised through PGs	12,000	16,892 (Exceeded)
1.4 Farmers Producer Companies (FPC) registered	20	20 (Met)
1.5 No. of FPC achieved threshold shareholder capital of 3 lakh	20	16 (Moderately not met)
1.6 Number of FPCs facilitated with institutional credit	10	11 (Exceeded)

Provide supporting narrative for the score

output 1.1, 75973 farmers mobilized against a target of 75,000. This was achieved though community resource persons (CRPs) deployed as part of BAGRI team.

output 1.2, 3451 PGs were formed against the target of 3,750. A conscious call was taken, after last year’s annual review, to saturate the number of PGs already formed vis-à-vis forming new PGs just to meet the numeric target. Moreover, the programme had already met its target of reaching 75,000 farmers. In the last year of project implementation, post mobilisation of intended number of farmers, focus was more on capacity building of these informal farmers’ groups and its effective market linkages through FPCs.

output 1.3, BAGRI interventions have so far led to mobilization of 16,892 women in various PGs which is about 40% higher than the envisaged target, thereby taking the women farmer participation to about 22% in the programme.

output 1.4, Out of the 20 FPCs formed, 10 were formed in year 2017-18 while other 10 were facilitated to be formed in year 2018-19. All the 20 FPCs are engaged in agri-produce marketing through Rural Haats, BAGRI Kisan Bazar, Kray Kendra and Kisan Seva Kendra (Agri-input).

output 1.5, 16 of the BAGRI promoted FPCs have achieved threshold share capital of Rs. 3 lacs (against the target of 20 FPCs). This achievement is largely driven by FPCs which were registered in 2017-2018 and early 2018-19. Covid & subsequent lockdown has impacted share capital mobilisation drive in last leg of the project specially for newer FPCs and hence leading to a slight shortfall in targets.

For output 1.6, as against target of 10 institutional financial linkages, 11 were facilitated including for working capital loans, warehouse receipt financing and matching equity grants.

Lessons identified this year linked to this output and recommendations for future programmes

BAGRI programme as per its design could offer only technical assistance in farmer mobilization, formation and strengthening of FPCs. FPCs have faced acute shortage of working capital to effectively scale up their operations. While, BAGRI helped mobilize funds from NBFCs and other sources for the FPCs, there has been limitations on the scale of funding considering small shareholder corpus held by recently federated FPCs.
Recommendation: It may be useful for future programmes on community mobilization to have components of financial assistance in terms of revolving funds or agri-infrastructure funds etc. to complement the Technical Assistance inputs.

BAGRI programme originally focused on horticultural crops only. While, it soon became evident that in order to add greater value in lives of farmers, the interventions have to cater to most of their agricultural produce and there is a need to be relevant for its member farmers throughout various agricultural cycles. Hence, it would be important to design and implement FPCs or farmer programmes on round the year crops with more broad based scope than only fruits and vegetables.
Recommendation: Commodity neutral approach may be followed in FPC promotion with basic principles of aggregation.

The programme has provided active handholding and capacity building support to producer groups and have made efforts to imbibe business acumen through various trainings. Such community activities require long gestation to yield mature and self-sustainable social institutions. A large number of FPCs (set up in last 2 years) are low in their maturity and learning curve given these did not benefit from capacity building support over the full duration of the project.

Progress against recommendation of last AR

Recommendation	Progress
BAGRI will continue to strengthen the FPCs’ linkage to formal institutional finance in its last year of operation for all FPCs. The programme is actively pursuing a linkage with the Small Farmers Agribusiness Consortium (SFAC) for matching grant support to the mature FPCs. Receiving matching grant from SFAC will be a catalyst to boost the business volume.	Programme facilitated Equity Grant disbursement from SFAC for DFPCL while it also facilitated application for SFAC’s equity grant for four more FPCs. It has successfully facilitated adoption of four of BAGRI FPCs with a scheme of DoH which also have provision for grant of Rs 5 lacs.
In its last year of operation, the programme will focus on strengthening functional capacity of the FPC office bearers and the BoDs across all 20 FPCs. There will be strong focus on imparting trainings on management of finance, human resources, stock and inventory, procurement and quality management, marketing, internal audit, internal conflict resolution and other important functional areas. BAGRI will also ensure peer-to-peer learning through cross visits.	BAGRI has conceptualised, formulated and implemented comprehensive training programme for office bearers and the Board of Directors (BODs) of all 20 FPCs. These trainings include techno-managerial and soft skill modules. BODs were provided training and capacity building support on compliance management, business planning, SOPs, procurement and market linkage activities, leadership and negotiation skills etc. List of trainings provided attached as an annex.
In order to sustain the PGs, the programme will ensure that every PG has a functional role in the business operation of FPCs – either by being part of operational committees (procurement, logistics etc.) or maintaining books of accounts etc.	FPCs with PGs connected through effective business linkages and also through various income generation activities. BAGRI promoted entrepreneurship among PG members to participate in business activities of FPCs. / For example: Training and capacity building support was provided to women PG members of CBFPCL, Begusarai and have integrated their entrepreneurial ambitions with mustard processing and marketing operations undertaken by CBFPCL
The programme will explore possible linkages with other stakeholders, example SFAC, RABO Bank, so that the FPCs have access to a market readiness fund (working capital) which could be used even after the programme support comes to an end. The programme team will also firm up the projected cash flow statements and have a Business Plan (both in the way it is desired by formal financial institutions and simple language as understood by farmers) for each FPC. It is imperative that Board of Directors are involved in preparing business plans and participate in the discussions with the formal financial institutions.	Facilitated adoption of FPCs under existing programmes to ensure that the FPCs are getting required mentorship post programme closure. It has facilitated innovative collaboration between S.V. Agri and FWWB to provide financial linkage and business facilitation to 10 FPCs post project closure. It facilitated adoption of another 4 FPCs with Samunnati and 4 under a scheme of DoH named BHDS. All three facilitations will provide financial linkage and business linkage support to FPCs. Table of linkages facilitated has been provided in an annex.
For business operations BAGRI FPCs have been utilizing the equity/share capital contributed by the smallholders, however as the operations expands there is requirement of creating a readiness fund/working capital support with the FPC.	Thus during last year, it facilitated warehouse receipt finance, working capital finance and also grants from government agencies including SFAC, DoH and ATMA. BAGRI has facilitated linkage of FPCs with FWWB for working capital and Aryadhan for warehouse receipt capital.
As the programme has reached its target of forming 20 FPCs, the output indicator 1.4 in the logframe (FPCs Registered) will be replaced with an indicator on Financial and Business Efficiency and Sustainability Readiness of PGs and FPCs (Total annual sales; Gross margin (Direct Income {income from direct sales} – Direct Costs), Net Profit, Current ratio (Current assets to Current liabilities); Debt equity ratio, break even sales, operational margin, inventory turnover ratio).	Post successful incorporation of 20 FPCs a few new indicators were introduced to capture the quality of business and efficiency of the FPCs. / They are the following: / Number of FPCs accumulated share capital of INR 3 Lakhs / Percentage of PGs directly linked with business transactions
The 20 FPCs that have been formed under BAGRI have different levels of maturity. To enable GoB (and the FPCs themselves) track their functional efficacy, the programme will develop a baseline Maturity Index of BAGRI FPCs. The Index will capture performance of the FPCs on parameters like: / o Membership (active members to total members; attendance in board meetings; members attending the General Board meeting; legal compliance met); / o Governance and Management of FPC (Annual General Meeting quorum, Board Meeting), / o Business Plan in place and approved by the BoDs. BoD aware of their responsibility and attended the training); / o Business Operations (FPC having transparent payment and cash flow systems – maintains accounts book, ledger and stock register), / o Financial Management – % of profits generated, Reserve Fund, % of Overhead expenditure met with own resources, trained accounting staff and effective accounting system, Audited statements of PCs are accessible) PC has access to long term affordable finance to fund operational plan/business plan.	FPCs have been categorised in three types based on five elements namely Governance Capabilities, Management Capabilities, Business Linkages, Financial Capabilities and Ecosystem support. These broader themes comprised subthemes like membership, business operations, financial management, Governance among others. / Accordingly the categorization of 20 BAGRI FPCs is as under : / Early Maturity stage (4 FPCs), / Progressive Stage (4 FPCs) and / Nascent Stage(12 FPCs). / It helps in designing interventions, training and capacity building in very targeted manner.

Output Title	Strengthening the Marketing Chain and Market, wherein Small / Marginal & Poor Farmers are Effective Partners
Output number per LF		2	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
2.1 No. of new market linkages developed at FPC level	20	20 (Met)
2.2 % of PGs facilitated with better market linkages	30%	30.02% (Met)
2.3 Market linkages turnover facilitated through FPCs/PGs	£2.5 m	£2.4 m (~ Met)

Provide supporting narrative for the score For output 2.1, Target of 20 market linkages was achieved. Multiple innovative business models were piloted to drive market linkage activities with serious intent and enthusiasm which is reflected through wide range of institutional partnerships that were facilitated such as with ITC, IFFCO, Bayer, BigHaat, Mother Dairy, Big Basket, DeHaat, Harvest plus, BISA, BRBN, S.V. Agri Processing Pvt Ltd, Arya Collateral etc.
Beneficiary Feedback:

Arvind Tiwari, BOD of DFPCL:

In our village, individually we were selling wheat to private traders at INR 1500 per quintal. There was always uncertainty in this proposition as it was solely dependent on the wish of the trader. With the formation of DFPCL, we entered into a contract with ITC limited on a fairer term of trade. By registering DFPCL as one of the vendor with ITC, the FPC bypassed two levels of market intermediaries, resulting in additional realization of at least INR 70-INR 80 per quintal to member farmers.

DFPCL procured wheat at INR 1670-1800 during the entire season thereby ensuring immediate minimum gain of additional 5% to the member farmers.

For output 2.2, market linkages target of 30% for PGs was met. BAGRI conceptualized and facilitated innovative marketing models for collective input and output linkage of 1036 PGs. This should also be noted here that post formation of FPCs in all project blocks, transactions and their recording has shifted to such FPCs. This means that spread of PG level transaction is wider than the numbers reflect here as each FPC has a mandate to serve all PGs in respective catchment district. Hence strengthening of FPC enhances its capacity to serve the constituent PGs.

For output 2.3, Designing and implementing new market linkages as well as scaling and replicating existing ones have cumulatively resulted in achievement of the milestone with turnover of £2.39m. As a result of Covid-19 induced lockdown, business transaction of FPCs has been drastically impacted in last two quarters of the project. The projected turnover constitutes over £0.96m worth of collective agri-input linkage and £1.43m of agri-output linkages. BAGRI has also focused to institutionalize market linkage activities through Input Shops, Collection Centre, Kisan Bazar, mini cold storages to develop in-house capabilities to carry forward the linkage initiatives beyond project closure.

Lessons identified this year linked to this output and recommendations for future programmes

The programme has successfully piloted multiple market linkages and innovative business models. However, absence of post harvest agricultural infrastructure at FPCs’ level created challenges to suitably scale and replicate these initiatives.
Recommendation: Some form of provisions for building relevant agri-infrastructure with FPCs to facilitate institutionalisation of learnings and experiences would help ensure sustainability of the linkages developed.

The programme faced challenges to facilitate commencement of business operations at FPC level in absence of minimum capital to procure various regulatory / statutory certifications. Additionally, the programme in its current structure does not have any provision for market development like packaging material development, branding, participation cost in any national or international food/agri-produce fairs etc.
Recommendation: Future programmes should consider having Market Development Assistance Fund. This can facilitate better market outreach and functions.

Market linkages were established during early stage of FPC formation, and the same have gained about three years of active handholding support from BAGRI. Those formed during the early days of the project are relatively well matured than the ones which have been piloted and established recently. It has been observed that FPCs need about 3 years of handholding support for any socio-business intervention to become self-sustainable and entirely community driven.

Learning from the potato contact farming model with PepsiCo in Rohtas district, BAGRI facilitated FPCs to enter potato buy back arrangement with Maharashtra based SV Agro Pvt. Ltd. Unlike PepsiCo model wherein entire quality testing process was done at PepsiCo factory gate, SV Agro has agreed to complete all its processes at farm gate for BAGRI FPCs and provided minimum price guarantee per kg or market price whichever is higher. Such innovative solutions can be an effective replicable market linkage model for perishable commodities.

BAGRI provided extensive training and capacity building activities to impart skills required for implementing forward or backward linkages including quality testing, crop specific training, training on managing books of accounts etc. Further, the team collaborated with Arya Collateral to impart managing collection centre skills, S.V. Agri for agri-input demand generation, etc. These training and capacity building activities orient growers towards market led productions.

Progress against Recommendations of last AR:

Recommendation	Progress
To remedy the issue of distress-sell and inadequate cold storage for perishable goods, the programme will be piloting two models in the next year which can be subsequently scaled up by GoB: / First, BAGRI has already operationalized Bagri Kisan Bazar (BKB) linked to all its FPCs – that creates an aggregation of farmers around a 200 km radius of the FPCs where farmers can sell their products are fair market prices without relying on local market aggregators who takes commissions (thus reducing the farmers’ profits). In the next year BAGRI will ensure BKBs cover all its 20 FPCs across the 11 districts. / Second, BAGRI is in advanced discussion with agri-tech start-ups to pilot mini cold storages in one of the BKBs. This cold storage can store perishable items for 6 to 7 hours – thus reducing the farmers’ stress to sell their produce on the same day at a throw away price. The cold storage will be operated by the FPC on a commission basis – which will be used by the FPC for operation and maintenance of the facility.	In order to enable farmers not to do distress sales, both models were piloted through BAGRI promoted FPCs. / BKB model piloted vegetable and fruits marketing with 4 FPCs; piloted BKB model for dry agri-produce with 8 FPCs through temporary harvest season based collection and marketing centres; collaborated with Arya Collateral to enable FPCs avail warehouse receipt finance and facilitated piloting of the model with CBFPCL. Because of various constraints like flood, drought, lack of appropriate financial linkages from banking institutions to newer FPCs of BAGRI and Covid induced lock downs, the BKP model could not replicated for the 20 FPCs within the project period. / Cold room enabled fruits and vegetable marketing centres in Muzaffarpur and Patna were piloted. BAGRI facilitated collaboration with Cool Crop Pvt Ltd. who provided the facilities on minimum monthly rental basis. Though because of various factors including shortage of vegetables during draught and floods, market rate sky rocketed and farmers didn’t feel the need to store their vegetables in cold storage as a result during last year utilization rate of the facility was not able to touch break even point. Though it came handy during marketing of litchi in collaboration with DoH and Indian Post.
Each FPC will have a designated office bearer responsible for corporate compliances, record keeping and ensuring transparency. The team will design specific training modules to ensure this.	Various training and capacity building modules on corporate compliance, record keeping and ensuring transparency have been developed and related training and capacity building support were provided to the office bearers of FPCs. Additionally, FPCs have been enabled with standard operating procedures to ensure transparency.
The programme will revisit the relevance of output 2.2 (% of PGs facilitated with market linkage). Since all 20 FPCs have now been formed, market linkage efforts will be focused at the FPC level only (output 2.3) to track market linkages turnover facilitated through FPCs only (aggregation at the FPC level only – as it will help in strengthening the balance sheet of FPC). Each FPC has a mandate to serve all PGs in respective catchment district. Strengthening of FPCs means that it would have better capacity to serve the PGs.	During last year, due emphasis was provided on market linkage activities and turnover of FPCs. Through detailed monthly planning, growth rate of 126% in turnover of FPCs over cumulative turnover till 2018-19 was achieved. During 2019-20, BAGRI has facilitated turnover of about £1.33m. One of BAGRI’s FPCs i.e. DFPCL have cross turnover of Rs 4 Crs whereas two of the BAGRI’s FPCs have crossed turnover of Rs 0.75 Crs.
The programme team will also track the progress of FPCs on the maturity index (as outlined in the section above), capacitate the BoDs and other office bearers on business plan, negotiating terms of trade with private sector and engaging with institutional buyers/market linkages with long term agreements.	As per this maturity index, BAGRI 20 FPCs were categorised under three types namely Early Maturity stage (4 FPCs), Progressive Stage (4 FPCs) and Nascent Stage (12 FPCs). / Capacity Building programmes were carefully conceptualized and formulated for FPCs based on their maturity level e.g. learning modules on governance and management, compliance management, scheme convergence and books of account management. / Trainings that cuts across FPC life-cycle were given to all three categories of FPCs whereas enhanced support on business incubation, agricultural value chain and innovation in Agri-value chains were given to ‘Early Maturity stage’ & ‘Progressive stage’ FPCs to enable them to establish effective market linkages and pilot innovative business models (more details in output description above)

Output Title	Enabling Accessibility to Clear, Reliable and Dynamic agricultural Information
Output number per LF		3	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
3.1 No. of districts facilitated with mechanism to collect agricultural market price from BAGRI project areas	11 districts	11 districts (Met)
3.2 No. of farmers getting access to BAGRI facilitated real time market information	5,000	5,491 (Exceeded)
3.3 No of farmers getting access to better knowledge and technology inputs through electronic / mobile- services, one stop shops/other improved models facilitated by BAGRI	20,000	80,552 (Substantially Exceeded)
3.4 No. of farmers facilitated for improved soil testing infrastructure through MSTL and advisory services facilitated by BAGRI	15,000	Not met
[note] The achievement of 5,491 represents total number of app downloaded by PG members
[note] Total 80,552 – (J-Farm Services: 70661, BKSK: 4000, BKB: 400, BAMIS: 5491)

Provide supporting narrative for the score

For output 3.1, BAGRI has facilitated creation of market information mobile application named BAGRI Agricultural Marketing Information System (BAMIS). CRPs have been given additional responsibility to update market rates of various vegetables in their respective mandis. While BAGRI also motivates farmers to download the application. CRPs are given training on market rate updating and other techno-functional aspects of the application.

For output 3.2, as per BAMIS application download data, 5,491 farmers have downloaded the application and are receiving price and market information on their mobile phones on a regular basis. It is to be noted that the overall benefit of timely access of price information percolates to far higher number of farmers as typically 9 farmers get benefit of price information from 1 member farmer who has downloaded the app and has access to price information through the same. This implies that around 49,000 farmers have access to price and market information through the app. Market prices are collected through the FPC owned mobile application with the support of CRPs and disseminated to various farmers.
[note] This is derived through FGDs conducted in Muzaffarpur, Gaya, Rohtas and Nalanda

For output 3.3, more than 80,552 farmers against target of 20,000 are getting access to better technology input through mobile and internet services, KISAN'S ADVANCEMENT THROUGH CASHLESS INNOVATIONS (KANCHI) enabled one stop shops and other innovative models – facilitated by BAGRI. This was made possible because of effective training and capacity building provided to CRPs who in turn disseminates the same to farmers during monthly PG meeting. All 20 FPCs have been facilitated to open one-stop-shops in the form of BKSKs for knowledge and technology dissemination.

For output 3.4, the contract negotiation with the selected private party for operating Mobile Soil Testing Laboratory (MSTL) vans through Public-Private-Partnership (PPP) has been unsuccessful and therefore re-tendering of the same is in process. This will now be taken up by Government of Bihar.

Lessons identified this year linked to this output and recommendations for future programmes

There was useful collaboration between KANCHI with BAGRI promoted FPCs; wherein KANCHI has provided free of cost hardware to all the FPCs and have facilitated installation of KANCHI in 15 FPCs. Adoption rate of these interventions are very low and evolving.
Recommendation : FPCs need extensive training and capacity building support to promote adoption of KACNHI.

BAGRI also promoted collaboration with J-Farm to facilitate implementation of Farmer to Farmer based radio taxi model of custom hiring services of farm equipment. The initiative has been scaled to onboard more than 80,000 farmers and 6,000 renters. value of orders booked through J-Farm app is about INR 80 million.
Recommendation : There is a need to further scale the initiative and also provide added benefits through the app like rate forecast of fresh fruits and vegetables

BAGRI has helped establish one-stop-shop for agri-input (BKSK) with each of the FPCs. Farmers get updated information on price, newer agri-technologies etc through the centre.
Recommendation: There is need to digitize these centres to display Realtime information through display boards etc.

Currently farmers are facing multiplicity of data/information from various sources and are unable to establish authenticity of information.
Recommendation: Need to work with government agencies to improve credibility and authenticity of information disseminated amongst farmers.

Progress against recommendations of last Annual Review

Recommendation	Progress
The programme team has already been working closely with GoB to bringing in a sustainable solution in providing real time price and market information to farmers in Bihar. In the final year of operation, the programme team will intensify its focuses on this support to GoB on modernization of the now defunct market yards and timely procurement of private suppliers for managing market prices and related information and display real time price information through LED boards.	Project supported GoB in getting a full DPR prepared for renovation of erstwhile market yards in the state. This DPR is being prepared by Bihar Rajya Pul Nirman Nigam Limited (GoB undertaking), the project has provided technical inputs to develop the same. The DPR has mechanism for price dissemination and market information in Bihar.
As the finalization of government procurement for MSTL vendors is in its final stages, BAGRI will help GoB with the process and ensure operationalization of the service by next year.	The contract negotiation with the selected private party for operating Mobile Soil Testing Laboratory (MSTL) vans through Public-Private-Partnership (PPP) has been unsuccessful and therefore re-tendering of the same is in process.

Output Title	Strengthening institutional capacity, introduction of regulatory reforms and facilitating private sector investment in agribusiness in the state
Output number per LF		4	Output Score	A+
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
4.1 No of policy & institutional reforms initiated by BAGRI	14	35 (Substantially Exceeded)
4.2 No of proposed reforms adopted by Agri Department and/or Roadmap	8	20 (Substantially Exceeded)
4.3 No of policies and schemes facilitated in practice by BAGRI - include pursuing E Kisan Bhawan	1	8 (Substantially / Exceeded)
4.4 E-Kisan Bhawans operationalised through BAGRI facilitation as pilot	2	1 (Unmet)
4.5 No of partnerships with academic universities focused on agri through UK linkages in agricultural research	2	2 (Met)

Provide supporting narrative for the score

For output 4.1, during the project period, BAGRI has facilitated the Agriculture Department in developing more than 35 policy and institutional reforms in the intervention areas of Seed, PPPIAD, agri. marketing, farm mechanization, Jal Jivan Hariyali abhiyan, Agri Investment Promotion, strengthening of BRBN and BAMETI, Bihar Organic Mission, agri. education and research, state level FPC institution, etc. The programme also supported the BHDS in effective implementation of schemes, investor profile development and other policy related initiatives.

BAGRI also facilitated private sector investments in agriculture sector across Bihar, including facilitating private investments worth £40 million having commenced commercial production.
For output 4.2, during the project tenure, 20 of the proposed reforms under BAGRI have been adopted by DoA including Agri Investment Policy, PPPIAD, Seed Production Policy, Bihar Agriculture Market Information & Intelligence System, Bihar Organic Mission, Streamlining state sponsored schemes, Agri-investment promotion policy, Agri-incubation at BAU, Jal- Jeevan – Hariyali scheme etc.
Government of Bihar Feedback:

Shri Adesh Titarmare, Director, Department of Agriculture, Govt. of Bihar and MD, BRBN

During BAGRI handover meeting on 18th June 2020, Director, DoA, GoB has expressed his deep satisfaction for the quantum and quality of work done under BAGRI towards various policy and institutional reforms and recognised efficacy of various recommendations provided including recommedations for Seed Sector and BRBN Reforms.

Under output 4.3, BAGRI interventions led to 8 of the policy and institutional reforms coming into practice (viz. implementation of eNAM, Jal Jivan Hariyali Abhiyan, III Cell, J-Farm, etc.) while some of them being at the final stages of being implemented (Bihar Organic Mission, Agri Investment Policy, PPPIAD, etc.).

For output 4.4, building on the success of the e-kiosk bhavan operationalized under said programme, BAGRI targeted operationalization one additional e-Kiosk. However, the pandemic situation due to covid-19 hindered the same and target could not be met.

For output 4.5, BAGRI interventions have facilitated two critical academic partnerships for BAU with UK Universities (Natural Resources Institute (NRI) at Greenwich University and Burnell University). The collaborations with UK Universities have been a contributing factor for BAU improving its ranking in the All India ranking of Agricultural Universities (24th in 2017 to 18th in 2019). It has also been touted as the best Agriculture University in Eastern India.

Lessons identified this year linked to this output and recommendations for future programmes

Introducing policy and governance reforms require very meticulous and diligent systems-based approach to get all concerned stakeholders in confidence. A compelling value proposition through the reform is paramount and then seeking a go-ahead from multiple levels is time taking and strategic process. Gradual trust building and keeping the wider Government system in loop helps to contain loss of institutional knowledge due to frequent transfers and avoid system delays.

BAGRI played a crucial catalytic role in conceptualizing the policy reforms and making them fact and need based for GoB and this crucial role led to the wider adoption and trust on the reforms proposed by BAGRI. Such catalytic roles are crucial for Government to innovate and thing beyond the normal.

Progress against recommendations of last Annual Review : NONE, There were no recommendations for this output in the last AR.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

Department of Agriculture, GoB supervision and support

Thematic experts

DFID’s financial and technical inputs through BAGRI project

Performance of agriculture sector in Bihar improves significantly to reflect higher private sector investment, higher production and price realisation by farmers

- Additional private sector investment in agriculture sector in Bihar
- Average increase in production/productivity of select horticulture crops in project districts
- Average increase in income of farmers for select horticulture crops in project districts
- Number of reforms implemented by GoB

Output 3: Enabling Accessibility to Clear, Reliable and Dynamic agricultural Information
- Facilitating agriculture price dissemination across programme districts
- Enabling farmers with IT enabled techniques
- Providing farmers improved soil testing and advisory services
Output 1: Enabling Formation of Farmers Producer Group / Co-operatives for Maximizing Profits to Farmers and Strengthening their Bargaining Power
- Mobilizing men and women farmers for formation of farmer collectives (PGs/FPCs)
- FPCs raise share capital internally for sustainability
- FPCs facilitated with institutional credit
Output 4: Strengthening institutional capacity, introduction of regulatory reforms and facilitating private sector investment in agribusiness in the state
- Policy and institutional reforms initiated
- Number of reforms adopted by state government
- Capacity building of Bihar’s agricultural University

Increase in agricultural growth rate between 2016-17 and 2019-20
Inputs
Outputs

Outcome
Impact
Output 2: Strengthening the Marketing Chain and Market, wherein Small / Marginal & Poor Farmers are Effective Partners
- Develop and strengthen market linkages at PG and FPC level
- Market linkage turnover facilitated by PG/FPCs

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

TA inputs through BAGRI have led to various outputs which were periodically reviewed and improved for adaptation to evolved scenarios in a way that each one of them contributed towards enhanced attainment of the project outcomes and goal.

Through multiple well designed activities in field, programme has collectivized more than 75,000 farmers including 17,000 women farmers in 3,451 primary producer groups of 20-25 farmers each thereby making these groups unit for effective dissemination of various Agri-technology and good practices. More than 5,000 trainings and 1,000 field demonstrations have been conducted over the project period which has seen participation from more than 66,000 farmers. It has also encouraged small and marginal farmers to collectivize various agricultural practices including procurement of agri-inputs and marketing of agri-produce to increase farm income encashing on economies of scale.

Furthermore, programme has also federated these producer groups in 20 Farmers Producer Companies; which are registered under Company Act 2013. With these FPCs, the programme has successfully been able to promote positioning of farmers up in the value chain. It has facilitated direct institutional linkages with agri-input companies like IFFCO, Bayers, BRBN etc. and agri-produce marketing companies like ITC, Mother Dairy and Big Basket etc. It has resulted in additional cost saving of up to 10% in agri-input and 20% enhanced realization in agri-produce marketing. With multiple innovative business models like women entrepreneurship-based processing, encouraging farmers to become seed grower from food grower etc, it has increased resilience of farmers and producer groups.

Similarly, the programme also supported Government of Bihar in policy reforms like Organic Mission, PPP-IAD and State Seed Policy etc which has led to unlocking of growth opportunities in agricultural sector across Bihar. It has provided institutional strengthening to multiple agricultural institution of Bihar like BRBN, Bihar Agricultural University and BAMETI etc. Additionally, it has actively promoted private investment ecosystem of agricultural sector and have provided active handholding support to ground more than £40m of investment in the State

The programme has contributed towards better jobs and income opportunities for more than 38,000 people and towards improvement of resilience of about 27,436 farmers. It has actively observed the state winning prestigious Krishi Karman Award twice during the tenure of the programme. Against baseline of -2.2% of sectoral annual average growth rate between 2011-12 to 2015-16 at constant 2011-12 prices, the sector during project period has observed average growth rate of 4.4%
[note] Economic Survey of Bihar 2018-19 (average for two years 2016-17 and 2017-18)

Progress at Impact and Outcome Level :

Impact Statement: Improved Growth in Agricultural Sector in Bihar
Indicators :	Target	Progress
Increase in agricultural growth rate between 2016-17 and 2019-20	At least 2 percentage point Increase in annual average growth rate of agriculture between 2016-17 to 2019-20 at constant 2011-12 prices)	Bihar has observed agricultural growth rate of 4.53% between 2014-15 and 2017-18 at constant 2011-12 prices)
Outcome statement: Performance of agriculture sector in Bihar improves significantly to reflect higher private sector investment, higher production and price realisation by farmers
Additional private sector investment in agriculture sector in Bihar	£10m over the baseline of £31m average annual investment in Food processing in Bihar	Facilitated cumulative investment of £45.5 m over project period
Average increase in production/productivity of select horticulture crops in project districts	Cumulative 8% improvement / Baseline: / Fruits : 15MT / ha / Vegetables : 16.5MT/ ha	Average Improvement in productivity of 7% / Fruits: 15 MT/Ha / Vegetables: 19.23 MT/Ha
Average increase in income of farmers for select horticulture crops in project districts	Cumulative 30% increase over the baseline of 0.87 lacs / acre / annum	As per project estimates there is 20% savings in cost of inputs due to aggregation and farmers are getting a minimum of 10% increased realization due to consolidated sales.
Number of Reforms implemented by GoB	Cumulative 5	8 policies/institutional reforms are in practice

Explain major changes to the log frame in the past year (1/2 page) – No Changes

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

Economy: Spend for the project has been £7,582,139 as against the approved budget of £10m thus providing savings of about £2.5m without any serious impact on activities on the ground. Various steps were taken to economize operations. For example, premises for the BAGRI team in Patna were given free of any charges by GoB resulting in a direct saving of minimum £40,000 each year that yielded savings of about £200,000 over project period. Similarly, programme tried to achieve better economy by using Community Resource Person to form and strengthen Produce Groups instead of district-based team. The programme has leveraged resources such as software, manpower and call centre support from TAFE (a tractor and farm equipment company) to implement J- Farms services, a key initiative from BAGRI. The economies achieved in this programme are better relative to other similar government programme. GBP spent per professional per year for BAGRI is £2,734 as compared to £3,869 for a somewhat similar programme of livelihoods in Bihar.
[note] http://sfacindia.com/UploadFile/Statistics/Farmer%20Producer%20Organizations%20Scheme.pdf page 26

Efficiency: The implementation efficiency under BAGRI is reflected in time-bound and early achievement of targets set against each milestone. As a result, BAGRI has been efficient in converting inputs into outputs and also in comparison with other comparable projects running with similar milestones. The programme has taken 14% less time to form PGs as compared to industry standards. Similarly, while comparable programmes have used more than £1,600 in establishing an FPC, BAGRI has been successful in completing the same in half the cost, without compromising on the milestone. Inputs have also led to significant policy reforms. While 35 reforms were developed, 20 of them were adopted by GoB. This exhibits considerable efficiency relative to comparable programmes. The programme has also been able to help to bring in private investment worth more than £40m in relatively less time (compared to state benchmarks as Udyog Mitra etc). GBP spent per farmer member of PGs under this programme is about £14.41 as compared to £23.17 spent under somewhat similar livelihood programme.
[note] The total efficiency gains calculated through lesser time taken for creating each Producer Group (~10%) and for federating each FPC (~25%), higher training hour per farmer (~20%), higher turnover in million GBP per PG/ FPC (~20%), higher farmers footfalls / usage facilitated through one stop shops/ models (~40%), lesser turnaround time for reform initiative, lesser turnaround time for strengthening activities and lower facilitation time per million GBP investment (~50%)

Effectiveness: Evidence suggests that interventions being executed in project districts have led to reduction of agri-input cost in overall surrounding area where BAGRI operates. Various unfair practices like charging more than market price on urea etc. have reduced. Similarly, since BAGRI Kisan Bazar waives off commission paid by farmers, other commission agents also started feeling the pressure to reduce commission charged from farmers. Convergence through research institutes have also led to increased productivity. Thus, BAGRI interventions are positively impacting lives of non-members too. The notification and grounding of many key policy reforms proposed by BAGRI have also led to making huge impacts on the Agribusiness segment of the state such as Agri-marketing, BRBN strengthening, BAU strengthening, Jal Jeevan Hariyali like programmes. The grounding and operationalization of private investment units have added to employment generation and value addition perspectives.

Equity: BAGRI has consciously worked on driving equity among various beneficiaries of the project. Not only small (18%) and marginal (71%) farmers but landless (11%) farmers have also benefited from this programme. The programme has enhanced its reach to women farmers to over 22% and has also given them voice and agency through mandatory board membership and linkages with agri-allied livelihood development initiatives (like jata sattu, mustard etc.). 84% of the member base consist of OBCs (67%) and SCs & ST (17%). Similarly, private investments have led to considerable employment generation (more than 1,000) and comprise 200 females amongst those benefited.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Key Risks (and Residual Risk Rating Post Mitigation)	Mitigation measures
Delivery: Low sustainability of FPCs after programme ends. [Major]	In current status of broader FPC ecosystem in India and specially in Bihar, it takes active handholding support for 6-8 years for FPCs to become self-sustainable. Covid-19 induced disruptions in business cycles of BAGRI FPCs have also contributed to relatively decreased sustainability of these FPCs. / GoB is aware of the programme’s timeline and the team has facilitated handover of these FPCs with Directorate of Horticulture. Additionally, the programme has taken several initiatives to document key processes that BAGRI steered, develop SoPs and transfer documentation and capabilities to the FPCs and GoB officials to mitigate the risk.
Delivery: processes of implementation of Initiated and adopted policy and institutional reforms may slow down [Major]	There is high chance that momentum developed by the programme towards implementation of initiated and adopted policy reforms may lose traction. To mitigate the risk, the team has closely engaged with key stakeholders and decision makers to effectively facilitate handover and sensitize concerned officials.
Delivery: Unprecedented Covid-19 pandemic situation and imminent closure have given less time to sensitize key stakeholders and beneficiaries resulting in a sense of disassociation and disillusionment [Major]	Team has faced challenges in completing handover activities due to restricted access specially for FPC wise handover at field level. As a result most of the activities have been undertaken remotely with the help of local team and close co-ordination. Observing government issued guidelines, team has met each stakeholder and have tried to sensitize them about project closure activities and way ahead. Team has also provided beneficiaries with necessary tools like SoP, Business Plans, Go-to-Modules, various reports documenting current statuses etc to mitigate the risk

Update on partnership principles (1/2 page)

DFID India’s Partnership Principles state that DFID India’s support is based on a shared commitment to the following four principles:
- Helping India reduce poverty and leave no one behind
- A commitment to respecting human rights and other international obligations
- A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
- A commitment to strengthening domestic accountability

BAGRI complies with DFID India’s partnership principles and where funding is channelled through partner organisations this is done in accordance with these principles. Compliance to these principles is ensured through procedures such as due diligence, financial audits and technical reviews in close collaboration with the Government of Bihar.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

The BAGRI implementation team has been sensitive and aware of the importance of adhering to timelines in terms of achieving overall deliverables and related commercial performance. The team has taken considerable effort in keeping key deliverables on track even in difficult situations like flood and recent Covid-19 related complications along with administrative challenges owed to changes in senior officials in the agriculture department during the project implementation period. The programme deliverables are well aligned to overall goal and outcome areas.  An independent mid-term review conducted in June 2019 also confirmed this. During the entire 5 years, the team has ensured that the project is well on track both in terms of technical delivery as well as budgeted spend.

The quality of financial management was good for the programme duration. The spend was as per the agreed forecast and delivery plans.  Fee of experts was agreed by Procurement and Commercial Division and project expenses were reimbursed on actual basis.

The milestone targets and actual submission period that have been agreed in various Project Steering Committee meetings chaired by the Development Commissioner, GoB.

In addition to the agreed milestone deliverables, BAGRI team has also delivered additional tasks on various policy reviews and reform recommendations on the request from the agriculture department such as Employment generation strategy for migrant labourers during CoVID, Investor meets for seeking consensus on Agribusiness investment promotion policy, Agri- infrastructure funds, Designing mandi shop allotment plans/ policy, Atmanirbhar Bihar strategy, R&D stock taking strategy in Bihar, Agri exports construct and design etc.

Date of last narrative financial report	N.A.
Date of last audited annual statement	N.A.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Monitoring
The log frame has been the basis for monitoring. The following are used as monitoring and evaluation methods to track BAGRI’s progress:
- Quarterly progress Reports with output wise information update, key achievements and challenges faced.
- Programme Steering Committee meeting held every quarter and chaired by the Development Commissioner – to assess progress, address bottlenecks and identify emerging needs/priorities.
- Regular visit by DFID task team including site visits, discussion with beneficiaries, key government counterparts and implementing partner.
- Deliverable linked payments are agreed between DFID and implementing partner at the beginning of the programme year. The Programme Steering Committee vets the same.
- The programme was also scrutinised by other officials from within and outside DFID India. This included visits by Inclusive Growth and Investment Team’s Team Lead, Senior Programme Manager and Results Adviser. An independent MTR was undertaken in December 2018 and this Annual Review Team consisted of three DFID India team members external to the programme. The goal was to gather dispassionate views about BAGRI’s progress, its strategic fit in DFID’s India partnership and looking at long term sustainability and methods of enhancing value add, going forward.

Evidence
The programme lays significant impetus on evidence guided planning and implementation. Best practices within the country are being used to design and implement the interventions. Stringent measures are put in place to establish baselines and realistic milestones are arrived at, which are tracked and monitored throughout the programme cycle. Case studies are collected periodically to understand the programme’s progress. A third-party mid-term evaluation was undertaken in December 2018 that provided benchmarks of the programme’s progress against similar other programmes and also provided recommendations for course correction.

Learning
In order to increase relevance of FPCs for farmers, its business activities should be designed by keeping member farmers at its centre and should cater to its demand be it for horticultural commodities or dry cereals. Comprehensive FPC formation and promotion programmes should be commodity neutral.

In order to increase effectiveness and sustainability of FPCs, there should be financial assistance component to support FPCs in its working capital requirements, agri-infrastructure needs and market development etc.

Forward linkage related interventions require relatively longer period of training, capacity building and hand-holding support. It remains a challenge specially in absence of agri-infrastructure setup at FPCs level

To ensure authenticity and broader trust on real-time information dissemination systems, the programme should collaborate with government agencies.

Policy and institution reform initiatives require longer gestation period and for to be sustainable, policy and institutional reforms as envisaged in the programme require continued and comprehensive technical support and handholding.

Annexure 1 List of Policy and Institutional Reforms documents developed under BAGRI programme

SN	Policy Reform Initiative	Submitted	Adopted	Implemented
1	Bihar Agricultural Marketing Development Agency (BAMDA) Bill	√
2	Investment note on warehousing and cold storages	√
3	Farm Mechanization Policy	√
4	Seed Production Promotion Policy in Bihar	√	√
5	Introducing Public Private Partnership Initiatives for Integrated Agriculture Development (PPP-IAD) schemes	√	√
6	Roadmap for introduction of PPP-IAD scheme in Bihar	√
7	Strengthening plan for Bihar Rajya Beej Nigam (BRBN)	√	√	√
8	Sectoral Scan of Farm Mechanization in Bihar	√
9	Bihar Agriculture Market Administrative system (BAMAS)	√	√
10	Farm Mechanisation & Promoting Custom Hiring services Policy	√	√
11	Strategic action plan for operationalization e-Kisan Bhawan	√	√	√
12	Action plan for Agriculture Investment Facility Desk (AIFD)	√
13	Action Plan for Strengthening BAMETI	√	√	√
14	Strengthening agriculture research capacity of the Bihar Agriculture University	√
15	Functional and Technical Requirement Specifications for Bihar Agriculture Market Information & Intelligence System (BAMIIS)	√	√
16	Operating MSTL under PPP mode	√	√	√
17	Operational guidelines for Seed Production Promotion Policy	√
18	Bihar Seeds Order on Restricting Spurious and misbranded seeds 2018	√
19	Action plan for increasing the reach of Agricultural schemes	√
20	Strategy plan for strengthening State Seed farms in Bihar	√	√
21	Roadmap for Developing Plant Protection Centres in Bihar	√
22	Report on International Capacity Building Program at BAU	√	√	√
23	Knowledge Transfer Programs (KTP) for University Industry Collaboration Initiatives- III Cell creation	√	√	√
24	Roadmap for establishment of Agricultural Implement Units	√	√
25	Streamlining State Schemes for efficient delivery and Institutional Strengthening of Agriculture Department	√	√
26	Road Map for Bihar Organic Mission	√	√
27	Action Plan for promoting Agri-exports from Bihar	√
28	Jal Jeevan Hariyali Abhiyan - Designing Agriculture Department’s component for the scheme	√	√	√
29	Strategy note on revamping institutional mechanism for agricultural marketing	√
30	Conference on potential of Ag-tech for Bihar agriculture	√	√
31	Facilitating wider implementation of “Jfarm Services”	√
32	Facilitating state level Federation of FPOs in Bihar	√
33	Workshop & capacity building programme on making BAU a leading Agri Incubation cum Innovation Centre	√	√
34	Agri Investment Promotion Policy	√	√
35	Action plan for implementation of eNAM	√	√	√

Annexure 2: List of Market Linkage Activities Facilitated by the TAST

No	Market Linkage Model Name	Type
1	Onion Market Linkage with ITC	Forward
2	Wheat Market Linkage with ITC	Forward
3	Direct Supply of Fertilizer from Manufacturer	Backward
4	Market Linkage - Papaya Value chain development in Bihar	Backward
5	Litchi Market Linkage under BAGRI Project in Collaboration with FnF	Forward
6	Input Market Linkage - BAGRI Kisan Seva Kendra (BKSK)	Backward
7	Market Linkage - BAGRI Kisan Bazar (BKB)	Forward
8	Backward Market Linkage Model involving Research Institutes	Backward
9	Market Linkage of Hand Processed Gram - Jaata Sattu	Forward
10	Backward Linkage of Hybrid Rice Seed	Backward
11	Forward Market Linkage of Paddy	Forward
12	Forward Market Linkage of Soybean	Forward
13	Market Linkage of Raw Turmeric (Mother Dairy) & Processed Turmeric (Samastipur)	Forward
14	Market Linkage Report of Seed Production and marketing by FPCs	Backward
15	Market Linkage Report of Maize	Forward
16	Market Linage Report: Wheat Collection Centers in collaboration with Arya Collateral	Forward
17	Market Linkage Report of Litchi – Big Basket	Forward
18	Market Linkage Report of Horticulture Nursery	Backward
19	Market Linkage of Potatoes with S.V. Agri Processing Pvt Ltd.	Backward
20	Market Linkage of Litchi in Collaboration with India Post and Directorate of Horticulture	Forward

Annexure 3: List of training provided to Board of Directors of FPCs

Sr. No.	Key training area
Techno Managerial Trainings
1	Statutory compliance and Record keeping
2	Financial and Accounting literacy
3	Government schemes & Institutional linkages
4	Market strategy and linkage
5	Business plan for Farmer Producer Companies
6	Agricultural Value Chain
7	IT & Computer skills
Supporting Skills Training
8.	Effective communication, Negotiations and Counselling
9.	General Leadership, Team Building and Time Management
10.	Participatory Planning and Management of the Company
11.	Governance and transparency

Annexure 4: Illustrative depiction of Backward Linkage facilitated with various organisations under BAGRI

BAGRI established multiple backward market linkage for FPCs through BKSKs and on standalone basis. A few of them are as tabulated herewith
Sl. Name of the linkage partner Type of organization / 1 Borlaug Institute for South Asia (BISA) International research institute / 2 Bihar Rajya Beej Nigam (BRBN) Govt. of Bihar corporation / 3 Krishi Vigyan Kendras Govt of India & ICAR supported / 4 Siddhivinayak Agri Processing Private Limited Private organization / 5 Indian Farmers Fertiliser Cooperative (IFFCO) Multi-state cooperative society / 6 Agrivolution Pvt Ltd. Private organization / 7 Bihar state co-operative marketing union Ltd (BISCOMAUN) State apex cooperative society / 8 Bayer Crop Sciences Multinational pharmaceutical and life sciences company / 9 Harvest plus A part of CGIAR Research Program on Agriculture

Annexure 5: Illustrative depiction of Linkage facilitated with various organisation under BAGRI

BAGRI established multiple forward market linkage for FPCs. A few of them are as tabulated herewith
Sl. Name of the linkage partner Type of organization / 1 Arya Collateral Warehousing Services (P) Ltd. Private Organization / 2 Mother Dairy Fruit & Vegetable Pvt Ltd Subsidiary of the National Dairy Development Board (NDDB) / 3 Big Basket online grocery store / 4 Harvest plus A part of CGIAR Research Program / 5 ITC Limited Indian multinational company / 6 Siddhivinayak Agri Processing Private Limited Private organization / 7 Agrivolution Pvt Ltd. Private organization / 8 Coolcrop Technologies Pvt. Ltd. Private organization / 9 Bihar Horticultural Development Society Govt of Bihar society / 10 Milk basket Mobile based goods delivery / 11 NCDEX e Markets Limited (NeML) Leading National Spot Exchange / 12 Ergos Business Solutions Private Limited. Private firm in warehousing

Annexure 6: Illustrative activities to strengthen FPC – PG Linkage

Sl.	Details of Activity taken up by FPC for Strengthening PG Linkage
1	Supplying quality agri-input in timely and competitive manner to PG members
2	Aggregating Produce of PG member farmers and facilitating market linkage
3	Involving PG members in market linkage activities (demand & produce aggregation)
4	Partnering with PG Women Entrepreneurs for Jata Sattu Manufacturing
5	Partnering with PG Women Entrepreneurs for Mustard Processing
6	Facilitating Convergence with BHDS for identified crops grown by PG farmers
7	Facilitating training and exposure visits organized by ATMA and KVKs
8	Promoting PG members to become shareholders through regular meetings