ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Teacher Effectiveness and Equitable Access for Children in Zimbabwe (TEACH)
Country or region targeted	Zimbabwe
Type of cost extension (if applicable)	No cost time extension
Original project budget	- Original Business Case value = £39,842,000 / - Increased by £15,700,000, to £55,542,000 by addendum approved in July 2023
Original project start and end dates	Original business case dates were 31 July 2019 to 31st July 2024 / No cost time extension approved in 2021 to 31 October 2025 / Further costed extension approved 2023 to 31 March 2026
Cost extension value (if applicable)	n/a
New reduced budget (if applicable)	n/a
New project end date (if applicable)	31 December 2026
Business Case Quest Document No.	https://iati.fcdo.gov.uk/iati_documents/D0002689.odt

INFORMATION
What is the project’s purpose?
The impact and outcome statements of the TEACH Programme are as follows: / Impact Statement: Contribute to a positive shift in the trajectory of learning outcomes in Zimbabwe: leaving no one behind. / Outcome Statement: Strengthened and more sustainable national education system that is improving the quality of teaching and equitable access for all. / These objectives are fully consistent with the continuing priority in UK foreign policy placed on enhancing quality of, and access to education for girls.
What is the objective of the cost extension or other changes?
This addendum seeks approval for a no-cost time extension to 31st December 2026. The purposes of which are: / To allow UNICEF an additional 9 months for the completion of a delayed second phase of school solarisation (March 2026-December 2026), while incorporating learning from the ongoing external evaluation. / To allow Think Equal an additional 3 months to complete implementation of the delayed Social and Emotional Learning component (April 2026 to June 2026. / To extend the provision of Teacher Professional Development (TPD) support provided by Education Development Trust (EDT) by 8 months (November 2025-June 2026), to deepen the impact of this high-performing component.
What is the additional and total support the UK will provide?
This is a no-cost extension, so no additional funds are requested beyond the current approved maximum project budget of £55,542,000. However, this plan will necessitate the reclassification of £1,600,000 currently designated as C-Del (Solar) to R-Del (Teacher Development).
What are the expected results?
Completion of installation of 10kva solar electricity equipment to at least 75 remote rural schools, benefitting an estimated 32,000 pupils and teachers. / Completion of delivery and evaluation of Social and Emotional Learning (SEL) training and materials to 4,350 Early Childhood Development (ECD) classrooms. / Extending the period of delivery of TPD support aimed at improving the skills of at least 75,000 educators in 42 districts and 300 inspectors nationwide.
What is the approach to implementation?
Solarisation will be delivered through a £2,400,000 (9 month) extension of the existing Contribution Agreement with UNICEF for TEACH. This will partially utilise the additional sum of £4,000,000 approved by Ministers in the cost extension addendum of 2023. This sum will be sufficient to complete solarisation of at least 75 additional schools benefitting. / Completion of SEL teacher development will be delivered through a three month no-cost extension of the existing Accountable Grant Arrangement (AGA) with Think Equal. / The extension of funding for teacher professional development support through EDT will be delivered through a new AGA with EDT. It will not be possible to extend the existing contract with EDT through the International Multi-Disciplinary Programme Framework (Lot 13) because the maximum value (£12,000,000) of funding allowable through this instrument has now already been allocated. Additional funding of £1,600,000 will therefore be provided through a new AGA with EDT, for which EDT are eligible because they are classified as a non-profit company in both UK and Zimbabwe. Funding will be provided within the existing maximum project value (full life) of £55,542,000 by the reclassification of £1,600,000 from C-DEL (Component 105) to R-DEL.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
This addendum requests only for the time extension of activities already approved as consistent with the existing Theory of Change (ToC) approved in the original business case and the reiterated in the addendum of 2023. / The approved Theory of Change can be articulated in words as follows: / If (Outputs) TEACH: (i) supports equitable access to schools for marginalised girls and boys including CWDs, (ii) Increases the capacity to teachers and administrators for quality teaching and learning, (iii) strengthens the education system and (iv) supports out-of-school adolescent girls to access basic education. And identified assumption hold - / Then (Outcome Statement) this will result in a strengthened and more sustainable national education system that is improving the quality of teaching and equitable access for all. / This will contribute to (Impact Statement) a positive shift in the trajectory of learning outcomes in Zimbabwe - leaving no one behind. / The extension will also allow scope to incorporate learning and recommendations from the Annual Review cycle and from two ongoing and planned external evaluations into the closing stages of the programme: / Evaluation of Solarisation of Schools (August-November 2024) / TEACH process and Impact Evaluation, focusing on components led by UNICEF and EDT (November 2024-March 2025).