Annual Review Template

Title: Tax Transformation Programme (TTP)
Programme Value £ (full life): £20.27m		Review date: April 2025
Programme Code: 300553	AMP start date: 8 August 2018	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	B	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300553 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300553 Documents

List of Key Acronyms

AR: Annual Review
BE: British Embassy
BC: Business Case
BPT: Business Process Transformation
CBU: Capacity Building Unit
DPO: Development Policy Operations
ETB: Ethiopian Birr
EY: Ethiopian Calendar Year
EFY: Ethiopian Fiscal Year
EU: European Union
FY: Financial Year
GoE: Government of Ethiopia
GDP: Gross Domestic Product
HMRC: Her Majesty’s Revenue and Customs
HMRC : Her Majesty’s Revenue
IMF: International Monetary Fund
ITAS: Integrated Tax Administration System
KPIs: Key Performance Indicators
LTO: Large Taxpayers Office
MTO: Medium Taxpayers Office
MoR: Ministry of Revenues
MoF: Ministry of Finance
MoF TPU: Ministry of Finance Tax Policy Unit
MTRS: Medium Term Revenue Strategy
NRET: National Revenue Enhancement Taskforce
OANDA – Online Automated Network Data Access
ODA – Overseas Development Assistance
PAF: Performance Assessment Framework
SIGTAS: Standard Integrated Government Tax Administration System
STO: Federal Small Taxpayers Office
TTP: Tax Transformation Program me
TSTP: Tax Systems Transformation Programme
TTO: Tax Transformation Office
ToC: Theory of Change
TADAT: Tax Administration Diagnostic Assessment
VFM: Value for Money
WB: World Bank

A. SUMMARY AND OVERVIEW

The Tax Transformation Programme (TTP) was established in 2018 to support reform of Ethiopia’s tax system. Initially split between two units, in the Prime Minister’s Office and Ministry of Revenue (MOR), TTP evolved to focus on MOR, with a respected group of long-term embedded advisers in the Tax Transformation Office (TTO). From 2020 TTP faced disruption from Covid, conflict and budget cuts. Growing macroeconomic crisis in Ethiopia worked against the impact objective of reversing the decline in tax to GDP. High inflation rapidly eroded the real wages of officials leading to a sharp deterioration in capacity at the MOR. This trend was particularly acute in audit and IT, as growing wage differentials with the private sector led to increasing challenges in recruitment and retention of staff.

Over time these changes, in resources and operating context, forced a refocus of the programme from transformation of the tax system to stabilization, particularly of core IT systems. This shift was quite deliberate in the past year, the first of a two-year extension secured explicitly to continue providing IT stabilization support and support preparation for a possible IMF programme. All shifts in focus were made following close consultation with the GOE via a Steering Board.

During the past year TTP has continued to enhance the stability and functionality of the MOR core IT system, SIGTAS, replacing manual processes, and fixing bugs related to automated SMS and email systems to enhance communication. TTP implemented a deduplication engine to reduce duplicate records and improve data quality in SIGTAS. This will support a key objective of making SIGTAS a ‘single source of truth’ for revenue data. Independent reviewers emphasized the importance of the embedded IT consultants to the maintenance of SIGTAS operations and prevention of system collapse. Essentially, TTP has continued to help safeguard a critical state function. Work to strengthen the system will help to ensure ongoing stability, but an exit plan for this work will developed in the next year.

On 29 July 2024, one third of the way through this reporting period, the GOE secured a USD 3.4 billion IMF programme to support macroeconomic stabilization and build the foundations for inclusive and private sector-led growth. Reversing Ethiopia’s long decline in tax revenue is a key objective of the IMF programme, with quantitative targets on revenue collection. The following day, the World Bank (WB) Board approved the first in a series of four complementary Development Policy Operations (DPOs), expected to provide a total of USD 3.7 billion. Tax reforms are also among the DPO objectives.

In August 2024 the GOE published a National Medium-Term Revenue Strategy (MTRS), prepared with UK assistance, outlining further targets and high-level reform objectives. A National Revenue Enhancement Taskforce (NRET) was subsequently formed, chaired by the Prime Minister’s Office, emphasising political commitment to revenue collection and reform. Ethiopia’s Prime Minister has commented that the macroeconomic reform process is “revenue led”. Despite this high-level attention, capacity within the MOR remains limited and TTP advisers are closely involved in a technical level taskforce reporting to the NRET.

While weathering these extraordinary shocks, TTP has maintained excellent relationships with policymakers and officials. Long term embedded advisers, supported by TTP since 2019, are highly trusted by Ministers and senior officials in the Prime Minister’s Office, MOR and MOF, as well as among development partners including the WB and IMF. Consequently, the programme has been well placed to respond quickly and flexibly to increased demands over the last year. Independent evaluators noted that “the programme has demonstrated significant positive developments…strengthening its team [and] incorporating international consultants to enhance implementation efforts”.

Changes of personnel within the MOR were judged by our independent evaluators to have “introduced a new cadre of personnel across several departments with an improved understanding of tax administration...and increased commitment to strengthening tax administration”. The evaluators also judge that there are both opportunities and risks from the increased political commitment to revenue reform. The supplier, Cowater, agree, noting a step-change in interest among senior officials. A recent training session provided by HMRC had five times as many participants as anticipated. The Prime Minsters Office has directly requested that the UK support continue to the end of the IMF programme, and Minsters in MOF and MOR have endorsed a new prioritized workplan for TTP.

Significant risks stem from the pressure on revenue targets. These could create incentives among tax collectors to maintain informality and arbitrariness, because this allows them to adjust assessments to meet targets. Such behaviour, widely reported by businesses, poses a significant threat to the investment climate – an issue FCDO should attempt to mitigate in support of wider objectives.

During the last year, increased funding for TTP facilitated an expansion of activities intended to help the MOR to prioritise reform activities. This included utilizing short-term international experts to complete light touch diagnostics in key areas such as taxpayer registration, filing, audit and debt management. Major weaknesses and targeted inventions identified in these diagnostics has informed a reform strategy at the MOR. Third parties, including the independent evaluators, have highlighted the quality of these reports. Collaboration with the Tax Filing Directorate has led to more focused efforts to identify non-filers, manage amended returns more effectively and enhance SIGTAS functions to support these tasks. Alongside these efforts TTP has developed comprehensive manuals (including an Officer’s Manual, Trader Manual and Inspection Manual) to provide clear guidance for both officers and licensed traders, outlining responsibilities and adherence to regulatory requirements.

As reported in our last annual review, the extension period for TTP was intended to i) deepen impact ii) allow the UK to play a convening role in tax support iii) pivot our support towards transparent taxation of large taxpayers – including international investors - and consider the impact of reforms on vulnerable groups. It has been 8 months since the IMF deal was secured during which important progress has been made on these objectives. Obtaining an IMF deal was far from certain when the extension was approved. While revenue targets were a predictable part of such a deal, the consequent level of commitment from the GOE was also uncertain. TTP is well placed to capitalize on the opportunities from the political commitment that has emerged, and to mitigate the risks.

Summary supporting narrative for the overall score in this review

TTP has performed well in the past year, meeting expectations.

Partners interviewed for the independent review, including from MOR, the World Bank and IMF, continue to report that the TTP provides critical support, that is complementary to their programme. TTP IT advisers help ensure continued operation of the MOR IT infrastructure. While this may raise concerns about sustainability, the challenging environment, with fundamental issues in recruitment and retention of staff, limit alternative strategies. Resolution of this issue rests in a wider process of civil service and governance reform that will take time. In this context, supporting the MOR core functions is a valuable objective. The reform programme the GOE embarked on in July 2024 provides a route to sustainability. The key issue for the next year of TTP, scheduled to be the last, is how best to support the GOE to succeed in the domestic revenue components of the IMF and WB programmes, while preparing to hand over as much of the capabilities as possible.

During the reporting year, independent evaluators report a strong performance by the suppliers. They have worked quickly to enhance the services provided to the MOR. A new workplan has been developed with prioritised activities. International experts were recruited to complete light touch diagnostics in key areas, identifying key weaknesses and targeted interventions. Responding to a request from the Minister of Revenue, an international expert has been secured to provide strategic advice, helping to refine, sequence and prioritise reform efforts, capturing them in an adaptive workplan. Recommendations from the independent reviewers have been captured under the relevant outputs.

Overall, outputs met expectations which led to the overall score of “A” for this Annual Review. TTP has developed of a clear workplan, with robust priorities. A revised logframe, key recommendation of the last annual review – has better captured critical activities and made explicit the pivot to IT stabilisation.

	Output	Score	Weighting %
1	SIGTAS system is enhanced, and data quality is strengthened	A	50
2	An improved robust and high-functioning Tax administration system	A	30
3	Strengthened tax policy analysis and legislative drafting capacity in the Ministry of Finance	B	10
4	Programme is managed effectively and plays a central role in supporting donor coordination on tax.	A	10

Key Achievements

Independent evaluators note that significant progress has been made towards stabilizing SIGTAS and efforts to progress data cleansing and matching are underway, moving towards the goal of SIGTAS as a ‘single source of truth’. The evaluators also noted that “FCDO have engaged deeply with the State Minister, tax advisors, and task force members, effectively advancing the stabilization and administrative reform agenda”. The Cowater team has engaged a senior international expert to provide strategic advisory support to the Minister and senior officials within MoR—a crucial step in ensuring political commitment and ownership.

Diagnostics in key areas including as taxpayer registration, filing, audit, communication, and debt management. Collaboration with the Tax Filing Directorate has led to more focused efforts to identify non-filers, manage amended returns more effectively, and enhance SIGTAS functionalities to better support these tasks.

Major lessons and recommendations for the year ahead
The path forward acknowledges Ethiopia’s unique political economy. Tax administration cannot be divorced from broader governance challenges. The suppliers have completed a political economy analysis in the last year to inform activities. Reforms must balance technical precision with pragmatic realism, prioritizing quick wins (e.g., digitizing arrears tracking) while embedding longer-term cultural shifts, such as fostering a compliance-centric ethos. Recognizing the limited resources for the programme and in the MOR, in the context of stretching short-term revenue targets, the programme should encourage incremental changes and pilots in parts of the system.
During the next year we need to resolve the future of the programme. Approval of the IMF programme – unexpected and uncertain until the last moment - and the GOE Medium Term Revenue Strategy has significantly changed the context. Commitment to reform has increased and there is an opportunity to support transformation. But there is only one year remaining. Increasing revenue collection is critical to rebuild public finances in Ethiopia. Excess focus on short-term revenue targets risks deterring investment with impacts on both FDI inflows and the real economy – undermining the revenues available in future years. A National Revenue Enhancement Taskforce (NRET) has been established under the Prime Minister’s Office, illustrating high level political interest. TTP advisers are well known to and trusted by the members of the NRET. Consequently, the programme is well placed to support efforts underway as part of the MDTF and IMF programme, which expire in June 2028. This would require an extension. Alternatively, during the next six months we must finalize an exit plan, particularly with respect to the support on IT. Either option should be completed in coordination other donors through the forum TTP has started.
Recommendations
Continue deep engagement with senior GOE leaders to champion administrative reforms and ensure alignment across all relevant ministries. Encourage a focus on strengthening processes and systems rather than solely on achieving revenue targets. (ongoing)
Continue to encourage incremental change to avoid overwhelming limited capacity in MOR. Smaller, sequenced initiatives should include refining the registration, focusing on communication and taxpayer guidance, building audit capacity, data cleansing and automating arrears management. Build this into a strategic plan. (Target Q1)
Encourage human resource management reform at the MOR – using the existing staff, skills and equipment more effectively – including through greater experimentation and piloting of approaches. Encourage bottom-up feedback on reform efforts, adaptation of reforms, and partnerships with academic and other tax experts. Build both into strategic plan. (Target for plan Q1)
Continue to engage in donor coordination, seeking a unified donor strategy aligned with the MTRS. This will avoid duplication, assist resource optimization and support a sustainable exit. (Target Q1 for next donor meeting)
Work to build trust through greater operational transparency, via supporting a well-functioning website, publishing clear procedural manuals, audit criteria, taxpayer guidance notes, and taxpayer rights.
Concentrate reform efforts on the Large Taxpayers Office to maximize impact within current organizational capabilities. This approach would enhance operational efficiency while simultaneously minimizing systemic risk during the implementation of comprehensive reforms. The LTO represents an optimal controlled environment for testing critical procedural and technological changes before proceeding with nationwide implementation. The LTO offers the greatest return on investment, given it contributes approximately 70% of federal tax revenue. Reducing discretionary enforcement in the LTO and increasing transparency and predictability will also improve the investment climate, supporting wider macroeconomic reform objectives.
As of March 2025, Ethiopia is experiencing negative shocks to the overseas development assistance (ODA) it receives, with uncertain impacts on the financial for its external transactions and the fiscal budget. For the foreseeable future these receipts are expected to be materially lower than in the recent past. Needs remain elevated. / Sustainably increasing domestic revenue, while protecting and improving the environment for investors, is even more critical in this environment. The TTP, and UK, is well placed to support. Embedded advisers under TTP have built long standing and trusted relationships with key decision makers. / In the next year we must think very carefully about how to respond to this increased need, opportunity and risk.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The TTP Theory of Change (ToC) describes a process where the provision of technical assistance to the MoR and MoF in key areas (including improvements to tax legislation, IT systems, and business processes) combined with analytical support from a centrally managed programme on tax policy analysis, and peer-peer support from HMRC, notably in risk assessment, data analysis and compliance, leads to improvements in tax outcomes. These outcomes include a more equitable and business friendly tax environment while, at the impact level, an improvement in revenue collection. This TOC remains unchanged. Broad outlines of the activities remain unchanged. From the outset the programme was intended to be adaptive, changing activities depending on needs, opportunities and conditions. In early stages of the programme the deteriorating macroeconomic conditions in Ethiopia meant revenues declined. But impacts should be measured against a counterfactual: would the impact have been worse without the programmes activities. The evidence we have gathered through several annual reviews is a resounding yes.

As reported last year, the deteriorating context and reduced programme resources, means that the originally defined outcome and impact indicators are no longer suitable. It is clear, for example, after the extraordinary deterioration of macroeconomic conditions that tax will not increase as a share of GDP (the original indicator). As described in part A, TTP effectively became a stabilisation programme, preventing a severe breakdown of the system. But this is a critical objective in Ethiopia. The programme is now well placed to support successful completion of the IMF and WB programmes, but would need another extension to realise this opportunity. TTP’s independent reviewers and other development partners, including the WB and IMF, agree.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to meet expected outcomes and impact. The revised logframe better suits the current operating context, following a turbulent period after inception.

The major economic reforms, launched in July 2024 and supported by the IMF and WB, have dramatically increased political commitment to revenue reforms. This is being felt through the MOR and MOF, presenting opportunities to drive impact. But a focus on short-term targets risks undermining these efforts, the investment climate and the revenue base in future years.

TTP advisers and external experts have played a crucial role in the past year, working to exploit the opportunities and mitigate risks. GOE have requested this support to continue throughout their 4-year Medium Term Revenue Strategy. All high level objectives for 2024/25 set out in last years annual review have been achieved.

In the year ahead the programme will:

- Assist development of a strategic reform plan for the MOR, working with the Ministers and an international expert (already hired)
- Determine whether to continue, via a request for an extension, to support delivery of the IMF programme or whether to exit.
- If we exit, establish a robust exit plan, handing over analytical materials to the GOE and other partners.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The TTP has adapted to changing circumstances to deliver with good value for money. Many outcome level indicators remain on track. The recognition of the shift to a stabilisation programme has improved understanding of what TTP does, even as events (the commitment to a macroeconomic reform programme supported by the IMF and WB) have presented the best opportunity for revenue reforms since the outbreak of Covid 5 years ago. TTP has adapted to this opportunity, drawing on the deep and trusted relationships that have been developed between embedded advisers and key policy makers to introduce new ideas from external experts, challenging conventional understanding. Ideally this support would remain throughout the Medium-Term Revenue Strategy (2024 – 2028), working with the grain of this opportunity to advance reforms while mitigating the risk from a focus on short term targets.

Impact: GoE can self-finance its development through increased, sustainable revenue collection

Indicator 1.1: Tax revenue collected by the Federal Government
Ethiopia’s tax-to-GDP declined steadily from 2014 and revenue collection declined in real terms during the high inflation of recent years. Due to this the original indicator of tax:GDP was overtaken by context. During the logframe review we dropped it in favour of a revenue collection indicator. When it became clear a Medium-Term Revenue Strategy was in preparation, this was designated as data source for targets.
Drawing on this, the milestone for 31 March 2025 is ETB 347 billion. The GOE have over performed on revenue collection, buoyed by a sharp increase following the ER reform. By the end of October 2024 actual collection amounted to ETB 444 billion – and the first real terms increase in years.

Outcome 1: Improved Voluntary Compliance

Outcome Indicator 1.1: No. of active taxpayers as % of total number in the register
This indicator stabilised at a very high target percentage such that continued progress was not a priority. Consequently, this indicator is not being reported during the extended period.
Outcome Indicator 1.2: % of tax collected from filings/returns to total domestic tax revenues
84.7% has been reported by TTO using SIGTAS data against a target of 84%. This is on track. But there are concerns about future years. Businesses and accountants report that in many cases tax auditors are imposing arbitrary tax demands to meet top-down revenue collection targets. Companies must then pay deposits of 25% - 50% before negotiation or arbitration. This amount is taken as an advance payment, which might inflate the total tax collection. The intense focus on revenue collection is building the amount of advance tax that taxpayers can offset against future liabilities, which may create problems for later years. Depending on how it is addressed, this distortion could impact the numerator or denominator, or both, of the calculation of the % from filing. We will carefully review this target in the coming year.

Outcome Indicator 1.3: % of Large Tax Office taxpayers with improved perception of the tax system, indicating equitability and fairness

[Unable to conclude due to lack of timely baseline] We intended a baseline survey for this new indicator to be completed by the end of July 2024. Negotiations with the IMF and WB, leading to board approvals for programmes in the 29 and 30 July prevented this from happening. Only one survey was conducted. This surveyed 730 taxpayers across three tax offices (Large, Medium and Small taxpayers). The findings show a partially favourable view of the MOR.

Only 30 large taxpayers were contacted out of the total. Of these LTO respondents, 80% reported receiving tax information from MoR revenue officers, and 47% report the tax administration processes to be transparent. 46% report spending more than an hour paying taxes, partly due to the complexity of their affairs and partly due to frequent system downtime (highlighting the importance of our support to IT stabilisation). 93% of respondents would like more information / training on how to complete tax forms – something the TTP prepared Manuals should begin to address.

These survey results will provide a baseline, and point to areas for intervention.
Recommendations
Improve the design of the survey to increase the coverage of large taxpayers.

        Outcome Indicator 1.4: % of tax revenue paid on time (Disaggregated by VAT and CIT)
On Track. Target VAT 80%, CIT 55%. Result: VAT 77%, CIT 51%. While these results are marginally below the target, we judge the margin to be small.
The independent evaluators report that during the period 2023-08 to 2024-07 72.35% of the CIT returns, 74.37% of the Excise returns, 82.42% of the VAT and 52.01% of PAYE returns were filed on time out of the data provided. Reducing the gap between filing returns and paying on time is a key objective.
There are risks about data sources: the independent evaluators report that there remain at least 4 sets of revenue data: a) SIGTAS, b) revenue tabulation through phone call, c) and National Bank data, d) personal data sets kept at the officer level. Differences between the SIGTAS and National Bank data are not consistent and can be significant. This is a major problem and highlights the importance of the work TTP is doing to cleanse the data in SIGTAS to aid the objective of making it a ‘single source of truth’.
Outcome 2: A tax environment that encourages business

Outcome indicator 2.1: % of taxpayers using e-filing for VAT and Corporate Income Tax disaggregated by: Large/Medium/Federal Small Tax Office in Addis Ababa

Baseline	Milestone	Achieved
VAT	VAT	VAT
LTO: 99.6%	LTO: 99.6% (maintained)	LTO: 99.6%
MTO: 99.9%	MTO: 99.9% (maintained)	MTO: 99.9%
STO: 92.8%	STO: 95%	STO: 92.8%
CIT	CIT	CIT
LTO: 96.7%	LTO: 97% (maintained)	LTO: 97%
MTO: 94.3%	MTO: 95%	MTO: 94.3%
STO: 51.5%	STO: 60%	STO: 51.5%

On track. Significant progress was made on e-filing in previous years and achievement is high. Further improvement is either highly unlikely or will take disproportionate effort relative to the available benefits. Accordingly, the objective here is maintenance of the high rates of e-filing in the large and medium tax offices, which are responsible for the majority or revenue, and if possible, incremental improvements in the small taxpayer office. Maintenance has been achieved.

Independent evaluators note that the most significant challenge across all tax segments is frequent system downtime, which affects all Large taxpayers surveyed, 96% of Medium taxpayers, and 92% of Small taxpayers. Other key issues include disabled fields preventing taxpayers from completing transactions (affecting 32% of Large taxpayers), inability to view or download tax statements (affecting 34% of Small taxpayers), and system miscalculations of taxes and penalties, though this is the least reported issue.

Given the scope and challenge of economic reform since July 2024, we are content that the high level of e-filing is being maintained.

Outcome 2.2: The time taxpayers take to file taxes

[Unable to conclude due to lack of timely baseline] During the logframe revision we agreed that this indicator would be informed by a taxpayer survey conducted by July 2024. However, as before, the intensity of discussions with the IMF and WB in the run up to approval of their programmes on 30 July meant this could not be conducted. Consequently, no baseline or milestone was defined.

We will look to establish a baseline in the next year to inform GOE reform efforts.

Outcome 2.3: The time taxpayers take to pay taxes

[Unable to conclude due to lack of timely baseline] During the logframe revision we agreed that this indicator would be informed by a taxpayer survey conducted by July 2024. However, as before, the intensity of discussions with the IMF and WB in the run up to approval of their programmes on 29 and 30 July meant this could not be conducted. Consequently, no baseline or milestone was defined.

We will look to establish a baseline in the next year to inform GOE reform efforts.

Recommendations:

- The TTO must continue to support the MOR to improve the experience of the e-filing and e- payment systems, maintaining the high levels of use and (with lower importance) incrementally improving them
- Improve the taxpayer survey in future rounds: i) better sampling and stratification of respondents, ii) standardisation of wording and questions for easy comparison, iii) greater granularity, particularly for the LTOs, iv) greater frequency (biannual?)
- Surveying taxpayers is a new thing for the GOE, and the first step was unlikely to be perfect. TTP should work with MOR and MOF to demonstrate the benefits of taxpayer surveys.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

TTP is now entering the final year. However, there is a clear need for this support to continue. As described, TTP continues to play a critically important role in stabilising SIGTAS and mitigating against a collapse of this central IT system. Independent reviewers credit the programme with achieving incremental improvements to both tax administration and law. The programme is well regarded by the MOR, MOF, the Prime Minister’s Office and other development stakeholders such as the WB and IMF.

Economic reform programmes from the IMF and the WB, approved in July 2024, have dramatically changed the incentives around tax reform bringing new opportunity and risk. As set out in the summary, once again the operating context changed significantly. Increased political interest and financial incentives from the IMF and WB programmes have created new opportunities to make progress on transformative reforms. While other partners are becoming engaged in the revenue space, none can replace the trusted relationships held by our embedded advisers. There are several reasons for this, including internal constraints on the types of support provided. We are observing growth in fly-in-fly out technical support and finance for new equipment and systems. It is critical the GOE have the capacity to coordinate this support around a prioritised reform plan, that adapts to events as time progresses. This requires trusted embedded advisers, which in turn takes time. TTP is therefore complementary.

There is also a clear need for the programme to continue in the context of FCDO’s wider portfolio in Ethiopia and the UK growth Mission. Support to domestic revenue mobilisation while considering the investment climate, is critical for the macroeconomic reforms, reduce reliance on ODA and improve opportunities for trade and investment. Tax policy and administration are a key concern among existing and potential investors.

C. DETAILED OUTPUT SCORING

Output Title	SIGTAS system is enhanced, and data quality is strengthened
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since the last AR?	Yes
Indicator			Milestone	Progress
1.1 Number of BPT SoPs developed, agreed and implemented for enhanced SIGTAS functionalities.			2	2
1.2 Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during the period.			70%	77%
1.3 Number of improved SIGTAS reports: / i) # reports produced and used in practice / ii) reports improved.			i) 2 new types of reports produced and used / ii) N/A	i) 45 new types of reports produced / ii) 20 reports used
1.4 Improved capacity of Ministry of Revenues IT Officers measured by: / i) Number of staff trained (disaggregated by gender). / ii) % satisfied with training. / iii) Average % improvement in pre-post test			i) 28-33 IT Officers trained / ii) 95% / iii) 15%	i) 30 IT officers, / ii) 100%, / iii) Not carried out

Source: SIGTAS data

Briefly describe the output’s activities and provide a supporting narrative for the score.

Indicator 1.1 Number of Business Process Transformation (BPT) Standard Operating Procedures (SOPs) developed, agreed and implemented for enhanced SIGTAS functionalities.

This indicator moderately did not meet expectation. The indicator measures both the development of new SOPs and the implementation of them, which aim at enhancing SIGTAS reporting and functionalities. It measures the improved system efficiency and logically also the data quality. The BPT SoPs were developed but not implemented. The implementation is delayed by the SIGTAS enhancements which rests with the Data/IT team owing to the increased demand for their services across the project.

Indicator 1.2 Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during the period.

This indicator moderately exceeded expectation. The indicator measures the resolution rate of critical issues within SIGTAS, with the objective of measuring the reductions in downtimes and operational disruptions. It also measures any increases in system reliability/improvements in usability. Data for this indicator is collected using information from the data centre on issues logged/resolved.

Indicator 1.3 Number of improved SIGTAS reports:

This indicator substantially exceeded expectation. The indicator measures the production and utilisation of enhanced reports generated by SIGTAS, to measure any increases in the practical use of system-generated reports which provide actionable insights and data for decision making within MoR. Data on the number and type of reports can be generated from SIGTAS, while information around their usage and improvements can be gathered from surveys.

During the revision of logframe, the programme team committed itself to 2 new types of SIGTAS reports produced and used. The improvement is planned for 2025/26 and is not applicable for 2024/25. Those targets were determined based on historical trends from SIGTAS data and were validated by the longstanding IT Consultants who have attempted to train MoR officers on SIGTAS usage over the past few years. The terminology of the output was also specifically designed to measure the uptake of these reports (‘use’) as what had been seen previously was that MoR officers creating new reports, but not actively using them.

The disparity between the targets and reported/achieved is due to an unanticipated (and unprecedented) uptake in the use of SIGTAS reporting by MoR staff. In particular, the Filing Directorate, under huge pressure from senior leadership and the revenue enhancement taskforce, have ordered staff to use these reports as a means of identifying potential revenue sources (e.g. non-filers). The TTP IT team and leadership had expected there to be a significant challenge in training officers to create, use and improve these reports, however owing to a change in the approach and demand from the GoE, these figures have been significantly surpassed.

Indicator 1.4 Improved capacity of Ministry of Revenues IT Officers

This indicator has met expectation. The indicator measures 3 core tenets of capacity building efforts: 1). The number of staff trained within the IT space of MoR; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall, this measures the enhancement of technical skills and knowledge of IT staff. Out of the total 30 trained, 8 were women (27%).

The pre and post tests were not carried out due to reluctance of the attendees. This was flagged during the Steering Committee where the State Minister of MoR has committed to discuss with her staff and take corrective measures for the future trainings.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output following revision of the logframe during the last quarter of 2024. It is not expected to change for 2025/26 but some indicators like indicator 1.3 will need to be discussed and revised. As one of the core elements of the TTP, this output requires continued focus, and we will further scrutinise the need for its continuity during the final year of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Revision to the logframe was made following the recommendation of the previous AR.

Lessons learned
- Staff are often pulled away for operational needs on a frequent basis. However, over the past year, there has been an increase in the number of tickets resolved, showing significant improvement (mainly due to the high priority of SIGTAS for the leadership).

- The big change in the number of reports produced and used against the target shows how leadership’s commitment and focus on an issue can make a real difference.

- The independent reviewers observed that although training target has been achieved, the knowledge transfer within IT Directorate does not seem to have made progress and MoR remained dependent on the TTP consultants.

Recommendations
- The data in SIGTAS needs to be cleansed (both Registration and Financial information) - that is, finding and removing errors, inconsistencies, duplications, and missing entries.

- More number of practical or on the work trainings need to be conducted ensuring that the MoR equipped and carry out the SIGTAS stabilisation. Regular pre-post assessment and refresher training is necessary.

- The e- training modules need to be introduced to be more cost effective and sustainable.

- Some milestones for this output will need to be reviewed and revised given the shifts in political commitment to revenue reforms following the GOE commitment to an IMF programme in July 2024, publication of a Medium-Term Revenue Strategy in August 2024 and creation of a National Revenue Enhancement Taskforce to ensure delivery. For example, milestone 1.3 was planned to be 2 while the progress indicated as 45, indicates a higher level of achievement is possible with the leadership’s enhanced commitment. The programme team will need to discuss with the MoR and consider revising the indicator.

Output Title	An improved robust and high-functioning Tax administration system
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since the last AR?	Yes

Indicator	Milestone	Progress
2.1 Number of LTO audit cases started/completed with audit expert support.	2	2
2.2 Number of tax forms simplified and rationalised.	2	2
2.3 Improved capacity of Large Taxpayer Office auditors measured by: / i) Number of staff trained (disaggregated by gender): / ii) % satisfied with training. / iii) Average % improvement in pre-post-test.	i) 20-25 Trained / ii) 95% / iii) 15%	i) 11 / ii) 100% / iii) 0

Briefly describe the output’s activities and provide a supporting narrative for the score.

Indicator 2.1 Number of LTO audit cases started/completed with audit expert support

This indicator has met expectations. The indicator measures the number of audits in which TTP experts have supported the process within the Large Taxpayer Office (LTO). The logic is that the presence of the expert will enhance the quality, and ultimately the efficiency of the audit process, which has an impact on the overall functionality of the tax administration and the perception of taxpayers who may experience more efficient audit activities. The indicator has been disaggregated by started/completed to take account of the time often taken to complete an audit process. The two audits completed with the audit expert support are i) manufacturing sector, and ii) the manufacturing sector with Excise.

Indicator 2.2 Number of tax forms simplified and rationalised

This indicator has met expectations. The indicator measures the efforts to simplify and streamline tax forms, which ultimately seeks to measure the improved usability of the forms which should have an impact on compliance rates through reducing the administrative burden for taxpayers. The simplified and rationalised were forms for Excise and Tax Expenditure.

Indicator 2.3 Improved capacity of Large Taxpayer Office auditors

This indicator moderately did not meet expectation. The indicator measures 3 core tenets of capacity building efforts: 1). The number of staff trained within the audit department of MoR; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall, this measures the enhancement of technical skills and knowledge of auditors. Out of the 11 total trained, 2 were women (18%).

Describe any changes to this output during the past year, and any planned changes as a result of this review:

This is a new output following revision of the logframe during the last quarter of 2024 and not expected to be changed in 2025/26. As one of the core elements of the TTP, this output requires continued focus, and we will further scrutinise the need for its continuity during the final year of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead]:

This output was added recently following the recommendation of the previous AR.

Recommendations
- Effectiveness of the audit manual. It was reported that the manual was prepared and approved in 2021 but there is no evidence that the manual is used effectively. The independent reviewers recommended a review and effective use of the manual.

- Computerised audit training. The reviewers recommended for the Large Tax Office to prioritise computerised audit training and the need for skills upgrade continually.

Output Title	Strengthened tax policy analysis and legislative drafting capacity in the Ministry of Finance
Output number:		3	Output Score:	B
Impact weighting (%):		10	Weighting revised since the last AR?	Yes

Indicator	Milestone	Progress
3.1 Number of pieces of tax policy analysis delivered and accepted by counterparts.	2	2
3.2 Improved capacity of Ministry of Finance tax policy officers measured by: / i) Number of staff trained (disaggregated by gender). / ii) % satisfied with training. / iii) Average % improvement in pre-post-test.	i) 2-4 tax policy officers trained / ii) 95% / iii) 15%	No progress
3.3 Improved capacity of Ministry of Finance legislative drafters measured by: / i) Number of staff trained (disaggregated by gender). / ii) % satisfied with training. / iii) Average % improvement in pre-post-test.	i) 55-65 legislative drafters trained / ii) 95% / iii) 15%	i) 45 legislative drafters trained / ii) 100% satisfaction / iii) Not measured.

Briefly describe the output’s activities and provide a supporting narrative for the score.

Indicator 3.1 Number of pieces of tax policy analysis delivered and accepted by counterparts

This indicator has met expectations. The indicator measures the production, delivery and acceptance (marked by approval of the Ministry) of tax policy analyses and recommendations made by TTP experts. Pieces of tax policy analysis includes TTP's evaluation of previous policies, as well as responses to ad hoc demands from MoF to analyse new/proposed policies. The indicator seeks to ensure that TTP is providing robust, and useful tax policy advice to MoF to inform evidence-based decision making. The policy analysis delivered and accepted by counterparts are i) Income tax, and ii) Presumptive tax.

Indicator 3.2 Improved capacity of Ministry of Finance tax policy officers

This indicator substantially did not meet expectation. The indicator was designed to measure core elements of capacity building to the Tax Policy Directorate of the MoF. Owing to the poorly staffed and limited capacity within the Tax Policy Directorate, it has not been possible to identify and begin work with any specific tax policy officers to improve their skills development. The number of tax policy staff existing with the MoF Tax Policy Directorate was insufficient for the level of mandate they have. When the logframe was revised in December 2024, the Ministry was planning to recruit more staff and release some of them for the training planned by the programme. However, the recruitment did not go ahead. The ministry also was not able to release the existing few staff for the training due to work pressure.

Indicator 3.3 Improved capacity of the Ministry of Finance legislative drafters

This indicator moderately did not meet expectatio. The indicator measures the enhancement of technical skills and knowledge of the staff. Out of the total target of 55-65, the number of staff trained were 45. Out of the total 45 trained, 17 were women (38%). The programme was ready to provide training to a greater number of people, but the MoF was not able to make trainees available due to staff shortage.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Like others, this output was added following the recent review of the logframe in late 2024, in response to the last year AR recommendatoins. The programme team will need to review and revise the output if the MoF is unable to help deliver this output going forward due to pressure on their staff.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Lessons learned
- The Directorate of Tax Policy within the MoF is poorly staffed and has been the major reason for limited progress with the output.

- The independent reviewers observed that the coordination and integration between the MoF and MoR were areas calling for improvement. Tax laws, directives, interpretation of changes and practical applications must be participatory and easily owned and understood by the relevant staff of both institutions.

Recommendations
- The size of the Tax Policy staff is incompatible with the level of analysis required for a country the size of Ethiopia. The MoF should be able to recruit and deploy more qualified staff. If the Ministry is unable to do this, the programme team will need to revise the output and plan for more realistic and achievable target.

- MoF and MoR should publish not only the law and proclamations, but also explanatory guidance and views on how the legislation should apply to both generic and specific cases. MoR needs to publish tax notes illustrated with specific examples. The programme must be able to provide advice.

- Both MoF and MoR should publish information in a way easily accessible on their websites and must be up to date to keep taxpayers and other interested stakeholders well informed.

Output Title	Programme is managed effectively and plays a central role in supporting donor coordination on tax.
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since the last AR?	Yes.

Indicator	Milestone	Progress
4.1 % progress of planned initiatives / Green - on track / Yellow - delayed / Red - not on track	Green: 85% / Yellow: 10% / Red: 5%	Green: 94.7% / Yellow: 5.3% / Red: 0%
4.2 Effective donor coordination, measured by: / a) Quarterly sharing of information / b) Number of meetings convened.	a) 2 reports shared / b) 2 meetings held in the year	a) 1 report shared / b) 1 meeting held in the year
4.3 Workplan Agreed	Yes	Yes
4.4 Number of minuted Steering Co meetings held annually (minimum 2)	2	2

Briefly describe the output’s activities and provide a supporting narrative for the score.
Indicator 4.1 % progress of planned initiatives
This indicator has exceeded expectations. The indicator monitors the progress of the programme initiatives by categorising them as either on track, delayed, or not on track. The objective of this indicator is to flag the extent of any issues in implementation, and to keep planned programme activities on track. Most of the KPIs have been achieved. The quality of reports was much better than the previous years. The programme had also proper workplan with timelines and prioritisation.

Indicator 4.2 Effective donor coordination
This indicator has met expectations partially. The indicator measures the effectiveness of donor coordination. More coordination and meetings are considered important particularly during this period when Ethiopia has embarked on major macroeconomic reform. Though a second donor coordination was not scheduled, the TTP has emerged as a key point of contact for all donors looking to work on revenue. Coordination such as this is an area of weakness for the MOR, owing to serious capacity gaps and intense pressure following the commitment to macroeconomic reforms that include stretching targets on revenue collection.
Indicator 4.3 Workplan Agreed
This indicator has met expectations. The indicator measures whether the programme workplan has been agreed with counterparts and FCDO. The 2025/26 draft work plan was submitted by the programme team to the GoE and FCDO. The work plan was also discussed at the Steering committee meeting held on 26 February 2025. The implementation work plan has been approved during the validation workshop held in the first week of April 2025. The Cowater and TTO team will share the minutes of the workshop.

Indicator 4.4 Number of minuted SteerCo meetings held annually
This indicator has met expectations. The indicator monitors the oversight and governance of the programme, as measured by the number of steering committee meetings held each year. These Steering Committee meetings were important to discuss and agree the priorities for and scope of the programme support.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output added during the logframe revision in late 2024, following the recommendation of the previous AR. There is no plan to change this output.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Recommendations:
- Given the current context of changing aid environment and the programme’s final year, it is important for the programme team to prepare exit/handover strategy to ensure sustainability and or avoid erosion of the progress made to date.
- It is also important to put more effort on donor coordination to ensure sustainability of the MoR operations. The programme team needs to work closely with the World Bank, EU and Gates Foundation so that they will build on what the MoR has achieved with the support of UK aid; this is important particularly if UK’s support to tax programme ends after March 2026.
- It is important to engage periodically with the newly established National Revenue Enhancement Taskforce, led by the Prime Minister’s Office, which is the steering body looking at revenue mobilisation.
- The agreement of the workplan should be documented and saved for reference. The programme dashboard

D: VALUE FOR MONEY

We consider the Tax Transformation Programme (TTP) to represent value for money.

The VFM could be strengthened or weakened at several stages including at economy (for example at recruitment of staff, setting fee rates and expenses, cost of training), efficiency (for example delivering good quality assignment or delivering in time), effectiveness (for example delivering the desired result, delivering to the customer satisfaction), or equity (for example fairly impacting social groups like gender disaggregation). The programme has been a key SIGTAS stabilisation for the MoR without which the entire system collapse would have been possible. GoE officials on a couple of occasions said that the TTP contracted staff were instrumental to saving the core IT system from collapse, as well as driving the tax policy reform.
[note] One of the advisers to the Prime Minister, who is in charge of revenue mobilisation taskforce, mentioned some TTP advisers by name whose role were critical for stabilising SIGTAS and driving policy reform.

During the year, the programme was streamlined sustaining only a small team of embedded advisers in the MOR and MOF while ending contracts of long-term technical and administrative staff operating from distance, resulting in more cost reductions.

Key costs and cost drivers

The biggest cost has remained advisory fee with a share of 77% for the year. This is a reduction from the previous years of about 95%.

Economy

TTP’s fee rates compare favorably to similar positions for FCDO programmes delivered by COWATER in other countries (e.g Somalia and Zimbabwe). While advisers were paid for between 17-20 days for the work, each of them works effectively full-time hours, often working flexibly when they are needed including beyond their terms of contract to support the ministries. MoR and MoF officials continued to maintain their high expectations of both the advisers’ availability and the programme deliverables throughout the year. Contracts with both our main supplier COWATER and the M&E supplier IPE Global were amended to reflect precise spending trend in the remaining period of the programme. Profit margins by the supplier were strongly scrutinized by the FCDO TTP team together with the commercial team and a robust agreement has been reached.

Efficiency

During the year in review, the programme has planned to deliver 13 milestone indicators. Out of the total, it has delivered 9 meeting or exceeding expectations. Three milestone indicators did not moderately meet expectations. One output milestone was not delivered. These deliverables were made within the challenging context when MoR staff were occupied with competing demands due to high pressure on short term revenue mobilisation, causing distraction from long-term reform activities.

The VfM was strengthened by the agreement and application of performance-based payment with the supplier. That means, 25% of their monthly service fee payment was retained and linked to the supplier’s KPI achievements. Despite the hike in cost of living, COWATER hasn’t made cost of living adjustments to its advisers. Though external international advisers had increased in the past year, FCDO’s standard travel policies including use of economy class for flights were duly applied. Travel expenses remain moderate.

Effectiveness

As discussed under the outcome assessment, the nominal tax revenue (tax collected as a share of planned collections) has significantly increased during the year. Following the IMF backed reforms, revenue growth was positive in real terms.

Most importantly, this review recognises the reality that the TTP has become a stabilisation programme. The independent reviewers have confirmed that the programme has been very effective at maintaining and stabilising the core IT architecture of the MOR – as also evidenced by feedback from MOR officials to FCDO officials, World Bank and IMF experts. This shift – recommended in the last annual review – recognized the budget and operating context realities facing the programme. However, the political commitment to improving tax performance in Ethiopia appears to have shifted significantly since the IMF programme was agreed in July 2024. If the programme were able to continue to the end of the IMF programme we, and the independent evaluators, assess that the possibility of driving substantial reform is much improved.

Equity

The revised logframe has required disaggregation of milestone data by gender when appropriate. The programme has been encouraging more female participation in the trainings provided. However, the programme is not at parity. Figures for the year show proportionally a smaller number of female participations. Out of the 30 IT officers, 8 were female (27%); out of 9 audit officers, 2 were female (22%); and out of 45 legislative drafters, 17 were female (38%). Although not parity, independent evaluators noted that the proportions achieved compare well to other programmes.

The programme has tried to add a gender mainstreaming lens in tax reform and a concept note to a possible development partner was submitted by Cowater. The intention was to provide an extra budget with which to fully resource complementary advisory capacity to the existing gender components within the TTP. Raising awareness of the differential impacts of tax administration and tax policy on different social groups, including women, and strengthening capacity of ministers to support and engage women taxpayers were the focus areas. This failed to secure the additional funding due to the programme’s prioritization of core IT system and operational stability of the core administrative systems.

Incidence analysis – the effect of tax on the economic welfare of different parts of the population – is an important objective in tax policy that this programme would like to support. The reality of the current operating context (for example, very low tax: GDP, macroeconomic crisis, very weak capacity in the MOR and MOF, and stretching short-term revenue targets) means attaining political support for this is challenging. Stabilising, strengthening and enhancing the resilience of the existing system, is a significant challenge and clear short-term priority.

On the other hand, the programme has been promoting equity and fairness within the tax system. Two examples of this that were delivered include: i) simplification of presumptive taxation for micro, small and medium enterprises by reducing administrative burdens and promoting compliance. This supports smaller businesses in formalising and accessing tax benefits more easily; and ii) adjustments to personal income tax system by proposing changes to raise the tax-free threshold and revise marginal tax rates aiming to create a more progressive system. These adjustments focus on easing the tax burden for lower-income earners, ensuring fairness and aligning with taxpayers' ability to pay.

E: RISK

Overview of risk management
The program is assessed to have a Moderate overall risk rating, which includes nine identified risks with residual risk ratings of five as moderate, three as major, and one as minor. The programme maintains both an offline and an online risk register (accessible via AMP), which is regularly updated at least once every quarter. Cowater, the programme’s main supplier, also maintains its own risk register, updated on a quarterly basis. Furthermore, the programme conducts quarterly risk meetings with Cowater, as well as internal meetings, to review and revise its risk register in accordance with the outcomes of these discussions.
The programme remains within the FCDO risk appetite (table below):
Table 1. Distribution of risks in relation to appetite
Risk category	Total risks	Ratings	Programme risk appetite	FCDO Ethiopia risk appetite	Total Risks Outside programme/FCDO risk appetites
Strategy & Context	3	Major	Receptive	Receptive	0
Policy & Programme Delivery	3	Moderate	Cautious	Receptive
Reputational	1	Moderate	Cautious	Cautious	0
Public Service Delivery & Operations	1	Moderate	Minimal	Cautious	0
Financial & Fiduciary	1	Minor	Minimal	Receptive	0
Total	9

The main risks identified in the risk register were:
The ongoing conflicts in the Amhara and Oromia Regions, along with the political instability in the Tigray Region, hinder revenue generation in these areas. Additionally, regions affected by conflict may be overlooked for assistance related to the tax transformation programme. To mitigate this risk, key measures have been implemented, including maintaining an updated Political Economy Analysis, and sustaining open communication with the MoR, MoF and BE to understand how data and initiatives from the Tax Transformation Programme affect the conflict and the overall context in Ethiopia.

Lack of GOE strategic leadership in the transformation of the tax system, largely due to political pressures and the unpredictable nature of the national context, diverts attention from long-term sustainable reforms towards the allocation of resources for short term goals. To counter this risk, it is vital to leverage program structures, such as the Steering Committee, to build consensus and strengthen the transformation agenda. Additionally, introducing flexibility into the programme will facilitate the integration of new appointees. Effective communication between leadership and technical staff with the Ministry of Revenue and the Ministry of Finance is also essential.

Risk associated with excessive pressure on government to meet both internal and external revenue requirements. The pressure to boost revenue may cause overstretch to taxpayers, affect businesses, erode voluntary compliance, damage government-taxpayer relationships, and potentially cause social unrest. To address this risk, the following measures have been suggested: (i) collect current data on how the push for increased revenue is influencing government-taxpayer relations (ii) attend and provide advice in the MoR/MoF/Customs Technical Committee and (iii) promote adherence to international best practices and support the creation of a formal reform roadmap.

Risk associated with donor support duplication and overlapping priorities due to the growing interest from donors to support GoE’s DRM. To address this risk, the TTO will serve as a central hub for various donors' tax support initiatives, offering essential background information and updates on progress in different tax reform areas. The FCDO, in collaboration with the supplier Cowater and the TTO, will continue to facilitate coordination among tax donors.

Poor trust and weak working relationships between the programme team and the key technical counterparts in the GoE results in delays in implementation and jeopardizes the achievement of target outputs and outcomes. To mitigate this risk, it is essential to maintain ongoing close engagement with senior GoE officials and technical experts at appropriate levels, enhance transparency and communication, and conduct regular discussions based on an agreed agenda aimed at strengthening relationships and building trust.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Tax Transformation Programme continues to assist the Ministry of Revenue (MoR) in modernizing Ethiopia’s tax administration by focusing on different initiatives and activities. The intervention mainly targets improving the IT systems, rationalizing the tax systems, improving processes and procedures and work to maximize donor coordination. The programme has been under implementation for the last six years. It began in March 2019 with an initial total value of £35 million. In the first quarter of 2024, amendments were made to the contracts for two of its suppliers (Cowater and IPE) which extended the end date to March 2026. HMRC also renewed its MoU with the Ministry of Revenues for one year. In addition, an addendum to the business case was also made which reduced the value of the programme to £20.27 million. To date, the programme has spent £16,415,646 million. The table below shows the detailed breakdown of the TTP expenditures in the review year:

Component	Description	Budget/ / Forecast 2024/25	Spend to end of March 2025	Budget utilization
300553-101	Support to Tax Transformation through Service Provider	£2,559,000	£ 2,435,554	95.18%
300553-101	TTP audit	£10,000	£7,552	75.5%
300553-103	Analysis, research, and programme support	£69,079.19	£69,079.19	100%
Total		£ 2,638,079.19	£ 2,512,185.19	95.23%

Component 1: Accelerated Delivery: Technical assistance support to the Ministry of Revenue through the Tax Transformation Office (TTO). Cowater International is the main supplier of the Tax Transformation Programme.  The contract was amended in 2024 to extend the programme until March 2026. The amendment also decreased the value of the contract from £ 27,167,193 to £18,005,643. Cowater is responsible for the overall project leadership and supervising the Tax Transformation Office (TTO), a delivery unit embedded within the Ministry of Revenues (MoR). During the review period, Cowater spent £2,435,554. Under this contract, £2.425 million is also allocated for the final year of the extension period (FY 25/26).
Component 2: Peer-to-peer support from HMRC.

The HMRC team is directly working with the Ministry of Revenues and Ministry of Finance to help them develop sustainable capacity. In July 2024 the team renewed its MoU with the Ministry of Revenues for a further year. The MoU aims to   establish the basis for a cooperative institutional relationship to encourage and promote bilateral technical cooperation between MoR and HMRC. HMRC also provided capacity building and technical assistance on tax reforms to strengthen domestic revenue mobilization efforts. The team also gave practical assistance through peer-to-peer support and transfer of skills through a real-time, “learning by doing” approach.
During the review period, the HMRC team made five visits and delivered support on the data & risk work stream, the compliance/VAT space and helped senior leaders in the MoR on Leadership & Communications in line with MoR strategic priorities. The team also maintained direct communication with the Ministry of Finance.
Component 3: Strategic Tax Transformation Support Fund.
IPE, a supplier taking part in the evaluation and analysis of the Tax programme, has engaged in different activities during the year.  In the review period, the IPE team shared their comments and observations on Cowater’s work plan and the TSTP’s logframe based on their experience of conducting the annual review of the programme over the years. In addition, the team collected inputs for the annual report while reviewing various documents and conducting online and in-person interviews with stakeholders of the programme, including directorates of the MOR, World Bank, IMF, HMRC etc.

Commercial and Finance:

At the beginning of the review period TTP had an annual budget of £2.5 million. A further request was made for the budget by the main supplier which raised the total budget of the programme to £ 2.63 million. However, time constraints hindered the full utilization of the allocation which put the yearly budget utilization rate of the programme to 95.23%. Compared with the previous financial year the annual budget of the programme has increased by nearly 40%, though it remains well below that originally envisaged. The programme broadened its engagement by recruiting different technical advisors such as excise tax administration, filing and dept management, audit and risk, IT governance etc.
A detailed work plan of the extension period was also prepared by the Cowater team and commented by FCDO and the IPE. Halfway through the review year, FCDO and Cowater also had a budgetary uplift discussion to undertake activities that are additional to the approved workplan and to include two new roles.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Different arrangements are in place for monitoring, implementation support and evaluation of the programme. These include:
- Quarterly Ministerial and Development Director level Steering Committee meeting
- Fortnightlies stock take and implementation support meeting between the supplier and the FCDO programme team
- Quarterly technical report and performance assessment
- Monthly financial forecasts and reports
Weekly SRO, PRO and Programme Officer catch up
- Annual stock take and evaluation by an independent firm (IPE Global)
- Annual audit report
Quarterly risk and delivery plan updates
- Annual asset spot checks
- Ad hoc meeting with the relevant GoE officials (as necessary).

Every month, the team has two sets of meetings with the main supplier to check the progress of key deliverables and to discuss issues of programme management. The status of financial expenditure is also reviewed on a monthly and quarterly basis. The performance of the programme is evaluated during each quarter using weighted indicators that examine progress against the outputs and management performance which evaluates the programme’s responsiveness to FCDO and GoE needs. The team also makes sure that the reported spend is within the 5% variance of the forecast. The team has conducted the annual asset spot check in March 2025 and found no gap in the asset management.

During the review period, FCDO has conducted three quarterly KPI assessments against the agreed Performance Assessment Framework (PAF): in the first quarter (April-June 2024), second quarter (July-Sep 2024) and third quarter (Oct-Dec 2024). The implementing partner has met 100% of the key performance indicators in the above mentioned three quarterly assessments.

In February 2025, the independent monitoring and evaluation supplier, the IPE team, assessed the progress of the programme while conducting various interviews with Cowater, MoR, MoF, monetary institutions, and other concerned stakeholders of the programme. Findings of these assessments are shared with the TTP team and used to prepare this year’s annual review.

The up-to-date audit report of the programme was prepared in January 2025. The report found no financial discrepancies. However, it noted Cowater to consistently use of OANDA exchange rate for expenses, and to apply proper documentation for small incentive payments that is made to coordinators supporting the programme. The FCDO TTP team followed the status of the recommendations and received assurance from the Cowater that the issues are resolved.

Evidence

Deep dive report provided by the independent evaluator identifies various factors as to why the tax transformation agenda wasn’t hugely effective and why the current assistance by the FCDO is critical to stabilise the tax system/ MoR rather than transforming it. Compared to the original BC, institutional, operational, and human resource related challenges were worsening, and productive capacity of the economy was impacted by conflict and other factors, making the real transformation agenda too ambitious for the realities faced by the MOR.

The programme will run until March 2026. The no-cost extension period of the two years (2024/25 and 2025/26) will allow in key deliverables around business process transformation, support to critical IT infrastructure and embedding of capacity development and supporting domestic resource mobilization. The extension will also allow continued assistance to a key priority of the GOE in tax policy.

Learning
The TTP team engaged in several face-to-face and conference call meetings with suppliers of the programme and tax donors in the country. These meetings were helpful not only to draw lessons from the implementation at different phases of the programme but also to understand policy and contextual level challenges.
The feedback TTP team received from the Africa Risk Lead regarding the management of the risk of the programme was a good lesson of the review period. Based on this feedback, the team is regularly updating the risk appetite, elaborated the risk description to avoid vagueness, strengthened the mitigation, and actively kept only those relevant to the programme.
Some indicators where the milestones substantially exceeded expectations are helpful learning points showing how the high-level government commitment can make difference in meeting or exceeding expectations. If the programme is to extend beyond the current period of 2026, FCDO will need to sit with the top level of government to identify and agree limited areas of their priorities where they commit themselves to prioritise but with high impact on the tax sector.
Another key learning point is the importance of engagement at the top level of government. Engagement with the Prime Minister’s Office and Steering Committee have been useful means of understanding the government thinking and the value they attach to UK’s partnership, with implication on Ethiopia-UK diplomatic relationships and business deals

Date of last audited TTP annual statement (s)	Mar 2025
Date of last TTP narrative and financial report(s)	Mar 2025