Trade Centre of Expertise Business Case

Business Plan Summary: The Trade Centre of Expertise (Trade COE) Programme contributes to the Growth Directorate’s outcome objectives on: / International development and poverty reduction through trade; and / A free and fair global trading system which maximises the opportunities for free trade and sustainable economic growth.

Title: Trade Centre of Expertise Programme
Programme summary: The Trade COE aims to increase trade from and between developing countries in order to drive export-led growth which reduces poverty and increases people’s resilience to climate change. It will provide technical assistance to governments and businesses in developing countries and in multilateral fora to enable them to overcome the barriers to trade, to compete in global markets and to make the global trade rules work for developing countries. It will provide world-class expertise on trade to Posts that is responsive, flexible, inclusive and value for money and is accompanied by a separate Trade COE Evidence and Innovation programme.
What is the rationale for UK Aid spending? The Trade COE will strengthen long term, mutually beneficial economic partnerships with countries in the Global South, helping them to grow their economies and lift themselves out of poverty, particularly African countries. It will strengthen the multilateral institutions that underpin the global trading system such as the WTO, World Bank and joint donor funds to create an equitable platform for the growth and economic development of all countries. / By focusing on sustainable, inclusive trade the Trade COE will contribute to Sustainable Development Goals 8 (Jobs and Growth), 5 (Gender Equality), 13 (Climate) and 17 (Partnerships). / The Trade COE directly addresses the recommendations in the 2023 Independent Commission for Aid Impact (ICAI) Report on Aid for Trade (AFT) to link trade interventions more clearly to impact on poor people and to work more closely with the international institutions underpinning the rules-based trading system. / The Trade COE will help deliver FCDO and DBT’s Outcome KPI on increasing preferential trade under the Developing Countries Trading Scheme (DCTS) and Economic Partnership Agreements (EPAs). Growing trade from developing countries supports the UK’s economic growth and security by building the markets of the future for UK goods and services. / The Trade COE Programme is complemented by the Trade COE Evidence and Innovation Programme that provides monitoring, learning and advocacy on Trade for Development.
Programme Value: up to £XX million ODA (over 5 years) of which up to £XXm is estimated to be funded by post based on their demand		Country/ Region or Sector: / Trade for Development
Department/Country Office confirmation of review processes		Trade for Development, Growth Directorate
Contact name		Simon Calvert, Trade for Development
Threshold for final approval of Business Case: Ministerial
Date of Approval of Concept Note:	10 May 2024	Name and role of Approver / Minister Mitchell
Date of Approval of Business Case:	17 October 2024	Name and role of Approver / Minister Dodds
Programme Code:	AMP Start Date: April 2025	AMP End Date: March 2030
Overall programme risk rating:	Moderate

Acronyms
ABT	Addressing Barriers to Trade
ACP	African, Caribbean and Pacific states
ACWL	Advisory Centre on WTO Law
AFT	Aid for Trade
BSI	British Standards Institute
CBAM	Climate border adjustment mechanism
COE	Centre of Expertise
DBT	Department for Business and Trade
DCTS	Developing Countries Trading Scheme
Defra	Department for Environment Food and Rural Affairs
EIF	Enhanced Integrated Framework
EME	Early Market Engagement
EO	Executive Officer
EPA	Economic Partnership Agreement
EPO	Export promotion organisation
EU	European Union
FCDO	Foreign, Commonwealth and Development Office
FTE	Full time equivalent
FY	Financial year
G7	Grade 7
GDD	Global Development Delivery
GDP	Gross domestic product
GTS	Global trading system
HEO	Higher Executive Officer
HMG	His Majesty’s Government
HMT	HM Treasury
ICAI	Independent Commission for Aid Impact
ICF	International Climate Finance
ISO	International Organization for Standardization
ITC	International Trade Centre
KPI	Key performance indicator
LDC	Least developed country
MC	Ministerial Conference (WTO)
MoU	Memorandum of Understanding
MREL	Monitoring, reporting, evaluation and learning
MSMEs	Micro, Small and Medium Sized Enterprises
MTH	Making Trade Happen
ODA	Official development assistance
OECD	Organisation for Economic Co-operation and Development
PRO	Programme Responsible Owner
PrOF	Programme Operating Framework
RDEL	Resource delegated expenditure limit
RMG	Ready made garments
SDGs	Sustainable development goals
SEO	Senior Executive Officer
SPS	Sanitary and phytosanitary measures
SRO	Senior Responsible Owner
TA	Technical Assistance
TAF	Trade Advocacy Fund
TBT	Technical barrier to trade
TFA	Trade Facilitation Agreement
TOR	Terms of reference
UKTP	UK Trade Partnerships Programme
WTO	World Trade Organization

## Strategic Case

Trade, economic development and poverty reduction

International trade is vital for achieving sustained economic growth and poverty reduction.  Recent experience in Asia and South America has shown that for developing countries, opening-up access to international markets can have positive transformative effects on the economy and poverty. Export-led growth is a pre-requisite for poverty reduction in Africa as exports can stimulate overall growth and investment, acting as the primary source of foreign exchange earnings, without which progress on incomes, poverty and public services cannot happen.
[note] The Role of Trade in Ending Poverty, World Bank/WTO, 2015
[note] EED Library (Open) - Africa's FX Constraint (2023), Nick Lea, FCDO Deputy Chief Economist

The development outcomes of participation in global value chains can be significant; they contribute nearly 30% of developing country GDP (compared to 18% for developed countries) and lead to larger growth rates per capita. At a firm level, free and fair trade can have positive effects on productivity and investment as firms derive economies of scale from accessing new markets and adapt to global competitive forces. Smaller firms that successfully integrate into global value chains experience more growth and are more competitive and longer-lived.
[note] World Investment Report: Global Value Chains: Investment for Trade and Development, UNCTAD 2013
[note] Trading Up: The benefits of exporting for small firms, Atkin and Jinhage, International Growth Centre November 2017
[note] Exporting and Firm Performance: Evidence from a Randomized Trial, David Atkin† Amit K. Khandelwal‡ Adam Osman

The UK is a champion of fair and sustainable trade within a transparent global rules-based system. The UK has played a leading role in opening its markets to developing countries to support their export-led growth, through the recently launched Developing Countries Trading Scheme (DCTS) and our network of Economic Partnership Agreements (EPAs). Together, these mean that the UK offers duty-free or nearly duty-free trade in goods to more than 90 developing countries.

However, despite preferential trading terms with many developed countries, developing country exports remain low and often overly focused on commodities or primary agricultural produce. Only 8% of global goods trade involves low income and lower middle-income countries, despite these countries being home to nearly half the world’s population. Least Developed Countries (LDCs) are home to 13% of the world’s population and 40% of the world’s poor, but account for less than 1% of global trade and are heavily reliant on the export of commodities with volatile prices, such as oil, minerals and unprocessed agricultural goods. Between 2019 and 2021, 74% of LDCs relied on commodities for 60% of their goods export earnings. At the same time, trade in services – where most future growth and jobs will be created – is lagging. LDC trade in services makes up a fraction of their total exports: in 2022 LDCs exported a total of $37bn in services compared to $277bn in goods.
[note] The Role of Trade in Ending Poverty World Bank and WTO (2015).
[note] UNCTAD Least Developed Countries Report 2023
[note] World Trade Statistical Review 2023 WTO 2023, page 27

Trade benefits poorer people through income growth but the benefits of trade are not always universally felt, with those in low-income households, women, micro/small and medium sized enterprises (MSMEs) and people in economically marginalised groups less likely to benefit without targeted interventions and adjustment policies. There are diverse impacts of trade on different groups of people, depending on, for instance, which sectors their livelihoods are linked to and where they live. Age and education can also impact the ability of individuals to benefit from trade with younger, more educated individuals more likely to participate in export-orientated trade. Trade can also, in some circumstances, exacerbate inequality between workers. It has been seen to increase inequality between educated and less educated workers within a firm and, in manufacturing, it has been associated with growing wage gaps between men and women.
[note] Systematic literature review on trade liberalization and sustainable development (September 2022) Laura Barros, Inmaculada Martinez-Zarzoso
[note] The Role of Trade in Ending Poverty World Bank and WTO (2015).
[note] Aid for trade and its role in promoting trade for poverty reduction, Literature Review, Independent Commission for Aid Impact (ICAI), June 2023
[note] The Impact of Trade on Inequality in Developing Countries, Nina Pavcnik National Bureau of Economic Research Working Paper 23878, September 2017
[note] Summarised from The Impact of Trade on Inequality in Developing Countries, Nina Pavcnik National Bureau of Economic Research Working Paper 23878, September 2017
[note] Menon N, Rodgers Y. 2009. International trade and the gender wage gap: new evidence from India’s manufacturing sector. World Dev. 37(5):965–81 cited in Trade liberalization and poverty: What have we learned in a decade?” L Alan Winters and Antonio Martuscelii, 2014

Trade can also exacerbate climate change issues if there are no or few remedial actions taken during the cross-border movement of goods and services. However, trade can also allow greater diffusion of low emission goods, services and technologies. The increased economic development which trade brings to developing countries has the potential to improve the resilience of individuals to climate change and enables firms to adapt to the impact of climate change and take mitigating action, for example by using greener production methods and technologies.
[note] The Trade and Clmate Change Nexus: The Urgency and Opportunities for Developing Countries Brenton, Paul; Chemutai, Vicky; World Bank 2021

Problems for developing country trade and poverty reduction

Developing countries face a range of problems in their export-oriented business sectors, including macroeconomic factors, the enabling business environment, infrastructure provision, access to finance and the skills and capacity of the workforce. Whilst these factors may influence the ability of developing countries to trade, they are wider issues of economic development which are not specifically trade related and are not, therefore, the primary focus of this business case.
[note] This business case will work closely with the other economic development Centres of Expertise address these issues particularly on Green Inclusive Growth, Infrastructure and Finance

Developing countries themselves have identified a number of priority trade-related challenges. According to the WTO, these include trade facilitation, export diversification, MSME growth, connecting to global value chains, e-commerce and agriculture and expansion of service exports. Based on this analysis and experience from FCDO AFT programmes, three broad trade-related problems have been identified, which are explored and evidenced in further detail in Annex A:
[note] Aid for Trade Global Review 2022 WTO

  1. Addressing Trade Barriers: Tariff barriers are at a historic low thanks to wider coverage of Free Trade Agreements and to the preferential trading arrangements like the DCTS. However, a number of factors limit the benefit of these more liberal trading conditions including the need to comply with non-tariff barriers (standards, sanitary and phytosanitary requirements, licenses, labelling requirements, certifications etc) and sustainability and environmental requirements (e.g. Carbon Border Adjustment Mechanisms), complex and costly customs processes and procedures as well as wider corruption and political economy challenges.
  2. Competing in Global Markets and “Making Trade Happen”: Firms in developing countries struggle to produce competitive products that meet the market expectations of businesses and consumers in developed countries. Many firms have inadequate market knowledge and struggle to build credibility and business relationships overseas. Buyers in developed countries have identified issues relating to quality, reliability, scalability, responsiveness to new regulations, credit terms and currency fluctuations which limit their ability and willingness to source from developing countries.
  3. Making the Global Trading System Work for Developing Countries: The rules based international trading system, with the WTO at its centre, provides the framework for free and fair trade. However, developing countries (which make up 75% of WTO members) struggle to accede to and actively participate in WTO negotiations due to a lack of resources and capacity, increasing the risk that global rules do not adequately reflect their needs. A global trading system that does not take into account the needs of all countries will be less effective in advancing global economic growth. Developing countries also lack the resources to effectively implement WTO agreements and struggle to realise the full associated benefits of reduced trade costs and increased in investment.

Proposed Interventions

Aid for Trade (AFT) is the broad category of support which helps developing countries to use trade to foster economic growth, sustainable development and poverty reduction. It focuses on integrating developing countries into the global trading system and helping to build their supply-side capacity and trade related infrastructure. Analysis from the WTO highlights four types of effective AFT:
[note] WTO Aid for Trade at a Glance OECD
1. Technical assistance: helping countries to develop trade strategies, negotiate more effectively, and implement outcomes.
2. Infrastructure: building the roads, ports, and telecommunications that link domestic and global markets.
3. Productive capacity: investing in industries and sectors so countries can diversify exports and build on comparative advantages.
4. Adjustment assistance: helping with the costs associated with tariff reductions, preference erosion, or declining terms of trade.

These targeted efforts contribute to reducing trade costs and enhancing trade capacity. The Trade COE will focus on trade related technical assistance and will work closely with other Centres of Expertise and UK ODA interventions to support comprehensive change. For example, the Green Cities and Infrastructure COE may fund trade-related infrastructure work; the Green Inclusive Growth COE may tackle wider binding economic constraints and support business investment; and the British International Investment may make catalytic investments and provide trade finance. It is more effective to draw on these existing sources of leading expertise than developing them anew under the Trade COE and close collaboration and coordination will be put in place between these centres to ensure interventions combine to deliver long term improvements in trade.

Based on existing evidence from programme results and wider Trade for Development evidence, interventions at the level of government, businesses and the global trading system can effectively tackle the problems outlined above (and described further in Annex A) in order to maximise trade and its inclusive impact. Our proposed technical assistance interventions and their evidence base are described in further detail in Annex B and can be summarised as follows:

Intervention Level	Areas of Technical Assistance (See Annex B for more evidence and detail)
Government (including regional bodies)	Design and implementation of trade policy reforms to develop inclusive, export-led growth policies. / Implementation of bilateral, regional (e.g. ASEAN or Regional Economic Communities) and WTO trade agreements and responding to global trade-related regulatory changes. / Adoption and implementation of international standards by national and regional standards bodies. / Strengthening quality infrastructure at regional and national levels to enable businesses to demonstrate compliance with global standards and technical rules. / Streamlining customs processes and procedures to facilitate trade and reduce export time and cost. / Regulatory environment improvements which tackle corruption and create a more transparent and open trading environment.
Business	Providing trade and export promotion support to businesses (e.g. trade missions). / Providing more inclusive access to export market information and buyers. / Supporting compliance with quality standards for high value export markets. / Supporting compliance with private quality standards and certification schemes. / Building capacity of business networking organisations to advocate for trade policy reform.
Global	Supporting developing countries to meet WTO accession requirements. / Building developing country negotiation capacity at the WTO, including technical and logistical support. / Providing legal advice support for participation in the WTO Dispute System.

The choice and combination of interventions in each country will be based on systemic analysis of the challenges and opportunities for export-led growth and will be delivered in close partnership with those working in related fields such as the COEs for infrastructure and green inclusive growth.

Rationale for UK intervention

The Trade COE will strengthen long term, mutually beneficial economic partnerships with countries in the Global South, helping countries to grow their economies and lift themselves out of poverty, particularly in Africa. It will strengthen the multilateral trading system and its institutions such as the WTO and UN Committee on Trade and Development to create an equitable platform for the growth and economic development of all nations. By focusing on sustainable, inclusive trade the Trade COE contributes to Sustainable Development Goals 8 (Jobs and Growth), 5 (Gender Equality), 13 (Climate) and 17 (Partnerships). It will support long term UK economic growth and security by building the markets for the future for UK goods and services and diversifying our supply chains.

As a Centre of Expertise, the Trade COE has been designed to make available the right kind of technical trade expertise and capabilities to Posts and partners in a way that is easy to navigate, good value for money and promotes UK expertise and values. To ensure technical assistance is as impactful as possible, robust and systemic analysis will need to be undertaken first to ensure the right technical assistance is delivered in the right way and targeted at the right place at the right time. Prioritising longer-term assignments will improve the likelihood of technical assistance leading to systemic change.

ICAI has endorsed the design of the Trade COE and coordination function noting that “The Trade Centre of Expertise, if implemented effectively and as planned, will help to improve coherence, coordination and collaboration between centrally managed programmes and the overseas network for those programmes with access to the Trade Centre for Expertise”.

The Trade COE is expected to provide three types of technical assistance:
1. Short term assignments for Posts: Demand driven assignments of up to 12 months for standalone interventions. These could include technical assistance to address specific gaps in a country’s trading environment, scoping assessments and the design and development of proposals for longer term technical assistance.
2. Long term assignments for Posts: Demand driven assignments lasting beyond a year to deliver continued technical assistance. Where possible these would be designed to combine multiple points of intervention at the government/business/global level or to complement activities undertaken by bilateral or other programming, including from other COEs.
3. Long term centrally driven interventions: Targeted, long-term projects designed jointly with Posts which combine multiple points of intervention, to drive a more systemic shift in trade in one of the Trade COE’s priority countries.

There is strong demand from Posts for the kind of trade-related technical assistance which the Trade COE will provide. Consultations with Nigeria, Ethiopia and Pakistan have identified demand for longer-term interventions. The UK’s Permanent Representative in Geneva supports the proposed global level scope of work. During the recent voucher scheme in 23/24, over 20 countries sought trade-related technical assistance, totalling £4.5m from existing trade programmes. Beyond the voucher scheme, Posts in Jordan, Ethiopia, and the Pacific have provided an additional £1.5m for technical assistance from these existing programmes. Further detail showing the level of demand from Posts for 2023/24 is shown below:

Figure 1: 2023/24 Demand from Posts

Fit with Existing Programmes and Lessons Learned from Previous Programmes

In its recent review of Aid for Trade in FCDO, ICAI identified 35 trade related programmes of note, and these are now the subject of an internal portfolio review. The Trade COE’s associated but separate Evidence and Innovation Programme will play an important role in synthesising the learning and insights from these programmes and driving a single-HMG approach to Trade for Development, including by leading on initial ‘scoping assessments’ to design new interventions jointly with Posts. This will allow Trade COE interventions to align with wider programming efforts, utilise insights and lessons learned from these efforts and maximise the cumulative impacts of all interventions. It will also deliver independent monitoring, reporting, evaluation and learning projects for the central Trade COE including process, value for money and impact evaluations in addition to yearly Annual Reviews.
[note] ICAI Review of Aid for Trade, June 2023

The Trade COE will work closely with Trademark Africa and with the other Centres of Expertise to ensure alignment and collaboration on trade facilitation and wider economic development interventions that impact on trade respectively. This includes the Green Inclusive Growth COE and the Green Cities and Infrastructure COE. Most of the proposed support under each of these COEs is distinct, but there may be some potential for overlap, for example, where partner Governments are interested in promoting export led growth through a wider package of economic transformation that could involve multiple COEs. To manage this potential for overlap a clear process for coordinating responses to Posts has been agreed (see Annex G) and common governance arrangements have been put in place which include other COE representatives on the Management Board of the Trade COE (see Management Case). It is expected that the trade-focused technical assistance of the Growth Gateway (currently part of the Green Inclusive Growth COE) will migrate to the Trade COE’s work on supporting developing country businesses to make trade happen in 2026 to strengthen alignment.

The Trade COE design is shaped by evidence from legacy and live AFT programmes, the vast majority of which have scored an A or higher in Annual Reviews and include UK Trade Partnerships, SheTrades Commonwealth+ Standards Partnership and the Trade Advocacy Fund. Key lessons we have learned from previous programmes for programme design and delivery are:
1. The benefits of trade agreements and policies lie in their implementation.
2. Packages that include both negotiation and implementation support will deliver greater results.
3. The political economy can be a significant challenge when liberalising trade. It is essential for all trade programming to evaluate and integrate the political economy into its design and delivery.
4. Engagement with the private sector is critical for making progress on trade policy. Business associations and specialist networks, for example, for women-led businesses can be effective channels for policy dialogue between government and trading firms.
5. Increases in trade can sometimes lead to adverse impacts on specific groups of people, for example if jobs move away from specific sectors or regions or require higher levels of skills and education. All programming should robustly analyse the impacts and look to reduce and mitigate any unintended consequences.
6. The links between increases in trade and poverty reduction are difficult to measure and highly complex. The Trade COE Evidence and Innovation Programme will support the central Trade COE programme to improve this evidence base.

The Trade COE programme is accompanied by the Trade COE Evidence and Innovation Programme (a separate business case) which will formalise and mainstream learning from across the UK AFT portfolio and use this to inform FCDO policy and influence the adoption of pro-development trade policies by governments throughout the world. It will provide a more independent monitoring function for the Trade COE and will commission independent evaluation of aspects of its work.

Expected Impact and Outcomes

1. The expected impact of the Trade COE is increased trade from developing countries that is equitable, inclusive and sustainable. This will be measured by trade volumes, trade preference utilisation rates, change in the number of jobs sustained or created in export sectors (particularly for women and marginalised groups) and change in the number of people with improved resilience to climate change.
2. The expected outcomes of the Trade COE are more products and services exported to more markets (including the UK) from developing countries; more standards, customs processes and trade regulations that support exporting businesses in developing countries; and more developing countries participating in more multilateral negotiations.

Climate and Environment

This programme will contribute to International Climate Finance (ICF) objectives. Increasing economic prosperity across developing countries will empower countries to adapt their industries and to participate more directly in global climate change mitigation action to keep global warming to 1.5 degrees Celsius. Some activities are expected to support developing countries directly in meeting climate targets, e.g. by supporting them to develop their own carbon tax policies and implement green trade regulations and standards. All activities will be continuously assessed to ensure they do not adversely affect climate targets. The programme has the potential to contribute to several ICF indicators, on the basis that it improves the resilience, knowledge and adaptability to climate change of people in developing countries (ICF KPIs 1, 4, 5, 6, 9, 13, 14).

The expected increased trade through the Trade COE has direct climate and environmental risks (waste efficiency, pollution and water resources) and we will work to ensure that these risks are prevented/mitigated as part of any intervention. Our climate and environment risk assessment has identified the following key risks:
1. Trade COE interventions could be subject to climate impacts and exacerbate climate change if climate risk is not properly considered. This will be mitigated by assessing risk to climate in each intervention and will form a core part of assessment criteria.
2. Trade COE interventions could result in environmental harm by supporting or promoting trade that has an adverse effect on emissions, nature and biodiversity. This will be mitigated by assessing risks on emissions, nature and biodiversity in each intervention and will form a core part of assessment criteria.

The programme is in line with relevant legislation:

International Development Act - The Trade COE will ensure the requirements of the International Development Act are upheld, making poverty reduction central to all its ODA interventions.

Gender Equality and Public Sector Equality Duty - The Trade COE will consider fully the potential impact on gender equality and other protected characteristics of all its interventions, wherever possible within data constraints. It will use experience and evidence from existing programmes (SheTrades Commonwealth+ and UK Trade Partnership (UKTP)), and from the Trade COE Evidence and Innovation Programme. In allocating funding to different economic sectors, we will reflect what we know about where women and other people of protected characteristics work, for example in agriculture and ready-made garments and the types of firms that women own and lead, predominantly medium, small and micro enterprises. UK support to strengthening business support organisations for women entrepreneurs takes into consideration that women typically have limited access to such networks. Where support is directed towards government actors, such as policy makers and export promotion agencies, our technical assistance will include gender equality and other equality considerations. Some funds will be allocated to interventions that specifically target women entrepreneurs and workers, building on the approach in programmes such as SheTrades Commonwealth+. The Trade COE monitoring frameworks will include sex-disaggregated indicators, where it is possible to track the number of women entrepreneurs or workers benefitting from our interventions.

Terrorism - The risk of funds being misappropriated for terrorist purposes is assessed to be low, based on our experience of previous programmes, the types of delivery partners we expect to work with and the nature, context and location of activities envisaged. However, the related indirect risk will be monitored closely according to geographic locations, particularly in fragile and conflict-affected states. The programme will practice robust due diligence, monitoring and auditing of suppliers to ensure compliance with the Terrorism Acts 2000 and 2006.

## Appraisal Case
This Appraisal Case sets out the options we have considered for tackling the three problems for developing country trade outlined in the Strategic Case and Annex A of i) overcoming barriers to trade, ii) competing in global markets (“making trade happen”) and iii) making the global trading system work for developing countries.

The options are framed within the Centre of Expertise context and approach that has been approved by ICAI. This approach requires Centres of Expertise to be problem driven and responsive to the needs of Posts and to provide a single, unified point for specialist technical assistance across a range of existing programme areas, drawing on UK and global expertise as well as through multilaterals.

The responsive nature of much of the Trade COE’s work means that some of its interventions will be set by Post and cannot yet be determined. The Trade COE will also design and implement long-term interventions jointly with Posts, using central resources. The options appraisal considers the best approach to achieving the Trade COE’s results when delivering both demand-led and centrally-driven technical assistance.

Options Appraisal

Four strategic decisions have been appraised i) point of entry; ii) sector; iii) geography; and iv) delivery approach. Options for each of these strategic decisions have been appraised using the following criteria:
1. COE approach – delivers responsive, high-quality expertise for Posts and partners.
2. Impact – delivers long term, sustained impact.
3. Inclusion – ensures that everyone benefits from increased trade, including excluded groups.
4. Coherence – complements other interventions from FCDO, other donors.
5. Value for money and risk – is effective, efficient and within acceptable risk levels.

In addition to the above criteria, the criteria of building FCDO expertise and capacity has been included for the appraisal of delivery options.

Interventions will be undertaken following detailed, systemic analysis of the opportunities and challenges for export-led growth in a country/region. This analysis will be done jointly with posts, building on Inclusive Growth Diagnostics, and with other Centres of Expertise where appropriate, in order to identify where the technical assistance of the Trade COE can have long term impact (and also where it will not). This approach means that the Trade COE will not universally operate at all the levels, in all the sectors and in all the geographies discussed below but will take a targeted approach drawing on elements of its offer as required and working alongside others, like the Green Inclusive Growth COE, to address wider issues.

Strategic Decision 1: Point of entry

To increase trade from developing countries, it is possible to target support to developing country governments, businesses and/or global trade institutions. We have assessed the advantages and risks of providing UK technical assistance to each of these different points of entry.

Government

In designing effective support, the Trade COE would need to consider the government’s absorptive capacity (“bandwidth”), willingness to engage and perception of priorities. Where government capabilities are low, feasible options would focus in the short term on service provision to businesses (e.g. information on standards) and in the longer term on capacity building to introduce more substantive reforms and changes in the national quality infrastructure.

For the Trade COE, the advantages of engaging through governments include:

1. Impact: ICAI highlights that support to governments on trade policy has the largest positive effect on the quality of a country’s export. Aid for trade policy support - when combined with economic integration policies – also increases the quantity of trade, especially when it includes building the capacity of trade-related institutions.
  [note] Aid for trade and its role in promoting trade for poverty reduction: literature review, ICAI June 2023 page 10
  [note] Aid for trade and its role in promoting trade for poverty reduction: literature review, ICAI June 2023 page 10
2. Value for money: support to governments on policy reform has been identified by the Economic Development Best Buys as a “Great Buy” in terms of impact and overall cost effectiveness .
  [note] Best Buys in Economic Development for Growth, Chief Economist’s Office
3. Sustainability: the impact of policy and process changes introduced at a government level can be enduring and continue to impact the entire system of trade related economic activity in the long term.
4. Responsive and coherent: Trade COE support at the government level can be responsive to the needs of Posts and designed to complement other aspects of the bilateral relationship in country.

Limitations include:
1. Inclusion: government agencies tend to focus on larger, formal traders, for example in reforms of customs and border procedures. Women and poorer people are more likely to be smaller traders and engaged in informal trade. ICAI highlights the risk that support to export promotion agencies can benefit established exporters rather than supporting new firms to export.
  [note] Aid for trade and its role in promoting trade for poverty reduction: literature review, ICAI June 2023 page 16
  [note] Aid for trade and its role in promoting trade for poverty reduction: literature review, ICAI June 2023 page 12
2. Political economy: there is a significant risk that government level engagement can reinforce inequalities in the political economy if not managed appropriately.

Business

In designing effective support for businesses, the Trade COE would need to identify firms to support that deliver on its inclusive trade outcome and which are close to or can be supported to reach exporting-status. The advantages of engaging through these businesses and their networks include:
1. Impact: The UK Trade Partnerships programme found that $1 in technical assistance to smaller firms leads to an additional $5.7 in exports across all the countries, with the highest returns generated in West African countries (although this ratio is an average and impacted by a small number of highly successful interventions).
  [note] Evaluation of the UKTP programme, ITC Independent Evaluation Unit, December 2023
2. Inclusion: This precise targeting of beneficiary firms can help achieve UK policy goals to promote inclusive trade. Programme interventions such as SheTrades Commonwealth+ have demonstrated the effectiveness of targeting support to women owned, led and/or operated firms.
3. Responsive: Trade COE support to businesses can be directed to be responsive to the needs of Posts and delivered at pace.

Limitations include:
1. Insufficient alone: further action and policy reform from government may be needed to create the right conditions for businesses to export in the first place. Other challenges, such as access to finance and human capital constraints, may also require action, particularly for smaller firms.
2. Systemic impact: the provision of technical assistance to individual firms may lead to isolated development impact which is not amplified or sustained across the wider economy or beyond the life of the programme.

Global

For the Trade COE, the advantages of using our available resources to engage through the global trading system and multinationals include:
1. Value for money: Supporting countries to accede to the WTO can have economy-wide impact. Evidence suggests that five years after accession an economy is 30% larger, and that the impact of WTO entry on growth persists beyond the first five years.
  [note] EconStor: WTO accession and growth Tang and Wei Redux
2. Broad scope/impact: Multilateral trading rules can set important precedents which then influence other WTO agreements and global trading arrangements, including those of regional bodies such as ASEAN, African Continental Free Trade Area (AfCFTA). The impact of changes across the WTO membership can be significant – for example, the implementation of the Investment Facilitation for Development Agreement alone could increase global welfare by $296 billion.
3. Inclusion: Multilateral agreements can be a powerful tool to support inclusivity, for example gender equality provisions in WTO agreements.
4. Responsive: Trade COE support at the multilateral level can be responsive to the needs of individual developing country members or groups of members and delivered at pace, as evidenced by UK support through the Trade and Investment Advocacy Fund. For this support to be effective, the advice provided will be independent and impartial of UK positions. Therefore, it will be designed to be as demand driven as possible ensuring developing countries can engage with the topics of interest to them in the manner that they wish to.

Limitations include:
1. Long term, unpredictable impact: WTO multilateral negotiations have proved challenging. Negotiations can take years and the need to accommodate the different positions of other members which can result in watered-down commitments.
2. Value for money: with multiple donors and multiple recipient countries across a range of both short- and long-term interventions it is difficult to measure impact of UK multilateral aid for trade.

In summary, our appraisal for this strategic decision is that we will design interventions to ensure that the right trade conditions are in place through each of the government, business and global levels. This three-tiered approach will meet the criteria in the following ways:
1. COE approach: by offering support at a global, government and business level (separately or together), the Trade COE will be able to respond and adapt to the needs of each country.
2. Impact: all three points of entry have strong evidence on impact, and by delivering a package of support that includes them all we are able to operate simultaneously across these areas as required, thereby driving greater impact.
3. Inclusion: Interventions at all three points of entry are needed to ensure inclusive global trading frameworks are established, government policies and regulations are implemented in an inclusive way and businesses led by women/smaller firms are supported to trade.
4. Coherence: by delivering at all three points of entry, the programme will be better able to design interventions that are coherent with the particular needs in a country and with Post’s bilateral programmes, thereby tailoring support to be as coherent as possible.
5. Value for money and risk: the global and government points of entry have strong rationales for value for money.

Illustration of multi-level support to Ghana: The UK has provided support to Ghana at the business, government and global levels in recent years. In 2022, we supported the training of lead government auditors to improve the quality of food safety and the management of related supply chains so that Ghanian products could meet the required standards for export to world markets. We also provided technical support to medium and small Ghanaian businesses, including specific support to firms led by women so they could successfully promote their unique chocolate products at international trade fairs, helping them reach UK speciality importers. Finally, the UK has funded negotiating support to Ghana at a global level through its membership of the Africa, Caribbean and Pacific Group and logistical support to enable its officials and ministers to attend the WTO’s 13th Ministerial Conference in 2024.

Strategic Decision 2: Productive sectors

We have considered which sectors the Trade COE should prioritise for support in order to deliver its impact of more trade that is equitable, inclusive and sustainable. The considerations we have made include:
1. Inclusion: We know there are sectors where poorer people, including women, tend to work, for example agricultural production and ready-made garment manufacture and would give more weight to interventions that provide support in these sectors.
2. Trade in services as well as goods: We know that growth in services supports economic diversification and is associated with inclusive growth and yet LDCs represent less than 1% of global trade in services. Interventions would include support to developing country diversification from ‘traditional’ services such as tourism and telecommunications to professional, business and distribution services.
3. Impact and value: We would give weight to higher-value sectors (e.g. fruit and horticulture over commodity crops) and those requiring domestic value addition (e.g. processed food and drink products and light manufacturing). The focus would be on sectors where poorer countries have the capacity to compete effectively at the global level. We would also consider support in fast growing, “green” sectors such as goods with low amounts of embedded carbon emissions, sustainable goods that meet voluntary or official sustainability standards, green goods (e.g. goods used for solar panels and electric vehicles) and digitally delivered services.
4. Imports: We would consider support to sectors that are critical input-sectors for developing country exports.
5. Coherence: We would support sectors which are integral to achieving HMG’s wider Trade for Development objectives. This would include providing support to priority sectors for export to the UK under the DCTS and EPAs and priority sectors in the Developing Countries Imports Campaign.
6. Responsive: We would consider providing support in sectors of specific interest to Posts and partner government that want to buy-in to the Trade COE, in line with the agreed principles for centres of expertise.

We recognise that there are some sectors which constitute significant exports for many developing countries, such as extractives (oil, gas, coal), but have opted to not include these sectors in the scope of the Trade COE. This reflects the challenging political economy, low inclusive impact and negative climate impacts associated with these commodities and the limited opportunity for value addition and wider economic benefits from their increased trade.

In summary, the Trade COE will prioritise higher-value agriculture, ready-made garments, value added products and light manufacturing for goods. For trade in services the Trade CoE will remain entirely flexible, but could include tourism, telecommunications, environmental services and professional, business and distribution services. This targeted approach meets the criteria in the following ways:
1. COE approach: by targeting technical expertise towards these sectors the Trade COE will prioritise inclusive impact. By also offering a case-by-case response to other sectors, the Trade COE will retain the ability to be responsive to Posts’ needs. Other COEs are better placed to support other sectors, e.g. financial services through the Finance COE and more advanced manufacturing through the Green Inclusive Growth COE.
2. Impact and Inclusion: as set out above the sectors support the livelihoods of people who are economically excluded and marginalised.
3. Coherence: The prioritised list is coherent with HMG’s wider Trade for Development objectives. As the priority sectors of the Developing Countries Imports Campaign are defined, they will give an additional level of detail within these priority categories.
4. Value for money and risk: by introducing a sector focus we increase the programme expertise in the most impactful sectors, thereby driving the greatest value.

Strategic Decision 3: Geography
As a demand responsive programme, the Trade COE will be accessible to Posts in all developing countries for short- and long-term assignments on a buy-in basis. When considering which countries to prioritise for long term, centrally driven and funded interventions a number of factors will be considered:
1. Coherence: The Trade COE country prioritisation will be informed by and coordinated with that of other Centres of Expertise. The Trade COE will also prioritise countries where there is potential to increase the utilisation of the UK’s preferential trading arrangements (EPA, DCTS), which will support delivery of HMG’s Outcome Indicator on preference utilisation.
2. Responsiveness to demand from Posts: The Trade COE will prioritise Posts where demand is strong and work complements existing programmes and/or addresses gaps in programming.
3. Inclusion: Countries, such as Least Developed Countries, that are economically vulnerable (e.g. dependent on undiversified exports) and have high incidence of poverty and low economic performance that can be tackled through increased trade will be prioritised.
4. Political economy and risk: Countries that are sufficiently stable (not highly fragile states), avoiding contexts with extreme risk of corruption (Global Corruption Index) or with regimes that are hostile to private enterprise and making trade reforms.
5. We would consider how the country prioritisation that results from applying these criteria aligns with other development strategies, including the Commonwealth Strategy, Small Island Development States Strategy and Africa Strategy.
6. Other criteria that we will use include existing AFT programme footprint and post’s absorption capacity.

In summary, by applying the considerations above, our appraisal for this strategic decision leads us to an indicative long list of 24 priority countries for centrally driven interventions:
[note] WTO accession support will be prioritised based on momentum and poverty alleviation potential
1. Africa: Nigeria, Kenya, South Africa, Ghana, Tanzania, Uganda, Democratic Republic of Congo, Ethiopia, Rwanda, Sierra Leone, Senegal, Côte d’Ivoire, Mozambique, Madagascar, and Angola
2. South Asia: Bangladesh, Pakistan, Nepal, Sri Lanka
3. Indo-Pacific: Cambodia, Philippines, Fiji, Papua New Guinea
4. Caribbean: Jamaica
We have engaged directly with several of these countries, and indirectly through our Regional Trade for Development Advisers, to test the approach of the Trade COE. All have indicated the programme design is aligned with their needs and have indicated interest in the programme delivering in their country/region. During the programme mobilisation phase, the associated Trade COE Evidence and Innovation Programme will undertake an in-depth analytical project to further refine this indicative list down to 4-5 priority countries for centrally funded programme interventions. The Trade COE will allow all Posts to buy in technical assistance from the COE that is in line with the Trade COE’s scope and capacity constraints.
Strategic Decision 4: Delivery Approach

The feasible options we have considered for delivering a Trade COE that addresses the thematic priorities, points of entry, sector and country prioritisation discussed above are:
1. a commercial consortium with members that include a lead coordinating delivery partner and specialist institutions (e.g. think-tanks, non-governmental organisations), with expertise in trade and development;
2. a multilateral approach based on UK contributions to multilaterals like the World Bank Group;
3. a “portfolio approach” whereby FCDO programme staff lead and coordinate a portfolio of accountable grant arrangements and commercial contracts with a range of suppliers; and
4. a streamlined portfolio approach comprising a lead coordinating supplier with a subcontractor pool of experts, complemented by a collection of standalone agreements with designated experts on MOUs and accountable grant agreements, managed by a COE hub of programme funded roles.
5. do nothing.

Commercial consortium

This approach would involve a lead supplier working together with a small number of defined institutions with specialist expertise as part of a consortium. This approach could be taken for engagement with non-governmental and commercial organisations but oversight of support to any multilateral bodies (e.g. World Bank) would have to remain directly with FCDO.

The benefits of this approach include:
1. Coherence and synergies: a single consortium leader could bring together the planning, implementing and reporting of multiple partners and drive coherence and synergies across their interventions.
2. Strategic oversight and FCDO resources: FCDO programme teams would be free to focus on strategic oversight and integration with wider FCDO policy and programming objectives.
3. Flexible and responsive: Consortium could include a number of expert organisations that are flexibly used as interventions require.
4. Value for money: Suppliers would be appointed through a robust and competitive tendering process, ensuring the best possible VFM which evaluates technical and commercial elements.

Limitations of this approach include:
1. Expertise/impact: This approach reduces FCDO’s influence and control over the choice of delivery partners as sub-contractors are selected by the consortium leader. The expertise of some technical or specialist partners may not therefore be available under the Trade COE.
2. FCDO capacity development: This approach creates an additional contractual layer between FCDO programme teams and specialist sub-contractors which may reduce direct engagement and learning.
3. Programme management overheads: Although the use of a competitive tendering process will ensure the best fee rates, the lead supplier will incur programme management overheads relating to management of downstream partners.

Multilateral approach

Under this approach, delivery of Trade COE support would be provided through a range of multi-donor funds supporting global interventions. These could build on existing arrangements with the WTO’s Enhanced Integrated Framework (EIF) and the World Bank Group’s Trade Facilitation Facility and be expanded to include funds such as the IFC’s Advisory Services to provide technical assistance to businesses. Advantages of this approach are:
1. Programme resources: Requires less FCDO programme resource, compared to bilateral interventions.
2. Influence: Participation in the governance and decision-making of multi-donor funds creates the potential to influence the use of a larger pool of donor funds and to influence other donors’ priorities outside the fund itself.
3. Impact: Larger funds with multiple donors benefit from economies of scale and reach more countries.

Limitations include:
1. Less responsive to Posts: FCDO would effectively be delegating responsibility for key decisions (on what support is delivered and where our funds are spent) to multilaterals with limited ability to influence how funds respond to individual requests from Posts.
2. Speed: Typically multilateral funds take longer to mobilise from decisions to action, undermining the Trade COE’s focus on responsive delivery.
3. UK visibility: UK visibility for in-country interventions would be reduced.
4. Competition: no opportunity to influence costs through competition

Portfolio approach

FCDO’s centrally managed aid for trade portfolio currently comprises direct arrangements with several non-governmental organisations, commercial suppliers and multi-donor funds. The portfolio approach could be expanded to encompass partnerships with a range of suppliers in a technical assistance facility. This facility would be overseen by a hub of FCDO staff that would manage the planning, delivery and coordination of technical assistance across the portfolio.

Advantages of this approach include:
1. Expertise: Retaining control and flexibility in the selection of implementing partners enables FCDO to select the best experts for the Trade COE, irrespective of commercial and consortium arrangements.
2. Flexibility: It gives flexibility to select non-governmental organisations, commercial providers and multilateral funds where they are best placed to deliver the work of the Trade COE.
3. Capacity: Closer involvement of Senior Responsible Owners (SROs), Programme Responsible Owners (PROs) and programme funded staff with the implementers of the Trade COE’s work will increase FCDO capability and expertise in the areas of intervention and help to improve policy making and future programme design.

Limitations of this approach include:
1. Programme management: higher programme management resources are required to oversee a range of agreements with different implementation partners, rather than managing a single or fewer contractors under the consortium and multilateral approaches.
2. Coherence: there is a risk that multiple delivery arrangements managed by multiple programme managers will lead to a lack of coordination and coherence in the Trade COE’s activities.

Streamlined Portfolio approach

This approach has been added following endorsement of the previous business case by the Investment Committee in response to feedback from early market engagement exercises. It would combine delivery of the majority of in country technical assistance through a commercial consortium with a number of direct agreements and MOUs with specialist not for profit providers in other areas.

Advantages of this approach include:
1. Coherence: Having a single consortium responsible for coordinating and delivering most of the technical assistance in the COE and all in country technical assistance will improve the coherence and coordination between different providers of technical assistance. It will also reduce FCDO programme management requirements.
2. Expertise and Flexibility: FCDO would retain some control and flexibility in the selection of additional partners to deliver in specialist areas in addition to the technical assistance that is provided through the lead consortium
3. Flexibility: It provides flexibility to select non-governmental organisations, commercial providers and multilateral funds where they are best placed to deliver the work of the Trade COE.

Limitations of this approach include:
1. FCDO capacity development: The lead supplier approach creates an additional contractual layer between FCDO programme teams and sub-contractors which may reduce direct engagement and learning.
2. Programme management overheads: Although the use of a competitive tendering process will ensure the best fee rates, the lead supplier will incur programme management overheads relating to management of downstream partners. Furthermore, by continuing with some multiple direct grant agreements these could incur higher costs than via a commercial contract, and higher FCDO programme management resources will be required (although less than for the full portfolio approach).

Doing Nothing

If there were no centrally managed trade focused Centre of Expertise, there would still be aid for trade programmes funded by Posts, multilateral funds would continue to support developing countries but with fewer resources and there would continue to be trade elements in FCDO’s economic development portfolio. Bilateral programmes would not benefit from the availability of pre-selected experts in technical areas of trade, lower costs due to higher volume delivery or the support of the Trade COE in determining the most appropriate intervention based on experience and evidence from other programmes. We have dismissed this option because of ministerial priorities focused on trade and development, current expectations from Posts, including those with limited or no ODA budget, and the development results achieved through our current interventions.

A comparison of the different delivery options against the Trade COE selection criteria is shown below, indicating the preferred use of the Streamlined Portfolio delivery approach:

Table 1: Summary Appraisal of Delivery Options
Criteria	Commercial consortium	Multilateral	Portfolio	Streamlined Portfolio
COE approach	High: Responsive and flexible approach can be built into contract terms.	Medium: Partially responsive (subject to multilateral and other donor priorities). Low control over quality and choice of expertise.	High: Responsive and flexible. High control over quality and choice of expertise, including the use of UK expertise	High: Ability to directly appoint specialist providers combined with a competitively sourced consortium of technical experts
Impact on poverty	High: Positive impact likely but longer setup time	High: Positive impact likely. Multiplier effect from being part of a larger fund.	High: Positive impact likely. Shorter setup time and allows gradual construction of Technical Assistance Facility	High: Positive impact likely and early delivery possible through grant agreement components
Inclusion	High: with condition that consortium include inclusion expert.	High: core to partners’ strategic goals	High: delivery remains under direct control of development focused programme team	High: Combination of not for profits and commercial consortium incentivised to deliver inclusion
Coherence	High: Single implementing lead maximises integration and coherence	Low: low control over interventions, dependent on alignment with multilateral institution and other donor priorities.	Low: risk of fragmented delivery approach from multiple partners through separate agreements, overseen by FCDO staff	High: Reduced number of direct grant agreements and appointment of a single implementing lead will increase alignment and coherence.
Value for money	Medium: Day rates subject to competitive pressures but additional cost for managing sub-contractors	Medium: economies of scale from being part of a larger fund but no control over costs.	Medium: potentially lower cost in house delivery but no competitive pressure on day rates.	Medium: Competitive pressures will deliver the best value from the market but programme oversight will be paid for.
Risk	Medium: long delivery chain increases risk, reduces effectiveness	Medium: competing priorities of other donors and multilateral partners may prevail; performance management more difficult	Medium: requires ringfencing of FCDO resources to drive coherence across the portfolio; performance management of agreements more difficult than contracts	Medium: reduced risk of incoherence but increased risk from long delivery chains
Capacity building	Medium: SRO and PRO able to engage with all consortium members	Low: involvement in governance only and not day to day delivery	High: Strong involvement in technical delivery oversight and engagement HQ/Posts	Medium: Close involvement of FCDO in direct agreements and lead supplier management will build capacity

Summary of the Preferred Option

In conclusion, the preferred option is that the Trade COE will:
- Work with businesses, governments and at a global level, where appropriate at the same time in each country and where not, in close coordination with others working at the different points of entry.
- Target technical expertise to support exports in agriculture, ready-made garments, value-added products and light manufacturing, with a willingness to respond on a case-by-case basis in other goods and services sectors.
- Prioritise work in selected priority countries. The indicative long list for centrally funded work includes Nigeria, Kenya, South Africa, Ghana, Tanzania, Uganda, Democratic Republic of Congo, Ethiopia, Rwanda, Sierra Leone, Senegal, Côte d’Ivoire, Mozambique, Madagascar, Angola. Bangladesh, Pakistan, Nepal, Sri Lanka, Cambodia, Philippines, Fiji, Papua New Guinea and Jamaica. This list will be subject to further refinement during programme mobilisation and will be reduced to 4-5 priority countries.
- Be delivered through a “streamlined portfolio approach” overseen by the Trade COE Hub which combines a contract with the lead supplier for a consortium of technical assistance providers with a number of discrete agreements with specialist technical assistance providers in other areas.

Under the preferred option, the Trade COE will comprise:

1. Trade COE hub: the Hub will oversee delivery of the Trade COE and will comprise programme management staff (SRO, PROs) and FCDO facility management staff responsible for delivery and coherence of the Trade COE’s Technical Assistance Facility. Facility management staff will ensure:
  1. Strategic planning and direction of Trade COE activities, in line with the strategic direction set by the Trade COE Management Board and SRO.
  2. Engaging with Posts, presenting the Trade COE’s range of support areas, scoping intervention needs.
  3. Planning and overseeing the implementation of interventions by the lead supplier and not for profit organisations providing specialist expertise.
  4. Reporting the results and performance of the Trade COE as a whole.
  5. Liaising and coordinating with other COEs to ensure coherence across the portfolio.

The Trade COE Hub will also draw on dedicated adviser time in specialist areas (e.g. trade facilitation) and input from the network of Regional Trade for Development Advisers to plan and promote in country interventions (see Management Case).

Technical Assistance Facility: this facility will offer Posts the best technical expertise from a range of leading UK and global organisations. Delivery will be through a streamlined portfolio approach involving a lead commercial supplier supported by its consortium of subcontractors, and complemented by not-for-profit technical assistance providers to fill niche gaps which the lead supplier is unable to fill.

Evidence and Innovation Programme: the associated Trade COE Evidence and Innovation programme will pull together the learning and results from across the Trade COE alongside the wider evidence base on aid for trade. It will use this evidence to influence better policy making from the UK and other governments to drive inclusive, sustainable trade. It will also be the first point of contact for Posts through a ‘shop window’ of all the support available on trade to Posts, including from other central programmes like Trademark Africa.

Theory of change for preferred option

The diagram below sets out the programme level Theory of Change covering all the core elements of support and the intended outputs, outcome and impact. The draft logframe can be found in Annex D.
The desired long-term change of the combined Trade COE and the associated Trade COE Evidence and Innovation Programme (see separate business case) is an increase in equitable, inclusive, sustainable trade from developing countries (impact). This will be measured by export trade values and preference utilisation rates; jobs as employees or as business managers and owners, particularly for women and poorer people, in export sectors; and people with increased resilience to climate change. The theory of change for the Trade COE programme elements is discussed below.

Inputs to outputs

The principal inputs will be ODA finance used to fund technical assistance through MoUs, Accountable Grant Arrangements and commercial tenders. These resources will be supplemented by FCDO staff resources in the Trade COE Hub, in advisory roles and from Posts that opt to buy-in to the Trade COE. These inputs will be used to deliver technical assistance to enterprises and national governments, including their representatives in multilateral fora, primarily the WTO.

The expected outputs are:
1. Businesses have increased capacities and connections with buyers to market products that meet export demands and standards.
2. Business associations have more capacity and expertise to better support firms to export goods and services.
3. State institutions and agencies are more efficient, effective and transparent in operating standards systems, customs procedures, trade facilitation processes and rules in the regulatory environment.
4. National policy makers identify which areas to prioritise for reform of their trading environment.
5. Developing countries can meet the requirements to trade goods and services in more export markets (including the UK).
6. Developing countries progress to accession to the WTO and engage with global rules and the requirements of export markets (including the UK and other countries).

To track progress towards these outputs, we will monitor the number of:
1. businesses, SMEs, and women-owned businesses that have received training or support on standards or certification.
2. women-led businesses trained and supported with tools and information to improve their competitiveness.
3. business wins established with UK buyers (including for women business enterprises) as a result of participating in trade fairs.
4. business support organisations trained and/or supported with tools and information to improve their effectiveness.
5. training and capacity building events that reach a set quality criteria by business associations for their members (including data on participation of women business enterprises).
6. WTO Trade Facilitation Agreement (TFA) provisions implemented with UK support.
7. trade procedures and practices simplified, modernized and/or harmonized.
8. collaboration between domestic border agencies and the private sector that improve trade facilitation across borders (TF implementation score and UNCTAD’s reform tracker tool)
9. recommended procedures/firm-level policies/practices/standards/steps that were improved or eliminated.
10. national trade policy measures reviewed for inclusivity and climate change issues.
11. advisory missions to trade ministries on development issues and training activities on core technical issues and development issues (gender, pro-poor growth, social inclusion and climate change).
12. products that can be certified to international standards by national institutions (including products that meet green and climate standards).
13. interventions made by developing countries in their groupings or WTO on trade agreements and/or regulations.
14. WTO trade agreements/joint initiatives and/or trade regulations (e.g. CBAM requirements) implemented by developing countries.
15. training or compliance activities towards WTO accession.
16. new global trading agreements adopted and implemented that accommodate developing countries’ needs.
17. developing countries supported through advice and logistics support in global trading system legal disputes.

The most critical ‘Input to Output’ assumption is that there will be demand from Posts and partner governments for services from the Trade COE. Extensive engagement with Posts during the development of this business case has confirmed that significant demand for support already exists and our expectation is that this is likely to grow as the new approach becomes embedded.

Outputs to Outcomes

Over time, as these anticipated outputs materialise, the combined effects are expected to contribute to more products and services exported to more markets (including the UK) from developing countries; to more standards, customs processes and trade regulations that support exporting businesses in developing countries; and to more developing countries participating in more multilateral negotiations. To track progress towards these changes, we will measure:
1. Number of new products/services that are produced to export standard/expectations with UK support and the number of new markets to which these products/services are exported.
2. Number of new firms that are now able to export their products/services with UK support.
3. Time and financial cost of completing customs and export requirements in target countries/locations.
4. Number of government policies that are adopted and implemented that support inclusive export trade (disaggregated by inclusivity and climate change resilience).
5. Number of interventions that developing countries make during multilateral negotiations.
6. Number of pro-development and inclusive decisions made at MC14-18

The key output to outcome assumption is that our political economy analysis is sufficiently accurate to indicate whether governments and firms will act on the capabilities and opportunities they gain through our interventions. When supporting governments, prior to agreeing an intervention, we will look for credible indications of motivation e.g. plans to diversify exports, commitment from a central ministry (finance, presidential office etc) as well as line ministries (commerce, agriculture etc). When supporting firms, the mobilisation phase will include competitive application processes, as well as formal letters of commitment that set out roles and responsibilities, and some cost-sharing with firms (e.g. if an intervention includes participation in an international trade fair, participating companies would fund their visa and subsistence costs).

Outcome to impact

We anticipate that these outcomes will contribute to increased trade from developing countries that is equitable, inclusive and sustainable. To track progress, we will measure:
1. Value of target country export data disaggregated by sector including green and development friendly sectors
2. Proportion of world trade from (i) LDCs, and (ii) priority developing countries
3. Number of women or people in economically excluded groups employed in export sectors
4. Preference Utilisation Rates for (i) DCTS, and (ii) EPAs

The most critical ‘Outcome to Impact’ assumption is that the strength of developing country currencies continues at current relatively low levels compared to developed economies, making export earnings more attractive. Other assumptions relate to the sustained long term labour intensity of the sectors that are targeted and the impact of measures for improving individuals’ resilience to climate change.

Cost-Benefit Analysis

The strategic rationale for the interventions proposed, along with relevant evidence, has been set out earlier in the document. To undertake an extensive cost benefit analysis requires more certainty around both the relevant allocation of spending across the components of the programme and the exact nature of interventions in each area. The flexibility of allocations both across and within the areas are designed to be part of the model of the Centre of Expertise and will be subject to varying levels of demand from Posts.

Annex E summarises the cost benefit analysis of the programme by considering each point of entry in the theory of change in turn, identifying examples of potential or historic examples of the interventions proposed. Some of the key benefits identified include:
1. Trade promotion:
  1. a 10% increase in budgets for Export Promotion Organisation on average increases exports by 0.6% to 1%.
    [note] Export promotion agencies: Do they work?; Daniel Lederman, Marcelo Olarreaga, Lucy Payton, 2010
  2. $1 in technical assistance to SME firms on trade promotion in the UK Trade Partnerships Programme led to $5.7 in increased trade (although this ratio is an average and impacted by several highly successful interventions)
    [note] Evaluation of the UK Trade Partnerships programme, International Trade Centre, 2023
2. Standards:
  1. Implementing standards across an economy can increase company revenues by between 0.15% and 5%.
    [note] Economic Benefits of Standards; ISO (International Organization for Standardization), 2014
3. Trade facilitation
  1. Implementing the WTO’s Trade Facilitation Agreement can reduce trade costs for LDCs by 17%, and an aggregated global impact of 0.35-0.55% growth in GDP.
    [note] Trade Facilitation Indicators: The Potential Impact of Trade Facilitation on Developing Countries’ Trade; Moïsé and Sorescu, 2013
4. Global participation
  1. WTO accession is correlated with a 30% increase in size of economies 5 years after ascension.
    [note] WTO accession and growth: Tang and Wei Redux; Brotto and et al, 2021

The cost benefit analysis finds moderate evidence to support many of the major areas of activity of the Trade COE (e.g. export promotion, trade facilitation, help to meet quality standards and WTO accession). However, there are a number of areas with limited or weak evidence (e.g. implementing standards, improving WTO negotiation capacity) and we will prioritise analysis and evaluation to address these gaps through the Trade COE Evidence and Innovation programme.

Value for money statement for the preferred option

The Trade COE is designed to deliver a new value for money approach to FCDO Aid for Trade programming; improving efficiencies by providing a call-down service to Posts; strengthening the ability and the speed at which central and call-down programming can respond to opportunities and improving the internal evidence base and expertise on aid for trade.

It will enable Posts to access Aid for Trade expertise quickly and rigorously, improving the speed and quality of the advice and technical assistance provided. It will have the secondary impact of supporting and strengthening key in-country relationships as part of our diplomatic toolkit. Interventions will be prioritised that have the greatest assessed potential and development impact.

The overall approach to value for money will be finalised during the programme mobilisation phase and will be monitored and managed throughout its lifecycle. This approach will follow the 5 ‘E’s, and include the following:
1. Economy – the main programme costs will be measured and benchmarked to achieve greatest economy. This includes delivery partner costs for overheads, consultants and staff and travel and subsistence. We have benchmarked programme funded roles costs against similar positions in the private sector (Annex C) to ensure it presents value for money.
2. Efficiency – the programme will always aim to maximise its outputs for given inputs. We will do this by benchmarking against similar projects and maximising each projects value.
3. Effectiveness – the programme set up will aim to maximise results for given inputs and will monitor progress over time. This will also allow us to improve the internal evidence base on what works and feed this back into the design and prioritisation of future interventions.
4. Equity – the programme will integrate across all its projects the key aims of increasing equitable, inclusive, sustainable trade. This will include wherever possible disaggregating data by gender and other characteristics of exclusion such as ethnicity and geographical location (e.g. rural, remote) and integrating this into project design. We will also explore the use of equity focused KPIs with commercial partners and select not-for-profit partners with a strong commitment to equity.
5. Cost-Effectiveness – the programme will drive greater value from the current Aid for Trade portfolio, thereby boosting our efforts and will support increased utilisation of the UK’s trade preferences schemes (DCTS and EPAs). It will support the adoption of international standards (ISO) that are aligned with UK standards.

The assessment of value for money indicators will be supported by an Annual Review and by the monitoring and evaluation work of the Trade COE Evidence and Innovation programme which include a process evaluation at the end of year one and an impact and value for money evaluation in year four.

Table 2: Indicative Value for Money Indicators
Value for Money Element	Indicator
Economy	Overhead cost as a % of overall spend (and benchmarked against similar programmes) / Input costs per comparable unit measured (e.g. for similar types of technical assistance) / Variety of costs benchmarked to comparable programmes (consultant costs, travel and subsistence)
Efficiency	Unit cost of inputs compared to outputs (e.g. cost per business supported with export promotion, cost per additional product that can be assessed to global standards) / Speed of response to Posts call-down requests and level of satisfaction of Posts
Effectiveness	Unit cost of inputs compared to attributable outcomes (e.g. increased trade, increased number of women benefitting from increased trade) / Number of projects achieving intended outcomes.
Equity	Number of women-led businesses reached / Proportion of jobs supported that are performed by women
Cost-Effectiveness	Increased utilisation of the DCTS (Developing Countries Trading Scheme) and EPAs (Economic Partnership Agreements). / Increased levels of international trade in prioritised developing countries / Increase in number of countries adopting British standards or International Organization for Standardization (ISO) standards

## Commercial Case

The Appraisal Case concluded that a “streamlined portfolio” approach combining a lead technical assistance provider with separate smaller agreements for specialist expertise with not for profit and multilateral organisations where required was the most effective delivery approach. The Commercial Case sets out arrangements for implementing the preferred delivery option recommended in the Appraisal Case including a more detailed overview of the commercial aspects of each component and the approach to ensuring value for money.

As noted in the Strategic Case, the Trade COE will comprise three elements i) an internal FCDO Trade COE Hub with delivery oversight, ii) a Technical Assistance Facility comprising leading UK and global experts delivering activities under the Trade COE, and iii) an associated Trade COE Evidence and Innovation Programme, which will provide the evidence base for design and decisions (note this is a separate programme, already mobilised and so a detailed assessment will not be included in this section).

This Commercial Case focuses on the delivery of the Technical Assistance Facility and Trade COE Hub.

Technical Assistance Facility

The Technical Assistance Facility comprises i) in-country technical assistance to be delivered through a lead supplier appointed through a competitive procurement process, most likely via the Global Development Delivery (GDD) Framework: Trade and Economic Development Lot; and ii) specialist technical expertise to deliver additional and niche technical assistance where required.

This approach combines the efficiency of a single provider of central and in-country technical assistance with the flexibility to appoint a wide pool of specialist suppliers, irrespective of organisational model (profit/not-for-profit) and unrestricted by the limitations imposed by a single model. The final balance between the two sources of technical assistance will depend on available budget and demand from Posts and will prioritise value for money.

In-country Technical Assistance

Preferred delivery
The preferred delivery route for the technical assistance facility is to competitively source a supplier-led consortium. This consortium will bring together a range of technical assistance providers that together are able to meet the technical breadth of the COE as outlined in Annex B and to cover the COE country footprint as set out in paragraph 48. This role will involve conducting analysis of the technical assistance required in each country and developing proposals for project interventions. It involves assembling the right skills and expertise to deliver the project proposals from within the consortium, working closely with other partners (for example those with whom FCDO has other agreements in place) and managing the delivery of the agreed scope of work.

Rationale
The appointment of a consortium to deliver the majority of in country technical assistance will ensure coherence and coordination between project interventions. The supplier will define the scope of work required in a country, identify and appoint the best experts from within the consortium to deliver this work and then manage delivery and coordination between these experts and downstream partners. As well as coherence, this approach also maximises learning as the work across multiple countries is overseen and implemented by one team. Finally, a consortium is expected to be able to ensure strong in country presence to ensure project proposals are grounded in the local political economy and delivery includes national expertise and supports sustainable long-term outcomes.

The lead supplier will be required to establish a consortium of expert subcontractors to effectively respond to the needs of post, including, where there is merit, to engage experts with demonstrable expertise in delivering AFT programmes, even where they are not currently part of the GDD framework list of suppliers (GDD provides flexibility for lead suppliers to add to their list of subcontractors on a case-by-case basis).

In this way, the lead supplier approach is also suited to the COE requirement to be responsive to the needs of all developing country posts and offer a truly integrated single HMG vehicle for trade related technical assistance, with UK and global expertise.

The design team also considered the option of a portfolio approach without a lead supplier responsible for driving coherence and managing downstream partners. However, following market engagement, it was felt that the potential lead suppliers had the technical depth to effectively assess needs in each country and the contractual structures to efficiently allocate and manage the work of multiple consortium members across multiple geographies at the same time.

Sourcing strategy
A lead commercial supplier will be appointed through a competitive process, most probably under LOT 4 of the Global Development Delivery (GDD) Framework. Following two Early Market Engagement (EME) exercises, strong interest has been identified from the market to deliver the proposed technical assistance and to bring together technical assistance providers under a consortium approach. Specifically, prospective bidders indicated a willingness to bring niche providers of expertise into consortia as well as undertake some analysis and direct delivery themselves and to ensure strong in country presence and expertise. In order to maximise the involvement of specialist trade experts a further matchmaking exercise will be held in October to provide a platform for lead suppliers to meet other potential sub-contractors.

Funding Need
We estimate the cost of this component to be between £35m-£50m. The split of funding through the lead consortium and specialist not-for-profit providers will depend on available budget and demand from Posts and will prioritise value for money. About half of the spend through this route is expected to be funded centrally for long term projects with the remainder coming from posts on demand for long- and short-term projects.

Value for Money
The supplier will be required to maximise VfM and consider options for cost reduction, for example by sharing in-country resources and contacts with other Trade COE partners. Suppliers appointed through the GDD are already signed up to a fair and capped fee structure, which has been robustly tested, and a competitive tender exercise will drive the best possible value, ensuring vfm for the taxpayer.

The COE supports improved value for money for post, enabling them to buy into an established programme eliminating the need to create new programme structures to deliver interventions, saving money, time and human resources.

Economy	Will be achieved through a competitive approach to market which will drive down supplier costs, benchmarking of fees and costs, and an assessment of bids combining technical and commercial criteria to ensure the best overall solution. Procurement of the lead supplier through the GDD will ensure a fair and consistent fee structure that has already been established with suppliers with the GDD. The procurement will identify innovative proposals from the market and will compare the costs against the benefits of each proposal.
Efficiency	Will be achieved through management of the supplier, best practice in the contract model to incentivise delivery and impact including fee-linked KPIs. The programme team contract manager will complete the appropriate CMCP training. One lead supplier managing the majority of programming is also an efficient model vs multiple independent providers.
Effectiveness	Will be achieved through the programme theory of change, which demonstrates that trade related technical support can increase trade from developing countries that is equitable, inclusive and sustainable. The specific indicators to measure progress of the overall programme have been outlined in the logframe.
Equity	Will be achieved through contract KPIs which incentivise equity, a programme strategy which is focused on engaging and supporting economically marginalised and excluded groups, a Gender and Social Inclusion Strategy to guide implementation.
Cost-effectiveness	The supplier will be required to maximise VfM and consider options for cost reduction, for example by sharing in-country resources and contacts with other Trade COE partners.

Cost Drivers
The primary cost driver is expert fees. Additional cost drivers may include the costs of setting up country project offices (for the 4-5 larger centrally funded projects over 5 years), travel costs for contractors and some programme management and monitoring costs. Based on EME feedback from suppliers, we expect suppliers to incur programme management costs in the region of 10%-12% to cover the mobilisation and management of other consortium members, risk management and reporting. Some of these costs would normally be included in the programme costs of sub-contractors and there is a tension between minimising programme costs and including a suitably broad range of specialist providers in the consortium. We will structure the ITT to explicitly address this tension, for example by describing anticipated programme management structures and activities in the ToR and using KPIs to incentivise both lean programme management and the inclusion of expert technical assistance providers.

For projects requested by Posts, Posts will need to dedicate enough resource to engage with country government partners to understand their priorities, whilst procurement, management, in country delivery and additional supporting technical expertise is provided through the Trade COE. These costs should be far smaller than, for example, setting up and running programmes themselves but Posts will be more involved than they typically are in a traditional Centrally Managed Programme. The time required from staff at Post will be significantly lower than were they to manage such programme themselves.

Partner Requirements
The lead supplier, with support from their consortium members, will be required to have the following skills and knowledge:
1. Significant technical knowledge on trade and development to enable effective analysis and intervention design, including:
2. Aid for Trade programming, ODA requirements and the wider development context
3. Cross-cutting expertise on trade and gender, inclusivity and climate and trade
4. Knowledge of the rules-based international system
5. Knowledge of global supply chains and expertise in sectors of high-development impact
6. Technical expertise on trade policy and non-tariff barriers such as SPS, technical barriers to trade and trade facilitation.
7. In-country presence, knowledge and networks to inform delivery, including ability to assess the political economy
8. Proven ability to collaborate with other programmes and delivery partners, including with existing multilateral bodies
9. Ability to quickly respond to demand and adapt approaches where required.

Supplier Management
FCDO will manage the supplier through regular monitoring and reporting mechanisms, including review of the Key Performance Indicators. Based on feedback from the EME, suppliers are open to the inclusion of two types of KPIs which will directly link supplier performance to the milestones in the programme logframe:
1. 20% of fees would be dependent on meeting certain quality or output based KPIs (e.g. number of projects initiated, satisfaction and feedback responses from posts, quality and timeliness of reporting)
2. 10% of fees would be dependent on meeting certain outcome based KPIs (e.g. number of firms with new overseas trade contacts, number of new standards which governments can certify).

The Trade COE Lead Supplier will report to the Trade COE Manager who will be responsible for overseeing delivery of all aspects of the Trade COE, including all in-country scoping and delivery of projects, approving project proposals and leading engagement with Post. More detail on roles and responsibilities is provided in the Management Case.

Delivery Risks
The primary commercial risks relate to the procurement process, and the need to identify a capable supplier in a timely manner; the time to mobilise and establish the team and systems required to deliver the programme; and the performance of the contractor during implementation. There is also a risk that the consortium makeup may not include existing aid for trade delivery partners, with strong track record, that could continue to deliver effectively, as they are not part of the GDD framework. This will be mitigated by a planned matchmaking session between contractors and potential sub-contractors in October.

Another key risk relates to potential poor performance, any need to terminate the contract early and having to run an entirely new procurement process, which would set back the delivery significantly. To mitigate these risks, flexible and alternative delivery mechanisms will be explored in the sourcing strategy to ensure continuity. Delivery chain mapping and due diligence and monitoring will be used to manage delivery risk during implementation. Details of contract management arrangements will be provided in the sourcing strategy (post business case approval).

Specialist Expertise

Rationale
Despite the expected strong pool of lead contractors and potential consortium members, there will be novel and niche areas of technical assistance which can only be filled through direct agreements with not-for-profit partners that are uniquely placed to deliver the assistance. These include:
1. Initiatives that fulfil a unique role, such as the She Trades Outlook initiative, which provides benchmarking of national frameworks for measuring and increasing trade involving women.
2. Multi-donor and multilateral initiatives which enable FCDO to be a part of a bigger movement for change and can leverage the impact of a relatively small financial contributions, for example to the World Bank's Trade Facilitation Support Programme.
3. Initiatives where global institutions (e.g. World Customs Organisation) with other HMG departments (HMRC) are a delivery partner

Sourcing Strategy
We have strong, effective partnerships with several non-governmental organisations, multilateral and UN-linked bodies which we will consider partnering with in the Trade COE. Some of these organisations have been highlighted as potential partners based on several factors including:
1. Relevance and unique nature of technical expertise,
2. Geographic scope of service,
3. Track record of delivery,
4. Value for money and cost
5. Economies of scale
6. Opportunities for collaboration, influence and partnership with the wider donor community

Based on current experience and understanding of relevant technical assistance providers, the following funds and organisations may be engaged through separate standalone grant agreements:

Component	Possible Specialist Experts and Rationale
Addressing Barriers to Trade	World Customs Organisation: to provide support in areas related to the WTO Trade Facilitation Agreement. They offer unique expertise and experience in border management processes and procedures, and customs administration reform and bring regional specialists with a strong focus on digital trade. / Standards Trade and Development Facility: a WTO fund to provide SPS-related advice to developing countries. / World Bank’s Trade Facilitation Support Programme: a multi donor World Bank capacity building programme to help developing countries implement WTO Trade Facilitation Agreement.
Making Trade Happen	International Trade Centre (ITC): to support SheTrades Outlook and connection to SheTrades Hubs which are leading approaches to benchmarking gender equality in trade and coalition-building on women’s economic empowerment and trade. / British Chambers of Commerce (BCC): to collaborate with UK business chambers (including International Chambers) to maximise opportunities of business linkages and involvement in FCDO’s Import Promotion initiatives.
Global Trading System	Enhanced Integrated Framework a multi-donor WTO-led fund which supports LDCs to use trade as an engine for growth and develop their own capacity to utilise aid for trade. / The Advisory Centre for World Trade Organisation (WTO) Law (ACWL) for dedicated WTO law capacity building, advice and representation. / WTO Funds: such as the Global Trust Fund, which provides training to developing country WTO delegates or to provide logistical support to LDCs for participation in Ministerial Conferences.

Funding Need
We estimate that funds for these discrete agreements will be up between £10m and £25m. The split of funding through the lead consortium and specialist not-for-profit providers will depend on available budget and demand from Posts and will prioritise value for money. Posts will be able to supplement further the work of these not-for-profit delivery partners but as they are generally providing multi-country support (that cannot easily be ringfenced) and the central funding to each partner is relatively small, when this occurs it is unlikely to be delivered as part of the Trade COE programme.

Value for Money

Economy	This work is with not-for-profit organisations therefore profit will be eliminated. Benchmarking of fees, salaries and costs prior to signing agreements and consideration of how far direct procurement commercial principles can be applied to the arrangements will also help to ensure economy.
Efficiency	Assurance over efficiency will be provided through the track record of delivery partners, which is based on demonstrated capability to provide technical assistance on trade. Due diligence will also be carried out to ensure that efficiency is delivered while managing potential risks.
Effectiveness	Will be achieved through the programme theory of change, which is well evidenced and demonstrates that technical assistance to governments and businesses to build trade capacity leads to increased trade. The specific indicators to measure progress of the overall programme have been outlined in the Logframe.
Equity	Will be achieved through the selection of partners to ensure we work with those with a clear focus and mission on inclusive and sustainable economic development.
Cost-effectiveness	Explore opportunities to drive greater collaboration/efficiency from the organisation throughout the intervention, including collaboration across CoE delivery partners and the broader AFT Portfolio.

Cost Drivers
Cost drivers are likely to include the costs of sourcing of expertise and the logistical costs of supporting developing country WTO missions. Cost control measures will include a focus on working with organisations with national staff and field teams where this is more economical, benchmarking of day rates, and reducing reliance on international staff where possible.

Partner Requirements
Partner requirements will be determined by the nature of their appointment under specific components of the COE, and may include (but not limited to):

Addressing Barriers to Trade
1. Technical expertise in non-tariff trade barriers such as SPS and technical barriers to trade and understand the systems required to enable compliance with these requirements.
2. Trade facilitation and customs expertise encompassing all aspects of the WTO Trade Facilitation Agreement.
3. Coordination and collaboration with International Standards Organisation (ISO) and National Standards Bodies (NSBs).

Making Trade Happen
1. Understanding of challenges holding back SMEs, especially those led by women, to benefit from international trade. This may include continuation of UK engagement with global initiatives and earlier investments which require continuation to achieve desired impact.
2. Strong links with UK and international trade fairs to facilitate participation of businesses (those that are women-led in particular) from developing countries as part of the broader business network and matchmaking element of support.

Global Trading System
1. Specialist understanding of WTO law and rules, WTO dispute settlement mechanism, with provision of legal advice and training on these matters available to all WTO LDC and developing member countries.
2. Ability to support global provision of trade related technical support to LDCs and developing countries through “Funds” (e.g. those situated within Multilateral Development Banks), where the offerings are well established and working well with economies of scale, reach and experience that couldn't reasonably be duplicated.

For all components, delivery partners will need to further demonstrate their expertise in addressing cross-cutting issues, principally related to gender equality and climate change, in their delivery of trade for development interventions.

Supplier Management
Performance will be managed through targets set out in agreements, FCDO oversight of activities through steering committees and other governance arrangements, direct engagement with partners and monitoring of field activities. We will prioritise grant agreements rather than MOUs as these are more performance driven. Quarterly and annual reporting regimes will also be established by FCDO, in consultation with delivery partners.

Due diligence will be undertaken prior to entering into agreements, to ensure that partner organisation policies are meeting FCDO safeguarding, fiduciary and commercial requirements. This will include an assessment of procurement capability, where the organisation may be required to procure goods and services, to ensure alignment with FCDO's commercial requirements, guidelines and best practices.

KPIs will be set to incentivise the delivery of key outputs and, where possible, these will be linked to a percentage of total fees payable. All outputs will be specified in the Accountable Grant Arrangement to facilitate monitoring of progress and to ensure FCDO has a line of sight on progress against envisaged outcomes and has oversight of delivery risks. Risks will be managed according to the framework and approach set out in the Management Case and financial and commercial risks will be managed in line with the approach set out in the Financial Case.

Delivery Risks
There is a risk of diluted control and influence through support to multilateral funds if they are chosen (e.g. EIF). Multilateral funds allow for collaboration and economies of scale, but they do mean the UK is now one of many stakeholders and cannot direct funding exactly as they wish. We would mitigate this risk by being positively engaged in the governance of the funds we contribute to (for example, by sitting on advisory boards).

There is also a risk that the scope of direct agreements with not-for-profit providers grows and conflicts with the work of the lead supplier of in country technical assistance. Clear limitations on the scope of work and limited budgets along with careful management from the COE hub will help to mitigate this risk.

There is a risk that the number of direct agreements increases and the coordination and programme management of these agreements places an increased burden on FCDO and undermines the purpose of the lead supplier model for technical assistance. Limiting direct agreements to areas where suppliers have a unique offering and where the lead supplier is not well placed to engage will help to manage this risk.

FCDO COE Hub / Facility Management

The Trade COE Hub will be run and managed by a team of multidisciplined FCDO staff through a combination of in-sourced/programme funded roles, SRO, PROs, FCDO adviser time and support from the Regional Trade for Development Advisers (RTDAs). Initially, the COE Manager (Grade 7), Regional Leads for Africa and Asia (Grade 7), Delivery Manager (HEO), WTO Coordination lead (HEO) and part of the Monitoring and Learning lead (SEO) will be in-sourced and therefore within scope of this commercial appraisal (see Management Case for further information).

Rationale
Having both in-house experts and the expertise of outsourced service providers will allow us to respond to requests from Posts quickly and with the right level of expertise and organisational awareness. In-sourced experts will ensure terms of references for projects are well-designed and will ensure that interventions will have long term, sustainable results. In-sourced experts have a deeper understanding of the specific requirements of FCDO Posts and partners, leading to better outcomes and effectiveness. Over the long term, staff will gain experience and develop institutional knowledge that continues to benefit the overall capacity of the organisation.

Sourcing Strategy
TFD already has a pool of policy and programme staff with strong working relationships with posts, programme providers and RTDAs. It is envisaged that some existing staff members will transfer under "managed moves" into roles that correspond to their current roles (on level transfer) where the shift in responsibilities equates to less than 50% of their current role. Any gaps will then be filled through the usual resourcing process, working closely with HR.

Funding need
We estimate the cost of this component including all admin and programme funded roles is estimated to be £3m over 5 years. The programme funded roles estimated to cost £1.6m ODA over 5 years, equating to 3% of the overall COE ODA budget.

Value for Money
The value for money for the in-sourced roles is based on the comparison included in Annex C.

Cost Drivers
The main cost drivers in addition to salary and performance related in-year awards, will be associated overseas travel and accommodation for COE coordination, delivery, management and monitoring and evaluation.

Delivery Risks
The programme funded roles within the COE hub will use approximately £1.6m of programme funds over 5 years that otherwise would have been allocated for delivery of activities. These roles are only viable if the annual ODA allocation allows. We will demonstrate the value of these roles through effectiveness in their operations and ability to achieve results.

## Financial Case

Overview of costs

A budget of £XX million is proposed for the Trade COE over a 5-year period from FY 25/26 to 29/30. This budget represents an average annual spend of £12.6 million, equal to just 14% of FCDO's historic average annual spend on Aid for Trade programming focused on trade policy, regulation and facilitation.
[note] Estimate is informed by ICAI review of Aid for Trade, which reports a yearly fall in ODA spend on AFT, post COVID and ODA reduction, to approximately £90m.

The programme has been designed so that activities are scalable to allow the programme to adapt to lower and higher budget scenarios. The indicative budget of £63m assumes:
1. £36.2m of the budget will be centrally funded; and
2. £26.8m will be sourced from country/Post budgets to buy in support from the Trade COE over the five years. This amount is included here to provide sufficient headroom within the Business Case, on the expectation that funds will be transferred from post (in most cases) to the Trade COE.

Funding will be ‘programme’ spend (RDEL) and up to 20% of spend will be eligible to be classified as ICF, primarily on the basis that it improves the resilience, knowledge and adaptability to climate change of people in developing countries (ICF KPIs 1, 4, 5, 6, 9, 13, 14).

The spend profile (Figure 2) is shown below. It shows projected spend gradually increasing from £10.2m in year 1 (which represents a reduction of £2m when compared to current and recent historic allocation) to £15.6m in year 5 as the Trade COE becomes more established and demand from Posts grows.

Figure 2: Trade COE 5 Year Budget Profile
	25/26	26/27	27/28	28/29	29/30	Total
Central Funding	7.4	7.0	7.0	7.0	7.8	36.2
Post Buy-In	2.8	4.8	5.4	6.0	7.8	26.8
Total Business Case	10.2	11.8	12.4	13.0	15.6	63.0

From the total 5-year ODA budget it is estimated that £36.2m will be provided through central funding and £26.8m will be provided by Posts as they commission technical assistance through the Trade COE. The availability of funding is dependent on the outcome of the forthcoming Spending Review. The proportion of funding by Posts is expected to increase as the Trade COE becomes more firmly established as the go-to source of trade expertise. It is assumed that by year 5, half of Trade COE funding will come from Posts.  Even at this point, the Trade COE will account for less than a fifth of all FCDO Aid for Trade spending (based on historic spending) as it will focus on technical assistance (not trade related infrastructure or financing) and some legacy AFT programmes may still be in operation. A key indicator of success will be a steady increase in buy-in demand from Posts and Regional Departments.

This business case does not include non-ODA and will therefore only focus on support in ODA countries.

Cost drivers

The key cost drivers will be costs connected to delivering trade related technical assistance, policy advice, and capacity building support to drive export-led growth and poverty reduction in developing countries and will include:
1. Fee rates and expenses (travel and subsistence) for external delivery partners that will be benchmarked against suppliers that i) have previous experience of delivering successful Aid for Trade programmes, and ii) are appearing on Commercial Department’s approved list of GDD Framework suppliers.
2. FCDO staff resources and programme funded roles, travel and subsistence, and other miscellaneous delivery costs.

Service providers will be required to clearly justify their approach and associated costs irrespective of the various delivery routes adopted across the programme (i.e. contract/ Accountable Grant Agreement etc). This approach will involve providing a competitive incentive to propose the most cost-effective solution which delivers the outputs / outcomes / KPIs identified.  Furthermore, due to the uncertain level of Post funding, the contract will be flexibly structured with an “up to” maximum contract value that gives sufficient headroom for post buy-in. The ability of bidders to provide on demand expertise and to scale up in response to demand will be assessed during the tender process.

The programme will achieve economies of scale by identifying synergies across the Trade COE’s respective themes and by ensuring that delivery partners collaborate effectively. It will also seek to maximise ‘ripple effects’ by promoting the replication and amplification of successful and impactful activities into multiple geographies.

Cost by Trade COE Component

The component level budget is determined by factors including value for money (incorporating cost benefit analysis from the appraisal case), the timeframe for when activities will be delivered, and the need to create sufficient headroom for components to meet expected buy-in demand from Posts. This determination has also been informed by consultation with post, other programmes and Centres of Expertise (e.g. Green Inclusive Growth COE). The table below gives an indicative spend profile broken down by the three programme components.

Table 6: Budget by Programme Component (£ Estimates)

The allocation of funds between different components will be flexible, in part to respond to demand from Posts, and the scope of individual activities will be reviewed (and where necessary adjusted) on at least an annual basis to maximise impact through adapting to learning and any changing circumstances. Budget transfers will be agreed at the appropriate governance level and will be actioned on HERA in line with the budgeting timetable (i.e. at the beginning of the year and at the beginning of Q3). The programme will adhere to the appropriate PrOF guidelines when enacting country office requests to buy into Trade COE services.

Centrally funded programme activities will be delivered in 4-5 priority countries as outlined in Appraisal Case. The possible make up of project type, assuming that 80% of central funding is dedicated to in country technical assistance and 20% to discrete grant agreements is shown in the table below. These figures are estimates intended to illustrate the possible balance of activities across the portfolio, noting that there will need to be consideration for associated overheads costs of delivering the Trade COE.

Table 7: Illustrative Spend Profile by Project Type (Over 5 years)
Type of Project	Number of Projects	Estimated Average Cost	Indicative Total Cost
Short term responsive (<1 year) technical assistance for Posts e.g. provide technical and legal support to help a partner government negotiate on a WTO agreement	20
Long term responsive (>1 year) technical assistance for Posts e.g. analyse technical trade barriers (licenses, labelling, certifications) preventing a country exporting priority products to Europe, design and implement a programme to build government and business capacity to overcome these barriers.	10
Centrally driven long term technical assistance projects (>1 year) e.g. designing a coordinated programme in the cocoa sector to improve the quality infrastructure and national regulations and to support women owned chocolate and cocoa processing businesses to find new buyers and markets for their produce.	5

FCDO Staff Resources

The Trade COE Hub will be staffed by a mixture of in-house FCDO staff and in-sourced/programme funded roles as set out in the Management Case. The estimated cost of the staff resource will be £3m over the life of the programme including £1.6m for programme funded roles. These estimates may change following any revisions necessary upon appointment of the lead supplier and during the inception phase.

How Funds will be Disbursed

The implementing partners will be the direct recipients of the UK ODA funding. Depending on the final design of the programme and delivery model(s) adopted, payments to consortium partners and other third parties to procure goods and services may also be involved. FCDO will reserve the right to determine the level of funding for all third-party organisations, other government departments and consortia. In accordance with PrOF rules relating to the delivery of overseas aid programmes, delivery partner activities will take place outside the UK and are therefore outside the scope of UK VAT.

All financial agreements with delivery partners will require detailed backup documentation, such as receipts and financial statements, to support the invoices and a breakdown of costs and fee rates will also need to be included. MoU/Accountable Grant Arrangement funds will be distributed according to the agreement and based on performance against the results framework. This approach will ensure a full audit trail is kept on spend throughout the programme. FCDO will only make payments in Sterling (GBP) against invoices in arrears once it is satisfied that the delivery against duties obligations and responsibilities undertaken in any period are consistent with the value of the invoice.

Forecasting and Month-End Reporting

Annual activity work plans and budgets will be approved through the programme’s governance structures and through the Trade COE Management Board as set out in the Management Case. A quarterly reporting cycle will be adopted across all components of the programme detailing progress on programme implementation, expenditure reports and forecast updates. They will be reviewed by PRO/SROs and the Trade COE Management Board and used to assess the programme’s progress in achieving its targets. All delivery partners will be required to produce robust forecasts that meet FCDO’s standards. To facilitate strong financial planning, monthly forecast accuracy is expected to be within a 5% variance/tolerance against actuals. Forecasts will be challenged and reviewed regularly to ensure that this performance criterion is being met.

Payments will be released following receipt of accurate invoices and deliverables. It is not anticipated that the programme will purchase or acquire any assets, but if it does, they will be managed and disposed of in accordance with the PrOF guidelines. Any unspent funds will be returned to the FCDO Central Contingency budget within 18 months of programme closure in line with FCDO guidance. The programme will work with delivery partners to manage the potential uncertainty generated by unforeseen increases and decreases to the ODA budget.

Financial Risk and Fraud

The financial and fraud residual risks for the programme are considered to be minor. The SRO/PRO and COE Manager will contribute to the COE risk register that accurately captures and monitors fiduciary risk. A delivery chain risk map will be developed, and all programme delivery partners will undergo a due diligence review prior to being appointed. As part of the onboarding process suppliers will be required to set out how they intend to manage corruption and other risks – including conflict of interest issues. As in all programmes, a zero-tolerance approach will be taken to fraud and corruption. The programme will be subject to regular review as part of FCDO’s Annual Review process and may be independently reviewed by the Internal Audit Department.

Contracts and grants will be denominated in GBP so the delivery partners will carry the risk of exchange rate fluctuations. FCDO will work with delivery partners to manage long-term variations on the value of sterling, for example through modifying some deliverables or seeking greater value for money savings.
## Management Case

Management and Oversight

The Trade COE will be primarily managed through the Trade COE Hub. This hub will bring together FCDO resources responsible for managing and delivering this programme and will include roles from the Trade COE Evidence and Innovation programme. This combined single unit will include staff responsible for covering two broad sets of responsibilities:

Technical Facility Management, coordination and oversight:
1. Strategic planning and direction of Trade COE activities, in line with the strategic direction set by the Trade COE Management Board and SRO.
2. Engaging with Posts, presenting the Trade COE’s range of support areas and scoping intervention needs with Posts.
3. Planning and overseeing the implementation of interventions which may draw together multiple delivery partners in a country or region.
4. Reporting the results and performance of the Trade COE.
5. Managing the governance (incl. programme management board, financial management, risk management, contract management, Hub resourcing) arrangements for the Trade COE

Programme Management:
  1. Formal roles, responsibility and accountability for programme delivery as set out in the PrOF Appointment Letters issued by the Deputy Director with overall Delegated Authority for the Trade COE.

The roles in the Trade COE Hub are expected to comprise:

Table 8: Trade COE Hub
Roles	Grade, FTE Funding Type		Role Description
Technical Assistance Facility Management
Trade COE Manager		G7, 1 FTE / Admin funded	UK based / Strategic planning and reporting on all Trade COE activities. / Delivery oversight, quality control and coordination of all activities / Reports to SRO and Trade COE Programme Management Board / Engagement and liaison with other Economic Development COEs / Governance, risk and financial management / This role will work across all COE Hub roles and contribute to SRO and PRO responsibilities on programme governance, risk, finance and commercial management elements.
Africa and Asia Regional Leads		G7, 2 FTE / Programme funded	UK based / Engagement with posts to promote COE and scope out opportunities / Delivery oversight and coordination of technical assistance activities in individual countries and regions, in collaboration with RTDAs. / Coordination with other COE activity in the region, regional departments / Report to COE Manager.
Programme Delivery Manager		HEO, 1 FTE / Programme Funded	UK based delivery focused role / Support Africa and Asia Regional Leads / Working level coordination on delivery of approved interventions through supplier, providing PM assistance to post, monitoring and progress tracking and reporting. / Contributing to COE PRO on finance forecasting, payments, risks management; and inputting to MREL / Report to Regional Leads
WTO Coordinator		HEO / 1 FTE / Programme funded	UK based with frequent travel to WTO in Geneva / Coordination of Trade COE aid for trade with wider WTO files, including accession, negotiation support, (LDC, ACP, PIFs groups), ensuring technical assistance alignment with Trade COE objectives, in consultation with UKMIS and HQ, servicing AFT and other relevant committees and briefing UK reps (e.g. TFD DD, EIF Board Member). / Reports to Global Trading Systems team lead in Trade for Development
Monitoring, Reporting, Evaluation, and Learning lead		SEO, 0.5 FTE / Programme funded	Establish and run Trade COE’s MREL activities. / Support ongoing engagement with the MREL commercial supplier. / *This role will be funded 50/50 between the Trade COE and the Trade COE Evidence and Innovation Programmes*
Trade Policy/Technical Adviser input		G7 / 1.2 FTE (x3 40%) / Admin funded	Provide additional technical expertise to Trade COE in areas of Standards/Trade facilitation; Inclusion/WEE; Global system; Climate and environment. / Support Trade COE’s delivery and alignment with wider HMG inclusive policy objectives and commitments, including climate objectives. / Costs covered by TFD admin budget
Regional Trade for Development Advisers		G7 / 1.2 FTE (x6 20%) / Admin funded	Provide additional Post engagement and promotion of the Trade COE offer, working closely with the COE Regional Leads. / Costs covered by TFD admin budget
Programme Management
Senior Responsible Owner (SRO), Trade COE [and Team Leader]	G6, 0.5 FTE / Admin funded		Strategic oversight of Trade COE / Accountable for overall programme compliance with FCDO ODA rules and policies and Trade COE governance processes. / Lead relationships with partners and ensure delivery of HMG priorities, including on economic growth, transformation, and inclusion. / Lead Trade COE’s coordination with other COE programmes and integration within other HMG activities. / Ensure Trade COE has sufficient human resources and risks are appropriately managed and escalated with necessary. / This is a 50/50 split of the Team leader role covering COE SRO accountabilities and other Team Leadership responsibilities.
Senior Responsible Owner (SRO), Evidence and Innovation Programme	G7, 0.5 FTE / Admin Funded		SRO responsibilities as set out in the SRO appointment letter. / *This role relates to the Trade COE Evidence and Innovation Programmes and is shown here for completeness. Cost of this role is covered by TFD Admin budget, included here for completion*.
Programme Responsible Owner (PRO), Trade COE	SEO, 1 FTE / Admin Funded		Programme management lead as set out in the PrOF appointment letter, covering the formal PRO duties including programme compliance, financial management and forecasting, risk management, commercial leadership, annual reviews, and reporting. / This role will work closely with the HEO programme manager and HEO Programme Delivery Manager to maintain compliance and tracker performance, including financial forecasting and spend on AMP and HERA.
Programme Manager Trade COE	HEO, 1 FTE / Admin Funded		In support of the SEO PRO managing the programme cycle as set out in the PrOF appointment letter / Programme compliance, financial management and forecasting, risk management, commercial leadership, annual reviews, and reporting. / This role will work closely with the HEO Programme Delivery Manager to maintain compliance and tracker performance, including financial forecasting and spend on AMP and HERA
Programme Responsible Owner (PRO), Evidence and Innovation Programme	HEO, 0.5 FTE / Admin Funded		PRO responsibilities as et out in the PRO appointment letter. / *This role relates to the Trade COE Evidence and Innovation Programmes and is shown here for completeness. Cost of this role is covered by TFD Admin budget, included here for completion.
Programme Officer	EO, 1 FTE / Admin funded		Programme administration support across the Trade COE. / *This role is shared with Trade COE Evidence and Innovation Programme*

The formal roles above will be complemented by support from several central FCDO roles as needed throughout the programme cycle (e.g. Finance and Commercial Business Partners, specialist private sector and climate and environment advisers amongst others).

Spending Review 2022-25 enabled FCDO to create In-House Programme Implementation Roles (Programme Funded roles), where delivery of elements of programmes using FCDO’s own staff offers better outcomes and value for money when compared to outsourced alternatives. Several programme funded roles across Trade COE and Trade COE Evidence and Innovation Programmes have been incorporated into the delivery of the Trade COE in order to ensure dedicated, specialist resources are providing consistent and coherent oversight of all delivery partners. The exact number of programme funded roles and their specific responsibilities will be finalised once a lead supplier has been appointed.

 Delivery Process

As set out in the Strategic Case, the Trade COE is expected to provide short and long-term responsive technical assistance to Posts, along with strategic long term, problem driven, centrally funded technical assistance projects which will be jointly designed with Posts/region.

The “customer journey” and delivery process for the Trade COE’s responsive work for Posts is shown in the diagram below. In summary, post would collaborate with COE regional coordinators to scope out needs and submit a formal request for assistance (buy-in or centrally funded) through the shop front (new COE website). The request would be assessed and approved/rejected before formalising, moving to implementation and review/closure.

Figure 3: Delivery Process

The phases of the customer journey shown above involve:

Plan
COE Regional Leads will work with the Lead Supplier in collaboration with post, RTDAs and other stakeholders to scope out technical assistance needs and develop a package of support comprising elements from across the Trade COE components (the proposal) to be considered by the COE SRO/Board. This will ensure that strategic and systematic analysis is conducted of the context for change and the role of trade-related measures within it.

Where the request is potentially relevant for multiple COEs, the Trade COE Manager will ensure other COEs are involved in the assessment of needs as outlined in Annex G.
Post along with the Lead Supplier and COE Regional Leads (and other COEs where relevant) will use the initial assessment to jointly agree a Concept Note for the scope of work required.

A similar approach will be applied when buy-in support is requested. The degree to which the scoping is done will depend on several factors, including the level of funding available with the request. Post would navigate the COE offer and gain access to useful resources through the Trade COE website, which will act as the shopfront.

As the COE matures and is seen as a default option for delivering technical assistance, post would collaborate with the COE during the county business planning process to identify needs, with input from the E&I programme. This would enable a more holistic approach to the issues holding back trade, considering the full resources available to tackle the challenges, through COEs and beyond, and in the case of limited resources, agree the prioritisation of interventions. Early planning and agreement with post would also reduce administrative burden, for example, successful bids from Post in the resource allocation round could be transferred directly to the COE eliminating the need for it first to be transferred to post.

Approve
The approval of the Concept Note will be negotiated by the COE Manager and given by the SRO in accordance with the strategic priorities set by the management board and the SRO and in consultation with the Regional Leads. Approval of project over a certain value (e.g. £0.5m) will remain with the management board. The Concept Note assessment will be based on the criteria set out in the Appraisal Case and will also consider value for money, ease of delivery in country and level of funding being made available.

Mobilise
Before implementation can commence, the COE Manager will work with Post to finalise and agree a Terms of Reference (TOR) with identified delivery partner(s) confirming the responsibilities of the supplier and Post.  The COE Manager will agree a Service Level Agreement (SLA) which defines the roles, responsibilities and division of accountabilities between the Trade COE and Post, including on issues such as risk ownership and management, how to deconflict if issues arise, stakeholder management and results attribution.

The Trade COE SRO and PRO own and manage the relationship and agreements (contracts, MoUs) with suppliers.  Accountability, control, and schedule of disbursement of funds will be agreed in the TOR and in adherence to the PrOF on post buy-in approaches (covering the four possible options for buy-in).

Delivery of in-country projects will be overseen by the COE Manager and the Regional Leads for Africa and Asia with support from the Post to maximise coordination of Trade COE activities and coherence with other FCDO work in the country.

Evaluate
On conclusion of the activity, the Trade COE MREL lead will work with the project leads to complete a Programme Completion Review assigning an overall score to be agreed by Post and signed off by SRO.  For longer term interventions exceeding a year, Annual Reviews will be conducted at the 12 month point to monitor and report on progress followed by a Programme Completion Review at completion.

The closure review process will include feedback from Post and Supplier (and beneficiary where appropriate) to inform future process improvements and feed into supplier KPIs where relevant.

The COE PRO will input the results of the project into the AFT data tool (a live database of AFT related information developed through the Evidence and Innovation Programme) to build on the investment and impact evidence of our AFT interventions.  This will inform overall Trade COE evaluations as well as other forms of reporting (e.g. WTO Global Review, ICAI).  The MREL Lead will produce a short communications piece on the project to share learning as appropriate.

 Governance

The governance framework for the Trade COE is shown below:

Figure 4: Governance Framework

The key roles in the governance framework are as follows:
Component	Description
Economic Development and Partnerships Steering Board	This DG chaired Board will oversee delivery by all 5 economic development COEs. It will ensure coherence and coordination across the full range of strategies to which the UK Centres will contribute. The board will also make overall resource allocation decisions across the economic development COEs.
Head of Trade for Development	The Deputy Director for Trade for Development will have overall accountability for the Trade COE to the Economic Development and Partnerships Steering Board. The role will include: / Decision-making: on resource allocation at the programme and component level, material changes to COE (within delegated authority), singing off on strategic long-term interventions over £0.5m with the Management Board and independent evaluations. / Direction: Setting strategic direction for the COE in consultation with the SRO and approving adjustments to workplans. / Risk and compliance: overall risk ownership including escalation of risk outside of COE appetite to Economic Development and Partnerships steering Board; and oversight of implementation of ICAI recommendations. / Senior level engagement: keeping xHMG counterparts (DD level and above) informed.
Trade COE Management Board	The Trade COE Management Board will be chaired by the Deputy Director of Trade for Development. The Board will comprise representation from a wide range of stakeholders from across HMG, with the purpose of keeping them informed, managing relationships, contributing to decisions and delivery; as well as fostering a shared ownership of the Trade COE. The board will meet quarterly with the broad remit of maintaining oversight of the Trade COE, its development, delivery (and adjustments to log frames and KPIs) and future evolution. It will also make recommendations to the chairperson for decisions, based on sound evidence and options appraisal. / Permanent Board members will include: / Trade COE Manager, SRO, Trade COE Evidence and Innovation Programme SRO, and MREL Lead. / xHMG Trade for Development leads from DBT, HMRC / Economic Development COEs leads (for coordination and coherence) / Regional Trade and Development Advisers / Head of the WTO Aid for Trade team (based in UK Mission in Geneva) / Head of the Analysis and Evidence Team, Trade for Development / A representation from Trademark Africa (TMA) / Ad hoc membership (where appropriate) will include COE thematic leads, FCDO Regional Trade teams for Africa and Asia and Sector specific representation from other government Departments and Arm’s-length bodies (Defra, HMT, Food Standards Agency).
SRO	In addition to completing formal SRO responsibilities for all aspects of the Trade COE, the SRO will also have formal responsibility for approving all proposed in country interventions up to £0.5m and will participate in approval of larger interventions as a member of the Management Board.
Trade COE Manager	The COE Manager will lead the trade COE hub and cover: / Strategic planning and direction of Trade COE activities, in line with the strategic direction set by the Trade COE Management Board and SRO. / Planning and overseeing the implementation of centrally funded interventions which draw together multiple delivery partners in a country or region. / Approval of responsive technical assistance proposals for Post, in line with the strategic direction set by the SRO and the Management Board / Reporting the results and performance of the Trade COE as a whole, linking in with the work on evidence and learning planned by the Trade COE Evidence and Innovation programme. / Supporting engagement with Posts that will be led primarily by the Regional Leads / Facilitating deep dives and sharing learning across the Trade COE
Post	Post will play a key role in the governance structure as part of the feedback, challenge and scrutiny function, along with other stakeholders as illustrated in the diagram. Post will have firsthand experience of collaborating with COE to deliver their interventions, share associated risks, and be accountable for spend (to a degree) to their local stakeholders, and so their contribution to the governance of the COE will be critical and invaluable. They will also contribute to the ongoing improvements to the COE.

Risk
Risk management is a critical element of the COE governance framework. It will be owned by the SRO and managed by the COE Hub, ensuring periodic reviews, implementation of mitigation plans, and escalation and reporting requirements.

The overall risk rating for the Trade COE is moderate and within the FDCO organisational appetite as the nature of interventions and geographies are not considered novel or contentious. The main risks and mitigation plans for the Trade COE are at Annex F. All risks will be uploaded to the Aid Management Platform (AMP) and online reviews will be implemented as per the PrOF guidance.

Risk Appetite Statement

We will retain a receptive appetite for Strategy and context, and Policy and Programme Delivery risks, in line with FCDO risk appetite. The Evidence and Innovation programme will inform strategic planning, support assessment of demand and ensure interventions are aligned to Trade COE objectives as outlined in the TOC. Flexibility in the design of interventions and relationships with partners will help mitigate unpredictability and uncertainty in regards needs and resource availability.

We will retain a cautious appetite for People risk, in line with FCDO risk appetite. The Trade COE will continue to ensure a pipeline of suitably experienced people with the right level of professional expertise are engaged to manage and deliver Trade COE objectives. Pressure on administrative funding poses risks to the longer-term viability and evolution of the Trade COE. This will be mitigated, to a degree, by using programme funded roles where appropriate, flexible, and agile programming, and smart and efficient ways of working.

We will retain a cautious appetite for Safeguarding, Financial and Fiduciary and Reputational risks, in line with FCDO risk appetite. In terms of minimising these risks, and in line with good practice: the agreements with suppliers (procurement contracts and MOUs) will be agreed upon completion of Due Diligence Assessments and on the basis of payment in arrears against defined outputs and include break clauses; supplier bids will be scored on the basis of sound safeguarding/do no harm policies and procedures; and the Trade COE delivery process and governance framework will be reviewed periodically to ensure water tight approaches to safeguard against these risks.

Results framework
The Trade COE is designed to be responsive to demand from Posts with interventions that are problem-driven, owned by Posts and co-designed for country and context in line with Country Business Plans. Although it is not possible to be specific about what will be delivered and where at this stage as a result, it is possible to articulate the type of results that will be delivered based on experience, demand identified during Post consultation, and the proposed approach. These have been set out in the Strategic Case and the indicative Logical Framework that illustrates the types of indicators and results that will be sought (see Annex D).

In addition to the strategic programme objectives and anticipated results, response time and quality of delivery will be important success factors for the Trade COE. Another measure of success will be the gradual increase in demand for Trade COE support and increasing ODA share that is from Post.

The Trade COE Evidence and Innovation Programme is the primary provider of independent MREL support for the Trade COE. It will lead the design of a final results framework over the course of FY24/25 that is aligned to the Trade COE theory of change, in accordance with good practice and the Logical Framework PrOF Guide. The programme funded MREL lead will be primarily responsible for ensuring coherence between the monitoring, learning and reporting requirements on the Trade COE and the Trade COE Evidence and Innovation Programme.
Monitoring
Programme monitoring activities will be the responsibility of the PRO with oversight and coordination from the MREL lead and independent MREL support, working with Post and suppliers to organise and implement based on a structure that is consistently applied across the Trade COE. Monitoring exercises will be undertaken at contract/agreement/component/project and programme levels. These may include a mix of in-country and virtual/hybrid monitoring exercises. They will be documented, fed into the AFT data tool and used to inform reviews, learning and sharing. Monitoring exercises should ideally take place twice a year.

Reporting
The MREL lead will work across the COE to produce reports and case study resources to share with stakeholders throughout the life of the programme. These will have the aim of satisfying mandatory requirements to report on programmes (including via DevTracker), inform decisions through the governance structure, share learning, raise awareness and amplify achievements.

Evaluation
The Trade COE will follow the formal PrOF requirements for Annual Reviews and Programme Completion Reviews and the Evidence and Innovation Programme will facilitate Independent Reviews at key milestones during the life of the programme. Evaluations will focus on the Trade COE’s impact, performance, and its processes at an overall programme, Intervention and Contract/Agreement with supplier levels. Independent evaluations will include:
1. An Independent Process Evaluation towards the end of year one, which should provide valuable, early feedback on how the new Trade COE is operating enabling some initial lessons learned to be integrated.
2. An Independent and In-Depth Value for Money and Impact Evaluation during year 4. This will provide valuable insights into how effective the programme has been and integrate into design of next phase of the COE. The Evidence and Innovation Programme will organise these evaluations. The impact evaluation will assess the impact of the COE on poverty reduction (poor people), on women and on marginalised groups. This will support implementation of the ICAI recommendation to demonstrate the evidence linking trade to poverty reduction which is the primary aim of ODA spend. The findings of this evaluation will inform the payment of fees based on outcome-focused KPIs.

Learning
The monitoring and evaluation of the Trade COE will provide valuable intelligence for the Trade COE Evidence and Innovation Programme to use in its dissemination and communication activities and to inform FCDO policy making and future interventions. Learning from lessons is a critical part of the MREL process, as it helps to inform decisions around short- and long-term adjustments and development of the programme. It also addresses ICAI recommendation to prioritise learning and share lessons more widely in support of organisational developments.

Exit Strategies

The Trade COE will manage exits from interventions and agreements with suppliers through the established frameworks set out in the PrOF guide, detailed in the agreement documentation with suppliers and through the appropriate approval levels set out in the Trade COE governance framework. In exceptional circumstances where agreements with suppliers or interventions at post need to be exited earlier than scheduled, consideration will be given to risks around FCDO and COE reputation, risk of cliff-edge to beneficiaries, sustainability of legacy interventions and impact on suppliers.

Amending the Business Case
Business case extensions and amendments will be implemented in accordance with PrOF rules.

Annex A: Problems for Increasing Developing Country Trade

Problem 1: Addressing Trade Barriers

Tariff barriers are at a historic low thanks to wider coverage of in Free Trade Agreements and to preferential trading arrangements like the DCTS which developed countries put in place for developing countries. However, a number of factors limit the benefit of these more liberal trading conditions:
    1. Non-tariff measures: Non-tariff measures include trade barriers such as red tape and customs procedures, technical barriers to trade (TBTs, for example, product certificates, labelling regulations), sanitary and phytosanitary measures (SPS, for example standards on pesticide residues), procurement restrictions and local content requirements. Non-tariff measures are estimated to impact 96% of world trade and exporters from LDCs lose an estimated $23 billion a year (15% of their exports) because they are unable to comply with non-tariff measures.

       International standards play a necessary and largely beneficial role in facilitating trade by helping to ensure that goods and services meet important safety, health, environmental and consumer expectations. As well as facilitating market access, the use of standards can serve as a catalyst for productivity gains, stimulating the upgrading and modernising of supply chains, and resulting in increased economic growth. Standards help to build market confidence in the quality of a product, acting as a useful tool to generate consumer interest and trust, as well as encouraging investment.

       But non-tariff barriers relating specifically to standards, regulations and TBTs are particularly challenging for developing countries which do not have the facilities to test and certify goods to the standard required by developed country markets. TBTs and SPS measures affect about 65% and 20% of world trade respectively, but SPS measures tend to be used more intensively – an average of six SPS measures per product compared to two TBTs. Small firms are more adversely impacted by non-tariff barriers with business surveys showing that 51% of exporting firms with under 50 employees are affected, rising to about 60% in agri-food sectors 34.
      [note] Impact of Non-tariff measures and trade regulations on Global Trade UNCTAD
      [note] Tackling "non-tariff measures", the new frontier for global trade UNCTAD
      [note] Increasing the Ability to Comply with Standards or Regulations to Improve Trade and Investment. Brighton: Institute of Development Studies Quak, E. 2019
      [note] Firm-level surveys in developing economies found that certification to the international standard ISO 9000 achieved average productivity gains between 2.4% and 17.6% for three Central American economies, 1% for four Southeast Asian Economies, and 4.5% in China. In the UK, standards reform contributed to 13% of growth in labour productivity. Source: World Bank.
      [note] Standards Matter to Consumers BSI Group

    1. Sustainability and environmental requirements: some developing countries and sectors face difficulties in complying with sustainability and environmental requirements of developed countries. There has been a proliferation of competing standards and regulations in this space, for example, aiming to reduce deforestation, greenhouse gas emissions or use of environmentally harmful materials in textile production. Most recently the UK government announced its plan to develop voluntary product standards to differentiate between products of a higher and lower carbon content and the EU have recently agreed a new regulation to outlaw import of products that are connected to deforestation. This is an area of increasing attention as developed countries seek to address trades impact on the environment through measures such as the EU and UK’s proposed Carbon Border Adjustment Mechanisms.
      [note] For example, the ISO has produced more than 600 environment-related standards, including those that aim to open world markets to clean energy and energy-efficient technologies and support climate change adaptation and mitigation schemes.
      [note] Framework for the Voluntary Sustainability Standards (VSS) Assessment Toolkit UNCTAD
      [note] Carbon Conscious - UK announces plan to introduce UK CBAM by 2027, Julie Vaughan, Yves Melin, Wim Vandenberghe, Jin Woo Kim (reedsmith.com)
      [note] Parliament adopts new law to fight global deforestation European Parliament

    1. Customs processes and procedures: Reducing physical inspection of shipments at customs increases the overall value of trade, particularly for agricultural and manufactured goods: a one-day delay in goods reaching their destination is equivalent to reducing a country’s overall trade by 1%. Even within the EU, where customs processes are among the most facilitative, customs controls add around 2% to the cost to trade and worldwide a 1% reduction in customs compliance costs could generate $40 billion USD in savings. The cost of trade in developing countries is estimated to be 1.8 times higher, on average, than in developed countries. WTO signatories of the Trade Facilitation Agreement (2013) have agreed that public bodies, such as customs agencies, need to simplify, modernise and harmonise their export and import processes in line with international good practices and national governments need to align with agreed global expectations.
      [note] Trade facilitation and firms exports: Evidence from customs data ScienceDirect
      [note] An Overview of Customs Reforms to Facilitate Trade United States International Trade Commission
      [note] Trade facilitation and firms exports: Evidence from customs data ScienceDirect
      [note] An Overview of Customs Reforms to Facilitate Trade United State International Trade Commission
    2. Corruption and the Political Economy: The World Bank estimates that corruption contributes to about US$2 billion each year in lost revenue collection at customs borders. The OECD suggests that corruption is one of the costliest trade barriers and improving integrity across customs organisations can reduce trade costs by 1.1%. Political economy considerations can make trade liberalisation challenging. For example, domestic industries benefit from protectionist policies, some individuals benefit from rent-seeking behaviours, leading to a lack of coordination by or empowerment of key agencies in government.
      [note] Corruption is a barrier to trade Hinrich Foundation
      [note] Global Trade Without Corruption: Fighting the Hidden Tariff OECD

Problem 2: Competing in Global Markets and “Making Trade Happen”

Firms in developing countries struggle to produce competitive products that meet the market expectations of businesses and consumers in developed countries. Buyers may face issues relating to quality, reliability, scalability, responsiveness to UK regulations, credit terms, currency fluctuations which may limit UK firms’ sourcing from developing countries. Specific challenges include:

    1. Information failure leading to inadequate knowledge: Firms hoping to enter new markets face significant information constraints creating uncertainty about the profitability of moving towards export markets. For many firms, the costs of collecting technical information on tariff barriers, customs procedures and regulatory requirements in foreign markets can be prohibitively high. These costs can mean firms are unable to sell beyond a localised market. There is little incentive for firms to share any information they gather about export opportunities and market access, which would enable potential competitors to benefit without bearing the costs. When information barriers are overcome, high quality small firms grow and become more productive and consumer prices fall. Previous scoping work – consulting over 120 stakeholders from businesses, trade association and governments in Kenya, Ghana, Pakistan and the UK – corroborates these findings.
      [note] Information Frictions in Trade Allen 2014 and Information, Demand and the Growth of Firms: Evidence from a Natural Experiment in India Jensen and Nolan 2017
      [note] Information, Demand and the Growth of Firms: Evidence From a Natural Experiment In India Jensen and Nolan (ibid.)
      [note] DAI – Scoping study consulting over 120 businesses, trade associations, business support organisations and public sector bodies in Ghana, Kenya, Pakistan and the UK (November-December 2018)

    1. Inability to build overseas business relationships: Limited access to suitable business partners is a key barrier to exporting success. To address asymmetries of information between buyers and sellers, importers face screening costs to gather information about the reliability, trust worthiness and quality of prospective international business partners. Firms in developing countries lack effective means to signal their reliability. Firms struggle to secure adequate representation in target export markets or to identify appropriate foreign business partners, often due to the high costs of carrying out overseas business missions or attending international trade fairs. Studies from Nigeria and Egypt show that removing these barriers between importers and exporters - for example through export promotion services that help with matching firms - can significantly reduce trade costs, increase profits and productivity for developing country firms.
      [note] Exporting and Firm Performance: Evidence from a Randomized Experiment Atkin D et al. 2017 and The value of face-to-face: Search and contracting problems in Nigerian Trade Startz 2017

    1. Difficulties establishing credibility: A successful supply agreement does not stop with an exporter establishing contact with a suitable buyer. Trust is needed to cement deals – this takes time, commitment and reassurance that a business partner can meet quality, reliability and reporting requirements. Beyond the firm, negative market perceptions of developing countries deter many buyers from engaging in these markets. Studies from across a range of developing markets show that external intermediaries can play a pivotal role in brokering relationships between firms and helping exporters to establish credibility, in particular by facilitating knowledge transfer about the firms and international markets, translating messages between different corporate cultures and acting as an independent mediator. E-commerce platforms have also been found to increase trust through an expectation that minimum standards must be met, and the ability to return goods. Although e-commerce holds a lot of potential for developing country exporters it is still a very small portion of the market and the ‘trust mechanisms’ of e-commerce are not present in most supply relationships.
      [note] Exporting and Firm Performance: Evidence from a Randomized Experiment Atkin D et al. (2017) and The Ethical Agent: Fresh flowers in Kenya IIED 2012
      [note] There Goes Gravity: e-Bray and the Death of Distance Lendle et al, 2016

Problem 3: Making the Global Trading System Work for Developing Countries

The rules based international trading system, with the WTO at its centre, provides the framework for free and fair trade. The principle of “Special and Differential Treatment” that benefits developing countries is integral to the WTO and its agreements. However, a number of challenges are preventing the design and implementation of global rules that facilitate developing country trade:
Participation: governments in developing countries are not able to accede to or actively participate across the spectrum of activity at the WTO. Developing countries lack domestic experts, have weak domestic institutions and lack access to external experts, which prevents them from engaging at the WTO. For example, over the past decade, LDCs have raised only four concerns in the Technical Barriers to Trade Committee, compared to 155 concerns raised by developed countries.
[note] Nordström, H. (2003), ‘Participation of Developing Countries in the WTO - new evidence based on the 2003 official records’, Stockholm: Swedish National Board of Trade, http://www.noits.org/noits06/Final_Pap/Hakan_Nordstrom.pdf

Disputes: Governments in developing countries lack the capacity to raise disputes in the WTO if they believe another member is violating a WTO agreement or commitment. The WTO has one of the most active international dispute settlement mechanisms in the world, but disputes are predominantly between developed members. The ACWL provides LDCs and developing countries with legal support. The ACWL, if it was considered as a WTO member, would be the fourth most active participant in WTO dispute settlement, highlighting the demand for their services.
[note] Final Report on Operations 2023 Advisory Centre on WTO Law:

Implementation of agreements: Developing countries also lack capacity to comply with WTO agreements which serves as a further disincentive to participate in negotiations, although compliance with WTO agreements would make it easier for their domestic industries to trade internationally and make their markets more attractive to international capital flows. For example, compliance with the Domestic Regulation of Services Joint Initiative would result in better regulated and more accessible services markets in developing countries. According to WTO research, the implementation of this Domestic Regulation is projected to lead to a reduction in trade costs by 10% for lower-middle income economies and by 14% for upper‑middle income economies, resulting in global savings of USD 127 billion.
[note] Services Domestic Regulations Factsheet https://www.wto.org/english/news_e/news20_e/sdr_factsheet_nov20_e.pdf

Annex B: Proposed Interventions

Government Level Interventions

Government action and reform, at a national and regional level, is needed to enable businesses in developing countries to export globally. Areas for technical assistance and support include:
Trade policy reform: support is needed for governments to develop and implement inclusive export-led growth policies which support sectors where a country has a competitive advantage and that benefit excluded and marginalised communities. The FCDO Economic Development Best Buys found that both support for national level policy advice to promote pro-growth policies and reducing trading costs via domestic regulatory reforms are ‘Great Buys’. This would include export-focused support to marginalised regions and sectors employing women or poorer workers (e.g. agriculture, ready-made garments) and government incentives and regulations which support MSME trade and could involve support to export promotion agencies.
[note] Best Buys in Economic Development for Growth, Chief Economist’s Office

Support to implement trade agreements and respond to global regulatory changes: support is needed to help developing countries align their trading environments with regional standards and global norms. The WTO estimates that full implementation of the Trade Facilitation Agreement could reduce trade costs by an average of 14.3% and boost global trade by up to $1 trillion per year, with the biggest proportional gains in the poorest countries. Regional bodies, such as Regional Economic Communities in Africa, have the potential to accelerate trade reform but lack resources and capacity. Developing countries also need support to respond to the requirements of climate-related measures such as the proposed UK and EU Climate Border Adjustment Mechanisms (CBAMs) and US Inflation Reduction Act and requirements arising from innovations in areas such as the use of AI and blockchain.
[note] WTO website WTO | Trade facilitation

Improving domestic standards: support is needed to help governments adopt regional and international standards, for example ISO. This can increase trade by improving export market access, reducing the need to make multiple product adaptations to access different markets, reducing production and compliance costs and offering opportunities for economies of scale. This can also lead to an overall reduction in greenhouse gas emissions (ICF KPI 6) as the use of best practice standards helps to ensure that products are more environmentally sustainable and meet developed country climate requirements and standards.
[note] In addition, where countries use international standards as the basis for their regulation, they are presumed to be compliant with the WTO’s agreement on Technical Barriers to Trade, minimising the risk of another country raising a Specific Trade Concern or initiating a dispute against them.
[note] ISO - Climate Action, Standards | GHG Protocol

Strengthening domestic quality infrastructure: support is needed at national or regional level to enable businesses to demonstrate compliance with standards and technical rules. Regulatory agencies require capabilities to design and to implement the national “quality infrastructure” i.e. the standards, technical regulations, and SPS measures expected for participation in international trade. Better quality infrastructure regulations help to ensure that goods and services meet important safety, health, environmental and consumer expectations. By training regulatory agencies on best practice green standards, e.g. ISO, greenhouse gases or regulative measures on anti-deforestation and carbon leakage, the overall institutional level of knowledge on climate change and nature/biodiversity issues can be improved (ICF KPIs 13, 14).
[note] World Bank World Development Report 2020: Trading for Development in the Age of Global Value Chains
[note] Ensuring Quality to Gain Access to Global Markets, World Bank 2019
[note] Increasing the Ability to Comply with Standards or Regulations to Improve Trade and Investment. Brighton: Institute of Development Studies Quak, E. 2019

Streamlining customs processes and procedures: support is needed to implement improved risk management and border management processes, as well as time release studies and Authorised Economic Operator initiatives. Supporting the establishment of electronic single windows and other digital customs administration platforms will facilitate easier communications between customs organisations and traders. Single windows in particular can also help decrease corruption by increasing automation and the use of digital certificates.
[note] Managing the risk of corruption in Customs through single window systems Dennis Ndonga

Regulatory environment improvements: support is needed at a national and regional level to create a more transparent and open business environment and tackle corruption (centred on areas such as anti-bribery, governance and institutional performance), which can increase the attractiveness of developing countries as destinations for Foreign Direct Investment (FDI) and reduce the cost of corruption for exporting firms. Support to developing countries in regulating their net-zero transitions, e.g. through domestic carbon pricing, can also incentivise a general uptake of low carbon technologies (ICF KPI 9) across production and trade of goods.
[note] What are low-carbon emitting technologies? An expert explains | World Economic Forum 2022

Business Level Interventions

Technical assistance to firms and business organisations in the following areas has been shown to help them to overcome the challenges outlined above:
Trade and export promotion: To successfully export, firms need support in a variety of areas: maintaining sufficient, reliable supply and appropriate quality of products and packaging; considering how transport, different temperature zones etc may affect their product quality; finding and entering markets, by researching market opportunities and identifying buyers’ expectations; raising the firm’s visibility to potential buyers, for example by participating in trade fairs, establishing an effective online presence, including social media; and then growing the firm’s presence in those markets, so the firm can re-invest in its operations. In the UK’s existing AFT programming, this kind of “export promotion” support has been successfully provided to MSME businesses and has been shown to boost their trade by a ratio of $5 of trade for every $1 of technical assistance. AFT interventions have also successfully supported business associations and networks, including for women-led MSMEs, which provide services to businesses (such as processing export licences) and represent businesses’ views to government policy makers.
[note] ITC’s UKTP evaluation estimated the additional value of exports for each dollar (US$) of UK support to be US$5.7.

More inclusive access to information: Reliable and easily understandable market intelligence, especially about unfamiliar markets, is expensive and complex for businesses to obtain. This leads to access being limited to larger firms with resources and capabilities, but which have no commercial incentive to share with other market actors. Using public funds to carry out and publish sector studies and other market access analysis, for example through the Growth Gateway, not only directly benefits firms which have requested support through the facility, but can also make information a public good, available to all businesses, including new exporters and smaller firms.

Meeting quality standards: Businesses need to be aware of and able to comply with the requirements to be allowed to export, both their own country’s regulations and those applying to the destination markets for their products. Support to businesses to meet the SPS and quality standards required of high value export markets can significantly increase firm and individual incomes. An ISO study shows that implementing standards across a range of developed and developing economies can provide economic benefits of between 0.15% and 5% of companies’ annual sales revenues (at a company level). Technical assistance to exporters could enable them to gain from using geographical indications (GI) i.e. place names and words associated with a place that identify products’ origin, quality and reputation.
[note] WTO | intellectual property (TRIPS) - Geographical indications

Private quality standards and certification: support to help businesses and business organisations understand and adopt private standards such as Fairtrade, Rainforest Alliance and organic and sustainability standards can help alleviate poverty by securing higher than average sales prices. The increased income impact of these schemes has been found by various studies focusing on green tea, coffee and other agricultural products.
[note] Impacts of sustainability certification on farm income: Evidence from small-scale specialty green tea farmers in Vietnam Duc Tran, ScienceDirect (2019) and Do Private Sustainability Standards Contribute to Income Growth and Poverty Alleviation? A Comparison of Different Coffee Certification Schemes in Ethiopia Fikadu Mitku et Al, MPDI 2017

Support to business networking organisations: firms in developing countries are more likely to succeed in exporting if they have access to the information, training and other support services provided to entrepreneurs through business networking organisations, such as chambers of commerce and producers’ associations, particularly in sectors where poorer people, especially poorer women, work and business networking organisations specifically for women entrepreneurs and/or medium and small enterprises.
[note] Women entrepreneurs in and from developing countries: Evidence from the literature, Luisa De Vita Michela Mari and Sara Poggesi, European Management Journal, 2013

In order to maximise the development impact of technical assistance to firms, it is important to ensure that interventions benefit firms which contribute to more inclusive trade. The following criteria help to determine inclusivity:
1. Sector: Supporting large and small firms in some sectors, like agriculture, provides greater opportunities for poorer people to earn money and some, like ready-made garments, even more so for poorer women. Evidence clearly shows that the ready-made garment sector provides employment for unskilled female workers and contributes to women’s economic and social empowerment.
  [note] For example, see Impact of RMG Sector on Livelihood Change of Women Employees of Bangladesh Afsana Mustafa, M. Serajul Islam, Saiful Islam, Mahfuja Khatun Social and Economic Geography, 2016, Vol. 2, No. 1, 1-10
  [note] For example, see Ready Made Garments Contribution to Women Empowerment, A Study on Women Workers in Bangladesh Perspective Md. Ashfaqur Rahman, Mohammad Anamul Haque Nayan, Professor Dr. Md. Mayenul Islam (Bangladesh Open University, Gazipur, Dhaka, Bangladesh) 2022
2. Size: Smaller-sized firms are the most common type of firm but are under-represented in international trade. Whilst some large firms (e.g. those employing large numbers of women) can have a positive inclusive impact, smaller firm growth can “can drive structural transformation through innovation, provision of intermediate inputs and services and by increasing employment in both the modern and traditional sectors”.
  [note] Entrepreneurship, developing countries and development economics: new approaches and insights, Wim Naude, 2009, Small Business Economics
3. Gender: Firms led by women face some additional challenges compared with businesses led by men. Supporting women-led businesses and those employing large numbers of women to export not only generates income-earning opportunities but can also indirectly help change social attitudes about women’s roles in the economy.

As a result of these business level interventions, jobs will be sustained and created and the number of people with improved resilience to climate change and who can cope with the effects of climate change will increase, supporting delivery of ICF KPIs 1,4 and 5. Supporting access to information, to quality standards and regulations as well as to private standards and certificates some key sectors (particularly agriculture) will improve a understanding of how to cope with climate change and boost nature/biodiversity, e.g. by adapting farming methods to meet more sustainable standards.

Global Level Interventions

Given resource constraints in developing countries, technical assistance is needed to enable developing countries to participate in global rule negotiations and to fulfil the partnership principles of the SDGs, particularly SDG 17. Whilst multilateral negotiations are complex and take time, WTO trade rules can dramatically impact the international trading environment for developing countries. The WTO Enabling Clause permits developed countries to extend preferential tariffs to developing countries. The UK’s DCTS alone cuts tariffs on UK imports from 65 developing countries by over £770m annually. Studies estimate that the Investment Facilitation for Development Agreement could increase global welfare gains by at least $296bn if implemented fully.
[note] SDG 17.10: Promote a universal, rules-based, open, non-discriminatory and equitable multilateral trading system under the World Trade Organization, including through the conclusion of negotiations under its Doha Development Agenda (Goal 17 | Department of Economic and Social Affairs (un.org) ).
[note] Appellate Body Repertory of Reports and Awards 1995-2013 - Enabling Clause WTO
[note] Economic impacts of investment facilitation idos-research.de 2021

Through our engagement with developing countries, particularly at the WTO in Geneva, we have identified the following areas of particular need for support:

Accessions: DBT-commissioned research found that most countries benefit from WTO Membership with many of the largest beneficiaries being developing countries. The average WTO member saw trade cost falls equivalent to a 15% reduction in tariffs, with developing countries seeing costs falling by the equivalent of a 21% reduction in tariffs. However, accession is lengthy (12 years on average) and onerous and requires technical support. Of the 9 LDCs that have applied and successfully acceded to the WTO, all did so with technical assistance and financial support.
[note] Valuing the Impact of the World Trade Organisation Department for International Trade 2022

Support for developing country Negotiation Capacity in the WTO has helped to reform global trade policies and regulations. For example, UK funded technical assistance has supported developing country engagement and voice at negotiations on trade facilitation in Bali, agricultural support in Nairobi, fisheries negotiations in Buenos Aires and Geneva and most recently on agreeing more generous LDC graduation proposals at MC13 in Abu Dhabi. It is reasonable to assume that negotiated outcomes will not adequately accommodate developing country priorities if their voice is absent or diminished in critical end stage negotiations. For example, UK logistical support for Pacific Island Forum negotiators ensured they were able to influence WTO fisheries negotiations.

Legal advice: The WTO dispute settlement mechanism is a key element of the multilateral trading system, ensuring that rules are defended and applied impartially. Developed countries typically draw on specialist in-house legal expertise or hire private law firms. For many developing countries, and particularly LDCs, external legal counsel may not be available or financially feasible, leaving them unable to raise a dispute or defend a challenge effectively. The ACWL provides LDCs and developing countries with WTO legal support and has assisted in 20% of all legal disputes since its creation in 2001. This includes support for 33 countries through the provision of 3,712 legal opinions and assistance in 72 disputes. It is reasonable to assume that this demand or a proportion of this demand will have gone unmet in the absence of the ACWL. Legal capacity is also important for the ability to negotiate across the WTO.
[note] Final Report on Operations 2023 Advisory Centre on WTO Law

Annex C: Programme Funded Role Value for Money [REMOVE FROM PUBLIC VERSION]

Does it meet the criteria?

- A project funded in-house delivery role must offer better value for money than a feasible outsourced alternative. The programme funded role(s) proposed in this business case meet this criterion based on the assessment below.
- In addition, a project-funded in-house delivery role must be focused on programme delivery rather than programme management functions, which the role(s) will be. They will primarily be focused on the ‘Shop-Front’ function and undertake strategic communications and engagements for the programme.

Value for Money Assessment

- The programme funded roles have been assessed to represent good value for money in the following areas:
  - Economy – the input cost of a programme funded role can be directly compared to the cost of a similar role provided through a delivery partner. As set out in the table below, the input cost for the programme funded roles is significantly less than the cost for equivalent external experts.
  - Effectiveness and Cost-effectiveness – by integrating some of the delivery of the programme into the team via the programme funded roles, we are increasing our internal knowledge and capacity. This increases the impact of the programme by enabling us to manage it more effectively. In the longer term it also enables the embedding of the internal evidence base on ‘what works’ firmly in the team.

Table 9: Comparison – Estimated Costs FCDO In-house Staff vs External Contractor

	Estimated Cost In-house FCDO Staff			Estimated Cost – Similar External Roles, based on fee rates		Cost Diff (%)
Staff Location	CS Grade	Annual Cost (£)	Notes	External Contractor Cost (£)	Notes
UK	G7	82,280	UK based G7	95,000	Fee rates for UK based Senior Experts used for comparison	13
UK	SEO	62,958	UK based SEO	86,000	Fee rates for UK based Experts used for comparison	27
UK	HEO	52,493	Country Based Staff (Geneva)	60,500	Fee rates for National Experts operating in Europe used for comparison	13
[note] Using rates from the commercial fee rate database for similar UK-based roles across multiple programmes
[note] Estimated annual costs are based on FCDO rates (including £2k UK Allowance)

Annex D: Log frame - Separate Document

Annex E: Cost Benefit Analysis

Point of Entry	Supporting evidence	Applicability of evidence
Business level
Trade and Export promotion	Literature / A summary of literature on export promotion organisations (EPOs) highlights research that finds “Overall, most of these studies find positive impacts of export promotion efforts on different outcomes, across several countries”. This includes boosting export performance of firms already exporting and those new to exporting. One study identified that a 10% increase in budgets for Export Promotion Organisation (EPO) increases, on average, a 0.6% to 1% in exports. / UK Programme examples / An independent evaluation of the UKTP found that overall for each $1 spent, there were $5.7 of exports sales generated.	Moderate / The research literature on export promotion organisations shows positive impacts, including for developing countries. The extent to which upcoming activities will cover the most beneficial parts of an EPO are unknown, though the UKTP review corroborates programme work delivering export benefits. / More broadly, outputs are often measured in export growth rather than overall welfare or GDP effects. Other interventions could have greater impacts on business climate and exports
Supporting businesses to meet quality standards	Literature / An ISO report looking at a variety of case studies finds that implementing standards across a range of developed and developing economies can provide economic benefits of between 0.15% and 5% of companies’ annual sales revenues (at a company level) . / A World Bank report considers the economic impact of quality and standards. Quoting an earlier survey of firms (Wilson and Otsuki), the survey finds that in developing countries 44% of firms had to conduct significant duplication of testing procedures to meet foreign requirements after domestic requirements had been met, and 30% had to conduct complete duplication of testing procedures. 68% of firms cited testing and certification costs as an important reason for not exporting.	Moderate / Good evidence showing both the positive impacts on firms from adhering to standards, and that standards acts as a barrier to trade. / The applicability here depends on the exact programme of work and standards targeted as part of the programme. Improvements to standards will be beneficial, but not necessarily overcome issues of compliance in international trade.
Government Level
Improving Standards	A CEBR report finds that 22% of economic growth is associated with the increase of the net production of standards. / For the British economy, the results of elasticity of the stock of standards are similar compared to other studies. A 10% increase in the stock of standards can be associated with a 0.5%-1.1% increase in labour productivity or 0.32%-0.71% increase in total factor productivity (using the capital share 0.351 estimated from the 2015 study). Keeping everything else constant, a further increase of 10% of the stock of standards (that can deal with the same amount of economic problems found in the previous studies) can be associated with a further GDP increase of £6.95-£15.42 billion (in 2019 £).	Limited / Evidence shows a positive economic impact of implementing standards improvements. However, this angle looks at UK impact, hence unclear of applicability of results on developing countries.
Trade facilitation	Literature / There is an extensive literature on the impacts ­of barriers to trade, and the role that trade facilitation can have in overcoming these. Examples include: / The implementation of the Trade Facilitation Agreement could lead to a reduction in trade costs for LDCs of 17%, and an aggregated global impact of 0.35-0.55% growth in GDP / An estimated reduction in global trade costs from Trade Facilitation, ranging from 9.6-23.1% with developing countries observing the largest gains / UK Programme Examples / Accelerate Trade Facilitation Programme: Digitised process of cargo clearance in Lesotho has shown promising results in reducing time from 5 hours to less than 1 hour and reducing the operational/transactional costs. / TradeMark Africa: Automation of Tanzania’s Ministry of Livestock and Fisheries services has significantly reduced the time taken to issue livestock permits, down from 14 days to just one hour, and has increased government revenue collections by more than 100%.	Moderate / Evidence shows positive impact in economic growth through increased trade. Evidence has significant focus on developing countries and shows promising efficiency gains as well as successful compliance with TFA obligations. / However, limitations in evidence arise due to the difficulty of attributing global trade increases to improved trade facilitation alone.
Global Level
WTO Accession	Literature / Research on the impacts of the existence of the WTO and accessions finds: / DBT-commissioned research found a significant decrease in trade costs from WTO memberships for developing countries, this was equivalent of an average fall in ad valorem equivalents of 21%. / WTO accession has correlation with economic growth. Brotto and et al, 2021, found 30% increase in size of economies 5 years after ascension. / A recent 2021 study by Brotto and et al expanded on a 2009 paper by Tang and Wri, finding stronger positive impacts of WTO accession on GDP growth on developing countries.	Moderate / Strong evidence of positive impact of economic growth of WTO accession, specifically for developing countries. / There is limited evidence on the impact of specific policy actions or country support on the accession process and the impact it had on the success or timings of accessions.
Negotiation Capacity	Literature / The Investment Facilitation for Development Agreement agreed in 2023 with Trade and Investment Advocacy Fund (TAF2+) support. Studies estimate that the Agreement could increase global welfare gains by at least $295 billion if implemented fully. / UK Programme examples / The TAF and TAF2+ have supported developing countries participant effectively in many negotiations. Examples include the MC13 LDC graduation proposal put forward by the LDC group, and the Pacific Island Forum’s engagement during final stages of negotiations of Fisheries Subsidies Agreement.	Limited / Examples available of TAF and TAF2+ supporting developing countries with negotiating at WTO but due to multi-donor and multilateral nature of work difficult to quantify and attribute benefits.
Legal Advice	UK Programme examples / ACWL has assisted in 20% of all WTO disputes since 2002 and provides over 200 legal opinions per year. / To build capacity within developing countries, Training (internships) have been provided by the ACWL as part of our negotiations support package.	Limited / We have example of support provided to developing countries with positive feedback from recipients. There is limited evidence on the impact of this legal advice, and subsequent conclusions of litigation, on outcomes for developing countries.
Logistical support	UK Programme examples / £120k spend allowed 5 countries to attend MC13, who would otherwise not have attended. / In total, 27 delegates from 15 countries were supported.	Limited / Difficult to quantify and attribute impacts of supporting attendance to MC13 given complexity of outcomes and establishing counterfactuals.
[note] Anatomy and Impact of Export Promotion Cruz et al, 2018
[note] Export promotion agencies: Do they work?; Daniel Lederman, Marcelo Olarreaga, Lucy Payton, 2010
[note] UKTP Final Report 2023
[note] Economic Benefits of Standards; ISO (International Organization for Standardization), 2014
[note] Quality Systems and Standards for a Competitive Edge; J. Luis Guasch, Jean-Louis Racine, Isabel Sánchez, and Makhtar Diop, 2007
[note] # Assessing the Potential Benefit of Trade Facilitation: A Global Perspective; Wilson and Otuski, 2004
[note] The contribution of standards to the UK economy; CEBR. 2022
[note] Trade Facilitation Indicators: The Potential Impact of Trade Facilitation on Developing Countries’ Trade; Moïsé and Sorescu, 2013
[note] ANNUAL REPORT YEAR 1 – PHASE IV Accelerate Trade Facilitation; HMRC, 2023
[note] TradeMark Africa Annual Report; TMA, 2022
[note] WTO accession and growth: Tang and Wei Redux; Brotto and et al, 2021
[note] Investment Facilitation for Development Agreement: Potential Gains; Balistreri and Olekseyuk, 2024

Annex F: Trade COE Programme Risk Register

		Gross Risk				Residual Risk
Risk Type	Risk	Likelihood	Impact	Rating	Mitigating Action	Likelihood	Impact	Rating
Strategy and Context	It is challenging to measure the impacts of increased trade on the reduction of poverty or on marginalised groups, which may impact the ability of the programme to improve the evidence base in particular areas.	Highly Likely	Moderate	Major	Manage. The MREL design will explore appropriate methodologies and tools to facilitate improved disaggregation of results. The programme CBA will be tested through evidence and adjustments made where necessary.	Likely	Minor	Minor
	Climate and environment risk, activities could have an adverse effect on climate mitigation and encourage trade that negatively impacts on nature and biodiversity.	Possible	Major	Moderate	These risks will form a core assessment part of each activity.	Unlikely	Moderate	Minor
Policy and Programme Delivery	Trade COE may fail or not achieve comparable results to other COE and risk being closed down early or merged with another COE	Unlikely	Major	Minor	Manage. Deliver Trade COE as planned and achieve the results anticipated.	Unlikely	Minor	Minor
	Post reputation and credibility negatively impacted by poor delivery through COE or where interventions do not yield expected results.	Possible	Moderate	Moderate	Manage. Strong collaboration, planning, implementation and review as set out in the delivery and governance frameworks will ensure this risk is reduced. The SLA will set out Post specific needs and clarify steps to enable effective cooperation and conflict resolution between all parties.	Possible	Moderate	Minor
	Given the nature of multilateral funds, we will have limited influence over their activities, outputs and outcomes.	Likely	Minor	Minor	By increasing engagement with multilateral and donor counterparts we can increase the likelihood of programme activity aligning with UK priorities.	Possible	Minor	Minor
	There may be a lack of quality bids from commercial suppliers.	Possible	Major	Moderate	Manage. EME to engage potential suppliers, strong TORs for tender process, contingency plans e.g. GDD in the event there are no suitable bids.	Possible	Major	Moderate
People	Insufficient resourcing (short and long term) of Trade COE Hub could have significant implications for Trade COE delivery (with associated risks to COE/UK reputation).	Likely	Major	Major	Manage. Continue to make the case for Hub resourcing, explore options to convert roles to programme funded, incorporate flexible and agile programming in delivery, focus on smart and efficient ways of working.	Possible	Moderate	Moderate
Financial and Fiduciary	Funds being used for unintended purposes or not managed in accordance with requirements.	Unlikely	Major	Moderate	Manage. Delivery partners will undergo due diligence to ensure they have the required financial capacity to manage funds and strong management procedures will be established for the programme.	Unlikely	Moderate	Minor
	[Perception or actual] ODA funded prioritisation of activities and geography decisions made on basis of UK benefits over primary purpose of poverty reduction as highlighted in the ICAI review.	Unlikely	Major	Minor	Manage. COE’s robust delivery and governance arrangements will ensure this risk is mitigated. The intervention concept note will also ensure the primary focus of poverty reduction is clearly set out as a statement of intent and any potential for secondary benefit to the UK also clearly defined as secondary benefits.	Unlikely	Minor	Minor
	Buy-in funding from post represents nearly a third of the COE budget and so a reduction to this through lack of buy-in demand could have implications for COE and suppliers	Possible	Major	Moderate	Manage. Maintain a good level of engagement with post to ensure they are aware of COE as a viable option for delivering their AFT interventions avoid additional costs and need for creating new programmes and contracts/agreements. This will form part of the COE communications strategy	Possible	Moderate	Minor
	Supply and demand mismatch due to reducing ODA. Experience suggests demand is likely to far outweigh supply which would have implications for beneficiaries and COE approach and reputation	Likely	Major	Major	Manage. Actively manage expectations of Posts; use evidence to strengthen case for increased ODA allocation, focus on ripple effects, encourage interoperability between suppliers to deliver more with less and manage closely multilateral funds to achieve economies of scale.	Likely	Major	Majo
Safeguarding	Failure to establish and maintain strong safeguards.	Possible	Major	Moderate	Manage. Delivery partners will undergo due diligence to ensure they have the required safeguarding procedures established. This will be monitored throughout the programme.	Possible	Moderate	Minor
Reputation	The Global support funded by UK ODA could enable developing countries to negotiate against the UK and UK positions at the WTO	Likely	Major	Moderate	Tolerate. This is an accepted risk. It is a factor that puts trust and confidence in the Trade COE and demonstrates the UKs unbiased approach to supporting developing countries to meaningfully participate with the GTS.	Likely	Major	Moderate

A short, intervention level risk register will be included in the terms of reference, clearly setting out ownership and mitigation plans around specific risks associated with agreed activities.
Annex G: Coordination with other COEs