# ADDENDUM TO BUSINESS CASE
SUMMARY INFORMATION
Project Name	Mobilising Institutional Capital Through Listed Product Structures (MOBILIST)
Country or region targeted	Africa, South Asia, Latin America and South-East Asia
Type of cost extension (if applicable)	Cost and time extension
Original project budget	£164.1m (of which £19.8m RDEL, £5.3m fiscal CDEL, £139m non-fiscal CDEL)
Original project start and end dates	25/02/2020 – 30/09/2029
Cost extension value (if applicable)	Up to £100m non-fiscal CDEL (minimum 62% ICF)
New reduced budget (if applicable)	n/a
New project end date (if applicable)	30/09/2030
Business Case Quest Document No.	300921

INFORMATION
What is the project’s purpose?
Summary of MOBILIST / MOBILIST (Mobilising Institutional Capital Through Listed Product Structures) is the UK’s flagship public market investment programme. Partnering with major stock exchanges around the world, MOBILIST seeks to mobilise the deep pools of institutional capital that reside in public markets to support the SDG and climate financing gap in emerging markets and developing economies (EMDEs). / In practice, MOBILIST provides equity investment and technical assistance to support the listings of developing country assets on global stock exchanges, mobilising both domestic and international institutional investors. It seeks to draw in large scale investors, like pension funds, and to catalyse demonstration investment structures that can be replicated and scaled through public markets. / MOBILIST is the only programme of its kind among donors, MDBs and DFIs and sets the UK apart as a leader and innovator in private capital mobilisation (PCM). MOBILIST is a key partner and facilitator in supporting the City of London as a development finance hub, with several deals in MOBILIST’s pipeline seeking to list on the London Stock Exchange when conditions improve. / The individual investments made under MOBILIST sit on FCDO and HMG’s Balance Sheet directly, rather than grouped together in an intermediate investment vehicle or corporate structure. MOBILIST invests Pari passu on commercial terms. It looks to contribute to the UK’s ICF targets and deliver development impact. MOBILIST also provides technical assistance to support with product development and listing and conducts research and extracts policy content on opportunities and barriers to public markets mobilisation. / What gap is MOBILIST trying to fill? / An estimated additional $3 trillion is required annually to deliver the SDGs. It will be key to go further and faster to mobilise more finance from all sources to help end extreme poverty and tackle the climate crisis. Public finance alone will not be enough, with ODA comprising c.5% of finance required to deliver the SDGs. / Mobilising private finance at far greater scale is essential if we are to deliver our development goals, including climate action. An estimated $500 billion per year in international private finance will be needed to help close the financing gap, including from institutional investors such as pension funds and insurance providers. / Relatedly, international partners are telling us that the Global Financial System (GFS) is not fit for purpose. GFS reform is a top ministerial priority for the FCDO and HMG and our ambition is to work in partnership with the Global South and leaders such as Barbados Prime Minister Mia Mottley to change the system. This is so that countries can mobilise and access finance at the scale and speed required to accelerate their development ambitions and deliver the SDGs, respond to the climate and nature emergencies, and drive sustainable economic growth for all. / As part of the reform agenda, multilateral development banks and development finance institutions are being called to innovate to unlock substantially greater volumes of private investment through reformed business models and risk sharing. MDBs, for example, have already agreed to provide a further $200bn in lending over ten years by managing their balance sheets more tightly. / The majority of development finance investment takes place in private markets. However, the scale, governance and liquidity that institutional investors require is found in public markets. The value of debt and equity on public markets is thought to be more than 20 times the amount of capital invested in unlisted private market assets and 100 times the combined balance sheets of MDBs. / Publicly listed equities and bonds comprise the majority of institutional investors’ portfolios (about 90% of most large-scale institutional portfolios). The limited supply of developing country listed assets limits investors’ ability to allocate assets to the wider developing country universe where their capital would have the most impact. For example, the main emerging market index, MSCI Emerging Markets Index, allocates 81% of its weight to just five countries (China, India, Taiwan, South Korea and Brazil). / Moreover, international financial institutions can further deliver on this ambition by using public markets to free up space on their balance sheets to make room for additional lending. 2022 saw the publication of the G20-commissioned Independent Review of Multilateral Development Banks’ Capital Adequacy Frameworks. A key recommendation was that the global financial system needed to be bigger: unlocking more finance for global public goods, leveraging finite public resources to do so, but also bringing in substantially greater volumes of private finance through reformed business models and risk sharing. / MDBs and DFIs can transfer risk to public markets through exits or instruments such as securitisation. The international community is calling for a shift from an ‘originate-to-hold’ to an ‘originate-to-distribute’ business model. As a secondary market for development finance assets, public markets offer the potential to accelerate capital velocity and grow total capital deployment each year while also contributing to local capital market development. MOBILIST is poised to provide the bridge to move these assets, through a model call ‘securitisation,’ which enables the transfer of assets from MDB and DFI balance sheets to public markets. / However, at the current time, the opportunity presented by public markets is untapped. Overall, a larger proportion of global institutional investment assets under management is in developed markets rather than in emerging economies and developing countries. Reorienting just a fraction of the $98tn held by institutional investors could be transformative. OECD countries’ pension assets alone exceed $48tn. The largest 20 pension funds in Europe hold on average 8.7% of their total assets in EMDEs while the top 15 insurance companies allocate on average 2.2%. / MOBILIST to date: / MOBILIST is the only donor programme with a dedicated focus on public market investment. It aims to attract the largest global pools of capital into financing sustainable development, including the climate transition, at scale in emerging and frontier markets. / The programme makes equity only investments that enable securities to be listed on public stock exchanges around the world, with the aim of supporting products that address development and climate challenges in EMDEs. The aim is to recycle these investments back to FCDO. / MOBILIST works closely with Posts around the world on MOBILIST partnerships and IPO launches, in particular with South Africa, Nigeria, Kenya, Singapore, Brazil, Mexico and the Philippines. As such, MOBILIST has become a core element of the UK and FCDO’s development offer for the overseas network. / MOBILIST’s current business case is for £164.1m from February 2020 to September 2029 of which £19.8m is RDEL, £5.3m fiscal is CDEL, £139m non-fiscal CDEL reflecting an RDEL cost and time extension approved via BCA in July 2024. MOBILIST is weighted towards climate finance, with £86 million or 62% of the total FT allocation classified as ICF. / Current portfolio: / From 2020, MOBILIST has built a portfolio of six transactions, investing £87m in equity and equity commitments, four of which have been listed on stock exchanges around the world, mobilising £247.5m of private capital with a mobilisation ratio of 1:4.91. These transactions are set out as below: / Citicore Renewable Energy Company: in June 2024, MOBILIST supported the Philippines in its transition to renewable energy through a £9.9m local currency investment in the initial public offering (IPO) of Citicore Renewable Energy Corporation (CREC) on the Philippines Stock Exchange, Inc. (PSE), helping to decarbonise the Philippines power generation fleet by rapidly rolling out wind and solar, adding 2.3GW by the end of 2025 and 5GW by 2028. / Thai Credit Bank: in February 2024, MOBILIST participated in the $200m listing of Thai Credit Bank (TCRB) on the Stock Exchange of Thailand (SET) in local currency. MOBILIST purchased previously issued ‘secondary shares,’ allowing an MBD to exit a portion of their long-term investment, facilitating an ‘exit-mobilisation’. MOBILIST invested $15m into the only licensed bank in Thailand that focuses on loans to MSMEs, lending to over 250,000 small businesses in Thailand who otherwise lack access to basic banking services, including women-owned businesses, operating predominately in rural Thailand. / Bayfront Infrastructure Capital IV: MOBILIST’s £4m equity investment in September 2023 into a $410m securitisation vehicle that listed on the Singapore Stock Exchange and enabled the greening of bank balance sheets in Southeast Asia and attracted international investors into developing countries’ infrastructure. This transaction is the first example of a donor-backed sustainable tranche to enable greening of the underlying debt portfolios and one of the first examples of the ‘originate to distribute model’ for MDBs, with ADB participation in the transaction. It provided an example of how the G20’s recommendations on MDB reform can be implemented by demonstrating how securitisation can enable banks to transfer loans from their balance sheets, freeing up capital to deploy towards the SDGs and green finance, and is now being explicitly referenced by other MDBs and DFIs seeking to securitise financial assets. / Green Guarantee Company: MOBILIST’s February 2023 investment of £32.5m in a UK-based guarantee platform aims to bring down the cost of green bond issuances by the private sector, accelerate the pace of investment for climate mitigation and resilience, save CO2 emissions and delivers critical climate resilient infrastructure. This transaction aims to facilitate $5bn of loans and bonds which would see eventual financing of 125x the funds invested by MOBILIST. / Helios CLEAR Fund: MOBILIST’s April 2022 £5m equity commitment seeded Africa’s first dedicated climate fund investing in mid-sized African companies to avoid and reduce carbon emissions, enabling sectors and populations to become more resilient and to adapt to climate change. CLEAR will also acquire assets from PIDG allowing InfraCo Africa portfolio assets to be exited and capital proceeds recycled into new projects. CLEAR achieved first close on 22 July at USD205m, including an investment of £32.5m from the Green Climate Fund, £15.5m from BII, with other investors including USAID, Norfund and the Nigeria Sovereign Investment Authority. CLEAR aims to be first listed Africa-focused climate fund to list on a major international stock exchange. / Asia Energy Impact Trust (previously TLEIT): MOBILIST’s December 2021 £24.5m equity investment enabled the first ever renewable energy company that raised funds on the London Stock Exchange, exclusively financing renewable energy companies in EMDEs, saving CO2 emissions and providing electrification and energy security in the Philippines, India, and Vietnam. The IPO represented the first listed portfolio of developing market renewable assets and attracted investment from institutional investors including Schroders, Cazenove, Credit Suisse and Lions Trust. / TLEIT was beset by several issues which have eventually led to the Trust going into orderly wind-down, rather than scaling up in the way the equivalent first-to-market IPO achieved in the UK. The transaction is still set to achieve development impact by way of replication, having sent important price signals and demonstrated the viability of launching such a product. As a result, TLEIT has catalysed several successor propositions from other market actors, which are now anticipated to list on major international exchanges over the next year and show every potential to scale. / Moreover, the process used to manage issues related to TLEIT has provided a compelling demonstration of how public market governance works and provides investors with a suite of protections that are both unavailable and/ or unaffordable to investors in a private market setting. / As the first developing market renewable portfolio to list on the LSE, transparency has significant policy value in global efforts to implement a wholescale reconfiguration of energy systems. Investing with this objective will inevitably involve the risk of underperformance, but price signals – good and bad – are the basis for how capital can be optimally allocated and allows policy makers to re-calibrate. If the climate transition is to be given effect productively, the kind of information that public markets deliver is going to be essential to that ability to recalibrate. / Table 1: Summary of MOBILIST portfolio / Investee Listed Listing/Launch Date MOBILIST Investment Overall Investment at Listing/Launch / Asian Energy Impact Trust (AEIT) Yes (London Stock Exchange) Dec 2021 US$32.5m (£24.5m) US$115.4m (£87.1m) / Climate, Energy Access and Resilience Fund (CLEAR) No (potential to list in future) Aug 2022 US$7m (£5.8m) US$205m (£155.3m) / Bayfront Infrastructure Capital IV (BIC IV) Yes (equity unlisted, debt listed on Singapore Exchange) Sep 2023 US$5m (£3.9m) US$410.3m (£328.5m) / Green Guarantee Company (GGC) No (will explore possibility of listing in the future) Feb 2024 US$40m (£31.4m) US$100m (£79.2m) / Thai Credit Bank (TCRB) Yes (Stock Exchange of Thailand) Feb 2024 US$14.9m (£11.8m) US$205.2m (£162.4m) / Citicore Renewable Energy Company (CREC) Yes (Philippine Stock Exchange) June 2024 US$12.5m (£10.2m) US$90.2m (£70.9m) / Table 2: Mobilisation data for listed transactions / Investee Year MOBILIST investment Other public capital invested Total private capital invested Private capital mobilised by MOBILIST Private capital mobilisation ratio / Asian Energy Impact Trust 2021 £24.5m none £63.0m £63.0m 2.57 / Bayfront Infrastructure Capital IV 2023 £3.9m £63.0m £256.5m £90.5m 22.9 / Thai Credit Bank 2024 £11.8m £41.5m £109.6m £30.4m 2.58 / Citicore Renewable Energy Corporation 2024 £10.2m none £63.7m £63.7m 6.25 / Totals £50.4m £104.6m £492.8m £247.5m 4.91 / MOBILIST mobilisation and impact / Through four investments which have directly resulted in the creation of listed instruments, MOBILIST has been able to leverage scarce ODA funds of £50.4m to mobilise £247.5m of private capital to date (using OECD methodology to calculate attribution). There was a total of £492.8m private capital and £104.6m public capital (besides FCDO) involved in these products (AEIT, BIC4, TCRB, CREC). / MOBILIST’s £5.81m commitment in CLEAR Fund and £31.4m investment in Green Guarantee Company, which have not yet resulted in the creation of listed instruments, are expected to mobilise private sector capital when these products raise additional funding through either private or public markets. Both products have potential to list on major exchange such as the London Stock Exchange in the future. / To date, MOBILIST’s investments have created 660 direct jobs, avoided 727,364 tCO2e, and generated 961,897 MWh of renewable energy. / Policy and research: MOBILIST conducts research and provides policy content on product structures, barriers and opportunities to overcome public market mobilisation and market reform priorities. As such, MOBILIST has been able to establish itself as a thought leader on public markets, delivering detailed and industry-relevant pieces on areas such as: / “Demonstration effects” in financial transactions and what is required to see innovative transactions replicated in the market, with extensive well-worked case studies. / Balance sheet optimisation for MDBs, informing policy priorities at MDB governance discussions. / Detailed reporting on actual returns achieved in Sub-Saharan Africa renewables, supporting the case for institutional investment into this asset class through listed instruments. / Innovations in market tools such as indices to broaden public market capital flows to more frontier markets. / A detailed summary of MOBILIST research is at Annex 3 Part II ‘Key learnings from MOBILIST’s research’. / Innovative sourcing: MOBILIST has established an innovative and effective origination model through strategic partnerships with 9 stock exchanges around the world. These partnerships offer access to financial intermediaries (brokers and investment banks) as a source of MOBILIST’s pipeline of transactions. These partnerships comprise the London Stock Exchange (LSEG), Johannesburg Stock Exchange (JSE), Nigeria Stock Exchange (NGX), Brazil, Bolsa, Balcão (B3), Mexican Bolsa Institucional de Valores (BIVA), Singapore Stock Exchange (SGX), Philippines Stock Exchange (PSE), Bursa Malaysia and the Nairobi Stock Exchange (NSE). / Figure 1: MOBILIST Stock Exchange partnerships / Establishing new donor model: MOBILIST works across public and private sector financial actors (including MDBs and DFIs), building linkages between private and public market infrastructure. It seeks to elevate the role of public market infrastructure and stakeholders into policy formulation on private capital mobilisation.12 13 / New investment partnerships: In addition to partnerships with stock exchanges, MOBILIST has investment partnerships with the Nigerian Sovereign Investment Authority, Allianz Global Investors and Norfund (commercial investors), with USAID, the Green Climate Fund, IFC, AIIB and ADB, the Dutch ‘FMO’, and EIB and is working with Development Bank of South Africa (DBSA) and Brazil’s National Development Bank ‘BNDES’ on developing securitisation models, and directly with IFC on their Warehouse Enabled Securitisation Programme (WESP). / MOBILIST is now on the radar for major mainstream financial institutions in the UK, US, and Europe for EMDE investment which now have strong proposals in MOBILIST’s deal pipeline. These include major UK and European pension funds and insurers, and fund managers, including Europe’s largest fund manager, Amundi. Other major providers of capital are recognising the important role that MOBILIST can play in their own efforts to direct capital to EMDEs and this has led to growing engagement. This in turn allows MOBILIST to grow its footprint in EMDE capital markets and means that MOBILIST is a key partner – and facilitator - in supporting the City of London to position itself as a development finance hub as equity market sentiment begins to improve. / Box 1: Features of Public markets: / - They offer sustainable investment opportunities / - They involve lower capital costs in originating and transacting investments / - They have a stronger market governance framework, are transparent and require extensive financial and non-financial disclosures from issuers / - They meet institutional investors’ regulatory, liquidity and scale requirements. / - In efficient markets, prices of investments are updated frequently to reflect public information to capture an investment’s true value / - Provide greater liquidity and a route for investors to exit their private investments via a listing, enabling capital recycling / - Allows listed companies to attract new investments, which in turn can support products to scale and replicate, overall strengthening local capital markets / - Reduce the cost of capital throughout the economy as banks and other lenders must take into account the existence of a low-cost capital market alternative when setting credit conditions and interest rates / - Contribute to greater macroeconomic stability and sustainable economic development / Box 2: MOBILIST achievements / MOBILIST has created ‘firsts’ in public market mobilisation for development and the climate by: / - enabling the first ever developing market portfolio of renewable assets to list on the premium segment of the London Stock Exchange (AEIT); / - demonstrating the first use of donor capital to anchor an Infrastructure Asset Backed Securitisation (helping banks and MDBs green their balance sheets at an accelerated rate) (Bayfront BIC IV), supporting MDBs to securitise through research, policy advocacy and potential further investment; / - anchoring through investment the first dedicated commercial climate fund for Sub-Saharan Africa and (CLEAR Fund); / - creating the world’s first hard currency green guarantee provider (Green Guarantee Company); / - publishing research on creating demonstration effects through investing, impact-additionality as a public markets investor and improving public market data tools such as indices, as a thought leader on public markets mobilisation.
[note] Throughout the Business Case Addendum, there is reference to ‘EMDEs’ as a market grouping in the context of MOBILIST investments; and to the ‘Global South’ or partners in the Global South in the context of MOBILIST’s strategy and how this feeds into FCDO/ HMG’s international development strategy and objectives.
[note] OECD. 2024. 'International aid rises in 2023 with increased support to Ukraine and humanitarian needs’.
[note] The following sources underpin this statement: 1. Sifma. 2024. Capital Markets Fact Book 2024. Public markets capitalization estimated at $230trn. 2. McKinsey. 2024. Global Private Markets Review 2024. Private markets assets under management estimated at $13.1trn. 3. Per the G20 ‘Independent Review of the Multilateral Development Banks’ Capital Adequacy Frameworks’ (2022), MDB assets are estimated at $2trn.
[note] Mobilist website. Last accessed 31 October 2024.
[note] G20. Independent Review of Multilateral Development Banks’ Capital Adequacy Frameworks (Secondary Source: MEF Department of Treasury).
[note] For instance, with respect to the Bayfront BIC IV Infrastructure Asset Backed Securitisation, MOBILIST provided a £4m equity investment into a $410m securitisation vehicle that listed on the Singapore Stock Exchange. While the transaction did not involve MDB assets, it does provide an example of how the G20’s recommendations on MDB reform can be implemented. It shows how MDBs could use securitisation as an exit-mobilisation instrument to increase their lending capacity and deploy more capital.
[note] Securitisation can be a powerful tool for capital mobilisation because it enables banks – whether commercial or Multilateral Development Banks (MDBs) – to transform the long-term loans on their balance sheets into tradeable securities that can be sold to institutional investors, like pension funds and insurers. This means MDBs and banks can use the proceeds for new projects or loans. Securitisation can also reduce the cost of funding for new projects, because a diversified and collaterised portfolio of securities remote to the banks’s balance sheet can often obtain a higher credit rating than the bank itself.
[note] Attridge, S., Getzel, B., Gregory, N. ODI. 2024. ‘Trillions or billions? Reassessing the potential for European institutional investment in emerging markets and developing economies’
[note] MOBILIST calculates mobilisation ratios based on the OECD’s (Organisation for Economic Co-operation and Development) Development Assistance Committee (DAC) methodology. Direct overall comparisons of MOBILIST to other programmes are limited because MOBILIST covers multiple asset classes and modes of mobilisation. At the time of writing, the Helios CLEAR fund has reached first close, mobilising US$203m in investor capital. We await final details and this number is not included in the programme’s mobilisation figures.
[note] MOBILIST uses OECD DAC methodology to attribute private capital mobilised proportionate to amount invested and risk taken.
[note] From publicly reported information for investees that have deployed capital.

What is the objective of the cost extension or other changes?
How the context for MOBILIST changed / There is growing pressure across the climate and developing finance agenda to provide finance at scale and to tap into innovative financing solutions. In addition to the context on GFS reform noted previously, other key shifts relevant to the capital markets context are as follows. / Progress on the SDGs: The sustainable financing gap in developing countries has become more urgent and acute, with only six years left to achieve the SDGs. Developed country providers of aid funding will face heightened pressure to deliver on the SDGs, not least because of the growing prominence of the global financial system reform agenda and in the lead up to high-profile summits such as the 4th International Conference on Financing for Development in 2025. It will be critical to come forward with credible solutions, such as demonstrating the potential of public markets. The urgency of the development finance agenda also presents an opportunity to encourage other donors, MDBs and DFIs to join the conversation about how innovative public markets vehicles such as MOBILIST can shift the dial. / Climate finance: Moreover, financing the climate challenge will continue to be a focus for developing countries and EMDEs. At COP29, parties to the UNFCCC will come together to agree a post-2025 climate finance goal to follow on from the current goal for developed countries to provide $100bn a year for climate action. Based on recent estimates, EMDEs (excluding China) will need to spend c.$2.4trn a year by 2030 on climate action. The delta between public finance available from traditional developed country donors ($115.5bn in 2022) and estimated costs is significant. Moreover, the Paris Agreement outlines the ambition to make all finance flows consistent with a pathway towards low greenhouse gas emissions and climate-resilient development. As such, there will be an expectation from developing countries to see credible signals, whereby governments collaborate with the private sector to finance the climate transition. / Broad market shifts: Investor groups are increasingly conscious that more investment needs to flow into EMDEs to support the SDGs, including the climate transition. Several of the large investor groups have EMDE-focused working groups; and the UK Government recently called upon a group of UK institutional investors to assess recommendations to unlock capital towards EMDEs. However, institutional investors face challenges due to higher investment costs and limited opportunities to invest in EMDEs. Assets therefore tend to be concentrated in private markets within larger EMDEs – but these typically have higher transaction costs and less liquidity than public markets. / Although the market environment remains challenging, emerging market assets are becoming more attractive as interest rates in the US and developed countries begin to fall. MOBILIST can harness this investor confidence by supporting the supply of listed assets which meets their scale and liquidity needs, broadening the investment context beyond larger emerging markets. Feedback from market participants demonstrates that investors are seeking greater nuance in emerging markets as an asset class, recognizing there are growth and diversification opportunities outside the large markets. Currently this market gap means investors are primarily investing in higher cost illiquid private markets. / Why is the time extension requested? / This addendum requests a further one-year extension to the project end date to September 2030. While the aim is to allocate £25m/ year through the prospective £100m FT uplift, the time extension will allow the MOBILIST programme flexibility to deliver the uplift even in a scenario where annual allocations fall below £25m/ year. / Why is the cost extension requested? / MOBILIST is at an inflection point as a programme / As the first donor programme of its kind, MOBILIST has acted as a demonstrator since inception. This comprises a portfolio of six investment transactions including a range of instruments; 9 stock exchange partnerships; and a research portfolio that has elicited learning about the programme’s impact. After 4 years, the programme has a growing evidence base to demonstrate the significance of public markets to finance development and climate action at scale. The programme also has growing name recognition within the development finance community. / The next stage will be to capitalise on these gains. In addition to their standalone impact, the FT uplift will allow MOBILIST to further build the portfolio of listable products, extract replicable policy knowledge, access new sectors within the development and climate space, and give MOBILIST the scale to operate as a commercially viable standalone entity. This will provide a springboard to expand the programme’s evidence base to drive policy change within the wider financial system. / An uplift of up to £100m non-fiscal CDEL (FT) will support delivery of MOBILIST’s investment strategy / The three pillars of MOBILIST’s investment strategy are to: / Build a portfolio of diversified investment and demonstration transactions and support the development of innovative instruments and new asset classes in EMDE public markets. This aims to drive adoption, replication and scale for new instruments and asset classes. / Ensure that these align with the principles of GFS reform to support the transformation of MDB business models for climate and development finance, with a view to increasing private capital mobilised through public markets for climate and development in EMDEs. / Use FCDO’s equity participation to leverage private capital, support relevant investments to grow, support liquidity and, ultimately, to allow FCDO to exit the investment. This will enable ODA reflows back to FCDO which can then be redeployed. / Delivering this investment strategy will pave the way for private capital mobilisation to support delivery of the SDGs, to finance the climate and energy transition and support the real economy in the Global South. A funding uplift will also continue to support HMG’s commitment to provide £11.6bn of ICF financing by March 2026 and UK commitments to triple UK spend on adaptation internationally from £500 million in 2019, to £1.5 billion in 2025. Within the current portfolio, MOBILIST investee ‘CLEAR Fund’ aims to be the largest adaptation fund for Africa, while investee Green Guarantee Company (GGC) includes adaptation as a clear part of its business mandate. / Establish a path to MOBILIST 2.0 / The MOBILIST team is developing indicative options for the future delivery model of MOBILIST in late 2024 for discussion at the Financial Transactions Steering Board (FTSB). This will include commercial, legal and FCDO Finance advice on options for MOBILIST as a standalone entity, such as a Special Purpose Vehicle (SPV) or other arrangement. This would enable MOBILIST investments to be held a step away from direct HMG balance sheet holdings, enabling the benefit of diversification and financial efficiencies not currently possible as a series of separate holdings. It would also allow for an evolution of the governance structure beyond the current role played by FCDO acting on specialist technical advice. This shift would be subject to discussions with BII and PIDG, and with donor funding partners to MOBILIST, Norad, SECO and USAID. If required, a new Business Case would be submitted to Ministers in 2025/26. Continue building a portfolio of demonstration transactions in public markets / Support the supply of EMDE listed products by investing in existing product strategies and asset classes to establish their viability in developing countries. This would demonstrate that existing products that are established and well known by investors in developed markets or large emerging markets can be applied to finance sustainable development in EMDEs. Examples from MOBILIST’s pipeline include: Corporate IPOs, YieldCos (i.e high yileding operational assets), standard and familiar Investment Trusts (including Real Estate Investment Trusts or ‘REITs’), Exchange Traded Funds (ETFs) and portfolio strategies in sectors such as renewable energy, infrastructure, health and agriculture. To support the scaling and replication of such products, MOBILIST could further test how to shift institutional demand by considering a wider set of issues inhibiting the flow of capital between and within capital markets. For instance, it could focus on new areas of market building and efficiency, such as market making roles to support liquidity and tackle other constraints and support the provision of more market tools to improve the quality of information and flow to investors. / Demonstrate new and innovative transactions that have the potential for scale across EMDEs and are well-suited to financing their sustainable development. This could involve repeat transactions to generate comparable investments and build an asset class. Examples from MOBILIST’s portfolio and pipeline include the securitization of development finance assets, hard currency guarantee platform for green projects and, a listed debt and equity fund targeting gender equality. / Support Global Financial System reform by continuing to demonstrate how public markets support MDBs to mobilise at scale and stretch balance sheets through capital recycling instruments and exits. As the first development finance actor to provide equity financing to a securitisation vehicle, MOBILIST has been a leader in demonstrating securitisation as an exit-mobilisation instrument to increase MDB lending capacity and deploy more capital. With further investment capital (along with its research and technical assistance capacity) MOBILIST would be able to support the scaling of such an instrument across MDBs and DFIs. / Mobilise climate and nature finance in EMDEs. Given the nature of public markets, investments to date have largely been in renewables. There is scope for MOBILIST, as a leader in the intersection of public market and development finance, to consider the public markets investment case for a broader range of green sectors such as transport, industry, green infrastructure and housing, and energy efficiency. The programme could consider how to support products in novel and underinvested sectors, or relevant to SIDS and climate vulnerable countries, with a pathway to listing (for example adaptation, nature and biodiversity). / Broaden and deepen MOBILIST partnerships and offer in the Global South. The requested funding uplift will allow MOBILIST to establish a wider equity offer to new geographies and deepen the offer in geographies where MOBILIST is already a presence. MOBILIST is working to establish new exchange partnerships across Asia, Latin America and Africa, an approach which has already delivered comprehensive policy coordination of public market exchanges on a global scale. Additional funding will support this process, allowing for a strategic assessment of those geographies most important to the climate transition; and further expanding partnerships, including in Africa, enabling the UK to be positioned as the key donor interlocutor with public markets around the world. / Strategic alignment with UK foreign and domestic policy: / Through the programme’s ability to bring public market stakeholders and infrastructure (like exchanges) to the table, MOBILIST can strengthen the UK’s capital markets offer to developing countries. The programme can support the HMG network to be a key partner to capital markets globally, and can fill a critical investment and policy gap where other parts of the UK development finance toolkit have a more limited remit. By anchoring listings on the London Stock Exchange, MOBILIST is also a valuable partner of choice to the City of London, strengthening its activities as a development finance hub by helping link London’s expertise and capital to diverse capital markets. / Further, MOBILIST responds to UK Ministerial priorities on private capital mobilisation: faster reform of the global financial system for climate, nature and development, leveraging our position as a global sustainable financial hub through the City of London; sustainable economic development that delivers opportunity for all and modernising development resetting our relationship with the Global South by listening to the challenges partners face to unlocking investment and collaborating on solutions.
[note] Songwe-Stern, Grantham Research Institute on climate change and the environment. 2022. Finance for climate action: scaling up investment for climate and development.
[note] OECD. 2024. Climate Finance Provided and Mobilised by Developed Countries in 2013-2022.
[note] The Paris Agreement. UNFCCC. 2015. The Paris Agreement – Publication. Article 2.1c.
[note] Attridge, S., Getzel, B., Gregory, N. ODI. 2024. ‘Trillions or billions? Reassessing the potential for European institutional investment in emerging markets and developing economies’
[note] Based on conversations with frontier market fund managers, asset consultants and index providers.

What is the additional and total support the UK will provide?
This addendum seeks a Non-Fiscal CDEL (Financial Transactions) cost extension to the MOBILIST programme of up to £100m and a time extension of one year to September 2030. Non-Fiscal CDEL is an HMT-defined ring-fenced departmental budget which is part of the overall CDEL allocation for capital investment programmes. This will be overseen by FCDO’s Financial Transactions Steering Board (FTSB), which is responsible for strategy, policy and strategic financial management of FCDO’s portfolio of investment and guarantee financial instruments. / Capital will be deployed based on the pipeline of new transactions and timing for deployment is contingent on financial market conditions. The £100m uplift will be at least 62% ICF: this reflects the high supply of climate-aligned projects that have been sourced by the programme, while preserving flexibility for transactions that meet MOBILIST’s broad remit. / The remaining Business Case headroom available in 2025/26 is insufficient for the programme’s offer to exchanges and related intermediaries to remain viable. Partial FT funding for 2025/26 of up to £18m is available under the approved MOBILIST Business Case. Once deployed, there is a critical gap between forecast reflows from existing MOBILIST investments due to come on stream in 2026. / Additional funding of up to £100m and reflows sets MOBILIST on the path to become financially net-neutral. With an investment lifecycle of 3 to 5 years, we can expect the capital of £200m to allow MOBILIST to become a permanent presence in capital markets and driving public market mobilisation for years to come. The BCA will enable MOBILIST to increase the value of its investment portfolio to over £200m on a constant operating budget positioning the programme for design work under a further BCA ‘MOBILIST 2.0’ and consistent with BII’s model (whereby FT capital injections sit alongside reflows of approximately £1bn/year). It is anticipated that the uplift will enable programme overheads to fall to less than expected dividends (further detail in ‘Approach to Implementation’ under ‘Value for Money’. / Table 3: Programme expenditure across the current Business Case and the cost and time extension / Extension to be accommodated within FCDO’s International Finance Directorate budget for next SR period (2025/26). Total support detailed below, assuming FT is 62% ICF: / MOBILIST actual and forecast spend (£ millions) 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 2027/28 2028/29 2029/30 Totals / RDEL 0.40 1.50 1.61 1.73 1.63 2.40 3.30 3.30 3.43 1.65 20.95 / CDEL 0.74 0.90 0.94 0.96 0.96 4.50 / FT Subtotal 0.00 24.50 5.81 47.20 44.00 25.00 25.00 25.00 25.00 18.00 239.51 / Proportion ICF 100% 100% 75% 62% 62% 62% 62% 62% 62% 69% / FT, non-ICF, original BC 11.80 16.72 6.84 35.36 / FT, ICF, original BC 24.50 5.81 35.40 27.28 11.16 104.15 / FT, non-ICF, proposed BCA 2.66 9.50 9.50 9.50 6.84 38.00 / FT, ICF, proposed BCA 4.34 15.50 15.50 15.50 11.16 62.00 / Totals 0.40 26.74 8.32 49.87 46.59 28.36 28.30 28.30 28.43 19.65 264.96
[note] This business case addendum and any onward agreements with MOBILIST will have a break clause in March 2026.
[note] Indicative profiling is detailed in the table. MOBILIST’s FT allocations each year will continue to be determined by the Financial Transaction Steering Board (FTSB). HMG Spending Review settlements will also shape MOBILIST’s FT allocations

What are the expected results?
The additional funds provided will allow MOBILIST to continue building a portfolio of demonstration transactions in public markets, manage these investments and consider its longer-term structure. / MOBILIST can expect to deliver 3 new products in 2025 and 5-10 innovative and impactful investments over the remaining five years of the programme to September 2030. This is based on MOBILIST’s track record of completing between 1-3 investments each year and including recycled capital from reflows. / Increase the volume of private finance particularly institutional investment mobilised and contribute to the closing of climate and SDG financing gaps: by directly mobilising between £250m-£625m in private sector finance and catalysing a further £1.1bn to £2.9bn in indirect mobilisation of which a large majority will be from institutional investors. MOBILIST’s portfolio mobilisation ratio is currently 4.91 for its listed investments. / Results expected based on the current portfolio and pipeline: / Increase the supply of EMDE listed assets: Investments in MOBILIST’s current portfolio include corporate IPOs of i) financial institution (Thai Credit Bank); ii) renewable energy company (Citicore) and; iii) investment trust (AEIT). The pipeline includes i) an investment trust company of SSA renewable energy assets supporting the recycling of capital of project developers; ii) an investment trust investing in global emerging and frontier market equities supporting primary capital raising globally and; iii) an investment trust of agriculture credit in Latin America. These last three all have ambitions to list on the London Stock Exchange: as a portfolio, these would mark a step change in the role of UK institutional investors as financiers of EMDE assets on the London stock market. / Demonstrate new and innovative transactions: investments in MOBILIST’s portfolio also include the first hard currency green platform (Green Guarantee Company), establishing the infrastructure asset-backed securities as an asset class (Bayfront Infrastructure Capital IV), the first commercial African climate-focused private equity adaptation fund with ambition to list (Climate Energy Adaptation and Resilience (CLEAR)). MOBILIST’s pipeline includes the listing of a local currency guarantee platform supporting its shift to scale through private sector capital. This will be complemented by TA spend for product development which will also support the investment pipeline. / Support Global Financial System reform: Investments to support reform and FCDO’s objectives for MDBs and DFIs to ‘stretch’ or move assets off their balance sheets to free up space for more lending through ‘originate to distribute’ models and securitisation. Up to £20m for IFC’s Warehouse Enabled Securitised Platform (WESP) whose first issuance is expected to securitise $500m of IFC assets with plans to reach an annual issuance volume of $2-3 billion, freeing up significant balance sheet for new lending. Securitisation vehicles can expect very high mobilisation ratios: MOBILIST’s investment in BIC IV had a mobilisation ratio of 22.9. This investment will help to develop the asset class by demonstrating public markets as a viable exit for MDB/DFI assets and allow institutional investors to access development finance assets that meet their regulatory requirements. The size of the potential market of MDB private sector loans is circa $400 billion (12 largest MDBs). / Mobilise EMDE climate and nature finance: ICF spend of at least 62% across the portfolio, with the aim of mobilising £245m of private investment. Investments in MOBILIST’s current portfolio with a strong climate focus include: CLEAR (the first African commercial climate fund with an adaptation and resilience component), AEIT, BIC IV, GGC, and Citicore. Technical Assistance spend will also help to develop the future public markets case for products that support investment into more challenging climate themes such as adaptation, nature and biodiversity (for example the pipeline includes a securitisation vehicle to support loans for adaptation and resilience in SIDS). We can expect to report results for ICF KPIs as follows: / KPI 6: Tonnes of greenhouse gas emissions reduced or avoided / KPI 7: Volume of clean energy capacity installed / KPI 12: Private finance leveraged / Opportunities to support transactions with clear gender, disability and inclusion impact: in line with the 2X Challenge, MOBILIST addresses gender inclusion by assessing investees’ SDG 5 Gender Equality alignment and any gender-related development impacts, including female jobs directly created. Whilst neither of the 2023 listed investees reported specific operational strategies or initiatives for SDG 5, Thai Credit Bank, a 2024 listed investee, has a particular focus on women and female economic empowerment. Going forward, MOBILIST will actively further explore opportunities with a gender lens focus in its programming, as part of the programme’s assessment of transaction-specific ex-ante development impact, and in line with HMG international development priorities. / Exits and reflows: MOBILIST expects its investments to have a lifecycle of three to five years. Re-flows from the current portfolio are not anticipated until H2 2026 (although as listed products, FCDO can exit its investments at any time). From H2 2026 to 2029 it is currently expected that 60% of the invested portfolio – approximately £50m – will be returned to FCDO in the form of capital repatriation and dividends. This is detailed further below in ‘Approach to implementation’ under ‘Value for Money – Reflows’; and will be part of MOBILIST’s evolution towards a model of steady-state financial net-neutrality, as detailed in ‘Approach to implementation’ under ‘Value for Money – Efficiency’ / Deepening and enhancing partnerships with the Global South: MOBILIST will develop partnerships with at least 2-3 further stock exchanges, broadening its reach and increasing the benefit of lesson learning across the markets in which it operates. It will also deepen its 9 existing Stock Exchange Partnerships to continue to translate these high-level engagements into impactful and high-profile investments enabled and supported by the programme. The investments MOBILIST expects to make during the programme period can be considered complementary to, and also a direct result from, its partnership feeder network. By the same token, through these partnerships, MOBILIST will continue to leverage the value of its investments to ongoing policy dialogues which promote private sector capital mobilisation using listed markets, working in coordination with key Posts around the world. / Building the City of London as a global green financial centre: MOBILIST’s first partnership was with the London Stock Exchange and its first investment was anchoring an IPO on the premium exchange, including the first portfolio of EMDE renewable assets. Given MOBILIST’s objective in mobilising institutional capital and the City of London as a hub for EMDE finance, the additional funding from the BCA will see this partnership strengthen as we target at least three more listings on the LSE (under current pipeline and given market conditions). / Building out the learnings attributable to MOBILIST’s investments to accelerate replication and reform priorities: underlying these results will be a robust research agenda and MEL framework. MOBILIST has extensive research capability. Based on existing transactions, the programme has examined the key policy shifts that have the potential to unlock finance at scale, in relation to securitisation, guarantees and the programme’s general demonstration effects. Building a portfolio of evidence from MOBILIST transactions is key to influencing policy makers, financial sector actors including MDBs and DFIs, other ODA providers and aid-providing governments to tap into the opportunity that public markets offer. / Upgrading the MEL framework: MOBILIST has started to implement a MEL Evidence Platform and MEL Dashboard to capture log frame results and investee financial and impact reporting. Under this BCA, a full MEL framework will be delivered in the first six months to monitor results in line with public market reporting. In this next phase of MOBILIST, the MEL framework will monitor results on gender, adaptation, nature and climate vulnerable countries (see ‘Monitoring, Evaluation and Learning’ sub-section under ‘Approach to Implementation’ for more detail).
[note] Note that alignment (which MOBILIST is), and being 2X qualified, which is officially recognised.
[note] The MOBILIST portfolio is 2X aligned in the following ways: i. MOBILIST meets the basic 2X ESG and minimum Governance & Accountability requirements ii. MOBILIST can commit to fully meeting Criterion 3 through the ESMS within the next year. MOBILIST already reports share of jobs created that are for females and we can add an additional "quality employment indicator" to the ESMS. iii. MOBILIST meets Criterion 6B Portfolio for Funds (30-50% of portfolio) as three of the six portfolio investees (AEIT, GGC, TCB) meet the 2X criteria.
[note] AEIT measured gender impacts as part of its Social and Employee Matters indicators.

Approach to implementation
GOVERNANCE / MOBILIST investments sit on HMG’s balance sheet and are managed by a FCDO programme team with an SRO and PRO. / The Financial Transactions Steering Board (FTSB) Chaired by the DG Humanitarian and Development is a sub-committee of the Investment and Delivery Committee, responsible for strategy, policy and strategic financial management of FCDO’s portfolio of investment and guarantee financial instruments. FTSB reviews and oversees the Financial Transactions (FT) or Non-Fiscal CDEL element of the portfolio. FTSB is responsible for oversight of all FT programmes in FCDO, receives regular updates on the programme and can instruct a particular course of action if required. / Figure 2: Investment decision making governance structure: / Decision-Making Committee (DMC) is the approving body for MOBILIST investments. Its purpose is to oversee, review and approve recommendations put before it by the MOBILIST programme. DMC is responsible for ensuring that there is specific FCDO appetite for each investment against identified criteria and risks. Membership comprises FCDO Director of International Finance (IFD); FCDO Deputy Director and Head of Private Sector and Capital Markets Department; FCDO Deputy Director of Finance, Commercial and Delivery; FCDO DD Finance Business Partnering, and HMT Deputy Director of Global Financial Markets. / Steering Committee (SteerCo) is a sub-ordinate governance body to the DMC which provides market intelligence, technical advice and challenge for the delivery of the MOBILIST programme across product and policy and research work streams. This informs the wider strategy and context for DMC to reflect upon in its review of individual investments. SteerCo comprises bilateral partners Norway, Switzerland, and the US, senior independent financial sector figures (BII, the Impact Investing Institute) and SCS. Due to changes in members’ availability SteerCo will be strengthened to provide advice and guidance to FCDO’s MOBILIST team with respect to specific interventions in 2025 (and through to 2029). / The SRO oversees the ‘S3’ process set out below and operates the governance of the programme including reporting, makes recommendations to the Decision-Making Committee, and oversees and draws upon advice from within the FCDO MOBILIST team. / Source- Select- Support – the ‘S3’ MOBILIST process: / MOBILIST operates a robust three-stage Source-Select-Support’ (“the S3 process”), supported by a range of expert technical suppliers, including BII, building a pipeline of potential investment transactions and technical assistance opportunities that results in recommendations to Decision Makers. The S3 process is delivered by suppliers 18East Capital, Palladium Impact Capital, Chemonics, Dentons, other specialist advisors, and designated BII infrastructure specialists. As pipeline transactions reach readiness to go to market, the S3 process informs a recommendation from the SRO to support. / MOBILIST Sources investments by leveraging capital market infrastructure of its 9 partner stock exchanges around the world, to identify transactions that can mobilise private capital towards development. / Applications must be backed by sponsors (e.g. brokers and associated intermediaries) as licensed third-party endorsement of transaction readiness. / Eligibility assessment involves preliminary due diligence on transaction readiness and preparation for HMG gating process / Advancement through to more detail due diligence is then approval by DMC, which leads to the Select stage. / The Select function of the S3 process is designed to evaluate and identify proposal against five clear criteria: (i) additionality, (ii) feasibility, (iii) scalability, (iv) replicability and (v) viability, using a competitive market-based process. / Due diligence is undertaken comprising: / assessment internal to the programme, including from specialist advisers and contracted specialists with specific market or sector expertise relating to the target investee / external diligence commissioned by MOBILIST from some of the leading private risk assessment firms, tendered by competitive process / commercial legal assessment from one of the UK’s leading law firms, Dentons, supplemented as necessary by jurisdiction and product-specific external legal advisory / Due diligence assesses operational, financial, reputational, environmental and governance risks, is supported by dedicated advisory support from BII. / Additionally, MOBILIST applies International Finance Corporation's (IFC) Performance Standards as a key non-commercial investment screen, which is among the most well-adopted emerging and frontier market investment standards. / MOBILIST’s investment requirements also include FCDO policies related to fossil fuels and gender inclusion, the Task Force on Climate-Related Financial Disclosures (TCFD)’s analysis of climate-related risks, and BII scoring of development impact. / Transactions successfully passing due diligence which are ready to go to market then progress to the Support stage. / The Support function of the S3 process is designed to provide products graduating from the Select function with support in the form capital investment. This involves: / Determining amount of support: An underwriting approach is used to deliver the most efficient use of the funding made available by FCDO. This means that the amount of capital invested will be reduced should the product launch above a specified threshold size. / Validation of valuation: All investments are appraised for commercial viability prior to any investment by MOBILIST and are expected to maintain their value plus earn return over the period during which they are held. / Contracting: Following approval from decision makers, the team moves to execute/ close through MOBILIST’s nominated brokers (Shore Capital, UBS, etc.), including for private vehicles/ Limited Partnership Agreements. / All legal documentation is reviewed and approved by FCDO’s Finance Director, supported by assurance from MOBILIST’s commercial legal representatives, Dentons. Legal agreements are confined to only those investments that are structured as private vehicles, typically as partnership agreements (for listed products FCDO retains a share certificate but has not legal agreement with the target entity as such). / MOBILIST post-investment monitoring is then calibrated to the type of transaction. Publicly traded investments are monitored through public information platforms and interaction with analysts at the investment banks covering the market. Privately held instruments each have a dedicated monitoring lead. / Equity investments are made on the premise of an exit within 3 – 5 years, and the programme expects multiple exits during the remaining programme lifespan. Transactions within the current portfolio include: / two transactions which will automatically exit and return funds within the programme lifespan; / two publicly tradable listed investments exits from which exit will be recommended to DMC in line with MOBILIST’s internal “Exit strategy for public markets instruments”; / two privately held transactions which may return dividends but for full exit will either need to be sold on, exited through IPO, or undergo other bespoke means of redemption. / RISK / This section sets out the approach to financial risk being developed within the programme. / The risk profile of investments under this BCA are materially unchanged from the previous Business Case for investment capital, with no change in investment selection process proposed at the current point in time. Net risks after mitigations across HMG’s seven standard risk categories is set out at Annex 4. The MOBILIST Policy Platform’s risk register is included separately at Annex 5. / MOBILIST seeks to preserve its invested capital based on a commercial approach taken to investments. This is expected as the number of transactions increases and some benefits from diversification start to occur, translating over time to smoothed-out and more predictable financial results as systemic risk is reduced through diversification. Some specific risks will remain . / MOBLIST seeks to manage risk by selecting transactions in line with the Governance process outlined above, particularly: / Investing in line with private sector appetite on a ‘Pari passu’ basis, not on a concessional basis, although it is understood that different product structures may see commercial returns achieved over differing time horizons / Involving BII in each investment decision / Due diligence guided by carefully selected technical advisers / The programme always seeks to invest the minimum level of equity capital while delivering the greatest impact and enabling a successful listing, using what is termed an “underwriting approach.” This limits the size of investments made by the programme to the amount necessary in order to achieve the desired impact. / MOBILIST’s approach to investment risk is to be ‘risk aware’ rather than ‘risk averse’, subject to these criteria. A key point of risk-return calibration is alignment with commercial private sector capital seeking a market level of risk-return. This approach means that the programme does take investment risk and will make both losses and gains across its investments, resulting in an eventual non-neutral net result. / The public display of prices of exchange tradable instruments can also exhibit face-value volatility but MOBILIST investments only realise an actual gain or loss at the point at which an exit is made. Wider market conditions outside of investee performance affect the face value indicated by public prices. MOBILIST monitors the prices and trading volumes of its listed investments regularly, with the objective of identifying exit opportunities in line with its strategy. / A portion of the portfolio is also exposed to FX risk, exposing investments to FX gains and losses even when the nominal investment value has been maintained. / On the basis of the increased size of portfolio resulting from the investments made under this BCA, a standardised set of risk and portfolio procedures will be needed: as the existing round of 6 investments moves to a wider set of up to 12 investments, there will need to be a move from idiosyncratic monitoring procedures to a set of standard practices. / Risk appetite in relation to the investment selection criteria will be reviewed at the conclusion of this phase of programme, at which point the portfolio will have reached a critical mass and thus will provide an opportunity to reflect on the structure of the programme for managing investment risk. This includes the translation of currency risks into financial results, the management of reflows and reinvestment, and the ability to benefit from diversification of gains and losses made across the portfolio. / FINANCE / Affordability/ Budget Flexibility: the BCA seeks ‘up to £100m’ and including a break clause at end of 25/26. Assuming a flat/rollover Financial Transaction budget into Phase 2 of the SR, £25m per annum represents 4% of the total ringfence FT budget and would be managed within IFD/ PSCMD’s future resource allocation. / There is flexibility within the MOBILIST pipeline and investment decision making process to scale up or down depending on budget availability. This is deemed a reasonable budget assumption with investments of £87m to date over 3 years. Investments are expected to be at least 62% ICF eligible. / Valuation and ODA scoring: / MOBILIST's aim is to invest primarily in publicly traded investments. The valuation is therefore derived from the actively traded share price and is publicly available. / Only investments that are not listed would require initial measurement at cost and require independent external valuations to be carried out at least annually for FCDO year-end (31st March) reporting requirements. Valuation movements throughout the lifecycle of the investment will score to R-AME budget. / Subsequent accounting follows the Fair Value through Other Comprehensive Income (FVOCI) method, in line with most of FCDO’s existing investment assets. This means that increases in value pass into FCDO’s reserves while impairments impact Annually Managed Expenditure (R-AME). / Dividends received, or costs incurred by FCDO in respect of each investment are reported under Resource Departmental Expenditure Limit (RDEL). / The MOBILIST team is developing indicative options for the future delivery model of MOBILIST in late 2024 for discussion at the Financial Transactions Steering Board (FTSB). This will include commercial, legal and FCDO Finance advice on options for MOBILIST as a standalone entity, such as a Special Purpose Vehicle (SPV) or other arrangement. This would enable MOBILIST investments to be held a step away from direct HMG balance sheet holdings, enabling the benefit of diversification and financial efficiencies not currently possible as a series of separate holdings. It would also allow for an evolution of the governance structure beyond the current role played by FCDO acting on specialist technical advice. This shift would be subject to discussions with BII and PIDG, and with donor funding partners to MOBILIST, Norad, SECO and USAID. If required, a new Business Case would be submitted to Ministers in 2025/26. / Reflows and Exits: / ODA reflows from equity sales: / Capital reflows as exits from equity investments (i.e. where the proceeds are returned directly to FCDO) are returned as negative ODA Non-Fiscal CDEL, where the initial investments was 100% ODA eligible. These are challenging to forecast from a budget perspective due to the market-linked uncertainty of the timing and quantum. Where there is not a mechanism to recycle the investment within the investment structure, they are returned to FCDO and managed through in-year financial monitoring within the parameters of the FT ringfence. Under current SR 21 arrangements, these will be returned to FCDO as negative FT ODA, and it is for the Financial Transactions Steering Board to determine whether to reallocate these to the MOBILIST programme within the parameters of any SR period. / Capital reflows as exits from equity investments (i.e. where the proceeds are returned directly to FCDO) are returned as negative ODA Non-Fiscal CDEL, where the initial investments was 100% ODA eligible. These are challenging to forecast from a budget perspective due to the market-linked uncertainty of the timing and quantum. Where there is not a mechanism to recycle the investment within the investment structure, they are returned to FCDO and managed through in-year financial monitoring within the parameters of the FT ringfence. Under current SR 21 arrangements, these will be returned to FCDO as negative FT ODA35, Under the current Framework, the Financial Transactions Steering Board determine whether to reallocate these to the MOBILIST programme within the parameters of any SR period. / Gains and Losses on Exit: / On exit of an investment, a gain or loss will arise which will have a DEL impact. Losses/ write off in value of the investment scores to non-ODA RDEL where the initial investment scored 100% to ODA. Discretionary Non-ODA budget is limited in FCDO and any likely impacts would need to be monitored and managed into the next SR. . This is a budget risk for this type of programme under its current structure where investments are made directly by FCDO and not through a separate investment entity. MOBILIST 2.0 will seek to address and mitigate this risk. Today, this risk is managed throughout the lifecycle of the programme, but as public market listed investments with daily pricing and liquidity, price movements (volatility) is a function of public market investments. / Decision-making around exits: / Typically, MOBILIST decisionmakers will provide direction to the programme in relation to future exit approaches and have previously instructed MOBILIST to only provide a ‘liquidity role’ i.e. sell down FCDO’s holdings to provide liquidity to the market when this is achieved at a price higher than the initial strike price (TCRB). At all times, MOBILIST seeks to manage exit-timings at a point where the exit price is at par or better. MOBILIST’s exit policy is contained in Annex 1. / Redeployment of returned funds: / Given the strong investment pipeline of around £284m (FCDO’s forecast contribution towards investible products) as of July 2024, the programme will aim to redeploy any negative ODA reflows within the respective ODA reporting (calendar) year. This comparatively rapid recycling of investment capital is a core principle and objective of the MOBILIST programme. / Timing of redeployment: / At present there is no ability to carry forward into future year budgets any reflows that cannot be redeployed in the same FY. Market-driven uncertainties around timing of transaction mean that this constraint limits financial efficiency, simplicity, and ability of the programme to be financially net-neutral within a near-term time frame. Potential resolutions to enable this will require consideration during the course of the programme, subject to approval of in-scoping MOBILIST 2.0 recommendations, Spending Review considerations, and consistent with FCDO’s financial accounting principles. / Financial Breakeven: / Increasing MOBILIST’s equity portfolio by up to £100m opens up new avenues for the future direction of MOBILIST and could accelerate the programme’s journey towards becoming financially net-neutral in a steady state, as well as delivering increased impact, as outlined under ‘Efficiency’ in the ‘Value for Money’ section below. / A critical mass of performing investments could, at this level, provide sufficient income to cover operational costs, if such costs are appropriately managed. Dividends from investments provide a degree of regular income that could cover operating costs, while exits at or above the amount originally invested could provide additional income on an event-driven basis. / Value for Money (VfM): / The VfM case for MOBILIST has not materially changed since the original Business Case. As set out in Value for Money statement in the Business Case: the value for money for the programme broadly hinges on three key aspects of its design and theory of change – namely (a) the focus on mobilising investment capital specifically through public markets; (b) the way it does this by supporting the creation of a set of new listed investment products that are replicable and scalable and; (c) how the new listed products that will be developed are selected and their respective theories of change, leading ultimately to more sustainable investment in developing countries. / MOBILIST invests Pari passu with the private sector to demonstrate the commercial viability of the investment in order to reach scale and replication through public markets’ unique characteristics of transparency, price signals and lower transaction costs. This will ensure that FCDO support to the creation of markets is scalable and sustainable. / The FCDO’s latest Annual Review (2022/23) notes that the programme continues to represent good VfM, delivering within a challenging but impactful section of the market while taking steps to meet the VfM metrics. / Economy / The basis for investing is one both of capital preservation and the recycling of that capital by the programme and/ or FCDO every 3-4 years. This represents significant value to FCDO and ODA budgeting considerations: the programme buys results repeatedly using the same or growing capital base. / The application of FT on commercial terms ensures FCDO is a ‘Pari passu’ investor (on equal terms) with other investors. MOBILIST does not seek to take a first loss exposure and can expect a commercial return which may be re-invested into the programme or re-allocated to other FCDO needs. / Lead supplier contracts with FCDO are a primarily milestone-based, meaning that the supplier holds the risk of milestones not being delivered regardless of the level of inputs. As such, where the supplier has taken additional time or inputs to achieve milestones or deliverables, this is at no extra cost to FCDO. / Lead suppliers in turn sub-contract for specific services, for example relating to external due diligence for prospective investments, which follow a competitive sourcing process. This process includes the ongoing collection of market costs to improve the accuracy of cost projections, and more flexible RDEL budget allocations across workstreams for more efficient response to programme and market needs. / The feeder network model utilises intermediary organisations (primarily investment banks) to help the programme identify and match potential product applicants. These intermediaries are not paid for their time or efforts but are incentivised to work with MOBILIST because they receive payment from the product once a listing is achieved. / Efficiency / With MOBILIST’s operating budget approved to 2029, approval of this BCA will enable MOBILIST to increase the value of its investment portfolio to over £200m on a constant operating budget. / This will enable overheads to drop to less than 2% of assets under management. Annual running costs of the programme by the end of the deployment period are £3.4m. A hypothetical income level of 2% across the portfolio, if achieved from an asset base of over £200m, would therefore exceed the platform’s projected annual running costs. / Operating costs are kept efficient by the MOBILIST Policy Platform (MPP) clearly gating proposals to avoid spending significant amount of time on products that ultimately do not apply to MOBILIST. To achieve VfM, the Product Platform clearly and publicly articulates the MOBILIST offer and determines at the application stage whether products are suitable or not. Subsequently, products enter the formal pipeline, which entails more significant resource to assess and progress. / Intermediaries and exchanges are incentivised as part of this process because if products they support secure investment and are eventually listed, they benefit financially through a fee. These mutual incentives means that these partnerships come at no extra cost to MPP and help improve the efficiency of the process. By leveraging the infrastructure that already exists in capital markets in this way, the MPP is able to strengthen the quality of the applications received. / By developing its partner relationships while maintaining an active investment mandate across partner exchanges, MOBILIST continues to improve the number of high-quality applications received in future, which further improves the efficiency of the process. / Effectiveness / MOBILIST has proven its ability to deploy FT consistent with annual budget allocations, and into impactful products, having now invested £87.7m across six products. / Through the four investments which have directly created listed products, MOBILIST has been able to leverage scarce ODA funds of £50.4m to mobilise £247.5m of private capital to date (using OECD methodology to calculate attribution). A total of £492.8m private capital and £104.6m public capital (besides FCDO) was involved in these products (AEIT, BIC4, TCRB, CREC). / The effectiveness of the programme’s implementation is reflected in the increase over time of applications generated per funding round, the size and credibility of requests, and the quality of counterparts. The number of applications has trended upwards over time as more intermediaries and exchanges have been brought in as partners able to introduce products to MOBILIST, and as large international institutions have come to perceive MOBILIST as a credible institution with which there is merit in investing time and effort. / Operating effectiveness is measured and incentivised using the Logframe indicator OP1.2 Proportion (%) of selected products that receive support through investment and/or TA – Select and Support”, which seeks to capture a combination of quality and quantity of products that are presented to FCDO. This incentivises MPP to create and progress a healthy pipeline, and to bring only quality products to FCDO for TA and investment decisions. / Equity / Equity focuses on the fairness of impact, namely the degree to which the results of the intervention are distributed. MOBILIST’s S3 assessment process includes a range of assessment metrics and checkpoints, ensuring MOBILIST is only exposed to ODA-eligible countries, assessing priority countries, ICF/ climate targets, gender impacts and expected impact on the real economy. MOBILIST is currently providing TA to support the listing of Amundi’s first listed gender bond for EMDEs. Along with the gender-impacting Thai Credit Bank transaction, the programme is building a strong gender focus. / The programme makes investment decisions based on an assessment of historic and expected development impact. These include compliance against the full range of IFC Performance Standards. MOBILIST favourably views investments that deliver gender impact in line with SDG5: Gender Equality. To qualify for the 2X Challenge, an investment must already meet – or have an explicit commitment to meet – at least one of a list of criteria related to female entrepreneurship, female leadership, female employment, product or service benefit to women, or financial investment that benefits women. / Suppliers have their own diversity, equality and inclusion strategies and targets. For instance, Chemonics’ CEO has supported the CEO DEI pledge to “Cultivate environments that support open dialogue on complex - and often difficult - conversations around diversity, equity and inclusion; implement and expand unconscious bias education and training; share best-known diversity, equity and inclusion programs/initiatives — as well as those that have been unsuccessful; and to engage boards of directors when developing and evaluating diversity, equity and inclusion strategies.” / Cost-effectiveness / Cost effectiveness within the programme is achieved using a variety of measures. Key standard practices include carefully defined scope of work for tenders and an emphasis on proposals presenting the best value, obtaining the desired quality and outcome at the lowest price possible. For example, MPP undertake a market survey and obtain multiple quotes before commissioning external due diligence. If contracts are expected to reach a threshold of £25,000 then FCDO have instructed MPP to submit a “Procurement Waiver Request Form”, setting out a description of services required, market survey with multiple quotes, and justification for selection of subcontractor, signed off by FCDO before proceeding. / Suppliers benefit from large corporate level agreements with IT vendors, freight companies and an in-house travel agency. MOBILIST has been able to benefit from the competitive pricing and cost efficiencies generated at the corporate level. / Grant funding from international partners / Additional funding of £2.5m, made available by the Norwegian Agency for Development Cooperation (Norad), has allowed MOBILIST to increase its reach, both in terms of geographic footprint and the types of assets and structures with which the platform can engage. / While FCDO funding provided the platform with the labour resources required to execute project activities, grant funding from NORAD was leveraged in a complementary manner to pay for services that otherwise could not have been delivered at this scale over the same time frame. MOBILIST has so far used NORAD funding to carry out additional outreach activities, conduct due diligence, and provide technical assistance funding. / MOBILIST takes a unique approach as a development finance programme, and having demonstrated proof of concept, is an attractive proposition for donors. Norad, SECO and USAID have all proposed future collaboration on the programme, which enhances the VfM of the programme for the UK, as UK funding will be complemented by likeminded international donors, allowing the programme to achieve more in the same time frame, and contribute to diplomatic relationships. / Monitoring, Evaluation and Learning / MOBILIST has a MEL Framework made up of a MEL Evidence Platform, and a MEL Dashboard. The Evidence Platform captures logframe results and learnings across the programme feeding back into Theory of Change updates, while the Dashboard captures key metrics across the investment portfolio including financials and impact metrics: / Total direct, additional and female employment created / Total emissions avoided, newly installed renewable energy capacity, renewable energy generated / Total investee capital deployed, total loans supplied by investees, share of investees in LDCs/LICs, Africa, average recipient country income / MOBILIST investment, AUM of MOBILIST funded products, average total return / Mobilisation ratio portfolio, listed products, total private finance mobilized, / SDG alignment / Investee tracking of IFC standards / For publicly listed investments MOBILIST must manage its investments in accordance with public market regulations and standards. This means that the programme cannot seek to access Material Non-public Information. Doing so would create restrictions on selling shares and exiting without breaching public market regulations. MOBILIST therefore monitors investments as would any commercial investor, relying on the reporting frameworks that are mandated by the exchange on regulations in the relevant jurisdiction. However, MOBILIST can add value to the quality of investees’ public reporting under these public market rules, by offering technical assistance to elevate their reporting capability and ensuring that investees’ reporting meets market standards and sets new standards in the quality of reporting, on ESG and impact. As the first donor programme of its kind in the public markets, there is a role to play going forward on how results are monitored that build and potentially innovate on standard practices in asset management. / Portfolio Management and Reporting / The portfolio is managed and reporting adheres to a comprehensive Investment policy framework. Portfolio financial performance, including the management of capital reflows to FCDO, will be supported by an upgraded portfolio management and ESMS system during the coming year. / The metrics in Figure 3 below are all being and will be tracked, provided they are publicly available. A key difference of MOBILIST as a public markets investor, as opposed to private markets investors, is that the programme does not seek to determine what investees report on. However, the programme does consider that framework as part of due diligence and can provide TA to upgrade reporting post-investment. There exist minimum reporting requirements for listed products, dependent on the stock exchange they are listed on. / Impact investment standard industry practices are also emerging for estimating impact with methodological integrity where granular self-reported information is not available, as is commonly the case in emerging markets. MOBILIST will seek to integrate such practices to enhance the consistency and completeness of its impact reporting. / In line with the 2X Challenge, MOBILIST addresses gender inclusion by assessing investees’ SDG 5 Gender Equality alignment and any gender-related development impacts, including female jobs directly created. Neither of the 2023 listed investees reported specific operational strategies or initiatives for SDG5. Going forward, MOBILIST will aim to redouble efforts to embed these aspects into programming, to demonstrate inclusive development impact. / Figure 3: MOBILIST data mapping for investees as of Q1 2024 (Data is coded blue for available, grey if potentially available, white if not available) / Investee AEIT Bayfront Citicore CLEAR GGC TCRB / Portfolio Year 2023 2024 2023 2024 2024 2023 2024 2024 2024 / Total Returns / Dividends per Share / MOBILIST Investment Amount / Private Sector Mobilisation / Mobilisation Ratio / SDG Alignment / GHG emissions (Scope 1,2,3 tonnes of CO2 equivalent / GHGs avoided (tonnes of CO2 equivalent / Total installed renewable energy capacity (MW) / Renewable energy generated (MWh) / Jobs directly created (FTE) / Female jobs created / Loans supplied
[note] The ‘feeder-network’ core to the S3 Source function will systematically build market intermediaries-based channels through which a pipeline of public market investment products conducive to sustainable development in ODA countries can be most effectively sourced.
[note] Beginning in FY3 Q4, the MOBILIST Policy Platform began to codify MOBILIST’s environmental and social policies related to the investment process into an Environmental and Social Management System (ESMS) document based on IFC Performance Standard 1: Assessment and Management of Environmental and Social Risks and Impacts.
[note] The MOBILIST ESMS will codify MOBILIST’s current investment policy and practice guidelines and provide guidance for future updates and implementation. In FY3, the MOBILIST Policy Platform team built the MOBILIST Back-End Data System (an interactive digital platform) with FCDO to manage ESG and development impact data throughout the investment process. This provides access to data, relevant documents & narratives at the product level, and reporting at the MOBILIST portfolio level and enables the investees to submit reporting data through secure dashboards and forms.
[note] An assessment of commercial viability is predicated on demonstrable investment appetite for purely commercial investors (MOBILIST will only ever be a minority investor alongside these other investors).
[note] Naturally, the price of traded products can go both up and down and entails an inevitable degree of price fluctuation. Equity investments are also not free of idiosyncratic risk, which may materialise after the investment is made.
[note] MOBILIST will need to consider multiple factors when determining when and how to exit its investments: (i) preservation of capital, (ii) redeployment of the reflows in the same ODA reporting year or same financial year, (iii) availability of opportunities for impactful redeployment, and (iv) ensuring the successful long-term future of the company or fund being exited.
[note] Development Capital Investment Guide May 2015 “A loan with terms that are more favourable to the borrower than commercial market terms is described as concessional and the degree of concessionality is expressed as its grant element. For ODA purposes this must exceed 25%. The calculation takes account of the duration of the loan and number of years before repayment is required, frequency of repayments, interest rate charged and applies a standard discount rate of 10%.”
[note] An illustration of this approach is MOBILIST’s tapered commitment, based on different offer price scenarios during the Thai Credit Bank IPO. When demand was found to be strong and a higher offer price set, MOBILIST reduced its order to a lower subscription amount.
[note] Reflow of Capital may be able to provide part of the funding requirements but are market driven and very uncertain.
[note] Independent valuation would usually be required at least annually for 30th March year end reporting.
[note] FCDO's RAME budget is non-cash, but still must be managed appropriately as it is a control total. FCDO has two opportunities per year to request RAME budget through the Supplementary Estimates process. The programme team monitor the valuation trends and alert FCDO Finance if valuations are likely to move significantly to ensure sufficient R-AME budget is requested from HMT.
[note] [1] All these considerations are made with reference to MOBILIST’s Director-led Decision-Making Committee and involve working with FCDO Commercial and MOBILIST’s commercial legal advisers to manage timing of exits and to mitigate any accounting concerns.
[note] HMT has agreed in SR21 that reflows can be recycled within FCDO’s FT portfolio in the same year that they are received if the annual net total FT ringfence is not exceeded. This may change in future SR’s and there is a case to be made regarding carrying over reflows to future years due to the market driven uncertainty of the timing of reflows.
[note] The principles that underpin MOBILIST’s VfM strategy are as follows: - Seek to achieve the maximum results for the resources deployed, at the Output, Outcome, and Impact levels. - Assess the value for money offered by the different components of the Programme, and the proposed funding interventions (whether grant-based or technical assistance). - Maintain flexibility, so that we can adapt during execution to prioritise investment in the areas identified as offering the greatest value for money, including integrating learnings from working with product issuers early in the Programme to create iteratively more efficient processes. - Assess the cost-effectiveness of the Investment once we begin to achieve results. - Ensure the programme is well-managed financially and able to meet its forecasts.
[note] Note that alignment (which MOBILIST is), and being 2X qualified, which is officially recognised.
[note] The MOBILIST portfolio is 2X aligned in the following ways: i. MOBILIST meets the basic 2X ESG and minimum Governance & Accountability requirements ii. MOBILIST can commit to fully meeting Criterion 3 through the ESMS within the next year. MOBILIST already reports share of jobs created that are for females and we can add an additional "quality employment indicator" to the ESMS. iii. MOBILIST meets Criterion 6B Portfolio for Funds (30-50% of portfolio) as three of the six portfolio investees (AEIT, GGC, TCB) meet the 2X criteria.
[note] AEIT measured gender impacts as part of its Social and Employee Matters indicators.
[note] GHG Emissions (Scope 1,2,3 tCO2e): The sum of GHG emissions reported by all investees. GHG emissions figures for MOBILIST currently do not include investees’ financed emissions. In line with current market expectations, investees in non-financial sectors generally report their Scope 1, 2, and 3 GHG emissions and carbon footprint, whereas investees in the financial sector do not yet consistently report their footprint as financed emissions.
[note] Installed Renewable Energy Capacity (MW): The sum of installed capacity (defined by IRIS + as the total amount of energy the asset portfolio can transmit as of the end of the reporting period) reported by all investees.
[note] Jobs Directly Created (FTE) and Female Jobs Created: The sum of jobs (or jobs held by females) in directly financed companies (defined by IRIS + as the net number of new full time equivalent employees working for enterprises financed or supported by the organisation between the beginning and end of the reporting period) reported by all investees.

Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The Theory of Change has been updated several times since the original Business Case, as the programme has learned from its investments; as market conditions remained closed in London while opening elsewhere; and due to a complementary growth in demand from across the FCDO network for engagement. / The original theory of change had a stronger emphasis on London listings and attracting UK and European institutional investors with a simple causal chain between increasing new listings, more quality performance and pricing track record and replication. The updated theory of change has broken down this chain further to assess the programme components which contribute to demonstrating a proof of concept to investors leading to replication and scale across global stock exchanges. The expected impact of the programme in the context of financial markets and systems remains unchanged. MOBILIST aims to create systemic change that results in sustainable capital flows to Emerging Markets and Developing Economies (EMDEs) through public markets. Once products are listed, public markets offer the levels of transparency that taxpayers expect of ODA spending. / Delivery mechanisms for making investments have changed since the original business case. The introduction of the S3 process has enabled MOBILIST to ‘catch’ potential investment structures at a later, more mature stage of development. This has improved time to market, reduced design and execution risk and enables the programme to react more quickly, in line with market practices. / While the expected impact of the programme remains aligned with the original business case, the programme has established and continues to upgrade robust due diligence, technical assistance and ESMS systems to safeguard the alignment of specific investment outcomes and impact. / Key learnings overview / Broadening MOBILIST’s mandate beyond IPOs has enabled the programme to address important policy issues, such as reform of the MDB system. Securitisation transactions, as well as guarantees were not envisaged in the original business case but have provided formative learning opportunities for FCDO and policy makers. / MOBILIST has focused on increasing the supply of investment products, as a key constraint to investor demand for EMDE assets. Learnings from across the investment portfolio have demonstrated that there are other barriers to scale and replicability including gaps in market building and market making services which would facilitate liquidity and maintain value during adverse conditions (as in the case of the TCRB transaction). Programmatic learnings have also demonstrated the need for comparables to allow investors to benchmark new assets (e.g. AEIT). These are key components of supporting investor demand. / Relatedly, MOBILIST has identified a need to maintain a constant presence in some key countries, potentially completing repeat transactions of a particular assets class (like renewables) or particular structures (such as securitisations) to demonstrate viability of an asset class and support replication and scale. / The S3 process has been successful at capturing products close to listing. However there has been evidence of strong market demand in support of developing more innovative products upstream, as evidenced by demand for technical assistance. Highly innovative products that support SDGs and climate could be surfaced by making product developers aware of potential anchor investment. This would then enable them to begin testing products more effectively for investor demand. This has been evidenced in the indices workstream: while there is a market gap for climate-aligned EMDE products, there are challenges in the form of inertia on the part of major fund managers, an inability to scale and a lack of market products from innovative fund managers, and a need to prove the investment case to capture investor demand. / MOBILIST’s partnerships currently lean towards larger emerging markets but MOBILIST will need to consider its offer in frontier markets which face additional challenges and may need a more comprehensive offer across the programme’s components (research, TA, investment). This will support replicability and scalability of MOBILIST’s investments by tackling market infrastructure and enabling environment barriers that may be constraining investor demand and further development of products. MOBILIST research has identified that an ecosystem approach is needed alongside interventions, in order to enhance supply, demand, the enabling environment and market infrastructure. Investor engagement through roundtables also made clear that it is critical to develop the local capital market before international investment can flow in. Stock Exchanges in more frontier markets have started to engage with MOBILIST to access technical assistance to address these issues. / Learnings from the portfolio show that MOBILIST’s framework on additionality needs to be further refined, aligning it with OECD definitions and following the framework outlined in MOBILIST research on public market investors’ impact additionality. / As MOBILIST’s portfolio expands across a wider range of geographies, asset classes and currencies, there is an increasing need to upgrade tools and strategies to manage risk across the portfolio. MOBILIST should begin to align its portfolio management strategy and governance processes with more mature institutions and market standards to prepare it as a standalone entity.
[note] Mitchell, I., Hughes, S., Wickstead, E. Center for Global Development. 2023. ‘UK Development Finance beyond ODA, Mapping and Assessing the UK’s Non-grant, Development Finance’. This report rated MOBILIST “High” on Transparency (High” indicates historical data is available for all four main areas in the first column [i) face Value; ii) ODA and concessionality; iii) Climate Finance; iv) Private Capital Mobilisation] and also disbursements.
[note] IDB Invest. 2023. Beyond Leverage Ratios: A Strategic Approach to Blended Finance, p.20.

## Annex 1: MOBILIST’s Investment Policy
MOBILIST applies the following considerations during the investment decision-making process including:
ODA-eligibility: FCDO has integrated ODA-eligibility criteria into the S3 process, ensuring that any products that enter the process meet the overarching ODA requirement of having for a main objective economic development and welfare of ODA-eligible countries.

United Nations Global Goals: the product’s alignment with the relevant Sustainable Development Goals and how is impact integrated into the investee’s activities.

Mobilisation: MOBILIST considers how likely MOBILIST funding is to facilitate listing of the investment product or capital mobilisation more broadly. We consider the potential scalability, replicability, commercial viability, additionality and feasibility of the investment product. We also consider the likelihood that the investment will generate demonstrable outcomes for mobilisation within the programme’s time frame.

Overall Development Impact: MOBILIST evaluates the likelihood that the investment product will deliver the expected development impact, transform economic productivity, contribute to climate mitigation or adaptation, reach the poorest, or contribute to gender inclusion (i.e. progress towards the product’s stated impact objectives, theory of change, and impact measurement framework) and support to the broader MOBILIST Theory of Change. MOBILIST also considers any additional outcomes or learnings that contribute to the development finance ecosystem as a public good.

Additionality: MOBILIST supports products that clearly target the geographies, sectors and assets that are critical to the financing gap and meeting the SDGs, and where the private sector, through the medium of public listed instruments has, little or no access to investible assets i.e. where there is an identifiable market failure/ barrier that FCDO support can help over-come.

Ensuring a commercial rate of return: MOBILIST expects to receive the same commercial rate of return as other commercial (mostly institutional) investors in any product i.e. MOBILIST seeks to invest Pari passus, to complement, rather than distort markets and ensure value for money. Commercial returns are typically benchmarked against familiar instruments, such as government bonds or well-known indices, but they can vary depending on the risk return profile of the company, fund or vehicle (e.g. debt or equity), and the level of risk associated with the underlying assets (e.g. in infrastructure the amount of greenfield vs. operational infrastructure). A range of factors vary the return profile.

IFC Performance Standards: extent to which investee’s activities, processes, impact and risk management are in line with the IFC’s Performance Standards on Environmental and Social Sustainability.

Taxonomies: based on the investee’s geography or sector activities, extent to which taxonomies for classifying environmentally sustainable economic activities such as the EU Taxonomy apply. Is the product marketed as having a sustainable investment objective (e.g. Sustainable Finance Disclosure Regulation (SFDR) Article 9) or promoting sustainable impact (e.g. SFDR Article 8); is the issuer subject to regulation on disclosures related to environmental and/or social impact, such as SFDR?

FCDO Fossil Fuel Policy: Product adherence with the UK’s Fossil Fuel Policy (2021), (whereby FCDO will not make new investments in fossil-fuel sub-sectors that are not aligned with the Paris Agreement, in particular, crude oil or thermal coal assets), or gas assets unless they are consistent with a country’s clean energy transition plan.

Gender: In line with the 2X Challenge, MOBILIST addresses gender inclusion by assessing investees’ SDG 5 Gender Equality alignment and any gender-related development impacts, including female jobs directly created. Neither of the 2023 listed investees reported specific operational strategies or initiatives for SDG5, but gender impact is increasing and in 2024, MOBILIST investments include specific gender impacts in businesses supported. One MOBILIST investee measured gender impacts as part of its Social and Employee Matters indicators. 40% of the direct jobs created were held by women. The Company also measured the gender pay gap in the companies that it invested in, which fell from 37% in 2022 to 14% in 2023. The Company’s board had a 50/50 female to male gender ratio. MOBILIST can strengthen 2X ESG alignment by explicitly including 2X ESG criteria in the next version of the ESMS, including meeting Criterion 3 and explicitly adding 2X criteria at origination and due diligence; can strengthen the Governance and Accountability requirements by creating an action plan to increase investee 2X alignment and continuing to improve our impact measurement and management on gender.

Private Sector Asset Designation: FCDO ensures that (i) its own stake in the company or fund is not a controlling stake (for example, not giving rise to an equity share of over 50% or a controlling influence on the Board) and (ii) that the company or fund operates at arms-length, without FCDO’s day-to-day involvement in specific investment decisions. Both facets are desirable from policy and demonstration perspectives. By doing this, FCDO ensures that it does not inadvertently create an arms’ length body, ensures FCDO’s participation is compliant with the UK Subsidy Control Policy.

Exit Planning: The definitive ‘proof’ of a successful FT deployment is achieved when MOBILIST exits a position by selling shares to institutional investors, leaving behind a healthy vehicle capable of organic growth. Unlike private market vehicles, where exits are often difficult and determined by contractual ‘exit rights,’ with public listed vehicles MOBILIST exits are straightforward, much easier, and not governed by contract law. MOBILIST seeks to achieve preservation of capital and there is an expectation that FCDO tries to avoid exiting at a loss.
## Annex 2: MOBILIST Theory of Change

Annex 3 Part I: Key learnings from MOBILIST’s investment portfolio
- Project: Bayfront Securitisation Notes (Dec 2023), Supporting Research Note: Research Note: Securitisation for Sustainable Development: this MOBILIST Research Note on Securitisation shares insights from our investment an infrastructure asset-backed securities vehicle, the benefits of securitisation for both borrowers and investors and the different ways development finance actors can accelerate the use of securitisation for sustainable development. MOBILIST’s investment in an infrastructure asset-backed securities vehicle sponsored by Bayfront Infrastructure Management illustrated that investing in the equity tranche of a debt securitisation is commercially viable and can have a significant multiplier effect by enabling both commercial banks and MDBs to recycle capital faster.
- Project: Green Guarantee Company (October 2023), supporting Research Note: Guarantees for Sustainable Development – Achieving 10x Mobilisation: this MOBILIST Research Note on Guarantees explores their potential for private capital mobilisation. It explains how guarantees work, why they remain underutilised, and how development finance actors can contribute to a renewed expansion of guarantees for sustainable development.
- Project: Revego-MOBILIST Teaching Assistance (July 2024), supporting Research Note: ‘Financing Africa’s Energy Transition through the Public Markets’: MOBILIST-sponsored technical assistance, in collaboration with Revego Fund Managers, and delivered by Wood Mackenzie, shows that Africa’s ambition to achieve universal energy access and shift towards greener sources is a major economic opportunity for the continent, but also one of its greatest challenges. Equity capital is particularly scarce and has largely been financed by Developmental Finance Institutions. Secondary markets could increase the volume of capital available and accelerate deployment through ‘farm downs’ of de-risked assets. However, currency and regulatory risks compound the early stage of development of many assets – therefore appropriate secondary market structures and strategies are vital. Development finance actors have critical roles to play in building secondary markets to help finance SSA’s energy transition, as originators, investors, pioneers, and providers of hedging solutions and technical support.
- Project: Philippines Renewable IPO, supporting Research Note: ‘Philippines Renewables IPO demonstrates maturing markets for clean energy transition in EMDEs’: This transaction offers investors access to a vertically integrated, Philippines-focused, renewable energy platform that combines important features to address both regulatory requirements and investor priorities. The newly listed CREC’s (Citicore Renewable Energy Corporation) performs should also generate important learnings for the market in relation to the renewable energy sector’s strengths and vulnerabilities. The Philippines experience also demonstrates the central importance of regular public-private dialogue and of holistic management of energy sector and capital markets regulation in tandem, ensuring that capital market regulation evolves with that of the energy sector.

## Annex 3 Part II: Key learnings from MOBILIST’s research
MOBILIST – The Exit Mobilisation Opportunity in Africa (March 2021): Over the past ten years, there have not only been reductions in the proportion of ODA going to LDCs, but also reductions in overall ODA commitments. In 2022, only 21% of ODA from DAC countries went to LDCs and in 2023 DAC countries allocated only 0.37% of their GNI to fund aid, barely more than half of their long-standing commitment of 0.7%.
The research defines ‘exit-mobilisation’ as the process through which a public sector owned development finance institution (DFI) exits an investment by selling its holding to commercial investors. In this pioneering study, 18East explores the opportunity for DFIs to mobilise capital from African and international private investors into listed product structures. The study assesses the feasibility of, and the hurdles to, the implementation of exit-mobilisation to investments made by DFIs in sub-Saharan Africa.
Drivers of Investment Flows to Emerging and Frontier Markets (June 2022): the lack of investment opportunities in Emerging and Frontier Markets - especially in Africa – is striking. Listed stocks and tradable bonds markets in frontier countries tend to be shallow and illiquid, reflecting the lack of traded product on listed exchanges to date. Due to this lack of equity (and debt) investment opportunities, asset allocation to Africa, for example, by UK investment managers was only 0.3% in 2023 falling from the already meagre 0.5% in 2018.

The research provides compelling evidence that emerging and frontier markets require significant investments to accelerate sustainable development and fight climate change, but allocations from developed market investors fall short. In this inaugural MOBILIST study, Intellidex investigates what drives allocation strategies based on interviews with more than 50 institutional investors.

- Market Indices for Sustainable Development (October 2022): the research explores the role of market indices as a key factor in shaping and limiting capital flows to developing countries and the need for a new suite of development indices that target those markets where capital is most needed.
- Listed Product Structures for Sustainable Development in Emerging and Frontier Economies (March 2023): this research report showcases the commercially viable listed product structures that MOBILIST has identified to date, which hold promise for allocators in accessing the emerging and frontier markets. While the research is primarily focussed on product structures, to offer a full analysis of each structure’s potential we situate these structures in the context of proposed investment thesis and strategy.
- Resetting the ESG Investment Paradigm to Support Emerging Markets & Developing Economies (April 2023): the research report, commissioned by MOBILIST and produced by Fitch Solutions, argues that the mainstreaming of environmental, social, and governance (ESG) considerations is increasingly shaping the flow of capital to and among emerging markets and developing economies (EMDEs). The subsequent MOBILIST Research Note: ESG Investing Must ‘Do No Harm’ to Developing Countries” concludes that developed market regulators should consider EMDE impacts of new regulatory regimes, including ESG and impact regulations.
- Liquidity in Equity Markets: Its Sources & Significance in Developing Economies (June 2023): this MOBILIST research focuses not only on the extensive benefits liquid equity exchanges offer for investors and policymakers in developing markets and provides a tailor-made blueprint of building liquid exchanges providing a clear timeline of key priorities in early- mid- and late-stage capital market development. It also advises local stock market officials on some of the more controversial issues, including the sensitive topics of short-selling, margin- and high frequency trading.
- Financial Regulation and Capital Flows to EMDEs (June 2023): this Risk Control research, commissioned by MOBILIST, provides an overview of several cases where advanced economy regulations appear to penalise emerging markets and developing economies (EMDEs) or where developed market policy and regulations are incommensurate with the actual risk of EMDE assets, making recommendations how to address these regulatory frictions by eliminating information asymmetries and navigating global rulemaking.
- Development Finance through Public Markets: Originate-to-Demonstrate (Oct 3023): this MOBILIST research paper discusses how, by investing and exiting through public markets, official sector actors can attract large-scale institutional co-investors, accelerate capital velocity, generate demonstration effects, and have systemic impact by triggering domestic capital market development.

How MOBILIST’s research is shared/ disseminated, its targeted audience, and its impact:
- Webinars and Roundtables: this is the typical method to disseminate MOBILIST’s thought-leadership research. They could be organised either as stand-alone events or part of a larger development finance conference. The agenda of research dissemination webinars typically includes an introduction of the MOBILIST programme by the FCDO team, the introduction of the research by the MOBILIST research team followed by a brief presentation of key findings by the researchers.
- Product launch events: these events are typically related to the launch of MOBILIST-supported products. Their main purpose is to further eliminate information asymmetries, and to inspire copycat products launched by the broader investment community, including MDBs, DFIs, as well as private sector asset owners and managers.
- Capital market days: these conference-style events are typically organised locally, in countries targeted by the MOBILIST agenda. A recent example of a potentially significant investment project originally arising from the Securitisation Roundtable and further developed during the Brazil Capital Market Day confirms the effectiveness of allowing the direct brainstorming of key stakeholders.

## Annex 4: Risk levels against 7 Standard Risk Categories
Risk Category	Category Description	Risk Appetite	MOBILIST / residual risk level
Strategy and Context	Risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact.	Receptive	Moderate – no risks outside appetite
Policy and Programme Delivery	Risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing, and/or operational support. These risks undermine our impact and influence.	Receptive	Major – no risks outside appetite
Public Service Delivery and Operations	Risk arising from weaknesses in the delivery of consular services or the delivery of internal operations which support our core business and wider HMG, including security, legal, technology and information and property risks, impacting delivery, our people and British citizens.	Cautious	Moderate – no risks outside appetite
People	Risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance.	Cautious	Moderate – no risks outside appetite
Safeguarding	Risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations, reputational damage and legal challenge.	Cautious/Minimal	Minor – no risks outside appetite
Financial and Fiduciary	Risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage.	Cautious	Moderate – no risks outside appetite
Reputational	Risk arising from political or adverse events, including delivery failures and ethical violations, damaging the FCDO’s reputation, within the organisation and/or externally, and/or the UK’s reputation.	Cautious	Moderate – no risks outside appetite