Annual Review

Title: Public Resource Management in Somalia Phase 2 (PREMIS 2)
Programme Value £ (full life): £10 million plus a contribution of £2.3 million from Denmark		Review date: March 2025
Programme Code : 300862	AMP start date: / 7th March 2022	AMP end date: / 31st October 2025

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	B	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003476.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003475.xlsx

SUMMARY AND OVERVIEW
Description of programme
The Public Resource Management Programme in Somalia Phase 2 is designed to improve domestic revenue mobilisation and public financial management. It contributes (a) to Somalia’s state-building project by supporting the inter-governmental policy dialogue on fiscal federalism; and (b) to the debt relief process under the Highly Indebted Poor Countries (HIPC) initiative by aiding reforms needed to meet HIPC Completion Point requirements and policy benchmarks of the IMF Staff Monitored Programme under the Extended Credit Facility. PREMIS 2 is an important part of a wider portfolio of economic development and governance programmes to deliver on the UK’s strategic objectives.

PREMIS 2 has four components: (1) strengthening Domestic Revenue Mobilisation (DRM), with a focus on customs modernisation in major ports and airports across the country, as well as domestic tax collection in four Federal Member States; (2) further enhancing Public Financial Management (PFM) and Civil Service Reforms (CSR) in four Federal Member States; (3) supporting macroeconomic and fiscal policy; and (4) an independent evaluation. Components 1 and 2 are implemented via a three-year and £8.9m contract with Adam Smith International. Component 3 is implemented via a £0.6m financial contribution to the Somalia Country Fund for capacity development in macroeconomic policies and statistics, which is managed by the IMF and co-funded by the UK, EU, Canada, Italy and Sweden. Component 4 was planned as a mid-term evaluation, but it was decided not to proceed with this.

Operating Context
Contested political space
The programme is operating in a highly contested political space with unorthodox power dynamics between key member of the government regime, where fiscal federalism arrangements are in flux and not always adhered to in practice, and where the Federal Government and FMSs have limited influence over one another. This political contestation, and the ensuing blocks to reform and the mixed levels of political support/buy-in, is the key change faced by the programme to delivering impact.

Despite the agreements made in Baidoa (South-West state of Somalia) between the FGS and FMS on revenue sharing and fiscal transfer agreements, these have not been adhered to and follow-up meetings/agreement have been held back by political tensions within the country.

This political tension is greatest between the FGS and the Jubaland state of Somalia (JSS), due to the re-election of President Ahmed Madobe. For the last month of the year, political tensions meant that the programme had to reduce its visibility in Kismayo. There were walk outs by the JSS delegates at the Inter-Governmental Fiscal Federalism (IGFF) and a lack of technical working group meetings between the FGS and JSS on SOMCAS. This continued political tension has also impacted the programme’s handover process as there have been several disagreements on the future management of the system. FCDO and PREMIS are seeking solutions for this before the system financing ends in March 2025.

Insecurity due to the war with Al Shabaab and clan conflict
This has been a constant issue for the programme, as many areas around the FMSs continue to be liberated from Al Shabab, though others have fallen to it. The constant battles along these lines have had huge impacts on resource mobilisation and staff movements. These conflicts affected some of the work by the PREMIS programme, for instance insecurity in Hirshabelle State of Somalia (HSS) meant no advisers were deployed to the state. This, however, changed in September 2024 when both a civil service adviser and a PFM adviser went on a mission to the capital of the state, Jowhar, following successful cooperation with the authorities and ASI’s Duty of Care team. The lack of these two advisers by the HSS state had negatively impacted the training and significant technical support that had been planned.

Elections in the FMS
Concerns around domestic reform, particularly electoral cycles (and therefore, implicitly, how long current governments might remain in power) has been an issue for FMSs, with not only Ministers but also DGs being sucked into political processes. These concerns are at the heart of escalating tensions with JSS but also saw significant issues with SWS at an earlier point in the year.

Transformative potential

Strengthening economic governance is crucial to the transformation of Somali state out of its position of aid dependence and weak service delivery to one that is more fiscally sustainable and able to deliver what the World Bank calls the “minimal functions” of a state. With grant IDA from the World Bank ending in 3 years and donor support (including from the UK) on a downward trajectory, transformation of domestic resource mobilisation and public financial management are urgently needed. The PREMIS programme has provided support in this crucial area. It has played a pivotal role in the state building of federal member states (Jubaland, South-West, Galmudug and Hirshabelle) through the establishment of ministries and recruitment of civil servants for the implementation of financial systems including the BISAN, Human Resource Information System (HRMIS), Revenue Mobilisation Information System (RMIS) and finally the SOMCAS (customs automated system).
[note] Towards Building Somalia’s Social Contract, World Bank, 2024

These critical reforms have made profound impacts in addressing challenges in governance, economic resilience and institutional capacity. Supported by these reforms, Somalia has increased revenue collection, with customs contributing to 60% of the FGS budget. A more transparent and accountable system like the BISAN has ensured that all expenditures incurred by FMSs are tracked and visible to scrutiny and can be used as a benchmark by development partners for funding and supporting the payrolls for civil servants. FGS’s National Transformational Plan (NTP) aims for inclusive growth and reduced poverty across the country. Plans such as this are dependent on expanding the tax and revenue base. Despite the progress that has been made, the political economy challenges PREMIS 2 faced have constrained its transformative potential and limited achievements.

As we approach the end of PREMIS 2, the programme’s ultimate contribution to transformational change and increasing self-reliance depends in large part on a successful handover process for the aforementioned systems and the ongoing use of them. This hinges on the political will and commitment of FGS and FMS and cementing this should be a top priority during the programme’s last year.

Delivery Partner Performance

FCDO’s partnership with the ASI and IMF was strong and both performed well. Regular meetings by the IMF with donor partners after every mission has enabled there to be opportunities to discuss and find solutions to issues raised. The PREMIS 2 team also gets a regular catchup with the IMF mission team to update them on vital benchmarks such as on the SOMCAS.ASI closely liaised with FCDO providing progress updates on implementation, finances, and risks during bi-weekly meetings with FCDO and at the steering committee meetings. ASI submitted deliverables on time and of good quality, scored favourably against agreed KPIs on quarterly basis and made good progress on the strategic supplier relationship management scorecard.

FCDO Performance

FCDO performance on delivering PREMIS was good until the decision was made to reduce UK ODA to 0.3% globally towards the end of the review period. This led to uncertainty over funding for the programme’s final year, severely disrupting planning and (shortly after the review period when funding uncertainty was communicated) causing damage to the relationship with government and to FCDO’s reputation for reliability and predictability. It created a perception amongst some partners of a reduced commitment to PREMIS 2.

FCDO established good working relations with its development partners, sharing achievements when it comes to delivery on benchmarks set out by the IMF, World Bank and EU. FCDO is also part of the PFM donor working group, although this group has not been meeting regularly.

The working relationship between FCDO/PREMIS 2 and government was challenging at times. This was due to the programme working on issues central to the fragmentation between FGS and FMSs. This led to some Steering Committee meetings being fraught and required considerable effort to keep them on track. These meetings nevertheless provided an opportunity to discuss priorities challenges and achievements. There were also some tense discussions between FCDO/PREMIS 2, and FGS and FMS ministers and DGs on issues such as system handover of the SOMCAS, BISAN and HRMIS.

Summary supporting narrative for the overall score in this review

The programme’s performance over the last year has been scored as an A. This review has been undertaken by the programme team’s governance adviser and PRO, with 10% support from the Governance cadre. The review period is March 2024 – Feb 2025. The review draws on interviews with government counterparts and implementing partners, progress reports and deliverables, and minutes of three Steering Committee meetings held during the reporting period.

Output	Score	Weight
FGS, FMS, and their development partners use PREMIS advice to advance fiscal federalism reforms.	B	5%
Domestic Revenue Mobilisation policies, systems, and capacity formalised in FGS and FMS.	A	40%
Improved PFM policies, systems and capacity	A	40%
Strengthened civil service management through Civil Service Commissions	A	10%
Somalia Country Fund (SCF II) -The Federal Government of Somalia develop capacity to implement sound macroeconomic policies with IMF technical assistance.	B	5%

PREMIS’ contributions and ability to positively support the Inter-Governmental Fiscal Federalism (IGFF) were recognised in 2024 as the programme was given a formalised role to contribute at each IGFF meeting. Multiple briefing papers (e.g. on implementation of the policy framework) were produced for the IGFF, as well as significant work on tax policy and PFM legislation. PREMIS2 continued its focus on Somali Customs Automated System (SOMCAS) implementation throughout the year. To facilitate implementation, SOMCAS Business Process and Standard Operating Procedures (SOPs) and SOMCAS User Authorization, Identification and Authentication policies were approved, vital to improving the operations and management of the system. The Customs Trade and Transport Forum met twice during the year in each of Kismayo and Mogadishu.
[note] The Intergovernmental Fiscal Forum, which is supported by the World Bank through the RCRF project, comprises two bodies: (i) the IGFF-TC, which operates at the technical level; and (ii) the Finance Ministers Fiscal Forum for policy decisions.

FMS annual budgets were passed within statutory deadlines in all FMSs, with PREMIS supporting a number of significant measures to improve quality, credibility and engagement. These included: developing a new revenue model to underpin budget estimates and the development of Budget Framework Papers (BFPs); ensuring the BFPs and budget were presented to the relevant parliamentary finance committees to inform legislative scrutiny of the budgets prior to approval; and, for the first time, facilitating the Ministry of Finance (MoFs) to present the budgets publicly at citizen engagement workshops and through the production and publication of citizens’ budgets. The Women in Government (WiG) programme continues to go from strength to strength, with the 4th cohort of female civil servants completing the programme. Train-the-trainer sessions delivered for WiG will ensure sustainability of programme delivery beyond the life of PREMIS2. Capacity has been built in increasing competency and confidence of women within the ministries of the finance of the FMS.
[note] Citizens participation in the budget.
[note] Women in Government is an innovative and ground-breaking initiative designed during the inception of the programme to address attitude and cultural challenges faced by women in civil service. It was delivered to two cohorts of management-level female civil servants across the four FMS, with a view to changing their behaviour and raising their confidence.

By year-end, significant progress was achieved in the CDEL programme, with 9 of 11 construction projects underway, including 9 out of 10 in the FMSs. Two construction projects had not yet started by the end of 2024. In January the construction works in Mogadishu port began after the signing of an MoU between FGS and ASI to facilitate contracting. The construction of a revenue hut in El-Barf (HSS) was able to start due to security conditions improving. In SWS three revenue huts were completed while in JSS two of the construction works neared completion. All other projects in the FMSs are on track to be completed within the agreed timelines (and before the end of March 2025).

Major lessons and recommendations for the year ahead

Relying only on technical work to drive reforms doesn’t always work. This project focused on fixing PFM technical issues but, last year, political interests played a big role. A key example was the decision for FMSs to move from the BISAN system to the Somali Financial and Management Information System (SFMIS) in 2025. This decision will have the effect of reducing the sustained impact of PREMIS 2. The decision was driven by FGS and showed its influence on the programme and its results. The lack of inclusive dialogue on the move increased tensions as some FMSs would prefer to continue using BISAN. States such as JSS, who have used the BISAN since the creation of the state itself, have declined the future move to the SFMIS unless there is a tangible plan that includes the technical support necessary in implementing a new system. Such challenges show why programmes must be flexible and aware of political factors, especially in places where politics and different interests have a big impact.

Provide sufficient funding to PREMIS 2 to enable the programme to close strongly and secure the benefits from the investments it has made thus far. A key challenge for PREMIS 2’s final year is to ensure that the programme is able to deliver sufficient technical assistance and training to ensure strengthened systems are left behind once the programme completion point is reached in October 2025.

The announcement of UK ODA being reduced to 0.3% of GDP has created uncertainty and, to help manage this, ASI have provided scenarios for different levels of budgets which should be used to guide planning and decisions about making the best use of the funding available to the programme. In addition to adequate funding, securing political commitment to the handover process is critical and should be a priority for the final year. Diplomatic influencing should be done to support this.

The PREMIS programme should continue its coordination with development partners like the IMF and World Bank and strengthen it by setting up regular technical meetings to help ensure that there is proper support provided to the Federal Government and its member states once the programme comes to an end in October 2025. (By the end April/May 2025).

1. Strengthen FGS and FMS customs technical working group to better coordinate the work. Coordination meetings are crucial to any reform and strengthening progress on policy while also addressing any tensions between stakeholders (by start of April 2025).
2. There remains a major need to strengthen economic governance. FCDO should seek to provide support in this area after PREMIS 2 ends. In doing so, it should consider how best to take advantage of the work already achieved by the PREMIS 2 programme.

IMF Action Plan – work with IMF to develop, in consultation with donors, and implement an action plan to address the lessons learnt from the mid-term evaluation of Somali Country Fund II (SCF II), covering March 2021 and October 2023.

Extension to SCF II – Partner have decided extension of SCF II by one year until April 2026. FCDO has fully disbursed the funding to SCF II and this extension will go beyond the programme end date. Therefore, FCDO should consider whether to amend milestones to reflect this or consider a no-cost extension to the programme to allow for continued engagement and reporting.

Coordination of PFM Support – SCF II should continue to prioritise coordination with the Extended Credit Facility (ECF) of the World Bank, and with other development programmes on PFM and Tax, including ASI funded capacity development under PREMIS II.

Diversity of Consultants – In addition to tracking of participants’ gender, IMF should consider tracking of consultants’ gender as a first step to ensure sufficient diversity and representation of those delivering IMF capacity development.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Theory of Change for PREMIS 2, as set out in the Business Case
IF DRM capacity increases and becomes formalised, AND core PFM capacity is sustained; IF macroeconomic frameworks improve and fiscal policy capacity increases; AND IF FCDO leverages the programme’s influence and knowledge to advance the emerging agreement on fiscal federalism; THEN Somalia will be in a better position to reach HIPC Completion Point, DRM and PFM systems will be more effective, harmonised and transparent to manage the funds unlocked through HIPC and enhanced DRM, this should allow progress to be made on more equitable revenue sharing agreements (based on agreed functional and revenue assignments, and harmonisation of financial management systems) enabling sustainable intergovernmental fiscal transfers (IGFTs) which are needed for FMS governments’ financial viability. THIS IN TURN will support steps towards a more effective and trusted federated public administration contributing proportionally to the conditions necessary for building greater legitimacy, stability, and a resilient economy.

While the logic for the overall programme is largely valid, the theory of change is dependent on the assumption of there being adequate political buy-in and support. Without this, improving capacity is not enough to achieve programme objectives. Insufficient political support posed difficulties in some areas during the review period. The contested governance space between the FGS and its FMS posed barriers to programme outputs leading to change at the outcome level. For example, the political wranglings between FGS and JSS meant that there have been delays and changes to the programme’s support of customs modernisation. This will need to be addressed in the final year of the programme for it to achieve impact.

Amendments were made at the impact, outcome and output levels of the log frame, in discussion with the PREMIS 2 team. These changes were the result of the government’s priority on strengthening Domestic Resource Mobilisation (DRM).

At the impact level, FGS collected around $240m from DRM in 2024, which was 24% of the budget (an impact level indicator). A new indicator was introduced to capture the improvements in domestic resource capacity at the FGS level. The new indicator measures the country’s improved capacity to collect non-customs revenue. The significance of non-customs revenue is related to Somalia’s considerable dependency on customs taxes and lower reliance on more administratively complex forms of taxation. Hence measuring the increase in the share of such forms of revenue directly speaks to the key impact indicator – building a more effective and trusted federated public administration that contributes to conditions necessary for building greater legitimacy, stability, and a resilient economy.
[note] Close to 60% FGS revenue in 2023 was from customs.
The main changes at the outcome level focus on revising Outcome 1. Previously the outcome statement prioritised ‘More equitable revenue sharing agreements and sustainable Inter-Governmental Fiscal Transfers (IGFTs).’

However, it was felt that this outcome did not adequately capture the range of activities supporting DRM within the country. Consequently, the outcome statement was revised September 2024, and the new statement emphasizes the strengthening of domestic resource mobilization in the country. The indicators used to measure this outcome were also subsequently revised. Currently, this outcome is measured by three indicators:

- Shift to SOMCAS system in Mogadishu and Kismayo ports (Outcome 1.1),
- Shift to value-based import duty tariff and implementation of a single tariff in Mogadishu and Kismayo (Outcome 1.2),
- Development of new FMS Tax Policies and Legislation to reflect evolving fiscal federalism & harmonization policy framework (Outcome 1.3) (See ToC Diagram for more details).

The indicators for measuring Outcome 2: Enhanced harmonization and transparency of public resource management in Somalia, have also been revised. Since fiscal transfers between the FMSs and the FGS constitute a critical element of enhanced harmonization of public resource management, the indicator measuring the level of implementation of intergovernmental arrangements on FGS fiscal transfers to FMS (which was previously used to measure outcome 1), has been reclassified under this outcome statement.

Some indicators at the output level have also been changed. The main changes are under Output Statements 2 and 3. Under Output 2, which specifically measures improvements in DRM policies, systems and capacities, two indicators have been added to measure improvements in systems and capacities:
- Reform and modernisation of customs administration and systems (SOMCAS) at major ports and airports (Output 2.1),
- Number of customs administration training courses successfully delivered by PREMIS to frontline customs staff (Output 2.2).

Lastly, indicators used to measure improved PFM policies, systems and capacity (Output 3) have also been revised to more closely reflect the different levels of support being provided by the PREMIS team. Consequently, separate indicators have been included for budget preparation, the finalisation and publication of financial documentation and the number of training courses organised. Specifically, three new indicators have been included:
- Harmonised preparation and publication of budget documentation in 4/4 FMSs (3.1).
- Harmonized preparation and publication of financial documentation in 4/4 FMSs (3.2).
- Number of PFM training courses successfully delivered by PREMIS (2.3)

Describe where the programme is on or off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contributing to the expected outcomes and impact. The efforts in supporting reforms on revenue mobilisation at the FMS and customs modernisation at both the FGS and FMS have helped in the government’s efforts in achieving HIPC completion point.
On fiscal federalism, whilst progress was made against logframe outcome indicators, there were challenges not reflected by the indicators. The programme was able to exceed its milestone and draft two papers. A paper on fiscal decentralisation and the inter-governmental relationship between FMS - local government was drafted and later submitted to all FMSs. The second paper on Somalia’s accession to the EAC has also been drafted and shared. Additionally, a workshop was organised on revenue-sharing concepts and arrangements including the purpose of the revenue allocation commission which is to be established as per the Baidoa agreement on revenue sharing. However, when it came to the presentation of the paper there was partial achievement only. This was because the forum for this, the Inter-Governmental Fiscal Federalism, was unable to hold the relevant session due to political tensions between the federal government and Jubaland state. This limited the influence and impact of the work.

On domestic resource mobilisation, the programme has made significant progress in achieving the milestones on customs reform. It has faced challenges when it comes to the enhancement and modernisation of customs infrastructure. While there has been some progress in Jubaland, the biggest issues in customs infrastructure have been in Mogadishu port. This is due to procurement issues with the winning bidder on the cargo scanners, which prevented the procurement going ahead.

On the system handover of the SOMCAS, there has been an open contestation between FGS and JSS on the set up of the core team that will decide on the management of source code, data and changes in tariffs. There was not agreement on such SOMCAS governance issues during the review period, and if they are not reached subsequently there is a risk of derailment in the progress made by PREMIS on customs reforms.

The third component, on PFM policies, systems, and capacity in the four federal member states has been achieved. The milestone on the support to strengthening the civil service in the federal member states had also been met.

Outcome Indicator 1.1: End-to-end use of SOMCAS in Mogadishu and Kismayo (seaports and airports)

The first part of the milestone, the implementation of the customs strategic plan, was not fully achieved in 2024 but was signed and approved in January 2025. Therefore, there was a short delay. PREMIS2 continued to support the development of the FGS Implementation Workplan in January 2025. The FGS DG for Revenue has also approved the ToRs to establish the FGS Customs Reform and Modernization Committee to plan and monitor implementation of the Workplan. In JSS, greater progress has been achieved as the MoF accepted the Strategic Plan in Q2 2024 and approved the JSS Implementation Workplan in May 2024. The JSS Customs Reform and Modernization Committee was established in July 2024 and completed Q3 and Q4 monitoring reports on the implementation of the work plan.

The second milestone for the year, which included support for legislative options of alignment of customs legislation with the EAC framework, has also been achieved. Specifically, PREMIS2 completed a workshop with FGS legal experts to support the FGS MoF and Somali Customs to respond to its obligations to amend its legal framework to align with obligations arising from Somalia’s accession to the East African Community (EAC). Further workshops on EAC legislative alignment are planned for Q1 2025.

Lastly, the third milestone the Handover Roadmap has been achieved. The plan has been written and gone through several rounds of drafting. The training of MoF IT specialists, which will enable the sustainability of the system, has also been completed. A meeting is scheduled in Nairobi in February 2025 to finalise the handover of the management of the system and the source code. There have been challenges in getting the handover meeting to take place, with the FGS demanding that these only be done by themselves without the presence of the JSS team. However, we several attempts on a more senior level we have been able to finally agree to both a technical meeting with both FGS and JSS and a handover meeting to finalise agreements.

Outcome 1.2 Shift to value-based import duty tariff and implementation of a single tariff in Mogadishu and Kismayo.

At the end of 2023, the structure of the import duty tariff was harmonised while the harmonisation of reference values was only partially achieved. JSS initially agreed to apply FGS’s reference values to enable single-duty tariff schedules to be implemented across FGS and JSS. However, there was pushback from the private sector which refused to agree to immediately increase the costs of essential items. The ambition for the year (2024) was to increase 2a) the number and types of commodities in JSS tariff meeting FGS reference values and for more 2b) evidence-based harmonisation.
Additionally, The WB and IMF have both completed an impact analysis of Customs revenue due to the implementation of EAC rules of origin and WTO transaction value. These reports were done separately.

## Outcome 1.3 Development of new FMS Tax Policies and Legislation to reflect evolving fiscal federalism & harmonization policy framework.

All FMS validated a first draft of state tax laws in August 2024. The second draft was then later validated in December 2024. However, the tax rates included in the proposed drafts have yet to be confirmed. Additional workshops have been planned for January when these workshops will be conducted. Similarly, the drafts of the Tax Policy Statements which are the basis of the state tax laws have also been drafted (Milestone 2b) and are on track to being finalised. The finalisation of the law has however been delayed owing to the ongoing political conflict between FGS and JSS delaying JSS participation in the workshops. However, progress has been made and the workshops with JSS will be organised in Q1 2025. At this moment a date has not been set.

Additionally, although the State tax laws are meant to align with the FGS’s Income Tax Law and the Baidoa agreement (resource sharing agreement in Baidoa city on 15-17 March 2023) the FGS’s Law has yet to be approved by parliament.

## Outcome 2.1 Level of implementation of intergovernmental arrangements on FGS fiscal transfers to FMS.

The FGS and FMSs had agreed on a formula for inter-governmental transfers based on parameters agreed at the January 2023 IGFF, whereby the FGS was to receive 60% of the share of budget support from EU and Development Partners (DP), and the rest was expected to be shared with the FMSs based on performance criteria (PEFA-sub-indicators).

The budget support transfers were successfully made to three FMSs (SWS, HSS and SWS) and included in their budget. However, JSS did not receive the transfer due to political differences with the FGS, and its budget was approved before the workshops, meaning the transfer was not reflected in their planning.

## Outcome 2.2 FMS Average Scores on 3 PEFA indicators.
##
This outcome indicator, based on the PEFA methodology, assesses key aspects of Federal Member State’s Public Financial Management (PFM) systems through a combined average of three PEFA indicators. The target of achieving an average B score on at least two indicators by December 2024 was not met. The FMSs recorded a B+ on one indicator (legislative scrutiny of budgets) but overall reported an aggregate score of C+. However, there were positive developments, including timely budget approvals and accurate budget reports.

Budget Reliability (PI-9): The score remained D because FMSs did not publish all required budget documents. However, compliance improved from 4 out of 20 in 2023 to 12 out of 20 in 2024 (a 40% increase). Delays in publishing financial statements and audit reports were the main challenges. PEFA also requires budget execution reports within one month, while FMS rules allow 45 days, affecting the score.

Legislative Scrutiny (PI-18): The score improved from C+ to B+ with PREMIS2’s support. GSS and HSS published Budget Framework Papers (BFPs) online and got legislative approval, but JSS and SWS only shared them with lawmakers. PREMIS2 will now focus on earlier publication and including Medium-Term Forecasts in budgets.

Budget Reporting (PI-28): The score stayed at C+. FMSs produced detailed reports, breaking down expenses by ministry and project. However, in-year budget execution reports were not published within PEFA’s four-week deadline. All states met an eight-week deadline, but only GSS came close to the four-week target. Most states had accurate financial data, though SWS faced some issues with accuracy.

On a positive note, all FMSs received an A for timely budget approval, with GSS and JSS demonstrating strong planning. Also, for the first time, all states held citizen engagement meetings. Moving forward, PREMIS2 will continue helping Ministries of Finance improve reporting, data accuracy, and public access to financial information.

## Outcome 2.4: FMS Civil Service Commission average scores on HRM performance indicators

There has been a great effort put into providing technical assistance to all four FMS Civil Service Commissions to carry out recruitment exercises that ensure merit-based appointments in compliance with the RCRF threshold. To assess the level of improvement, the team continued to use the HRM assessment tool previously used, and these sub-indicators spanned the various stages of recruitment.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Somalia by the end of 2024 was able to reach the IDA 21 milestone proving to be the only country to receive this right after the HIPC completion point. As an achievement this proved to be significant, showing the country’s commitment to improving its economic reforms and governance. However, after this 3 years IDA grant is over Somalia will need to head towards greater self-reliance which in turns requires it being able to build a sustainable revenue mobilisation.

This increases the importance of tax reforms in both within the FGS and FMS, continued enhancement on customs modernisation and strengthened PFM. “To reach the 4.5 percent tax-to GDP ratio by 2030, Somalia will have to prioritize adapting the national tax system to regional integration with EAC; continued reforms in income tax, customs, indirect taxation; and finalise harmonisation and tax sharing across the federation.
[note] Toward Building Somalia’s Social Contract. World Bank paper No. D/23/168

## C. DETAILED OUTPUT SCORING

Output Title	FGS, FMS, and their development partners use PREMIS advice to advance fiscal federalism reforms.
Output number:		1	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of policy proposals or policy briefings on fiscal federalism developed and discussed with FMS and/or FGS.	2 papers / (a) Local government and inter-governmental relationship fiscal decentralisation (FMS - local government). / (b)Somalia's Accession to the EAC Policy paper for the FGS (draft stage).	A (Indicator met expectation) / The programme met the milestone for the year drafting two papers
1.2 Number of briefing papers or workshops on fiscal federalism delivered to other programmes and/or other development partners.	2 papers	B (indicator moderately did not meet expectation) / The milestone was partially achieved as only one briefing paper was drafted.

The programme's Fiscal Federalism and Harmonisation component seeks to support FGS, FMS, and development partners to advance fiscal federalism. Progress against this objective is measured through the number of policy proposals and briefings developed and discussed with the FMSs and FGS (1.1) and the number of briefing papers or workshops on fiscal federalism delivered to other programmes and other development partners (1.2).

Output Indicator 1.1. A paper on fiscal decentralisation and the inter-governmental relationship between FMS - local government was drafted and later submitted to all FMSs. A draft of the second paper on Somalia’s accession to the EAC has also been prepared. Additionally, a workshop was organised on revenue-sharing concepts and arrangements including the purpose of the revenue allocation commission which is to be established as per the Baidoa agreement.

Output Indicator 1.2. The briefing paper on IGFF harmonisation was completed but was ultimately not presented at the IGFF for political reasons. Additionally, PREMIS2 provided support on a policy brief developed by SSF on the ‘Integration and Harmonization of FGS-FMS Revenue Systems.

The PREMIS2 team has also been working to support the WB programme providing service delivery grants to local governments. At the World Bank’s request, the PREMIS team developed a template to be used for budgeting and recording transactions by District Councils, which allows for easy mapping onto the unified chart of accounts (UCoA) in use by FMSs and FGS. This was approved at the IGFF-TC meeting in Kigali in August 2024, with the intention of it being inserted into the manual referenced in the draft Grant Agreement by the World Bank. There has been a slight hiatus with the promulgation of the Template.

At the most recent meeting of IGFF-TC, both FMS Directors General and the Federal DG Revenue argued that the use of the template by DCs should be a requirement for both budgeting and ledger functions from next year, something with which the WB now agrees. The template will now be tabled at the next IGFF Technical Budget Sub Committee (currently nothing has been scheduled).

The preparation and submission of these papers has enabled the FMSs to be both fully aware and prepared in implementing agreed steps but also have the correct documentation to adhere to changes once agreements have been reached at the IGFF.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

PREMIS’ contributions and ability to positively support the IGFF were recognised in 2024 as the programme was given a formalised role to contribute at each IGFF meeting. Multiple briefing papers (e.g. on implementation of the policy framework) were produced for the IGFF, as well as significant work on tax policy and PFM legislation.

Another recommendation was for PREMIS to use the platform to provide policy advice, and this was implemented with the PREMIS team drafting two papers on fiscal federalism and decentralisation.

As mentioned in recommendation 4, it is important that the IGFF meetings are strengthened and there are regular meetings to strengthen fiscal reforms across both the FGS and FMS.

Output 2	Domestic Revenue Mobilisation policies, systems, and capacity formalised in FGS and FMS.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Reform and modernisation of customs administration and systems (SOMCAS) at major ports and airports.	(a) SOMCAS Business Processes and Standard Operating Procedures developed and approved / (b) ICT Policy developed and approved / (c) 70% of the customs modernisation and enhancement works completed at Mogadishu port and airport underway / (d) 70% of customs modernisation and enhancement works underway in JSS.	B (Indicator moderately did not meet expectation) / The first milestone (2a), which included the SOMCAS Business Processes and Standard Operating Procedures has been developed and approved by the FGS MoF. (2b) the development of the ICT policy has also been approved, and the milestone has been achieved. Milestone (2c & d) for the year has not been achieved, progress has been made in the enhancement and modernisation of customs infrastructure.
2.2 Number of customs administration training courses successfully delivered by PREMIS to frontline customs staff	7	A+ (Indicator moderately exceeded expectation) / The target for the number of training courses was exceeded and the milestone was achieved. A total of 10 training courses were conducted in place of the original target of 7.
2.3 PREMIS supports dialogue between Customs authorities and private sector representatives.	(a) Customs trade consultative forum meetings held biannually on the basis of the established schedule in Jubaland / (b) Customs trade consultative forum meetings held biannually on the basis of the established schedule in FGS.	A (Indicator met expectation) / In both JSS and FGS, the team has achieved the milestone for the year. JSS was able to hold this in Kismayo with the business community. On December 18th and 19th the FGS held the forum with the private sector in Mogadishu.
2.4 Improved fiscal policy capacity in 4/4 FMSs	(a) Budget Framework Papers (BFPs) for FY 2025 are part of the documentation sent to parliament. / (b) Robust domestic revenue modelling (tax and non-tax) is conducted, and feeds into the BFP for FY 2025. / Partially Achieved:	A (Indicator met expectation) / Progress against the milestone has been achieved, and the team has assisted the FMSs in drafting the Budget Framework Papers (BFPs) (2a) based on robust revenue models (2b) Representatives of the Macro Fiscal team attended workshops where revenue models were developed for own source domestic revenues in all four FMSs. For the first time, the Budget Directors also participated in the workshops, which facilitated greater collaboration and analytical thinking among the various teams involved in the budget development process.

Briefly describe the output’s activities and provide supporting narrative for the score.

The SOMCAS system has made important progresses but faced many challenges. The implementation of the system has encountered complex political challenges. For JSS implementation has been somewhat straightforward due to the lack of a previous system enabling its users to be trained on only one system and have full usage of that system. However, due to the presence of the PCMIS at the FGS, the implementation of the SOMCAS has always faced many political challenges due to the fact that one system offers complete usage without oversight whilst the other ensures there are clear oversight and transparency of usage. As a result, the full usage of the SOMCAS system has not been implemented in both Mogadishu seaport and airport. The transfer of ownership and funding responsibility to the Government of Somalia has also faced challenges, particularly around the ownership of the source code, the establishment of system governance arrangements and the partition between FGS and FMS. Disagreements in these areas remained unresolved at the end of the review period between the FGS and JSS, reflecting broader tensions around resource management and political trust. This slowed progress in finalising contractual agreements between the FGS and the system developers (which was unresolved at the end of the review period), creating uncertainty about long-term system sustainability and over continued use of a single unified national system by both FGS and JSS.

However, significant progress was made in achieving the milestones to reform and modernise the customs administration and systems. The first milestone (2a), which included the SOMCAS Business Processes and Standard Operating Procedures has been developed and approved by the FGS MoF. The second milestone (2b) the development of the ICT policy has also been approved, and the milestone has been achieved. This policy sets the conditions for the approval of users to operate the SOMCAS system, username and password. While the third milestone (2c) for the year has not been achieved, progress has been made in the enhancement and modernisation of customs infrastructure, particularly in JSS, where the construction of the server room at the MoF HQ in Kismayo and construction of the new Kismayo Airport Customs building are both progressing well.

At the FGS level, progress has been slower due to a variety of reasons. For example, the procurement for a cargo pallet scanner at Mogadishu Airport has not been completed as bids were not compliant with requirements set out in the Invitation to Bid (ITB). Unfortunately, at this moment no date has been given. Regarding the construction works at FGS port, a company has been selected to complete the building work at the port, however, contracting is ongoing, and the work has yet to commence (it is set to commence in January 2025).

PREMIS 2 aims to support the creation of more structured spaces for dialogue between the customs authorities and the private sector representatives. In the programme's first year, the original milestone for the second year was achieved and the Team was successful in supporting the organisation of the Customs and Trade Consultative Forum with Chambers of Commerce in Jubaland.

The milestones were subsequently revised and the ambition for the current year was to ensure that the Customs trade consultative forum meetings were held biannually on the basis of an established schedule.
[note] A forum held both in Kismayo and Mogadishu for to show case customs and trade in these respective cities and their ports.

In both JSS and FGS, the team has achieved the milestone for the year. The Customs Trade and Transport Forum (CTTF) was held in Kismayo and attended by 53 government and private sector representatives in Q2 and in Q4 (December). The ToRs of the CTTF Committee were agreed and a commitment to collaborate on reforms in Customs and Trade issues was established. Private sector representatives agreed to proceed with the full implementation of SOMCAS, following the provision of refresher training, organized by the MoF the week following the CTTF event. At the FGS level, while there were some delays, the meetings took place in Q3 (August) and again in Q4 (December).

Several issues were raised during these meetings. During the JSS Customs Trade and Transport Forum (CTTF) on the 5th of December 2024, tensions between FGS and JSS were highlighted as a key challenge for trade facilitation. Both local and international flights were suspended for close two months, and lower trade was experienced at the ports in the period leading up to the meetings. The FGS held a two-day CTTF on the 18th and 19th of December, providing presentations on the SOMCAS Business Process and SOPs, the Somali Customs Strategic Plan and the Customs General Regulations. The private sector expressed concern with the ‘double taxation’ following the application of VAT in addition to the 5% service tax on imports. Additional concerns were also raised regarding regulatory inconsistencies, infrastructural limitations, and gaps in inter-agency collaboration.

The target for the number of training courses was exceeded and the milestone was achieved. A total of 10 training courses were conducted in place of the original target of 7. Participants attending the Rules of Origin training for instance described how the training helped them to understand how to handle disputes among partner countries; ‘The training was valuable to improve the integration of EAC, it’s important to continue the training like this more often.’
The programme has supported the development of fiscal policy capacity that was embryonic in most states in FY2022. Progress against the milestone has been achieved, and the team has assisted the FMSs in drafting the Budget Framework Papers (BFPs) (2a) based on robust revenue models (2b).

The budget framework papers for FY 2025 were developed following a workshop that was organised with the FMSs. Representatives of the Macro Fiscal team attended workshops where revenue models were developed for own source domestic revenues in all four FMSs.

 Describe any changes to this output during the past year, and any planned changes as a result of this review.

Under Output 2, which specifically measures improvements in DRM policies, systems and capacities, two indicators have been added to measure improvements in systems and capacities including:

- Reform and modernisation of customs administration and systems (SOMCAS) at major ports and airports (Output 2.1),
- Number of customs administration training courses successfully delivered by PREMIS to frontline customs staff (Output 2.2).

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

PREMIS 2 programme is the only reform programme on customs in both Mogadishu port and airport as well as Jubaland port and airport. Based on the recommendation of the previous annual review, the programme has provided skilled personnel in the revenue department as a domestic revenue mobilisation adviser and an IT adviser. Through these personnel there have been greater input and support directly to the Ministry of Finance of the FGS.

Lesson

The major lesson has been that reforms without political will is challenging and at times near impossible. There were occasions when the PREMIS team’s work was impeded or disturbed by a lack of appreciation of the implications of federalism on the part of FGS. Most recently this has been demonstrated around the role that JSS might play over SOMCAS handover, but has also been evident in other areas, including tariff harmonisation. Internally, the Federal MoF is divided, with factions occasionally working together, politicised reporting lines and a lack of strategic messaging. There was an ongoing ‘withdrawal’ of Puntland from the reform, and the PREMIS team remained unable to engage with Puntland.

Recommendation

As the PREMIS 2 programme comes to an end in October 2025, it is important that there is sustainable plan in all aspects within the customs reform. This includes increasing the internal capacity of the technical teams who work through training-of-trainers (ToT). These trainings will ensure that there are sufficient capabilities within the ministry to continue the reform process even after the programme completion.

Output Title	Improved PFM policies, systems and capacity
Output number:		3		Output Score:		A
Impact weighting (%):		40%		Weighting revised since last AR?		No

Indicator(s)	Milestone(s) for this review	Progress
Harmonised preparation and publication of budget documentation in 4/4 FMSs.	(a) FY 2025 Annual Budget documentation prepared for submission to Parliament. / b) FY 2024 Citizens' Budgets prepared for publication. (12)	(a) Met expectation A: The budget documentation has been submitted to parliament. / (b) Met expectation A: The FY24 citizen budget has been published in both English and Somali.
Harmonized preparation and publication of financial documentation in 4/4 FMSs.	(a) FY 2023 financial statements published based on the Unified Chart of Accounts (UCOA) / (b) FY 2025 budget classification based on the unified CoA. / (c) Mechanism in place to ensure maintenance of harmonised Chart of Accounts.	(a) Met expectation A: FY 2024 accounting and financial reporting based on the unified CoA / (b) Met expectation A: FY 2025 budget classification based on the unified CoA: In progress / (c) Moderately did not meet expectation B: / There is quarterly meeting between the AG and the treasury departments at the FMSs that are ongoing.
Number of PFM training coursed successfully delivered by PREMIS.	9	Moderately exceeded expectation A+: / 12 PFM training course delivered
Enhancement and expansion of FMIS (Bisan ERP).	(a) Costed Bisan ERP Enhancement Concept Note approved by the Steering Committee	(a) Moderately did not meet expectation B Concept Note on BISAN enhancements was approved by FCDO however yet to be approved by Steering Committee.
[note] Training provided: Budget Execution Training; Financial Reporting and Super-users Training for FMIS, RMS, and BPM; Accounting and Cash Management Training; Asset Management System Training & Internal Audit Department Training; Budget Framework Paper Training; PFM User Account Validation System Admins Workshop; Budget Framework Paper; Parliament Finance Committee Workshop; Finance Committee Workshop; Citizen Engagement Workshop; IPSAS Workshop; Budget Document Harmonisation: Coordination Meeting between FMS Budget Directors and FGS Deputy Budget Director

The overall score for this output is ‘A’. This component of the programme aims to strengthen the overall financial management policies, systems, and capacity in the four Federal Member States (Galmudug, Hirshabelle, Jubbaland, and South-West).

There has been notable progress in publication of budget documentation, Budget classification based on unified Charts of Accounts and FMS citizens budgets prepared for first time. However, the decision of made by steering committee to use Somalia Financial Management Information System (SFMIS) instead of BISAN has created significant uncertainties regarding the scope and nature of PREMIS2 support for the remaining period of the programme.

Output 3.1 - Budget documentation successfully submitted to Parliament. The budget documentation includes Budget Framework Papers (BFP), summary, Minister’s presentation, and speech. The FY24 Citizen Budget was also published in English and Somali.

Output 3.2 – The FY2024 financial reporting and FY2025 budget classification were fully implemented using the unified Chart of Accounts (CoA) (Milestones 2a & 2b). The CoA Manual is currently in progress. Significant discussions on CoA maintenance have taken place with the FGS Accountant General and Treasury Departments at the FMS level to ensure proper implementation. Quarterly Treasury-AG meetings have strengthened coordination, and FMS Treasury Directors are now included in FGS-led capacity-building initiatives, such as a training program in Nigeria. Additionally, the PFM team delivered International Public Sector Accounting Standards (IPSAS) training to enhance financial reporting standards.

Output 3.3 – This is a newly added milestone for this year. A total of 12 training sessions were organised and completed, exceeding the target of 9. This training was designed in coordination with PREMIS 2 team and FMS Ministry of Finance team. Feedback was very positive (98%), with participants highlighting valuable insights into budgeting, revenue forecasting, and IPSAS compliance.
For example, attendees of the Citizen Budget Engagement training noted that it provided an overview of budget principles, relevant legislation under the PFM Act, revenue forecasting, and a deep dive into Budget Framework Papers (BFPs). Similarly, IPSAS training participants reflected on how the sessions improved their understanding of preparing financial statements that comply with IPSAS standards, ensuring consistency, comparability, and reliability across public sector entities.

Output 3.4 – A Concept Note on BISAN enhancements was approved by FCDO, securing 52 additional licenses (13 per FMS) and expanding access to three new ministries (Milestone 2a). However, approval from the Steering Committee has not yet been received. Instead, during its December 2024 meeting, the Steering Committee (SC) decided to transition from BISAN to SFMIS over a 12-month period (April 2025 to March 2026). This decision was driven by the FGS, however some of the states, such as JSS, oppose the change. They have suggested that there can only be a solution if the implementation of the SFMIS is alongside technical assistance – capacity had been built in the usage of BISAN and they want to ensure that their staff are fully versed on the usage and maintenance of a new system. The SFMIS which is used by the FGS has lacked modules such as the budget preparation whilst the BISAN system enables users to prepare budgets and execute budgets once approved by parliament.

Over the past two years, PREMIS2 has focused on upscaling capacity building in the BISAN system, with plans to decentralise its use. While FMSs appreciated the support for BISAN’s continued use, the decision to transition has introduced significant uncertainties regarding the scope and nature of PREMIS2 support for the remaining period of the programme until October 2025.

Describe any changes to this output during the past year, and any planned changes because of this review.

No change on this output since the last annual review. Output indicators 3.1, 3.2 & 3.3 were added.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Some of the workstreams and costs associated with the PFM component of PREMIS 2 could be responsibly closed and transferred to the governments before the end of the programme. Arguably, for example, the operations, maintenance, and enhancement of IT systems in the FMS could be financed more efficiently using World Bank resources.

Lesson:

The Steering Committee’s decision for FMSs to move from BISAN to SIFMIS in 2025 shows how FGS politics can shape the program. In such situations, success depends on being flexible, understanding political changes, and managing power dynamics wisely. The progress made so far from the last annual review is exit plan for specific activities has been discussed and agreed at PREMIS2 steering committee meetings (e.g. funding IT systems will end in March 2025 with responsibility for funding to reside with government counterparts, who may leverage SERP funding to do so).

However, due to uncertainties around final year budgets and joint planning with the WB SERP programme, a comprehensive and detailed exit strategy and handover plan is yet to be finalised. Insecurity due to the war with Al Shabaab and clan conflict has also had an impact on delivery. For much of the year PREMIS have been unable to deploy advisers to HSS, although in September they were able to send both the HR and PFM adviser on a mission to Jowhar following successful cooperation with the authorities and ASI’s Duty of Care team. For the last month of the year, the PREMIS team had to reduce their visibility in Kismayo because of tensions between JSS and FGS.

Recommendation:

PREMIS 2 should focus on two main priorities: (a) identifying possible support that will ensure smooth handover and sustainability of PREMIS work in the programme’s remaining period (Oct 2025) and (b) improving coordination with development partners. This includes working closely with Somalia Enhancing Public Resource Management Reform Programme (SERP)/The World Bank and the FGS, ensuring inclusive engagement, promoting joint planning, and clearly defining responsibilities for key processes like the BISAN-SFMIS migration.

Output Title	Strengthened civil service management through Civil Service Commissions.
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicators	Milestones	Progress
4.1. Implementation of the Competency Framework in FMS.	Competency Framework training programme conducted in 4/4 FMS.	A (Indicator Met)
Number of training programmes conducted annually by PREMIS. / Proportion of training participants who are satisfied with the training received.	12 / 90%	A+ (Indicator met) / 25 trainings achieved, Exceeded the initial 12 trainings that had been planned. These trainings were conducted participation satisfaction of 96%.
4.3. / Number of Women in Government training modules conducted annually by PREMIS. / Proportion of training participants who report strengthened capacity and empowerment to carry out their roles and responsibilities.	2 / 90 %	A (Indicator met) / 2 of 2 Women in Government (WIG) training modules conducted, with 100% reporting strengthened capacity and empowerment.

Briefly describe the output’s activities and provide supporting narrative for the score

The Civil service component seeks to strengthen civil service capacity, organisational design, and workforce management through Civil Service Commissions in four FMSs. Within the review period PREMIS II has completed competency framework trainings, which agreed the framework in principle, but the CSC commissions requested simplification in some areas to improve implementation.

A second round of workshops will be delivered in February 2025. 25 training programmes were delivered to Civil Service Commissions within the review period with a satisfaction rate of 98 percent. PREMIS II has recognised the importance of sustainability of training and has consequently prioritised equipping participants with the skills to share their learning more broadly across the Civil Service Commissions and other ministries. A train the trainer workshop was delivered for nominated staff, which included Women In Government (WIG) participants.

The Women in Government (WIG) programme has run for 4 years and has been delivered to an annual cohort. It is intended to empower women and support gender inclusivity in the public sector. Two WIG events were completed within the review period, with 100% of respondents agreeing the training strengthened their capacity and empowerment. Participants reported that the training is leading to colleagues and leaders gradually developing a better understanding of gender issues, contributing to more inclusive work environments. In addition to the outputs under this component, PREMIS II also provides technical assistance to the FMS Civil Service Commissions to carry out recruitment exercises to ensure merit-based appointments and support on induction processes. PREMIS II has advised that recruitments appear to be functioning well following PREMIS training and support, however political interference in appointments remains.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There are no changes to this output since the previous Annual Review. This output was added following the 2023 Annual Review, to specifically capture public sector administration results
.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

There were no specific recommendations related to this output in the previous Annual Review.

Recommendations:-

Granular Feedback – Given the high scores for participant satisfaction and strengthened capacity and empowerment, FCDO should consider requesting greater granularity of feedback to ensure that the technical assistance is meeting expectations and lessons learned for further improvement.

Recruitment and Induction – the training provided by PREMIS II to the Civil Service Commissions on recruitment and induction is not included in the logframe from PREMIS II. As this appears to be a major component of work, funded by FCDO and reported on by ASI, the programme team should consider inclusion of recruitment and induction as a logframe indicator.

Output Title	Somalia Country Fund (SCF II) - The FGS develops capacity to implement sound macroeconomic policies with IMF technical assistance.
Output number:		5		Output Score:		B
Impact weighting (%):		5%		Weighting revised since last AR?		No

Indicators			Milestones		Progress
5.1. Number of activities to strengthen tax policy and administration.			11		B (Indicator expected to meet milestone by end of IMF reporting period) / 9 activities conducted as of December 2024, with a further 2 activities planned between December 2024 and February 2025. / Of the 11 completed or planned activities, 5 were focused on tax policy, 5 were focused on revenue administration, and 1 on expenditure policy.
5.2. Number of activities to improve budget credibility and transparency.			3		B (Indicator expected to meet milestone by end of IMF reporting period) / 2 activities conducted and 1 planned between December 2024 and February 2025.
5.3. Number of activities to develop banking legislation, regulation and supervision.			3		B (Indicator expected to meet milestone by end of IMF reporting period) / 2 activities conducted as of December 2024 (1 on banking legislation and 1 on Central Bank organisation) and 1 further activity planned on Central Bank organisation between December 2024 and February 2025.
5.4. Number of activities to strengthen the compilation and dissemination of macroeconomic and financial statistics.			6		B (Indicator expected to meet milestone by end of IMF reporting period) / 5 activities conducted as of December 2024 and a further 1 activity planned between December 2024 and February 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is delivered through a contribution to the Somalia Country Fund (SCF II) for Capacity Development in Macroeconomic Policies and Statistics, which was established and is implemented by the IMF. The current phase of the Somalia Country Fund covers the period March 2021 to April 2025. It provides technical assistance to FGS in five areas: (i) deepening the development of a robust macroeconomic framework and policies; (ii) improving the management and operations of the central bank; (iii) modernisation of tax and customs policy and administration; (iv) strengthening PFM, public investment management, and public debt management; and (v) enhancing the capacity for the production and dissemination of macroeconomic data. Somalia needs extensive capacity development support to stay on track with the reforms under the ECF programme and, therefore, financing the IMF trust fund is critical.

Over the review period, SCF II has undertaken 13 capacity development missions, with a further 5 planned, covering 9 of the priority areas under PREMIS II. Despite liquidity challenges for SCF II, the programme has delivered on the expected outcomes. It should be noted that this output was scored B because milestones were not fully achieved in the review period ending in December 2024, despite the expectation that they would be completed with the IMF reporting period ending February 2025. Notable successes include i) the development of a medium-term revenue roadmap, ii) support to Somali Customs Automated System, iii) preparations for the Income Tax Law, iv) supported the amendment of the Public Private Partnerships Bill, and v) enhanced the functionality of the Somalia Financial Management Information Systems.

Somalia reached the Completion Point under the Heavily Indebted Poor Countries (HIPC) Initiative in December 2023, with total external debt reduced to 6 percent of GDP. Since HIPC completion, a new IMF supported programme, the Extended Credit Facility (ECF) has been approved to continue support to macro-fiscal reforms. There is an overlap in the priority areas of the ECF and SCF II. Given both are IMF programmes, duplication should minimise but it may be worth development partners considering whether two similar programmes represent additionality or whether greater coherence and reduced overheads could be achieved through a single IMF programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review. :-There have been no changes to this output since the previous Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead: -There were no recommendations related to IMF from the previous Annual Review.

Recommendations

IMF Action Plan – IMF to develop, in consultation with donors, and implement an action plan to address the lessons learnt from the mid-term evaluation of SCF II, covering March 2021 and October 2023.

Extension to SCF II – Partners to decide on extension of SCF II by one year until April 2026. Although FCDO has fully disbursed the funding to SCF II, this extension will go beyond the programme end date. Therefore, FCDO should consider whether to amend milestones to reflect this or consider a no-cost extension to the programme to allow for continued engagement and reporting.

Coordination of PFM Support – SCF II should continue to prioritise coordination with the Extended Credit Facility (ECF), with World Bank, and with other development programmes on PFM and Tax, including ASI funded capacity development under PREMIS II.

Diversity of Consultants – In addition to tracking of participants’ gender, IMF should consider tracking of consultants’ gender as a first step to ensure sufficient diversity and representation of those delivery IMF capacity development.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance: - The main cost drivers for the programme remain staff costs, security, travel, and procurement, with key focus on long term technical assistance fees, disbursements to facilitate institutional development, non-project associated costs and capacity building costs. FCDO has committed a total of £10m, to the delivery of PREMIS2 programme, with a further £2.3m coming from Denmark. FCDO has been monitoring disbursements in line with ProF rules. The speed of spending has been consistent apart from CDEL spending which has been slow due to procurement complexities. To improve effectiveness, the programme relocating high importance multi-day events to Nairobi to maximise on attendance. Though this was higher cost, the technical team reported significantly higher attendance and focus on meetings while attending other programme related meetings in Nairobi, evidence of good stewardship of resources.

VfM performance compared to the original VfM proposition in the business case:- The Value for Money Statement in the business case provided a combination of direct technical assistance on Somalia’s revenue raising capacity through customs, improved public financial management at the Federal Member State level, and strengthened Macro Policy though support of IMF.

The programme has been tracking the % of total number of days worked by National Advisers and average cost of workshops per participant trained. The use of National Advisors over the year was 65%, which delivers VfM due to lower average fee rates, reduced travel costs and increased ability to deliver training and workshops in JSS, GSS, HSS, and SWSS in 2024. On the Macro Policy front the planning of FY25 workplan and related budget was constraint by the liquidity of the SCF. Therefore, IMF prioritized the continuation of existing CD activities critical to the achievement of the SCF objectives and ECF benchmarks, such as PFM, Revenue Administration and Tax Policy. The implementing partners have been part of the FCDO compliance workshops and lesson learning on VFM, where knowledge and experience on VFM were shared.

Value for money performance: - At a wider programme level, efficiencies & effectiveness have been made and identified through technical collaboration. There has been increased focus on collaboration across the workstreams at a technical level, which has been reflected in the planning and programming of workshops and events. High levels of communication between PREMIS2’s Component Leads ensures that pockets of opportunity are found for joint programming or collaborative working. A key example of this is the collaboration between the Civil Service and Customs workstreams, where civil service workstream workshops which utilised individuals from FGS/FMS customs were scheduled and organised to align with existing customs workshops within their Y3 workplan.

On effectiveness VFM indicators related to cost effectiveness around customs indicated SOMCAS data from previous implementation has manifested from the previous declarations. On efficiencies PREMIS2 benefits from ASI’s shared services model under which recurrent operating costs such as office rent, finance and operations support, and transport are pooled and then shared proportionally between ASI’s projects in Somalia. This means resources and services can be provided more easily across projects, which leads to higher quality services for a given cost, more efficient spending on expenses, and a higher proportion of budget going towards the key output of the project particularly technical assistance.

The programme recognises the need for equity across programming, and the focus of equity reporting has been monitoring the programme’s engagement with women. PREMIS2 programme has committed to understanding, monitoring, and improving engagement with women.

The programme’s quarterly reports include reporting on how many female participants attend PREMIS2 workshops, as well as how many workshops are targeted directly at women. Over the year an average of 13.61% of participants trained in PREMIS2 workshops were women which is an improvement from the previous year. Training delivered by the Civil Service workstream had the highest female participation this year, and there was a continued increased in female participation at the Customs workshops. The Women in Government programme continues to work to enhance the confidence and skills of female civil servants and aims to empower them to realise their full potential through training and mentorship.

E: RISK

Overall risk rating: Major
Overall, we assess the risk as Major; this has not changed from the risk assessment at the last annual review. Delivery and operational, reputational, financial and political factors inhibit the achievement of the project purpose in this highly fragile context in which the programme is delivered. Enhanced controls applied to the management of this programme work well to manage the overall exposure levels. Some of the key control measures include Third Party Monitoring and quarterly risk reviews. PREMIS2 partners have adopted risk-based approaches in identifying and assessing implementation entities and project specific financial management risks.

The programme’s overall risk appetite at approval is receptive. The risk assumptions set out in the Business Case broadly hold true. PREMIS 2 engages on some of the most politically sensitive issues, which are critical to Somalia’s stability. The programme team has reviewed and updated the risk appetite for each of the FCDO six risk categories, and the risk register on a quarterly basis (see Table 1 below). The programme is being delivered within the British Embassy Mogadishu ‘receptive’ risk appetite for programme delivery. Risk management is fully embedded in the programme decision making and supported by the supplier systems and processes.

The full range of significant risks that affect the programme is documented in the updated programme Risk Register, which feeds into the BEM portfolio risk register. Relevant assumptions and mitigation strategies have been factored into the Risk Register and these are actively monitored by the programme team and implementing partners.

Policy and Programme Delivery (receptive risk appetite) - PREMIS roll-out of the £1 million CDEL project introduced potential fiduciary and reputational risks, particularly around mismanagement of funds, lack of transparency and difficulties managing the expectations of counterparts. To mitigate this, FMSs were required to adhere to procurement standards as set out in their legislation, with oversight from PREMIS2 including ex-ante approval of project design and procurement documents, ex-post review of contract award and management, real-time visibility over transactions in the FMIS, and continuous monitoring and audits and oversight including by ASI advisors. This has been relatively effective with all FMS CDEL projects underway by the end of 2024.

Contextual Risk (Receptive) - The programme continued to be implemented in a complex and fast-moving environment throughout 2024. This meant that several new risks emerged, and the nature of existing risks changed, necessitating the PREMIS2 team to stay attuned to the local and adapt delivery to mitigate their impacts where possible and within our control.

Public Service Delivery and Operations (Cautious)- Insecurity undermines delivery and impact. Providing technical assistance in Somalia bears significant security risks. IMF policy does not allow travels to Somalia and, therefore, most technical assistance and training under the Somalia Country Fund programme is delivered in a third country, such as in Addis Ababa and Nairobi.
The second partner ASI has put in place security measures that allow them to carry out activities in Mogadishu and in most FMS. This review has received positive feedback as shown in Steering Committee meetings and it represents vfm balancing effectiveness of prioritising in-person engagements.

Overview of programme risk

Public Resource Management Programme in Somalia is a complex intervention in a highly fragile and challenging operating context that carries several risks, including political instability and partial political settlement, weak government and institutional capacity, constrained monitoring and supervision access, and fiduciary and delivery risk.

Risk management

FCDO maintains a risk matrix developed as part of the business case of the programme which is reviewed at quarterly programme team meetings and updated as necessary. The risk matrix was recently reviewed and updated in January 2025. FCDO will continue to review the risk systematically. The programme has engaged a Third-Party Monitor who conducts regular monitoring and verifications of PREMIS2 work results as delivered by downstream partners. During this reporting period all risks remained within the risk appetites, so none were escalated.

Outstanding actions from risk assessment - There are no outstanding risk actions from the risk assessment.

 Table 1: Risk Appetite by Risk Category
Risk Category	Risk Appetite	Rationale
Strategy and Context	Receptive (major)	Considering the delivery context and the nature of the objectives pursued, we are willing to accept PREMIS carrying a major degree of residual risk in this category.
Policy and Programme Delivery	Receptive (major)	We are willing to accept a portfolio of interventions within PREMIS that contains a mix of high and low risk activities.
Public Service Delivery and Operations	Cautious (moderate)	Considering the fragile environment in which the programme is delivered, we are prepared to accept moderate operational risks.
People	Cautious (moderate)	We are willing to take moderate risks arising from weaknesses in programme leadership and staff capacity and capability that may impact on PREMIS performance.
Financial and Fiduciary	Cautious (moderate)	We are prepared to accept moderate financial risk, with effective controls to reduce fraud risk in place and zero tolerance for inaction and mishandling.
Safeguarding	Cautious (moderate)	We are prepared to accept moderate safeguarding risks, with effective safeguarding controls in place and zero tolerance for inaction and mishandling.
Reputational	Cautious (moderate)	We are prepared to accept moderate reputational risk, with effective reputational controls in place.

Safeguarding – There are no safeguarding cases reported in the last year. ASI has updated the team on safeguarding issues in each quarter report.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial: - The total budget for PREMIS2 programme is £12.3m. FCDO contribution is £10m and Denmark (Co – Donor) contributed £2.3m. Overall, the programme has spent £9.9m being 80% of the total budget amount with nine month into the closure of the programme (October 2025).

The co-donor funding of £2.3m has been fully absorbed. £600k of this was spent under the IMF component on macroeconomic and fiscal policy and the balance (£1.7m) on ASI component on domestic revenue mobilisation, public financial management and civil service management.

The year under review (March 2024 – February 2025) budgeted for £6 million. The total spend so far is £4.2m) being 70% of the budget. The programme is on track to execute its budget for the review period. We anticipate spending fully on all the components but may have potential delays on CDEL component due to procurement complexities on scanner at Mogadishu airport; this amounts to about £300k. Hence, we anticipate a CDEL underspend of £170k in the period under review.

Overall, the programme’s financial management has been satisfactory to date and with accurate forecasting. Despite the ODA cuts the programme has budgeted to spend £1m in the next FY subject to budget availability to finalise activities leading to the closure of the programme in Oct 2025.

Table 1: Total Budgets across programme life
FCDO PREMIS2 Programme Budget Profile Over Implementation Period
2022/23	2023/24	2024/25	2025/26	Total
286,362	2,500,000	6,000,000	1,213,638	10,000,000

Table 2: Breakdown per project
Component	Description	Partner	Budget	Spend to date
300862-103	Domestic Revenue Mobilisation. Public Financial Management & Civil Service Reform	ASI	4,400,000	3,335,523
300862-401	Macroeconomics and Fiscal Policy Reforms	IMF	600,000	600,000
300862-901	Public Financial Management - Capital	ASI	1,000,000	495,000
			6,000,000	4,430,523

Any deviations in spending were anticipated and promptly communicated to the FCDO team by the implementing partners, with revised forecasts provided at regular intervals to ensure transparency and effective planning. PREMIS2 is on track to fully spend the allocated budget by the end of the programme.

Delivery: - ASI have managed to deliver a strong performance all through the year against agreed key performance indicators with FCDO. The supplier has developed robust workplans against which programme activities are monitored and tracked through monthly technical and programme management meetings and quarterly steering meetings with the government.

To date, monthly and quarterly reports covering result delivery against workplans and KPIs, and finances have been submitted largely on time and met quality requirements. The supplier has also ensured to register all programme assets into the asset register. FCDO is currently planning to undertake asset spot check early next financial year. Asset registers are shared bi-annually.

Commercial: - Overall progress on the annual workplan has been positive. Quarterly reporting has included clear narrative areas that are on/off track and reasons provided. Bi-weekly meetings has provided a forum for political and programme discussion. Challenges have been raised and discussed promptly with programme team as well as with other stakeholders. A key challenge not related to FCDO procurement is the delay of various CDEL procurements, which have affected the spend. The supplier’s financial management performance has also been good, with strong monitoring on spend and tracking progress against forecast. Quarterly spend was within 5 per cent variance. CDEL project introduced potential delays in spending however by January 2025 CDEL component commenced spending.

The key downstream partners include: -
KasmoDev – PREMIS2 Delivery Partner: - Have been able to leverage their experience and resources in customs modernisations from work on the CRATES programme to provide continuity, institutional memory, and skills to continue driving customs modernisation work in Mogadishu and Kismayo.

Infotech – SOMCAS Provider: - As with 2023, the maintenance and support InfoTech has provided to Somali Customs for the Somali Customs Automated System (SOMCAS) has been mostly satisfactory. Service uptime throughout the year has been consistently high, however a number of untimely service outages have fed an FGS narrative that the system is unstable. Infotech has generally been very quick to respond to any reports of issues, bugs or cyber-attacks, in line with their contracted Service Level Agreement (SLA).

Bisan – FMIS/RMS/BPM Provider: - Bisan systems continued to provide excellent service throughout 2024. Responsible for the Bisan financial management system, they effectively hosted, supported, and maintained the Financial Management Information System (FMIS), Budget Preparation Module (BPM), and Revenue Management System (RMS) for Jubbaland State Somalia (JSS), Hirshabelle State Somalia (HSS), Galmudug State Somalia (GSS), and Southwest State Somalia (SWS). The systems under Bisan's management maintained 99.9% uptime and availability.

Risolto – HRMIS Provider
The transition to Risolto as the contractor for hosting, support and maintenance of the HRMIS system has been extremely successful, with Risolto providing exemplary service. The team has been highly responsive to requests for information and service uptime has been near above 99%.

Audit: A financial audit of the PREMIS2 programme covering the period October 2023 – October 2024 and the report was submitted in February 2025. No major issues stated in this report. The management letter was unqualified indicating the auditor found the financial statements to be presented in all materials in accordance with financial reporting framework hence no significant issues.

G: MONITORING, EVIDENCE AND LEARNING

Third Party Monitoring: - PREMIS2 continues the use of Tetra Tech as TPM for monitoring and verifying PREMIS2 activities. The TPM partner completed three rounds of fieldwork in the year. In addition, the TPM works closely with the PREMIS2 M&E teams to provide technical assistance and support cross-cutting thematic reviews.

Monitoring and verifications: - TPM conducted a total of 35 ASI verifications over three rounds in the reporting year covering the main component of DRM and PFM as well as activities under the support to Civil Service Commission outputs, included training, events and technical assistance to various FGS and FMS counterparts. Seven of the 35 activities verified flagged for good practice, indicating that findings pointed to evidence of successful programming in action, exemplary implementation or received positive feedback from participants. All the other 27 activities were delivered as planned with no issues identified.
Ad-hoc meetings between the FCDO team and ASI have worked well and resulted in ongoing discussion and problem-solving on key topics and risks as they arose. Continued programme related issues have been monitored through regular schedule of fortnightly meetings with ASI.

Somalia Country Fund / IMF component - Regular engagement between the IMF country team and the Somali authorities, including during the staff visit and ECF review mission in June and September 2024 respectively, is a critical aspect of the SCF monitoring. During missions, stakeholders assess progress made against reforms’ targets and adjust CD plans accordingly. In addition, formal monitoring of the SCF (and IMF CD overall) is carried out via the IMF Results Based Management (RBM) system. CD experts develop a specific logframe at CD activity level (noting the intended outputs, outcomes, impacts, and milestones towards the desired impact). The IMF report to partners on an annual basis on the outcomes’ achievement at workstream level (see FY2024 annual report).

Date of last narrative financial report	February 2025	Date of last audited annual statement	February 2025

# ACRONYMS
AG	Accountant General
ASI	Adam Smith International
ATMIS	African Union Transition Mission in Somalia
BPM	Budget Planning Module
BRA	Banadir Regional Administration
CDEL	Capital Development Expenditure Limit
CRATES	The Customs Reform and Trade Enhancement Somalia project
CRMC	Customs Reform and Modernization Committee
CSC	Civil Service Commission
CTTF	Customs Trade and Transport Forum
DG	Director General
DoC	Duty of Care
DLP	Defects and Liability Period
DRM	Domestic Resource Mobilization
EAC	East African Community
FCDO	Foreign, Commonwealth & Development Office
FGS	Federal Government of Somalia
FMFF	Finance Ministers Fiscal Forum
FMIS	Financial Management Information System
FMS	Federal Member State
GSS	Galmudug State of Somalia
HIPC	Heavily Indebted Poor Countries Initiative
HSS	Hirshabelle State of Somalia
HRMIS	Human Resource Management Information System
ICMS	Integrated Customs Management System
IGFF	Inter-Governmental Fiscal Forum
IGFF-TC	Inter-Governmental Fiscal Forum Technical Committee
IGFT	Inter-Governmental Fiscal Transfer
IPSAS	International Public Sector Accounting Standards
JSS	Jubbaland State of Somalia
KRA	Kenya Revenue Authority
LG	Local Government
MDA	Ministries, Departments, and Agencies
MERL	Monitoring, Evaluation, Research, and Learning
MFU	Macro-Fiscal Unit
MoF	Ministry of Finance
NCC	National Consultative Council
NPAC	Non-Personnel Account Costs
OAG	Office of the Auditor General
OSR	Own Source Revenue
PEFA	Public Expenditure and Financial Accountability
PFM	Public Financial Management
PREMIS	Public Resource Management in Somalia
PSS	Puntland State of Somalia
RCRF	Recurrent Cost and Reform Financing Project (WB)
RMS	Revenue Management System
SBDs	Standard Bidding Documents
SERP	Somalia Enhancing Public Resource Management Reform Programme
SFMIS	Somalia Financial Management Information System
SCF	Somalia Country Fund
SOMCAS	Somali Customs Automation System
SOP	Standard Operating Procedure
SPG	Specific Purpose Grant
SWSS	Southwest State of Somalia
TIN	Taxpayer Identification Number
ToT	Training of Trainers
TWG	Technical Working Group
UCoA	Unified Chart of Accounts
VfM	Value for Money
WiG	Women in Government