## Annual Review BEPAC 2025

Title: Building an Evidence Base on Humanitarian Protection of People Affected by Conflict (BEPAC)
Programme Value £ (full life): £18.1m		Review date: 17 April 2025
Programme Code: 300484	AMP start date: 02/02/19	AMP end date: 31/03/27

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300484 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300484 Documents

A. SUMMARY AND OVERVIEW

Description of programme
The ‘Building an Evidence Base on Humanitarian Protection of People Affected by Conflict’ (BEPAC) programme is designed to address evidence gaps in the protection risks faced by people affected by conflict and to identify what works to mitigate these risks. Overall, the evidence base for Humanitarian Protection is still considerably weaker than other areas of humanitarian action. All BEPAC research projects are focussed around six aspects of improving compliance with International Humanitarian Law (IHL) by state and non-state armed groups.
[note] I.e. Physical and mental health risks and risks to legal rights.
[note] The 6 themes are: IHL violations; protection programming; restraint; local protection mechanisms; recognition; and targeting. They were arrived at after consultation during the design of the Business Case.

Humanitarian protection is a policy priority for FCDO. Promoting humanitarian protection has been an under-researched topic in humanitarian policy. BEPAC’s theory of change is that high-quality research on the effectiveness of protection interventions, and the factors that either promote or reduce rights violations, will contribute to more effective programming and policies for FCDO and the wider humanitarian system. Previous FCDO-funded research on a similar topic by the International Committee of the Red Cross (ICRC) (Roots of Restraint) demonstrates this is possible. The research undertaken by BEPAC’s component projects is independent and rigorous. It is valued by FCDO’s humanitarian protection policy team and coordinated with them and with other relevant teams across FCDO including the Humanitarian, Food Security, and Resilience Directorate (HFRD), and the UK IHL committee.
[note] See for example the UK Humanitarian Framework (publishing.service.gov.uk)

BEPAC has four component projects, one of which (with the Arts and Humanities Research Council, AHRC) has now closed. The fifth output tracks communications and dissemination activities across all components:

Output 1: with the University of Manchester. ‘Researching the Impacts of Attacks on Healthcare’ (RIAH) started in 2019 and is a multi-institution and interdisciplinary research programme looking into the nature, frequency, and scale of attacks on healthcare in conflict and to improve the methodologies employed to measure the impacts of the problem. These direct and indirect impacts include the access to and availability of health services as well as broader public health and human development outcomes. RIAH is conducting research in Colombia, Afghanistan, Central African Republic (CAR), and Nepal and supporting data collection on attacks on heath care by Insecurity Insight. It is delivered by a consortium led by the University of Manchester (UoM). It was extended to 31 March 2026 in February 2024 with an additional £0.5m to enable more dissemination and uptake of research. Having agreed an additional £0.25m with FCDO in late 2024, the project is currently budgeted at £3.99m.
[note] Manchester’s Humanitarian and Conflict Response Institute (HCRI) leads the consortium, which includes Johns Hopkins University, Geneva Centre of Humanitarian Studies (formerly CERAH), and Insecurity Insight; with support from the University of California-Berkeley, and Chatham House (the Royal Institute for International Affairs).

Output 2: with the Abdul Latif Jameel Poverty Action Lab (J-PAL). The Humanitarian Protection Initiative (HPI), implemented by J-PAL and Innovations for Poverty Action (IPA), will conduct a number of Randomised Controlled Trials (RCTs) on humanitarian protection programmes. The aim is to equip humanitarian actors with a deeper understanding of cost-effective, scalable, and context-sensitive solutions for preventing and mitigating physical, psychological, social, and legal harm against conflict-affected populations. The main phase of this component was initiated and an AG signed with JPAL at the end of December 2023. It will be £3.3m over 4 years.

Output 3: with the UK Arts and Humanities Research Council (AHRC). The Collaborative humanitarian protection research programme consisted of 12 protection research grants which were awarded to academic partners through a competitive open call for proposals. This component ended in March 2024 and cost approximately £2.9m. See Annexe 9 for publications (including some new publications in 2024 recorded in this Annual Review).

Output 4: tracks the communication of research findings from across the outputs.

Output 5: ‘Beyond Compliance’ Consortium (BCC), is a 3-4 year, £5m research programme which launched in March 2024 following a competitive grant process. The programme aims to identify legal and extra-legal strategies, including armed actors’ compliance with international humanitarian law (IHL) and international human rights law (IHRL), to prevent, reduce, and respond to harm and need in war. Beyond Compliance is led by the University of York (UoY) and incorporates the University of Glasgow and Utrecht University, and six humanitarian and human rights organisations: Watchlist on Children and Armed Conflict, War Child Alliance, Diakonia International Humanitarian Law Centre, Center for Civilians in Conflict, Centre on Armed Groups and Fight for Humanity. The BCC co-produces work with local partners and local researchers in nine case study countries: Afghanistan, Colombia, the Democratic Republic of Congo, Myanmar, Somalia, South Sudan, Syria, Ukraine, and Yemen.

Review Period
This Annual Review covers the period January to December 2024.

Log frame composition
The BEPAC logframe is composed of indicators from each of component project’s logframes (these are referenced in the output tables below). In this reporting period there are 12 output indicators to be reported on – 2 from RIAH (Output 1), 3 from J-PAL (Output 2), 4 from the communication output (Output 4), and 3 from Beyond Compliance (Output 5). There are none for AHRC as this component has now ended. To ensure a fuller picture of progress, wider reporting on progress made by all projects has also been included.

Commitment to Gender in Research:

Commitment to gender equity is prevalent across the work of all three BEPAC partners. All RIAH publications include female authors, with a number of these articles focussing specifically on gender. Examples of these over the life of the project include: a study into maternal and child health in Afghanistan, looking into the impact of attacks to female health care workers in Colombia, and women’s experiences of insurgency war in Nepal. Another study looks into the importance of sex-disaggregated data in understanding the impacts of attacks on healthcare.

The inclusion of gender as a cross-cutting theme in the HPI original design has continued to promote equity in research. Eight Co-PIs from HPI-funded projects identified as female, non-binary, or agender, substantially exceeding the milestone set. A number of pilot and development grants focus specially on gender issues, for instance: ‘Sextortion and entrepreneurship in Burkina Faso’, ‘The impacts of safe spaces on network creation and gender-based violence among conflict-affected displaced women in Egypt’, and ‘Safe spaces and internally displaced women’s and girls' wellbeing in Burkina Faso’.
For the BCC, 100% of draft academic outputs and 52% of blog articles were co-authored by women. AHRC previously conducted gender-focussed research which focussed specifically on women and girls in the following study: The Cultural Problematic in Narratives of Violence against Women and Girls in South Sudan. AHRC also looked into male experiences in conflict settings with the following publication: Longitudinal Impact of Conflict-Related Sexual Violence Experienced by Men in Detention Since the Onset of the Syrian Conflict.
BEPAC will continue to focus on gender as a salient theme in protection research and this will be monitored and annually reported through specific logframe indicators and milestones as discussed in the subsequent output and VFM sections of this review.

Summary supporting narrative for the overall score in this review – A

Researching the Impact of Attacks on Healthcare (RIAH)

RIAH’s support to the collection and publication of data collection on attacks on health care has continued mostly as planned. Publication and dissemination of RIAH research and data has led to considerable media reporting of the data (see Annexe 3), and the data and research continues to be referenced in both academic and policy arenas (see outcomes). RIAH partners continue to be in demand in academic and practitioner seminars (see output 4). RIAH continues to collaborate with important stakeholders including Insecurity Insight, and ICRC, and has participated in high profile conferences for instance the World Innovation Summit for Health (WISH) 2024. Uptake is still in progress and will continue throughout the extension period.

Humanitarian Protection Initiative (J-PAL)

HPI has made good progress after an initial delay due to staffing gaps. HPI’s inaugural call for proposals led to the one RCT with a leading humanitarian organisation in a priority country, as well as two pilot studies that will lay the groundwork for research in fragile contexts, and five project development grants. The HPI Scholars Programme has expanded J-PAL’s network of researchers in contexts where research is being done, increasing the potential for results to resonate with affected communities. HPI has built and expanded partnerships with key humanitarian actors, such as UNHCR, ICRC, and the IRC, hosting several training sessions with humanitarians on tools to assess and enhance the effectiveness of their interventions.

Beyond Compliance Consortium (BCC)

BCC has also had a good first year. Whilst still a relatively new initiative, BCC has presented papers at academic conferences, contributed to expert workshops, had meetings with states and NGO representatives, and a series of meetings with scholars and humanitarian organisations to explore synergies. They have developed new collaborations with local partner organisations in case study countries and established and completed the pilot for the Research Line alongside FCDO country offices. The dissemination of the key BCC concepts has started through the Beyond Compliance Blog Symposium and the Beyond Compliance: In Conversation podcast which have proven successful. Case study field work began in early 2025.

Major lessons and recommendations for the year ahead

Lessons

L1. As reflected in the conclusions of a RIAH workshop early in the year, and the discussion in the impact section below, the link between BEPAC’s research outputs, its outcomes, and the desired impact of improving humanitarian protection outcomes is complex. This has become more apparent as the RIAH programme shifts from research production in its earlier stages to focus more on dissemination and uptake. Many of these issues were raised in an earlier RIAH paper. JPAL and BCC will likely face a similar evolution. In RIAH’s case, these lessons have led to FCDO financing a programme extension in 2024 with a greater focus on engaging advocacy networks concerned with attacks on healthcare and changing norms as a means to effect change. (Cross-BEPAC)
[note] Protection is notoriously hard to evaluate, see for example “ALNAP Guide: Evaluation of Protection in Humanitarian Action”
[note] Larissa Fast, Róisín Read, Using Data to Create Change? Interrogating the Role of Data in Ending Attacks on Healthcare, International Studies Review, Volume 24, Issue 3, September 2022, viac026, https://doi.org/10.1093/isr/viac026

L2. Some of the current outcome and impact indicators are proving to be less useful than expected in assessing results for similar reasons. For example, the current indicators do not focus on assessing conceptual outcomes, supporting networks of change agents, or changing humanitarian norms – all of which are likely to be key programme impacts. And some indicators are turning out to be duplicative in operation. (Cross-BEPAC)

L3. While there is demand for rigorous evidence on protection programming, it has proven more difficult than anticipated to turn this demand into RCTs. Sourcing and designing protection-related evaluations has required greater JPAL staff engagement and more time to develop research collaborations compared to other sectors in which JPAL has worked. This is probably a reflection of the high demands in time and expertise on humanitarian agencies of this technique. Successful RCTs and pilots have largely stemmed from building and cultivating strategic relationships with humanitarian actors who appreciate the value of impact evaluations and offering practical training sessions, allowing key stakeholders to gain a deeper understanding of impact evaluation concepts and supporting them in refining their project designs. The Request for Proposals (RFP) process been shortened in response. (HPI)

L4. Confirmation of the importance of relationship building where, with a large consortium (nine), with four academic and five practitioner agencies, the time spent on building trust and relationships will be important for the later stages of the work. Linked to this is an enhanced understanding of the important impact-generation potential within the consortium. During the first ten months of operation, BCC researchers have disseminated BCC concepts and methods within their own member organisations. (BCC)

L5. The importance of actively raising wider awareness within the FCDO about the existence of the BCC Research Line and its offerings, and to build direct relationships with the country teams to ensure take-up. (BCC)

Recommendations

R1. The BEPAC Theory of Change should be re-assessed, with a particular focus on setting realistic impact indicators and agreeing any consequent adjustments to programme activities in particular on dissemination and uptake. The logframe should then be revised, including revision to outcome indicator 3 to ensure better assessment of the programme’s conceptual impact. (Action: FCDO/SRO and BEPAC partners, by September 2025)

R2. BCC to conduct a series of seminars on IHL for FCDO humanitarian and conflict advisers to promote professional learning and help build the recognition and trust in FCDO for the BCC research line offer. (Action: BCC by end November 2025)

R3. Where relevant and useful for protection outcomes, the FCDO SRO and DPM to cultivate more linkages across BEPAC partners (throughout and by December 2025).

R4. FCDO to develop a VFM workplan for partners to ensure that qualitative and quantitative metrics are linked to logframe outputs and documented in greater detail. (Action: FCDO PM by June 2025)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Impact statement
Humanitarian protection outcomes are improved

Theory of Change
 Assumptions
- Practitioners and policy makers have appetite and resources to use evidence in policy making and programme design.
- Better evidence is vital for designing and implementing effective programming.

Outcome Statement
Humanitarian protection policy and operations are improved through better evidence of protection risks/mitigations and evidence of what works.

Assumptions
The programme strengthens capacity of partners to measure their impact.
- The programme produces high quality evidence that improves understanding of protection risk and outcomes.
- Channels exists to communicate research results and findings to the right audience.

OUTPUT 4
Research findings are accessibly communicated and synthesised and promoted to target audiences

OUTPUT 3
Improved understanding of the drivers of protection risks

OUTPUT 2
Improved evidence of the impact of protection interventions

OUTPUT 1
Improved understanding of the type, scale and impacts of attacks on healthcare

Assumptions

- It is logistically possible to access the necessary research in contexts affected by conflict related humanitarian emergencies.
- It is possible to apply rigorous research methodology in contexts affected by conflict related humanitarian emergencies.
- Research capacity exists to implement research in conflict and fragile affected states and humanitarian emergencies.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact: Humanitarian protection outcomes are improved	Milestone December 2024	Progress
Number of IHL duty-bearer and non-state actor commitments to protect healthcare	TARGET: Increase in frequency and strength of statements indicating commitment to IHL on protecting healthcare.	840 IHL duty-bearer commitments / 1 NS actor commitment
No. of times evidence or case studies used demonstrating uptake by policy makers or practitioners.	120 (+40) RIAH / 5 AHRC	206 (+85) (RIAH) / (However, as this is duplicative of outcome indicators 1 and 2 this will no longer be tracked)

Outcome: Humanitarian protection policy and operations are improved through better evidence of protection risks/mitigations and evidence of what works.	Milestone December 2024	Progress
Outcome indicator 1: Cumulative number of citations of project outputs in relevant high-level reports, policy papers or project documents.	37 RIAH (RIAH Outcome Indicators 1 and 2) / 5 AHRC (AHRC Outcome Indicator 1.3)	Annual total 82 RIAH (Substantially Exceeded) / Cumulative total 191 against a cumulative milestone of 106 / In 2024 RIAH products had 73 citations in academic/policy publications (see Annexe 1). Key examples include: / In March, Insecurity Insight data fed into a report published in the Lancet “3 years after the Myanmar military coup—the people are suffering”. / Violence against healthcare in conflict: a systematic review of the literature and agenda for future research was cited 37 times. / In 2024 RIAH project outputs were referenced in 9 statements/reports (see Annexe 1). Key examples include: / In April, Insecurity Insight data, including data on explosive weapons and attacks on healthcare, was used in the Explosive Weapons Monitor Annual report. / In May, for the third year running. Insecurity Insight global data on violence against healthcare and the damage caused by explosive weapons was cited by the UN Secretary General’s Report on the Protection of Civilians. / In December, Insecurity Insight data on healthcare was used in IRC’s 2025 Emergency Watchlist report.
2. Cumulative number of grants/awards/engagement which has informed or changed the work of the government or UN agency or local community / armed actors or NGO implementing partner on the evaluation/research	3 RIAH (Outcome Indicator 3)	Annual total 3 RIAH (Moderately Met) / Cumulative total of 24 against a cumulative milestone of 14 / RIAH outcome indicator 3 (Number of engagements / consultations with other organisations that have informed or changed the approach to data collection on attacks on healthcare): / The topic of violence against healthcare and its impact is used more frequently to complement the work of other communities in the humanitarian sector. The Explosive Weapons in Populated Areas initiative has begun to integrate data on violence against healthcare among its indicators of harmful explosive weapons use in populated areas. The 2023 Explosive weapons monitor included a special data category, referencing Insecurity Insight, for explosive weapons use affecting healthcare. A project workshop, attended by RIAH’s PI, combined looking at protecting aid workers and health workers from the effects of explosive weapons and used data collected by Insecurity Insight. Watchlist on Children and Armed Conflict has started to use Insecurity Insight’s data related to health services affecting children in their Credible List Report. / RIAH is driving change in future medical and humanitarian professionals’ knowledge and approach to these issues. Master’s courses for these specialties are increasingly requesting course segments to teach about violence against healthcare. Professional training programmes to which RIAH contributed include several undergraduate and master’s courses and a COP 29 Climate Conference side event. The material delivered incorporates sessions on violence against healthcare, data collection, and how to address it. / Insecurity Insight have been collaborating with ASAR in India on their data collection and research into violence against healthcare workers. Since early 2024 RIAH have been advising grassroots organisation NEST in Manipur, India on their data collection practices.
3. Cumulative number of research studies/grants/awards assessed as making a significant contribution to national or international policy debates	37 RIAH (Outcome Indicators 1 and 2) / 2 AHRC (Outcome Indicator 1.1)	No longer tracked – to be replaced, see below

Last year’s annual review included AHRC in the assessment of outcomes. 10 AHRC projects were assessed as having met Outcome Indicator 2. This year, with AHRC completed, JPAL and BCC in their early stages, and only RIAH in its dissemination stage, the project is in a different phase.

Overall, the programme is on track in terms of its outputs (having scored an A in all its ARs to date). In terms of outcome targets, it has met or exceeded 1 and 2 both annually and cumulatively. The impact milestones have also been met, and Impact Indicator 1 (Number of IHL duty-bearers and non-state actor commitments to protect healthcare) saw a significant increase (see Annexe 10 for a list of key UN resolutions and other international commitments on attacks on healthcare in 2024). However, this increase was seen in a year when the number of attacks on health care increased, and early signs are that 2025 will not be very different. The increase in commitments is probably a response to the increase in attacks over the last few years, and so, whilst Impact Indicator 1 may be a measure of changing international norms, it is not a measure of improved humanitarian protection outcomes – at least in the short-term.

This prompts a number of reflections: firstly, that the Theory of Change may need to be adjusted, for example there may be an intermediate step in the logic chain between outcome and impact on normative change that is not captured, and the role data and analysis play in normative change. Secondly, the impact statement is probably too ambitious, the decisions by combatants to attack healthcare is significantly beyond the reach of a research programme such as RIAH, and though in earlier stages, JPAL and BCC will face similar challenges to affecting the behaviour of combatants to promote protection outcomes. Again, a more realistic impact might be, for example, about positively influencing norms – international for RIAH and local/national for BCC – if not actual behaviour by combatants. Thirdly, it is credible, though hard to assess, that the increase in the quality of data and analysis produced by RIAH (and to a lesser extent by AHRC) contributed to the significant rise in UN resolutions in 2024 on attacks on healthcare.
[note] Larissa Fast, Róisín Read, Using Data to Create Change? Interrogating the Role of Data in Ending Attacks on Healthcare, International Studies Review, Volume 24, Issue 3, September 2022, viac026, https://doi.org/10.1093/isr/viac026

Impact Indicator 2 and Outcome Indicator 3 are also not proving to be useful in assessing results. As currently constructed, both are duplicative of Outcome Indicators 1 and 2 and they are not picking up wider, more relevant outcomes, for example, that for RIAH the work on improving the data for attacks on healthcare is currently getting more traction than the work on analysing impacts. (This is most likely due to the growth in the number of attacks, fuelled by the conflicts in Ukraine, Myanmar, and Gaza/OPTs, leading to a demand for more data rather than analysis of impacts). A new outcome indicator focussed on more a more qualitative assessment of outcomes, in particular conceptual outcomes, is needed to complement the more quantitative indicators 1 and 2. This is planned for the next reporting year and RIAH have proposed 2 topics for impact case studies (on the impact of their work on improving data collection and analysis and on capacity-building of local organisations). Further topics for case studies will be agreed during the next year.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

BEPAC should continue as it is producing new and in-demand research and data and is starting to have a wider impact at the outcome level. Humanitarian Protection is one of the 3 pillars of FCDO’s humanitarian framework. The programme is performing satisfactorily with considerable progress made in setting up the fieldwork for BCC and J-PAL during 2024. RIAH’s work has made substantial contributions to the understanding of the growth and impact of attacks on healthcare. This has considerable relevance globally, with 13 United Nations resolutions signed addressing directly the necessity to respect and protect healthcare in armed conflict during 2024.

Update on implementation of each of the recommendations from last year

Recommendation	Update on implementation
AHRC
FCDO to work with some of the AHRC grantees directly and with RIAH to develop impact and uptake case studies to both contribute to the assessment of outcome level achievements and continue to learn about promoting uptake.	Complete RIAH impact case studies have been agreed. It has not been possible to identify an AHRC grantee.
Incorporate the lessons learned from the AHRC component in particular to the Beyond Compliance Component at this early stage as well as improve the delivery of the wider programme	Completed. AHRC lessons on uptake have been reflected in BCC design and implementation, for example the Research Line support to FCDO, and in the consortium composition including a mix of academic and practitioner agencies.
General
FCDO to re-do the log frame to reflect the changes with the RIAH extension, JPAL coming on stream and the new output 5 (Beyond Compliance). This will include new output weighting. (FCDO by end July 2024).	Complete.
Ahead of the next annual review, a separate Value for Money (VfM) assessment is conducted by partners of each project of the wider BEPAC programme, so that a clearer assessment can be demonstrated of how the wider programme is in line with FCDO VfM policy. This needs to include clear criteria, based on the outcome indicators, to measure effectiveness so that there is assurance that the outputs are translated into outcomes that improve humanitarian policy and operations.	In progress: / Partners were given additional guidance and metrics in this reporting year to improve their annual VFM assessments. All three partners have provided more examples and narrative across the four themes. Detail is included in the VFM section below. FCDO should continue to work with partners to ensure that metrics are linked to logframe outputs and documented in greater detail.
Update the risk matrix to include safeguarding risk around sexual exploitation in line with other research programmes. This is relevant particularly the power imbalances between junior/senior researchers and other groups.	Complete. All partners have been receptive to feedback on documenting the risk of safeguarding and ensuring that their mitigation processes and procedures are adequately recorded in their risk registers.

## C. DETAILED OUTPUT SCORING

Output Title	Improved understanding of the type, scale and impact of attacks on healthcare (RIAH)
Output number:		1	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of reports produced including recommendations of impact analysis methodologies (RIAH 2.3)	1	Moderately not met / 0. Delayed, but in progress
1.4 Number of evidence-based synthesis of impact case studies (RIAH 4.4)	1	Moderately not met / 0. Delayed, but in progress

Supporting narrative

Output is moderately not met as the milestones are not fully achieved, but despite delays there has been substantial progress, hence the score of B. Details of this progress as well as rationale for not meeting the milestones are recoded below.

BEPAC indicator 1.1: RIAH previously published an online working version of the Impact Methodologies paper in which they collated work to date analysing existing impact-measuring methodologies and enhancing clarity on the conceptual issues raised when conducting research in this area. Based on research and case studies conducted for this project, RIAH drafted a single report summarising these insights (which would have met the indicator milestone). However, in order to make the findings more accessible for both researchers and practitioners, RIAH decided to reconfigure the report as two outputs, each aimed at the relevant audience. This has delayed publication, but RIAH has now drafted a shorter and more accessible piece and a manuscript for publication in a peer-reviewed journal. The report and the manuscript focus on the need for rigorous methods in conflict analysis, conceptual issues around measuring impacts of attacks on health, and the strengths and limitations of qualitative and quantitative methods in their research. The report is pending internal review, and the draft manuscript will be submitted to journals once approved by the team.

The paper synthesising findings from the case studies on the impact of attacks on healthcare (BEPAC indicator 1.2) has been delayed due to the late Afghanistan case study. However, a draft has been developed, and the paper is expected to be finalised in spring 2025 and submitted to the Global Public Health Journal. Dissemination is planned for 2025, including a chapter on impact data via the 2024 SHCC report. Based on the analysis to date, the key synthesis findings from across the case studies are:

1. Attacks against healthcare are significant and often unreported, in some cases due to a lack of reporting mechanisms, but often because they have become ‘normalised’ as part of operating in conflict contexts. These apparently ‘low-level/low-intensity’ attacks, which are rarely recorded, have impacts that long outlast the event.
2. The impacts of attacks on healthcare are cumulative and compounding, making it vital to think about impact in a holistic way.
3. Attacks on healthcare in violent conflict settings lead to informal transformations in the structure of healthcare delivery and healthcare seeking behaviour. For example, healthcare workers create mobile clinics, provide healthcare clandestinely / under the radar of authorities, and are forced to work outside of their areas of training. Healthcare seekers may change their behaviour, by scheduling c-sections, waiting longer to seek care, or refusing to travel at night to seek care, even in emergencies.

A more comprehensive picture of RIAH progress can be obtained from progress on the outputs from the RIAH-specific log frame. Some key updates are recorded below and under output 4.

In October 2024, RIAH supported the publication of the Security Risk Management for Health Care manual. The manual is a handbook on security risk management tailored specifically for the health sector and available in Arabic, English, French, and Spanish. It provides guidance on how to implement a range of actions intended to face and respond appropriately to violent incidents, also dealing with the aftermath of such events.

RIAH supported the data collection for the 2023 Safeguarding Health in Conflict Coalition (SHCC) report released in May 2024. The report collated data from 2023 to record more than 2,562 incidents of violence against health in 30 countries and territories in conflict, an increase on 2022, and has been widely cited.

Case-study research has concluded, but updates on the case study publications are as follows:

- RIAH’s collaboration with Tribhuvan University continues with a study exploring the relationship between humanitarian organisations and state authorities during conflicts.
- Work continues to build on findings from the Nepalese dataset and work with Jindal Global University to interpret the results for use in other contexts. This includes bi-monthly meetings of the ‘South Asia Research Network’ with academics and practitioners.
- For the case study in Afghanistan, RIAH worked with colleagues at Aga Khan University and the Monitoring & Evaluation / Health Information System unit of the Afghanistan Ministry of Public Health. Two papers based on these data are in progress but are not yet finalised.
- Additional publications are referenced in Output 4 and recorded in Annexe 2.

RIAH was working with International Medical Corps (IMC) US to develop a tool to integrate reporting of attacks into established health information systems to make data collection on attacks more routine. However, the USAID reductions in early 2025 have stopped work with IMC and RIAH are searching for an alternative partner.

RIAH collected 10 testimonies for the RIAH collection of the Humanitarian Archive held at the John Rylands Research Institute and Library at the University of Manchester. The collection contains interviews with individuals from several organisations and institutions including key figures in the development of significant data and advocacy initiatives on attacks on healthcare.

RIAH began work on a paper on the role of states in reinforcing and bolstering international humanitarian norms, specifically related to the protection of healthcare in conflict. The draft findings were presented to FCDO in early 2025. The final version of the report will be published in Spring 2025.

See Annexe 5 for all other RIAH publications.

Any changes to this output during the past year, and any planned changes as a result of this review.

In March 2024, the consortium hosted a workshop in Geneva that brought together around 20 experts in advocacy, protection, data analysis, and academia to translate the findings and methodological innovation of the RIAH research programme to implementable, operational interventions. There was a strong push from participants to be more ambitious in the uptake of the RIAH research, contributing towards a long-term strategic objective to enact change, supportive of the approach established in the theory of change to target different levels of stakeholders with a variety of activities.

RIAH has developed a more ambitious uptake strategy. Efforts for the extension will be focused on the socialisation and dissemination of the research produced in the initial years of the project. The revised strategy will also aim to strengthen normative change, via direct and ongoing engagement with a ‘community of concern’, and operational change by investigating tools to integrate reporting on attacks on healthcare into established health information systems; developing rapid assessment methodology; training staff on operational security to minimise the risks from attacks on healthcare. Changes have been made to the logframe to reflect this.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Section A.

Output Title	Improved evidence on the impact of protection interventions (JPAL)
Output number:		2	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
2.1 Cumulative number of grants awarded for high-quality, policy-relevant research proposals that address HPI priority questions (JPAL 1.1)	RCTs: 2 / Pilots: 2	Moderately not met. / 1 / 2
2.2 Number of HPI-funded projects that include at least one academic from traditionally underrepresented groups as co-PI, namely: / i) co-PIs who are from or based in an LMIC as measured by current university affiliation or having a high-school and/or undergraduate alma mater in an LMIC; / ii) co-PI who identifies as female, non-binary, or agender (JPAL 3.2)	i) 5 / ii) 5	Moderately exceeded. / i) 8 / ii) 7
2.3 Cumulative number of HPI Scholar teams who: / i) are paired with a mentor (current J-PAL affiliate or invited researcher) and / ii) complete the mentorship accompanying the implementation of their award. / iii) become Invited Researcher as a result of HPI (JPAL 3.1)	i) 2 / ii) 0 / iii) 0	Moderately not met. / i) 1 / ii) 0 / iii) 2

Supporting narrative

This output scored a B primarily due to the cancellation of one of the RCTs after the reporting period. Looking across the reporting year, despite a slow start due to a recruitment delay in JPAL, the team at HPI have worked quickly and efficiently to ensure the project timelines get back on track.

- HPI developed the Request for Proposals (RFP) document, published a blog post highlighting the launch, and opened two rounds of the competitive research fund in February and October. A third will be launched in early 2025.
- HPI’s Review Board in Round 1 elected to fund two full RCTs (BEPAC indicator 2.1) in the Central African Republic and Bangladesh.
- The Bangladesh RCT was subsequently cancelled due to J-PAL permanently disaffiliating the PI due to misconduct; no contract was signed, and no funds were committed.
- Two pilot studies in Burkina Faso were also funded. The total amount funded for these four studies was £567,808. Five travel and proposal development grants were funded for projects in Ethiopia, Burkina Faso, Nigeria, Egypt, and Brazil, totalling £37,979. See Annexe 7 for further details.
- In HPI’s first RFP, J-PAL received 36 expressions of interest (EOI): 17 pilot studies, 10 full RCTs, and 9 proposal development applications from 17 countries. HPI Round 2 received 32 EOIs, including seven full RCTs, 14 pilot studies, and 11 project development grants from 17 countries. HPI staff offered pre-proposal calls to six scholars in December 2024.
- The HPI Scholars Program was launched alongside the first RFP to create more opportunities for researchers based in or from low- or middle-income countries (LMIC). Scholars are provided with pre-proposal feedback support and, after funding, they receive mentorship from senior researchers in the network with extensive experience running rigorous impact evaluations. HPI staff offered pre-proposal calls to six scholars in December 2024.
- J-PAL led a condensed Evaluating Social Programmes training with a focus on humanitarian protection, which was attended by 79 humanitarian professionals from 40 different organisations. Training presented the challenges of implementing rigorous impact evaluations specific to humanitarian settings. J-PAL further developed this training into an abbreviated workshop, in partnership with WFP, UNICEF, and Uplift Afghanistan Fund at the United Nations Impact Evaluation Forum in December 2024.
- The HPI team led a series of Humanitarian Action Research Incubators, designed to support organisations working to enhance protection outcomes in conflict settings and promote sustainable livelihoods for forcibly displaced persons and host communities. The goal of these incubators is to develop projects and funding opportunities for HPI in tandem with the Displaced Livelihoods Initiative. The first incubator of the year took place in Bogotá, the second incubator was held on in Cairo, and the final incubator of the year took place in Nairobi.

In RFP1, every research team included at least one researcher based in or from an LMIC and/or a researcher who identifies as a woman (BEPAC indicator 2.2). Among all HPI-funded projects (both pilots and RCTs), all three projects have members who are based in or from an LMIC (Central African Republic and Burkina Faso) and include a woman co-PI. Additionally, among the five awarded project development grants, each includes a co-PI based in or from an LMIC (Burkina Faso, Brazil, Nigeria, Egypt, and Ethiopia), and four also have a woman co-PI. Overall, research projects involving an LMIC researcher make up 100% of the funded projects.

To maximise participation in the HPI Scholars programme, HPI collaborated on an extensive outreach effort, leveraging existing research networks and establishing new connections to promote the opportunity (BEPAC indicator 2.3). A total of 14 scholars submitted an expression of interest (EOI) to Round 1. For Round I, funding was awarded to two scholar research teams, and two other researchers whose projects were funded became J-PAL Invited Researchers.

See Annexe 6 for all HPI publications.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

HPI have requested an extension to the project as a result of delays in its first year (discussed in Risk section) to ensure that all work and planned RCTs can be completed and results disseminated. FCDO will assess this light of recent announcements about ODA.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Section A.

Output Title	Research findings are accessibly communicated and synthesised and promoted to target audiences
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of public engagements (e.g. conferences, workshops, forums) to promote research or policy findings (RIAH 5.5, JPAL 2.3, BCC 3.2 & 4.3)	8 RIAH / 20 J-PAL / 3 BCC (BCC 4.3)	Substantially exceeded. / 9 RIAH / 74 J-PAL / 11 BCC (1 in BCC 3.2 & 10 in BCC 4.3)
4.2 No. and type of research outputs available on project websites (RIAH 5.8, AHRC 4.4, JPAL 2.2)	2 RIAH	Substantially exceeded. / 5 RIAH
4.3 Number of policy-relevant materials available on websites (RIAH 5.9, AHRC 4.5, JPAL 2.2, BCC 1.2)	5 RIAH / 2 J-PAL / 20 BCC	Moderately exceeded. / 6 RIAH / 3 J-PAL / 21 BCC
4.4 Total number of (externally) peer-reviewed publications (RIAH 5.10, AHRC 1.2, JPAL 1.2, BCC 1.1)	1 RIAH / 2 BCC	Met. / 4 RIAH / 0 BCC (In progress) / 4 AHRC

Supporting narrative

Overall this output is met, with some areas exceeding. This output was designed to track collective BEPAC research communication and does not overlap with indicators in individual project outputs. BEPAC is on track to ensure findings from each component project are disseminated and promoted to target audiences.

4.1 Number of public engagements to promote research or policy findings

RIAH highlights include (see Annexe 2 for full list):

Panellist at protection of civilians week side event: Permanent Mission of Poland to the UN, Health care under attack – the imperative of ending the violence.
Panellist at ICRC Delegation Nairobi. IRC/ICRC/MSF Protection of Healthcare event at ICRC.
Presented at a briefing for the EU Working group on IHL on violence against health care and food security in conflict.
Humanitarian congress Berlin Moderation of Medical care under fire session.

J-PAL highlights include:
In 2024, HPI staff participated in 74 engagements with policymakers and practitioners to motivate evidence generation and evidence use. These included 3 evidence dissemination events focused on summarising protection-related research, 5 conferences aimed at building connections for future project development, and 66 meetings dedicated to advancing HPI project and partnership development.

The evidence dissemination events focused on summarising protection-related research:
- In March and November 2024, a presentation of existing evidence related to humanitarian protection was shared with all organisations joining the Training on Randomised Impact Evaluations for Humanitarian Professionals (March 2024), and the Humanitarian Action Research Incubator (November 2024).
- In November 2024, in collaboration with ICRC's Centre for Operational Research and Experience (CORE) and the Evaluation Office, J-PAL organised a joint learning event to continue the discussion on the role of RCTs in measuring the impact of protection interventions for people affected by conflict.

Several meetings aimed to advance project and partnership development with the goal of motivating partners to generate evidence through the competitive funding rounds. These included meetings with the ICRC, Save the Children, the Uplift Afghanistan Fund, UNHCR Protection teams, the Centre for Humanitarian Dialogue, Private Secretary of the president, MSF Evaluation Office, Catholic Relief Services, and War Child.

BCC highlights include (see Annexe 2 for full list):

- Meeting with World Food Programme re food insecurity database (June 2024)
- Expert participation in Wilton Park dialogue “Conflict trauma and youth” (July 2024)
- BCC participation at Geneva Peace Week (Oct. 2024)
- Meeting with Staff at the Civilian Protection Center of Excellence, Department of the Army, Deputy Chief of Staff, United States to discuss the BCC’s work (Nov. 2024)

4.2 No. and type of research outputs available on project websites

RIAH:
- Intimacy and the gendering of war healthcare: women’s experiences of insurgency war in Nepal (1996–2006)
- Impacts of attacks to female health care workers in three territories of Colombia
- “It's normal to be afraid”: attacks on healthcare in Ouaka, Haute-Kotto, and Vakaga prefectures of the Central African Republic, 2016–2020
- “I will take part in the revolution with our people”: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat
- The Impact of Violence Against Health Care on the Health of Children and Mothers: A Case Study in Three Health Zones in Eastern DRC

4.3 Number of policy-relevant materials available on websites

RIAH:
          1. Security Risk Management for Health Manual (published in EN, FR, AR, ES). In October 2024 RIAH supported the publication of the Security Risk Management for Health Care manual. The manual is a handbook on security risk management tailored specifically for the health sector. It provides guidance on how to implement a range of actions intended to face and respond appropriately to violent incidents, also dealing with the aftermath of such events.
          2. SHCC 2023 report: RIAH Supported the data collection for the 2023 Safeguarding Health in Conflict Coalition (SHCC) report released in May 2024. The report collated data from 2023 to record more than 2,562 incidents of violence against health in 30 countries and territories in conflict.
          3. Attacks on Health Care in Israel and the occupied Palestinian territories March 2024.
          4. Insecurity Insight continued to produce 25 of the global bi-monthly news briefs and some special reports (on Myanmar, Lebanon, and New Caledonia).

J-PAL:
- The Request for Proposal document and summarising blog.
- Blog: In conversation with Norwegian Church Aid: Understanding the catalyzing effect of J-PAL humanitarian trainings. The blog shares the experience of the Norwegian Church Aid (NCA) Somalia and the Center for Research and Integrated Development (CeRID) when participating in the Humanitarian Action Research Incubator.
BCC:
21 blog articles – See Annexe 8.

4.4 Total number of (externally) peer-reviewed publications (for all publications see Annexe 4)

RIAH:
- Intimacy and the gendering of war healthcare: women’s experiences of insurgency war in Nepal (1996–2006)
- Impacts of attacks to female health care workers in three territories of Colombia
- “It's normal to be afraid”: attacks on healthcare in Ouaka, Haute-Kotto, and Vakaga prefectures of the Central African Republic, 2016–2020
- “I will take part in the revolution with our people”: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat

Other achievements during the reporting period

Additional highlights from RIAH include:

- During 2024 RIAH had 1,400 users from 87 different countries across all continents accessing the project website.
- By the end of 2024 the Systematic Review, published in Conflict and Health in May 2021, has been accessed 22,000 times and appears in 157 Mendeley libraries. Using Data to Create Change (published in May 2022) paper has been accessed 1,900 times and Underestimating Attacks (published Feb 2023) 3,700 times.
RIAH media achievements:
- Over 42,000 downloads of the SHCC report.
- Over 51,000 views of the Insecurity Insight monthly news briefs and technical articles.
Over 43,000 downloads from Humanitarian Data Exchange of the thematic pages on violence against healthcare.
Additional highlights during the BCC reporting period include:
- Engagements include the BCC Public Launch – Roundtable “Addressing Need and Harm in War: From Non-Compliance to Beyond Compliance” (May 2024), BCC panel organisation & discussion at ABILA International Law Weekend (Oct. 2024), and a presentation at Annual International Humanitarian Law Half Day Seminar at Te Herenga Waka-Victoria University of Wellington (Nov. 2024).
- Developed new collaborations with local partner organisations in case study countries, concluded a new partnership agreement with DEval, and welcomed their first affiliated researcher whose PhD project focuses on IHL compliance.
BCC media achievements:
- 800 total downloads of the 7 podcast episodes published with more than 50 downloads per episode.
- Website launched in Sept. 2024. From launch: 2,456 active users (2.33 page views per active user, 36s engagement time per active user, 315 clicks to external links).
- Newsletter: 108 subscribers (avg. 57% open rate and 65% click rate).
- LinkedIn: 742 followers.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Section A.

Output Title	Improved evidence on the drivers for restraint and compliance with IHL by armed actors (Beyond Compliance)
Output number:		5	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of written submissions and oral briefings requested by the FCDO and provided to the FCDO through the FCDO Research Line (BCC 2.1)	0	Substantially exceeded. 2 / Written submission delivered (June 2024 Gaza / OPT brief / Written submissions delivered (Dec 2024) NW Syria cross border issues.
5.3 Percentage of outputs 1.1 and 1.2 (BEPAC outputs 4.3 and 4.4) co/authored by women (BCC 1.6)	50%	Substantially exceeded. / 100% of draft academic outputs are co/authored by women / 52% of blog articles are co/authored by women.
5.4 Percentage of outputs 1.1 and 1.2 (BEPAC outputs 4.3 and 4.4) co/authored by Global South researchers. (NB Global South researchers are defined as those from ODA recipient countries. These include all the 9 case study countries of the BCC programme) (BCC 1.7)	40%	Partially met. 37% average / 50% of draft academic articles are co-authored by Global South researchers / 24% of blog articles are co/authored by Global South researchers / NB: Recruitment of local researchers in some case study countries was delayed.

Supporting narrative

This output has scored an A+ reflecting good progress in its first year. Alongside the milestones above, the consortium is in good shape, a conceptual framework has been developed, a podcast series has been produced, and preparations for field research have gone well.

For BEPAC indicator 5.1, the BCC “Research Line” will provide real-time, on demand analysis to the FCDO, on policy options to assist their efforts to encourage IHL and IHRL compliance and restraint from violence and abuse. The Research Line will also function as an early-harvesting mechanism of research findings from the BCC research programme and a feedback mechanism into the substantive research. This year it was started with three of the BCC case study countries: Syria (Northwest and Northeast), South Sudan, and Myanmar, chosen to pilot the service for 6 months. Activities supporting the pilot phase included:

- The development of a Research Line Process Manual, determining internal processes within the Consortium, chains of responsibilities, and consent procedures.
- Weekly meetings of the Research Line to discuss ongoing assignments.
- Regular engagement with FCDO on the progress of the work package.
- Four introductory discussion sessions with FCDO country teams in Myanmar, South Sudan, Northwest Syria, and Northeast Syria.
- Two written submissions have been prepared in response to requests received (BEPAC indicator 5.1).

Other activities and outputs important for getting the wider work of the consortium started have included:
- The dissemination of the key BCC concepts through the Beyond Compliance Blog Symposium. To date, more than half of the blogs have been co-authored by women, with several blog articles having more than one woman author (BEPAC indicator 5.3).
- The Beyond Compliance: In Conversation podcast series discusses the key questions related to the BCC research programme with leading academics, researchers, and practitioners.
- Ongoing communication between BCC member organisations, local partners, and researchers (BEPAC indicator 5.4),
9 country literature reviews developed by members of the consortium that map conflict dynamics, armed and non-armed actors, and harm and need in case study contexts. They will be used to prepare fieldwork materials, including interview guides, and will serve as the basis for future blog articles, policy papers, and chapters in an edited volume.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Section A.

## D: VALUE FOR MONEY

Key cost drivers and performance

Key cost drivers from the Business Case remain valid and currently are the cost of research personnel to deliver high quality impact evaluations and case studies (70-80% of overall costs). The cost of research uptake (outreach activities), capital expenditure, management costs, the costs of providing operational support to programme teams, and monitoring costs make up the remaining key cost drivers.

VfM performance compared to the original VfM proposition in the business case

Economy

- RIAH received a grant from the Brocher Foundation, enabling them to engage project collaborators through a workshop and refine in detail the proposed next steps for the final year of the project. This will improve dissemination planning and execution during the extension process without requiring extra funds from the FCDO. Insecurity Insight has received complementary funding (e.g., from USAID, ECHO) which helps maintain and improve the data systems while reducing RIAH’s direct costs. All stakeholders who attended the workshops RIAH hosted in 2024 gave their time without cost to the project. These included experts from stakeholder institutions such as the IRC, MSF, SAMS, PHR, and Airwars.
- RIAH aims to leverage established platforms (like DHIS2 for reporting or DisasterReady for training) rather than building bespoke systems from scratch. This offers cost savings by avoiding duplication of tools and infrastructure and will help facilitate impact reporting and mitigation measures beyond the life of the project.
- J-PAL establish funding caps for different proposal types, for instance travel and pilot grants are capped at US$10,000 and US$75,000 respectively. This ensures HPI can economise FCDO funds and obtain research results for reasonable cost. J-PAL and IPA have an established local presence in over 30 countries, including FCDO priority countries, employing policy staff with deep knowledge of local contexts. This enables HPI to benefit from economies of scale with respect to the cost of implementing field research. Similarly, HPI benefits from the research infrastructure and resources J-PAL and IPA have built in many countries.
- BCC uses the same country case studies for qualitative and quantitative data collection, the Research Line, dissemination, and uptake, which ensures that the same teams will be involved in most aspects of the research. This keeps staffing, management, travel, and fieldwork costs to a minimum, and draws on established relationships and networks, which is more cost effective. BCC has leveraged savings through an in-kind contribution of staff time from DEval.
- Wherever possible, BCC opts for online meetings with internal and external stakeholders to save costs. BCC has identified that the number of online attendees at public events has exceeded that of in-person attendees and as such are exploring this as a cost-saving measure for future.

Efficiency

- RIAH’s research protocols used for the qualitative case studies have proven adaptable to different conflict contexts. All the papers are Open Access and RIAH have published research protocols on their website. The publication of the methods paper will ensure that the most important elements of methodological innovation are captured for policy and academic audiences to ensure research can be replicated and scaled in future projects or new contexts.
- J-PAL: by building on best practices from similar initiatives such as GCCI, HPI funds projects that build upon and complement each other. As the prime grantee, J-PAL implements HPI in accordance with financial regulations which draw from MIT’s financial procedures. These are built specifically to efficiently manage large-scale research efforts while providing reasonable oversight and control.
- By benefiting from the knowledge of country-based, established staff, BCC has ensured an efficient and smooth delivery of research as the project scales. BCC seeks to ensure efficiency through complementarity of skills and expertise across the work package. For instance, BCC sought to maximise the benefit achieved from the resources invested in the Research Line outputs by drawing on these in the International Development Committee submission. Similarly, the country literature reviews prepared by country research teams serve the dual purpose of structuring fieldwork plans/interview guides and serve as the basis for future publications.

Effectiveness

- RIAH’s outputs allow for more informed data collection and analysis of what works in the protection space, as well as development of new methodologies to inform key health, protection, and diplomatic actors’ decision-making and policy. Uptake of the data collection and analysis methodologies has and will continue to contribute to generating more robust evidence to support advocacy for policy change and future funding for resilient health programming in conflict contexts.
- In this reporting period RIAH saw the highest annual increase (82) in academic and policy citations, showing the growing visibility of the project. The number of engagements with organisations which have informed / altered their approach to data collection on attacks has risen by 3 in 2024, demonstrating RIAH’s commitment to raising the profile of attacks. Insecurity Insight news briefs reached an audience this year of 51,000, and references in online news media can be found in Annexe 3.
- HPI funding is directed towards key priorities for policy relevant research. Proposals are evaluated against standardised criteria, ensuring an effective process that holds all submissions to the same high standards. As part of the review process, proposals receive comments and feedback from top academic and policy experts in this thematic focus, helping to further develop the field and improve the quality of proposals. J-PAL and IPA are well positioned to engage in effective, results-oriented policy outreach given their longstanding, trusted partnerships with many governments and multilateral organisations including ICRC, Save the Children, MSF, and UNHCR. 90 organisations working in the humanitarian space attended capacity building activities organised as part of the HPI.
- Output indicators for delivery, for example the Blog Symposium, Podcast Series, and public events demonstrate good uptake in activities so far. The podcast series has gained public traction with 800 total downloads of the 7 episodes published.
- The BCC Research Line is taking longer than anticipated to build trust and an understanding of the offer to the FCDO country teams. This is learning for the Humanitarian Research Team and the BCC team, and an early survey provided has deemed the analysis submitted by the BCC as ‘very useful’.
- All three projects benefit from academic oversight as well as benefitting from in-country global networks which facilitate Southern partner engagement. The programme involves collaboration between academics and key humanitarian actors in the NGO and multilateral space, advancing conceptual and instrumental impact in humanitarian protection.

Equity

- RIAH’s activities are led by or include contributions from colleagues at organisations in LMICs in countries such as Nepal, Afghanistan, CAR, DRC, and India. There are seven named researchers in the project, three of which are women (including the PI). 100% of publications include female authors.
- The inclusion of gender as a cross-cutting theme in HPI original design has continued to promote equity in research. In 2024, 7 co-PIs from HPI-funded project identified as female, non-binary, or agender, exceeding the milestone of 5. Deliberate efforts to contract and support Southern researchers increases HPI focus on equity as does J-PAL’s efforts to support a new generation of emerging scholars. In 2024, 8 co-PIs from HPI-funded projects were based in an LMIC. These grants have increased the diversity and inclusion of researchers attending leading economics conferences by extending accessibility to scholars from low- and middle-income countries studying governance topics. In 2024 one HPI scholar research team was paired with an HPI mentor, and two other researchers became J-PAL invited researchers.
- The BCC programme has a commitment to gender equity. This is evidenced by the makeup of the leadership team, which is 75% women – with a woman principal investigator. In 2024 100% of draft academic outputs were coauthored by women and 52% of blog articles. Additionally, 50% of draft academic articles were coauthored by Global South researchers. The BCC is actively working with colleagues across different career levels and with research partners from indigenous and minoritised communities, with a focus on increasing research capacity. This includes support through mentoring, coaching, training sessions, and networking opportunities to four early career researchers and two local researchers from indigenous/minoritised communities in Colombia and Myanmar.

Assessment of whether the programme continues to represent value for money

Across the outputs and outcomes, our partners have met and regularly exceeded expectations for value for money. As the JPAL and BCC projects reach scale, FCDO expects to see additional valuable insight into humanitarian protection research from partners. It is not appropriate to measure outcome-level changes for the BCC and J-PAL programmes in this AR considering they are still in their early stages and field work is still being set up. RIAH’s work has made substantial contributions to the understanding of the growth and impact on attacks on healthcare. We have seen this particularly through their work with Insecurity Insight which has had data quoted in high profile publications including the Explosive Weapons Monitor Annual report, 3 years running in the UN Secretary General’s Report on the Protection of Civilians, and the IRC’s 2025 Emergency Watchlist report. RIAH’s work into the instance and impact of attacks on healthcare has considerable relevance globally, with 13 United Nations resolutions signed addressing directly the necessity to respect and protect healthcare in armed conflict during 2024. We will continue to encourage collaboration across all three partners and provide advice on the refinement of VFM metrics.

E: RISK

Overview of risk management

The risk appetite for the programme is Cautious. In the last reporting period, the overarching post-mitigation risk for the programme remains at a Moderate level.

Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	People	Financial & Fiduciary	Safeguarding	Reputational	Overall
Moderate	Moderate	Minor	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context

The primary future risk to programme delivery centres around the recent announcement to reduce ODA to 0.3% of GNI.

The fragile and volatile contexts in which much of our partners’ work takes place present logistical and potentially ethical challenges for conducting research. Fielding research teams in these contexts is often costly; constantly shifting states of political and social stability require high levels of flexibility, and randomly assigning interventions to segments of the population is not always politically feasible. Our partners use contingency planning such as focussing on desk-based research or conducting interviews remotely or in neighbouring countries. Partners are regularly in touch with FCDO to inform and consult on developing situations and planning, often informed by on-the-ground local expertise. When data collection is not possible at certain times, partners’ efforts can be redirected to activities such as analysis and dissemination. BCC has a budget for unforeseen emergency expenses that takes into account the nature and context of the field research. IPA has implemented an “Outside of Country Office” policy to assess potential engagements by level of risk, strategic value, and operational feasibility.

Policy and Programme Delivery

The closure of USAID poses a risk to partners across the humanitarian sector in receipt of USAID funding and relying on data collection funded by USAID. FCDO is liaising with RIAH on Insecurity Insights news briefs.

People

RIAH’s Afghanistan case study (and its wider synthesis) has been delayed; this was initially flagged to FCDO in June 2023. RIAH have proceeded with a draft of the synthesis paper and continue to work with the researcher to ensure the results of the study are published and included in the synthesis. By mid-2025 RIAH plan to submit the synthesis paper regardless of whether the Afghanistan papers are complete.

The HPI team have demonstrated a strong ability to quickly adapt to changes in staffing as various team members have departed and new team members have been brought onboard. J-PAL and IPA intentionally hire a mix of staff who are both sector experts as well as policy generalists so that, as staffing changes occur, it is relatively easy to transfer staff between teams if needed to supplement team capacity as new staff are brought onboard.

There is risk of staff turnover within the large BCC consortium due to the number of actors involved – this has been met with drawing on expertise from other members of the consortium and the associated organisations. There have been examples of departing staff being contracted to the project as consultants including in-kind contributions from new employers.

Financial & Fiduciary

J-PAL mitigates fund diversion risk by funding project teams on a cost-reimbursable basis. The postponement to the grant signature has had a cascading effect on J-PAL’s research sub-awards line, which represents the bulk of the grant’s underspend. FCDO will assess whether this project should be extended by one year to ensure that work is completed as planned despite initial delays.

Over the course of this reporting period, the main financial risks to BEPAC have been related to under/overspend by partners. This has been mitigated through ongoing monitoring and communication with FCDO and partners as well as a policy that allows partners to vire between budget lines.

The annual allocations for BCC were altered during the reporting period in an Accountable Grant amendment to account for delays in the commencement of the project.

All programme partners host regular meetings with funders and consortium members / partners to establish whether resources and spending are on track with research objectives. Mitigation processes include extensive due diligence before funds are committed, regular performance and financial reporting, and payment milestones which enable timely corrective action.

Safeguarding

The primary safeguarding risk for the programme is the safety of the researchers as they conduct the research for the different projects that make up BEPAC. BCC engages with state and non-state armed actors, but the wellbeing of their researchers is paramount. There is a risk of sexual exploitation, abuse and harassment (SEAH) in academia and research, due primarily to the inherent power imbalance between parties. To mitigate this, all partners have strong policies and robust reporting procedures to escalate potential risks of this nature to the first-tier partner, as well as escalated to FCDO Reporting Concerns so that suitable action can be taken immediately.

BCC is mitigating against the risk of SEAH by ensuring that all partners adhere to the IASC Minimum Operating Standards on PSEA and/or the Core Humanitarian Standard on Quality and Accountability. Further mitigation has been achieved through applied ethics trainings with researchers. At J-PAL, MIT have guidelines on vetting partnerships based on ethical concerns. These steps help ensure that J-PAL is not inadvertently working with or funding countries or partners that may be engaged in systematic human rights violations. Applicants are part of universities that require research to undergo internal ethical review boards before it goes forward. All staff are required to undergo a training on working with human subjects. RIAH conduct research with the appropriate ethical clearance led by the UoM University Research Ethics Committees (URECs). The Code of Practice for Investigating Concerns outlines the process followed if allegations of research misconduct are received.

In light of the fact that this is a research programme, environment impact will be kept to a minimum, especially with partners having such a strong international on-the-ground local presence which mitigates the need for excessive air travel.

Reputational

Given the nature of BEPAC’s humanitarian work, there are risks surrounding research ethics. To mitigate, applicants need to prove that their project can be delivered to the highest ethical standards. The initiative’s scope and focus on humanitarian settings necessitates a heightened investment in ethical research design and implementation as well as robust due diligence procedures.

J-PAL and IPA share proposals with FCDO country offices, enabling them to flag any concerns before they are reviewed by Review Boards. Review Boards take into consideration potential ethical and reputational risks of conducting research, which they factor into their award decisions.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance across the programme partners has remained to a high standard over the course of this reporting period. All partners on the BEPAC programme engage with FCDO on a regular basis and have been attentive to requests for additional information. Effective negotiations have meant that sound agreements are in place for all components of the project, and through regular engagement with partners we ensure bookkeeping is open and transparent.

All three partners engage with an annual external audit, the results of which are reported to the FCDO. RIAH provided their audit report signed off in January 2025 reporting no instance of material misstatement and JPAL provided their report signed off in October 2024 stating the same. BCC’s report will not be due until September 2025.

During this reporting year, accountable grant amendments were submitted for both RIAH and BCC. For RIAH, this involved an increase in budget of £0.5m in February 2024 and an extension of £0.25m for additional dissemination and uptake activities at the end of 2024. For the BCC, this involved a shift in annual allocations to reflect and account for the delays in the project commencement which contributed to significant underspend. Delays were due to necessary inter-consortium discussions, which led to less money being spent during the first quarter than forecast. This underspend is reflected in the table below and has been absorbed by the shift in allocations.

Delays in the signing of the accountable grant in 2023 for HPI with JPAL, plus a gap in staffing at JPAL, caused delays to fiscal expenditure for the reporting period for HPI, resulting in an underspend for the programme overall. The underspend for J-PAL will be more difficult to manage with the existing financial controls in place across the spending review and the ODA reduction.

Programme delivery team is still missing a PRO, this is a vacant position within the FCDO team. The role of PRO is being currently covered by the SRO and DPM.

Financial Performance

		Q4	Q1	Q2	Q3
Partner		Jan-Mar 24	Apr- June 24	July- Sept 24	Oct- Dec 24	Total
RIAH	Forecast	£184,694.24	£54,270.69	£66,785.21	£90,712.63	£396,462.77
	Actual (£)	£195,308.60	£42,637.79	£39,098.46	£87,598.10	£364,642.95
	Variance	-6%	21%	41%	3%	8%
JPAL	Forecast	£409,685.00	£129,705.60	£119,819.41	£133,079.48	£792,289.49
	Actual (£)	£298,585.16	£115,205.32	£159,823.79	£132,688.00	£706,302.27
	Variance	27%	11%	-33%	0%	11%
BCC	Forecast	£217,129.86	£278,229.18	£305,568.11	£422,378.56	£1,223,305.71
	Actual (£)	£50,165.03	£190,312.29	£285,184.38	£316,196.92	£841,858.62
	Variance	77%*	32%	7%	25%	31%

Please note: Variations for JPAL and BCC are based on FCDO’s expenditure predictions made at the start of this reporting period, and do not represent recent/updated forecasts of expenditure given by partners.

* See paragraph above regarding the accountable grant amendment as an explanation for this considerable variance caused by delays to the start of the project.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

This Annual Review was written by the Humanitarian Research DPM and SRO drawing upon information provided by the partners of the programme. FCDO has discussed this review with key partners during Q3 meetings, who have been obliging in answering our queries and providing additional information. Partners provided references to outputs where appropriate enabling these to be checked and tallied within the report.

Programmes apply a robust monitoring approach to monitor the performance and effectiveness of grants. FCDO and partners have been in frequent contact over the course of the reporting period, both for exchanges on the research and to discuss progress on deliverables, finances, and risks. Quarterly meetings are scheduled to discuss the projects and their progress. Each partner’s performance is tracked through a logframe, these are then combined into the wider programme level logistical framework to gauge overall performance.

Financial reports are submitted regularly, monitored against the agreed budget and checked to ensure that costs are realistic and represent value for money. All partners have received additional guidance in this reporting period to improve their value for money metrics, the related assessments are captured in Section D.

Evidence and Learning

The learning driver of the programme is to increase the understanding, knowledge of, and evidence base around protection. This is achieved primarily through the key areas captured in the logframe such as producing learning materials, making academic outputs widely available, and holding public engagements. In accordance with the ToC, as long as the assumptions hold, these learning products will go on to improve humanitarian protection policy and operations through better evidence.

RIAH continues to contribute to the evidence base on attacks on healthcare by capturing more fully the nature, frequency, and scale of attacks in conflict and to improve the methodologies employed to measure the impact of the problem. Where possible and where suitable, disaggregate information by protected characteristics is captured and utilised to strengthen the outputs of the programme, which means the BEPAC programme is actively supporting the ‘leave no one behind’ agenda.

During the reporting period J-PAL organised three evidence dissemination events focused on summarising protection-related research and five conferences aimed at building connections for future project development. These included Training on Randomised Impact Evaluations for Humanitarian Professionals (March 2024), the Humanitarian Action Research Incubator (November 2024), and a joint learning event with ICRC on the role of RCTs on protection interventions in November 2024.

BCC has gained traction with their blog symposium and podcast series which are accessible ways for people to access information on the protection space and understanding of IHL. The pilot of the Research Line has gone ahead in Myanmar, South Sudan, and Syria. Positive feedback from the FCDO has been received for the insights provided through oral and written briefings. Due to the pilot’s success the Research Line will be rolled out to additional case study contexts during 2025. The BCC facilitated learning and exchange between member organisations and local partners and set up internal learning processes via feedback forms.

Date of last narrative financial report	RIAH: February 2025 / J-PAL: February 2025 / BCC: February 2025	Date of last audited annual statement	RIAH: January 2025 / J-PAL: October 2024

Annexe 1 – Outcome Indicator 1 RIAH

64 Scientific journal citations (RIAH Outcome Indicator 1):
- Violence against healthcare in conflict: a systematic review of the literature and agenda for future research was cited 37 times.
- Underestimating attacks: comparing two sources of publicly-available data about attacks on health care in 2017 was cited 6 times.
- “There is a fear that you will be attacked just for the act of working in health”: a survey of experiences of violence against healthcare in Colombia was cited 6 times.
- Caring Under Fire Across Three Continents: The Hadfield-Spears Ambulance, 1941–1945 was cited 4 times.
- Impacts of attacks to female health care workers in three territories of Colombia was cited twice.
- “I will take part in the revolution with our people”: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat cited once.
- Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late was cited 8 times.
(Citation information is not consistently available, so RIAH are unable to add this information for articles published in the journal Humanity)

9 policy publication citations:
- In March, Insecurity Insight data fed into the following report published in the Lancet: 3 years after the Myanmar military coup—the people are suffering.
- The Safeguarding Health in Conflict Coalition (SHCC) report and data that RIAH funds via Insecurity Insight, was used in the following publications:
- Assessing the Impact of Russia’s Invasion of Ukraine on Health Services
- “Khartoum is not Safe for Women!” Sexual Violence against Women and Girls in Sudan’s Capital
- Worldwide Trends in COVID-19-Related Attacks Against Healthcare: A Review of the Safeguarding Health in Conflict Coalition Database
- Addressing transnational exploitation and armed conflict in the response to mpox
- Mobilising the health community to protect health care from attack
- A Spatial Analysis of the Israeli Military’s Conduct in
  Gaza since October 2023
In September RIAH was cited in the following opinion piece: Opinion – How Global Politics Exploits Women’s Health.
In November various publications produced by RIAH were cited in this report by the European Sting: Safeguarding the healers: protecting healthcare workers in armed conflicts.

Project outputs were referenced in 9 statements/reports (RIAH Outcome Indicator 2):
    1. In January, the Safeguarding Health in Conflict data were referenced in the Global Protection Forum.
    2. In April, Insecurity Insight data, including data on explosive weapons and attacks on healthcare, was used in the Explosive Weapons Monitor Annual report.
    3. In April, Insecurity Insight data on healthcare were used in Watchlist’s “A Credible List” Report that includes Recommendations for the Secretary-General’s 2024 Annual Report on Children and Armed Conflict.
    4. In May, Insecurity Insight global data on violence against healthcare and the damage caused by explosive weapons was cited by the UN Secretary General’s Report on the Protection of Civilians.
    5. In June, Insecurity Insight was used in the data for the UK Health Partnership for Myanmar’s annual report.
    6. In August, the Special Inspector General for Afghanistan Reconstruction issued a report July 2024 Quarterly Report to the United States Congress (SIGAR 2024-QR-3) that cited Insecurity Insight data.
    7. Insecurity Insight data on Myanmar is used in the Myanmar 2025 Humanitarian Needs and Response Plan prepared by UN OCHA.
    8. The WHO Health Cluster Coordinator for Myanmar confirmed that they are “following Insecurity Insight's reports on Myanmar closely and am highly dependent on the data your reports are providing.”
    9. In December, Insecurity Insight data on healthcare was used in IRC’s 2025 Emergency Watchlist report.
Grand total: 82

Annexe 2 – Output Indicator 4.1

RIAH:
- Interviewed for «Normalerweise gibt es Sicherheitsgarantien in Krisengebieten».
- The organisation of and contribution to a panel at HNPW 2024: Ensuring access to health care through community support and better security risk management for hospitals in the DRC.
- Participation in a Webinar: Casualty Recording and Healthcare in Sudan.
- Panellist at protection of civilians week side event: Permanent Mission of Poland to the UN, Health care under attack – the imperative of ending the violence.
- Panellist at ICRC Delegation Nairobi. IRC/ICRC/MSF Protection of Healthcare event at ICRC.
- Presented at a briefing for the EU Working group on IHL on violence against health care and food security in conflict.
- Presentation on attacks on healthcare in Myanmar at a THET learning event.
- Humanitarian congress Berlin Moderation of Medical care under fire session.
- Johns Hopkins Dean’s Lecture: Addressing the Catastrophe of Violence Against Health Care in War.

BCC:
- 1 x BCC Colombia Workshop in Bogota with Fight for Humanity, University of York, local partner organisation Indepaz, and the Indigenous community Resguardo Indígena de Huellas Caloto (Nov. 2024)
- 1x Meeting with What Works to Prevent Violence (Jan. 2024)
- 1x Attendance at FCDO Conflict Conference + MarketPlace presentation (March 2024)
- 1 x Keynote intervention at Domicide: The Killing of Home, Municipality of Rotterdam (May 2024)
- 1 x Meeting with World Food Programme re food insecurity database (June 2024)
- 1 x Expert participation in Wilton Park dialogue “Conflict trauma and youth” (July 2024)
- 1 x Participation and panel chairing at Geneva Policy Workshop on Children and Armed Conflict (Aug. 2024)
- 1 x BCC participation at Geneva Peace Week (Oct. 2024)
- 1 x Meeting with FCDO CAAC lead and Deputy Head of the Gender and Children in Conflict Department (Nov. 2024)
- 1 x Meeting with Staff at the Civilian Protection Center of Excellence, Department of the Army, Deputy Chief of Staff, United States to discuss the BCC’s work (Nov. 2024)
- 1 x Meeting with Geneva Call Ukraine colleagues working with the Armed Forces of Ukraine (Nov. 2024)

Annexe 3 – RIAH-supported data referenced in the media in 2024
II Myanmar	13/01/2024	BBC Radio 4: From Our Correspondent	https://www.bbc.co.uk/sounds/play/m001vc8m
II data	05/02/2024	Nurse leader condemns ‘rising’ attacks on nurses in warzones	https://www.nursingtimes.net/news/global-nursing/nurse-leader-condemns-rising-attacks-on-nurses-in-warzones-05-02-2024/
SHCC	12/01/2024	Ethiopia: Who Killed Red Cross Worker in Tigray?	https://developmentdiaries.com/ethiopia-who-killed-red-cross-worker-in-tigray/
Insecurity Insight	16/01/2024	Doctors caught in the Sudanese crossfire	https://www.cajnewsafrica.com/2024/01/16/doctors-caught-in-the-sudanese-crossfire/
II - oPt/Israel	23/01/2024	Against every instinct: 'How doctors in Gaza persevere amid Israel attacks	https://www.aljazeera.com/features/longform/2024/1/23/how-doctors-in-gaza-persevere-amid-israel-attacks
II - oPt/Israel	25/01/2024	Last functional hospital in Gaza under attack as medical personnel toll hits 192	https://thecurrent.pk/last-functional-hospital-in-gaza-under-attack-as-medical-personnel-toll-hits-192/
SHCC/Len/II	25/01/2024	Gaza-Israel conflict: Hundreds of medics are killed or arrested after intense attacks on healthcare facilities	https://www.bmj.com/content/384/bmj.q203?hwshib2=authn%3A1708189365%3A20240216%253Ac9ea01fb-7f79-445e-a576-03b591932276%3A0%3A0%3A0%3AndG22K6inwn0K7JLx2GMhA%3D%3D
SHCC	03/02/2024	Caught In The Line Of Fire: Health Workers Not Spared In Nigeria’s Unending Conflict	https://humanglemedia.com/caught-in-the-line-of-fire-health-workers-not-spared-in-nigerias-unending-conflict/
II - Myanmar	02/02/2024	Swiss Report: 900 Myanmar Medics Detained Since 2021 Coup	https://www.irrawaddy.com/news/burma/swiss-report-900-myanmar-medics-detained-since-2021-coup.html
II - oPt/Israel	07/02/2024	Humanitarian Crisis Revealed: Healthcare In Gaza Under Attack – Joint Statement By The Syrian American Medical Society (SAMS) And The Palestinian American Medical Society (PAMA) – Occupied Palestinian Territory	https://fiorreports.com/humanitarian-crisis-revealed-healthcare-in-gaza-under-attack-joint-statement-by-the-syrian-american-medical-society-sams-and-the-palestinian-american-medical-society-pama-occupied-palestinian/
II - Myanmar	13/02/2024	Supporting Myanmar’s health system	https://lordslibrary.parliament.uk/supporting-myanmars-health-system/
SHCC	16/02/2024	Afghanistan's Dual Crises: COVID-19 and Ongoing Conflict Overwhelm Healthcare System	https://bnnbreaking.com/breaking-news/health/afghanistans-dual-crises-covid-19-and-ongoing-conflict-overwhelm-healthcare-system
II - Myanmar	02/02/2024	Swiss Report: 900 Myanmar Medics Detained Since 2021 Coup	https://www.irrawaddy.com/news/burma/swiss-report-900-myanmar-medics-detained-since-2021-coup.html
II - Ukraine	23/02/2024	Putin is using a dirty tactic to destroy Ukraine’s entire health system	https://metro.co.uk/2024/02/23/putins-tactic-destroy-ukraines-entire-health-system-mapped-20326323/
II - Myanmar	04/03/2024	In Myanmar, Health Care Has Become a Battleground	https://www.thinkglobalhealth.org/article/myanmar-health-care-has-become-battleground
II - Myanmar	29/02/2024	12 attacks on Myanmar healthcare providers during two weeks in February	https://eng.mizzima.com/2024/02/29/7602
II - Ukraine	10/03/2024	Maternity hospital bombing in Oscar-winning “20 Days in Mariupol” is one of 1350+ attacks on health care in Ukraine	https://phr.org/news/maternity-hospital-bombing-in-oscar-winning-20-days-in-mariupol-is-one-of-1350-attacks-on-health-care-in-ukraine/
II - Myanmar	11/03/2024	Pregnant women in war-torn Myanmar face perilous childbirth	https://www.straitstimes.com/asia/se-asia/pregnant-women-in-war-torn-myanmar-face-perilous-childbirth
II - Myanmar	11/03/2024	Amid war, Gaza's women bear the greatest burden | Op-eds - Gulf News	https://gulfnews.com/amp/opinion/op-eds/amid-war-gazas-women-bear-the-greatest-burden-1.101583525
II - oPt/Israel	14/03/2024	Gaza: BMA calls for urgent investigation into mistreatment of doctors	https://www.bmj.com/content/384/bmj.q658
II - oPt/Israel	14/03/2024	Staggering Levels of Violence Against Health Workers in Gaza Warrant Investigation and Accountability: PHR	https://phr.org/news/staggering-levels-of-violence-against-health-workers-in-gaza-warrant-investigation-and-accountability-phr/
II - oPt/Israel	21/03/2024	Behind the numbers: Gaza’s unprecedented aid worker death toll	https://www.thenewhumanitarian.org/maps-and-graphics/2024/03/21/behind-numbers-gaza-unprecedented-aid-worker-death-toll
Len/SHCC/II	27/03/2024	Health workers should not be a casualty of war — they need protections, now	https://thehill.com/opinion/international/4557900-health-workers-should-not-be-a-casualty-of-war-they-need-protections-now/
II - oPt/Israel	04/04/2024	‘It’s Not Just a One-Off Incident:’ What the World Central Kitchen Deaths Reveal	https://time.com/6963079/world-central-kitchen-relief-workers-gaza-israel/
II - oPt/Israel	04/04/2024	Report: Over 1,000 Attacks on Health Care for Palestinians	https://accuracy.org/release/report-over-1000-attacks-on-health-care-for-palestinians/
SHCC	04/04/2024	World Health Day: Health Workers are Under Attack Worldwide	https://www.projecthope.org/world-health-day-health-workers-are-under-attack-worldwide/
II- Sudan	28/03/2024	Sudan Attacks on Healthcare Since April 15, 2023	https://sudanhrh.org/en/articles/sudan-attacks-since-2023-1
II Sudan data	11/03/2024	Sudan’s healthcare, the first casualty of war	https://3ayin.com/en/healthcare/
II - Sudan	10/04/2024	Conflict and Hunger in Sudan: an NGO call to action	https://coopi.org/en/conflict-and-hunger-in-sudan-an-ngo-call-to-action.html
II - Myanmar	13/04/2024	Attacks recorded on Myanmar healthcare providers	https://eng.mizzima.com/2024/04/13/8973
DRC study	22/04/2024	A new study by the International Rescue Committee (IRC) and partners reveals women and children are bearing the brunt of the ongoing conflict in Eastern Democratic Republic of Congo (DRC)	https://www.africa.com/a-new-study-by-the-international-rescue-committee-irc-and-partners-reveals-women-and-children-are-bearing-the-brunt-of-the-ongoing-conflict-in-eastern-democratic-republic-of-congo-drc/
II - oPt/Israel	02/05/2024	Hamas says it views cease-fire talks favorably amid pressure to accept deal	https://www.washingtonpost.com/world/2024/05/02/israel-hamas-war-news-gaza-palestine/#link-VSJEZHQJKNC3VMEXQCQLCPXNMA
II - oPt/Israel	03/05/2024	Senior Palestinian Doctor Dies in Israeli Custody	https://stratnewsglobal.com/world-news/prominent-palestinian-doctor-dies-in-israeli-prison/
II - oPt/Israel	02/05/2024	Prominent Gaza doctor dies in Israel prison	https://www.middleeastmonitor.com/20240502-prominent-gaza-doctor-dies-in-israel-prison/
II - oPt/Israel	03/05/2024	Palestinian doctor dies in Israeli prison after months of detention	https://www.dailysabah.com/world/mid-east/palestinian-doctor-dies-in-israeli-prison-after-months-of-detention
II - oPt/Israel	03/05/2024	Palestinian groups protest after death of doctor held in Israeli prison	https://ca.news.yahoo.com/palestinian-groups-protest-death-doctor-190841099.html
II - oPt/Israel	03/05/2024	Prominent Gaza doctor dies in Israeli prison	https://www.reuters.com/world/middle-east/prominent-gaza-doctor-dies-israeli-prison-2024-05-02/
II - oPt/Israel	04/05/2024	‘Heroic’ Palestinian surgeon dies in Israeli prison after months in detention	https://www.msn.com/en-ie/news/world/heroic-palestinian-surgeon-dies-in-israeli-prison-after-months-in-detention/ar-AA1o8n6F
II - oPt/Israel	10/05/2024	Biden’s weapons sales to Israel breach legal limits, former officials say	https://www.washingtonpost.com/world/2024/05/10/israel-gaza-biden-weapons-rafah/
SHCC/Rohini	14/05/2024	Attacks On Health Care In War Must Not Become New Norm	https://www.miragenews.com/attacks-on-health-care-in-war-must-not-become-1233661/
II - oPt/Israel	15/05/2024	Gaza’s invisible massacre: aid workers killed in record numbers	https://360info.org/gazas-invisible-massacre-aid-workers-killed-in-record-numbers/
SHCC	15/05/2024	Fights to end polio, contain Ebola made tougher by rising violence, research finds	https://ca.style.yahoo.com/news/fights-end-polio-contain-ebola-040100535.html?guccounter=1&guce_referrer=aHR0cHM6Ly93d3cuZ29vZ2xlLmNvbS8&guce_referrer_sig=AQAAAE-ZQItfdu3ap2Ev7j7o68xIUtNrQpTxRZiC_PSqgxL0t38H1YZsVnTrn7cw_67RGxfmghHu7eDqi9pElGzRC59ZjThPV_8e_ujD3zs1UTnDaxtwz8C6EbTf1dMB_trcvNYWGyN4nohx6ToTgsfI-TOoxzaeLyxJiX99Awz0Hv8Y
II - oPt/Israel	21/05/2024	Mapping the damage to Gaza’s hospitals: Battered, abandoned and raided	https://www.washingtonpost.com/world/2024/05/21/gaza-hospitals-attacks-bombed-israel-war/
SHCC	22/05/2024	Attacks on health workers in conflict zones at highest level ever – report	https://www.theguardian.com/global-development/article/2024/may/22/attacks-health-war-bombing-looting-hospitals-killing-medics-gaza-sudan-ukraine-humanitarian-law?CMP=Share_AndroidApp_Other
SHCC	22/05/2024	Fatal Attacks on Health-Care Workers Doubled in 2023	https://www.thinkglobalhealth.org/article/fatal-attacks-health-care-workers-doubled-2023
SHCC	22/05/2024	Violence against health staff in conflict zones reached record high in 2023	https://www.bmj.com/content/385/bmj.q1140
SHCC	22/05/2024	International Community Urged to End Impunity for Violence Against Healthcare in Conflicts	https://www.ipsnews.net/2024/05/international-community-urged-to-end-impunity-for-violence-against-healthcare-in-conflicts/
SHCC	22/05/2024	Health Facilities and Workers in Conflict Zones Suffered a Record Number of Attacks Last Year	https://www.motherjones.com/politics/2024/05/health-facilities-and-workers-in-conflict-zones-suffered-a-record-number-of-attacks-last-year/
SHCC	22/05/2024	Attacks on health care in war zones up 25%, NGOs say	https://www.middleeastmonitor.com/20240522-attacks-on-health-care-in-war-zones-up-25-ngos-say/
SHCC	22/05/2024	Attacks on health care in war zones surge 25% last year, NGOs say	https://urldefense.com/v3/__https:/www.reuters.com/world/attacks-health-care-war-zones-surge-25-last-year-ngos-say-2024-05-22/__;!!PDiH4ENfjr2_Jw!Bq_e0bRfo8SEXZ3RXqavsgGJFMYeFmrgpbW6kmV6qYH9wtH_Lq9raH2jP0ctswv6gZ6XBGvbBbE0jaAQjhlPqqMZA9Va-hisA2n6kDuh-DJ7gV3z$
SHCC	22/05/2024	Attacks on health workers in conflict zones reach highest level on record	https://www.msn.com/en-ca/video/news/health-matters-attacks-on-health-workers-in-conflict-zones-reach-highest-level-on-record/vi-BB1mRzGg#details
SHCC	22/05/2024	International Community Urged to End Impunity for Violence Against Healthcare in Conflicts	https://www.ipsnews.net/2024/05/international-community-urged-to-end-impunity-for-violence-against-healthcare-in-conflicts/
SHCC	22/05/2024	Attacks on health care in war zones surge 25% last year, NGOs say	https://www.deccanherald.com/world/attacks-on-health-care-in-war-zones-surge-25-last-year-ngos-say-3033817
SHCC	23/05/2024	Devex CheckUp: All you need to know in preparation for WHA 77	https://www.devex.com/news/devex-checkup-all-you-need-to-know-in-preparation-for-wha-77-107646
SHCC	27/05/2024	Sudan recorded highest violence against healthcare staff in conflict zones in 2023: Report	https://www.downtoearth.org.in/africa/sudan-recorded-highest-violence-against-healthcare-staff-in-conflict-zones-in-2023-report
SHCC	30/05/2024	Israel's war on Gaza live: No safe shelter as dozens killed in Rafah - Al Jazeera	https://www.aljazeera.com/news/liveblog/2024/5/30/israels-war-on-gaza-live-no-safe-shelter-as-dozens-killed-in-rafah?update=2935143
SHCC	04/06/2024	Healthcare in the crosshairs	https://borneobulletin.com.bn/healthcare-in-the-crosshairs/
SHCC	04/06/2024	Sudan recorded highest violence against healthcare staff in conflict zones in 2023: Report	https://jara.news/sudan-recorded-highest-violence-against-healthcare-staff-in-conflict-zones-in-2023-report/
SHCC	04/06/2024	Caring for Patients in Armed Conflict: Narratives from the Front Lines	https://www.thehastingscenter.org/caring-for-patients-in-armed-conflict-narratives-from-the-front-lines/
II/SHCC - Ukraine	06/06/2024	Russia’s Attacks on Ukraine’s Energy Infrastructure Imperil Healthcare Access	https://www.justsecurity.org/96466/attacks-on-healthcare-access/
II - Myanmar	12/06/2024	Insecurity Insight continues recording attacks on Myanmar health care facilities	https://eng.mizzima.com/2024/06/12/10766
II - Myanmar	25/06/2024	12 attacks on healthcare in Myanmar recorded at beginning of June	https://eng.mizzima.com/2024/06/25/11140
SHCC	24/06/2024	What’s Behind Israel’s Attacks on Hospitals in Gaza?	https://inkstickmedia.com/whats-behind-israels-attacks-on-hospitals-in-gaza/
SHCC/II	27/06/2024	Ethiopia health sector attacked during civil war	https://www.cajnewsafrica.com/2024/06/27/ethiopia-health-sector-attacked-during-civil-war/
II - Myanmar	04/07/2024	Insecurity Insight records 12 attacks on Myanmar healthcare from 12-25 June	https://eng.mizzima.com/2024/07/04/11420
SHCC	08/07/2024	Len Rubenstein, Johns Hopkins University: “The policy is hand-wringing… Total impunity.”	https://www.csis.org/podcasts/commonhealth/len-rubenstein-johns-hopkins-university-policy-hand-wringing-total-impunity
II - Myanmar	31/07/2024	Insecurity Insight records 16 attacks on Myanmar healthcare from 10 to 23 July 2024	https://eng.mizzima.com/2024/07/31/12311
SHCC - Nigeria	16/08/2024	Lagos doctors stage solidarity walk, demand release of abducted colleague	https://www.premiumtimesng.com/news/top-news/725075-lagos-doctors-stage-solidarity-walk-demand-release-of-abducted-colleague.html
SHCC	27/08/2024	Report details COVID-related healthcare worker attacks, injuries, deaths around the world	https://www.cidrap.umn.edu/covid-19/report-details-covid-related-healthcare-worker-attacks-injuries-deaths-around-world
SHCC	28/08/2024	Abduction: Enugu resident doctors join nationwide strike, demand rescue of colleague	https://www.tvcnews.tv/2024/08/abduction-enugu-resident-doctors-join-nationwide-strike-demand-rescue-of-colleague/
Insecurity Insight	27/08/2024	Drug piracy threatens millions of lives in the Sahel	https://apanews.net/drug-piracy-threatens-millions-of-lives-in-the-sahel/
Insecurity Insight	27/08/2024	Au Sahel, le pillage des médicaments menace des millions de vies	https://fr.apanews.net/news/au-sahel-le-pillage-des-medicaments-menace-des-millions-de-vies/
SHCC	01/09/2024	Kidnappers threaten health services as 109 workers abducted in five years – Report	https://punchng.com/kidnappers-threaten-health-services-as-109-workers-abducted-in-five-years-report/?amp
SHCC	04/09/2024	Escalating Cameroon conflicts claim hundreds of lives	https://www.cajnewsafrica.com/2024/09/05/escalating-cameroon-conflicts-claim-hundreds-of-lives/
SHCC	12/09/2024	Healing the Brain Drain: Nigeria’s move to stem health workers migration	https://www.premiumtimesng.com/health/health-features/733575-healing-the-brain-drain-nigerias-move-to-stem-health-workers-migration.html
II - Myanmar	23/09/2024	Reading the tea leaves in Myanmar and SE Asia	https://eng.mizzima.com/2024/09/23/14271
SHCC	29/09/2024	Attacks on health care during war are becoming more common, creating devastating ripple effects	https://theconversation.com/attacks-on-health-care-during-war-are-becoming-more-common-creating-devastating-ripple-effects-237484
SHCC	07/10/2024	Attacks on healthcare during war becoming more common	https://www.downtoearth.org.in/health/attacks-on-healthcare-during-war-becoming-more-common
II - Myanmar	23/10/2024	Cyclonic storm causes heavy rain and strong wind some states and regions of Myanmar	https://eng.mizzima.com/2024/10/23/15395
SHCC	30/10/2024	Militant attacks in Pakistan hinder polio immunization campaigns	https://www.voanews.com/a/militant-attacks-in-pakistan-hinder-polio-immunization-campaigns/7845343.html
SHCC	31/10/2024	After 10 months in kidnappers’ den, Kaduna doctor regains freedom	https://www.premiumtimesng.com/news/top-news/750687-after-10-months-in-kidnappers-den-kaduna-doctor-regains-freedom.html
II - Gaza	19/12/2024	II data for AoH in Israel and oPt mentioned in Al Jazeera live blog
II - Gaza	19/12/2024	Morning Update - Middle East Eye	https://www.middleeasteye.net/live-blog/live-blog-update/morning-update-200?nid=415313&topic=Gaza%2520Under%2520Attack&fid=540970
SHCC	28/11/2024	Safeguarding the healers: protecting healthcare workers in armed conflicts	https://europeansting.com/2024/11/28/safeguarding-the-healers-protecting-healthcare-workers-in-armed-conflicts/
SHCC - Nigeria	22/11/2024	Of Alice, Ganiyat, and Hamdiyya: Lessons in resilience and courage, By Zainab Suleiman Okino	https://www.premiumtimesng.com/matchesresults/756194-of-alice-ganiyat-and-hamdiyya-lessons-in-resilience-and-courage-by-zainab-suleiman-okino.html?tztc=1
SHCC - Nigeria	20/11/2024	Alice, Ganiyat’s unbroken spirit and Hamdiyya’s saga	https://blueprint.ng/alice-ganiyats-unbroken-spirit-and-hamdiyyas-saga/

Annexe 4 – RIAH Journal articles (previous years greyed out)
Date	Journal	Title
07 May 2021	Conflict and Health	Violence against healthcare in conflict: a systematic review of the literature and agenda for future research | Conflict and Health | Full Text
26 May 2022	International Studies Review	Using Data to Create Change? Interrogating the Role of Data in Ending Attacks on Healthcare | International Studies Review | Oxford Academic
30 January 2023	Conflict and Health	Underestimating attacks: comparing two sources of publicly-available data about attacks on health care in 2017 | Conflict and Health | Full Text
09 April 2023	Social History of Medicine	Caring Under Fire Across Three Continents: The Hadfield-Spears Ambulance, 1941–1945 | Social History of Medicine | Oxford Academic
12 June 2023	Conflict and Health	The crisis of maternal and child health in Afghanistan | Conflict and Health | Full Text
24 October 2023	Conflict and Health	“There is a fear that you will be attacked just for the act of working in health”: a survey of experiences of violence against healthcare in Colombia | Conflict and Health | Full Text
3 April 2024	Conflict and Health	Impacts of attacks to female health care workers in three territories of Colombia
22 April 2024	Humanity	Project MUSE - "Like a Yam Between Two Stones": Remembering Healthcare at War in Nepal (1996–2006)
22 April 2024	Humanity	Project MUSE - Introduction: History Writing and Attacks on Healthcare
12 July 2024	International Feminist Journal of Politics	Intimacy and the gendering of war healthcare: women’s experiences of insurgency war in Nepal (1996–2006)
20 August 2024	Conflict and Health	“I will take part in the revolution with our people”: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat
27 August 2024	Conflict and Health	“It's normal to be afraid”: attacks on healthcare in Ouaka, Haute-Kotto, and Vakaga prefectures of the Central African Republic, 2016–2020

Annexe 5 – RIAH, other publications (previous years greyed out)
Title	Document Type	Publication Date	URL
Impact Methods Meeting Summary	Thematic Summary	13 February 2020	2019-Panels-Summary-for-Website.pdf
Health workers at risk: Violence against health care	Report	2020	SHCC2020final.pdf
Conceptual issues and methodological approaches to evaluating the wider and longer-term impact of attack on healthcare in conflict	Working Paper	December 2020	Impact-Methods-Working-Paper-min-1.pdf
Case Study: Exploratory Analysis of Publicly Available Data on Attacks on Health in Colombia	Case Study	22 April 2021	RIAH-Columbia-Online-Surveillance-WebCopy.pdf
No Respite: Violence Against Healthcare in Conflict	Report	2021	SHCC 2021 Report No respite Violence against health care in conflict.pdf
Afghanistan Interview Guides	Protocol	2021	Afghanistan Interview Guides – RIAH – Researching the Impact of Attacks on Healthcare
Unrelenting Violence: Violence Against Healthcare in Conflict	Report	2022	SHCC%202021%20Unrelenting%20Violence2%20FINAL.pdf
Accounting for gender when it is not counted Highlighting the importance of sex-disaggregated data in understanding the impacts of attacks on healthcare	Briefing	February 2022	HCRI_Policy_Brief_Gender-_25.02.22.pdf
Gendered health impacts of civil war in Nepal	Briefing	January 2023	RIAH-Policy-Brief-Nepal-gender-Jan-2023-FINAL.pdf
What do we Learn from the History of Attacks on Healthcare?	Briefing	May 2023	Research-Brief-05.23-What-do-we-learn.pdf
Ignoring Red Lines: Violence Against Healthcare in Conflict	Report	2023	SHCC-Report-Ignoring-Red-Lines.pdf
Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late	Discussion Paper	6 December 2023	Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late | Conflict and Health | Full Text
The impact of violence against health care on the health of children and mothers a case study in three health zones in Eastern DRC	Case Study	April 2024	ERSP UCB RIAH IRC - ATTACKS AGAINST HEALTHCARE DRC.pdf
Critical Condition: Violence Against Healthcare in Conflict	Report	2024	2023-SHCC-Critical-Conditions.pdf
Security Risk Management for Health Care Handbook	Handbook	2024	Security Risk Management for Health Care Security Risk Management for Health Care Security Risk Management for Health Care - Insecurity Insight
HUMVI: A Multilingual Dataset for Detecting Violent Incidents Impacting Humanitarian Aid	Article	15 October 2024	2410.06370

Annexe 6 – J-PAL Publications
Date	Publication Type	Title	Country	J-PAL/IPA Website link
13/02/2024	Blog	New Humanitarian Protection Initiative Will Help Reduce Harm to People Affected by Conflict	Global	https://poverty-action.org/new-humanitarian-protection-initiative-will-help-reduce-harm-people-affected-conflict
15/07/2024	Policy Brief	Preventing Individual-Level Violence in Conflict Settings	Global	https://poverty-action.org/sites/default/files/2024-07/Humanitarian-Protection%20Policy-Brief%231%20%283%29.pdf
14/02/2024	Policy Publication	Request for Proposal Document	Global	https://www.povertyactionlab.org/sites/default/files/HPI_RFP%201_Feb2024.pdf
19/12/2024	Blog	In conversation with Norwegian Church Aid: Understanding the catalyzing effect of J-PAL humanitarian trainings	Global	https://www.povertyactionlab.org/blog/12-19-24/conversation-norwegian-church-aid-understanding-catalyzing-effect-j-pal-humanitarian?lang=fr

Annexe 7 – JPAL/HPI’s RFP Round I: Funded Projects
Full RCTs
Growing Stronger Together: A Family Strengthening Approach to Reduce Child Engagement with Armed Forces in Central African Republic - Amber Peterman (University of North Carolina at Chapel Hill, UNC), Kathryn Falb (Johns Hopkins Bloomberg School of Public Health), Yvonne Agengo (IRC), Camille Fabbri (London School of Hygiene and Tropical Medicine), Clement Bicaba (IRC); with the International Rescue Committee (IRC). This study aims to reduce child engagement in armed forces through an innovative approach that combines curriculum- and group-based effective parenting programming with tailored support for families who have had children engaged in or at risk of recruitment into armed groups.

Cancelled: Forced Displacement, Couples’ Mental Health, and Gender-Based Violence: Evidence from the Rohingya Refugees in Bangladesh - Asad Islam (Monash University); Bilge Erten (Northeastern University); with the Bangladesh Rural Advancement Committee (BRAC). This evaluation provides Cognitive-Behavioural Conjoint Therapy (CBCT) to Rohingya refugee couples living in camps in Cox’s Bazar, aiming to reduce post-traumatic stress and improve communication and conflict resolution skills. Researchers expect improvements in mental health and reductions in risk of SGBV and expect positive spillover effects on couples that did not participate in the program.

Pilot Studies
- Sextortion and entrepreneurship in Burkina Faso - Oana Borcan (University of East Anglia); Doris Aja-Eke (Dublin City University, DCU); Robert Gillanders (Dublin City University, DCU); W. H. Eugenie Maiga (Université Norbert Zongo, Burkina Faso), with IPA and Empow’Her. This pilot study of interventions to prevent sexual exploitation of female entrepreneurs in Burkina Faso. This pilot study investigates if a training and peer support intervention for IDP women entrepreneurs in Burkina Faso can protect women against sextortion, which is particularly prevalent in business registration and financing offices.
- Layperson first responder trainings to improve trauma care for civilian casualties of explosive violence in Burkina Faso - Nicolas Meda (Co-PI, Government of Burkina Faso / Université Joseph Ki-Zerbo); Hannah Wild (University of Washington) Moumini Niaone; with the Mines Advisory Group. This pilot project seeks to improve laypersons’ ability to respond to physical trauma of civilian victims in the immediate aftermath of mine explosions and enhance coordination between the UN Humanitarian Cluster System’s Health and Protection Clusters to reduce preventable deaths and injuries in armed conflict zones.
Project development grants
- Fostering peaceful behaviours among farmers and herders: Impacts of community-driven initiatives and edutainment (Nigeria). This project, aimed at fostering peaceful behaviours among farmers and herders through community-driven initiatives and edutainment, directly addresses this policy issue by promoting conflict resolution and enhancing social cohesion.
- The impacts of safe spaces on network creation and gender-based violence among conflict-affected displaced women (Egypt). This project aims to evaluate how social network interventions in safe spaces can protect displaced women from gender-based violence (GBV) and mitigate its psychological and socioeconomic impacts.
- Safe Spaces and Internal Displaced Women’s and Girls' Wellbeing (Burkina Faso): The project aims to address GBV issues in conflict-affected areas of Burkina Faso by implementing two interventions: the creation of safe spaces offering support, awareness, and empowerment activities for displaced women and girls, and a home-based outreach programme to engage the broader community in GBV prevention and response efforts.
- Improving Adolescent Outcomes in Conflict Settings (Ethiopia). The proposed pilot research lays the groundwork for a rigorous randomised evaluation of timely and policy-informed multi-level, multi-faceted programming aimed at the reduction of GBV and support for GBV survivors in conflict-affected settings in Ethiopia. The eventual full evaluation will fill existing evidence gaps on the effectiveness of combinations of policies shown to work in other settings but not proven in regions affected by conflict.
- Explaining and Preventing Environmental Conflict in the Amazon (Brazil). This project aims to generate rigorous empirical evidence on the rising but understudied violence against land and environmental defenders while evaluating mechanisms to protect remote, vulnerable communities from harm. By addressing gaps in data and understanding, it seeks to inform more effective prevention and protection strategies.

Annexe 8 – List of Beyond Compliance Consortium research outputs
Date	Publication type	Title	Authors
April 2024	Conference paper (not published)	"Generating compliance, respect-protect-fulfil, or restraint in armed conflict – what’s in a frame?”, International Studies Association (ISA) conference, San Francisco	Ioana Cismas
June 2024	Conference paper (not published)	"Seeing Like a State: What is in an (IHL) Frame? International Law Association (ILA) conference, Athens	Katharine Fortin
September 2024	Conference paper (not published)	'The Beyond Compliance Consortium: Design and Methods', European Society of International Law, Tallinn	Katharine Fortin and Ioana Cismas
17 September 2024	Blog Symposium	“Why and How to Go “Beyond the Law” to Address Negative Lived Experiences of Armed Conflict”, Beyond Compliance Symposium, Articles of War and AGIL. Available online.	Katharine Fortin, Ezequiel Heffes, Ioana Cismas and Jennifer Maddocks
18 September 2024	Blog Symposium	“What’s in a Frame? Understanding Everyday Lived Experiences of Armed Conflict Through a Lens of ‘harm + need’”, Beyond Compliance Symposium, AGIL. Available online.	Katharine Fortin and Rebecca Sutton
18 September 2024	Blog Symposium	“Compliance + Restraint Towards Full(er) Protection in War”, Beyond Compliance Symposium, Articles of War. Available online.	Ioana Cismas and Anastasia Shesterinina
24 September 2024	Blog Symposium	“Beyond typologies of actors: ambiguous boundaries in non-international armed conflicts”, Beyond Compliance Symposium, AGIL. Available online.	Anastasia Shesterinina
25 September 2024	Blog Symposium	“Why armed actors should pay more attention to civilian self-protection efforts”, Beyond Compliance Symposium, Articles of War. Available online.	Marc Linning
26 September 2024	Blog Symposium	“Strategies for reducing harm and need in war through a decolonial and intersectional lens”, Beyond Compliance Symposium, AGIL. Available online.	Samantha Holmes
2 October 2024	Blog Symposium	“Redressing Civilian Harm and Going Beyond International Humanitarian Law Compliance”, Beyond Compliance Symposium, Articles of War. Available online.	Luke Moffett
3 October 2024	Blog Symposium	“Practical Measures to Prevent and Mitigate Conflict-induced Food Insecurity”, Beyond Compliance Symposium, AGIL. Available online.	Katherine Kramer
3 October 2024	Blog Symposium	“A rights-based approach to addressing harm and need in armed conflict?”, Beyond Compliance Symposium, Articles of War. Available online.	Rocco Blume
10 October 2024	Blog Symposium	“Armed Groups, Compliance and International Law: There is more than meets the eye”, Beyond Compliance Symposium, AGIL. Available online.	Ezequiel Heffes
15 October 2024	Blog Symposium	“Beyond Compliance Symposium: War is not skin deep – International Humanitarian Law and mental health”, Beyond Compliance Symposium, AGIL. Available online.	Samantha Holmes
22 October 2024	Blog Symposium	“Systemic impacts of war in protracted conflicts”, Beyond Compliance Symposium, Articles of War. Available online.	Joshua Joseph Niyo
29 October 2024	Blog Symposium	“Security beyond the physical – Addressing the Nasa Indigenous people’s spiritual harm in armed conflict”, Beyond Compliance Symposium, AGIL. Available online.	Piergiuseppe Parisi
5 November 2024	Blog Symposium	“The Harm Mitigation Holarchy: Human Security, Protection of Civilians, and Civilian Harm Mitigation and Response”, Beyond Compliance Symposium, Articles of War. Available online.	Dan E. Stigall
12 November 2024	Blog Symposium	“Buddhism's Psycho-ethics of Non-Harm and Restraint for All Sentient Beings During Armed Conflict”, Beyond Compliance Symposium, AGIL. Available online.	Andrew Bartles-Smith
19 November 2024	Blog Symposium	“Towards the full protection of civilians”, Beyond Compliance Symposium, Articles of War. Available online.	Simon Bagshaw
26 November 2024	Blog Symposium	“Recognising and Addressing Harm to Children Caused by Explosive Weapons”, Beyond Compliance Symposium, AGIL. Available online.	Bethany Ellis
5 December 2024	Blog Symposium	“Quantifying Compliance: Challenges of Measuring Compliance with International Humanitarian Law”, Beyond Compliance Symposium, Articles of War. Available online.	Christoph Dworschak and Hyunjung Park
10 December 2024	Blog Symposium	Research Consultations with Non-State Armed Groups”, Beyond Compliance Symposium, AGIL. Available online.	Pascal Bongard and Anki Sjoeberg
17 December 2024	Blog Symposium	“Providing a Framework for NATO’s Human Security Approach”, Beyond Compliance Symposium, Articles of War. Available online.	Alexander Gilder and Daniel Linsdell
19 December 2024	Blog Symposium	“The UN Children and Armed Conflict agenda as an accountability mechanism”, Beyond Compliance Symposium, AGIL. Available online.	Rocco Blume and Samantha Holmes
9 September 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 1 “Engaging Armed Groups”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Matthew Bamber-Zryd and Dr Tilman Rodenhäuser
20 September 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 2 “Civilian Agency in Violent Settings”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Emily Paddon Rhoads and Juan Masullo
4 October 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 3 “Mexico – Civilian Agency Outside of War Zones”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Anjan Sundaram and Chiara Redaelli
18 October 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 4 “Negotiating with Armed Actors”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Riyad Anwar, Ashley Jackson and Abellia Anggi Wardani
1 November 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 5 “Decision Making in Armed Conflict”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Mara Revkin and Justin Schon
15 November 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 6 “Armed Groups and Counter-Terrorism”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Sophie Haspeslagh and Gloria Gaggioli
29 November 2024	Podcast	Beyond Compliance: In Conversation Podcast Series 1: Episode 7 “Victimhood & Everyday Peace”. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guest: Kieran McEvoy and Roger Mac Ginty
26 June 2024	Research Line memo (not published)	The Situation in the Occupied Palestinian Territory – Impact on Humanitarian Norms”	Research Line team
2 December 2024	Research Line briefing (not published)	What is the legality of UN cross border operations from Türkiye into North-West (NW) Syria in the event of the non-resolution / arbitrary withdrawal of consent by the government of Syria?	Research Line team
November 2024	BCC Newsletter	Introducing the Beyond Compliance Consortium, BCC Newsletter No. 1, Available online.	University of York
	Website & LinkedIn	https://beyond-compliance-consortium.org/ / @beyond-compliance-consortium	University of York

Annexe 9 – Peer-reviewed articles from AHRC (previous years greyed out)
Date	Title	Journal
17 Feb 2022	“One Man’s Meat Is Another Man’s Poison”: Marungi and Realities of Resilience in North-West Uganda	Civil Wars
June 2022	The Cultural Problematic in Narratives of Violence against Women and Girls in South Sudan	Journal of Asian and African Studies
March 29 2023	Coloniality and frictions: Data-driven humanitarianism in North-Eastern Nigeria and South Sudan	Big Data and Society
26 April 2023	Data gathering and utilization: humanitarian targeting and ethical issues in northeastern Nigeria	Journal of Humanitarian action
21 March 2023	“These people are lying to us”: Mutating Vaccine Fears and Colonial Histories in Arua, North-West Uganda	Medical Anthropology Quarterly
June 2023	‘All in good faith?’ An ethno-historical analysis of local faith actors’ involvement in the delivery of mental health interventions in northern Uganda	Transcultural Psychiatry
August 2023	“I embroider the beauty that is my head and not the dead trees around me” art heritage and resilience in South Sudan: a gendered view	Journal of Humanities and Applied Social Sciences
Jan 2024	Conceptualising and challenging child neglect in humanitarian action: Protecting displaced children in Jordan and Palestine	Child Abuse and Neglect
Jan 2024	Longitudinal Impact of Conflict-Related Sexual Violence Experienced by Men in Detention Since the Onset of the Syrian Conflict	eClinical Medicine (Lancet)
April 2024	Parenting and family interventions in lower and middle-income countries for child and adolescent mental health: A systematic review	Comprehensive Psychiatry
October 2024	Engaging Data Literacies in Displacement	Journal of Humanitarian Affairs
2025	“You already know enough: Certainty and Ignorance in Data-Driven Humanitarianism”	Geopolitics

Annexe 10: Number of IHL duty-bearers and non-state actors’ commitments to protect healthcare in 2024, disaggregated by nature of commitments.

Summary

In 2023, 381 IHL duty-bearer commitments and one commitment by a non-state armed actor from the MENA region to protect healthcare were made. In 2024, 840 IHL duty-bearer commitments and one commitment by a non-state armed actor from the DRC to protect healthcare were made. This uptick has occurred in a context where attacks and threats to health care continue to increase.

13 United Nations resolutions addressed directly the necessity to respect and protect healthcare in armed conflict:

1. The United Nations Security Council adopted Resolution 2736 on the reports of the Secretary-General on the Sudan and South Sudan which called for all parties of the conflict in Sudan to comply with their obligations under international law and to respect and protect medical facilities, medical and humanitarian personnel as well as their means of transport.
2. The United Nations Security Council adopted Resolution 2729 on the reports of the Secretary-General on the Sudan and South Sudan (UNMISS) calling for the end of the use of hospitals and other civilian premises for purposes that could make them subject to attacks and called for conflict parties in South Sudan to protect and respect all medical and humanitarian personnel.
3. The United Nations Security Council adopted Resolution 2731 on the reports of the Secretary-General on the Sudan and South Sudan, which expressed concern over continued violence against medical and humanitarian personnel, facilities and convoys in South Sudan and expressed concern over the imposition of taxis and illegal fees which hamper the delivery of humanitarian assistance.
4. The United Nations Security Council adopted Resolution 2730 on the protection of civilians in armed conflict which reiterated the need to promote and ensure respect for the rules and principles of international humanitarian law and expressed concern for the growing number of attacks on humanitarian personnel and their premises.
5. The United Nations Security Council adopted Resolution 2743 on the question concerning Haiti (BINUH) which called for the prevention and abuses against children, as well as attacks on schools and hospital and the denial of humanitarian access.
6. The United Nations Security Council adopted Resolution 2765 on the situation concerning the Democratic Republic of the Congo (MINUSCO) which called for all parties to the conflict to respect and protection all humanitarian personnel including medical personnel, their means of transport and equipment, as well as hospitals and other medical facilities.
7. The United Nations Security Council adopted Resolution 2764 on children and armed conflict calling for access to health care and psychosocial support for girls and boys, including children with disabilities.
8. The United Nations Security Council adopted Resolution 2760 on the reports of the Secretary-General on the Sudan and South Sudan (UNIFSA) which noted the insufficient access to food, medical care, and other essential services in the Abyei Area (South Sudan).
9. The United Nations Security Council adopted Resolution 2759 on the situation in the Central African Republic calling for an end of attacks on schools and hospitals and condemned all attacks on and the use for military purposes of schools, medical centres and humanitarian premises.
10. The United Nations General Assembly adopted Resolution A/79/L.28 on the request for an advisory opinion of the International Court of Justice on the obligation of Israel in relation to the presence and activities of the United Nations, other international organisations and third State calling for Israel to refrain from attacking, destroying, removing or rendering useless objects that are indispensable to the survival of the civilian population.
11. The United Nations General Assembly adopted Resolution A/79/L.41 on the assistance to the Palestinian people stressed the need to ensure the safety and security of humanitarian personnel, premises, facilities, equipment, vehicles and supplies and the ensure safe and unhindered access of humanitarian personnel and the delivery of supplies and equipment.
12. The United Nations General Assembly of the United Nations adopted Resolution A/79/L.36 on strengthening of the coordination of humanitarian and disaster relief assistance of the United Nations, including special economic assistance: strengthening of the coordination of emergency humanitarian assistance of the United Nation which condemned all acts of violence against humanitarian personnel and their facilities, including medical personnel.
13. The United Nations General Assembly of the United Nations adopted Resolution A/79/L.32 on the safety and security of humanitarian personnel and protection of United Nations personnel which recalled the specific obligation to respect and protect medical and humanitarian personnel, their means of transport and equipment, and hospitals and other medical facilities and to ensure that wounded and sick receive the medical care and attention required.
There were also six statements on the protection of healthcare:

1. The Special Rapporteur on the right for everyone to the enjoyment of the highest attainable standard of physical and mental health released a statement on 06 May 2024 calling for the end of impunity for attacks on medical facilities and health worker and the respect for international law on the part of all warring parties.
  [note] OHCHR. Impunity for attacks on medical facilities and health workers must end, says UN expert. 06 May 2024. Available at https://www.ohchr.org/en/press-releases/2024/05/impunity-attacks-medical-facilities-and-health-workers-must-end-says-un
2. A report published on 31 December 2024 by the UN Human Rights Office found that Israel’s pattern of deadly attacks on and near hospitals in Gaza has pushed the healthcare system to the brink of total collapse and called for the protection of hospitals and health care and for independent, thorough and transparent investigations of all incidents of attacks on health care in Gaza.
  [note] OHCR. Pattern of Israeli attacks on Gaza hospitals raises grave concerns – report. 31 December 2024. Available at: https://www.ohchr.org/en/press-releases/2024/12/pattern-israeli-attacks-gaza-hospitals-raises-grave-concerns-report
3. The EU High Representative/Vice-President and the Commissioner for Crisis Management issued a statement calling for attacks against health-care workers, hospitals and ambulances in Gaza and the West Bank to end. They also condemned the use of hospitals for any purposes other than medical and reiterated that all parties to a conflict must respect international humanitarian law.
  [note] ECHO. Palestine: statement on attacks on medical and civilian infrastructure in Gaza and the West Bank. 20 May 2024 Available at: https://civil-protection-humanitarian-aid.ec.europa.eu/news-stories/news/palestine-statement-attacks-medical-and-civilian-infrastructure-gaza-and-west-bank-2024-05-20_en
4. The WHO Eastern Mediterranean Regional press briefing on 04 December 2024 highlighted the increase of health needs in the region and that in 2024 more aid workers were killed than in previous years – most of these deaths occurring from large-scale warfare and mass civilian losses in Gaza and Sudan.
  [note] WHO Eastern Mediterranean Region. Regional press briefing on health emergencies. 04 December 2024. Available at: https://www.emro.who.int/media/news/regional-press-briefing-on-health-emergencies-4-december-2024.html
5. The WHO called for an immediate and lasting ceasefire and the removal of the obstacles to the delivery of urgent humanitarian assistance into and across the Gaza Strip in statement on 03 May 2024. It also called for the sanctity of healthcare to be respected and for parties of the conflict, who have the coordinates of health facilities, to actively protect health facilities and ensure that these facilities remain accessible to patients, health workers and partners.
  [note] WHO. Rafah incursion would substantially increase mortality and morbidity and further weaken an already broken health system. 03 May 2024. Available at: https://www.who.int/news/item/03-05-2024-rafah-incursion-would-substantially-increase-mortality-and-morbidity-and-further-weaken-an-already-broken-health-system
6. In a statement on attacks on hospitals and health workers in Lebanon, on 16 October 2024, the WHO reiterated calls for attacks on health care to stop and for health care to be protected at all times.
  [note] WHO. Attacks on hospitals and health workers jeopardize provision of health in Lebanon. 16 October 2024. Available at: https://www.who.int/news/item/16-10-2024-attacks-on-hospitals-and-health-workers-jeopardize-provision-of-health-in-lebanon