##

Title: Kenya Integrated Refugee and Host Community Programme (PAMOJA)
Programme Value £ (full life): £61.4 million.		Review date: February 2024
Programme Code: 300139	AMP start date: 21/11/2018	AMP end date: 31/03/2025

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024
Overall Output Score	A	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Deathrocker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/48893306.odt
Deathrocker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003027.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme
The Kenya Integrated Refugee and Host Community programme – known as PAMOJA (“Together” in Kiswahili) is a £61.4 million, 6-year (2018 – 2025) programme that was initially designed to support approximately 450,000 refugees and 50,000 host community members living in and around the Dadaab and Kakuma camps as well as Kalobeyei integrated settlement in Northern Kenya. The programme is designed to provide cost-effective humanitarian assistance and promote social economic integration between refugees and host communities – key elements to avoid refugees' migration to Europe. A component of the programme supports private sector investments designed to unlock the economic potential of refugees and their hosts in Turkana County as well as policy engagement, research, and learning.

PAMOJA contributes to UK’s longer-term vision to reduce humanitarian needs by providing solutions and building resilience for refugees and host communities. It operates within the FCDO Humanitarian Framework 2022-2025 which looks at longer term inclusion of crisis-affected marginalised groups (including refugees and IDPs) within national plans and responses. It complements UK’s core funding to the multilateral agencies and delivers the UK’s reform agenda at the country level. Furthermore, the programme is aligned to the UK Foreign Secretary’s priority on ensuring a rapid and agile UK humanitarian operation which supports the world’s most vulnerable and tackling irregular migration.
[note] UK humanitarian framework - GOV.UK

Kenya has been hosting refugees and asylum seekers since its independence (1963) and has a welcome policy to refugees. The numbers of refugees have steadily increased in the past four decades reflecting the political instability, civil unrests, and natural disasters in the countries in the Horn i.e., Sudan, South Sudan, Somalia, Ethiopia, and the Democratic Republic of Congo. For example, over the last 4 years the refugee numbers have almost doubled, which has strained the quality and levels of services being provided to refugees. Kenya currently hosts 823,932 refugees and asylum seekers with the largest numbers being from Somalia, South Sudan, and the Democratic republic of Congo. Kakuma and Dadaab were originally constructed to accommodate 100,000 and 90,000 refugees respectively and now accommodate 298,053 and 416,403 refugees with over 100,000 urban refugees. The programme has been adjusted to provide support to an increased number of refugees since it’s design.
[note] Kenya Statistics Package - 31Dec24.xlsx

Refugee management is guided by various legislative, regulatory, and policy frameworks. These include the 1951 Convention, its 1967 Protocol, the OAU Convention 1969 and the Refugees Act, 2021. The implementation of these is complemented by different processes and activities at the international and national level aimed at finding long-term solutions to the refugee. The launch of the Kalobeyei Integrated Socioeconomic Development Plan (KISEDP) in 2018 and the Garissa Integrated Socioeconomic Development Plan (GISEDP) in 2023 to integrate refugees into Kenyan society with potentially far-reaching social and economic prospects, both for the refugees and the host communities, herald a new era in refugee management in Kenya. This came after Kenya adopted the Global Compact of refugees (GCR) and its Comprehensive Refugee Response Framework (CRRF).

In May 2023, the Government of Kenya (GoK) initiated the development of the Socio-economic Hubs for Integrated Refugee Inclusion (Shirika Plan), which builds on the GCR and the CRRF.

The Shirika Plans ‘main objectives are:
1. Facilitate the gradual transition from the refugee camp management model to integrated settlements.
2. Ease the pressure on the country as a refugee host.
3. Facilitate the transition of refugee basic service delivery from a humanitarian-led approach to government-led systems; and
4. Promote refugee and host community socioeconomic inclusion for enhanced self-reliance and resilience.
While GoK ambition and commitment to implement the Shirika plan remains, there have been setbacks in finalising the plan. The Plan was initially scheduled to be launched in June 2024, however, there have been significant delays from GoK attributed to Gen Z protests. Anecdotal evidence suggests that it remains GoK priority to move forward with the plan and are currently conducting consultative forums for a launch in the first quarter of 2025. However, like any plan, the implementation will require resources, and it is not clear where the resources will come from. The Plan aligns with the PAMOJA programme as it a formalised approach by the GoK towards transforming the refugee camps into integrated settlements supporting the socioeconomic inclusion of refugees and hosting communities in Garissa, Turkana, and urban areas.

PAMOJA’s impact and outcome statements (refer to section B) remained valid with recommended changes at the output levels. Milestone targets were revised in line with the budget amendments.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, the programme scored an ‘A’ – met expectations on output scoring, with most outputs exceeding the targets set.

Output 1 was on enhanced relationship with government and other relevant policy stakeholders on refugee policy that supports social and economic integration of refugees and host communities. The output scored A+ due to the impact of the enhanced relationship of the partner with GoK and other relevant policy stakeholders on refugee policy. During the reporting period 1,661 refugee cards and 15,797 birth certificates were issued. These identification documents are especially important for refugees in accessing essential services such as education, health services, food, travel, and protection and took a lot of effort in lobbying GoK at various levels to approve and issue them. It is also important to have these documents when returning to their home countries or when applying for resettlement in a third country. 597 GoK officials were also reached through a series of sensitisation and training workshops as part of capacity building efforts on refugee rights and duties and the various roles duty bearers have in securing refugee protection as envisaged in the Refugees Act 2021 and the Refugee Regulations.

In addition, government initial steps in drafting the Shirika Plan also demonstrates government ambition and commitment to integrate refugees into Kenya society. While limited progress has been achieved, many partners working in the sector, including the UK, have been advocating, lobbying, and engaging GoK to consider this long-term solution. This will be even more important in the current operating contexts with USAID freeze and many donors projecting reduced funding.

While the programme did not include a specific indicator for the Shirika Plan, it is important to assess its possible impact on refugee management in Kenya. The Plan has potential to generate positive change if fully implemented. Government, working with UNHCR, are currently undertaking country wide consultations which will feed into the final draft of the document. While a Plan might be approved this year (2025) efforts should be geared towards making legislative changes that will allow full implementation, for example, refugees right to work, open bank accounts and have access to mobile phones.

Output 2 was on the provision of cost-effective health, food, nutrition, water, and sanitation services available and accessible to refugees and their hosts; greater use of cash-based interventions in provision of humanitarian assistance where appropriate; increased identification and resolution of protection issues; refugees supported with durable solutions; voluntary repatriation and provision of complementary pathways. The output scored an A. The use of cash for humanitarian assistance was prominent and in line with best practice. 241,378 people received unrestricted cash for health, shelter, WASH, core relief items while 593,389 refugees received food assistance through Cash Based Transfers (CBTs). These numbers exceeded the targets set out at the beginning of the year. This was attributed to the increased number of refugees needing humanitarian assistance as well as efficiency of the partners in allocation of funding. Evidence generated by the Overseas Development Institute (ODI) shows that cash transfers make refugees less likely to resort to harmful coping strategies and directly benefit the local economy and can contribute to peaceful coexistence with host communities. There was payment of premiums for 13,920 households totalling to 69,600 refugees and host community member in Kakuma refugee camp and Kalobeyei integrated settlement that enabled access to health services using the National Hospital Insurance Fund (NHIF) card. Other notable successes include 1,024 voluntary repatriations to Burundi as well as the UNHCR inauguration of a Refugee Resource Centre (RRC) with the University of Nairobi.
[note] Cash transfers for refugees: an opportunity to bridge the gap between humanitarian assistance and social protection | ODI: Think change

Output 3 was on enhanced access to livelihood opportunities including increased delivery of services by the private sector for refugees and host community. This output scored an A++ as KKCF invested in 126 businesses and supported1,275 jobs. Beyond these indicators, over 190,000 people benefited from access to improved cookstoves, over 21,000 refugees now access reliable electricity from the mini grid in Kalobeyei, about 36,000 people access healthcare products and services, and 4,600 benefit from access to water. The Biashara Centre is now operational in Kakuma, with eight service desks offering permit and license applications (in water, cyber services, trade, public health, revenue, environment, liquor retail, and agriculture).

However, the programme did not make progress on output 4 which was on increased generation and use of evidence for lasting solutions for refugees and host communities and cost effectiveness in delivery of humanitarian assistance. This output scored a C which was the same as the previous year. The key milestones for the indicators were the review of NHIF, the revisions of the refugee database to remove non-refugee residents (Kenyan citizens that are on the Dadaab refugee database) and the KKCF Medium Term Review. The output was affected by the countrywide shift from the National Hospital Insurance Fund (NHIF) to the Social Health Security Fund (SHIF) which required registration of all previously registered refugees as stipulated in the Social Health Insurance Act. Another indicator under this output was the revision of the refugee database to remove non-refugee residents - Kenyan citizens that are on the Dadaab refugee database. Although there were consultative processes between the GoK and UNHCR, as well as collective effort by the refugee donor group to engage GoK on this issue, the matter remains extremely sensitive and political with limited success. Currently there is an ongoing court case by the registered Kenyans requesting the courts to remove them from the database. The lack of progressive to achieve this output is due to external conditions, outside the programmes control such as GoK actions, political will, and bureaucracy.

While the programme attained most of the quantitative targets in terms of humanitarian support and reaching the most vulnerable, there was significant lack of progress in GoK supporting the required legislative and regulatory changes for integration of refugees as a durable solution. This is very urgent in the current context with shrinking donor funding and an increase in the number of refugees. As noted above, while the GoK took initial steps to approve the Shirika Plan limited progress was achieved – we believe this transformational and bold decision from government to integrate refugees is moving in the right direction to provide long-term solution to this protracted case load despite the speed. There needs to be more robust action by the GoK in terms of the integration pathway, beginning with regulatory changes that allow refugees to fully integrate socially and economically. This will require a shift in UK engagement to support policy engagement.

Major lessons and recommendations for the year ahead [1/2 page]
Below were the recommendations from last year and the progress made towards achieving them.

Lesson 1 – Protracted refugees caseload requires long term solutions. Refugees cannot stay in camps for their entire life. The Shirika Plan could be transformational and a dial shift if fully implemented. Any integration process requires strong political will to ensure the right legislation is in place, as well as finances during the transition phase.

Lesson 2 – Flexibility in programmes are critical, particularly in current Volatile, Uncertain, Complex, and Ambiguous (VUCA) contexts. PAMOJA has been flexible to increase the target beneficiaries and into filling important gaps in the support, for example this year the programme was able to support additional food and cash transfers at critical time when refugees were demonstrating/rioting.

Recommendation from the previous AR	Progress/achievements
Recommendation 1: Restructuring PAMOJA programme. / The programme will pivot to align to the GoK’s Shirika Plan with a focus on refugee management documents, the Refugee Act, Shirika Plan, KISEDP, GISEDP and the proposed refugee management policy as well as Gender Equality and Social Inclusion (GESI).	The humanitarian team did consider options including refugees in other long- term programmes to shift from an emphasis on humanitarian support to the socio-economic inclusion of refugees and resilience against shocks. / However, in the context with limited resource we are being realistic about achieving this recommendation. We recommend closing this recommendation
Recommendation 2: Need to Support implementation of the Shirika Plan. / The UK should consider technical assistance to support the Shirika Plan design/finalisation. Once the plan is finalised and launched in December 2024, expertise and resources will be required to implement the plans under different thematic areas. This recommendation also includes commissioning of evidence to inform policy dialogue on Shirika Plan with a focus on countrywide movement of refugees. This will support strands of the refugee policy transition, which provide a conducive regulatory environment, opens movement and other livelihood opportunities. The UK Humanitarian Framework for 2022-2025 advocates for programming and influencing at Post supported with technical assistance, rigorous research, evidence, and dissemination of learning on what works.	The Shirika Plan was not launched in December 2024 as envisioned. In 2024, there was production of evidence from a number of partners/ actors in the refugee space on the countrywide movement of refugees. The UK commissioned research on climate resilient livelihoods which supports Pillars 4 and 5 of the Shirika Plan on climate action and Sustainable Economic Development. The first draft of the report is expected in June 2025.
Recommendation 3: Leave no one behind. / The UK will continue to prioritise the primary needs of refugees, with numbers increasing in the context of fragility and climatic shocks. As Humanitarian actors pivot towards social and economic integration, the focus on basic provisions needs to underpin the shift. We will continue to use UK’s influencing capacity to advocate partners to increase funding and to do more in this space to ensure there isn’t a funding vacuum.	The programme was able to adjust significantly to accommodate increased humanitarian needs emerging from the influx of new arrivals within 2024 which saw numbers increase from 714,137 in January to the current 823,932.
Recommendation 4: Localisation / The UK will champion engagement with local partners and Refugee Led Organisations (RLOs) to build resilience and inclusion. Local organisations play a critical role in understanding contextual nuances. Additionally, refugee women-led organisations can play a critical role in identifying and supporting the specific needs of women and girls in the camps. This approach is in line with the UK’s grand bargain and current UK priorities.	The programme began initial engagement with RLOs on the production of evidence. The programme commissioned a study on climate resilience livelihoods which significantly engages refugee researchers in the production of knowledge. / The UK earmarked funding decisions this year for protection needs of women and girls.
Recommendation 5: Need to review and update the programme logical framework (LF).	Completed

Recommendations for the year ahead.

Recommendation	Responsibility	Time Frame.
Recommendation 1: Extension of the PAMOJA programme / This will enable IFC to fully implement activities. Given the nature of the Trust Fund if UK decides not to extend it will require reframing the Fund, and this will have significant impact in the programme in its final year of implementation.	Humanitarian Programme Team	April 2025
Recommendation 2: Enhanced engagement with both the National and County Governments / To fully understand the political economy for implementing the Shirika Plan. This will allow better UK policy alignment. The UK should set out periodic meetings with County Governments of Garissa and Turkana. The UK should also work with the Kenya political team to ensure current analysis of local political nuances on the Shirika plan.	Humanitarian Programme Team	September 2025
Recommendation 3: Advocacy for changes in regulatory and policy framework / Identify low hanging fruit within the legislative and regulatory framework that can make a significant difference in the full socio-economic integration, and lobby DRS to move forward in implementing the changes. These could include the provision of documentation (asylum seekers pass, refugee ID, work permits); administrative barriers in access to services, including access to financial services; backlog in refugee status determination and limitations of freedom of movement. The UK as part of the refugee donor group should add its voice to the collective push by development partners for GoK to pass the regulatory changes.	Humanitarian Programme team	September 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

There were no changes in the ToC outcome and impact indicators. The programme’s expected impact: “Refugees and host communities have increased access to basic shared services and livelihood opportunities promoting a more equitable and socially cohesive society,” remains on track and relevant.
Through UNHCR, the programme was able to increase access to services such as healthcare, WASH, GBV response to both host communities and refugees within Kakuma and Dadaab. The programme utilised cash transfers for food and non-food items. This has stimulated markets and growth within the refugee camps. Through the KKCF programme, more livelihood opportunities have been realised with support to businesses and job opportunities for both host and refugee communities.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

	Outcomes	Risk exposure / opportunities
1	An enabling legal and policy environment that supports integration of refugees and members of hosting communities.	Risk: The shared understanding on the Shirika Plan is that as the shift from encampment to integrated settlements happens, refugees will be part of the social, economic, and civil life in the host counties and municipalities. However, there are still a number of policy and administrative pain points that are hindering full socio-economic integration for refugees and asylum seekers in Kenya. These include the provision of documentation (asylum seekers pass, refugee ID, work permits); administrative barriers in access to services, including access to financial services; backlog in refugee status determination and limitations of freedom of movement. / The UK will continue to engage with GoK and relevant stakeholders to lobby for engagement and consultation of all stakeholders in the implementation of the Shirika Plan.
2	Equitable access to basic services for refugees and their hosts: lower cost of providing humanitarian assistance in the Kenya refugee operation.	Valid: / The number of refugees increased significantly to 823,932 by the close of 2024 this resulted in an increase in humanitarian needs and demand for basic services by both refugees and host communities. The programme adjusted the approach to respond to increase needs by prioritising sectors, i.e. food and protection as a minimal. / In recognition that no additional funding will be available from most donors, WFP, UNHCR and DRS are leading the development of a Differentiated Assistance Framework (DAF) that proposes providing support to refugees tailored to their specific needs and abilities rather than blanket support based on their status. This will ensure that the most vulnerable are targeted for basic humanitarian assistance while others are supported towards economic livelihoods to support transition to self-reliance and over time reduce dependency on aid.
3	Sustainable job and market opportunities created and accessible to refugees and host communities.	Valid: In 2024 the KKCF successfully attracted an additional 83 companies, the majority of which are local small and medium enterprises (SMEs). Since its launch in 2019, the program has invested in 126 businesses, created 1,275 direct jobs, and provided services to over 200,000 people. These businesses are essential to Kakuma’s development as a new municipality and highlight the region’s significant potential for economic growth. / As part of KKCF’s efforts, IFC has facilitated a $20 million Risk Sharing Facility (RSF) with Equity Bank Kenya, enabling the bank to extend loans to refugees, host communities, and vulnerable populations across 14 counties in northern Kenya. These counties include Turkana and Garissa, home to the Kakuma and Dadaab refugee camps.
[note] WFP Kenya Country Brief, July 2024 - Kenya | ReliefWeb

The plan to fully integrate refugees is a significant moment for refugees in Kenya. However, we need to be realistic that even if the Shirika Plan is approved it will take years and significant resource allocation to fully implement the Plan. The UK needs to position itself strategically to support low hanging fruit opportunities that will enable an environment for the transition.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Kenya is a stable country in the middle of several conflict affected countries (Somalia, Sudan, South Sudan, and DRC). Furthermore, climate shocks are intensifying resulting in major movement of people between countries. These factors have resulted in an increase in refugees in Kenya. Our forecast is that refugees will continue to increase in the coming year.

Enhancing economic opportunities for the refuges is critical at this as it will better prepare them for either a full integration and/or provide them with skills so they can use it if they return to their origins. The KKCF programme provides a great opportunity to maximise the benefits achieved to date. During this year, the KKCF will complete its activities and create more opportunities for the refugees and host communities.

Furthermore, as noted in this review so far, the Shirika Plan has the potential to be transformative. The UK should continue to play a critical role in influencing government to implement the Plan, and this should start by implementing legislative changes to allow freedom of movement, access to key documentation and ability to open bank accounts, etc. To achieve this, the UK will strengthen its policy and influencing/lobbying engagement, either directly or via the refugee donor group.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Enhanced relationship with government and other relevant policy stakeholders on refugee policy that supports social and economic integration of refugees and host communities.
Output number:		1	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review	Progress	Score
Outcome 1.1 Number of GoK officials reached through advocacy efforts and capacity building.	450 GoK officials reached through advocacy and capacity building.	597 GoK officials were reached through a series of sensitisation and training workshops focusing on refugee rights and duties and refugee protection which ensured better service delivery for refugees.	A+
Outcome 1.2 Number of people supported to obtain identity status documentation.	Number of Refugee ID cards: Target 450 / Number of birth certificates issued. Target: 8,000	1,661 refugee cards were issued. / 15,797 birth certificates were issued	A++

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
Overall, this output scored A+ Outputs moderately exceeded expectation.
Through enhanced relationship with GoK and other relevant policy stakeholders on refugee policy, the partner was able to make a number of gains, including an increase in the efficiency of documentation issuance such as birth certificates and refugee IDs. UNHCR continued to provide technical support to the Department of Refugee Services (DRS) by building the capacity of DRS registration staff, addressing outstanding training needs, and supplying necessary tools for registration activities.
Additionally, UNHCR assisted DRS in ongoing registration processes, such as data quality checks, litigation interviews, and Biometrics Identity Management System (BIMS) enrolment. These efforts facilitate refugees' ability to credibly demonstrate their identity when accessing services and opportunities, including financial inclusion activities.

These are critical steps to ensure full integration of refugees. While it took time and stronger lobbying, this demonstrates that it can be achieved.

Output indicator 1.1 scored A+ Outputs moderately exceeded expectation.
A total of 597 government officials including police, border officials, immigration, National Registration Bureau and DRS were trained on the new Refugees Act, 2021 and the 2024 regulations. This was done to build the capacity of the officials and to align their knowledge with the existing legal framework. The trainings provided an avenue for border officials to reach out to DRS as the main interlocuter and government agency dealing with asylum seekers and to direct new arrivals for them to receive services. Additionally, the trainings also brought new staff in these agencies up to speed on the latest developments and changes in the framework to facilitate access to asylum for new arrivals and mitigate any refoulement by the authorities for new arrivals and asylum seekers.

Output indicator 1.2 scored A++ Outputs substantially exceeded expectation.

Documentation for refugees is the gateway to fundamental rights, protection, and participation. Through technical support provided by UNHCR to DRS registration staff a total 1,661 refugee cards and 15,797 birth certificates were issued, respectively. These documents allow refugees the chance to access essential services and access livelihood opportunities. From the field visits conducted by the programme team, refugees mentioned that identification documents are very critical documents for them. They mentioned with refugee cards and birth certificates, they can access humanitarian assistance, education, open businesses, access employment with NGOs as incentive workers and qualify for resettlement.
[note] The Problem - Part Two: Documentation Challenges (Moving Beyond the Complexities of Identity Status in Kenya)

The refugee determination process can be complex and tedious with several administrative procedures and steps. To ease the process, UNHCR also supported necessary tools for registration activities, data quality checks and litigation interviews. It should not be underestimated how bureaucratic and time consuming these processes can be which often leading to delays.

Kenya’s order to close the refugee camps in 2016 resulted in stopping refugee registration except in an ad hoc stop-and-start fashion, leading to a backlog of 100,000 refugees. The DRS and UNHCR are working to clear this backlog while sensitising the refugee communities on the importance of refugee cards where thousands remain uncollected.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were changes to the indicators based on the feedback from the last AR. Past indicators looked at the number of consultative forums that had been held with government officials. The indicators were changed to reflect the outcome of the engagements such as output of the trainings as well as enhanced access to identification documents.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from last AR	Status
Continued advocacy for the implementation of the Shirika Plan. Support GoK and engage key stakeholders to adopt the Shirika Plan and have a roadmap for its implementation by 2024.	UK continued to lobby GoK and UNHCR to increase stakeholder engagement. While the progress has been slow, we have noted that the consultations have now started at county level.
Update PAMOJA log frame to incorporate outcome indicator(s) to help measure this output.	completed.

Recommendation: Enhanced engagement with the GoK and other stakeholders for advocacy on the legislative and regulatory changes that will enhance the socio-economic integration of refugees, this will include all levels of engagement from senior colleagues to technical teams.

Action: Development of an engagement plan for the Kenya Leadership Team (KLT) and Humanitarian Programme Team (PRO, April 2025) to lobby for the legislative and regulatory changes which foster the socio-economic integration of refugees.

Lesson: Influencing requires clear strategy, engagement plan and above all good understanding of the political will. The UK continued to lobby and advocate for Shirika Plan. Despite these efforts, the achievements were minimal, this was due to issues outside UK control, i.e. Gen Z and GoK fiscal pressures. In addition, at some point it was not clear if the Shirika Plan remains priority for Gok. By having a good political economy understanding and contacts with strategic stakeholders, the UK was able to understand that it remains GoK priority. But the implementation will require continuous lobbying at highest level of government and a good engagement plan in place that can be adjusted as required.

Output Title	Cost-effective health, food, nutrition, water, and sanitation services available and accessible to refugees and their hosts; greater use of cash-based interventions in provision of humanitarian assistance where appropriate; increased identification and resolution of protection issues; refugees supported with durable solutions; voluntary repatriation and provision of complementary pathways.
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR.	N

Indicator(s)	Milestone(s) for this review	Progress	Score
2.1 Proportion of refugees receiving unrestricted cash for health, shelter, WASH, core relief items and food assistance	UNHCR reaching 220,000 forcibly displaced people with cash transfers. / WFP reaching 580,000 registered refugees.	241,378 reached by UNHCR. / 593,389 registered refugees reached. Target exceeded.	A
2.2 Number of refugees and host communities receiving multi-sectoral assistance (health, protection, nutrition, WASH, food - e vouchers) - data to be disaggregated by sector, group, gender, PWD etc.	Health (NHIF) = 45,000 refugees and 1,500 host community. / Persons with disabilities (PWD) Total number of PWDs 3,000 (2,000 Kakuma, 1,000 Dadaab.) / Latrine coverage - Kakuma 65%, Dadaab 60% / Nutrition Severe Acute Malnutrition (SAM) treatment: 3,000 - Kakuma: 1,000 Dadaab: 2,000 / Best Interest Determination (BID) – Total:450 (Kakuma 400 Dadaab 50) / Sexual and Gender Based Violence (SGBV) PEP in 72 hours. 100% - / Complaints reported and resolved within reporting time. / 80% Dadaab, 65% Kakuma	Health (NHIF) = Payment of premiums 68,000 refugees 1,600 host communities / PWD receiving support Total number of PWDs is 9,211 (4,247 in Kakuma and 4,964 in Dadaab) / Latrine Coverage / Kakuma: 76.3% / Dadaab: 54%"% / Nutrition Severe Acute Malnutrition (SAM) treatment Total 6,471 - Kakuma:1,159, Dadaab: 5,312 / Best Interest Determination. A total of 484 BIAs (Kakuma -438; Dadaab - 46) were conducted. / Sexual and Gender Based Violence (SGBV) PEP in 72 hours Kakuma – 20 cases (100%) Dadaab – 31 out of 36 cases (86%) Overall is 91% / Complaints reported and resolved within reporting time. Dadaab: 67% of complains resolved. Kakuma (100%). Average resolution rate: 84%	A+
2.3 Number of refugees willing to repatriate supported to return to country of origin	300	1,024.	A+
2.4 Number of alternative legal pathways	Number of refugees accessing complimentary pathways 300	A total of 3,179 individuals departed to various resettlement countries during the reporting period.	A+
2.5 Refugees and asylum seekers benefit from modern and sustainable energy provision	New indicators: Number of people benefitting from clean energy/direct and indirect. Target 60,000	The total number of beneficiaries from the energy cookstoves was therefore approx. 38,000 (average HH of 5 pax).	B
2.6 Number of joint operational plans/assessments developed and operationalised by UN agencies and implementing partners.	A joint UN survey.	The World Bank in collaboration UNHCR and the University of California-Berkeley disseminated findings on the cross-sectional survey on refugee and host populations living in camp (Dadaab, Kakuma and Kalobeyei) and urban (Nairobi, Nakuru and Mombasa) locations. / UNHCR inaugurated a Refugee Resource Centre (RRC) at the University of Nairobi (UoN	A

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scored A Outputs met expectation. This output focuses on the delivering cost-effective multi-sectoral humanitarian assistance to refugees and host community members and appropriate inclusion of disadvantaged people using cash transfers where appropriate. Additionally, it provides one of the durable solutions for refugees by through voluntary repatriation (Volrep) to their countries of origin.
Output indicator 2.1 scored A Output met expectations.

UK leadership was crucial in the delivery of core humanitarian support to the most vulnerable using a modality that enabled displaced persons to engage in the market and exercise choice. This output was implemented by two partners- UNHCR and WFP. UNHCR surpassed its target of 220,000 forcibly displaced people receiving unrestricted cash for humanitarian support reaching 241,378 people. WFP successfully delivered CBTs via electronic vouchers to 593,389 forcibly displaced persons (including 294,274 women and girls) in Dadaab and Kakuma refugee camps, exceeding the initial target by 2.3%. UK funds the CBTs which enhance refugees purchasing power and stimulate economic activities in the camp markets.

The current food situation with rations at 40% poses a significant risk within the refugee camps. 53% of the refugee population in the camps are children who may develop life-long difficulties if deprived of food at vital stages in their development. The reduction in food rations increase the levels of acute malnutrition, stunting and anaemia. Therefore, UK support aimed at preventing refugees from resorting to negative coping mechanisms, such as skipping meals or reducing meal portions. It also aimed at mitigating against refugees resorting to begging, transactional sex, or early or forced marriages to be able to afford food.
[note] The New Humanitarian | Dadaab Voices: Despair as refugee food rations in Kenya slashed by 60%
[note] Refugee Welfare in Kenya: Challenges and Solutions | IntechOpen

Output indicator 2.2 scored A+ Outputs moderately exceeded expectation.

The programme exceeded expectations across all the indicators in this output. 13,920 households totalling 68,000 refugees and 1,600 host communities against a target of 45,000 refugees and 1,500 host community were enrolled and continued accessing health services using NHIF across NHIF-accredited health facilities both in Kakuma and outside Kakuma during referrals. This represents 60% of the total population in Kalobeyei. UNHCR continues to engage with Ministry of Health (MoH) on the roll out of the new SHIF which will replace NHIF. The regulations have a provision for inclusion of both refugees and asylum seekers.

UNHCR was able to exceed targets towards supporting PWDs who are particularly affected as their difficult living conditions heighten their susceptibility to risks and limit their access to services. 9,211 (PWDs) were provided with appropriate assistive devices. UNHCR was able to reach more PWDs in Dadaab due to UNHCR efforts in partnering with an organisation that collaborates with people with disabilities. Lessons from this are being implemented in Kakuma.

Latrine coverage in Dadaab was not reached due to high numbers of new arrivals (54% reached against a target of 60%) whilst in Kakuma and Kalobeyei, the targets were reached with a coverage of 76.3% and 72.6% respectively against a target of 65%.

More Severe Acute Malnutrition (SAM) cases were treated in Dadaab (5312) than in Kakuma (1,159). The increase in SAM cases in Dadaab was due to i) additional refugees arriving from Somali (78,179 refugees) ii) decrease in food rations and iii) impact of El-Nino and MAM rainfall. Refugees and asylum seekers are not able to take the recommended dietary intake of 2,100Kcal. As a result of the flooding, there were also increased diarrhoea and respiratory cases.

Socio-cultural stigma and the Somali Masala system of conflict resolution continue to hinder timely reporting and care in Dadaab. In Dadaab, 649 complaints were received of which 433 complaints resolved totalling to 67% of complaints were resolved. While in Kakuma 2,321 complaints were received and resolved (100%). The success in Kakuma is a result of more structured complaints and feedback mechanisms that includes the maintenance of regular protection counselling services across all four field posts where refugees and asylum seekers schedule appointments with UNHCR using the Kiosk Automated Services and Information (KASI), a self-service application designed to provide access to important information about their cases, allow for updates to biodata, and facilitate appointments with UNHCR staff at various service locations. Complaints and service requests were received via the Kenkaprt Mailbox (kenkaprt@unhcr.org) and the 12 complaint boxes situated throughout the camp. Dadaab has a much more complex complaints system owing to socio-cultural and religious dynamics.
[note] Continuous registration in UNHCR Operations – UNHCR – Guidance on Registration and Identity Management
Output indicator 2.3 scored A+ Outputs moderately exceeded expectation.
Cumulatively for 2024, 1,024 individuals were repatriated to Burundi against a target of 300. From October 2023, Sub-Office Kakuma has been assisting the Uganda operation with creating voluntary repatriation (volrep) cases to facilitate the repatriation of several hundreds of onward movers registered in Kakuma who spontaneously departed to Uganda to benefit from repatriation to Burundi. However, the volrep process in Kakuma is marred with challenges related to irregular data activities which make the process of maintaining accuracy and integrity of the data difficult. UNHCR has been continuously engaging and training DRS on maintaining accurate data.
Output indicator 2.4 scored A+ Outputs moderately exceeded expectation.
As a result of enhanced collaboration with partners and stakeholders, significant strides were made across multiple pathways, offering refugees opportunities for education, labour mobility, private sponsorships, and family reunification. Against a target of 300 refugees accessing complimentary pathways, a total of 3179 individuals departed to various resettlement countries during the reporting period.
Output indicator 2.5 scored B Outputs moderately did not meet expectation.
Energy supply tends to be the most serious environment-related issue associated with refugee camps. In Kakuma Refugee Camp for instance, where firewood is the main source of fuel, the competition for the dwindling natural resource base can be a trigger for tension between the refugees and host communities. In this situation, environmental degradation is thus inevitable, and the impacts can be long lasting and difficult to reverse.
UNHCR worked with three local NGOs- two in Dadaab and one in Kakuma to produce energy saving stoves which were provided to new arrival households and vulnerable families. The number of stoves produced was 7,600 (5,200 in Dadaab) targeted 7,600 households including 500 host community households. The total number of beneficiaries was therefore approximately 38,000 (average household of 5 people). Due to the increased number of refugees in Kenya last year, the target was not met as the partner pivoted towards providing lifesaving support.
Output indicator 2.6 scored A Output met expectations. UNHCR continued to work collaboratively with other agencies to ensure its operations are underpinned by evidence. UNHCR inaugurated a Refugee Resource Centre at the UoN which will function as a hub for research and knowledge exchange on forced displacement and statelessness.
[note] University of Nairobi and UNHCR launch Refugee Resource Centre, to foster research and policy changes on forced displacement | UNHCR Africa
The Centre, jointly supported by UoN and UNHCR, is set to bridge the gap between academia and practitioners on forced displacement, becoming a research hub that will feed into public policy and practice. The establishment of the Centre is significant due to Kenya’s pioneering transformative approach to refugee management and the Shirika Plan. Therefore, there is expectation that the centre will learn lessons from the Kenya process to share globally.
The Centre will undertake a range of activities, including socioeconomic research on forced displacement, facilitating the use of and creating new pipelines for the microdata library, organising policy dialogues, running a young leaders’ program, facilitating the selection of research topics for students to encourage evidence generation on forced displacement, and organising an annual conference on the Shirika Plan.
UNHCR and the World Bank released the Kenya Longitudinal Socioeconomic Study of Refugees and Host Communities(K-LSRH) which is the first nationally comparable survey of registered refugees and hosts in Kenya, offering a unique opportunity to inform the socioeconomic integration of refugees, including the Government of Kenya's proposed shift from camps to integrated settlements. Unlike previous surveys that lacked comparable host-refugee data, K-LSRH includes both refugee and host communities, providing comprehensive insights into their living conditions and challenges. The survey instrument addresses various household level, individual-level, and children’s outcomes. It delves into less understood themes such as psychosocial wellbeing and trust, aiming to advance knowledge and programming in these areas.
[note] Kenya Longitudinal Socioeconomic Study of Refugees and Host Communities (K-LSRH): Summary of Findings from Wave One
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during this review period.

Lesson: Programme flexibility is critical and important to respond to context changes. The programme was able to respond to urgent increase in needs. For example, i) Dadaab saw a significant increase of refugees due to instability and climate chocks in Somalia. The programme was able to increase support to Dadaab via UNHCR. ii) decrease in food ration to 40% resulted in several demonstrations in the camps, the programme supported WFP to increase food ration from 40% to 45%. While this is not a significant increase it contributed to reduce number of malnutrition cases and associated diseases.

Output Title	Enhanced access to livelihood opportunities including increased delivery of services by the private sector for refugees and host community (data to be disaggregated to include people with disabilities and other special needs groups).
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR.	N

Indicator(s)	Milestone(s) for this review	Progress	Score
3.1 Number of initiatives established to provide innovative cost-effective services, sustainable jobs and market opportunities for refugees and host communities.	Number of jobs supported 350 (100 women) by December 2024. / 70 businesses supported (2025 target) by December 2024	Number of jobs supported. / 1,275 (417 jobs women, 858 men) and / (450 refugees, 825 host communities.) / 126 businesses supported.	A+

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, this output scored A++ Outputs substantially exceeded expectation.

This output supports the transition from humanitarian to developmental strategies and KKCF supports private sector investments that unlock the economic potential of refugees and their hosts in the Kakuma-Kalobeyei. The IFC is the lead KKCF implementing partner and is supported by the Africa Enterprise Challenge Fund (AECF) as a down-stream partner. KKCF has invested in 126 businesses creating 1,275 jobs ((417 women, 858 men) (450 refugees, 825 host community)). This is a significant milestone for the region and the refugees considering the regulatory challenges for them in accessing employment.
[note] The Kakuma Kalobeyei Challenge Fund (KKCF) is IFC’s first refugee and host community focused program in sub-Saharan Africa. It enables private investment with the goal of unlocking the economic potential of refugees and their hosts in the Kakuma Kalobeyei refugee-hosting area in Kenya’s Turkana County. KKCF is a program of the International Finance Corporation (IFC), implemented with the Africa Enterprise Challenge Fund (AECF), Turkana County Government, and UNHCR. https://kkcfke.org/

Output indicator 3.1 scored A++ Output substantially exceeded expectation.

As noted above the KKCF made significant progress in supporting businesses and creating jobs in a complex environment. Beyond these indicators, over 190,000 people benefited from access to improved commercial cookstoves, over 21,000 refugees now access reliable electricity from the solar mini grid in Kalobeyei, about 36,000 people access healthcare products and services, and 4,600 benefit from access to water. Microfinance institutions have disbursed 3,944 loans whose value is $1,956,544. Companies in the agribusiness sector have reached 2,888 farmers with capacity building on vertical agriculture, beekeeping, and poultry-keeping.

The Biashara Centre is now operational in Kakuma, with eight service desks offering permit and license applications (in water, cyber services, trade, public health, revenue, environment, liquor retail, and agriculture. The Centre serves on average 100 customers per month. However, to be fully functional it requires national government services for example immigration and civil registration services be moved to the centre, something that IFC continues to lobby government. The delays in having the national services could be due to financial pressures to increase the number of civil servants required. If fully functional, it will serve as a vital hub offering essential government and business services under one roof, catering to both Kenyan citizens and refugees residing in the region.

KKCF continues to be at the forefront of boosting women businesses. The 2024 women’s day celebrations in Kakuma featured podcast recordings for the Africa Enterprise Challenge Fund (AECF)/KKCF social media platforms by six of KKCF's investee companies — KDII, Rama Beauty, Blue Light Prince Academy, Kakuma Kalobeyei Medical Centre, Hydroponics, and Inkomoko. These recordings highlighted the companies' positive impact on women, aligning with the year's theme of ‘Investing in Women.’ Each company shared the unique strategies they use to empower women within their industries, showcasing their dedication to creating a more sustainable future for all.

The businesses continue to create both intended and unintended impact. For example, Hive Limited which was awarded a grant to Turkana Beekeeping Enhancement Project is supporting inter-community integration and promoting peaceful coexistence between communities living along the Kenya-Uganda border. The excellence centres are providing opportunities for training and spaces for selling harvested honey, providing socio-economic alternatives to farmers’ pastoralist activities.

IFC assists larger companies by offering customized market and feasibility assessments, conducting scoping and business development missions to identify potential barriers to investment, linking them to IFC financing, and offering technical assistance (TA). Within the period, IFC assisted Goodlife pharmacy which offers human telemedicine, vaccination, and specialized services to different agency staff, sale of drugs, vitamins, and beauty products in Kakuma. As the branch has reached its growth trajectory in Kakuma, the company is interested in exploring opportunities in Lodwar (Turkana County), Garissa, and Wajir. There was a scoping mission to Garissa whose findings are currently under review.

The UK undertook two field visits, and it witnessed the impact of these programmes on communities and refugees. Several women shared their challenges in accessing finances/credits from banks. With the support from programme, they were able to take their businesses to next stages, employing several people and expanding the businesses. For example, Mrs Mary started by having a small tailor employing 2 staff and managed to expand the business to employ 10 staff. She is now opening a school which will teach various courses, tailoring, plumbing, bookkeeping etc.
[note] Fictitious name

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the review period. KKCF has adapted to the prevailing context, thus providing flexibility in managing this component. KKCF has requested an extension to realise full implementation of activities and ensure a responsible exit. Recommend PAMOJA is extended by one year to support KKCF complete its activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations for the year ahead	Responsible	Timeframe
Continue engaging and lobbying KKCF to leverage these gains and potentially replicate the model in Dadaab refugee camp. While this seems to be almost impossible due to security issues, there will be elements that can be adapted.	Humanitarian Programme Team	October 2025

Lessons: Companies funded by grant at initial phase of the business have a higher chance of success as it enables them to access commercial credit much easier. This allows them to expand businesses and grow. The UK team witnessed this during the field visits. Whereas companies within the Local Enterprise Development (LED) are not required to provide matching capital, all the top-up companies committed to invest their own funds into their businesses. The majority of KKCF beneficiaries continue to inject additional capital into their businesses. Therefore, key conclusion could be, small start-ups require a capital injection from the start to access commercial credit.

Private and development capital delivered through innovative financial instruments has the flexibility and potential to unlock new funding to meet short and longer-term needs and development goals. It is able to catalyse lasting systemic change by addressing the underlying causes of humanitarian crises. This kind of humanitarian impact finance offers a new paradigm: one that leverages public and private capital to support market-based, scalable, and sustainable solutions to intractable problems.

Output Title	Increased generation and use of evidence for lasting solutions for refugees and host communities and cost effectiveness in delivery of humanitarian assistance.
Output number:		4	Output Score:	C
Impact weighting (%):		15%	Weighting revised since last AR.	NA

Indicator(s)	Milestone(s) for this review	Progress	Score
4.1 Number of collaborations by FCDO and by implementing partners with research institutions, private sector to enhance use of evidence in programme planning and implementation.	1 - Review of NHIF	Review yet to happen due to the shift from NHIF to SHIF.	C
4.2 Planning based on evidence leading to targeted assistance for vulnerable persons of concern.	Revisions of the refugee database to remove non-refugee residents - Kenyan citizens that are on the Dadaab refugee database.	Consultative processes ongoing between UNHCR and DRS on the revision of the database. (A highly political issue which has been ongoing for years)	C
4.3 Number of feasibility studies and scoping missions conducted by the IFC to inform implementation of KKCF.	KKCF – Mid Term Review	KKCF – Mid Term Review (MTR) completed by IFC.	A

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scored C - Outputs substantially did not meet expectation. This output was affected by the reforms in NHIF as it transitioned to SHIF as well as political nuances around removing Kenyans from the Dadaab refugee database. There has been collective effort by the refugee donor group to engage GoK on this issue, however the matter remains very sensitive.
Output indicator 4.1 scored C Output substantially did not meet expectation.

This process was not undertaken following the change of the health insurance system under the NHIF Act to Social Health Insurance (SHI) following the gazettement of the Social Health Insurance Act (SHIA) on 19 October 2023, and the issuance of the Social Health Insurance Regulations. The transition phase has been a challenge country wide including various court cases challenging the provisions of the new law. Eventually the SHIA replaced the NHIF Act with registration of users including employees commencing from October 1, 2024. In the refugee context, UNHCR experienced challenges transitioning beneficiaries to the new system due to the changes in configuration of the data base and the different individual data. Despite the challenge, UNHCR efforts succeeded in transferring the data and some beneficiaries are already benefitting from SHI. UNHCR continues to lobby government to ensure more refugees are registered.

Output indicator 4.2 scored C Output substantially did not meet expectation - Double registration refers to the process where genuine Kenyans, particularly those living near refugee camps such as Dadaab, were incorrectly registered as refugees. This rendered them ineligible for national identity cards. Without these vital documents, they have been unable to access basic services such as opening bank accounts, securing business premises, receiving healthcare, education, or formal employment.

The issue of removing Kenyans whose fingerprints were captured in the refugee data base continues to generate debate from the political class. It has been linked to security as well as political numbers / potential voters from the Somali community within Northeastern Kenya.

Development partners, UNHCR and WFP, continue to lobby the GoK to complete this exercise linking it to sustainability of humanitarian assistance under the differentiated assistance model.

Output indicator 4.3 scored A - Output met expectation.

KKCF underwent an extensive and consultative MTR. The mission results show that KKCF can be considered a successful pilot initiative, a novel and complex intervention in a challenging context. It has effectively delivered on most of its output targets across the various workstreams and has resulted in some important outcomes having promoted: (i) increased private sector activity in the Kakuma and Kalobeyei (KK) area; (ii) a more conducive business environment and investment climate in Turkana (West); and (iii) improved awareness of market opportunities in the Kakuma area. The Program has also supported access and opportunities for refugees and women, as well as promoted some initial environmental and social learnings among investees. Finally, prospects for sustainability are mostly favourable, but access to funding especially remains a challenge.

The MTR outlined the following lessons the need for sufficient time (and patience) not only to engage, select and support private sector enterprises, but also to build partnerships and stakeholder relationships, raise awareness and foster understanding within the local community. It also highlights the benefits of a supportive comprehensive local policy framework and the importance of local government support and ownership. In an area with generally low skill levels building community awareness and investee capacity is essential. Preparatory analytical work has been crucial for an understanding of the local market and context towards informing the design and implementation of the Program. Despite this positive progress there has been challenges with limited absorption capacity, especially among local enterprises.

The MTR has informed the decision for KKCF to extend the programme so that activities are completed and lessons learned for future ICF programming. To address the challenges in funding, in June 2024 Equity Bank and IFC signed a Risk Sharing Agreement (one of the first of this kind in the world) to collaborate and expand Equity Bank's loan portfolio in 14 fragile counties in Kenya, including underserved refugees and host communities. The facility will support a maximum portfolio of $20 million with at least 20% of the portfolio catering to individual, microfinance, and SME loans for refugees and host communities from Kakuma and Dadaab. The facility will be complemented by an advisory program aimed at improving Equity Bank’s microfinance lending practices and enhancing utilization of the facility.
[note] Equity Bank and IFC Partner to Launch $20 million Facility for Refugees and Host Communities | Equity Bank Kenya

Describe any changes to this output during the past year, and any planned changes because of this review.
There were no major changes to this output in the last year. However, the KKCF Medium Term Review recommended a no cost extension of the programme for one year.

Action: The PAMOJA programme should consider an extension to enable IFC complete the programme activities. (SRO, April 2025).

Lesson: To be realistic about achieving outputs that requires political will, for example the revision of the database. While the programme should set ambitions targets, it is important to bring realism and ensure there is enough time to adjust/amend if political will is not realised.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

The refugee camps are in two of the poorest counties in Kenya characterised by weak basic service delivery, insecurity, and strong climate impacts (droughts and floods). There was an increase of 15% in the number of new arrivals due to conflict and climate impact in the bordering countries – this increased the needs. PAMOJA’s cost drivers are linked to the operational location, security, transport costs, materials and supplies, and refugee influxes. In addition, the increase in the cost of living and high inflation also impacted the programme cost drivers.

VfM performance compared to the original VfM proposition in the business case.

On balance, the programmes VfM performance aligns with the Business Case indicators and is satisfactory across the four core VfM criteria – economy, efficiency, effectiveness, and equity – taken in aggregate.

VfM criteria	VfM action
Economy	In Dadaab, 20% of all the energy for water abstraction is solar powered as an alternative to diesel powered. Although this fluctuates depending on weather conditions (between 17%-22%) during the year, savings from the use of solar range from 30-40% depending on the season. In Kakuma, 17 out of 21 boreholes have been solarised, using hybrid systems while in Dadaab 25 out of the 28 boreholes have been solarised. Devices to monitor water use online have been installed in both Dadaab and Kakuma providing real-time monitoring. This is substantial improvement and with an increase in the price of diesel significantly increased the cost of delivering water in the camps. / Both UNHCR and WFP used cash transfers to deliver humanitarian assistance as opposed to in kind provision of food and non-food items. Evidence has shown that cash transfers is more efficient to deliver than in-kind modalities, suggesting that they might be more cost-effective on average. In addition, studies undertaken in Kenya suggests that mobile money cash transfers, such as Bamba chakula, are the most efficient transfer method as it is convenient and safe.
Efficiency	UNHCR has continued to align its staff and administrative costs for greater efficiency in the last three years with the staff & admin costs dropping from 41% in 2023 to 34% in 2024. UNHCR undertook a staff rationalisation exercise and made changes to ensure that more direct funding is targeted to project activities rather than operation costs. / WFP works closely with UNHCR to utilize robust biometric verification systems for accurate beneficiary identification. This ensures that only eligible refugees receive CBT entitlements, preventing waste and maximizing resources directed towards those most in need.
Effectiveness	WFP actively build the capacity of traders within refugee camps. This not only fosters market development and profitability but also enhances value for refugee customers through potentially improved product selection and pricing. / Financial inclusion for refugees: WFP capitalizes on existing policy frameworks approved by the GoK to promote financial inclusion for refugees. This empowers beneficiaries and contributes to a more sustainable future. / Through the KKCF programme, the UK has invested 2 million pounds in the multi-donor trust fund which has resulted in significant gains in unlocking the economic potential of refugees and their hosts in the Kakuma Kalobeyei. Through the programme, 1,275 jobs have been created from the support of 126 businesses supported.
Equity	WFP and UNHCR are committed to the principle of “Leaving No One Behind” and upholds inclusivity in all aspects of delivering support. The programme recognizes specific vulnerabilities faced by various refugee groups including persons with disabilities, women at risk, the elderly, orphans, and vulnerable children (OVC), and child-headed households. The special groups receive prioritized attention during registration and distribution. Out of the 593,389 reached by CBT, 294,274 were women and girls. This is 49.6% of the population. / Cash Based Transfers are also able to cover dietary deficits for women and girls, a 2024 WFP baseline revealed high food insecurity among refugees and that the in-kind food basket lacked adequate dietary diversity, particularly for women and girls of reproductive ag due to a lack of fortified blended foods.
[note] Cash and In-Kind Transfers in Humanitarian Settings: A Review of Evidence and Knowledge Gaps | World Food Programme

Assessment of whether the programme continues to represent value for money.
The programme presents a strong VfM and continues to achieve its milestone targets at the output level and on course to achieve its forecasted outcomes. Progress to date show that the programme continues to deliver humanitarian interventions efficiently in line with cost drivers reaching the most vulnerable.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk of this programme remains ‘Cautious.’ The risk appetite statements for all categories were last updated in November 2024 and it’s in line with the BHC (British High Commission) Nairobi’s overall risk appetite as below.

Risk category	Programme risk rating	BHC risk appetite		Risk category	Programme risk rating	BHC risk appetite
Strategy & Context	Major	Receptive		Safeguarding	Moderate	Cautious
Policy & Programme Delivery	Major	Receptive		Financial & Fiduciary	Moderate	Cautious
Public Service Delivery and Operations	Moderate	Cautious		Reputational	Moderate	Cautious

During this period there were no residual risks above the programme’s and/or BHC Nairobi’s risk appetite requiring escalation. UK and partners continue to pro-actively review risks and mitigation measures.

The programme team maintains a programme risk register which is reviewed quarterly to assess validity of risks and effectiveness of mitigation measures. The programme team also discusses risk management with the implementing partner on a quarterly basis where emerging risks are identified and mitigation measures instituted. Routine visits to project sites by FCDO the UK team are also used as a risk management tool.

Overview of key risks

Risk 1: GoK does not prioritise implementation of the new Refugee Policy and does not commit sufficient resources to ensure the shift from refugee camps to settlements. Last year the GoK showed mixed commitment in implementing the refugee policy shift. There have been significant delays in finalising the Shirika Plan. Given how critical it is for the programme to achieve its outcome and impact it is important to continue monitoring the risk and be realistic on the timelines. FCDO The UK continues to engage with GoK and other development partners to ensure this remains a key priority.

Risk 2: The increased number of refugees and shrinking donor funding means that service delivery especially for new arrivals may be compromised. This year the food rations went down to below 40% and there were anecdotal reports on the deplorable conditions in Dadaab. For the year ahead, we expect Kenya to receive more refugees especially from Somali following La Nina and the implementation of vulnerability testing. WFP and UNHCR are working on the differentiated model of assistance to ensure the most vulnerable are prioritised for core humanitarian assistance.

Risk 3: The impact of the US aid freeze on the humanitarian landscape in Kenya. Currently the education, child protection and livelihoods sectors are severely impacted. The sudden cessation of humanitarian services will adversely impact both refugees and host communities who rely on US funded programmes for accessing basic services.
The UK will aim at supporting more sector wide reforms which support the transition from a reliance on humanitarian aid towards a more integrated approach into GoK systems such as envisioned in the Shirika plan.
UNHCR, WFP and IFC have a zero tolerance for inaction approach to tackling safeguarding issues and this applies to their downstream partners. Strong measures are in place to report and respond appropriately when reports arise. The complaints and feedback mechanisms include the use of ‘’The Kiosk Automated Services and Information’’ (KASI) used by both refugees and host community members for this purpose is easily accessible. Reports garnered from the mechanism are investigated by the partner and reported at the quarterly risk meetings held for the programme.

Despite this, minimal safeguarding complaints have been raised. The programme team continues to emphasize to partners, including downstream partners, on the need to test out their safeguarding systems, refresh the relevant policies and ensure that they create a safe environment for reporting.

The programme aligns with the Paris Climate Agreement on environmental protection. The programme assesses climate and environment risks, impacts, opportunities, and the steps taken to mitigate any harm.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Performance of partners and FCDO, notably on commercial and financial issues.

PAMOJA’s delivery partners are the United Nations High Commission for Refugees agency (UNHCR) and World Food Programme (WFP) delivering humanitarian assistance and the International Finance Cooperation (IFC) addressing private sector solutions through a multi-donor trust fund, the Kakuma Kalobeyei Challenge Fund (KKCF). PAMOJA also has 12 downstream partners.

The overall performance of all partners (UNHCR, WFP and IFC) during the review period is satisfactory. They provided timely and quality quarterly and bi-annual reports. Programme management meetings between FCDO and the partners were held on quarterly and bi-annually to review risks and overall progress.

The quality of financial management is satisfactory across the board. Partners appreciated the predictability of funding during this FY as compared to previous years, thus allowing them to effectively plan and manage resources for timely delivery. Programme Team undertook field visits to Kakuma, Kalobeyei and Dadaab and met with downstream partners who reported their ability to plan and coordinate better given the stability of FCDO funding.

PAMOJA’s implementing partners UNHCR, WFP and IFC have partnership agreements with their downstream partners. The agreements set out terms of engagement including execution of contract: reporting, monitoring, and financial obligations, expected ethical, integrity and personal conduct, risk management and other essential requirements.

The Fraud Risk assessment for the programme is updated periodically. We consider fraud risks regularly and discuss with partners quarterly. Despite this, there has been limited fraud reporting – we continue to discuss with partners on the need to be vigilant. As part of the due diligence refresh done on UNHCR and WFP, we sought assurance on their fraud reporting mechanisms including how they are cascaded to partners and emphasised on the need to report any suspected cases to FCDO. UNHCR has strengthened their risk capability and has invited FCDO to attend their national integrity working group which monitors and oversees risks throughout UNHCR programming. This will provide sufficient assurance of their risk management processes including with downstream partners.
Financial performance
The overall PAMOJA budget is £61,450,807 represents a 27% reduction from its original value of £84M. The table below provides a detailed breakdown of cumulative spend to date with all partners against the budgetary allocations.

Summary of programme finances

Programme	Approved BC amount	Anticipated spend by end of FY24/25	Available headroom for FY25/26
PAMOJA	£84.0m	£61.45m	£22.55 m

Partner	Approved BC Budget	Total Budget	Spend to date	Spend FY 24/25
UNHCR	35,000,000	34,120,547	34,120,547	7,800,000
WFP	25,000,000	25,282,700	25,282,700	6,400,000
MDTF/IFC	5,000,000	2,000,000	2,000,000	0
Tripline (M&E)	500,000	47,560	47,560	0
Virtual & Prog IRF	12,500,000	0	0	0
Voluntary Repatriation	5,000,000	0	0	0
Policy	1,000,000	0	0	0
Total	£84,000,000	£61,450,807	£61,450,807	£14,200,000

UNHCR and WFP have continued to forecast on timely manner i.e. quarterly, and we have regular discussions about financial performance during our quarterly meetings.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
The UK conducted three field missions to Kakuma and Dadaab within this reporting period.
The main observations included:
- The positive impact of businesses funded by IFC, particularly on women entrepreneurship and smaller businesses.
- Potential impact on increase of malnutrition and health diseases.
- The Shirika plan requires a lot of engagement, most stakeholders either did not know about the Plan or believe GoK was introducing it to reduce the services.
- Innovative programming on livelihoods, for example IOM is working on climate resilient farms for the host communities which are changing the ecosystems of village.
- The need to enhance integration in our programming between host communities and refugees.
- Disability remains a huge challenge in the camps. there was a good practise in Dadaab where mothers took children with disabilities to learning centres for playing and/or rehabilitation.
- While funding was not enough, refugees are receiving basic services – including a level 4 hospital in Kakuma which is caters for both refugees and host communities.
- Beneficiaries confirmed their preference for cash where possible instead of in-kind support. This allows them the freedom to prioritise a mixed food intake.
- There were several refugees awaiting their status approval, some of them have been in transit centres for over years without accessing schools for children, while they live in very poor and crowded shelters.

The observations were shared across post and with the refugee donor group. Findings from the mission enabled the crafting of the key messages between development partners and the GoK including the need for wider consultations and sensitisation on the Shirika plan among all stakeholders.
Observations from field visits also allowed programme team to take informed decisions regarding funding priorities, for example we prioritised core humanitarian assistance especially for new arrivals in the camp.
The partners (KKCF, UNHCR and WFP) routinely share their internal monitoring data through periodic reports. The information was verified by FCDOs monitoring visits. For example, the KKCF MTR highlighted key successes of the programme but also drew attention to the fact that programme activities would not be completed by the December 2024 initial timeline. A no cost extension has been sought to enable to programme complete the overdue components.
Evidence - the UK commissioned research through the UK East African Research Hub on climate resilient livelihoods among refugees and host communities in Kenya and Uganda. The research is currently ongoing. Its overall objective is to explore how livelihoods/self-reliance programmes for refugees and host communities (E.g. cash and graduation models, Market-systems development) can better support resilience to extreme weather events as a result of climate change in Kenya and Uganda.
This will enable the humanitarian teams in Kenya and Uganda to understand the key climate related trends, risks, and vulnerabilities. Recommendations will be shared with wider humanitarian partners and may inform UK global programming.
In August 2024, a report based on the Kenya Longitudinal Socioeconomic Study of Refugees and Host Communities was launched. The study is a component of the Kenya Analytical Program on Forced Displacement, a collaborative effort by the World Bank, United Nations High Commissioner for Refugees (UNHCR), and the Centre for Effective Global Action (CEGA). Key messages from this enhanced the evidence across this report.
The study revealed that protracted displacement was highest in Dadaab, where 95% of refugees have lived for over a decade. When it comes to reasons for displacement, 73% of refugees attributed their displacement to at least three reasons, with insecurity being the most dominant factor.
Poverty levels were found to be high in the camps, with multidimensional poverty up to 80% higher than in urban areas. Severe multidimensional poverty was highest among Turkana hosts, affecting 86% of those surveyed. Food insecurity was also a major concern, with the highest levels observed among Turkana hosts and refugees. In Nairobi, 67% of refugees and 55.9% of hosts face food insecurity.
The study highlighted the crucial role of aid and assistance in refugee communities as well as the needs of the host communities. Nearly 100% of refugee households in camps receive food aid coverage. However, gaps remain in social assistance coverage among hosts. In terms of employment, only 14% of camp refugees are employed, compared to 43% of camp hosts. The situation is better for urban refugees, with 54% employed, which is significantly higher than in camps.

Audited financial statements.
Audited financial statements are aligned to a calendar year and will be received after December 2024. The auditors’ opinion from the last audit statements was ‘unqualified.’

Date of last narrative report	February 2024	Date of last audited annual statement	May 2024

Asset management
N/A. No assets have been purchased under PAMOJA.

PAMOJA downstream partners