Business Case – June 2024

Summary Sheet

Portfolio/ Business/Country Plan Summary: / This programme will be a core delivery mechanism for Goal 5 in the British Embassy Kyiv’s Country Plan - UK efforts strengthen accountability and inclusivity reforms, in line with the stated aspirations of Ukraine’s people and Government, bolstering its resilience during the war and laying the groundwork for effective post-war recovery, reconstruction, and Euro-Atlantic integration. / This business case is also aligned with the mission statement of the draft UK Recovery and Reconstruction Strategy for Ukraine (2024-2029) which states that the UK will support accountable and inclusive Ukrainian institutions that enable a more resilient Ukrainian state, drive faster and deeper economic and social recovery, and support Ukraine’s Euro-Atlantic trajectory.

Title: Ukraine – Governance Reform Programme
Programme summary: / To help Ukraine win the war, make progress on conditions for membership of the EU and NATO, and lay the foundations for long-term resilience and recovery, the Governance Reform Programme (GRP) will support the Government of Ukraine to create independent, effective, and accountable institutions that deliver for Ukrainian people. Working in partnership with close-minded allies such as the US, EU and the G7 Ambassadors’ reform group, GRP will advance long-term reform in the areas of anti-corruption and rule of law and support Ukraine’s ambitious digitalisation agenda, while deepening UK understanding of ‘what works’ on reform in wartime through the creation of a political economy analysis facility.
What is the rationale for UK Aid spending?: / Without more independent, effective, and accountable institutions, the success of Ukraine’s war effort, economic and social recovery, and Euro-Atlantic trajectory are all at risk. The UK has been supporting Ukraine’s institutional reforms financially since 2016 and has contributed to some notable successes. But reform is a long-term endeavour, and the full-scale invasion is severely straining the Government of Ukraine’s human and capital resource. Though government ambition and public demand for reform have risen with the prospect of EU and NATO membership, international assistance is needed. This programme builds on the evidence and lessons learned from the past nine years of UK ODA support to Ukraine’s reform and proposes continuing to engage in complex areas where we have a comparative advantage on anti-corruption reform, judicial reform, and digitalisation, with reform efforts strengthened across the portfolio due to a new political economy analysis facility. / Support to Ukraine is the UK’s top foreign policy priority. The Governance Reform Programme contributes to the delivery of: / The UK-Ukraine Bilateral Security Agreement / The 100-Year Partnership / Ukraine Recovery and Reconstruction Strategy / Independent Commission on Aid Impact (ICAI) 2024 recommendations
Programme Value: Up to £38m		Country/ Region or Sector: Ukraine
Department/Country Office confirmation of review processes
Contact name		Rosie Coombe, rosie.coombe@fcdo.gov.uk
Threshold for final approval of Business Case: Director General
Date of Approval of Concept Note:	31/10/2024	Name and role of Approver / Minister Doughty, Minister for Europe / Minister Dodds, Minister for Development
Date of Approval of Business Case:	06/12/2024	Name and role of Approver / Jonathan Allen, DG Defence & Intelligence
Programme Code:	AMP Start Date: January 2025	AMP End Date: June 2028
Overall programme risk rating:	Moderate

## Strategic Case

What has been done to date

The Good Governance Fund (GGF) started in 2016 providing support for economic and governance reform in Ukraine and across the ‘Eastern Neighbourhood’ to advance and consolidate the reforms needed to enhance UK security and prosperity and counter Russian aggression. It became a Ukraine-specific programme in April 2022, just after Russia’s full-scale invasion of Ukraine. Following a period of reflection and lessons gathering, this document makes the case for its successor in the governance reform space, the Governance Reform Programme (GRP). This programme builds on the successful components tested under GGF over the past nine years, and provides a more streamlined, strategically coherent and higher ambition approach to the reform of Ukraine’s institutions, tailored more explicitly to Ukraine’s wartime context and needs, while carefully balancing both short-term and longer-term priorities. The economic reform components of GGF have predominately been folded into our new economic development portfolio.

Historical context

When Ukraine gained independence in 1991 with the collapse of the Soviet Union, institutional reform started from a low base. The functional effectiveness of the institutions Ukraine inherited was severely limited. Institutions were hollowed out by neo-patrimonial leadership, meaning narrow interest groups and oligarchs regularly exercised undue and corrupt influence on state institutions and decision-making processes, including the privatisation of state-owned assets. Most state institutions were oversized, corrupt, inefficient, and filled with public sector staff who either lacked the skills or motivation to deliver.

Following the 2014 Revolution of Dignity, new reform dynamics emerged. There was a clear need for reform (economic crisis and Russian aggression in the East); sustained pressure from below (an energised civil society); new resources within the system (entry of committed reformers with greater integrity); and increased external pressure (mobilised and invested international community endowed with significant leverage through the IMF programme, macro-financial assistance, and aid).

The 2014-2019 period saw a number of institutional success stories. Some argue Ukraine saw more institutional reform in this period than in the 20-plus years of its post-Soviet existence (with others arguing the 2019-2024 period is even more significant).Key success stories include: establishing an independent and competent National Bank of Ukraine that stabilised the economy; energy sector and Naftogaz reform that reduced a major source of corruption; defence sector reform that started to professionalise Ukraine’s military; the creation of new anti-corruption institutions; public procurement reform that saves billions of dollars for Ukraine’s state budget; decentralisation that started to devolve power and budget to the local level; and, the beginnings of Ukraine’s digital transformation.
[note] Introduction | Chatham House – International Affairs Think Tank

Though some reforms proceeded rapidly others, such as judicial, engendered resistance from vested interest. And though these achievements were impressive, continued frustration with corruption and the conflict in the East, meant they did not meet the expectations of the Ukrainian people. This part explains why in 2019, outsider, Volodymyr Zelenskyy, won the Presidential election on a ticket promising renewed reform and a real fight against corruption.

The February 2022 full-scale invasion of Ukraine has created challenges for the reform of Ukraine’s institutions. International and domestic demands on Ukraine are high and the Government is under pressure to balance responding to the immediate needs of the war with the long-term reform agenda. However, their institutional capacity is strained due to conscription, high workloads, and budget austerity during wartime. Vested interests have been weakened but remain powerful. We are witnessing an increasingly “unicentric” model of governance and the centralisation of decision-making. And martial law has resulted in a tighter hold of information, resulting in less transparency over public spend and decision-making.

However, the war also provides opportunity for reform progress. It has interrupted oligarch’s domination of key sectors, there are historically low tolerance levels for corruption, and there is unprecedented national consensus on Euro-Atlantic integration and strong civic activism. The EU, NATO, and IMF conditionalities and private sector feedback all incentivise continued reform, especially on fundamental reform areas such as tackling corruption, strengthening the rule of law, building state capacity, and improving the investment climate.

Zelenskyy’s administration has remained committed to reform despite the war. In many areas, reform has been accelerated, albeit with increased dependence on international partners. On anti-corruption for example, on the eve of the European Commission Summit in Brussels where the issue of Ukraine’s candidacy was decided, the Ukrainian Parliament adopted the long-awaited Anti-Corruption Strategy of Ukraine 2021-2025. Immediately after the adoption of the strategy and National Agency for Corruption Prevention (NACP) started working on the development of the State Anti-Corruption Programme (SACP). Other acute problems were also resolved, such as the lack of leadership in 4 out of the 5 anti-corruption institutions. In 2022, new Heads of SAPO, NABU, ARMA and the High Anti-Corruption Court were appointed. And in 2024, the Government appointed a new Head of the NACP.

Need for UK intervention

The UK is a long-standing, trusted partner of Ukraine. Pre-full-scale invasion, the National Security Council Strategy for Ukraine established the UK’s vision of an independent, resilient, and prosperous Ukraine. Since the invasion, our bilateral partnership has deepened significantly and we are often viewed as Ukraine’s diplomatic partner of choice, aided by our reputation of being a ‘first mover’ on military support. The UK-Ukraine Bilateral Security Agreement commits Ukraine to “continuing institutional governance reform in the interest of building a resilient and inclusive democracy”. The proposed 100-Year Partnership reinforces this message, by highlighting the importance of governance reform and identifying opportunities to strengthen cooperation. For example, on judicial reform, our Ministries of Justice will work together to improve the functioning of the penal system in criminal justice and improve the procedure of enforcement and ensuring respect of court decisions.

To capitalise on the opportunity for institutional reform and limit the risk of backsliding, there is a clear role the UK can play to strengthen the independence, effectiveness, and accountability of the Ukrainian state, which supports us to meet our wider objectives, such as:

- Ensuring Ukraine’s resources go to the war effort: tackling corruption in public spend is critical to ensuring resources are allocated to and reach the areas they are most needed. Ensuring risks around reform and corruption are managed is also important to reducing instability which left unchecked, could spill into the military efforts.
- Attracting international investors: reform is critical to Ukraine’s economic outlook and creating the conditions needed for Ukraine to attract private sector-led growth and investment, to fund Ukraine’s large-scale reconstruction needs and to break Ukraine’s dependence on international assistance. British companies regularly cite challenges of corruption and selective application of the law as reasons for not doing business in Ukraine. Evidence suggests that past anti-corruption efforts undertaken by Ukraine yielded benefits equivalent to 6% GDP.
  [note] Ukraine's Fight Against Corruption: The Economic Front (Ier.Com.Ua)
- Ensuring Ukraine meets its Euro-Atlantic obligations: reform is critical to meeting criteria around EU, NATO and OECD accession and meeting IMF, World Bank, and US conditionalities. The Government of Ukraine’s Reform Delivery Office showed that Ukraine is expected to undertake 240 reform-linked activities in 2024 and there is a need to ensure that these are underpinned by meaningful implementation. Progress is critical to maintaining the confidence of the international community and the military and financial support they provide.
- Meeting the aspirations of Ukrainian people: who consistently vote in favour of reform. January 2024 data shows that Ukrainians seek a fully consolidated democracy, membership in Euro-Atlantic institutions, and a society based on human rights and the rule of law, with 90% viewing corruption as a threat to their way of life.
  [note] Ukraine's Views on the War and Its Future | National Democratic Institute

The UK’s draft Recovery and Reconstruction Strategy for Ukraine sets out what the UK brings to the reform space and how it should engage. It recognises that on reform, our strong relationship with Ukraine lets us offer advice and challenge as a critical friend. We are viewed as influential, trusted and well placed by the GoU to support them to deliver on some of the more controversial and hard-to-reach reforms. Our funding is reinforced by our soft skills, technical expertise, political analysis and influence, as well as our growing reputation as an honest broker and convener with GoU, civil society, media, and the private sector. Unlike the key players (IMF, EU, World Bank and the US), we do not set conditions for our support, but we align our reform work with others particularly through the G7 Ambassadors’ Reform Group.

The Recovery and Reconstruction Strategy highlights the importance of a “twin track approach” that allows the UK to respond to Ukraine’s immediate needs while laying the foundations for the future by strengthening the reform agenda. It sets out the UK’s ambition on reform, which is to sit just behind, and in alignment with the EU and the US (the “mega donors”). And it recognises that although the UK will not be able to match their levels of funding, we will use our trusted voice to advance critical reforms and defend institutions against attempts from vested interest to undermine their independence. In addition, while others do ‘big ticket’ technical reforms, we will offer support that pays attention to political economy to catalyse more difficult reform and make technical inputs more effective. The Strategy states that “the UK will not be a full spectrum donor” and, over the next five years, we will prioritise and focus on areas of reform where the UK has a comparative advantage and interest.

The design process required difficult decisions about where the UK should not engage (e.g. on decentralisation, public administration, and public financial management (PFM) and public investment management (PIM) – though a decision on future support to PFM/PIM will be taken in the first year of programming). The selected approach recognises that Ukraine’s reform journey will be long and complex. Ukraine has not had long to build integrity into its institutions and to learn from what works. Our approach therefore favours continued engagement in areas where we have engaged historically and where we have seen progress. However, it also recognises that Ukraine’s reform environment is complex and successful programming will depend on being able to respond to windows of opportunity. We will therefore initiate a new research component, retain flexibility to respond and build in regular reflection points to ensure our resources are directed where they are most needed.

In these selected areas, why is UK support needed?

Anti-Corruption Reform

Since 2014, Ukraine has been making great progress on reform, climbing Transparency International’s Corruption Perceptions Index from 142/172 in 2014 to 104/180 in 2023, which placed Ukraine among 17 countries demonstrating their best-ever performance. But despite these advances, 94% of Ukrainians still consider it a pervasive issue. Ukraine’s anti-corruption ecosystem is relatively nascent and there is more work to do to ensure anti-corruption bodies have clear mandates (backed by sufficient legal standing), full independence and autonomy, and the resources to deliver as well as to mainstream anti-corruption across all government ministries. Historically, international support on fighting corruption has focused on national-level systems, and sub-national institutions in particular need financial and technical resource to help them establish the necessary anti-corruption safeguards, particularly ahead of Ukraine’s reconstruction.
[note] Ukraine - Transparency.org
[note] National Corruption Perceptions and Experience Poll 2023 - USAID/ENGAGE
[note] OECD, 2018

Corruption risks vary according to sector. Though the UK has a comprehensive approach to tackling corruption, one area we are particularly interested in due to the high state corruption risks relates to the control and management of Ukraine’s 3,300 state-owned enterprises. Many of these are loss making and poorly managed with excessive direct state involvement. SOEs make it harder for the private sector to compete in key sectors and often have links – directly or indirectly – to oligarchs. If captured, a Ukrainian SOE can generate income through procurement fraud, sales fraud, direct theft and embezzlement, and all with the central government covering operating losses. The State Property Fund estimates that SOEs had combined losses of $5bn in 2019. Their reform is intricately linked to EU accession and the Ukraine Plan, which aims to create a ‘functioning market economy’ and a level playing field between private companies and SOEs.

The UK is interested in tackling corruption as it undermines Ukraine’s democracy and is important if Ukraine is to progress from a ‘limited access order’ in which a narrow group of powerful individuals exercise political and economic dominance, to an ‘open access order’ based on a wider set of interests. Corruption has deeply corrosive effects on public trust in institutions and the ability of the GoU to fulfil obligations to its citizens. It impedes Ukraine’s economic growth and prosperity by preventing businesses from competing on even terms, and it slows development hampering Ukraine’s ability to mobilise revenue and facilitate growth and investment. Furthermore, it undermines delivery of our objectives across our portfolio. There is particular concern around the corruption risks in Ukraine’s reconstruction, which is projected to cost up to $486bn. Tackling corruption is critical to maintaining domestic and international support.
[note] The cost of rebuilding Ukraine and other urban transformation news | World Economic Forum (weforum.org)

In the Independent Commission of Aid Impact Report on Ukraine 2024, it was recommended “that FCDO’s new anti-corruption programme should include support for Ukraine’s anti-corruption bodies to manage risks relating to reconstruction.” This programme responds directly to this recommendation by supporting the Pro-Integrity programme we co-designed with the US to work with anti-corruption institutions at the national- and sub-national level, with a component focused on supporting the Ministry for Restoration and the State Agency for Restoration and Development of Infrastructure of Ukraine (SARDI) to manage corruption risks associated with reconstruction. As stated above, we can bring our role in the G7 and strong relationship with the Government of Ukraine to offer support and have difficult conversations when needed, and our strong policy and programming join-up allows for mutual reinforcement of diplomatic and programme objectives. We are seen as long-term supporters of this agenda, as we have engaged on anti-corruption since 2015 when we lent support to Ukraine’s nascent anti-corruption institutions. More broadly, the UK has a strong track record as a global leader in the fight against corruption. We have made substantial investments to strengthen the evidence on corruption and identify what works, including through the world-leading Anti-Corruption Evidence programme and the U4 Anti-Corruption Resource Centre; the resources of which will influence our programming inputs.

Judicial reform

1. Historically Ukraine’s judicial system has been a tool of control rather than one upholding the law. There has been some progress under Zelenskyy’s administration. In the European Commission's 2024 assessment, they concluded “Ukraine has some level of preparation in the functioning of the judiciary”, citing their efforts to implement the reform of selection of Constitutional Court of Ukraine, the resumption of the HQCJ’s role in selecting judges, and restarting the process of vetting for judges with involvement of the Public Integrity Council. But it has typically been one of the more difficult areas of reform for the following reasons:
  [note] Ukraine 2024 European Commission Report, October 2024: 1924a044-b30f-48a2-99c1-50edeac14da1_en
  1. Corruption, political interference, and low public trust: The level of trust in the judiciary among the population remains extremely low (61% of distrust), and the perception of corruption is high (4.52 out of maximum of 5). Political actors still interfere in judicial proceedings and the governing bodies still contain some judges appointed during the Yanukovych era who oppose reform. In the last few years, under-funding and administrative challenges have led to delays in judicial vetting and appointments.
    [note] Динаміка довіри соціальним інституціям у 2021-2023 роках https://kiis.com.ua/?lang=ukr&cat=reports&id=1335&page=1
    [note] https://nazk.gov.ua/uk/bez-kategoriyi/dovira-do-instytutiv-suspilstva/ 6 Дослідження НАЗК
  2. Structural issues: The efficiency of the administration of justice in 2023 decreased by almost 8% compared to 2022. As of May 2024, there were over 2,233 judicial vacancies according to the HQCJ website. The judicial governance system is complicated, with different institutions having overlapping mandates. In recent years, the judicial system has been underfunded. And legal and judicial training is seen as inadequate, undermining the overall quality of the judiciary.
    [note] Аналітичні таблиці щодо стану здійснення правосуддя за 2023 рік
  3. The impact of the war: The war has damaged infrastructure and reduced human capacity. It is also contributing to new cases which risk overwhelming the justice system as currently configured. As of March 2024, the Office of the Prosecutor General had registered about 124,000 criminal proceedings related to war crimes. While the focus of the Ukrainian legal system on seeking accountability for war crimes (including CRSV) is admirable, the burgeoning caseload may undermine the speedy and fair resolution of non-war related cases.

Ukraine’s judicial reform matters to the UK as it is critical if Ukraine is to meet its EU and NATO accession conditions, so it is often at the top of G7 agendas. It is closely linked to Ukraine’s business environment, as low trust in Ukraine’s judiciary is perceived to be a major barrier to foreign investment and economic development. In turn, it could contribute to the recovery and reconstruction of post-war Ukraine, the country’s economic growth and generate opportunities for UK businesses. Judicial reform is also part of deepening Ukraine’s democratic transition, as it contributes to creating transparent, accountable and predictable state institutions that deliver for citizens. It is critical to ending a culture of impunity, making Russia accountable for war crimes (another UK priority) and is tightly connected to other reform agendas, such as anti-corruption. Higher public trust in the judiciary and a speedier and fairer resolution of the population’s legal and judicial disputes have the potential to strengthen the social contract between Ukrainian citizens and the state.

The UK also has a lot to offer Ukraine on judicial reform. We are highly engaged in this sector and respected for the expertise we bring. In 2021, a 6-member Ethics Council was established to check the integrity of member of the HCJ and a retired British judge, Sir Anthony Hooper, sat on this panel bringing British expertise and credibility to the process. The inclusion of international experts in important integrity-building processes is now seen as best practice in judicial reform. Because of the UK’s strong reputation, peer-to-peer exchange is a key part of the (draft) 100-Year Partnership, which demonstrates how we are aiming to deepen collaboration between our justice ministries, prosecutors’ offices, and private justice and legal service sectors. GRP’s judicial offer – to support advocacy and the operationalisation of key judicial reform priorities – should therefore be viewed within a wider ‘package’ of support the UK is providing Ukraine on rule of law.

Digitalisation

There is strong political will behind the country’s digital transformation, kick-started by the September 2019 launch of the Ministry of Digital Transformation (MDT) and its subsequent outpouring of strategies and initiatives that support regulating, opening, and spurring innovation in the digital space.

Ukraine’s digitalisation has been a catalyst for many of Ukraine’s other successful reforms. For example, when party financing legislation was re-introduced, donor-backed digital solutions helped the National Agency for Corruption Prevention (NACP) process a backlog of 400,000 cases. Digital reform helps the Government to deliver higher quality and more equitable services. The launch of the citizen portal, Diia, with over 20m users, vastly improved citizen-to-government interaction by supporting Ukrainians to pay taxes, register vehicles, access medical records, open bank accounts, register births, receive childcare and other benefits, and start businesses. It has been a lifeline for displaced persons throughout the war, allowing citizens to access government services no matter their location. Digital reform is also helping to combat state corruption and deliver value for money. The UK-funded development of Ukraine’s e-procurement system, ProZorro, is estimated to save GoU $1bn a year. And the UK-supported, Digital Restoration Ecosystem for Accountable Management (DREAM) - a transformative website/app providing “end-to-end” transparency for all infrastructure reconstruction projects (currently worth $4.7bn) – allows for radical oversight and accountability.
[note] Digital-resilience-in-a-time-of-war-Final.pdf (brookings.edu)

Though Ukraine has made strong progress on this agenda and achieved impressive results, the demands and the opportunities are enormous. The Government of Ukraine’s ambition was to make 100% of public services available online by 2024. Though this has been delayed by the war, the ambition remains. There is more work to do to harness the opportunities the digital reform agenda can bring and to mitigate the risks, such as those relating to the digital divide, meeting General Data Protection Regulation, and overcoming restrictions relating to the control of information under martial law. Ukraine still needs support in developing its digital infrastructure and equipping its workforce of the future to maintain and build Ukraine’s digital technologies.

The UK has supported digital reform in Ukraine since 2016. We were an early supporter of the ProZorro system alongside the US through our support to the Transparency and Accountability in Public Administration Programme (TAPAS) and a first mover on backing the transparent reconstruction tool, DREAM, which has since become institutionalised within the GoU’s Public Investment Management systems. TAPAS is a well-known brand in Ukraine and strongly associated with US/UK support. As the UK looks to strengthen its partnership with Ukraine on digital and e-governance (e.g. through TechBridge and the proposed 100-Year Partnership), our support to the ‘new TAPAS’ – the Digital Transformation Activity (DTA) – will be another key asset, providing opportunities to demonstrate our commitment to this agenda and build linkages to wider UK initiatives.

What support will the UK provide and what will the programme achieve?

GRP will provide up to £38m over 3.5 years. It will add value to BEK’s existing portfolio by creating a streamlined and coherent approach to Ukraine’s governance reform to achieve the impact level statement in the Theory of Change (see page 14 in the Appraisal Case): Ukraine has more independent, effective and accountable institutions that deliver for people and business, are less corrupt and able to tackle corruption and further along their Euro-Atlantic integration.

1. The programme will contribute towards the following long-term outcomes:
  1. Ukraine’s institutions better harness digital opportunities to deliver higher quality services and prevent corruption
  2. Ukraine’s institutional anti-corruption capability is strengthened at national and sub-national levels
  3. Ukraine has improved judicial reform legislation and strengthened rule of law institution(s)
  4. The UK is better able to track and influence reform conversations.

It will do this by:
1. Continuing to support Ukraine’s anti-corruption reform by building the capacity of Ukraine’s anti-corruption architecture at the national and sub-national level, with a focus on supporting the National Agency for Corruption Prevention to work with all line Ministries to bolster their anti-corruption control and compliance (more info in Box 1, p.14). For the first year at least, it will also tackle corruption by supporting state-owned enterprise reform.
2. Continuing to support judicial reform in a strategic way focused on UK USP. Since the start of 2024, we have undertaken thorough scoping to identify future pathways. Future engagement could focus on a) an operational component focused on the continuity of support to transparent judicial selection and institutional capacity building of the High Council of Justice, High Qualification Commission of Judges and the Disciplinary Inspectors Service, and b) an advocacy component focused on reform of the Supreme Court, the establishment of a High Administrative Court, and Bar Reform (more info in Box 3, p. 16).
3. Continuing to support Ukraine’s digitalisation by helping to digitalise government services, make the Government of Ukraine more transparent, advance its procurement systems, and support small- and medium-sized businesses via digitalisation (more info in Box 2, p. 15).
4. Helping to increase UK influence on reform through the establishment of a Political Economy Analysis to help us identify constraints and opportunities for better leveraging our policy and programmes in support of reform (more info in Box 4, p. 17), as well as supporting targeted secondments (e.g. to MDCP, OECD) and UK-hosted reform conferences.

Coherence with broader UK programming in Ukraine

GRP will directly contribute to Goal 5 of BEK’s Country Plan – UK efforts strengthen accountability and inclusivity reforms, in line with the stated aspirations of Ukraine’s people and Government, bolstering its resilience during the war and laying the groundwork for effective post-war recovery, reconstruction, and Euro-Atlantic integration.

GRP will complement a broad range of UK interventions in Ukraine. By fighting corruption in government and building the capacity of the state, and surfacing political economy constraints and opportunities, GRP will have positive benefits to programmes interacting with key ministries. More specifically, GRP links to:

1. Good Governance Fund: GGF’s technical assistance facility, the Managed Fund, will operate until March 2026 to support wider reform efforts linked to helping GoU with macro-economic analysis and technology and innovation (see Annex A).
2. [Proposed] Governance programme on democratic resilience and political inclusion: this complementary governance programme (the two combined will make up BEK’s governance portfolio) will aim to build trust in local and national government in Ukraine, by developing more representative and inclusive processes, so martial law limits people’s freedoms only as absolutely necessary and Ukraine’s political system takes account of the widest possible set of stakeholders. The theory of change and the issues that will be tackled will be different, but complementarities will be sought.
3. Economic Recovery and Reconstruction: GRP will help to tackle some of the core issues (e.g. judicial reform, procurement) which are holding back foreign direct investment and are key to unleashing private sector growth. It will also help to ensure integrity in Ukraine’s reconstruction efforts, including within the private sector, thereby complementing the objectives of our private sector investment programme (TIGER) and reconstruction programme (FIRE).
4. Social Recovery: Social recovery has a strong focus on institutional reform and lessons can be shared between the programmes. GRP will help to fight corruption and digitise government services which will help the government to deliver higher quality services, including some social services. The new PEA facility could help to inform institutional reform within the Ministry of Social Policy.
5. Energy: British Embassy Kyiv has provided £100m in aid to the energy sector since 2022. Historically, energy has been one of the sectors in Ukraine more vulnerable to state capture and corruption. Therefore, there is clear potential for our anti-corruption work to have an energy focus and work with Ukraine’s energy institutions and companies to prevent and detect corruption. Our PEA facility will be able to explore corruption concerns in more detail.
  [note] Source: OECD.
6. Illicit Finance: SOCnet have been working to combat Russian Illicit Finance by working with Ukraine to improve their ability to identify, investigate and prosecute illicit financial flows. There are opportunities to find linkages with the anti-corruption reform work under this programme, such as on anti-money laundering and support to the State Financial Monitoring Service.
7. ISF Strategic Communications and Disinformation programming: The anti-corruption work will support Ukraine’s anti-corruption agencies to use evidence to communicate progress on anti-corruption in a way that doesn’t feed Russian disinformation narratives. This workstream will be aligned with ISF’s work to combat disinformation and StratComms support to the Government of Ukraine.
8. Defence procurement: The UK was instrumental in setting up Ukraine’s non-lethal procurement agency and adding functionality to ProZorro on non-lethal defence procurement. We will continue working with the Special Defence Adviser to find opportunities to reinforce their objectives.
9. Rule of law: The UK is working closely with Ukraine’s legal system to aid judges and prosecutors in holding Russia to account for war crimes committed on Ukraine’s territory. We will work with ISF-funded interventions to ensure they benefit from GRP’s strengthening of Ukraine’s judicial system.

How does the programme comply with counter-terrorist financing and anti-money laundering legislation?

The risk of financing terrorism in the programme is low. Financial flows are clear, and finance will be delivered through USAID and reliable international and local partner organisations, with strong oversight mechanisms judged to be sufficiently robust to ensure full compliance with UK legislation and policy on terrorism and money-laundering.

How does the programme comply with the FCDO’s principles on climate and environment?

The impact on climate change and the environment in this programme is low. In line with the Paris Agreement on Climate Change, the programme team will track possible impacts on climate and environment through ensuring all projects:
1. Cohere with National Plans on Climate: The SRO/PRO will consider how GRP components align with BE Kyiv commitments under the Paris Agreement and related national plans.
2. Assess risk: As the programme is providing technical assistance there is unlikely to be direct climate or environment impacts though there may be secondary impacts including risks related to the provision of hardware and air travel. Due Diligence Assessments and project approval mechanisms will consider and where feasible, seek to mitigate these risks.
3. Do not support Fossil Fuels: The programme will not support initiatives that are linked to investments in fossil fuels.
4. Are reviewed for ICF Financing: GRP programme team will review grant spending to determine if any of the grants meet the criteria to qualify as ICF (e.g. support to fighting environmental corruption), though this is unlikely in most the areas of intervention.

Through engagement with the new CLEAN helpdesk – who are strengthening their relationship with the Centre of Expertise for Democracy and Governance – the SRO/PRO will also seek opportunities to better understand the impact of governance programmes on climate and the environment.

How does the programme comply with the Partnership Principles?

A key factor that will impact the effectiveness of the Governance Reform Programme will be the approach and commitment of the Government of Ukraine. Though this programme will not provide direct financial support to the Government of Ukraine, it will be providing substantial technical assistance and some in-kind support. The programme will use the four Partnership Principles to assess the appropriateness of this type and level of support throughout the lifetime of the programme, monitoring this by considering Ukraine’s commitment to:
1. Reducing poverty and achieving the sustainable Development Goals (SDGs).
2. Respecting human rights and other international obligations.
3. Strengthening financial management and accountability and reducing the risks of funds being misused through weak administration or corruption.
4. Strengthening domestic accountability.

How does the programme comply with the Gender Equality Act and Public Sector Equality Duty?

Gender Equality and Social Inclusion (GESI) considerations will be mainstreamed throughout. Work on digitalisation will focus on closing Ukraine's 'digital divide' and work on fighting corruption will integrate GESI policies and operations into anti-corruption institutions. Specific workstreams will seek to support veterans. For example, the anti-corruption work plans to find ways to engage veterans as watchdogs overseeing recovery and reconstruction processes and work on digitalisation plans to support veteran-owned businesses. We expect as a minimum that all components will be gender sensitive and able to demonstrate that they are doing no harm to any individual or community and effectively safeguarding against sexual exploitation, abuse, and sexual harassment (SEAH).

Specific actions will be taken to strengthen the programme’s gender and social inclusion (GESI) offer. This will include:
1. Ensuring that GESI analysis has been undertaken by each delivery partner.
2. Ensuring that each delivery partner responds to this analysis via a GESI strategy or equivalent, which shows how they are mitigating any perverse GESI impact as well as seeking to promote better GESI outcomes in their programming.
3. Ensuring that each delivery partner has GESI-related indicators in their results framework.
4. Building a GESI learning objective into the programme’s MEL plan.
5. Drawing on the advice of British Embassy Kyiv’s Social Development Adviser who will allocate 5% of their time to supporting GRP to meet GESI objectives.

Building on feedback in Annual Reviews, GGF made a concerted effort to mainstream GESI into its governance and economic reform work. Due to the continuation of some of these components, we will continue to build on the lessons learned and progress made. This includes:
1. Anti-corruption: Pro-Integrity’s design was underpinned by GESI analysis. They have recruited a GESI Advisor, have developed a GESI strategy, and have GESI activities in their workplan and indicators included in their results frameworks to monitor progress. The GRP programme team will monitor their progress.
2. Digital reform: DTA is already underpinned by thorough GESI analysis and has a robust GESI strategy in place, which we helped to develop and reflects UK priorities and ambition on GESI. We will continue to provide oversight of the implementation of this strategy.
3. Judicial: Recognising we could be missing opportunities to promote GESI within our judicial reform work, in 2024 we conducted a GESI review of our judicial programme. This identified a range of intervention options (e.g. training on GESI-friendly legal drafting, embedding GESI training in legal education programmes). The next phase of our work on judicial reform will build on these learnings and may include GESI more comprehensively in the advocacy work.
4. PEA: All PEA will include GESI considerations.

How does the programme ensure conflict sensitivity?

The full-scale invasion has caused a significant shock to the governance system of Ukraine. Despite the severity of this shock, Ukrainian institutions have proved exceptionally resilient. However, the speed at which officials have had to respond to the crisis and the subsequent imposition of martial law has exposed structural weaknesses. Components of the GRP will address some of the driving forces of governance weakness and instability within the Ukrainian system by building fairer power-sharing structures and effective and legitimate institutions. Such efforts to reform the governance space challenge the status quo and there is clear potential to create conflict through the shifting of established power dynamics between groups of people, threatening vested interests, removing established mechanisms of political patronage, and reducing financial gain. We will ensure these are captured in risk registers and will monitor them closely with delivery partners.

GRP is committed to mainstreaming a conflict sensitive approach across all pillars of the Programme. GRP will deliver through trusted vehicles which have a track record of delivering results in a conflict-inflicted environment since 2022. Though we have predominately supported national-level systems through our historic programming, this programme (e.g. through Pro-Integrity) will have a greater focus on the sub-national level and in areas that are closer to the frontline. This poses new delivery risks, and the programme team will work closely with our delivery partners to manage these. We will be able to help assess delivery through use of the Embassy’s Third-Party Monitoring programme, VERITAS. GRP will continue to refresh its understanding and learning by commissioning research (e.g. through the PEA facility). Interventions will be designed and implemented in close cooperation and consultation with national, local and international partners in a transparent and inclusive manner.

Key risks to the success of the programme

Given the situation in Ukraine, both EECAD and BEK have a receptive appetite and high tolerance for risk. We do not expect to work outside of the FCDO Ukraine’s bilateral risk appetite. The key risks are as follows. The mitigation strategies are included in the Management Case in para 94.
1. Reputational: There are reputational risks related to working in politically sensitive areas and challenging vested interest could have implications for the UK’s relationship with the Government of Ukraine.
2. Strategy and context: Government priorities can shift quickly, particularly if there’s a deterioration in the war effort. We may experience resistance in some reform areas (e.g. due to power of vested interest and/or centralised decision making) which blocks progress or undermines work in other areas. Sudden changes in leadership can result in a change of political will.
3. People: an over-stretched Government and low absorption capacity may impede progress. Internally, we need to ensure we have adequate UK Embassy resourcing to deliver.
4. Policy and programme delivery: Due to the close partnership and joint programming with the US there are political and delivery risks relating to a potential divergence in approach on these issues and programmes becoming affected by possible tensions in the US-Ukraine relations. We will also need to ensure the portfolio retains a balance between supply- and demand-led and that reform strategies do not become too technocratic and remain sufficiently attentive to difficult underlying political economy factors.

## Appraisal Case

Solution options appraisal

This section appraises the different ways of responding to the need for anti-corruption reform, judicial reform, digitalisation, and enhancing UK influence on reform, as set out in the Strategic Case. The main options that have been considered in the development of this business case are:

Option 1 – Do nothing
Option 2 – Costed extension to the Good Governance Fund
Option 3 – Support to anti-corruption reform only
Option 4 – Focus on a mix of anti-corruption reform, judicial reform, digitalisation, and methods to increase UK influence on reform

Option 1 – Do nothing

Under this option the UK would scale down and exit from our support to long-term reform in Ukraine in the areas of anti-corruption reform, judicial reform and digitalisation. We would exit from the longstanding joint programming relationship we have with the US. This option could impact our relationship with the US, and it would have symbolic implications to the Government of Ukraine and to our international partners – demonstrating a stepping back from and lack of belief in Ukraine’s reform agenda. It would also mean we are unable to deliver on our strategic ambition laid out in the UK-Ukraine Bilateral Security Agreement, 100-Year Partnership, and Country Business Plan.

Option 2 – Costed extension to the Good Governance Fund

This option would involve renewing, or slightly streamlining, the 10-12 components of the GGF focused both on governance and economic support. The programme remit would remain broad, and the programme would continue to run as a ‘Fund’ supporting a wide range of activities under the same (or similar) delivery models. The benefits of this approach would be that we would keep the GGF brand that has been established over the past ten years, and it would allow the continuation of successful components initiated under GGF. However, as demonstrated in the Development Capability Review Data Pack, when the GGF oversaw 13 components, it had the second highest number of components per SRO, PRO and PM to manage across the entire organisation. GGF was also a regional (EECAD) programme that became bilateral (Ukraine) soon after the full-scale invasion, meaning it inherited some priority areas and ways of working from being a regional programme. Designing a new programme provides the opportunity to reflect on what has been trialled and learned under the GGF and to focus on proven or promising components that provide a more focused and coherent programme. With British Embassy Kyiv’s growing economic development portfolio, there is also an opportunity to consolidate economic reform work into one team and to review options for future programming on the economic reform side in that space. As such, this option is not recommended but it should be noted that all the components that are recommended are continuations of, or successors to, GGF programming.

Option 3 – Anti-corruption support only

This option would involve a more streamlined reform programme, providing a narrow and strategic focus that goes for depth rather than breadth and therefore has the potential to dig deeper. Under this option we could increase our contributions (e.g. up to 20% total contributions) to existing anti-corruption support (Pro-Integrity and Digital Transformation Activity) making us more equal partners and making fighting corruption part of our ‘identity’ on reforms. We also considered establishing standalone programme on anti-corruption giving us full control on the type of support provided. But we decided we didn’t have the capacity to do this, it would complicate coordination in an already crowded space and we feel aligned to the type of support the US are providing.

Using existing anti-corruption programmes would be light on management as the US take on the programme management burden, which would free up valuable resource to support delivery in other parts of the portfolio. However, with the US programmes, due to the history of our partnership and the value of the wider contributions we make – including as a joint advocate on politically sensitive issues – we receive full credit and branding rights and influence for meeting 10% of programme costs. An increased contribution to 20% will not, therefore, result in a change in activity or in better value for money for the UK. The programmes are also already large scale: $90m for Pro-Integrity (2023-2027) and $150m for DTA (2024-2029). While we assess that GoU has the absorption capacity to support the programmes, we do not believe additional financing will result in better results for programme recipients. In practice it is also more likely that the USA will simply adjust its own payments to accommodate increases/decreases we wish to make so the total programme value will remain the same.

Focusing solely on anti-corruption reform would also involve a number of trade-offs. We would lose our breadth of engagement and ability to influence a range of governance reform areas and the G7 Ambassador’s agenda, notably on judicial. If all our money is allocated to USAID programmes, we will have less flexibility to respond ‘as the UK’ on issues that really matter to us, and we may lose some of the reputation we have built e.g. as a donor that responds quickly (thanks to the responsiveness of the Managed Fund), or as a valued player in certain thematic spaces e.g. judicial. We also increase the risk of being too dependent on US priorities and programming, should these alter. Focusing purely on anti-corruption would close us off from engaging in the areas of justice and public finance and investment management. We recently conducted a thorough review of our PFM options and while we have elected not to fund PFM beyond SOERA at this point, an anti-corruption programme would shut down future opportunities for engagement on PFM and public investment management (PIM).

Option 4 – Focus on a mix of anti-corruption reform, judicial reform, digitalisation and increasing UK influence on reform

This programme would involve selecting an integrated package of anti-corruption reform, judicial reform and digitalisation as our strategic entry points. This option would involve refreshing our approach to judicial reform. We undertook extensive XHMG consultation to reach this decision. It was decided that judicial reform was too tightly linked to Ukraine’s other reform areas and was too important a reform area to not engage, particularly as it is often a priority of the G7. Feedback from the EU and US was that they valued the UK’s contributions in this space. We therefore recommend continuing and more information on our programming options is in Box 3 below. Under this option we would also establish a fourth component, focused on tracking and increasing UK influence on reform agendas. This would be achieved via a mix of secondments (to the OECD and Donor Platform), the hosting of international conferences on reform, and the establishment of a political economy analysis facility that allows us to catalyse more difficult reform and make technical inputs more effective. PEA underpins the ‘Thinking and Working Politically’ (TWP) approach which is regarded as a ‘high potential’ governance ‘Best Buy’ (see Box 4 below).

Option 4 presents strong interlinkages between these reform agendas, which means activities reinforce one another ensuring that our contributions are a greater sum of their parts (see Theory of Change on p. 14). For example, they would all contribute to GoU institutions becoming more independent, transparent, inclusive and rules based. They would all seek to find ways to close the space for vested interest to operate and to improve the business environment. They would all depend on oversight and accountability from civil society, media, the public and internationals. And they would all result in GoU institutions providing higher quality services – making use of digital tools to do so – to prevent wastage, improve value for money and ensure integrity in reconstruction. These reform areas align closely to the steers provided within the Recovery and Reconstruction Strategy. This option allows us to commit to areas of reform that are systemic and long-term, while having flexibility built in to respond to emerging areas. As this option allows us to achieve a streamlined, coherent and balanced portfolio on institutional reform that delivers in areas of UK comparative advantage, while allowing us to commit to meeting long-term and short-term reform needs, this is our preferred option.

Box 1: Pro-Integrity

Promoting Integrity in the Public Sector (Pro-Integrity) is a $90mn five-year UK-US flagship anti-corruption programme being delivered by DAI. Pro-Integrity aims to reduce corruption incidence and risks to build back a better Ukraine. It works to achieve this purpose by addressing three interconnected objectives:

Strengthen national-level anti-corruption institutional capacity to advance corruption prevention, detection, and deterrence.

Under this objective, Pro-Integrity will support the Government of Ukraine to undertake reforms linked to their EU and OECD integration (e.g. providing expert advice to help the GoU align anti-corruption legislation with the EU acquis), while also supporting their implementation. For example, supporting NACP to build a lobbying Transparency Registry and a Data Warehouse / Data Management Facility: a digital analytical suite that will help scan for corruption risks and identify violations. On this objective, the National Agency for Corruption Prevention (NACP) is a key interlocutor as the programme will bolster their capacity to implement, coordinate and monitor the State Anti-Corruption Programme. The institutional resilience of specialised anti-corruption and other relevant agencies will also be targeted, with support provided on communication and in other flexible and demand-led areas. For example to Ukraine’s Civil Service Agency (NAUCS) on promoting integrity across all public sector official appointments and Ministries involved in enhancing Ukraine’s beneficial ownership enforcement, implementing whistleblower management systems, and working on anti-money laundering prevention. This objective will have a particular focus on understanding the gendered impacts of corruption and promoting the leadership and decision-making role of women in anti-corruption.

Strengthen anti-corruption compliance and control in local governance.

The UK helped to guarantee the programme’s focus on the sub-national level during the design stage of Pro-Integrity. Under Objective 2, Pro-Integrity will bolster anti-corruption measures, minimising the occurrence and risk of corruption at the local level. We have been working with Pro-Integrity to refine their methodology for selecting the 75 local governments (24 in the first year) that will be supported to efficiently use scarce resources to build back better – both physically and institutionally. The programme will focus on improving institutional abilities (e.g. through the development of Integrity Improvement anti-corruption technologies (e.g. for civic participation and digital transparency) and promoting rigorous civil society monitoring – through support to NGOs and investigative journalists – to ensure local authorities are held responsible. This objective will include developing a comprehensive and sustainable approach to supporting the NACP to build the capacity of Ukraine’s (thousands of) Anti-Corruption Officers operating at the regional and local levels.

Advance transparency and accountability in resilience, recovery, and reconstruction efforts.

This objective will focus on mainstreaming anti-corruption throughout reconstruction institutions and projects. Support to the State Agency for Reconstruction and Development of Infrastructure (SARDI) will be a key part of this objective. This objective will support the development of new tools for reconstruction transparency. Support will also be provided to minimise environmental corruption risks and enhance environmental compliance in reconstruction. There will also be a focus on promoting business integrity in reconstruction, such as assisting the Business Ombudsman with defending the rights of businesses. Again, civil society engagement and participation will be promoted to safeguard integrity.
Plans), creating and implementing advanced

Box 2: Digital Transformation Activity

Digital Transformation Activity is a $150mn five-year UK-US programme aimed at bolstering Ukraine’s digital transformation to support good governance by fighting corruption, opening data, and creating new digital services; transparent reconstruction by digitising recovery and strengthening e-procurement; and economic revitalisation by creating a sustainable digital economy infrastructure and accessing digital services for businesses. It takes over from the hugely successful, TAPAS programme, described by First Deputy Minister of Digital Transformation Oleksii Vyskub as the most impactful development programme ever in Ukraine.

Digitalisation for Good Governance

Objective 1 involves fighting corruption through digitising services and making government data more transparent. DTA will support all ministries and tens of municipalities to publish data on a regular basis while also encouraging Ukrainian civil society and entrepreneurs to use open data and develop open data-based services. TAPAS helped to digitalise 43 government services and DTA will build on this progress, helping to improve people’s day-to-day lives and build trust in the state.

Digitalisation for Transparent Reconstruction
Objective 2 includes support to upgrading Ukraine’s e-procurement system, ProZorro, as well as the wider enabling environment through support to legislation and the training of procurement professionals and civil society on providing effective oversight. This objective will bring digital tools to enhance state oversight and audit systems. It will also include our ongoing support to DREAM: a portal that provides “end-to-end” transparency for all infrastructure reconstruction projects from planning to implementation, allowing coordination and accountability.
Digitalisation for Economic Revitalisation

DTA will support the simplifying of business registration and licensing processes. It will use digital tools to simplify export processes, such as by digitising export certifications and digitising the transportation sector e.g. through eQueue; an online tool to reserve a place in online queues to cross borders to reduce border wait times and opportunities for corruption. This objective will enhance the Diia.Business and Diia.Business.Export platform, which helps to promote and support Ukrainian entrepreneurship in domestic and foreign markets. This objective will also help to foster investments into Ukraine’s ICT infrastructure and will support the reskilling of the labour market to ensure the human resource exists to maintain it.

Box 3: Judicial Reform

The UK currently provides some targeted programmatic support to the High Council of Justice and the High Qualifying Commission of Judge, and UK expertise was instrumental in the reboot of these bodies. Recognising there is potential to expand/refine its work in the judicial space, BE Kyiv commissioned independent consultants to take stock of UK support to date and to identify entry points for the UK in the judicial reform space, both for political / diplomatic influencing and programmatic interventions. The following options were identified and, following the final presentation of results in July 2024, a decision was taken to proceed with Option 1.
1. Continue the UK’s approach to date of focusing on a targeted area of judicial reform which builds independence and integrity. The initial focus could be to speed up the vetting and selection processes for existing and new judges. It could also include new funding for CSOs to bolster domestic demand or engaging in legal education, judicial training and the transformation of the Bar Association.
2. Dispute resolution for businesses. FCDO could seek to improve (i) judicial effectiveness from the point of view of domestic and international businesses and (ii) the use of ADR to divert cases away from the courts and resolve disputes faster. Longer term structural reforms to the judiciary would also improve outcomes for businesses (e.g. unified Supreme Court addressing only the most important commercial cases).
3. Access to justice for vulnerable populations. This approach would involve researching the most pressing legal and judicial issues faced by specific vulnerable groups, and then empowering Ukrainian actors to devise issues-based strategies to resolving them. These solutions may involve working with legal professionals and judicial authorities but could also rely on alternative coalitions or diversion away from legal and judicial solutions.

Following further consultations, we believe Option 1 can be delivered through two workstreams:
1. an operational component focused on the continuity on support to transparent judicial selection and institutional capacity building of the High Council of Justice, High Qualification Commission of Judges and the Disciplinary Inspectors Service. This also involves making decisions about where not to engage, such as on legal education reform.
2. an advocacy component getting into more complex political issues, advocating for more complex and politically important reform priorities such as reform of the Supreme Court reform, establishment of the High Administrative Court of Ukraine and Bar Reform.

To deliver this, we would like the implementing partner to adopt a flexible approach to how they identify, define and take forward their advocacy objectives. This will require regular political scanning to identify where there are opportunities to engage, strengthening coalitions (if necessary) and learning from what works. We would expect the team to work closely with our political section colleagues on this to ensure we make full use of diplomatic levers. It will require a new approach to MEL to reflect shifting outputs/outcomes, and learning (and failing) from different strategies. We also think there is an opportunity for increased ambition on GESI, but for this work to be wrapped into the advocacy component.

Box 4: UK Influence on Reform

This component would focus on utilising different levers to increase UK influence on reform. These would be delivered through:
- The establishment of an Embassy political economy analysis
- UK hosting of an annual reform conference
- UK-funded secondments to the Donor Platform and OECD
- UK representation at high-level anti-corruption and reform-focused international conferences

Political Economy Analysis (PEA) Facility

Our assessment is that the GRP should include a Political Economy Analysis Facility that is centred on the pairing of international and local experts to deliver Political Economy Analysis to deepen the UK’s understanding of Ukraine, particularly at the sub-national level. Following the full-scale invasion UK ODA to Ukraine has increased exponentially. The UK is programming in new areas, many of our delivery partners are new to the context, and travel has become more difficult due to the security situation, meaning our networks have become more focused on the capital. The aim of this Facility will be to ensure the UK’s strategy, policy and programmes are informed and influenced by up-to-date and on-the-ground analysis that get ‘under the skin’ of how change happens in the current, complex operating environment of Ukraine.

The PEA facility would provide us access to experts on Ukraine that would focus on:
- Deepening understanding of Ukraine’s national and sub-national political economy under wartime conditions and the post-war transition (in the case of that eventuality).
- Building understanding of national and sub-national level political economy incentives and constraints affecting delivery of the UK’s ODA portfolio and recommending practical actions to manage risks to advance programme delivery.
- Generating demand for and deepen HMG and HMG’s partners’ understanding, uptake and utilisation of political economy research, including how to conduct PEA in house.

The Facility will draw on lessons from other similar FCDO facilities across the world, such as the Horn of Africa research facility in Ethiopia.

UK hosting of an annual reform conference

In 2023, the UK used its convening power to host a 3-day conference at Wilton Park titled ‘Building the enabling environment for Ukraine’s economic growth: the role of its reform agenda’. This conference focused on prioritising the key reforms needed to secure investment to rebuild and improve its prospects of EU and NATO accession. Following a successful conference, the Donor Platform requested a follow up conference in 2025 to keep the conversation moving forward, which Germany offered to co-host with us. Having funds available to allow the UK to play a convening function and host such high-level events will help to increase our reputation and influence on reform.

UK-funded secondments to the OECD and MDCP

We will support two secondees to work with the OECD in Paris to improve donor coordination on reform and support with macro-economic analytical pieces. We will also fund a secondee to the Donor Platform (currently in Brussels, but due to move to Kyiv) who will focus on donor coordination on reforms.

UK representation

We will reserve a small amount of budget (£20,000 a year) to allow British Embassy Kyiv staff to represent the UK at international events on reform in Ukraine, such as the International Anti-Corruption Conference and the OECD Global Anti-Corruption and Integrity Forum.
Theory of Change for Option 4

Theory of Change

The Theory of Change (TOC) of the preferred option is as follows: IF GoU better harnesses digital opportunities to deliver higher quality services and prevent corruption AND Ukraine’s Institutional capabilities are strengthened at the national and sub-national levels AND Ukraine has improved judicial reform legislation and strengthened rule of law AND the UK is better able to track and influence reform conversations THEN in the long-term Ukraine will be further along its Euro-Atlantic Integration, with reduced corruption and improved rules-based systems that deliver for Ukrainian people and business.

The TOC is depicted above. Each component will programme towards specific outcomes that jointly drive the longer-term impact. Though the log frame will capture results at the component-level, the programme will also determine shared objectives that unite the components, and these will also be reported against as part of the Annual Review process. This approach will be detailed in a GRP MEL Strategy. Cross-cutting outcomes might be:

1. GoU institutions are more independent and rules-based, providing less space for vested interest to operate and an improved business environment
2. GoU institutions are more transparent and inclusive resulting in oversight and accountability from civil society, media and the public
3. GoU institutions provide higher quality services – making use of digital tools to do so – to prevent wastage, provide VfM and ensure integrity in reconstruction

It is important to note that digital and anti-corruption reform outcomes are a shared responsibility with USAID. Opportunities to steer these components to influence the remaining outcomes will be kept under close review through the life of the programme.

The key assumptions underpinning the theory of change are below. Each assumption is rated according to their likelihood of holding true, based on judgements of available evidence. Through the life of the programme, the assumptions will be reviewed during the annual review process to ensure the TOC is fit for purpose. Any modifications, or updates will be agreed as part of the review process.

Assumption	Rating
Cross-cutting
Invasion, war trajectory and economic shocks don’t detract from reform priorities
UK funding levels the same
Enough delivery partner capacity, TA and government absorption capacity to deliver programmes
Enough political will in the system to continue progress on reform (vested interest doesn’t block)
Reform all interconnected so progress needed outside of programme for programme to benefit
Interventions will last beyond lifecycle of programme
Programme team have the human resource to deliver
Outcome to Impact
Transparency not necessarily translating to accountability (Outcome 1)
Digital transformation benefits everyone and people aren’t left behind (Outcome 1)
Digital tools provide a higher quality service for people and business than non-digital (Outcome 1)
Depth of support is enough to lead to systemic change at sub-national level (Outcome 2)
Rule of law reform in itself improves the business operating environment (Outcome 3)
Strengthened rule of law results in more prosecutions (Outcome 3)
TA has positive implications for UK reputation and can meaningfully substitute for low government capacity (Outcome 4)
Output to Outcome
Corruption free contracts transfer into a higher quality service (Component 1)
Cyber-attacks do not derail digital service provision (Component 1)
Data protection and privacy regulation keep pace with transformation and does not detract from Euro-Atlantic obligations (Component 1)
Level of reform keeps pace with the expectations of civil society (Component 2)
Martial law doesn’t continue to block the open government agenda (Component 1)
Sufficient understanding of national and local political economies to understand actual reform pathways (Component 2)

Expected results

At the Outcome Level, the following medium-to-long term results are expected:
1. Ukraine’s institutions better harness digital opportunities to deliver higher quality services and prevent corruption
2. Ukraine’s institutional anti-corruption capability is strengthened at national and sub-national levels
3. Ukraine has improved judicial reform legislation and strengthened rule of law institution(s)
4. The UK is better able to track and influence reform conversations.

1. Components 1 (anti-corruption) and 2 (digital) are pre-existing within the current Good Governance Fund (GGF) Programme. Headline achievements in the past few years have been as follows:
  1. Component 1:
    1. Under Pro-Integrity’s mobilisation, they have MoUs are in place with 12+ GoU institutions with grants being agreed and disbursed to 6+ CSOs.
  2. Component 2:
    1. Development of Ukraine’s world-leading e-procurement system, ProZorro, which is assessed to save GoU $1bn a year through increased efficiencies and less corruption.
    2. 43 government services digitised. Qualitative examples include the rapid establishment of a digital compensation system for Ukrainians whose homes were damaged or destroyed because of hostilities. In 2022, more than 50,000 people received payments totalling over $113m. The development of Diia also allowed internally displaced persons to be geolocated making it clear if they have been displaced and made it easy for people to access state benefits.
    3. Support to 3 start-ups to run competitions by accessing open data.
    4. Development of the DREAM transparent reconstruction system which covers over 4,000 projects, worth over US$4.7bn. Though born from civil society it has now become institutionalised within the Ministry of Restoration and the GoU Public Investment Management Reform Roadmap.
  3. Component 3:
    1. The High Council of Justice resumed its work after 2 years and the High Qualification Commission of Judges appointed new members and resumed its work after 4 years.

1. Under the current programme the expected indicators/results for these components at the output level are as follows (targets will be assigned in due course):
  1. Component 1 (anti-corruption reform): NACP’s success in implementing the State Anti-Corruption Programme; improved effectiveness of the implementation of anti-corruption tools in institutions; # of Pro-Integrity supported local government partners that have achieved the minimum compliance benchmark; # of civic initiatives supported by Pro-Integrity that help prevent, expose and counter corruption and corruption risks; # of businesses making progress on compliance; narrative explaining what GESI considerations have been made and what activities have been delivered.
  2. Component 2 (digital reform): Decrease in the average time for border crossing inspection procedures for cargo trucks; number of business-related permits and licensing services digitised; number of business-related permits and licensing services digitised; percentage of reconstruction projects substantively improved relative to those closely monitored as the result of civic oversight and scrutiny; number of e-services implemented in corruption-prone sectors; improvements in Ukraine's score in the Online Service Index within the United Nations E-Government Development Index (EGDI); number of women and representatives of vulnerable groups empowered with new knowledge and skills through project training programmes.
  3. Component 3 (judicial reform): TBD depending on how we decide to proceed.
  4. Component 4 (UK influence on reform): It is difficult to say at this stage, but indicators could look at the number of PEAs that are delivered on time that are deemed to be of high quality; evidence that analysis has influenced UK policy and programming decisions; number of trainings on PEA delivered across the Embassy; number of PEA materials developed as part of BEK induction processes; number of trainings delivered to UK delivery partners on PEA. We will undertake conversations with secondees to determine how we can best capture their influence on reform agendas, as well as with the Reforms Hub on monitoring the impact of UK-hosted conferences.

## Appraisal Case

As set out in the Appraisal Case, the preferred delivery option is Option 4, which involves supporting: anti-corruption reform through support to Ukraine’s anti-corruption institutions and state-owned enterprise, judicial reform, digitalisation and increasing UK influence on reform through PEA, targeted secondments and use of UK-hosted conferences.

In the selection of the implementing partners and instruments, we have prioritised where we have existing agreements in place with the US. For the other components we have considered the capacity of the Governance Team to manage multiple instruments and the track record of delivery mechanisms supporting similar work within Ukraine. GRP will be delivered through different instruments, set out by component below. The programme will retain a certain level of flexibility and funding may be shifted between partners over the course of the programme.

Anti-Corruption Reform

The current vehicle for our anti-corruption reform work is the joint UK-USAID programme, Pro-Integrity, and we expect to continue with this approach. We began our partnership on Pro-Integrity in November 2023. We have been heavily involved in the design of the programme, spearheading an entirely new component on sub-national support to 75 municipalities. Under GGF we trialled providing dedicated FCDO advisory resource to the programme and so far, this set-up is working well, with the UK able to influence delivery while benefitting from the programmatic insights. Pulling out now would therefore be poor Value for Money given investments made to date and would severely compromise our working relationship with the US; one of our closest allies on reform. Our experience has also taught us that joint programming on sensitive areas, such as anti-corruption, works well, because we can share analysis and deliver joint messages to the Government when needed. We therefore assess that continuing with this delivery option – via a Delegated Cooperation Agreement (DCA) with USAID offers better value for money than establishing a new contract with a commercial supplier.

On state-owned enterprise reform, we also recommend continuing with our joint US-UK programme, SOERA. We have been engaged on this programme since 2022 and it is performing well. In the first year of programming (likely December 2025) we will take a decision about whether the UK should continue supporting state-owned enterprise reform as part of its economic reform package. For 2024/25 we therefore recommend committing to the Delegated Cooperation Agreement we have in place with USAID.

Digital Reform

Our partnership with USAID on digital reform is longstanding and, as with anti-corruption, our recommendation is to continue with the joint UK-USAID programme – Digital Transformation Activity. The UK has a strong identity in this reform area, which is an area that continues to gain momentum. The delivery partner, Eurasia Foundation, has been working on Ukraine’s digital reform with the USA and UK since 2015 and therefore has deep expertise and a refined delivery model, which offers high value for money. DTA is seen as the landmark programme on digital reform in Ukraine and has strong and established relationships with GoU. The support it can provide to Ukraine’s institutions is broad and meaningful and, despite only making a 10% contribution to the total cost of the programme, we receive full credit and branding rights. We therefore assess that continuing with this delivery option offers better value for money than establishing a new contract with a commercial supplier and recommend extending our Delegated Cooperation Agreement with USAID until 2028.

Judicial Reform

On judicial reform, our delivery approach under GGF has been to programme via the international NGO International Development Law Organisation (IDLO). In the past we have also supported the well-known local NGO, De Jure Foundation. Our Accountable Grant with IDLO ends in March 2025. To select a new supplier to deliver one of the options outlined in Box 3 we are likely to run a call for proposals and use an Accountable Grant to continue working with either an international or a local NGO.

Wider Reform

Political economy analysis facility: We explored whether this could be delivered through the Centre of Expertise model, but it wasn’t possible. It is likely this will be delivered through a commercial contract. Our options for delivering this are via a standalone commercial contract through the GDD either through Lot 7 or 14, depending on the value of the overall contract.

MDCP and OECD secondments: the OECD secondments will be delivered via an MoU with the OECD which will be put in place under the current form of GGF. The MDCP secondment will be delivered via a payment to the EECAD budget line.

A UK-hosted Reform Conference: to leverage and shape international conversations and leverage donors on the key reform areas we care about e.g. by continuing the Wilton Park conference on anti-corruption and transparency reform. This will be delivered via a budget transfer to Wilton Park.

Evaluation and Learning

Support for Evaluations and Reviews: Third Party Monitoring (TPM) of support provided under Component 1 and 2 will be covered by BE Kyiv’s portfolio level TPM programme, VERITAS. A separate allocation under GRP is not required for TPM. For components 1, 2, 3 and 4, GRP may either look to co-fund evaluations along with USAID and/or procure for a small value mid-term/end-term evaluation (or review) of the judicial reform and/or PEA component should it be deemed feasible to do so. If a procurement is required, then GRP will use FCDO’s commercial Global Evaluation and Monitoring Framework Agreement (GEMFA-2) as needed.

To ensure we capture key learnings from the programme, we will agree ‘learning objectives’ with each delivery partner. Example questions could be:
  1. In what ways has the programme helped to build accountability integrity in institutions? Are the programmes delivering in ‘function’ as well as ‘form’? I.e. are there examples where G7 lobbying/improved legislation has resulted in an institution becoming more independent on paper, which has then been reinforced by follow up GRP interventions?
  2. How have the programmes contributed to EU/NATO accession?
  3. How has the programme contributed to an improved business environment? Will business be more likely to operate in Ukraine at the end of the programme?
  4. To what extent is the ‘sandwich strategy’ still applicable in Ukraine and how is accountability and reform achieved under this new context of martial law? In what ways has the programme improved transparency, which has then resulted in greater accountability?
  5. How equitable is Ukraine’s digitalisation? Do Ukrainians believe the digital services they receive are higher quality than non-digital services? Is there evidence that digitalisation has saved the GoU money in terms of less corruption or greater efficiency?
1. Will there be less corruption and more oversight of reconstruction because of this programme?
2. What works in terms of improving access to justice to Ukrainians in a time of war?
3. How has our GESI support resulted in better outcomes on GESI? What GESI lessons can be applied to other governance programmes?

Expected procurement timelines

As the programme starts, the Governance Team will have to navigate two competitive processes to mobilise the portfolio. The team will mitigate the management burden of this through careful sequencing of programme mobilisation over the first year. It will prioritise the DCAs as these are light touch and allow for immediate spend. It is envisaged that component 1 and 2 will be mobilised quickly, in the first 2 months for spend to occur 2024/2025. Component 3 will be carefully sequenced to allow for implementation to begin at the start of the FY 2025/26. Component 4 will be sequenced to mobilise in the middle of FY 2025/26.

There will not be a programme-wide inception phase for the programme, but individual inception or mobilisation phases may be agreed with partners selected to lead on judicial reform and the PEA facility. We anticipate that the commercial partner will require a 3-month inception phase to hire staff, finalise workplans and budgets and key documentation. For non-commercial partners, the team will work with them to develop and finalise proposals, budgets, results frameworks and risk registers, prior to signing agreements. Continuation of funding will be dependent on continued performance (technical, compliance and financial).

For the USAID programmes, the partners have already been identified and the programmes are delivering. Once DCAs are in place, disbursement can happen immediately with payment for DTA and SOERA happening FY2024/2025.

For the support to judicial reform via an Accountable Grant, terms of reference will be developed in parallel to the business case approval process to ensure a call for proposals can commence as soon as the business case is approved. We will aim to have a new agreement in place on judicial reform by April 2025.

For the commercial contract for the PEA facility, the Governance Team will engage with commercial experts to identify the best route to implementation, whether via procurement via an FCDO framework contract or a new procurement specific to this programme. We anticipate this process to begin at the start of 2025 with a new supplier in place by the end of 2025.

For the GEMFA-2 commercial contract, the earliest this would take place is half-way through the programme’s life. Before procurement, a detailed evaluability feasibility assessment will be conducted by using FCDO’s centrally managed “EQUALS” programme.

Key Cost Drivers

The primary cost driver for the GRP is fees for international experts and payment to downstream partners. There will also be payments international experts. For any contracts, there will be competitive tendering and fee rates and programme costs will be evaluated against the market with a preference for output-based payments. Programme delivery costs via NGOs and other donors include cost recovery rates plus any administration and management costs. We will negotiate these to drive further value for money, and ensure they reflect agreed benchmarks used by FCDO in broader institutional agreements. We will aim to maximise the fund flow to NGOs through a core grants model (e.g. as part of the US programmes). Wherever possible, we will seek to work with local partners or implementing organisations directly or as part of delivery through other organisations (for larger projects where fiduciary concerns making working directly with smaller suppliers less appropriate). Not only does this often demonstrate better value for money in terms of immediate costs, but by using local expertise we are more likely to cement government buy-in and produce more sustainable results.

Value for Money

By helping to advance reform and fight corruption, this programme will increase the effectiveness of UK spend across the portfolio. The programme builds on components that have been tried and tested by the GGF – meaning we have confidence in their impact – but through a more streamlined and coherent programme. The components being continued are influential, with strong relationships with the Government of Ukraine. The choice to work mainly through joint programming with USAID offers strong VfM. Despite being a minority donor (10% on some components) we receive full credit and branding rights allowing the UK to be recognised as a leading voice and donor in these reform areas. Drawing on USAID project management allows frees up FCDO staff time to focus on the technical and strategic inputs needed to influence the large-scale programmes. We shifted our approach towards this model in October 2023 and are already seeing the benefit. Joint programming also allows us to deliver joint messages to the Government on sensitive issues, improving our impact in the more challenging reform areas.

Supplier Performance Management

Our experience of joint programming with USAID has given us confidence in their supplier performance management and programmes have benefitted from an additional layer of donor oversight. On USAID programmes we can undertake standard programme management oversight such as influencing and approving workplans, results frameworks, programme strategies (e.g. GESI), and the disbursement of funds to downstream partners. For DTA, we are in close contact with the team, and we receive weekly written updates and take part in quarterly reports. For Pro-Integrity, we have weekly check-ins and are even more involved in the weekly decision-making underpinning the project. We sign off on MoUs with the Government of Ukraine and on grants awarded to CSOs. We have helped them to align their systems to FCDO programme management where necessary e.g. in the development of risk registers, development of ToCs, and indicator selection in their results framework (moving away from an input dependent model). Despite being a minority donor, the deliver partners treat us as equal partners and are receptive to our questions and demands and we have always been able to obtain clarifications or additional details when needed. For the accountable grant on judicial reform and the commercial contract for the PEA Facility we will maintain rigour in our supplier performance, committing to quarterly check-ins (at a minimum) to review progress, risks, results and finances, as well as ad hoc meetings if the need arises.

## Financial Case

This section of the Business Case describes how the preferred option is affordable, is the best use of FCDO funds, and that the principles of sound financial management of public funds are followed.

The Good Governance Fund spent between £8m and £14m a year split between economic and governance reform. With the Governance Reform Programme we will aim for similar level of disbursement but focused purely on the areas of governance reform to help deliver the UK’s Recovery and Reconstruction Strategy.

The Governance Reform Programme has been conceived as an up to £38m, 3.5-year programme. This may be extended up to 3 additional years depending on its performance and spending cycles/decisions. The breakdown by component is as follows:

	Component		2024-2025	2025-2026	2026-2027	2027-2028	Total
1	Anti-corruption reform / Pro-Integrity / SOERA			£4m / £2m	£3.5m / £2m	£3.5m / £2m	£11m / £6m
2	Digital reform		£2m	£4m	£4m	£4m	£14m
3	Judicial reform			£1mm	£0.75m	£0.75m	£2.5m
4a	Wider reform	PEA Facility		£0.75m	£0.75m	£0.75m	£2.25m
4b		OECD Secondments		£0.4m	£0.4m	£0.4m	£1.2m
4c		Reform conference	£0.1m	£0.1m	£0.1m	£0.01m	£0.31m
4d		MDCP secondee		£0.15m	£0.15m	£0.15m	£0.45m
4f		Programme team representation at international events		£0.02m	£0.02m	£0.02m	£0.06m
5	Evaluation and Learning			£0.1m	£0.1m	£0.1m	£0.3m
6	Programme-funded role			£0.06m	£0.06m	£0.06m	£0.18m
							£38m

This programme has capacity to absorb more funding via a business case extension, should additional financing become available. An increase in allocation would likely be absorbed by component 1, 2 or 4a (though noting the VfM points made in para 43). Reallocation across components would similarly be determined based on reform momentum and the war outlook.

Monitoring, evaluation and learning is built into the USAID programmes (i.e. Component 1 and Component 2). As noted in the commercial case above a separate allocation for TPM is not required under this business case as it will be covered by British Embassy Kyiv’s portfolio level TPM programme. An allocation of £0.06m a year will be set aside for other evaluation and learning activities under this business case to cover the cost of MEL for the components we are delivering bilaterally (not through USAID).
Cost Profiling and Planning
British Embassy Kyiv will be responsible for cost profiling and planning, taking into account the contextual environment, existing programmatic commitments, and an assessment of the strategic value and risk associated with different programmes. We have not developed a rigid resource allocation model, but will assess need, demand and absorptive capacity between components during planning stages each year. The programme team will work with partners to apply their knowledge of project activities and context to ensure forecasts are as accurate as possible. We will aim for variances of less than 10% in project reporting as standard and ask partners to report the reasons for higher variances. Internally, we will aim for less than 5% variance monthly forecasts and 1% variance for annual forecasts and budgets.

For the USAID programmes, we will agree a contribution to be paid over the lifetime of the programme upfront. We have commitments with the US to meet at least 10% of the total size of the programme to receive full credit and branding rights. Given the size of the programmes we are supporting, our experience of joint programming with the US, and the fact they are established programmes (beyond their first year of programming) with regular burn rates, we can be confident that the anticipated spend forecasts will be met. Funding will be disbursed as a pre-payment (not in advance of need). We have agreed to align to USAID reporting requirements which includes quarterly financial updates.

For the judicial reform programme, the selected implementing partner will be expected to deliver to an agreed workplan with payments made as quarterly advances so long as 80% is spent ahead of the next disbursement. FCDO will receive regular reporting on project delivery and finance from the implementing partner.

For the PEA Facility commercial contract, funding will be disbursed quarterly in arrears upon production of project delivery and financial reporting/actuals. Invoices will require agreement by the SRO.

For the MDCP and OECD secondments: the Person on Loan will continue to receive his/her salary, benefits and allowances from the FCDO. The administrative charges for the Person on Loan to the OECD, which include the provision of office space, information technology services and other support services, will be reimbursed by the FCDO to the OECD.

Evaluation and Learning: A commercial contract procured under the GEMFA-2 framework, will be used depending on evaluation feasibility assessments.

Assessment of financial risk and fraud

Ukraine remains a high-risk operating environment due to the ongoing war. It also remains one of the most corrupt countries in Europe. However, our assessment of the programme’s financial and fraud risk is low. We are delivering through trusted suppliers and risk will be managed by ensuring we are compliant with the PrOF.

## Management Case

The team is envisaged to be structured as follows:

- 1 x 0.5 FTE G7 Governance Adviser (with the other 0.5 spent on the second governance programme on democratic strengthening and political inclusion), Team Leader and SRO responsible for the programme meeting its objectives, providing strategic leadership and decision-making (BEK). The SRO will lead on the delivery of the PEA facility.
- 1 x FTE programme-funded Grade 7 CBS Governance Adviser acting as lead adviser on Pro-Integrity, DTA and judicial reform, responsible for day-to-day management and decision-making.
- 0.3 FTA G7 Economic Adviser acting as lead adviser on SOERA, the OECD secondments and providing cross-cutting economic support.
- 1 x FTE HEO Programme Manager and Programme Responsible Officer to lead on day-to-day programming, finances, risk management and oversight of the components under the programme.
- 0.3 FTE x HEO Finance and Contracts Manager.
- 0.2 FTE x G7 Senior Programme Manager responsible for wider portfolio compliance and programme excellence (BEK).
- Close cooperation with members of the Political, Economic and Communications (PEC) Team, who will benefit from programmatic insights and can help to unblock programmatic obstacles such as through G7 engagement and wider diplomacy.

The GRP team will be bolstered further by cross-cutting inputs provided by BEK’s multi-disciplinary team of a Social Development Adviser, MEL Adviser, Economic Adviser, Infrastructure Adviser, 2 x Humanitarian Advisers, a 7 Private Sector Development Adviser, and a Conflict Adviser. Y

GRP will need to respond as required to an ever-evolving context. The programme team will set out clear parameters for when partners need to revert to FCDO for approval of project or budget changes, whilst allowing some flexibility within the agreed parameters of each project. Day-to-day changes to components will be approved at PRO level, with the SRO sighted as appropriate, and more significant or high-risk decisions being taken at SRO level. Where appropriate, decisions or risks will be escalated through the BEK governance structure. The SRO will provide updates into the Post Programme Board which has the responsibility for setting overall programme direction. The SRO will also encourage lesson sharing through the Democracy and Governance Delivery Group.

Monitoring Evaluation and Learning

The programme has been set up with four components, each working on complex governance reforms including on separate systems and processes. These are long-term processes, subject to uncertainty due to factors outside of the programme’s control making it challenging to measure. As the history of Ukraine’s reform progress shows, progress does not always appear in a linear way, but jerkily and unpredictably. Some of Ukraine’s greatest achievements since 2014 have been the least predicted.

The Theory of Change is clear in its depiction that individual components are programming for discrete outcomes. However, as mentioned above, opportunities in the way each component interacts with each other to drive outcomes beyond their own will be actively pursued. These opportunities will be embedded into the MEL framework for each component. This is described in the table below.

Component	MEL Framework
Component 1: Pro-Integrity and SOERA	Logframe: USAID’s established results monitoring system will be used to create the logframe for this component. Typically, these indicators tend to be output/activity based. A set of core-indicators will be agreed upon with implementers to reflect the UK's contributions to Pro-Integrity and SOERA. The reporting cycle, milestones and targets of each of these indicators will be agreed to align with FCDO’s annual review dates. / Third Party Monitoring: British Embassy Kyiv’s portfolio TPM programme will be used to verify, and quality assure the results being reported by implementers. Where USAID is already using its own TPM facility, duplication of efforts will be avoided. The embassy team will co-ordinate with USAID’s TPM implementor to either separate out verification responsibilities or co-ordinate efforts for maximum coverage. / Evaluation: USAID have their own evaluation cycles in place. The embassy team will look to either collaborate on design of the evaluation and/or co-fund efforts as necessary.
Component 2: Digital Transformation Activity
Component 3: Judicial Reform	Logframe: A dedicated logframe under the accountable grant agreement will be established with the implementer. This logframe will reflect output level results that are entirely attributable to this programme’s funding. / At outcome level, the questions detailed in the theory of change section will be explored with the partner and integrated into the logframe as needed. / Third Party Monitoring: As it stands, the current expectation is that this component will not be amenable for TPM. However, if possible independent feedback could be collected from GoU users and experts to assess the quality of TA provided under this component. / Evaluation: A mid-term evaluation or review could be undertaken to assess the components progress towards the overall outcomes. Findings from this could inform course-correction as needed. Potential evaluation/review questions could cover the questions within the Theory of Change section above, if the partner data-system can feasibly be used to provide the analysis required. At a minimum, an independent evaluation/review question could focus on assessing the quality of the processes for driving meaningful judicial reform and offer on a judgement on their sustainability.
Component 4: PEA	Logframe: A dedicated logframe will be agreed with the successful commercial supplier. This component is intended to be flexible and responsive. Though a strategy for PEA will be developed at the start of each programming year, the aim is for the facility to be responsive and demand-led, so the log frame (indicators, milestones and targets) will be updated as needs are identified and research is provided on short- and long-term bases. / TPM and Evaluation: It is unlikely this component will be amenable for TPM. However, if possible independent feedback could be collected from GoU users and experts to assess the quality of PEA provided under this component. / Evaluation: A review or evaluation of the PEA used under this component could be undertaken to assess which of these delivered most impact and had most uptake and application. If feasible to do so, a process evaluation could be undertaken to assess the strengths and weaknesses of the manner in which the PEA has been provided under this component.

To ensure that the individual component outcomes are jointly driving the longer-term changes at the impact level, a Steering Committee will be established. This committee will include representation from each component, alongside the embassy team to take stock of the progress being made under each individual component, share lessons learned with other components, including any relevant findings from TPM and evaluations and assess the key programming and contextual assumptions underpinning the theory of change. At minimum, this committee will aim to meet ahead of the annual review each year. A detailed terms of reference will be developed during the mobilisation phase.

Principles of MEL: The following principles will be used when managing the MEL frameworks for each component:
1. Component Logframe Development and Maintenance: Each component will be monitored against its results framework which will be finalised prior to the start of the programme and updated on a six-monthly basis (at a minimum). The logframes will follow the logic chain as outlined in the Theory of Change, with the potential for more join-up if the outcome monitoring system can be agreed within components. The logframes will also contain flexible elements considering that results cannot be fully defined upfront. This is particularly anticipated for Component 4. Overall, the logframes will be living documents that are reviewed at least annually to confirm the appropriateness of indicators, milestones and targets.
2. Overarching logframe: Consideration will be given during the first year of the programme on the pros and cons for maintaining an overarching logframe that draws on individual component results framework. At minimum, an overarching logframe will include a core-set of indicators for each component that best reflects the priorities for the programme year and/or the logic chain within the Theory of Change.
3. Monitoring GESI and Conflict Sensitivity: Within each component dedicated GESI indicators and conflict sensitive indicators are to be included where appropriate. Wherever relevant and possible, individual level results data will be disaggregated along the following dimensions (e.g. age/sex/disability status/geography).
4. Partner progress: The embassy programme team will verify the satisfactory delivery of agreed outputs within the components through regular monitoring of project activities, incorporating beneficiary feedback. Quarterly, strategic meetings will be held with implementers with a focus on results, risk and adaptation.
5. Evaluation feasibility: Before any evaluation is undertaken, a detailed evaluability assessment will be undertaken, potentially by drawing down from FCDO’s central resource of expertise “EQUALS” (at no extra cost). If the EQUALS assessment is that the component is amenable for an evaluation, the embassy programme team could then choose to move forward with either co-funding an evaluation with USAID or procuring its own targeted evaluation (e.g. under component 3).
6. TPM: The Embassy programme team, and USAID will work closely with BEK’s TPM programme to develop a workplan each programme year (as relevant) to monitor outputs and activities under components 1 and 2. The TPM will use the opportunity to also monitor and diagnose aid-diversion and fraud risks under these components.

Risk management

Overall we assess the programme risk to be major taking into consideration the issues the programme will seek to resolve. Risks will be tracked by the PRO who will ensure that programme partners have programme-level risk registers in place and that risk discussions happen quarterly. They will report to the SRO routinely on risk and they will be responsible for identifying risks that sit outside of appetite and flagging these to the SRO. The PRO will be responsible for maintaining the programme level risk register.

The following table lists the main risk appetites in place for UK support to Ukraine. BEK and EECAD have a higher tolerance to risk than the rest of FCDO. The overall risk appetite is receptive.

FCDO risk category	Appetite	Key risks
Strategy and Context	Eager	Difficulty accessing areas affected by war; particularly Russian-controlled areas and including besieged cities. Targeting or abduction of humanitarian aid by militaries. Lack of preparedness for chemical, biological, radiological, or nuclear weapons use. Erosion of state legitimacy. Large migration out of Ukraine or movement of internally displaced people makes reaching those in need difficult.
Policy & Programme Delivery	Eager	Sanctions restrict ability of partners to deliver in Ukraine due to weakened delivery chains; chilling effect means partners refuse UK funds or withdraw. Lack of supplies and fuel inhibits delivery. Lack of capacity to respond to rapid-onset emergency due to lack of preparedness or experience of context.
Public Service Delivery & Operations	Cautious	Safety and security of FCDO and partner staff (we do not have duty of care for the latter). Destruction of HMG and partner assets in Ukraine inhibits partner operations, particularly dual use (e.g., generators, shared operational facilities). Risk of duplication and/or inefficiency in cross-HMG coordination.
People	Receptive	Morale of FCDO and partner staff. Need to retain and recruit a flexible workforce in a new and challenging context. Importance of supporting staff resilience through crisis working. Space on platform in Kyiv.
Safeguarding	Cautious	Specialist protection needs associated with refugee population that is predominantly women and girls, and unaccompanied children.
Financial & Fiduciary	Cautious	Theft or abduction of aid; or aid diversion through new supply chains and untrusted partners. Items appropriated for dual use (e.g., armoured vehicles or generators)
Reputational	Cautious	Risk of UK aid funds inadvertently being made available to sanctioned entities. Risks of Ukrainian actions that are counter to HMG humanitarian objectives (e.g., aid appropriation). Risk of coming into conflict with GoU over specific reform issues.

Governance Reform Programme Risk Register and Assumptions

Risk	Impact	Gross / Likelihood	Mitigation	Impact	Net / Likelihood
External/Contextual Risks
Due to the close partnership and joint programming with the US there are political risks relating to a divergence in approach on these issues and programmes becoming affected by tensions in the US-Ukraine relations.	3	3	Use our voice within the joint programmes to influence the US approach and ensure that it remains constructive. Use our position within the G7 to ensure broader coherence on objectives and messaging. Review the approach once the priorities of the new US administration are clear. Stay in close contact with other donors and open to other anti-corruption programming options, noting we can stop our support at any time.	2	3
Tangentially supporting re-oligarchisation via the privatisation of state-owned enterprise	3	2	SOERA ensures there are technical safeguards in place to avoid re-oligarchisation, while at the political level we work closely with the EU, IMF, US and others to ensure due process is followed. We follow auctions, there is public and media scrutiny, and the G7 Ambassadors’ group and individuals in the Rada voice any concerns. Privatisations are held publicly on a transparent, electronic auction platform giving all bidders an equal chance and the Anti-Monopoly Committee plays an important role in limiting oligarch ownership.	2	2
Vested interests or other blockers prevent progress on reforms and/or there is a general decline in public demand for reform.	4	3	Ensure all implementing partners are conducting regular political and economy analysis (PEA) of the context so programmes target areas where political will exists and progress is demonstrated.	3	3
Deterioration in the war leads to a reprioritisation towards short-term needs away from long-term reform.	4	3	HMG diplomatic and wider programmatic engagement builds resilience and allows Ukraine to continue to focus on the long-term. / Governance Reform Programme uses HMG analysis and early warning to inform strategic and adaptive programme delivery.	3	3
High levels of conditionality and focus on reform by partners result in a lack of absorption capacity and the Government of Ukraine is unable to deliver.	4	3	GRP will support embedding experts within Government institutions where possible to improve their capacity to deliver reform	3	3
Operational Programme Management/Delivery Risks
Principal-agent problem results in supply-led portfolio with poor VFM.	3	3	Effective and engaged oversight and monitoring of delivery partners ensures demand-led, strategic approach.	2	1
Inadequate capacity and/or capability of staff reduces ability to provide sufficient oversight and assurance.	3	2	Plan for and recruit sufficient staff, build capability and set effective standards through adherence to Smart Rules.	1	1
Inadequate capacity and/or capability of advisory staff prevents advisory unit from providing and drawing upon analysis of local context and political economy.	3	3	Plan for and recruit sufficient advisory staff and build capability.	2	1
Changes in primary stakeholders leads to diminished engagement in reform work.	3	2	Development of deep and broad delivery relationships with key government counterparts. Continued political engagement and close monitoring of overall local context.	4	2
Financial Risks
Fraud or corruption leads to misuse of UK taxpayer money	3	3	Robust financial systems; strong fiduciary controls; no use of financial aid; adequate training of staff and application of FCDO policies, including proportionate due diligence.	2	1
Insufficient oversight or management leads to resource and programme slippage	3	3	Strategic over-programming; rigorous financial profiling and variance management; engagement with partners to ensure timely delivery.	2	2
Safeguarding Risks
Increasing awareness of poor governance and corruption and/or high public expectations of reform as a result of UK and other donor projects or diplomatic pressures leading to protests and instability.	2	2	Project delivery accompanied by clear advocacy and communications strategies around benefits and importance of reform; work with government counterparts to ensure reforms are realistic and reflect the right priorities.	2	1
Reputational Risk
UK supports reform that bear negative unintended consequences or disproportionately empowers certain groups.	3	2	Regular conflict sensitivity support/considerations in project approvals and PEAs will help programme teams track political developments and reflect on conflict sensitivity and political economies	2	2