## Smart Guide (hidden)
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. |  | 35
50
IMPACT WEIGHTING |  | 10
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome. |  | 5
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.

## FCDO Mar 25
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Climate Resilient Infrastructure for Basic Services (CRIBS) - Health and Education in Nigeria
| Impact Indicator 1 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
Improvement in access to climate-resilient basic services and improved environmental conditions for patients, health workers, teachers and students in CRIBS facilities | Reduced ratio of internal to external temperatures in 31 selected post-treatment schools/PHCs. | Planned | February 2025 averages Kano (schools) - 0.93 Jigawa (schools) - 0.89 Kano (PHCs) - 0.96 | N/A | N/A | N/A | N/A | Reduced ratio of internal to external temperatures in 100% of selected CRIBS post-treatment facilities (31)
Achieved
Source
R-CRIBS data collection and analysis
| Impact Indicator 2 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| Improvement in electricity access in post-treatment PHCs. | Planned | June 2024 Electricity supply was identified as the most urgent concern across health facilities, with 87% ranking it as urgent. . | N/A | N/A | N/A | N/A | 100% of CRIBS treatment PHCs (44) report in electricity access and/or reliability of more than 16 Hours per day.
Achieved
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation PHCs
| Impact Indicator 3 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| Post-treatment schools/PHC with adequate access to safely managed drinking water, and hygiene and sanitation practices | Planned | June 2024 Water access was identified as one of three urgent priorities by 87% of schools and 64% of PHCs | N/A | N/A | N/A | N/A | 100% of CRIBS treatment facilities (88) have 24 hour access to safe water source, and improve hygiene and sanitation standards which are resilient to climate change risks.
Achieved
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation schools/PHCs
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026) | Assumptions
Women and children in vulnerable communities of northern Nigeria have increased access to climate-resilient basic health, education and WASH services. | Proportion of post-treatment schools/PHCs demonstrating reduced vulnerability to climate risks in at least four areas of the climate vulnerability assessment (comparing the climate vulnerability assessment from baseline to endline) | Planned | June 2024 School vulnerability 0.74-0.99 PHC vulnerability 0.66 - 0.93 | N/A | N/A | N/A | N/A | 100% of CRIBS treatment facilities (85) demonstrate a 40% reduction in overall vulnerability scores, with reduced vulnerabilities in at least four assessment areas.
Achieved
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation schools/PHCs
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026) | Assumptions
Primary health care facilities and schools in zero-dose and high out-of-school LGAs are renovated, rehabilitated and equipped to ensure climate and disaster-resilient, carbon-neutral and sustainable basic service delivery for vulnerable populations. | Number of PHC with at-least one carbon-emission minimisation intervention in place (e.g. solarization) | Planned | 0 (0%) PHC with at least one carbon emission minimisation intervention in place | N/A | N/A | Design and procurement process completed for 70% (27) of planned CRIBS treatment PHCs | 70% (27) of CRIBS treatment PHCs have at least one carbon emission minimisation intervention in place | 100% (39) of CRIBS treatment PHCs have at least one carbon emission minimisation intervention in place | Selected interventions are appropriate to the climate vulnerabilities identified by the assessments and are implemented to an adequate standard. There are systems in place for the protection and maintenance of upgraded (44) primary health care centres and (44) schools.
|  | Achieved |  |  |  | Design and procurement completed for 31 PHCs | Design and procurement completed for all 39 PHCs, and retro-fitting work ongoing in all facilities.
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation schools/PHCs
| Output Indicator 1.2 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| Number of PHC/schools with assessment identified interventions in place | Planned | 0 CRIBS treatment faciltiies have infrastructure updates in place | N/A | N/A | Design and procurement process completed for 65% (55) of planned CRIBS treatment facilities | 65% (55) CRIBS treatment facilities have interventions in place that address all climate vulnerabilities identified in assessment that are related to capital investment | 100% of CRIBS treatment facilities (85) have interventions in place that address all climate vulnerabilities identified in assessment that are related to capital investment
|  | Achieved |  |  |  | Design and procurement completed for 55 facilities | Design and procurement completed for 85 facilities, and retrofitting work ongoing in all facilities.
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation schools/PHCs
| Output Indicator 1.3 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| Number of health care facilities and schools with climate resilient WASH infrastructure | Planned | 0 CRIBS treatment faciltiies have climate resilient WASH infrastructure in place | N/A | N/A | Design and procurement process completed for 65% (55) of planned CRIBS treatment facilities | 65% (55) of planned CRIBS treatment facilities have climate resilient WASH infrastructure in place as identified in the CRIBS climate vulnerability assessment | 100% of CRIBS treatment facilities (85) have climate resilient WASH infrastructure in place as identified in the CRIBS climate vulnerability assessment
|  | Achieved |  |  |  | Design and procurement completed for 55 facilities | Design and procurement completed for 85 facilities, and WASH facilities upgrading work ongoing in all facilities.
Source
UNICEF monitoring - CRIBS vulnerability assessment and survey of post-implementation schools/PHCs
IMPACT WEIGHTING (50%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%) |  |  |  |  | Other (£) | Total (£)
INPUTS (HR) | HR and operation costs are shared equally between outputs
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026) | Assumptions
Capacity is strengthened at the facility level to improve service delivery and sustainability. | Number of PHC staff trained on management and maintenance of installed solar systems and low carbon emission equipment or devices | Planned | Not Applicable | N/A | N/A | N/A | 70% (27) of CRIBS treatment PHCS have maintenance of solar systems and low-carbon emission equipment intergrated in the PHC comprehensive plan and budget | 100% of CRIBS treatment PHCS (39) have maintenance of solar systems and low-carbon emission equipment intergrated in the PHC comprehensive plan and budget | There are a clearly defined mechanisms (functional WASHCOMs / facility staff) in place at the selected facilities to receive capacity building. The training delivered by UNICEF is of adequate quality and supporting infrastructure, resources and organisation structures are in place. Staff and WASHCOMs are able and willing to operate, maintain and manage these resources.
Achieved
Source
Project Report - to be received in 2025
| Output Indicator 2.2 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| # of WASH Committees (WASHCOMs) whose capacity on operation and management of the climate resilient WASH services in PHCs and schools are strengthened | Planned | Not Applicable | N/A | N/A | N/A | WASHCOMS in 85 CRIBS treatment facilities demonstrate strengthened capacity on operation and management of the climate resilient WASH services in PHCs and schools | WASHCOMS in 100% of CRIBS treatment facilities (85) demonstrate strengthened capacity on operation and management of the climate resilient WASH services in PHCs and schools
Achieved
Source
Project Reports - to be received in April 2025 and February 2026
IMPACT WEIGHTING (20%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%)
INPUTS (HR) | HR and operation costs are shared equally between outputs
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Target (May 2025) |  | Assumptions
Climate risks and facility level assessment carried out for vulnerability to, and sustainability in the face of, climate change impacts. | Assessment and solution selection approach developed, pilot tested and agreed by CRIBS expert and oversight group | Planned | N/A | Initial tools, approach validated and endorsed by the Expert Group | N/A | N/A | Revised tools, approach validated and endorsed by the Expert Group |  | There are sufficient primary health care centres and schools viable for the available climate resilient tools and approaches; there is positive interest by all actors in the development of (39) primary health care centres and (46) schools to meet climate resilient standards.
|  | Achieved |  | Achieved. Initial tools and approach validated and endorsed by the Expert Group.
Source
Reports documenting the tools and minutes of Expert Group meetings
| Output Indicator 3.2 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Target (April 2025)
| # of communities assessed for climate risks and vulnerability and data analysed | Planned | N/A | At least 92 assessments completed | At least 92 assessments completed, and final report validated and endorsed by Experts Group | N/A | At least 92 assessments completed, and report summarising assessment and solution selection approach, with LGA analysis and solution selection completed.
|  | Achieved |  | Data gathered as part of climate vulnerability assessments successfully conducted in 92 facilities across Kano and Jigawa | Summary report submitted to FCDO and endorsed by Experts Group following presentation of key points.
Source
Assessment report
| Output Indicator 3.3 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Target (May 2025)
| #of PHCs, schools assessed for climate climate risks vulnerability, data analysed and solutions identified | Planned | N/A | At least 92 facilities assessment completed | N/A | N/A | At least 92 facilities assessment completed, and final report summarising the assessment approach and solution selection validated by the Expert Group.
|  | Achieved |  | Climate vulnerability assessments successfully conducted in 92 facilities across Kano and Jigawa |  |  | Climate vulnerability assessments successfully conducted in 92 facilities across Kano and Jigawa, and facility level reports shared with Experts Oversight Group.
Source
Rapid assessment for vulnerability to, and sustainability in the face of, environmental and climate change issues and final Project Report
| Output Indicator 3.4 |  | Baseline | Milestone 1 (June 2024) | Milestone 2 (Sept 2024) | Milestone 3 (Dec 2024) | Milestone 4 (March 2025) | Target (January 2026)
| Finalisation and publication of tools in partnership with WHO and Expert Oversight Group | Planned | N/A | N/A | N/A | N/A | N/A | Final tools published with endorsement of WHO and the Expert Oversight Group
Achieved
Source
Rapid assessment for vulnerability to, and sustainability in the face of, environmental and climate change issues and final Project Report
IMPACT WEIGHTING (30%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%)
INPUTS (HR) | HR and operation costs are shared equally between outputs

## Definitions
CRIBS Vulnerability Assessment
Scorecard was designed to rank the severity of climate hazards affecting a facility and assess vulnerabilities in key facility components (e.g., water supply, energy access, waste management).
Data was gathered by enumerators visiting facilities, observing the conditions and conducting a series of qualitiative interviews and focus group discussions.
The assessment covered multiple hazards and each was given a score (0-100%).
A similar process was followed for assessing vulnerability based on the key indicators identified. Each indicator was then given a vulnerability rating using a traffic light system (red, amber, green).
These scores were then combined into a single vulnerability index figure on a 0-1 scale.

## CRIBS Prog Logical Framework
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Climate Resilient Infrastructure for Basic Services (CRIBS) - Health and Education in Nigeria
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Q1) | Milestone 2 (Q1) | Milestone 3 (Q1) | Target (March 2025)
Reduced mortality and morbidity, and improved time on task in school (OR improved attendance) among children in North-West Nigeria most vulnerable to the impacts of climate change | Reduction of Carbon emission | Planned | TBD - after baseline assessment | N/A | N/A | N/A | Reduction of 9,739 CO2 e (Kg) per month per PHC
Achieved
Source
UNICEF/NPHCDA Health Facility Solar Electrification assessment and Final Project Report
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| % increase in average time on task for learning OR % increase in attendance rate among children in the target facilities | Planned | TBD - after baseline assessment | N/a | N/a | n/a | Time on task increases by at least 15% OR Attendance rate increases by at least 15%
Achieved
Source
MICs 2021, 2026
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| % of target population with adequate access to safely managed drinking water, and hygiene and sanitation practices | Planned | TBD - after baseline assessment | N/A | N/A | N/A | 20% of baseline figure
Achieved
Source
ASC
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025) | Assumptions
Women and children in vulnerable communities of northern Nigeria have increased access to climate-resilient basic health, education and WASH services. | Number of PHC/schools implementing carbon emissions reduction strategies | Planned |  | NA | NA |  |  | CRIBS project interventions and strategies will be the basis for taking measures towards energy efficiency within PHCs/Schools to reduce corporate footprint It is assumed that at least 20% of the populaiton in target LGAs will be covered by CRIBS programme. Actual pouplation will be determinsed after the assessment.
Achieved
Source
Administration data/WHO-UNICEF Joint Report Framework
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| Number of schools demonstrating reduced vulnerability to climate risks (comparing the overall score in the vulnerability section of the CRAT from baseline to endline) | Planned | TBD - after baseline assessment | n/a | n/a | n/a | 30 schools show decreased score on vulnerability
Achieved
Source
MICs 2021, 2026
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| Number of people in target LGAs using climate resilient and safely managed drinking water services | Planned | TBD - after baseline assessment | 0 | 10% of total population of target areas | 20% of total population of target areas | 20% of total population of target areas
Achieved
Source
WHO-UNICEF Joint Report Framework
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%)
INPUTS (HR) | HR and operation costs are shared equally between outputs
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025) | Assumptions
Primary health care facilities and schools in zero-dose and high out-of-school LGAs are renovated, rehabilitated and equipped to ensure climate and disaster-resilient, carbon-neutral and sustainable basic service delivery for vulnerable populations. | Number of PHC/schools with at-least one carbon-emission reduction intervention in place (e.g. solarization) | Planned | 0 (0%) PHC/Schools with at least one carbon emission intervention in place | Identified carbon emission interventions for each of the facilities and procurement completed | At least 50% of the carbon emission intervention implemented | 54 (100%) PHC/schools with at least one carbon emission intervention in place | 54 (100%) PHC/schools with at least one carbon emission intervention in place
Achieved
Source
Rapid assessment for vulnerability to, and sustainability in the face of, environmental and climate change issues and final Project Report/ Programme Monitoring Reports
| Number of PHC/schools with climate resilient infrastractures in place | Planned | 0 (0%) PHC/schools with climate resilient infrastractures in place | Identified climate resilient infrastructure upgrade for each of the facilities and procurement completed | At least 50% of infrastructure upgrades completed | 100% (54 facilities) of infrastructure upgrades completed | 100% (54 facilities) of infrastructure upgrades completed
Achieved
Source
Rapid assessment for vulnerability to, and sustainability in the face of, environmental and climate change issues and final Project Report/ Programme Monitoring Reports
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| Number of health care facilities and schools with climate resilient WASH infrastructure | Planned | 0 | Design and procurement process for all 54 facilities completed | At least 50% of infrastructure upgrades completed | 100% (54 facilities) of infrastructure upgrades completed | 100% (54 facilities) of infrastructure upgrades completed
Achieved
IMPACT WEIGHTING (53%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%) |  |  |  |  | Other (£) | Total (£)
INPUTS (HR) | HR and operation costs are shared equally between outputs
OUTPUT 2 | Output Indicator 2.1.a |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025) | Assumptions
Output 2: Social service systems (Health and education) are strengthened for enhanced service delivery and sustainability. | Number of PHC staff trained on management and maintenance of installed solar systems and low carbon emission equipment or devices | Planned | Not Applicable | 40 (50%) Maintenance of solar systems and low-carbon emission equipment intergrated in the PHC comprehensive plan and budget | N/A | N/A | 80 (100%) Maintenance of solar systems and low-carbon emission equipment intergrated in the PHC comprehensive plan and budget
Achieved
Source
Project Report - to be received in 2025
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| % of schools meeting at least 70% of safe school minimum standards, including for climate resilience | Planned | TBD (data pending, Feb 2024) | Monitoring conducted mid-2024 shows progress over baseline (TBD) | n/a | n/a | All intervention schools demonstrate 70% of the minimum standard, including for climate resilience | Climate-resilience renovations and repairs will contribute to the schools' adherence with the safe school minimum standards, especially in these 2 result areas/pillars
Achieved
Source
Safe schools minimum standards monitoring and dashboard
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| Number of children able to access continuous learning during climate or other disasters | Planned | 0 | 30 schools (180 classrooms) equipped with solar radios | n/a | n/a | 10,500 children | Equipment effectively delivered; equipment kept easily accessible to be rolled out as necessary during disaster; school personnel capacity to use and deliver distance learning is maintained
Achieved
Source
Supply/distribution reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| # of WASH Committees (WASHCOMs) capacity strengthened on operation and management of the climate resilient WASH services in PHCs and schools | Planned | 0 | 0 | 27 | 54 | 54
Achieved
Source
Project Report - to be received in 2025
IMPACT WEIGHTING (22%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%)
INPUTS (HR) | HR and operation costs are shared equally between outputs
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025) | Assumptions
Output 3: Climate risks and facility level assessment carried out for vulnerability to, and sustainability in the face of, climate change impacts. | Assessment and solution selection approach developed, pilot tested and agreed by CRIBS expert and oversight group | Planned | 0 | Final tools, approach validated and endorsed by the Expert Group |  |  | Final tools, approach validated and endorsed by the Expert Group
Achieved
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| # of communities assessed for climate risks and vulnerability and data analysed | Planned | N/A | 54 assessment completed | Final report validated and endorsed by Experts Group |  | Report summarising assessment and solution selection approach, with LGA analysis and solution selection completed.
|  | Achieved | 54
Source
Assessment report
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (March 2025)
| #of PHCs, schools assessed for climate climate risks vulnerability, data analysed and solutions identified | Planned | N/A | At least 54 facilities assessment completed, and design, BOQ and tender documents approved |  |  | Final report summarising the assessment approach and solution selection validated by the Expert Group.
|  | Achieved | 54
Source
Rapid assessment for vulnerability to, and sustainability in the face of, environmental and climate change issues and final Project Report
IMPACT WEIGHTING (16%)
INPUTS (£) | FCDO (£) Govt (£) Other (£) Total (£) FCDO Share (%)
INPUTS (HR) | HR and operation costs are shared equally between outputs
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cut - No longer a major focus.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain - sceptical on whether we will see this by March 2025
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove - Not a major focus
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain - Focus on solar usage?
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove
Note on B67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove
Note on B72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on B92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Retain
Note on E57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure training will necessarily translate to inclusion in plan/budgets, we would need to advocate for that