## Master-sheet-FCDO
PROJECT NAME | CDB Special Development Fund (SDF 10) for the period 2021-2024 - Log frame drafted as part of Business Case preparation in 2020/early 2021. Minor edits made to the indicators (to update RMF titles) were made following updates to the CDB Strategic Plan in Q4 2021 to ensure these matched the new RMF.
IMPACT | Impact Indicator 1 |  | Baseline 2019 | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
Regional progress towards selected Caribbean-specific SDG targets and development outcomes | GDP per capita growth rate (%) As of 2023 this does not include Haiti | Planned |  | >1.7% | >1.7% | >1.7% | >1.7%
|  | Achieved | 1.7% | 3.3% | 10% | 11.3%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.6. Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.6.
OUTCOME | Outcome Indicator 1 |  | Baseline 2018 | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024) | Assumptions
CDB's contribution to country and regional outcomes | Secondary School graduates achieving 5 CXC General Proficiency or equivalent in National Assessment passes or more (including Maths and English) (% male, %female) | Planned (m, f) |  | 40%, 45% | 45%, 50% | 55%, 60% | 65%, 65% | Partner governments are able to sustain the benefits of SDF programmes and are able to generate sufficient resources for other investments required to meet the SDGs as well as create the right environment for private sector investment.
|  | Achieved (m, f) | 31.8%, 38.7% | 38.5%, 42.3% | 22.2%, 24% | 33.4%, 35.3%
|  | Planned (CDB) (m, f)* |  | 35%, 41% | 37%, 43% | 39%, 45% | 42%, 47%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.7. Special Development Fund Annual Report 2023 and Finacial Projections 2024-2026. Table 3.3, Indicator 7, p26 (targets updated 2023) Baseline: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.7. * Male, female
| Outcome Indicator 2 |  | Baseline 2016 - 2019 | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Social Protection expenditure as a percentage of GDP (%)* | Planned |  | 2.8% | 3% | 3.3% | 3.5%
|  | Achieved | 2.4% |  | 5.9% | 2.1%
|  | Planned (CDB) |  | 2.8% | 3% | 3.3% | 3.5%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.5. Special Development Fund Annual Report 2023 and Finacial Projections 2024-2026. Table 3.32(B), Indicator 5, p25 Baseline: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.5. *This indicator was updated in Q4 2021 to better reflect UK priority areas and align better with output indicators below(previously it related to regional trade)
| Outcome Indicator 3 |  | Baseline 2018 | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| RE as a % total energy mix produced | Planned |  | 23% | 25% | 28% | 30%
|  | Achieved | 20 | 13% | 14% | Not Available
|  | Planned (CDB) |  | 23% | 25% | 28% | 30%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.14. Special Development Fund Annual Report 2023 and Finacial Projections 2024-2026. Table 3.6, Indicator 14, p29 Baseline: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.14.
| Outcome Indicator 4 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Reported economic losses resulting from natural disasters and climate vulnerability (% GDP, 3 year average) | Planned |  | <8.6% | <5% | <3% | <1.5%
|  | Achieved | 8.6% | 2.4% | 2.51% | 2.5%
|  | Planned (CDB) |  |  |  |  | <1.5%
Source
Sources: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.16. Special Development Fund Annual Report 2023 and Finacial Projections 2024-2026. Table 3.6, Indicator 16, p29 Baseline: CDB SDF Results Framework 2021-2024. RMF Level 1, Indicator 1.16.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (US$) |  | DFID SHARE (%)
| 21000000 |  |  |  | 222 million |  | 12%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024) | Assumptions
Project Outputs - direct impact of SDF10 projects across CDB BMCs | Classrooms and Educational Support facilities build/upgraded according to minimum standards (cumulative* 2021 - 2024) | Planned |  | 200 | 800 (600) | 1250 (450) | 1,634 (384) | Project outputs will be used by local populations and maintained to a reasonable standard by borrowing country governments and will therefore contribute positively to development outcomes. Borrowing country governments and local populations maintain high quality and good availability of staff and materials (books, equipment etc.)
|  | Achieved | 473 | 210 (210) | 479 (269) | 730 (251)
|  | Planned (CDB) |  | 280 | 780 | 1280 | 1,634 (384)
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.1. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.8(A), Indicator 1, p30 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.1. *Data reported is cumulative 2021 - 2024 and is for Regional Projects and Groups 2/3 Countries.
| Output Indicator 1.2 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Land improved through irrigation, drainage, and/or flood management (hectares - cumulative* 2021 - 2024) | Planned |  | 205 | 500 (295) | 750 (250) | 1000 (250)
|  | Achieved | 285 | 0 (0) | 295 (295) | 485 (190)
|  | Planned (CDB) |  | 225 | 500 (275) | 750 (250) | 1000 (250)
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.5. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.9(B), Indicator 5, p31 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.5. *Indicator is cumulative 2021 - 2024 and is for Regional Projects and Groups 2/3 Countries.
| Output Indicator 1.3 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Renewable power generation capacity installed (MW- cumulative) | Planned |  | 1 (1) | 2 (1) | 3 (1) | 4 (1)
|  | Achieved | 1 | 2.3 (2.3) | 2.3 (0) | 2.3 (0)
|  | Planned (CDB) |  | 1 (1) | 2 (1) | 3 (1) | 4 (1)
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.22. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.9(B), Indicator 5, p31 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.22. Indicator is cumulative 2021 - 2024 and is for Regional Projects and Groups 2/3 Countries.
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| MSMEs benefitting from credit (number) BMCs with increased capacity to undertake PPP arrangements (number, cumulative) | Planned |  | 18 | 292 | 394 | 1166
|  | Achieved |  | 47 | 245 | 273
10% |  | Planned (CDB) |  | 18 | 292 | 394 | 1,166
Reduced from 20% |  | Source | [5 empty] | RISK RATING
|  | Source: CDB SDF Results Framework 2021-2024. RMF Level 3.6, Indicator 17 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3.6, Indicator 17 Indicator is cumulative 2021 - 2024 and is for Regional Projects and Groups 2/3 Countries. | [5 empty] | medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 21000000 | [5 empty] | 12%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024) | Assumptions
Strategic focus - Banks alignment with UK priority issues (gender, climate, private sector work) as part of SDF10. These were issues prioritised by the UK during SDF negotiations and Bank agreement to prioritise these was a significant part of UK agreement to contribute to SDF10. | Approved projects with a) gender mainstreamed rating or b) gender-specific (as a % of total projects) | Planned |  | a) 70% b) 2% | a) 80% b) 5% | a) 90% b) 8% | a) 90% b) 10% | Focus on priority areas identified will lead to improvements in the quality of design for SDF projects and will not contribute negatively to the speed or quality of delivery and monitoring, thereby leading to improved development outcomes
|  | Achieved | a) 70% b) 0% | a) 88% b) 3% | a) 68% b) 4% | a) 76% b) 4%
|  | Planned (CDB) |  | a) 67% b) 1% | a) 68% b) 4% | a) 75% b) 4% | a) 85% b) 5% (orginally a) 90% b) 10%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.16. Indicator is as a % of all projects. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.17, Indicator 16a, 16b, p40 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.21. Indicator is cumulative 2021 - 2024 and is for Regional Projects and Groups 2/3 Countries.
| Output Indicator 2.2 |  | Baseline | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| SDF Approvals Supporting Building Environmental Resilience SDF Approvals supporting environment, renewable energy/energy efficiency and climate change Bank management agreed to revise the target for environmental resilience financing upwards to 27% bank wide. We have retained the 21% target as a reasonable 2023 milestone towards the more modest current level of ambition, albeit there will need to be substantially increased ambition to meet even this level of expectation. | Planned |  | Not Available |  |  | 21%
|  | Achieved | 24.6% (2021) | 24% | 8% | 14%
|  | Planned (CDB) |  | Not Available | Not Available | Not Available | 21%
Source
Source: ANNUAL REPORT 2023 AND FINANCIAL PROJECTIONS 2024-2026 CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.19(a). Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.19(a). Figure is as a % total of SDF financing. CDB are now tracking approvals by SDF theme and targets have been adjusted to be more aligned with the indicative programming identified in the SDF 10 Contributors' report (Box 4). This shows the indicative programming for SDF 10 (20.9). Consistent with the SDF 10 2023 annual report (table 3.17). The planned milestones shown are obsolete and the planned target is now 21% for 2024 This is Based on the suggestion by Contributors during the Mid-Term review of SDF 10 that approvals be tracked by theme.
| Output Indicator 2.3 |  | Baseline (2017 - 2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| SDF Approvals supporting Building Economic Resilience for Inclusive Growth SDF Approvals supporting Private Sector Development | Planned |  | Not Available | 7.9% | 13% | 11%
|  | Achieved | 2.9% (2021) | Not Available | 15% | 16%
|  | Planned (CDB) |  | Not Available | Not Available | Not Available | 11% (Previously 18%)
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.19(c). Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.19(c). Figure is as a % total of SDF financing. CDB, are as of 2023, tracking approvals by SDF theme and targets have been adjusted to be more aligned with the indicative programming identified in the SDF 10 Contributors' report (Box 4). Consistent with the SDF 10 2023 annual report (table 3.17).
| Output Indicator 2.4 |  | Baseline (2020) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Climate Related Commitments (adaptation and mitigation finance) (% Bank commitments) | Planned |  | 18% | 20% | 22% | 25-30%
|  | Achieved | 13% | 8% | 24% | 13.6%
|  | Planned (CDB) |  | 13% | 18% | 24% | 25-30%
Source
Source: CDB Strategic Plan 2022 - 2024. RMF Level 4.6. Baseline Source: CDB Strategic Plan 2022 - 2024. RMF Level 4.6. This target is a corporate level indicator, rather than SDF specific.
| Output Indicator 2.5 |  | Baseline (2017 -2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Financing directed to less developed BMCs (% 3 year average) | Planned |  | 78% | 79% | 79-80% | 80%
|  | Achieved | 63% | 57% | 73% | 62%
|  | Planned (CDB) |  | 78% | 79% | 79-80% | 80%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.16. Indicator is as a % of all projects. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 17 Level 3, Indicator 14, p93 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.21.
IMPACT WEIGHTING (%) | Output Indicator 2.6 |  | Baseline (2017 -2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| No of BMCs with strengthened resilience and gender responsive adaptive capacity to climate related hazards (including DRR strategies)- cumulative | Planned |  | 2 (2) | 3 (1) | 4 (1) | 4 (0)
|  | Achieved | X | 1 | 1 | 1
30% |  | Planned (CDB) |  | 2 (2) | 3 (1) | 4 (1) | 4 (0)
|  | Source | [5 empty] | RISK RATING
|  | Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.26. Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 2, Indicator 2.26. | [5 empty] | medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 21000000 | [5 empty] | 12%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024) | Assumptions
Operational quality and effective portfolio performance - Assessing whether CDB is making improvements across operational areas identified by the UK as affecting CDB project effectiveness | Portfolio performance rating for implementation (% rated highly satisfactory to satisfactory) | Planned |  | 97% | 97 - 98% | 90% | 90% | Faster and more effective project administration does not come at the expense of the quality of design and monitoring and as a result contributes to positive development outcomes by allowing the CDB to do more in a shorter space of time
|  | Achieved | 97% | 52% | 67% | 66%
|  | Planned (CDB) |  | 97% | 97-98% | 97-98% | 98%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.1. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.15, Indicator 1, p39 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.1.
| Output Indicator 3.2 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Approved Country Strategies in use with results frameworks (number) | Planned |  | 6 | 7 | 8 | 9
|  | Achieved | 5 | 7 | 5 | 6
|  | Planned (CDB) |  | 5 | 7 | 8 | 9
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.15. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.17, Indicator 15, p40 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.15.
| Output Indicator 3.3 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Average time taken from appraisal mission to first disbursement (months) | Planned |  | 10 | 8 | 7 | 6
|  | Achieved | 12 | 6 | 12 | 15
|  | Planned (CDB) |  | 10 | 8 | 7 | 6
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.4. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.15, Indicator 4, p39 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.4.
| Output Indicator 3.4 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Projects under implementation with extensions (%) | Planned |  | 60% | 57% | 54% | 50%
|  | Achieved | 62% | 58% | 67% | 50%
|  | Planned (CDB) |  | 58% | 57% | 54% | 50%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.5. Special Development Fund Annual Report 2023 and Finnacial Projections 2024-2026. Table 3.15, Indicator 5, p39 Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.5.
| Output Indicator 3.5 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Disbursement (efficiency) rate (%) (without PBLs) | Planned |  | 100% | 100% | 100% | 100%
|  | Achieved | 239% | 54% | 105% | 178%
|  | Planned (CDB) |  | 90% | 90% | 95% | 100%
Source
Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.13. Baseline Source: CDB SDF Results Framework 2021-2024. RMF Level 3, Indicator 3.13.
IMPACT WEIGHTING (%) | Output Indicator 3.6 |  | Baseline (2021) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
35% Up from 30% | Client Satisfaction Survey (% clients satisifed with CDB's services including lending and non-lending instruments) Indicator has been moved from output 4 to output 3 in 2023, given it aligns closer with operational quality and performance. | Planned |  | 73% | 74% | 74-75% | 75
|  | Achieved | 73% | Not available | Not available | 70%
|  | Planned (CDB) |  | 73% | 74% | 74-75% | 75%
|  | Source | [5 empty] | RISK RATING
|  | Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.8 (Indicator added in Q4 2021 following addition to 2022 - 2024 RMF) Baseline Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.8 (Indicator added in Q4 2021 following addition to 2022 - 2024 RMF) | [5 empty] | medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 21000000 | [5 empty] | 12%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 4 - All indicators only in DER which records Bank wide results | Output Indicator 4.1 |  | Baseline (2017 - 2019( | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024) | Assumptions
Organisational effectiveness of CDB (administration and human resources) - Assessing whether CDB is making internal improvements in areas identified by the UK as critical for VfM and ensuring the Bank is internally effective. All output 4 indicators relate to the CDB institution as a whole and are not specific to the work of the SDF programme. | Administration expenses per 1 million US$ of project disbursements (3 year average) $000s | Planned |  | 125 | 130 | 140 | 158 | Improved organisation effectiveness, in terms of administration and human resources, does not come at the expense of programmatic effectiveness and the design and delivery of CDB projects and contributes postively to development outcomes by allowing the CDB to do more with fewer or equal resources
|  | Achieved | 120 | 106 | 121 | 143
|  | Planned (CDB) |  | 141 | 158 | 185 | 158
Source
Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.5. Baseline source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.5.
| Output Indicator 4.2 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Ratio of professional staff to support/administrative staff | Planned |  | 2.01:1 | 2.2:1 | 2.4:1 | 2.61:1
|  | Achieved | 1.98:1 | 2.01:1 | 2.5:1 | 3.78:1
|  | Planned (CDB) |  | 2.01:1 | 2.2:1 | 2.4:1 | 2.61:1
Source
Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.2 Baseline Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.2
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (2019) | Milestone 2021 | Milestone 2022 | Milestone 2023 | Target (2024)
| Staff in management positions who are women (%) | Planned |  | 40% | 45% | 50% | 45 - 55%
|  | Achieved | 36% | 35% | 38% | 37%
25% |  | Planned (CDB) |  | 40% | 38-40% | 41-43% | 45-55%
Up from 20% |  | Source | [5 empty] | RISK RATING
|  | Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.4 Baseline Source: CDB Strategic Plan Update 2022 - 2024. RMF Level 4.4 | [5 empty] | High (updated in 2023 from medium)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 21000000 | [5 empty] | 12%
INPUTS (HR) | DFID (FTEs)
0.5
Note on C56: Nick Wright (Regional Development Banks): Indicator changed by FCDO team to better reflect the Banks work in the private sector
Note on C73: Nick Wright (Regional Development Banks): Indicator updated in 2022 as the Bank changed the metric it tracked.
Note on C79: Nick Wright (Regional Development Banks): Indicator updated in 2022 as the Bank changed the metric it tracked.
Note on I38: Nick Wright: 1822 Until 2022
Note on I40: Nick Wright: 1822 Until 2022
Note on I79: Nick Wright: Target updates as per banks revision
Note on I81: Nick Wright: Target updates as per banks revision
Note on I97: Nick Wright: Target updated in 2023 to 4 from 5 a in the context of achievability of milestones and banks own advice
Note on I99: Nick Wright: Target updated in 2023 to 4 from 5 a in the context of achievability of milestones and banks own advice