## Annual Review

Title: Climate Resilient Infrastructure for Basic Service (CRIBS) – Health and Education
Programme Value £ (full life): Up to £19 million		Review date: 11 June 2025
Programme Code: 400118	AMP start date: 1/04/2024	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006303.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006179.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
Programme Overview
‘Climate Resilient Infrastructure for Basic Services – Health and Education’ (CRIBS) will spend up to £19 million over 2024-2026 on climate adaptation in health and education in Nigeria, in partnership with the Nigerian government, and implemented by UNICEF. We developed the CRIBS approach through a partnership of organisations and experts, working through a ‘CRIBS Expert and Oversight Group’. Initial plans were for a single year of CRIBS implementation in Kano and Jigawa States, but budget allocations for financial year 2025-26 have enabled a second phase that will focus on working in partnership with the Federal government and leadership of a wider set of states to support the delivery of health and education sector transformation goals.
Nigeria is highly vulnerable to the impacts of climate change and ranks in the bottom 15 countries globally for climate change readiness (in the Notre Dame Global Adaptation Initiative (ND-GAIN) index). CRIBS aims to develop and test a scalable model to improve climate resilience of primary healthcare clinics (PHCs) and schools in Nigeria, with the goal of national scale-up by the Nigerian government. It aims to minimise the impact of climate change on access to quality health and education services through a comprehensive system for: (1) assessing facility level climate risks and vulnerabilities; (2) identifying capital / infrastructure interventions to minimise those risks; and (3) implementing these interventions in existing PHCs and schools. By ensuring context-responsive, climate-resilient infrastructure, CRIBS will ensure that people can access health services and children can continue to learn in schools in the face of the growing impacts of climate change – for example during heatwaves (by ensuring classrooms are cooler so children can continue to learn), and flooding (by ensuring continued access to clean water necessary for safe health services). CRIBS will contribute to the ability of communities in Nigeria to adapt to climate shocks, and to protect the most vulnerable in particular.
As far as we are aware, CRIBS is the first attempt to develop and implement a comprehensive approach to understanding and addressing the climate vulnerabilities of health and education facilities in low or lower-middle income country (LIC / LMIC) contexts. The first year of the programme has focused on developing the CRIBS approach and testing this in two States: Kano and Jigawa. The second year will focus on integrating this into wider government revitalisation programmes for health and education facilities to drive scale-up across the country.
Approach to CRIBS development
In developing and implementing CRIBS, as FCDO and UNICEF we have drawn on global experts through an Expert Oversight and Advisory Group, as well as targeted support from the World Health Organisation (WHO), Crown Agents, World Bank, Jigsaw Consulting and Fab Inc. This has both improved the quality of the work and built a wider constituency that are engaged with ensuring the scale-up and sustainability of the approach. The primary driver of sustainability is the quality of the partnership with the government of Nigeria and local communities – and this is reflected in CRIBS’ approach to working closely with Federal government, State governments, local government and communities in the selection of facilities and design of interventions.
CRIBS is supported by a research element funded through FCDO’s West African Research and Innovation Hub (WARIH) which will evaluate the effectiveness of the CRIBS approach. This will gather the knowledge generated through CRIBS to inform domestic scale-up within Nigeria, and support dissemination to contexts beyond Nigeria – with other countries already reaching out to learn how to replicate this approach given the growing importance of climate adaptation in health and education.
Approach to CRIBS scale-up and transition to self-reliance
CRIBS has maintained a focus on government partnership from the outset, including the potential for future scale-up through domestic resource to drive impact at scale. FCDO Nigeria health and education advisers have worked with the Nigerian government and the World Bank to incorporate the CRIBS approach into the disbursement linked indicators (DLIs) in both the ‘HOPE PHC’ and ‘HOPE Education’ World Bank ‘Payment for Results’ operations. These are large health and education sector transformation programmes, which will provide strong monetary incentives for the Nigerian government to deliver the CRIBS approach at scale (for example, HOPE PHC provides incentives to scale-up the CRIBS approach to 2,000 PHCs across Nigeria). FCDO Nigeria health advisers are working closely with the National Primary Health Care Development Agency (NPHCDA) to incorporate the CRIBS approach in the government’s ‘Primary Health Care Revitalisation Programme’, including integrating core CRIBS elements into the baseline facility assessment covering 9,000 facilities. FCDO Nigeria education advisers are seeking opportunities to support CRIBS integration into Federal and State education facility revitalisation efforts. The next phase of CRIBS will be focused on the partnership between CRIBS and Federal government and State leadership to ensure that it supports the delivery of government of Nigeria health and education sector transformation goals.
UK-Nigeria partnership on climate adaptation in health and education
CRIBS is part of the wider UK-Nigeria partnership on climate adaptation in health and education. There is a strong policy window for driving forward action on this priority following the appointment of Professor Muhammad Ali Pate as Coordinating Minister for Health and Social Welfare in August 2023, who has marked Nigeria out as a leader in this area at COP28 and COP29. This has latterly extended to the education sector following the appointment of Dr Tunji Alausa as Federal Minister of Education in October 2024. This is complemented by sub-national leadership on climate adaptation, particularly by the Governor of Jigawa HE Umar Namadi. This partnership includes:
- Direct engagement by FCDO technical experts and programme-funded technical assistance (TA) to support Nigerian government policy and planning. For example, Minister Pate commissioned Nigeria’s first ever climate and health ‘Vulnerability and Adaptation Assessment’ (VAA) and ‘Health National Adaptation Plan’ (HNAP), and the UK provided funding and technical assistance to deliver this through the ‘Climate Resilient and Sustainable Health Systems’ centrally managed programme (CMP) and the ‘Lafiya’ bilateral health systems strengthening programme. Our experts are also working closely with the Nigeria Climate Change Committee (NCCC) on adaptation commitments for health – and exploring opportunities to engage on education – in Nigeria’s Nationally Determined Contributions (NDCs) ahead of COP30.
- On the ground implementation of priority actions on upgrading existing health and education infrastructure through CRIBS, working hand in glove with government to build our shared understanding of ‘what works’ against a backdrop of scant global evidence or guidelines.
- Direct engagement of multilateral and wider development partners by FCDO technical experts – both bilaterally and through convening development partner groupings – to drive alignment and coherence of health and education climate adaptation work by development partners in Nigeria. These include multilateral partners that the UK is a major investor in, such as the World Bank, the Global Partnership for Education, and the Global Fund to Fight AIDS, TB and Malaria.
Across these inter-linked strands of work, our partnership aims to contribute to the outcome of greater climate adaptation in the health and education sectors in Nigeria.
Key CRIBS achievements in year 1
- Developing and field testing a new approach (with corresponding tools) for vulnerability analysis and intervention selection at PHCs and schools. The approach and tools were field tested in Kano state and later validated at two levels – first by the State level authorities in Kano and Jigawa, and second by the CRIBS Expert Advisory and Oversight Group.
- Implementing a full package of climate adaptation interventions in 14 facilities (8 schools and 6 PHCS) in Kano and Jigawa based on their climate vulnerabilities, with a further 67 on schedule to complete by the end of June.
- Securing national and global recognition for the CRIBS approach as a much-needed comprehensive approach to understanding and addressing climate risk of health and education facilities in LIC / LMIC settings. There has been substantial buy-in from government stakeholders reflected by the integration of CRIBS into their programmes and policies (for example, ‘HOPE PHC’ and ‘HOPE Education’). At the global level there has also been interest in adopting the CRIBS approach in other countries, which has resulted in government-led programmes in both Sudan and South Sudan, with interest emerging from more countries.
Summary supporting narrative for the overall score in this review
CRIBS has performed strongly in the context of a highly ambitious set of aims, and a challenging timeline for a new capital investment programme. The development of the CRIBS vulnerability assessment and intervention selection approach and tools met expected log-frame targets, while also achieving a far higher level of interest and buy in than was anticipated, including internationally.
The level of interest generated in CRIBS is a reflection of the quality and comprehensiveness of the approach, whilst remaining applicable and acceptable in a LIC / LMIC setting like Nigeria. This work has also closed a major global gap in terms of practical and usable climate vulnerability assessments and interventions selection approaches at the facility level. Moreover, owing to the integration of the approach into government plans, such as the World Bank ‘HOPE Health’ operation, we are likely to see wider impact well beyond the aims and funding package of the original programme.
Whilst the physical implementation of the interventions at facility level is a little behind schedule, this is due to a very ambitious original timeline for implementation. This was added to as the programme approach proved more efficient than expected and generated under-spends, which we decided to re-invest in increasing the number of facilities we would upgrade relatively late in the programme year. Interventions are well under way across all facilities and are expected to be completed by the end of June 2025, with handover to state authorities following shortly afterwards.
Recommendations for the year ahead
Recommendation 1: The design for the next phase of CRIBS should integrate learning from the first phase and from the CRIBS research component. This includes, but is not limited to:
- The challenges of cooling spaces and installing ventilation in spaces where there is a greater need for privacy (e.g. labour wards).
- Drawing on early findings from the pilot study being conducted by the research component in Lagos State.
- Exploring a wider range of interventions and adopting a more experimental approach where appropriate.
- Recommendation 2: The next phase of CRIBS should consider how the approach and learnings from the last year could be applied to the construction of new facilities (as CRIBS has only supported the renovation of existing facilities), given the considerable interest in expanding health and education service coverage, as well as the wider range of options this would create for climate resilience interventions.
- Recommendation 3: Operation and maintenance (e.g. of solar panels and pumps) is a major challenge for the long-term impact of CRIBS. We are already in discussion with State governments around the governance and sustainable financing for this, but should link with sister FCDO technical assistance (TA) programmes working in Kano and Jigawa (Partnership for Learning for All in Nigerian Education (PLANE), Partnership for Agile Governance and Climate Engagement (PACE), and Lafiya – UK Support for Health in Nigeria) to explore different options and support the development of state-led systems or public-private-community partnerships.
- Recommendation 4: There is significant interest in adopting the CRIBS model from a range of Nigerian states and the Federal government, as well as other countries (e.g. Sudan, South Sudan and South Africa). Taking advantage of this opportunity will require addressing significant capacity gaps at both the national and sub-national level. We should therefore explore how to crowd-in resources to help develop accessible and practical tools and intervention specifications that can enable easy uptake and adaptation of the CRIBS approach. This is particularly urgent given the upcoming availability of finance for climate-resilient infrastructure through the World Bank ‘HOPE PHC’ and ‘HOPE Education’ operations, which provide a considerable incentive and opportunity for states if they have sufficient capacity in place.
- Recommendation 5: We need to update the CRIBS log-frame to increase ambition following confirmation of the programme budget for the 2025/26 financial year and to integrate International Climate Finance (ICF) outcome indicators.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The CRIBS theory of change can be summarised as:
“IF facility level climate hazards, and specific climate vulnerabilities in PHCs and school facilities are assessed and IF this information is used to design a package of climate resilient (CR) interventions, and IF these CR interventions are implemented, THEN, those PHCs and schools become more resilient to climate risks and vulnerabilities. Subsequently, the vulnerable children and their care givers relying on those PHCs and schools would have more reliable access to the critical health and education services.
Furthermore, CRIBS made the assumption that IF local and state government officials have the technical capacity to plan for and finance the maintenance and further adaptation of the climate resilient infrastructure, and IF facility personnel, local communities and beneficiaries themselves have the knowledge and skills needed to care for, maintain, and fully utilise these facilities to protect themselves from the impacts of climate change, THEN climate-resilient health and education infrastructure will be sustainable and climate resilience will be institutionalised as an approach in the health and education sectors.”
The main elements of the CRIBS theory of change remain valid and in line with the experience of the programme. One element that will be further explored and tested this year is around the assumptions made regarding local capacity for operating and maintaining the interventions. Progress has been made towards capacity building of communities, and a range of options are being explored for financing maintenance, but this remains a major challenge for infrastructure projects in general that requires addressing. We will address this through engaging our TA programmes in line with ‘Recommendation 3’ in Section A.
The ‘Outcome’ and ‘Impact’ indicators have been refined from the original log-frame to reflect:
- The types of impacts that are realistic to observe during the timeframe of the programme (i.e. a focus on changes in conditions in facilities rather than changes in learning outcomes etc.)
- Decisions made regarding the types of interventions (e.g. implementation of solar power infrastructure only in PHCs given the relative cost-effectiveness); and
- Limitations to the extent of monitoring on some indicators due to challenges in aligning the research and construction timelines.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
CRIBS is on track to meet its expected outcomes and impact. The sole outcome indicator is focused on reduced climate vulnerabilities at the facility level, while the three impact indicators relate to improvements in specific climate resilience indicators (i.e. reduced temperatures and improved access to water and power).
We have set outcome and impact indicator targets for January 2026 to ensure that there is sufficient time to observe and evaluate performance following the completion of facility level interventions. Implementation is expected to be completed by the end of June 2025.
CRIBS is well placed to have significant impact beyond the elements set out in the log-frame, particularly given the national and global interest, and the discussions with government around national scale-up, including through the World Bank ‘HOPE-PHC’ and ‘HOPE-Education’ operations, and through State budget allocations (e.g. Jigawa State).
Plans for the coming programme year will involve an expansion of the number of CRIBS facilities and the State footprint – in line with government direction and alignment with the Sector Wide Approach (SWAp) in health and coordination measures in the education sector. The approach will also learn from the experience of the first year of CRIBS, in line with the recommendations made by this AR.
We will also undertake aligned activities to strengthen uptake of the CRIBS approach. We will develop an online tool that encompasses the climate risk and vulnerability assessment, the intervention selection process, and detailed guidance on how to implement the interventions. We will be engaging more closely with the Universal Basic Education Commission (UBEC) on climate adaptation in the education sector and the potential of the CRIBS model, and discussions are ongoing regarding utilising some of the Global Partnership for Education (GPE) System Capacity Grant to fund TA to facilitate this.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
CRIBS has demonstrated strong performance in its first year of operation. In partnership with the government, we developed, tested, and validated a novel approach to assessing and addressing climate vulnerabilities at the facility level. We also made strong progress towards facility level implementation at a higher level of ambition in terms of the number of facilities reached, given the cost-effectiveness of the model. The consultative approach and engagement with the World Bank on their ‘HOPE’ operations has helped create an enabling environment where funding for scale up is available. CRIBS also has the potential to work closely with FCDO Nigeria TA programmes, including PLANE, Lafiya and PACE, to maximise the sustainability of the approach through supporting government partners to move forward with sustainable governance and financing for this approach.
CRIBS delivers on two of the areas within the Nigeria-UK Strategic Partnership signed by the Foreign Secretary in November 2024: to work with Federal and State government, as well as businesses, to address climate change in key sectors’; and to work together to … support human capital development. This reflects the FCDO priorities on ‘climate’ and ‘development’, and the ‘global health’ priority under development. The partnership approach with the Nigerian government – evidenced by the progress on national scale-up through domestic resources – also exemplifies the ‘new approach with Africa’ of respectful partnerships focused on long-term solutions. This is also a clear commitment in the Nigeria-UK Strategic Partnership: Nigeria and the UK are committed to a partnership that encourages long-term and sustainable development by building local institutional capacity and capability to address needs and priorities.’
Ending the programme at this point will mean a significant missed opportunity to move from CRIBS concept development and testing to integration and scale up in alignment with national health and education revitalisation programmes. An additional year of work to take the programme to its full business case length will help increase the number of facilities directly reached by CRIBS, allow further refinement of the CRIBS approach and see its full integration into government health and education facility development approach – as well as delivering on key pillars of the Nigeria-UK Strategic Partnership.

## C. DETAILED OUTPUT SCORING

Output Title	Primary health care facilities and schools in zero-dose and high out-of-school LGAs are renovated, rehabilitated and equipped to ensure climate and disaster-resilient, carbon-neutral and sustainable basic service delivery for vulnerable populations
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of PHC with at-least one carbon-emission minimisation intervention in place (e.g. solarisation)	65% (29) of CRIBS treatment PHCs have at least one carbon emission minimisation intervention in place	Partially not met. / No facilities have yet had interventions for carbon emission reduction (i.e. solar equipment) put in place, although this is in process and expected to be completed in June 2025.
1.2 Number of PHC / schools with assessment identified interventions in place	65% (57) CRIBS treatment facilities have interventions in place that address all climate vulnerabilities identified in assessment that are related to capital investment.	Moderately exceeded. / Interventions to address climate vulnerabilities have been put in place in 96% of facilities (81). Extent of completion varies, but it is anticipated that all interventions will be in place across all facilities by end of June 2025.
1.3 Number of health care facilities and schools with climate resilient WASH infrastructure	65% (57) of planned CRIBS treatment facilities have climate resilient WASH infrastructure in place as identified in the CRIBS climate vulnerability assessment.	Partially not met. / Implementation of WASH interventions is ongoing in 46% of facilities (39), while others will be started after initial construction work is completed.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 focuses on the implementation of interventions in PHCs and schools to address their climate vulnerabilities and adapt them to improve resilience. This is conducted through rehabilitation of existing buildings and facilities, rather than new construction. Given its centrality to the CRIBS programme, this output carries half of the weight of the annual review scoring. The overall score of ‘A’ reflects the fact that whilst two of the three indicators were partially not met, the reasons for this are: (1) the extremely ambitious timeframe for delivery (and the impressive performance in light of this); and (2) the mid-year decision by FCDO to increase the number of facilities in light of cost-savings due to the model proving more efficient than expected. This is further explained in the narrative below.
Specific interventions focused on a combination of rehabilitation to repair damaged infrastructure and retrofitting to ensure resilience to key climate-related risks and disasters. These included flood-resistant foundations; stormwater management; wide windows and doors for natural ventilation; trees for shade and as windbreakers; raised and reinforced roofs; false ceilings; and highly reflective roof materials. We also prioritised improved access to water and sanitation, with the installation of deep solar bore-holes and WASH facilities with climate resilient elements, including flood resistance. Interventions in PHCs also included installation of solar equipment to provide electricity throughout the facility, particularly for cold chain equipment, as well as retrofitting to ensure running water in all wards – necessary to deliver an acceptable standard of healthcare provision.
Progress on intervention implementation – and the output indicators – has been slower than anticipated. As of May 2025, 14 facilities (8 schools and 6 PHCS) are in the final stage of implementation and will be handed over to State authorities by June. Of the remainder, 67 have at least one climate resilient infrastructure adaptation in place and all facilities are on schedule to complete by the end of June.
These delays are in part due to the fact that the aim of developing a novel approach from scratch on this timescale was always extremely ambitious. There was additional development time required on evidence-based approach and tools to assess and address facility climate vulnerabilities, and identification and selection of appropriate facility level interventions. These processes took longer than anticipated, but allowed a high quality of output and strengthened overall buy in to improve overall programme impact. As a result of these delays – and the time taken to contract external engineering firms – actual implementation of interventions did not begin until December 2024.
Another important factor in the delays was the decision by FCDO to increase the ambition from reaching 57 facilities to 84. The original target was based on UNICEF cost estimates, but the process of developing the CRIBS approach demonstrated that the selected interventions could be delivered at a much lower cost and so enabled a stretch target of 84 facilities.
Changes to this output: The most significant change to this output was the increase in the number of facilities targeted from 57 to 84 – an increase of almost 50%. As noted above, this was due to the value for money (VfM) gained through identification of cost-effective and low-cost technologies.
Lessons learned and recommendations
Lesson learned: Based on issues observed during the AR visits, the list of agreed interventions should be revisited for the next phase of CRIBS. One issue is that many of the interventions selected for cooling facilities (as opposed to insulation them from heat) are focused on ventilation and require the presence of some form of cross breeze. This creates challenges for cooling rooms and facilities that require privacy (e.g. labour wards) or are in built up areas where there is less movement of air. Another factor is areas where an absence of drainage affects not only the facility, but the surrounding communities and so improving site drainage alone will be insufficient. Options here include infrastructure changes (e.g. raised walkways) and wider LGA engagement (looking for options to address wider drainage issues).
Recommendation: The next phase of CRIBS should consider a wider range of potential interventions drawing on the lessons learned from the last year and the findings of the CRIBS research team. Consideration should also be given to greater experimentation through variations across facilities to ensure the most cost-effective approaches are being integrated into the model.
Lesson learned: While there were a range of factors that delayed the implementation of interventions, delays in procurement and construction are those that are most likely to be repeated in the next phase of CRIBS. There is also the potential for procurement to be politically sensitive with the Governor of Kano having commented on the absence of local contractors during a visit to one of the CRIBS facilities. The timeline and milestone targets for the next phase of CRIBS should therefore assume an extended procurement window to allow engagement with local contractors and encourage them to bid, as well as a longer timeframe for actual construction.
Recommendation: Log-frame targets should be reviewed to increase the level of ambition following confirmation of the CRIBS budget for the 2025/26 financial year and to ensure that procurement and construction timelines are realistic.

Output Title	Capacity is strengthened at the facility level to improve service delivery and sustainability.
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of PHC staff trained on management and maintenance of installed solar systems and low carbon emission equipment or devices.	65% (29) of CRIBS treatment PHCs have maintenance of solar systems and low-carbon emission equipment integrated in the PHC comprehensive plan and budget	Partially not met. / Installation of solar systems has not commenced and training is scheduled for after this. Several PHCs also have O&M agreements that include maintenance of solar systems.
2.2 Number of WASH Committees (WASHCOMs) whose capacity on operations and maintenance (O&M) of the climate resilient WASH services in PHCs and schools are strengthened	WASHCOMS in 57 CRIBS treatment facilities demonstrate strengthened capacity on operation and management of the climate resilient WASH services in PHCs and schools	Substantially exceeded. / WASHCOMs and facility management teams in 81 facilities have been trained on O&M mechanism and accountability framework.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2 focuses on ensuring that the impact achieved by the interventions funded through CRIBS is sustainable by putting in place capacity building and structures at the facility and community level that will allow effective operation and maintenance of the infrastructure. This comes from a recognition that many infrastructure programmes fail due to a lack of ongoing maintenance. In the context of CRIBS, solar power sources or boreholes often suffer from malfunctions or damage and then are not repaired due to a lack of technical knowledge, financing or community ownership. The overall score of ‘A’ reflects the fact that one of the two indicators was substantially exceeded, and the other was partially not met for reasons described under ‘Output 1’.
Progress against targets under ‘Output 2’ has been mixed, largely due to necessary delays to site implementation to ensure that the approach would deliver on the quality and sustainability desired, as well as the decision to include additional facilities late in the procurement process. Training of Water Sanitation and Hygiene Committees (WASHCOM) and facility management teams on operation and maintenance (O&M) of toilets and water sources has been conducted in 81 of the facilities, which is well beyond the set target. However, training on maintenance of solar systems will not commence until the intervention has been installed in all sites (late June 2025).
As observed during the AR field visits, the consultative approach used by UNICEF has helped build local ownership for the O&M systems. They have also been working with Kano and Jigawa State governments to develop a model for ensuring sustainable O&M of PHCs and primary schools. This includes a concept for public-private-community partnership (PPCP) for which they conducted consultations at three levels in its development: across 20 facilities which focused on identifying challenges to O&M and working up practical solutions; then at the LGA-level, to analyse and refine the challenges and way forward identified during facility-level consultation with stakeholders from 71 LGA; and finally at the state-level, where stakeholders came up with a potential accountability framework for sustainable O&M. These consultations also served to help improve the knowledge and capacity of actors regarding O&M challenges and solutions. The effectiveness of these approaches is still uncertain and this area will remain a key challenge to sustained impact.
The AR field visits highlighted important differences between the health and education sectors. In the health sector, PHCs can draw on the Basic Health Care Service Provision Fund (BHCPF, a government funding mechanism which provides monthly disbursements to facilities) and revenue from service charges to finance ongoing O&M. Whilst these are not large figures, they give some flexible financing to cover critical maintenance issues. At present there is no equivalent fund for primary schools and – formally – there are no mandatory charges. Encouragingly, most PHCs and primary schools visited had O&M contracts in place with a defined service provider (usually the local area mechanic) and responsible authorities at the facility level. PHC facility staff were also aware of the resources of the BHCPF and planned to use these for O&M alongside revenue from service fees. However, discussions with School Based Management Committees and head teachers demonstrated that at present they do not have any consistent source of funding for O&M and are reliant on raising ad hoc resources from the immediate community and school alumni. This raises questions regarding the sustainability of interventions in the primary schools, particularly the solarised boreholes and WASH facilities.
At the State level, Jigawa appears to have advanced further than Kano in terms of focus on O&M. The Secretary to State Government (SSG) of Jigawa State has published an official ‘Guidance Note for Sustainable O&M’ and has directed related Ministries, Departments and Agencies (MDAs), PHCs and primary schools to commence implementation. We will monitor the implementation of this guidance, noting this will ultimately produce little positive impact without corresponding domestic budget allocation and release.
Changes to this output: As with Output 1, the level of ambition was raised as a result of lower than anticipated costs per facility – increasing the facilities targeted from 57 to 84. Consultation at the facility level therefore expanded to the newly added facilities, leading to some delays completing the overall models for facilitating contracts among the stakeholders.
Lessons learned and recommendations
Lesson learned: CRIBS has highlighted several potential mechanisms to support sustained impact through operation and maintenance, including facility level contracts, O&M training for communities and facility staff, and the use of specific federal and state resources, alongside fees for service, to address the issue of consistent funding in primary health centres. However, it has also highlighted more limited options for schools, which are reliant on ad hoc fundraising from communities and School Based Management Committees due to a lack of wider funds and an inability to apply service charges. Working with state governments and communities will be vital to addressing these issues and ensuring sustained impact.
Recommendation: UNICEF should engage with the PLANE programme in Jigawa and Kano to coordinate engagement with state governments to budget for O&M of primary schools, and FCDO should raise this during the next round of the Mutual Accountability Framework discussions with the Governors of Kano and Jigawa.
Recommendation: The next phase of CRIBS should look at a wider range of options for developing and sustaining systems for O&M and the facility level, including the potential for cost-sharing (e.g. charging for community water access) and community ownership. This may involve drawing on PLANE, Lafiya, PACE and relevant FCDO CMPs.
Recommendation: Log-frame targets should be reviewed and the level of ambition re-calibrated following confirmation of the CRIBS budget for the 2025/26 financial year.

Output Title	Climate risks and facility level assessment carried out for vulnerability to, and sustainability in the face of, climate change.
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Assessment and solution selection approach developed, pilot tested and agreed by CRIBS expert and oversight group	Revised tools, approach validated and endorsed by the Expert Group	Met. / Climate vulnerability assessment and intervention selection tool has been developed, validated by a range of actors, updated in consultation with stakeholders and endorsed by the CRIBS Expert Oversight and Advisory Group.
3.2 Number of communities assessed for climate risks and vulnerability and data analysed	At least 92 facilities assessment completed, and report summarising assessment and solution selection approach, with LGA analysis and solution selection completed.	Met. / LGA level analysis completed for 92 facilities assessed, as well as community elements of climate and vulnerability assessment being conducted.
3.3 Number of PHCs, schools assessed for climate risks vulnerability, data analysed, and solutions identified	At least 92 facilities assessment completed, and final report summarising the assessment approach and solution selection validated by the Expert Group.	Met. / The climate and vulnerability assessment was conducted in 92 facilities and details of findings and solution selection shared with and validated by the CRIBS Expert Oversight and Advisory Group.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 focuses on the development and implementation of a climate risk and vulnerability assessment and intervention selection approach. Completion of this output was one of the prerequisites for the selection and implementation of climate resilient interventions in selected facilities. The development of a comprehensive and validated approach has also been critical in the wider sensitisation and dissemination of CRIBS, which is already seeing uptake and scale up both nationally and internationally. The process for the development of the assessment and interventions selection approach has been key to the success of this output areas, with all three targets being met in the annual review year – leading to a score of ‘A’.
A novel tool was developed for assessing the climate risks and vulnerabilities of PHCs and schools, which was then field tested and revised based on initial test results in the second quarter of 2024. This used a combination of secondary data analysis, primary observations, and conducting both interviews and focus group discussions with facility staff, users / students, and community members. The facility level vulnerability assessment, and the tool to select interventions based on the vulnerabilities identified, was validated by the CRIBS Expert and Oversight Group and through workshops with State and Federal government representatives and a range of key stakeholders.
Data was collected from 92 facilities across Kano and Jigawa using this assessment, with a total of 46 enumerators comprising 27 government staff across health and education, and 19 externals with mixed technical backgrounds across WASH (9), education (12), and health (25) – trained and mobilised by UNICEF. Analysis was presented in a dashboard format to the State governments in a workshop on 13-14 June 2024. The State level workshop oriented them to the “what, why and how” of climate resilient interventions, and their feedback was that the CRIBS approach and tools were innovative, contextually appropriate, and useful for the State government. State officials were then provided with the outcomes of survey, and climate risk and vulnerability analysis with ranking of facilities based on the overall vulnerability scores. The State officials then made the final decisions on facility selection for assessment and implementation of interventions.
A further revision on this design took place later in the year to encompass experiences and learning following the facility level assessment, data analysis and interventions selection. This was delivered through a workshop with members of the CRIBS Expert and Oversight Group, Federal, State and LGA representatives. As well as revising and providing a final validation for the CRIBS approach, key aspects of the CRIBS assessment were integrated into National Primary Healthcare Development Authority (NPHCDA) Primary Health Care facility assessment, which was rolled out to 9,000 facilities in 2025.
Changes to this output
No significant changes were made in the last annual review year.
Lessons learned and recommendations
Lesson learned: The piloting of the climate risks and vulnerability assessments and subsequent engagements with both State and Federal level officials highlighted the importance of avoiding use of technical terms and ensuring that questions were simple, but clear in their meaning. It also brought out the ‘Christmas tree’ risk – which is to say that, as additional stakeholders are consulted, the assessment becomes a ‘Christmas tree’ with additional questions or themes being added until it becomes unwieldy. The development of new tools and guidance in the next phase of CRIBS will continue to bear these issues in mind.
Lesson learned: While the specific vulnerabilities identified for individual facilities varied, the overall level of vulnerability were consistently high, and several issues were present across all facilities. This highlights the need for action at scale to address climate vulnerabilities and suggests that a standard package of interventions could still have a significant impact if government procurement systems were unable to offer a more tailored approach. However, regardless of the approach, there will need to be a site visit by an infrastructure engineer to apply context specific interventions that will address the identified climate vulnerabilities identified.
Lesson learned: The approach taken to selecting facilities effectively balanced taking a needs-based approach by initially conducting vulnerability assessments in areas of greater marginalisation (i.e. those with higher levels of unvaccinated children, and higher levels of deprivation), with a sustainability focus by ensuring that State governments alone made the decision on which facilities to prioritise – informed by the technical assessments. We will continue to take this approach the next phase of CRIBS, in line with our partnership approach.
Recommendation: UNICEF and members of the CRIBS Expert and Oversight Groups should work closely with consultants involved in refining the climate vulnerability assessment and interventions selection tool, developing schematic guidance for implementing CRIBS interventions, and launching an online tool to enable wider uptake. This will ensure that lessons learned from CRIBS are built into the design, as well as providing a check on the complexity and utility of the tools being developed.
Recommendation: Log-frame targets should be reviewed and the level of ambition re-calibrated following confirmation of the CRIBS budget for the 2025/26 financial year.

## D: VALUE FOR MONEY

Key cost drivers and performance
CRIBS considered value for money from the five E’s of FCDO’s value for money framework – economy, efficiency, effectiveness and equity (including gender equality and disability), and overall cost-effectiveness.
The explicit intention for CRIBS to develop a low-cost scalable approach to building climate resilience in low resource settings has helped drive strong cost effectiveness and value for money. A range of options were considered as part of the intervention selection to determine low cost but effective approaches. Notable examples include the use of light-coloured ‘stucco paint’, made with cement, sand, and lime used as roofing materials for PHCs and schools, which is more cost-effective and durable in terms of reducing temperature than the original proposition of painting these white. There was also a focus on using locally available construction materials, for example where feasible old-timber beams were utilised instead of buying new ones. Discussions between UNICEF and FCDO resulted in highly cost-effective model with a cost profile suitable for domestication within government budgets, increasing the chances of adoption. As a result, the overall budget initially estimated for 54 facilities was sufficient to cover the cost of 84 facilities (cost per facility decreased to almost 64% of the original estimate).
In terms of cost breakdown, the average cost for a PHC block was £70,492 (based on selected interventions and a block of 600 square metres), while the average cost per school was £16,241 (based on a school with 2 classrooms of 60 square metres and additional office space).
In terms of equity, the sites chosen by government partners – following the technical needs assessment – were focused in zero-dose LGAs in both States (i.e. those where children have not had a single dose of vaccine in their lifetime). This is a common proxy indicator for multiple deprivations, allowing us to have confidence that the communities targeted by the pilot sites were among the most vulnerable in Nigeria.
In terms of procurement of solar systems, UNICEF used pre-vetted suppliers and procured for all facilities in bulk, which helped to increase value for money. Similarly, for supervision work, UNICEF used prequalified engineering consulting firms that had signed ‘Long Term Agreements’ (LTAs) with UNICEF for provision of services. Use of LTA firms ensured timely fast-tracked procurement process while keeping overall costs down.
Engagement of local State and LGA authorities in each step of the development of the climate risk and vulnerability assessment, as well as facility selection, helped achieve local buy-in of the entire process and approach, adding value for the overall investments made.

E: RISK

Overview of risk management
CRIBS has had a very tight time-schedule to conclude all planned activities. UNICEF used a weekly monitoring mechanism to keep track of all planned activities and limit the extent to which there were major deviations from the original schedules. These weekly meetings were chaired by the senior management of UNICEF, ensuring that all collaborating teams (Climate, WASH, Health, Education, Procurement, Supply, Construction), both in Kano and the Abuja country office, had clearly defined action points and timelines to deliver.
The potential for delays in completing the construction of climate resilient interventions was significant from the outset, due in part to the long period of time required to select contractors through an open competitive bidding process. This was considered the major risk at the point CRIBS was conceptualised. As a mitigation measure, UNICEF engaged with the UNICEF (global) Supply Division to prioritise CRIBS and reduce the standard procurement time for the construction contractors. The senior management at the Nigeria Country Office also supported the fast-track approval process for CRIBS, enabling a substantial reduction of time on contractor selection. These measures managed the demand for high quality interventions and very tight timelines for delivery, with all finances committed well in advance of the first year of programme delivery.
Other key risks for the programme include:
- Insecurity is pervasive and often difficult to predict in Nigeria: this carries the current and future risk of programme disruption or compromises to service delivery. UNICEF manage this through their network of field offices and security teams, who regularly monitor security threats and adjust advise accordingly. UNICEF and FCDO consider programme implementation decisions based on understanding of security situation.
- Fraud and misappropriation of funds among downstream partners: as part of our Due Diligence Assessment (DDA), UNICEF has demonstrated evidence of capacity building of implementing partners on a harmonised financial approach. This is consolidated by regular financial systems assessments and spot-checks, and programmatic monitoring visits to verify appropriate use of funds. FCDO programme managers also review and verify all programme financial reports.
- Operational maintenance of facilities: investment in systems and budget allocation for maintenance is lacking or limited across many facilities, with risks to the sustainability or impact of interventions over the medium to long term. This is partly mitigated through only selecting PHCs covered by BHCPF, and working with State governments and facilities on private-public partnerships and community engagement to support on ongoing operational maintenance.
These risks have been managed by FCDO and UNICEF, working with government and wider partners to identify, understand and agree on mitigation measures for all risks. We have also held regular CRIBS programme management meetings to review risks and associated mitigation measures, with timely escalation to the CRIBS SRO as required.
The overall risk rating of CRIBS remains Major. This is premised on grounds of CRIBS being a capital investment programme, with a target of spending its budget allocation within the financial year, which came with uncertainties and the need for strong fiduciary risk management. There are also substantial risks associated with the operational maintenance of facilities which is common across capital programmes in Nigeria. Much of this risk is mitigated by programme management and delivery actions detailed above. However, a strong residual risk remains in such an operating context, which is reflected in the overall risk rating.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Performance of Implementing Partner
CRIBS has been delivered through a strong partnership between UNICEF and FCDO, via a signed Contribution Arrangement, now amended to end the 31st of March 2026 to align with the approved programme end date. UNICEF had a good performance in the year under review with 100% utilisation (spent or committed) of the full £8 million CDEL ODA allocation by 31st March 2025.
The CRIBS budget was utilised in line with FCDO PrOF guidelines for delivering value for money. 6% of allocated budget covered overhead costs, while 94% went into direct programme activities, including construction work, integration of climate resilient interventions into health and education facilities, facility level assessments, and streamlining of the CRIBS approach and tools. Funds were also used in strengthening WASHCOMs and establishing mechanisms for operators and mechanics of WASH facilities in PHCs and schools. The AR field visit provided a satisfactory level of evidence of quality of rehabilitation of PHCs and schools. This is aligned with expectations of high impact / low cost intervention selection and implementation to deliver maximum value for money.
Based on the review of documentation and field visits conducted for this AR, we assess UNICEF as having provided strong programme management and stakeholder relationship management. This includes a review of quarterly reports including financial performance and updates on risks in line with FCDO programme management expectations. There was also strong transparency in flow and utilisation of funds, with developing issues flagged for early mitigation. This enabled close management of the value for money delivery of the programme.
Summary of Programme Spend (2024/25 financial year)
Description	Budget (£)
Staffing, consultancy & supervisory cost	£468,919
Direct programme cost	£7,531,081
Total	£8,000,000

Assets Monitoring and Management
In line with guidelines on CDEL spend, CRIBS programme has been designed to create tangible assets which will over time require regular monitoring and management. Assets created are to be handled in line with current FCDO branding guidelines and handed over for maintenance following UNICEF Asset Management policy. The FCDO programme team will be in copy of all assets created and spot checks will be carried out periodically during field visits.
Delivery Against KPIs
The CRIBS programme, implemented in Kano and Jigawa states, successfully developed and tested a framework for assessing climate risks and vulnerabilities at the facility level. It focused on identifying and implementing climate-resilient interventions in 84 facilities - 45 schools and 39 PHCs – across nine LGAs. As of the latest update, the overall implementation progress stands at 69.88%. Implementation levels vary, with 14 facilities reaching the final stage of retrofitting, while others remain at earlier stages due to a late decision by FCDO to expand the number of facilities to be targeted for completion.
On balance, CRIBS delivered well against assessed outputs and delivered well above the expected scale of activity originally planned for at programme conception.
Despite significant progress, the programme identified key capacity gaps at the sub-national level and among private sector partners in understanding climate resilience. In response, the CRIBS team is developing detailed intervention specifications and compiling tools, standards, and guidance into an accessible package. FCDO is working with government and delivery partners to prepare for scaling the CRIBS model to additional states in Nigeria. This next phase will focus on completing current activities, documenting lessons learned, building partner capacity, and expanding the use of the CRIBS assessment tool to new facilities.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
CRIBS and its component activities are monitored at multiple levels. At the overall programme development level, the CRIBS Expert and Oversight Group reviews and approves all programme development milestones. There are also various subgroups set up to deliver on key elements of the programme such as ‘facility level assessment approach and tools’, ‘intervention selection and specification’ etc. There are also regular FCDO and UNICEF programme management meetings to monitor programme deliverables.
UNICEF technical staff (from the country and field offices) undertake regular field monitoring and quality assurance visits at various points in implementation period. There are also weekly CRIBS programme monitoring meetings, chaired by the UNICEF Deputy Representative. These meetings have been crucial fora to discuss overall progress, any emerging issues and action needed to accelerate progress.
There have also been several joint field missions by FCDO and UNICEF in the development phase and later to review the progress of implementation at facility sites, and as part of this AR. The intelligence gathered from this site visits have helped to improve the approach and have also been fed into the next phase of CRIBS delivery.
The focus of the approach to learning and integration of evidence has been through the multi-agency and multi professional Expert and Oversight Group. This group have provided expert guidance and advice on all key deliverables of the CRIBS programmes, and provided oversight and direction to ensure that CRIBS utilises the highest level of evidence in delivering on its core aim and objectives.
The CRIBS research component is funded and managed through the FCDO West African Research and Innovation Hub (WARIH) Evidence Fund. This provided expert inputs during the development of the climate vulnerability assessment and the selection of interventions, as well as conducting a baseline assessment of a sub-set of facilities and an initial process analysis of the implementation of the programme. A final evaluation will be conducted in early 2026 which will deliver further insights on the implementation of the CRIBS process, as well as the impacts of the interventions, which will feed into the next annual review and final log frame. CRIBS will also benefit from emerging findings from the pilot of a wider range of interventions that the research component is conducting in a small number of facilities in Lagos State.
Date of last narrative financial report	January 2025	Date of last audited annual statement	April 2024/March 2025