## IFFIm Annual Review 2024

Title: International Finance Facility for Immunisation (IFFIm)
Programme Value £ (full life): £2.59 billion		Review date: August 2025
Programme Code: 111073 & 201185	AMP start date: 2007	AMP end date: 2029

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	A	A	A+	A	A+	A+	A+	A+	A+	A+	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/47127690.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

IFFIm is an innovative financing mechanism used to frontload donor pledges to fund Gavi’s vaccination programmes, including the now-concluded COVAX Advance Market Commitment (AMC). IFFIm raises money for Gavi by selling 'vaccine bonds' on the international capital markets. These bonds are backed by long-term, legally binding pledges from donor governments. In this way, IFFIm is a flexible financing mechanism, making large volumes of future donor funding immediately available for Gavi programmes as and when needed. The diagram below illustrates how IFFIm works, showing how legally binding donor pledges are turned into funds that are immediately available for Gavi Board-approved vaccination programmes.

Gavi decides the size, timing and sources of funding required from IFFIm based on its long-term projections for expenditures, income and cash flow. In making this determination, Gavi considers the relative financial efficiencies between IFFIm disbursements and all other sources of funding available to it.

IFFIm has played a key role in supporting Gavi’s evolution as a global health organisation. IFFIm was originally established in 2006 to enable Gavi to scale up rapidly to meet immediate and urgent vaccine needs to accelerate progress towards Millennium Development Goal 4 (reducing child mortality). IFFIm has evolved with Gavi to provide the following functions:
IFFIm has enabled Gavi to efficiently frontload donor resources to scale up life-saving vaccine programmes in developing countries, such as accelerating the global rollout of pentavalent and pneumococcal vaccines at a much faster rate than otherwise would have been possible, thus helping to save millions of lives.
IFFIm provides Gavi with a reliable and predictable source of funding, backed by long-term donor commitments that span multiple strategic periods. This financial stability allows Gavi to make sustained commitments—critical for shaping vaccine markets and driving impact. With IFFIm’s backing, Gavi can send early, clear signals to manufacturers about vaccine demand, encouraging investment, fostering competition, and securing better prices. During the Ebola and COVID-19 responses, early access to IFFIm funding accelerated vaccine development and availability by giving manufacturers strong confidence in the financial readiness of both Gavi and the Coalition of Epidemic Preparedness Innovations (CEPI).
IFFIm’s flexible surge financing capability enables Gavi to respond swiftly to health emergencies and outbreaks, helping to contain disease spread and ensure timely vaccine delivery where it’s needed most.
The UK is the largest donor to IFFIm. The existing core Gavi IFFIm commitments total £2.09 billion over 23 years made up of three legally binding pledges; the first made in 2006 for £1.38 billion and payable over 20 years (2007 – 2026), the second for £250 million, made in 2009 and payable over 20 years (2010 – 2029), and the third for £461 million, made in 2022 and payable over 4 years (2026 – 2029). In addition, in 2020, the UK pledged £500 million to Gavi via IFFIm for the COVAX Advance Market Commitment to provide COVID-19 vaccines to 92 eligible lower-income economies.
This review assesses the performance of IFFIm as a funding instrument of Gavi.
As of June 2025, IFFIm has received legally binding grants from eleven donors totalling approximately US$ 10 billion and spanning 32 years to 2037. To date, IFFIm has disbursed a total of approximately US$ 6.2 billion to Gavi, comprising around 16% of Gavi’s total resources. This includes disbursing US$ 266 million of funding on behalf of Norway, US$ 6 million on behalf of Italy and US$ 44 million on behalf of Spain to CEPI for its vaccine research and development activities including for COVID-19 (C19) response.
IFFIm’s asset base significantly increased following the 2020 Global Vaccine Summit. During and after the summit, IFFIm received additional pledges of (1) US$ 1.72 billion from Canada, Italy, Norway, the Netherlands, Sweden Spain, and the United Kingdom (reprogrammed from direct contributions to contribution via IFFIm) for Gavi 5.0 programmes; (2) US$ 1.10 billion from Australia, Norway, Sweden, and the United Kingdom for the COVAX AMC; and (3) US$ 354 million from Norway, Italy and Spain for CEPI. With diversified assets of over US$ 3 billion, IFFIm remains well-positioned to support the final year of the Gavi 5.0/Gavi 5.1 cycle, with an anticipated total disbursement of c. US$ 3.3 billion.
Looking beyond Gavi 5.1, a substantial proportion of IFFIm’s historical pledges are set to mature over the next five years. For the first time, this has required new commitments from donors to enable IFFIm to continue to be able to issue bonds throughout the 6.0 period, and support Gavi’s core activities. As part of Gavi’s 6.0 replenishment in order to provide a similar proportion of flexible funding as in previous cycles, IFFIm sought new contributions from donors totalling US$ 1.9-2.5 billion for 7-to-15 year pledges. So far, IFFIm has secured around US$ 800m of new commitments post-replenishment, including a new pledge from the UK. Discussions with current and prospective donor countries are ongoing to secure additional funding commitments.
Given the global decline in ODA and current uncertainty around the trajectory of the multilateral reform agenda, there is an opportunity for financing mechanisms like IFFIm to help overcome short-term funding constraints and provide flexible funding to Gavi, particularly for times of emergency. IFFIm needs to review its position as part of the ongoing global shift in order to be well adapted to the new environment. To that effect, and to ensure that IFFIm remains fit for purpose in the new financing architecture, the IFFIm board of directors and the Gavi Secretariat will be conducting a strategic review of the IFFIm model starting in October 2025.
Aligned with Gavi’s five-year strategic cycle, IFFIm may seek a new round of funding to support Gavi’s 2031-2035 strategic period. By that time, a clear vision should demonstrate IFFIm’s continued value, particularly within the context of a shifting aid architecture. A reimagined IFFIm model could unlock greater impact by leveraging its unique access to capital markets.
Recommendations for the year ahead

Ensure opportunities for donors to influence the outcomes of IFFIm’s upcoming Strategic Review. The review will take place over the latter half of FY2025 and the first half of FY2026 to explore opportunities to strengthen impact, flexibility, and efficiency. It is important that donors are engaged early as possible to shape the Terms of Reference. It will be valuable to push reviewers towards:
  - Examining IFFIm’s previous successes at past replenishment events, and find improvements for making a strong case in future replenishments
  - Finding efficiencies and opportunities to improve IFFIm’s delivery directly to Gavi
  - Thinking broadly about what direction the mechanism could take in the future in light of the fundamentally different ODA landscape.

It is expected that this review will develop several recommendations that will shape the reform mandate for IFFIm. Donors will be keen to see action on this in 2026.

Hold bi-annual engagement sessions with donors on IFFIm. There is significant room to improve engagement with existing and prospective IFFIm donors. Engagement sessions could provide a space to plug information gaps, and to open up more discussion around the performance of the mechanism.

1. Improve lines of sight and communication for donors to the World Bank, as IFFIm Treasury Manager. The World Bank is highly influential in IFFIm’s operations. Donors have limited access to information, which can create delays and miss opportunities. There is also little room for donors to encourage a more flexible approach to IFFIm’s conservative financial management - an increasingly important consideration given shifts in the ODA landscape. IFFIm and Gavi should consider opportunities to facilitate donor feedback to the World Bank. For example, through better join-up between the Gavi and IFFIm Boards, hosting dedicated technical sessions, targeted bilateral engagements or group exchanges, as appropriate.
2. Improve comms and donor involvement around bond issuances and key events. Existing donors can be critical in helping to build the IFFIm brand and to bring on-board new donors to IFFIm.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

IFFIm is a multilateral development institution set up in 2006 to rapidly accelerate the availability and predictability of funds for Gavi. Gavi is a public-private partnership set up in 2000 to accelerate access to life-saving vaccines for children in the world’s lowest income countries.

IFFIm issues "vaccine bonds" on international markets bought by investors who, in return, receive interest over a fixed period, at the end of which they are repaid their original investment. The money raised by these bonds provides Gavi with large volumes of funds immediately available to deliver life-saving vaccination programmes. The predictable and flexible nature of this funding means that Gavi can plan effectively and respond to new developments in disease prevention.

The process of transforming long-term donor commitments into immediate cash for Gavi is called frontloading. Put simply, it is the process of shifting financial resources from the future to the present. Frontloading is important to Gavi because there is zero value vaccinating a child in 10 years if they die from a vaccine-preventable disease this year. The majority of Gavi’s core programme of vaccines need to be given to children within a few years of birth. Withholding or delaying this access can prevent children from leading healthy and productive lives. A healthy child is an asset to his or her family, the wider community and ultimately the national economy. By frontloading future resources, IFFIm has helped Gavi immunise more children in lower-income countries more rapidly.

IFFIm’s effectiveness lies in its ability to:

Provide Gavi with flexibility either to frontload resources, or to draw down funds over a longer period, enabling Gavi to use funds when they are needed most and when they provide best value for money,
Provide long-term, predictable funding to enable Gavi to support market shaping activities that includes driving-down the cost of vaccines and enhance Gavi’s ability to make long-term funding commitments.
- Provide Gavi with predictable surge funding capacity to respond swiftly to unexpected events, such as disease outbreaks and health emergencies.
- Offer donors a cost-effective way to have an immediate impact whilst spreading contributions over future years.

Since inception, IFFIm has demonstrated its versatility in responding to Gavi’s changing needs by efficiently funding Gavi’s programmes and maximising its life-saving impact. In its first five years, IFFIm’s frontloading capability nearly doubled Gavi’s available funding, dramatically expanding vaccine coverage and bolstering health systems. During the 2011-2015 period, IFFIm’s frontloading supported the global rollout of the pneumococcal vaccine while flexibly funding Gavi’s unforeseen needs, such as providing standby funding for the Ebola crisis. From 2016 to 2020, IFFIm’s role evolved into more flexible financing to support Gavi’s tactical investments, such as scaling up a new typhoid conjugate vaccine and forging a strategic partnership with the Coalition for Epidemic Preparedness Innovations (CEPI). In the 2021-2025 period, IFFIm has once again become a crucial frontloading platform for both Gavi and its donors, facilitating the scale-up of high-impact routine immunisation and a swift response to the Covid-19 (C19) pandemic through COVAX.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The annual review for the Gavi core programme (300871) constitutes the main performance monitoring document for vaccination programme outcomes, with this annual review focused on IFFIm’s performance as a financing mechanism for Gavi.

IFFIm’s continuing ability to generate more efficiency and more effectiveness in Gavi’s funding has helped Gavi immunise more than 1 billion children, avert more than 18.8 million future deaths, and accelerated the delivery of vaccines by making the money from long-term pledges available immediately. Between 2006-2024, IFFIm facilitated the immunisation of over 265 million of the total 1.2 billion children. Of these children, 154 million were immunised because of IFFIm’s[1]￼. This frontloaded funding mechanism provided crucial support to Gavi well ahead of actual donor payments, ensuring timely immunisation efforts, and accelerating broader economic benefits. Between 2000 and 2024, Gavi-supported programmes immunised over 804 million children with the pentavalent vaccine, 406 million against rotavirus, and 627 million with one or two doses of IPV[2]among many other achievements.
[1] As part of Gavi's impact analysis, Gavi estimates how IFFIm funds have contributed to the immunisation of children, i.e. Unique Children Immunised (UCI). There are three key components underlying IFFIm's impact figures: The first is Gavi support in routine immunisation ("Gavi's impact") as presented in the Annual Progress Report 2022, which estimates the total number of unique children immunised at 1,074 million. The second is IFFIm's share of contribution to Gavi's impact, which is based on IFFIm's funding in proportion to Gavi's spending ("IFFIm's impact"). The third is the proportion of Gavi impact due to IFFIm's frontloading capabilities ("IFFIm's frontloading impact"). This frontloading impact arises when Gavi accesses cash in advance of receiving actual incoming IFFIm donor grants to contribute to the vaccination of children.
[2] These figures exclude individuals vaccinated through Gavi-supported preventive campaigns. Data from Gavi campaigns, along with impact estimates for both routine and campaign activities, will be published in Gavi’s annual progress report later this year.

In the current strategic cycle, IFFIm is on track to meet its objectives in maximising frontloading and flexible financing for Gavi’s core programmes and the pandemic response, which include:

Enabling a flexible Gavi response: IFFIm was projected to contribute, along with other funding sources, to Gavi’s anticipated time-flexible spending of US $2.5 to $3 billion during the Gavi 5.0 period, in line with the Gavi Board-approved long-term funding strategy (December 2012) and IFFIm’s 2021-2024 Investment Case (2020). IFFIm is on track to disburse US$ 3.3 billion to Gavi in its 5.0/5.1 period (including COVAX AMC), with US$ 2.8 billion already disbursed. IFFIm contributed 19.5% of Gavi’s total funding for core programmes in 2023 and 13.3% in 2024. In 2021 and 2022, its share was approximately 29%, making it the leading annual contributor among Gavi’s funding sources during those years. This significant financial backing has played a pivotal role in strengthening Gavi’s efforts to sustain routine vaccination programmes and bolster health systems, particularly amidst the resource constraints exacerbated by the pandemic. During this period, notable high-impact programmes that IFFIm supported, among others, include pneumococcal (~US$ 541 million), inactivated polio (~US$ 167 million), yellow fever campaign (~US$ 244 million), HPV (~US$ 110 million) and health systems strengthening (~US$ 89 million). IFFIm also supported the launch of Africa’s first malaria vaccine rollout, contributing US$33.3 million—representing 25% of Gavi’s total investment across 20 countries.

Frontloading to rapidly respond to global health security challenges: The COVID-19 pandemic underscored the power of IFFIm’s frontloading capacity to rapidly mobilise resources. IFFIm was one of the first funding sources to support Gavi COVAX’s global pandemic response, frontloading over 90%, or US$ 975 million, of donor pledges for the COVAX Advance Market Commitment (COVAX AMC) alongside an additional US$ 206 million for CEPI’s C19 response.

Providing financial efficiency to Gavi’s balance sheet: IFFIm is the main mechanism for managing Gavi’s large-scale cash flow. This is especially important when unexpected funding needs arise during a fiscal year. For example, IFFIm helped sustain Gavi’s core programme funding during a period of financial constraint by providing a US$200 million backstop for the COVAX AMC Cost-Sharing Mechanism in 2021, which supported expanded COVID-19 vaccine coverage in AMC countries in 2021.

For the 2021-2025 strategic period, IFFIm is expected to fully utilise its financial resources to support Gavi 5.0/5.1, reducing significantly its assured resources available for the 2026-2030 strategic period. As of June 2025, based on the outstanding donor asset base beyond 2025, IFFIm can make available up to an estimated US$ 795 million[3] in assured resources for the 2026–2030 period. This funding will help bridge any potential gaps as Gavi transitions into its next strategic period and while new donor pledges are being signed.
[3] Subject to change

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

IFFIm has been highly effective in achieving its objectives and enhancing Gavi’s ability to deliver vaccines, even amid challenging financial market conditions. Between 2021 and 2024, IFFIm raised US$2.8 billion through four bond issuances, including a 3-year, US$1 billion fixed-rate vaccine bond issued in 2024. A similar amount– US$ 2.8 billion–was disbursed to support Gavi’s programmes—including its COVID-19 response via the COVAX AMC.

So far in 2025, IFFIm has completed two additional bond issues, bringing its total cumulative funding raised to over US$10 billion for the first time since its inception, further advancing Gavi’s life-saving immunisation efforts. In April, IFFIm tapped its October 2024 issue, adding US$250 million and bringing the total to US$1.25 billion, its largest bond to date. The transaction was successfully executed despite volatile market conditions. Then in June, IFFIm returned to the sterling market after three years, raising £300 million through a 3-year fixed-rate bond. This marked its largest GBP benchmark and third overall in pounds. Nearly 90% of demand came from UK-based asset managers and institutional investors, reaffirming strong support in the UK for vaccine bonds as a tool for global health. Repeat investors have included leading asset managers Legal & General Investment Management and Record Financial Group.

These achievements validate IFFIm’s theory of change and underscore the value of the instrument to the UK in advancing Gavi’s mission. Notably, IFFIm’s efficiency has continued even in a rising interest rate environment, where IFFIm’s cost of funding has remained broadly aligned with the weighted average of its donors, while its administrative costs have stayed below target.

The next strategic period for IFFIm will be crucial to demonstrate continued relevance and impact. The shifts in the ODA landscape will require IFFIm to operate in a way that is fit for purpose and well-adapted for the future.

## C. DETAILED OUTPUT SCORING

Output Title	Demonstration that IFFIm is a feasible, efficient and acceptable mechanism, and is an effective tool for development financing.
Output number:		7 (Gavi logframe)	Year	2023	2024
			Output Score	A+
Impact weighting (%):		100%	Weighting revised since last AR?	No

Indicators	Baseline	Target	2023 achieved	2024 Achieved	Progress
7.1 Nominal value of cumulative past disbursements for operating expenses and administrative fees should not exceed 3% of cumulative value of all IFFIm outlays to date / (This a revised indicator, as highlighted in the section below)	<3%	<3%	1.5%	1.5%	Exceeded target
7.2 The spread (in bps[4] per annum) between IFFIm's cumulative Cost of Financing (CoF) and that of donors over IFFIm’s entire lifetime	IFFIm's cumulative CoF does not exceed that of its donors	IFFIm's cumulative CoF does not exceed that of its donors	IFFIm's CoF 7bps higher than that of its donors	IFFIm's CoF 9bps higher than that of its donors	The Treasury Manager continues to monitor funding opportunities for IFFIm and optimise its funding cost in consideration of IFFIm's funding strategies.
7.3 Cost of carry (in bps per annum) - expressed as the average investment return minus average funding cost in the past 3 years	Positive cost of carry	Positive cost of carry	Zero cost of carry: average funding cost equal to average investment return	Positive cost of carry: average investment return was 14bps higher than funding cost of IFFIm in the past 3 years	No milestone, but on track with the baseline.
7.4 Overall support by Gavi of IFFIm's operations and activities, as indicated by the IFFIm chair.	Satisfactory	Satisfactory	Satisfactory	Satisfactory	Met milestone
7.5 IFFIm’s continuing strategic relevance to Gavi, i.e., IFFIm continues to play a significant role in Gavi’s funding strategy	Minimum drawdown of 50% of assured resources over 2021-2025	Minimum drawdown of 50% of assured resources over 2021-2025	Assured IFFIm Resources: / c. $3.10bn / Cum. actual drawdown by Gavi (2021-2023): / $2,480 m / Utilisation rate to date: 80%	Assured IFFIm Resources: / c. $3.30bn / Cum. actual drawdown by Gavi (2021-2024): / $2,800 m / Utilisation rate to date: 85%	Exceeded milestone
[4] bps is an abbreviation for basis points. One basis point is equal to 1/100th of 1%, or 0.01%.

Briefly describe the output’s activities and provide supporting narrative for the score.
7.1: Nominal value of cumulative past disbursements for operating expenses and administrative fees should not exceed 3% of cumulative value of all IFFIm outlays to date.
This indicator serves as a measure of IFFIm’s economy as a funding mechanism and can be viewed as a proxy for the overheads of the mechanism, expressed as a percentage of IFFIm’s total outlays over its lifetime.

In 2024, IFFIm’s combined spending on Governance-related operating expenses, including Gavi administrative support costs, and World Bank treasury management fees accounted for 1.5% of all IFFIm’s total outlays to date. While Gavi covers the cost of administrative support in its role as IFFIm’s Secretariat, these contributions are included in the calculation to provide a comprehensive view of overheads.

Total governance costs and administrative fees in IFFIm totaled $4.7m in 2024.

7.2: The spread (in bps per annum) between IFFIm’s cumulative cost of financing and that of donors over IFFIm’s entire lifetime.

This indicator measures IFFIm’s lifetime efficiency at converting long-term donor pledges into front-loaded support to Gavi. It compares the cost of borrowing by IFFIm’s donors (weighted average) to the cost of borrowing of IFFIm, reflecting IFFIm’s ability to efficiently access the market at a reasonable cost. With the US$1 billion IFFIm bond issuance in 2024, IFFIm’s cumulative CoF rose by 2bps, bringing it to 9bps above that of its donors by year-end. This 9bps margin above donors can be roughly to approximated to US$ 6.3 million over three-years, based on an average debt outstanding of over US$ 2.3 billion.
While IFFIm, at its inception, was expected to have higher funding cost than its donors, it enjoyed a period of lower cumulative funding cost than that of its donors until 2021, largely due to elevated funding costs that IFFIm’s donors experienced during the European debt crisis. As donor borrowing costs improved over time and IFFIm continued to issue bonds, the cumulative cost for donors eventually fell below that of IFFIm.
While such changes in financial market conditions have resulted in a higher cumulative cost of financing for IFFIm relative to donors, these factors are beyond IFFIm’s control and do not necessarily reflect poor performance directly. 9bps is an acceptable margin for the unique value that IFFIm offers Gavi. Investor demand for IFFIm bonds also remains strong, supported by its solid financial position and proven development impact.

The average IFFIm funding cost for all outstanding bond issues as of December 2024 is US$ SOFR+ 48 bps, 40 bps higher than the weighted average spot rate of donors’ funding cost of US$ SOFR + 8 bps. Total spending on interest costs for IFFIm for the year 2024 was $106.4m on outstanding debt of over US$3.0 billion.

7.3: Cost of carry (in bps per annum) – expressed as the average investment return minus average funding cost in the past 3 years.

The purpose of this indicator is to compare the returns IFFIm generates on its assets with the costs it incurs to borrow on financial markets, known as ‘cost of carry’. IFFIm’s funding costs, incurred in supporting Gavi's activities, are partially offset by returns from its liquidity portfolio, which is invested in high-grade fixed-income instruments. Under its risk management policies, IFFIm is required to hold a minimum level of liquidity, the equivalent of 12 months of debt service. However, it may hold additional liquidity to prepare for unforeseen needs or to take advantage of favorable market conditions. Therefore, IFFIm's relative funding cost versus investment return, or "cost of carry", reflects one aspect of its financing efficiency. It measures whether IFFIm is incurring any incremental cost for holding its liquidity beyond its standard borrowing costs—costs it would need to bear regardless of when raising funds in the capital markets. A positive carry implies that IFFIm's liquidity is yielding a higher return than IFFIm's funding costs. It shows whether IFFIm’s cash balances provide beneficial outcomes, i.e., IFFIm generates investment income that can partially offset its interest expenses. The aspiration is for IFFIm’s average cost of funding to be equal to or lower than its investment return.
In 2024, IFFIm’s liquidity generated 14bps more than its cost of funding, up from 0bps in 2023, primarily due to favorable market opportunities for investing its assets. Similarly, in 2023, IFFIm’s return on its liquid reserves improved to equal its cost of funding, up from a negative return of 11bps in 2022. These positive developments reflecting continuing gains from prudent investment strategies.
IFFIm’s total investment income in 2024 was US$ 45.3 million. The World Bank, acting as IFFIm’s Treasury Manager, continues to manage IFFIm’s liquidity investments prudently, monitor market developments, and optimise both investment returns and funding operations.
7.4: Overall support by Gavi of IFFIm’s operations and activities, as indicated by the IFFIm chair.

This indicator is a process indicator to measure coordination, smooth and uninterrupted operations, and good governance of a complex development finance instrument such as IFFIm. This includes IFFIm's capital market activities, Board meetings, donor engagement, financial reporting and interactions with rating agencies and other external stakeholders, among oth-ers.

In line with good governance, the IFFIm Board conducts an annual evaluation of the quality and adequacy of Gavi’s support in ensuring IFFIm’s smooth and efficient operations. The outcome of this assessment is communicated to the Gavi Secretariat. For 2024, the IFFIm Board confirmed its satisfaction with Gavi’s overall support. Historically, Gavi has consistently maintained a satisfactory level of support for IFFIm.

7.5: IFFIm’s continuing strategic relevance to Gavi, i.e. IFFIm continues to play a significant role in Gavi’s funding strategy.

This new indicator measures how Gavi is continuing to utilise IFFIm by drawing down funding against the level of Assured Resources from IFFIm as defined at the start of Gavi’s five-year strategic period and updated from time to time throughout the period. The assured resources include all expected proceeds based on available donor pledges within its gearing ratio limit (GRL) and risk management measures as adopted by the IFFIm Board. IFFIm is critical in Gavi’s financial strategy as a source of long-term, predictable and flexible funding. The Long-Term Funding Strategy approved by the Gavi Board in 2012 requires Gavi to maintain flexible funding tools to manage its balance sheet and cash flow efficiently. As part of Gavi’s five-year financial forecast for funding its strategic goals and in line with its long-term funding strategy, Gavi also defines the level of Assured Resources expected from IFFIm for the period, which is updated from time to time as and when IFFIm receives new pledges or signs new grants from donors and reflecting applicable foreign exchange and interest rates and the GRL.
As of January 2024, IFFIm was expected to provide approximately US$3.3 billion in assured resources for the 2021–2025 period. This estimate was based on all available pledges, including those for the COVAX AMC, and took into account actual cumulative disbursements to Gavi. By December 2024, Gavi had drawn down a cumulative total of US$2.8 billion from these resources: US$1.8 billion for its core programmes and US$975 million for the COVAX AMC.
By the end of 2024, IFFIm's disbursements reached an 85% cumulative utilization rate, significantly exceeding the strategic target of 50%. Looking ahead, Gavi is expected to utilise the majority of the remaining assured resources from IFFIm to support its Gavi 5.0/5.1 strategy.
For clarity, this information is also set out in Table 1 below:

Table 1: IFFIm’s expected assured resources
	2021	2022	2023	2024	2021-2024
Assured Resources 2021-2026 (Total, cumulative) (US$ Million)	$2,120	$2,860	$3,100	$3,290	$3,290
Gavi Draw-Down of IFFIm Assured Resources (Total, cumulative) (%)	57.4%	71.5%	80%	85%	85%
Gavi Draw-Down of IFFIm Assured Resources (Total, in-year) (US$ Million)	$1,214	$829	$435	$322	$2,800
Of which Gavi Draw-Down of IFFIm Assured Resources (Gavi 5.0/5.1, in-year) (US$ Million)	$434	$634	$435	$322	$1,825
Of which Gavi Draw-Down of IFFIm Assured Resources (COVAX, in-year) (US$ Million)	$780	$195	-	-	$975

In the first two years of this strategic period, IFFIm maximised frontloading and flexible financing to support Gavi’s core programmes and its global COVID-19 response—delivering a record level of funding in a short timeframe. As noted earlier, during 2021 and 2022, IFFIm accounted for approximately 29% of Gavi’s total funding for core programmes, making it the largest annual contributor among Gavi’s funding sources. This demonstrated IFFIm’s flexibility and effectiveness in providing upfront resources during moments of urgent need.
As Gavi shifted its focus toward strengthening routine immunisation and expanding broader vaccine initiatives in the post-pandemic period, IFFIm continued to provide flexible and timely support—most notably in the launch of Africa’s first malaria vaccine rollout and the scale-up of the HPV vaccine programme.
Overall, IFFIm has substantially exceeded Gavi’s expected utilisation, surpassing initial targets and reinforcing the critical role of its flexible financing model within Gavi's funding strategy.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
In 2024, IFFIm met all its output targets related to economy and effectiveness, while continuing to offer efficiency and flexibility in Gavi’s financial management. The UK has made four long-term, legally binding commitments to IFFIm, in addition to a new pledge announced at the Gavi 6.0 replenishment event. IFFIm has proven highly effective in achieving its objectives and enhancing Gavi’s ability to deliver vaccines—even amid challenging financial market conditions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following a recent review, Indicator 7.1 of the IFFIm logframe has been revised to more accurately reflect the mechanism’s overhead. The updated indicator now focuses solely on operating expenses and administrative fees, including Gavi-donated services and the World Bank’s treasury management fees. Net interest costs, which were previously included, have been excluded due to their market dependency and IFFIm’s limited control over them.

This refinement ensures that only directly incurred and controllable operational costs are measured. In line with this change, the threshold for the indicator has been reduced to 3%. This update builds on the comprehensive re-evaluation conducted in 2023, which aimed to ensure all indicators are fit for purpose and that they fairly capture IFFIm-attributable results.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:

Gavi should continue efforts to expand IFFIm's donor base given the significant volume of resources assessed by Gavi and the World Bank as the minimum amount necessary to maintain the efficiency of IFFIm as a financial mechanism.
Gavi has concluded its Global Summit for the 2026–2030 strategic period, thus far securing over US$9 billion toward its target budget of US$11.9 billion from both existing and new donors. Additional commitments are expected in the coming months.

As part of this outcome, several donors—including the UK—have reaffirmed their commitment to IFFIm. Discussions with current and prospective donor countries to secure additional funding commitments are continuing, with good prospects that 1-2 new donors will join IFFIm in the next few months.

Currently, IFFIm has around US$ 800 million of new pledges, somewhat short of its target of US$ 1.9-2.5 billion. This is due in part to the recent external uncertainty in the ODA landscape, but also due to challenges amongst new and existing donors in pre-allocating long-term resources amid an unpredictable budgetary outlook. IFFIm needs to remain committed to its efforts to expand the mechanism’s donor base and present a clear vision that overcomes information barriers.

Gavi, IFFIm and the World Bank, IFFIm’s Treasury Manager, should continue to monitor the impacts of higher interest repayments on the financial efficiency of IFFIm.

The IFFIm Board and the World Bank Treasury Manager remain highly focused on the impact of interest payments on IFFIm’s financial efficiency. Both parties have worked diligently to secure the most favourable market terms to meet IFFIm’s funding needs while maintaining cost control. The recent rise in interest payments is primarily driven by increased debt levels, resulting from several bond issues over the past few years to address liquidity requirements. This trend also reflects broader market dynamics in the current higher interest rate environment.

Despite these developments, the impact remains well within the expected range. The World Bank continues to actively monitor global market movements and interest rate trends to identify optimal opportunities, ensuring that IFFIm’s funding strategy remains both efficient and responsive.

IFFIm should engage existing donors early on any proposals to diversify IFFIm's utilisation beyond its mandate for Gavi, with an objective to attract additional pledges and increase the scale and associated secondary market liquidity of its bond issues.

The Gavi Secretariat and the IFFIm Board have initiated a joint process to commission a strategic review of IFFIm and its Finance Framework Agreement (FFA) in the second half of FY2025. This review will explore potential opportunities to strengthen IFFIm’s impact, flexibility, and efficiency in support of Gavi’s 2026-2030 strategic goals and beyond. Existing donors will be engaged early in the review process to understand their current experiences and expectations. The insights gained will directly inform proposals to enhance and expand IFFIm's role.

Gavi should continue to leverage IFFIm's flexibility for maximum efficiency. This includes finding the optimal balance between drawing down funds and maintaining headroom in IFFIm. FCDO will continue to monitor this in Gavi annual reviews.

IFFIm’s financial flexibility has been instrumental in enabling Gavi to determine the timing and amount of drawdowns for Gavi’s immunisation programmes, while preserving headroom for emergency needs (such as during the COVID-19 pandemic). In 2024 alone, IFFIm disbursed approximately US$322 million, bringing total disbursements to US$2.8 billion between January 2021 and December 2024. Based on its current asset levels, IFFIm has the capacity to disburse approximately US$500 million in additional funding for Gavi 5.0/5.1 during the remainder of the 2021–2025 strategic period.

Of the total $2.8 billion disbursement, US$975 million was initially allocated to support COVAX, with the remainder directed to Gavi’s core programmes. However, as the pandemic threat eased and demand for COVID-19 vaccines declined, around US$480.2 million remained unspent at the conclusion of the COVAX programme. In consultation with donors and following their agreement, these funds will be fully reallocated to other IFFIm-eligible, Gavi Board–approved programmes, consistent with their original intent. These include the African Vaccine Manufacturing Accelerator, which supports the development of commercially viable vaccine production in Africa; the Big Catch-Up targeting “zero-dose” children affected by pandemic-related immunisation setbacks; and the First Respond Fund, a rapid-response financing pool under the Day Zero Financing Facility for early pandemic response.

As Gavi shifted from pandemic response to strengthening routine immunisation and expanding into broader vaccine initiatives, IFFIm continued to provide flexible, timely support. In 2024, IFFIm helped launch Africa’s first malaria vaccine rollout, contributing US$33.3 million—25% of Gavi’s investment across 20 countries. It has also scaled up support for Health System Strengthening (HSS), with total contributions reaching US$554 million by December 2024, helping improve vaccine access in hard-to-reach communities. Additionally, IFFIm provided over US$132 million for the HPV vaccine rollout, covering more than 21% of Gavi’s total investment in this area.

During Gavi’s 5.1 strategic period, IFFIm also backed the creation of a letter of credit facility to support Gavi’s market-shaping transactions through UNICEF. This facility, which sunsets in 2025, reflects the continuing strength of the partnership between IFFIm and Gavi.

IFFIm’s frontloading mechanism has further enabled strategic partnerships, bringing together Gavi, CEPI, and donor countries such as Norway, Spain, and Italy to fund vaccine R&D for emerging diseases, including COVID-19. In 2024, IFFIm frontloaded approximately US$44 million of the €75 million committed to CEPI, with the remaining amount to be paid in 2036 following Spain’s final payment obligation on its December 2023 grant.

Gavi/IFFIm should keep donors updated on IFFIm’s support for Gavi programmes through at least one annual donor meeting, and through proactive communications on new bond issues, IFFIm activity, or significant changes to financial market conditions affecting IFFIm.

In 2024, the IFFIm Board and Gavi Secretariat held three donor consultations (in March, May, and June) to help define IFFIm’s role in Gavi 6.0. These collaborative sessions, involving the IFFIm Board, Gavi Secretariat, donors, and the World Bank, directly informed the development of the 2026-2030 IFFIm Investment Case as part of the broader Gavi 6.0 replenishment effort.

Following the release of the IFFIm Investment Case, complementing the 2026-2030 Gavi Investment Opportunity launched in Paris on 20 June 2024, IFFIm donors have been engaged bilaterally ad-hoc, but not convened regularly in a group setting. There may have been a missed opportunity to better engage donors on IFFIm leading up to the Gavi 6.0 replenishment, given IFFIm’s current funding shortfall. A group setting would have given opportunity for donors to informally support others’ and relieve some burden from the secretariat; it will be a valuable dynamic to develop going forward, especially as IFFIm undertakes its Strategic Review.

Over the past year, there were instances of communication challenges between Gavi and the World Bank, as IFFIm treasury manager. This delayed the flow of information to donors, leading to missed opportunities for donor countries to amplify communications or celebrate successes. The Secretariat and IFFIm Board have acknowledged these concerns and recommended to the World Bank a more proactive approach to IFFIm’s funding strategy, with a focus on strengthening communication protocols between donors, Gavi, and the World Bank.

Gavi and IFFIm should continue to participate in ongoing multilateral discussions and international fora – including G7 and G20 – to ensure that future developments of Gavi’s Day Zero Financing Facility, including the IFFIm Contingent Financing Mechanism (CFM), align with other global processes on surge financing and platforms for medical countermeasures (MCMs).

Gavi’s 2026–2030 strategy reinforces its role in global health security, with its 6.0 strategic goals closely aligned with G7 and G20 priorities on Pandemic Prevention, Preparedness, and Response (PPPR). IFFIm has been positioned as a critical funding instrument to support this mission.

Throughout its replenishment campaign, Gavi actively engaged in key multilateral discussions - including G7 and G20 processes - to ensure its financing tools remain relevant and well-integrated within the broader global health security architecture.

As part of Gavi’s Day Zero Financing toolkit, the IFFIm Board and Gavi are developing a Contingent Financing Mechanism (CFM), a standby facility designed for rapid activation during future health emergencies. While progress on the CFM was paused in 2024 due to the focus on Gavi’s 6.0 replenishment, work may resume if there is renewed donor interest during the IFFIm strategic review.

D: RISK

Overview of risk management

The overall risk rating for IFFIm is moderate.
The main programme risks and mitigation strategies are outlined below:
Risk	Description	Mitigation strategy
Credit rating risk	IFFIm’s current credit ratings are AA-/Aa1/AA by Fitch Ratings, Moody's, and Standard & Poor respectively. IFFIm’s rating is primarily driven by the rating of its top largest donors, the UK, Norway and France; if their ratings deteriorate then further downgrades (or upgrades if their ratings improve) to IFFIm are possible. Credit rating downgrades will lead to a higher cost of funding for IFFIm issuances and higher proportion of funds going towards interest payments.	The strength of donor support and commitment, and the conservative risk management approach overseen by the World Bank as Treasury Manager, are both cited as positive aspects supporting IFFIm’s current credit rating. Maintaining these supporting factors is crucial to maintaining a stable credit rating. This is only a partial mitigating strategy since further credit rating downgrades to donors are outside IFFIm's/WB control. / Note that in recent years, Moody’s has rated IFFIm higher than the UK, reflecting IFFIm’s high liquidity, strong commitments from donors and the IBRD’s involvement as Treasury Manager. France was downgraded by Moody’s to Aa3 in December 2024, and S&P revised its outlook to ‘Negative’ in February 2025. Similarly, Fitch changed France’s outlook to ‘Negative’ in October 2024 and subsequently updated IFFIm’s outlook to ‘Negative’ in the same month. S&P and Moody’s, however, continue to maintain a ‘Stable’ outlook for IFFIm.
Currency and interest rate swap exposure	A key risk for IFFIm continues to be management of currency swap exposure and its impact on attracting new pledges. Exchange rate and interest rate volatility and credit rating downgrades have led to high levels of exposure imposed on the Treasury Manager.	In order for IFFIm to convert its long-dated non-USD pledges into USD (therefore to mitigate the FX risk associated with the pledges), IFFIm needs swap lines from its swap counterparties. In May 2020, IFFIm and IBRD executed a swap restructuring transaction which gave IFFIm additional swap lines and enabled new pledges to IFFIm in non-USD denominated currencies at the Global Vaccine Summit in 2020 and subsequently. This has been important in adding commitments of donors unable to pledge in USD. Further, IFFIm and IBRD have put in place external swap counterparties for additional swap lines, which allowed hedging all new IFFIm pledges since 2021.
Investment risk	IFFIm’s investment income is generated from its investible assets, namely its cash holdings as mandated by its liquidity policy. Investment income earned from assets ideally should more than offset the cost of governance and management of the IFFIm portfolio. However, investment performance of IFFIm's portfolio is subject to market risk.	Continued high quality treasury management by the IBRD should mitigate this risk to an extent. While some market risks are unavoidable, regular monitoring of these risks is enabled through the World Bank's quarterly updates that include information on investment income. As noted earlier in this memorandum, recent experience has been that IFFIm’s invested reserves have produced a positive carry.
Interest rate risk	Recent IFFIm bond issues have had a higher cost of funding than that of the donors’ weighted average. Factors such as the significant change in the economic environment (principally the much higher interest rate environment now vs. the historically low interest-rate environment before 2022) and the effect of the past downgrade of IFFIm’s credit rating on its cost of borrowing have led to this difference in performance. Higher cost of funding for IFFIm issues is a negative factor because a higher proportion of funds will go towards interest payments.	Prudent financial management by IBRD, such as IFFIm’s Asset Liability Management policy that results in IFFIm’s assets (including its donor pledges and liquidity investment) and liabilities being hedged into USD floating rates, significantly lowers IFFIm’s interest rate risk. That said, it should be noted that further credit rating downgrades to donors could negatively affect IFFIm’s financials but lie outside IFFIm's control.
Risk that IFFIm is used for purposes beyond its mandate	The key risk associated with this is to the effectiveness and efficiency of IFFIm as a financing instrument to enable Gavi to achieve its core immunisation mandate. However, diversifying IFFIm's utilisation could attract additional pledges, increase the scale and associated secondary market liquidity of its bond issues (thus reducing the cost) and create reputational advantages for IFFIm, Gavi and IFFIm's donors.	IFFIm financial management is governed by the IFFIm legal agreements, including the Finance Framework Agreement. These set out how donor payments are made and how funds are managed by the World Bank as Treasury Manager and transferred to Gavi. These also require that all funds disbursed by IFFIm are used for Gavi Board approved programmes. Gavi is responsible for monitoring the risk of misuse of IFFIm funds and regularly reports back to IFFIm on the outcomes. Gavi has zero tolerance for misuse and is currently the main beneficiary of IFFIm’s funds (CEPI is an additional beneficiary under a special arrangement). IFFIm has been in compliance with all applicable regulatory requirements. While certain CEPI programmes have been designated as Gavi programmes so that they can be funded through IFFIm, this arrangement makes clear that Gavi is not accountable for the results of CEPI’s programmes. Donors’ support for CEPI through IFFIm are financial resources that are intended solely for CEPI (net of reasonable costs that Gavi incurs to facilitate this arrangement)
Risk that IFFIm will cease to operate in providing flexible funding to Gavi	IFFIm’s ability to raise funds effectively depends on it having a sufficient pool of donor pledges. This ensures that IFFIm has the capacity to issue bonds efficiently to provide flexible and frontloading funding for future investments.	IFFIm is a small sovereigns, supranationals and agencies (SSA) issuer. / At Gavi’s Global Vaccine Summit in Brussels on 25 June 2025, several donors reaffirmed their commitment to IFFIm as part of Gavi’s US$9 billion replenishment. We are confident that this risk has been mitigated through the new commitments made at the Summit.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Delivery performance

As of December 2024, IFFIm provided over US$6.2 billion to Gavi, including critical support for the COVAX AMC and CEPI’s COVID-19 vaccine research and development, representing 16% of Gavi’s total resources since IFFIm’s inception in 2006. In its first five years alone, IFFIm contributed more than half (53%) of Gavi’s funding, demonstrating its ability to frontload resources and reshape the vaccine financing landscape.

Between 2021 and 2024, IFFIm raised a total of US$2.8 billion through vaccine bond issuances to support global immunisation and the COVID-19 response. This included US$1.0 billion in 2021 for Gavi 5.0 and COVAX, US$0.8 billion in 2022 for Gavi 5.0/5.1, and another US$1.0 billion in 2024 for Gavi 5.0/5.1.

Commercial performance/performance of partnership(s)

The IFFIm Board, currently consisting of eight directors with extensive experience in banking, capital markets, and supranational and development financing, is responsible for governing IFFIm. Since inception IFFIm’s governance has drawn to its Board of Directors talented and experienced professionals under the leadership of four Chairs. The small, efficient Board has supported IFFIm’s innovation and flexibility without creating an overly heavy bureaucracy.

Partnerships perform adequately, but there is room for improvement in the lines of communication to the World Bank acting as IFFIm’s Treasury Manager. The World Bank works closely with the IFFIm Board and the Gavi Secretariat in ensuring IFFIm best supports donor financing needs. There is room to develop stronger links between IFFIm donors and all IFFIm partners, to better provide feedback and guidance as needed to support IFFIm’s strategy and operations.

Financial performance

IFFIm’s financial reporting is in line with international best practice. IFFIm’s annual financial statements are currently audited by Deloitte LLP, an external independent auditor, who is also Gavi’s auditor. Since IFFIm’s inception, its auditors have issued unqualified audit opinions on its annual financial statements. Financial forecasts for IFFIm disbursement are aligned with Gavi’s needs and are reported to the IFFIm Board on a quarterly basis.
The World Bank is IFFIm’s Treasury Manager. It manages IFFIm’s finances to the same standards that it manages its own finances. With its strong institutional reputation and financial market expertise, the World Bank enables IFFIm to leverage donor pledges for Gavi’s vaccination programmes issuing vaccine bonds on international capital markets.

IFFIm and the World Bank actively manage IFFIm’s funding cost to maximise its overall efficiency while also taking into account the opportunity that any new market provides to Gavi in increasing its profile and visibility. IFFIm is also required to keep cash on hand to cover its obligations one year before the bonds are due in line with conservative best practice. IFFIm’s hedging policy ensures its assets and liabilities are matched in USD so it is insulated from the uncertainty of foreign exchange fluctuation.

Value for money

Due to market conditions since 2020, the overall total cost of running IFFIm has trended higher. With IFFIm playing a more significant role in supporting Gavi 5.0/5.1 and as a critical pandemic response tool for COVAX, this is to be expected as IFFIm’s overall operational and financing activities have increased. Table 1 presents the actual IFFIm governance costs, Treasury Manager fees, and investment income from IFFIm’s inception in 2006 until the end of 2024.

Table 2: Overview of governance costs, Treasury Manager fees, interest costs and investment income, 2006 – 2024 (US$ millions). The bottom row – surplus / deficit – is obtained by subtracting all costs and fees from the Investment Income row.

	2006	2007	2008	2009	2010	2011	2012	2013	2014	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024
Governance Costs	1.6	2.2	2.8	3.0	2.9	2.7	3.0	2.7	2.8	1.9	2.0	1.8	2.0	2.1	2.1	2.4	2.3	2.4	2.3
Treasury Manager Fees	1.9	1.3	1.8	2.0	2.2	2.6	2.4	2.3	2.3	2.3	2.0	2.0	1.9	2.1	2.1	2.2	2.9	2.8	2.4
Interest Cost	-	53.0	37.1	11.7	4.0	1.6	4.7	1.3	-0.6	2.5	4.4	9.9	15.7	13.3	2.7	-2.9	22.2	122.3	106.4
Investment Income	3.5	14.4	4.5	10.8	5.7	10.8	5.6	3.8	3.0	4.8	8.2	15.0	20.6	23.4	4.5	0.6	10.9	45.9	45.3
Surplus/ deficit	N/A	-42.1	-37.2	-5.9	-3.4	3.9	-4.5	-2.5	-1.5	-1.9	-0.2	1.3	0.9	6.0	-2.4	-1.1	-16.5	-81.6	-65.8

Source: World Bank and IFFIm’s Financial Statements
Note: excluding CEPI transaction costs as these were reimbursed directly by Norway
In 2024, the governance costs decreased by approximately 4% from the previous year primarily due to a decrease in project-based legal fees incurred by IFFIm. The Treasury manager fee is comprised of two broad categories:

financial service cost including bond issue design and execution costs, investment management and swap fees; and
support costs which include fund and relationship management, rating maintenance, legal services, and accounting and reporting costs
Similarly, the treasury management costs were down by about 14%, providing overall savings in IFFIm’s administration costs. The decrease was primarily due to lower costs for management of IFFIm’s funding program and asset and liability management risk, lower legal and accounting costs, and lower costs for the preparation and reporting for IFFIm Board meetings.
In 2024, interest costs remained elevated following IFFIm’s issuance of a new US$ 1 billion bond, which increased the volume of debt exposed to interest and swap-related expenses in a persistently high SOFR environment. This upward pressure on costs reflects broader market trends, as USD interest rates remained elevated throughout the year. Additionally, IFFIm's average liquidity balance increased to US$ 893 million in 2024, up from US$ 820 million in 2023. The higher balance reflected the minimum level of liquid assets required under IFFIm’s Liquidity Policy, which is equivalent to the cumulative contracted debt service payments for the 12-month period in 2024.  Looking ahead, the trend in interest costs will largely depend on future interest rate movements and IFFIm’s financing and liquidity needs.
IFFIm’s investment income is primarily driven by the size of its liquidity and prevailing market conditions and is generated from investible assets held under the same prudent risk-return framework that mandated for the IBRD-TRUST pool, specifically its cash holdings. In 2024, IFFIm’s investment return was approximately SOFR +53 basis points, compared to SOFR +61 basis points in 2023. As previously noted, interest rates remained elevated throughout 2024, albeit slightly lower than in 2023, following three rate cuts by the U.S. Federal Reserve in September, November, and December, totalling 100 basis points. Persistently high inflation, a resilient labour market, and strong economic indicators led the Federal Reserve to adopt a more measured and gradual approach to monetary easing. The sharp increase in investment income in 2023 was largely driven by a significant rise in average liquidity—from US$ 478 million in 2022 to US$ 820 million—and higher interest rates. With little changes in the interest rate environment and a modest increase in average liquidity to US$ 893 million, investment income in 2024 remained relatively stable.
The timing and size of IFFIm’s bond issues are first and foremost driven by the funding need of IFFIm for a given funding year, whether that need is for refinancing of IFFIm bonds or disbursement for Gavi’s immunisation programmes. Once the funding need is determined, its overall funding strategy is premised on the intention to optimise the following three objectives: funding cost, diversification and raising the profiles of IFFIm and Gavi to increase awareness of Gavi’s immunisation mission. IFFIm continues to achieve this strategy by issuing bonds in different currencies and regions, attracting new investors and broadening its geographical reach.
In October 2024, IFFIm issued 3-year fixed rate vaccine bonds in an amount of US$ 1 billion, which provided Gavi with funding to support routine immunisation in lower-income countries. The bond attracted interest from a diverse group of investors, including 64% from central banks and official institutions, 22% from asset managers and insurance/pension funds, and 14% from banks, bank treasuries, and corporates. Geographic distribution comprises 42% Europe, Middle East & Africa, 38% Americas, and 20% Asia. This issue was oversubscribed by more than four times, attracting $4.3 billion in orders, making this IFFIm’s single largest transaction since its first bond in 2006.

In April 2025, IFFIm tapped the October issue with a further US$250 million, providing additional funding to Gavi. The transaction will mature on 29 October 2027, has a re-offer price of 100.261%, and carries a semi-annual coupon of 4.125%.

IFFIm’s gearing ratio has trended upward since 2021, indicating higher net debt as a percentage of the present value of donor pledges in line with Gavi’s needs for IFFIm funding. IFFIm’s gearing ratio was 57.7% against its GRL of 73.5% in December 2024, up from 54.2% against its GRL of 71.8% in December 2023. The gearing ratio is a function of net debt (outstanding debt net of liquidity) and present value of outstanding donor pledges and fluctuates due to factors including changes in donor credit ratings and the High-Level Financing Condition (the risk of recipient countries falling into arrears with the IMF). For example, the downgrade of France’s rating by Fitch in 2023 contributed, among other factors, to the GRL declining to 71.8% in Q4 2023. As of Q2 2025, IFFIm’s gearing ratio limit (GRL) was 74.7% i.e., the value of outstanding borrowings, less cash held by IFFIm, must not exceed 74.7% of the present value of outstanding pledges.

Date of last narrative financial report	December 2023 (published August 2024)	Date of last audited annual statement	December 2024 (published June 2025) / (https://iffim.org/sites/default/files/trustees-reports/IFFIm-2024-Trustees-Report-and-Financial-Statements.pdf)