## Annual Review – Unitaid – 2025

Title: Unitaid
Programme Value (full life): £790 million		Review date: 06 Jan 2026
Programme Code: 111074	AMP start date: March 2007	AMP end date: March 2026

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A+	A+	A	A	A	A	A	A	A+	A+
Risk Rating	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod

DevTracker Link to Business Case:	Project approved without a Business Case in 2006 (multilateral long-term programme for market shaping)
DevTracker Link to results framework:	Logframe will be published alongside Annual Review – Unitaid DevTracker Link

A. SUMMARY AND OVERVIEW

Description of programme
Unitaid, a global health initiative and hosted partnership of the World Health Organisation (WHO), is an important, high-performing actor in the global health landscape. It aims to expand and accelerate access to innovative health products in lower income countries. Unitaid’s portfolio covers malaria, TB, HIV/AIDS and co-infections, maternal and child health (particularly post-partum haemorrhage and pre-eclampsia), regional manufacturing, pandemic preparedness (particularly medical oxygen), and climate-smart health products.

Unitaid use their wide-ranging expertise in market-shaping and equitable access to identify the most important health innovations, barriers to widespread access for lower-income countries, and appropriate pathways for accelerating access. Through financial grants to partners alongside global influencing and coordination, Unitaid help address the various access barriers for health innovations. Barriers include affordability, lack of clinical and/or real-world effectiveness evidence, demand generation, manufacturing supply, and medical regulation. In this way, Unitaid shapes the market for health innovations, establishes the viability of health innovations in real world settings, and enables partner organisations and governments to make these innovations widely available at scale. Unitaid bridges the gap between upstream product innovation and country healthcare programmes, promoting equitable access, and therefore is a critical enabler, amplifier and accelerator for both the FCDO’s other global health investments (e.g. the Global Fund, Gavi, WHO, GFF) and its broader global health strategy. The UK was a founding donor of Unitaid in 2006 and remains a committed supporter and investor in Unitaid’s mission. This review reflects UK funding of £14m for 2024.

Summary supporting narrative for the overall score in this review

Unitaid scores an A+ in this review, moderately exceeding expectations for the second year in a row. Through 2024 and 2025, Unitaid made strong progress towards their headline objective of delivering 30 innovative health products by 2030 with the addition of 11 new products to their portfolio – Unitaid are now ahead of targets with 27 products supported so far. This notably includes lenacapavir, a potentially groundbreaking HIV prevention tool, for which Unitaid are a leading actor in accelerating access. In September 2025 Unitaid achieved a landmark pricing deal for generic (non-branded) lenacapavir. Unitaid are adopting an integration-focused mindset in the innovations they’re introducing which will help move away from vertical approaches to strengthening health systems, for example through multiplex diagnostics and bundled maternal health interventions. Unitaid-supported innovations are continuing to scale effectively, with Unitaid-supported products now reaching an increased number of 320 million people globally each year in over 100 countries. 60% of products in Unitaid’s scale-up dashboard are achieving ‘Good’ to ‘Strong’ scale up.

Unitaid’s cross-cutting access work on regulatory system strengthening is supporting timely approval of new medical products and is aligned with Unitaid’s portfolio (e.g. green regulatory pathways), while Unitaid moved to implementation of an encouraging regional manufacturing programme in Africa that’s aiming to act as a set of catalytic blueprints for price-competitive, quality manufacturing of diagnostics and therapeutics. Unitaid took important steps for establishing a future climate and health portfolio pending specified funding, are integrating climate considerations across their portfolio, and continue to act as a global convenor for climate-smart health products, including contributing studies on decarbonising HIV products and the benefits of long-acting technologies. Unitaid are a leading actor in accelerating access to medical oxygen as both an important pandemic countermeasure and broader essential drug for health systems strengthening. Collaboration with the Global Fund remains effective and clearly complementary, and Unitaid should act as a leading voice on the future of market-shaping in discussions on global health architecture reform. Partnerships with country, regional and civil society actors are being strengthened, with Unitaid starting promising workstreams aimed at going further to achieve inclusive, collaborative ways of working.

Unitaid responded effectively to the global health financing shifts of 2025 with clear, structured prioritisation and have undertaken a comprehensive Mid-Term Review of their 2023-2027 Strategy with considered recommendations. But effectively prioritising implementation of these recommendations will be challenging. In a difficult fundraising environment Unitaid made progress on resource mobilisation and are pursuing new, more innovative sources of finance. Going forward Unitaid should prioritise addressing delays and complexity in their grant agreement development process, strengthen implementing partners’ safeguarding reporting, and need to be mindful of stretched staff capacity and wellbeing when taking forward a significant portfolio and series of change initiatives.

Output	Score
1. Accelerate introduction and adoption of key health products	A+ Moderately exceeded expectation
2. Create systemic conditions for sustainable, equitable access	A Met expectation
3. Foster inclusive and demand-driven partnerships for innovation	A+ Moderately exceeded expectation
4. Unitaid governance, management and operational work is economical, efficient and effective and embraces equity consistent with its Operating Model	A+ Moderately exceeded expectation

Major lessons and recommendations for the year ahead
This review identifies recommendations within each programme output; these are copied below with the recommendation number referenced to the 4 outputs. The ‘Major’ label denotes priority recommendations.

Recommendation 1.1 (major): Unitaid should build on the integration successes of their current portfolio (e.g. multiplex diagnostic platforms, maternal health bundles) when developing their next multiyear strategy beyond 2027 to prioritise innovations that will maximise integration opportunities. With constrained global health financing, the health SDGs remaining off-track, and increased domestic financing and ownership, integration-focused innovations will be essential for strengthening health systems and minimising vertical approaches. Strong, clear-sighted management will be needed to align more diverse funding streams (growing specified funding and innovative financing) with Unitaid’s core portfolio and to avoid undermining an integration-focused approach. Effective engagement with communities, civil society and countries will be key to success here (see recommendation 3.2).

Recommendation 2.1: global health financing changes in 2025 will likely impact on WHO RPQ’s capacity and workflow going forward. Unitaid should consider how to adapt their core RPQ Enabler investment, alongside how to best support the African Medicines Agency (AMA) as part of regulatory system strengthening. Unitaid will need to work closely with WHO RPQ, other RPQ donors, key global health partners, and national and regional regulatory bodies to clarify the role and ambition of WHO RPQ going forward, other actors’ roles and responsibilities, and how gains made to date can be protected and continued.

Recommendation 3.1: The Unitaid and Global Fund partnership is strong and mutually beneficial, but the external narrative and framing for newer, unfamiliar audiences risks confusion and ambiguity on their overlapping market-shaping work. Unitaid should use the strengthened partnership to clearly communicate their unique market-shaping role and the importance of Unitaid to the Global Fund. Discussions on global health architecture reform, the future of market-shaping and shift 5 of the Lusaka Agenda present an important opportunity to make this clearer. By working with the Global Fund, other market-shaping partners and investors including the FCDO, Unitaid should help map out key future roles and responsibilities in market-shaping.

Recommendation 3.2 (major): Unitaid should continue to work closely with the Communities, NGO and African countries’ delegations, alongside the rest of the Executive Board, to refine and agree a set of clear, realistic and costed changes to its Operating Model, to be piloted over the second half of this Strategy, which will help deliver inclusive, demand-driven partnerships with countries, communities and civil society. The current shifts in the global health ecosystem and the growing importance of domestic financing present important opportunities.

Recommendation 4.1 (major): Unitaid should prioritise addressing the Mid-Term Review findings on the administrative complexity, burden and delays in their grant agreement development (GAD) process. This should identify nearer-term fixes for the rest of this strategy (until end 2027) and more structural changes that could be introduced in the next strategic period. Increased agility will be valuable in an increasingly fragmented global health ecosystem with intensified funding competition and the need to align more closely with country and civil society partners.

Recommendation 4.2: Building on the successful donor country briefs and the June 2025 ‘Reimagining Global Health’ report, Unitaid should move towards a formal public annual report to bring a range of already available information into one clear document. This could usefully combine the ‘Unitaid in numbers’ approach of the Reimagining Global Health report with tracking of KPI progress. It could also serve to more clearly distinguish the unique nature of Unitaid’s market-shaping contributions (linked to recommendation 3.1), raise Unitaid’s profile, and be used as an advocacy tool by Unitaid champions (including the Executive Board).

Recommendation 4.3: Unitaid should prioritise addressing BDO’s recommendations in their 2025 Ethics and Safeguarding report. This includes ensuring systematic due diligence of partners’ safeguarding capacities during grant development and requiring ongoing reporting, building on Unitaid’s updated guidelines and standards for implementing partners since April 2025, as well as a case management tool for tracking and reporting partners’ safeguarding incidents to the Executive Board (or the Financial Accountability Committee) on a 6-monthly basis, as is done for financial wrongdoing. Unitaid should also prioritise understanding 2024 staff survey scores on experiencing and witnessing harassment or discrimination at work to ensure a zero-tolerance approach, alongside reviewing staff survey scores for staff psychological safety and wellbeing to ensure a safe to challenge, open culture that supports wellbeing.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Unitaid’s Strategic Framework for 2023-2027 (see below) outlines the organisation’s vision for maximising equitable access to health innovations and ensuring healthy lives globally. It sets out a roadmap of strategic objectives designed to drive progress towards Unitaid’s mission. This overarching theory of change remains unchanged.
This year, Unitaid and FCDO worked together to agree updated milestones for output indicators where necessary to adequately capture and report on the progress of Unitaid’s strategy. These minor changes to milestones are explained in each output in this report.

This Annual Review’s logframe reports on output indicator results for the calendar year 2024, in line with Unitaid’s reporting cycle where full calendar year results are reported in June for the preceding year. However, this Annual Review also captures Unitaid’s broader work in 2025 up to the time of writing (November 2025) where possible, to reflect the latest real-time assessment of Unitaid’s work.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Unitaid sustained impressive progress across its portfolio and remain on track to deliver the public health impact and outcomes set out in their 2023-2027 Strategy, despite continuing to operate in a constrained funding environment. Unitaid appear ahead of milestone targets for their overarching objective to bring 30 innovative products to market by 2030, with 27 products supported so far. These products are also overall on track to meet their target access profiles and target equity conditions, which together will help monitor the conditions for widespread equitable access – although long-acting products continue to be off-track in this respect (except for lenacapavir). Unitaid are responding with deprioritizing certain long-acting products, while prioritizing others (e.g. lenacapavir). Overall, the scale-up dashboard continues to show solid results in key products achieving widespread access in terms of magnitude, speed and equity, and Unitaid are doing well to ensure 86% of their grants support an integrated approach. Unitaid’s investment in WHO RPQ performed well in 2024, but will likely face challenges ahead, and Unitaid continue to demonstrate a clear pathway from their support to valuable evidence generation for improved global health policy and guidelines. Both the regional manufacturing and climate and health initiatives continue to perform strongly, although the pandemic preparedness strategic initiative is mainly limited to medical oxygen following Unitaid’s decision to deprioritise investing in monoclonal antibodies given funding constraints.

Unitaid have strengthened their partnerships with a range of partners, including a clearer complementary approach with the Global Fund on bringing innovation to scale, new regional partnerships in Africa and Latin America and a new Partnerships team making improvements to country and civil society engagement. Further improvements will be important for keeping country and civil society partnerships on track towards inclusive, equitable approaches.

Unitaid continue to strengthen their in-house operations as they focus on optimizing their operating model and raising the bar as a competitive global health partner. Prioritisation and understanding of their portfolio have been strengthened thanks to a consultative Mid-Term process, and there are promising prospects in the funding pipeline for core, specified and new more innovative financing approaches. Financial management has remained solid with no concerns. However further attention is needed to accelerate the process for grant agreement development following delays in grant-making in 2024. This may require accepting greater managed risk in Unitaid’s ways of working and will be an important area of review in 2026 and looking ahead to Unitaid’s next multi-year strategy. Important improvements including implementing partner guidelines have strengthened Unitaid’s safeguarding approach, with useful recommendations identified on how Unitaid can strengthen further – mainly related to monitoring and reporting of implementing partners. Overall staff satisfaction is impressively high, but Unitaid must carefully monitor staff wellbeing following reports of strained work-life balance across the Secretariat in the 2024 staff survey.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on this report’s findings of strong performance across all outputs, the UK’s investment in Unitaid should continue. Unitaid has delivered impressive results in accelerating access to innovative health products, with over 100 countries now procuring Unitaid-supported products that reach approximately 320 million people annually, including 53 million children. This programme cannot be considered in isolation of the FCDO’s wider global health portfolio and strategy given that Unitaid’s wide-ranging market-shaping helps address key access barriers for bridging the gap between innovation and widespread scale-up of life-saving health tools. With an expanded portfolio, Unitaid amplifies and accelerates impact across FCDO’s global health priorities, including: maternal and child health through safer birth and newborn health, reducing deaths from infectious diseases (HIV/AIDS, TB and malaria), addressing the intersection of climate and health, contributing to efforts to tackle disease resistance, strengthening preparedness for future pandemics, and helping move to a more equitable and partnership-based global health landscape with increased global South health sovereignty. Unitaid are on track to deliver targets set out in their 2023-2027 strategy but there remains significant work with the UN’s health Sustainable Development Goals off-track. The FCDO’s 20-year funding agreement with Unitaid concludes in March 2026: extending our investment beyond this point and continuing our partnership would help Unitaid to continue accelerating access to life-saving innovation.

## C. DETAILED OUTPUT SCORING
Output Title	1. Accelerate introduction and adoption of key health products
Output number:		1.	Output Score:		A+
Impact weighting (%):		25%	Weighting revised since last AR?		No
Indicator(s)	Milestone(s) for this review			Progress
Output 1.1 / Key health products supported by Unitaid contribute to the delivery of global health goals by 2030.	Continued progress by Unitaid to invest in key health products that align with the 30x30 objective (30 products by 2030), and wider 2023-2027 Unitaid Strategy.			Substantially exceeded expectation (A++) / In 2024 Unitaid added 11 new products to its portfolio. This increases the total number of new products supported since the beginning of the 2023-2027 strategy to 23, representing very strong progress from the 12 products as of end 2023. Against the overall target of 30 products by 2030: 27 of 30 product classes are now supported by Unitaid (including 4 investments from before the 2023-2027 strategy), with Unitaid appearing comfortably ahead of their 2030 goal. Added products reflect a diverse pipeline across HIV prevention and treatment (including landmark work on lenacapavir), maternal and newborn health, and ending vertical transmission of Chagas, HIV, Hepatitis B and syphilis – together aligning strongly with global health priorities.
Output 1.2 / Key health products supported by Unitaid are on track to meet their target access profiles.	80% of products on track to meet their target access profiles.			Met expectation (A) / 79% (22 of 28) of products were on track to meet their Target Access Profiles.
Output 1.3 / Total number of key health products on track to meet their target equity conditions / Total number of key health products with a target access profile.	80% of products on track to meet their target equity conditions, with a stronger focus on women and girls.			Met expectation (A) / 79% (22 of 28) of products were on track to meet their target equity conditions, with 100% of equity conditions focused on women and girls fully on track.
Output 1.4 / Unitaid enables the successful scale up of key products, in coordination with countries and scale funders, across three dimensions: magnitude, speed and equity.	Strong demonstration by Unitaid of continuing to enable adoption and scale-up of key health products by countries and scale funders, including The Global Fund. This could include increased scale-up of ongoing products or initial scale-up of new products/interventions. e.g. evidenced through normative and national policy development, product procurement plans and forecasts, and published evidence (e.g. from WHO disease reports and similar sources).			Moderately exceeded expectation (A+) / 2024 saw strong performance in scaling up key innovations with more than 100 countries procuring and providing access to Unitaid-supported products, reaching an estimated 320 million people, including over 53 million children, a 6% increase from 300 million people in 2023. The scale-up dashboard expanded from 24 to 27 product classes across HIV and co-infections, tuberculosis, malaria and maternal and child health, with 60% assessed as achieving Good to Strong scale-up (compared to 54% in 2023).
Output 1.5 / Products supported by Unitaid contribute to integrated approaches which support stronger and more resilient health systems.	At least half (50%) of the portfolio (by number of grants) supports a more integrated approach; clear evidence of how key health products strengthen health systems.			Substantially exceeded expectation (A++) / 43 of 50 (86%) of active or actively closing grants seek to support integration in some form.

Output 1.1: Key health products supported by Unitaid contribute to the delivery of global health goals by 2030

In 2024 Unitaid added 11 new products to its portfolio, spanning HIV prevention and treatment, maternal and newborn health, and Ending Vertical Transmission (EVT) of Chagas, HIV, Hepatitis B and syphilis. Specifically, this covers:
- Lenacapavir: a groundbreaking HIV long-acting prevention tool. Delivered as a twice-yearly injectable, clinical trials demonstrated near 100% efficacy and it could be game-changing for overcoming daily pill fatigue in both treatment and prevention (a key barrier). This long-acting prevention regimen can enhance adherence, simplify care delivery, and reduce missed doses.
- Calibrated delivery drapes for improving the early detection and treatment of postpartum haemorrhage, a leading cause of maternal mortality. These are simple, low-cost devices designed to collect and measure postpartum blood loss objectively, replacing subjective visual estimates and other cumbersome methods.
- An integrated package of 9 diagnostic and prophylactic (i.e. preventative) tools to be delivered through antenatal care for ending vertical transmission of Chagas, HIV, hepatitis B and syphilis. This includes point-of-care rapid tests for hepatitis B and HIV/syphilis, hepatitis B birth-dose vaccination, benzathine penicillin G (BPG) to prevent congenital syphilis, and prophylaxis against vertical transmission of hepatitis B. Together this package expands access to screening and prevention by overcoming barriers to clinic-based tools (stigma, travel, clinical hours), streamlining their integration into existing health services, and producing significant cost savings.
Of particular significance is Unitaid’s investment in lenacapavir, with Unitaid being the first multilateral partner to invest in accelerating access to lenacapavir in 2024 through pathfinder initiatives in South Africa and Brazil with Wits RHI and Fiotec respectively to generate early lessons on delivery models, acceptability and integration into existing HIV prevention programmes. In 2025 Unitaid developed a further $25m of grants focused on testing large-scale implementation approaches that can rapidly reach substantial numbers of people at high risk of HIV infection, particularly for populations facing barriers to existing prevention services. Through the second half of 2025 Unitaid further demonstrated their critical role in the ecosystem through a landmark price agreement that will make generic (i.e. non-branded) lenacapavir available for just $40 per year in 120 low-income countries from early 2027 (compared to the originator price of over $28,000 in the USA). Achieving this agreement less than two years after regulatory approval in high-income countries is a major milestone and reflects Unitaid’s global leadership in market-shaping interventions.

Output 1.2: Key health products supported by Unitaid are on track to meet their Target Access Profiles

A Target Access Profile (TAP) outlines, for a health product or product class, the desired profile or conditions necessary for the product to become readily accessible (i.e., equitable, fit-for-purpose, affordable, and rapidly available) to the people and communities who need it most. TAPs encompass issues relating to supply, demand, affordability, regulatory readiness and long-term sustainability risk. Each TAP captures both programmatic progress and a risk assessment of long-term sustainability and scale-up potential of a product or product class. TAPs are an essential tool for assessing progress against access barriers and for proactive performance management of investments.

In 2024 22 (79%) out of 28 products/product classes monitored were on track to meet their TAPs, a similar performance to 2023’s 78% (21 of 27 products), and on-track with Unitaid’s 80% target. TAPs are on track and performing strongly in the portfolio areas of maternal and child health (100% with 5/5 TAPs on track), HIV (89%, 8/9 TAPs on track) and TB (83%, 5 out of 6 TAPs).

TAPs in malaria are just missing the 80% target (75%, 3/4 TAPs on track), while the long-acting portfolio continues to be the area most off-track with 25% (1/4) of TAPs on-track. This long-acting portfolio was similarly the area most off-track in 2023 and as outlined in last year’s Annual Review reflects the greater risk, complexity and earlier R&D stage of long-acting health products. The overall steady, consistent performance of the portfolio in the round reflects Unitaid’s adoption of a diverse portfolio that balances lower risk innovations that are more certain bets for scale-up, alongside higher-risk products like those in the long-acting portfolio which may have more transformative public health potential. The importance and benefits of remaining invested in the long-acting portfolio were highlighted with the significant steps towards lenacapavir being rolled out at scale in the near to medium-term future (see output 1.1). It is encouraging to see Unitaid being dynamic by strategically prioritising where products or product classes have significant sustainability risks from an access perspective – for example Unitaid closed their investment in long-acting ivermectin (for malaria prevention).

TAPs have also evolved into a strategic tool within Unitaid’s Access workstream (aimed at better integrating grants with overall organisational objectives and enhancing the interconnectivity of Unitaid’s work). TAPs are increasingly being recognised in the global health ecosystem as a useful framework for tracking progress on access conditions. TAPs have been used in market shaping workshops with partners and received positive feedback from WHO, the Gates Foundation, MedAccess, the Global Fund and civil society. For example, CHAI led (with Unitaid support as part of their Advanced HIV disease investment) a thorough consultation on near point-of-care diagnostics which led to a fully aligned TAP across key partners working in this space.

Going forward Unitaid is planning to expand the use of TAPs to inform joint investment planning with partners, guide manufacturer engagement, support the development of global policy guidance and facilitate country-specific uptake strategies. This growing use of a shared evidence base and monitoring framework will help improve coordination in accelerating access to innovations.

Output 1.3: Total number of key health products on track to meet their target equity conditions (out of Total number of key health products with a target access profile)

Target Equity Conditions (TECs) set the equity benchmarks within each Target Access Profile (TAP) that must be met to ensure innovations benefit priority populations, including women, children and other underserved or marginalised groups. This integration of equity considerations into TAPs strengthens Unitaid’s ability to embed inclusive design features – such as formulations, decentralised delivery models and community-driven demand creation – into innovations so they are better at reaching those who need them most. In 2024, Unitaid maintained good momentum in advancing equity across its portfolio, with 22 out of 28 products (79%) on track to meet their TECs. This is a steady improvement on last year’s 74%. Notably, all TECs specifically focused on women and girls remained fully on track.

As with the target access profiles, for target equity conditions progress towards access is strongest in maternal and child health (100%, 5/5 TECs on track), TB (83%, 5/6 TECs) and HIV (100%, 9/9). Malaria TECs are more significantly off-track than for TAPs, with just 1 out of 4 TECs on-track (25%) – delays in evidence generation and user acceptability studies mean ivermectin, spatial repellents and p.vivax radical cure are all off track for malaria. As with TAPs, the long-acting portfolio remains an area of higher risk with 50% of TECs (2/4) on-track. To manage these risks, Unitaid monitors TECs through routine performance reviews, early identification of bottlenecks and collaboration with partners to overcome regulatory, market and implementation barriers. Again as with TAPs, those areas off-track for TECs reflect Unitaid’s willingness to take calculated risks in pursuit of transformative technologies. As the global health ecosystem moves into a more challenging period following major funding reductions, it will be essential for Unitaid to proactively monitor these access risks and prioritise products as necessary.

Output 1.4: Unitaid enables the successful scale up of key products, in coordination with countries and scale funders, across three dimensions: magnitude, speed and equity

Unitaid’s scale-up dashboard tracks the extent to which Unitaid enables the successful scale-up of key health products in coordination with countries and scale funders (e.g. the Global Fund) against the 3 dimensions of magnitude, speed and equity. Magnitude captures procurement volumes and/or market share of the product or product class, including baseline, current status and, where available, forward-looking projections. Speed assesses how quickly scale-up occurred after the initial investment by Unitaid, as well as the state of product adoption globally and at country level. Equity determines the extent to which scale up is occurring in an equitable manner across geographies and populations groups. For 2024 the scale-up dashboard expanded from 24 to 27 product classes, with additions including the 6-month all-oral regimen of bedaquiline, pretomanid and linezolid (BPaLM) for multidrug- and rifampicin-resistant tuberculosis, and a paediatric fixed-dose combination dispersible tablet for children living with HIV (pALD). In total 60% were rated as achieving Good to Strong scale-up, a solid improvement from 2023’s 54%, with progress driven by five high-impact areas: optimal HIV treatment (dolutegravir), HIV self-testing, seasonal malaria chemoprevention, dual-active-ingredient bed nets and TB preventive therapy (3HP). Notable scale-up achievements across the portfolio included:
- HIV self-testing: with ~21 million tests and policies in 107 countries.
- Adult dolutegravir (DTG): ~95% coverage of first-line anti-retroviral therapy (ART) for people living with HIV in LMICs; while paediatric DTG for children has ~85% market coverage.
- Malaria control: ~235 million dual-AI nets (improved efficacy against insecticide-resistant mosquitoes) planned for delivery 2024–2026 (72% of Global Fund’s procurement of insecticide-treated nets).
- Cervical cancer: Thermal ablation devices (portable, low-cost) for treating pre-cancerous lesions are now available in 32 countries.
- Newborn care: Unitaid-supported oxygen and respiratory solutions (including oxygen blenders and Vayu’s low-cost and highly adaptable CPAP device) have helped treat over 260,000 newborns to date.

Of the 27 products or product classes now being scaled up, maternal and child health constitutes the smallest portion with just 2 products – reflecting its more recent addition to Unitaid’s portfolio – while HIV products remain the largest portion (12 products) and then malaria (7) and TB (6). Over half of the scale-up dashboard (14 products) is made up of Unitaid’s portfolio from before the current 2023-2027 strategy period and it will take some time for the more recent additions to Unitaid’s portfolio (output 1.1) to reach the global scale-up phase.13 of the 30 products that Unitaid are looking to introduce by 2030 are currently being scaled up.

While performance for scale-up has been strong for 2024, Unitaid and partners face significant challenge ahead given the major reductions to global health financing since January 2025. The FCDO has found Unitaid to be on the front-foot in their response to this landscape shift throughout 2025, with comprehensive risk analysis of the products facing greatest risk to large-scale rollout, and proactive identification of mitigations to help safeguard continuity, adjust product introduction plans where needed, and prioritise the most efficient, high-impact delivery approaches. Unitaid’s analysis indicates that half of the product classes in scale-up could experience heightened risk, especially for prevention and diagnostic products. For example, a temporary reduction in HIV prevention services in parts of Nigeria, Kenya and Uganda alone affected an estimated 2.2 million people. Protecting sustainable scale-up of key health products going forward will require Unitaid to remain responsive and proactive in coordinating closely with key scale-up partners and country governments and prioritising the most impactful products and delivery pathways.

Output 1.5: Products supported by Unitaid contribute to integrated approaches which support stronger and more resilient health systems

Unitaid defines integration in their grants as supporting one or more of the following:
- Enabling access to a health product that addresses more than one disease or condition (e.g. multi-disease diagnostic platforms).
- Addressing the needs of people affected by more than one disease (e.g. treatment of co-infections, this is particularly significant for Unitaid’s HIV and co-infections portfolio).
- Reaching people for a health issue through another programme or clinical interaction (e.g. leveraging child health services to diagnose malaria in children).

Unitaid’s performance in 2024 was strong, with 86% of grants incorporating one or more integration aspects – far surpassing the 50% benchmark. With Unitaid having achieved a 78% result in 2024, this upward trend demonstrates that integration is being embedded into Unitaid’s approach to programming with a focus on supporting innovations that strengthen health systems and help address different demands. This is nicely illustrated in the diagram (overleaf) showing how different parts of Unitaid’s product portfolio together address the overlapping and holistic needs of a pregnant mother and her newborn child. An example of Unitaid’s below approach to integration is highlighted in output 1.1 where Unitaid introduced a package of 9 diagnostic and preventative tools to be delivered through antenatal care for ending vertical transmission of Chagas, HIV, hepatitis B and syphilis.

Notable examples of grants in Unitaid’s portfolio that promote integrated approaches include:
- Medical oxygen grants for production capacity and infrastructure in Tanzania and Kenya, alongside grants for accelerating access to innovative respiratory care products. Oxygen is a life-saving drug essential for a wide range of conditions – particularly for maternal and newborn health.
- Multiplex diagnostics: supporting platforms that can test for multiple diseases, and are focused on self-testing, point-of-care and near point-of-care testing technologies that can easily be adopted by health systems as they offer significant advantages in terms of patient reach, reduced healthcare worker needs and overall reduced costs. For example, triplex RDTs that enable simultaneous point-of-care detection of HIV, hepatitis B, and hepatitis C virus or syphilis from a single capillary blood sample in 15-20 minutes – streamlining integrated screening in antenatal and community settings with minimal training or equipment.
- SafeBirth Africa: focused on a first response bundle of care for postpartum haemorrhage in pregnant mothers which integrates early detection and effective treatment, in line with WHO recommendations for clinical integration in maternal health programmes.
- Regional Manufacturing for Equitable Access: the diagnostics strand of Unitaid’s African manufacturing programme prioritises dual and triple-use rapid diagnostic tests (RDTs) for screening multiple disease conditions in antenatal care, community outreach and HIV services.
While Unitaid-supported products are effectively promoting integrated approaches, the pressure and scrutiny to go further and better align different products and approaches will only increase following major cuts to global health financing. Unitaid will need to continue taking difficult decisions in prioritising certain product classes and products over others, including deprioritising innovations that may offer significant benefits but be too vertical or limited in their use.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to the KPI targets over the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Overall Unitaid are assessed as having responded effectively to last year’s recommendations.

Previous year’s recommendation(s)	Actions taken
Recommendation 1.1: / Unitaid to ensure they’re taking a strategic approach to investments in the long-acting portfolio, balancing the potential for very large public health impact against the greater uncertainty and risk, and still backing clearer ‘winners’ in the portfolio, particularly in the current context of constrained financial resources. Unitaid to consolidate learnings from managing the long-acting portfolio, for informing future investments in long-acting products.	Overall Unitaid have evidenced taking a strategic approach to their long-acting portfolio, balancing the higher risk against the transformative potential and ensuring a diverse portfolio of other products – as illustrated by the strong results across this output. Unitaid reviews of the continued relevance, grantee capacity to deliver, and value for money of their long-acting grants has resulted in important prioritisation in 2024 and 2025: / Terminating in November 2024 the Medincell grant for the development of long-acting ivermectin. / Closing in 2025 the GLAD grant with the University of Washington due to operational weaknesses in addressing significant risks. / Protecting investments in long-acting HCV treatment and TB preventive treatment with the University of Liverpool given strategic relevance and grantees’ strong operational capacity. / Continuing to use phased stage-gate approaches, time-to-market analyses, and Product Introduction Plan updates to mitigate risks for ongoing long-acting grants. / Recommending the University of Liverpool’s Centre of Excellence for Long-Acting Therapeutics (CELT) also work on the nexus between long-acting technologies, climate and health for greater cross-cutting impact across Unitaid’s portfolio and in line with global health priorities.
Recommendation 1.2 (major): / Unitaid to continue paying close attention to scalability issues for products in their maternal and child health portfolio, including grants on cervical cancer and safe pregnancy through tackling pre-eclampsia and post-partum haemorrhage. Unitaid to collaborate with partners - including FCDO, the Global Financing Facility and UNFPA among others - to share thinking and develop case studies and evidence on how these products can be best scaled up, including through incorporation into Ministries of Health’s domestic procurement plans. Learnings should inform strategic discussions of Unitaid’s portfolio balance for their post-2027 strategy.	Unitaid have demonstrated significant attention to scalability issues in their maternal and child health portfolio and working with partners to identify clearer scale-up pathways: / Organising a full day donor partner meeting at the 2025 World Health Assembly to bring together 6 key donors – the Beginnings Fund, CIFF, FCDO, Gates Foundation, GFF, and Unitaid - to identify areas for mutual planning and engagement. This platform will support ongoing coordination at national and global levels. / Through the SUPREME Grant Agreement process (for pre-eclampsia and anaemia), Unitaid and partners led country co-design workshops in Kenya, Senegal, Tanzania, Ghana and Malawi to ensure grant plans in each country reflected government and procurement and regulatory agency priorities, as well as the work of other donors (e.g. CIFF, Beginnings Fund, Gates – building on the above platform). / Unitaid co-chair the EWENE Health Products Working Group (supporting countries in scaling up life-saving maternal and newborn commodities), resulting in the development of a Framework for Action to align partners. / Unitaid mobilising country commitments and a longer-term domestic scale-up pathway for cervical cancer tools by co-hosting Global Forums on cervical cancer in Cartagena (2024) and Bali (2025). These had ministerial-level participation and secured commitments to elimination and financing contributions. / Investing in self-care models for cervical cancer which can further strengthen their health system integration and lower-cost scale-up, for example support for community-based self-collection for HPV screening. / Unitaid is exploring AI-based screening technologies for cervical cancer which could improve the quality of services and their affordability, so strengthening a future scale-up pathway.

Recommendations for the year ahead

Recommendation 1.1 (major): Unitaid should build on the integration successes of their current portfolio (e.g. multiplex diagnostic platforms, maternal health bundles) when developing their next multiyear strategy beyond 2027 to prioritise innovations that will maximise integration opportunities. With constrained global health financing, the health SDGs remaining off-track, and increased domestic financing and ownership, integration-focused innovations will be essential for strengthening health systems and minimising vertical approaches. Strong, clear-sighted management will be needed to align more diverse funding streams (growing specified funding and innovative financing) with Unitaid’s core portfolio and to avoid undermining an integration-focused approach. Effective engagement with communities, civil society and countries will be key to success here (see recommendation 3.2).

Output Title		2. Create systemic conditions for sustainable, equitable access
Output number:			2.	Output Score:		A
Impact weighting (%):			25%	Weighting revised since last AR?		No
Indicator(s)	Milestone(s) for this review				Progress
Output 2.1 Demonstrated progress in planning for and investing in more rapid pathways to regulatory approval	Continued progress in planning for and investing in more effective and efficient regulatory systems and more rapid pathways to approval, enabling timely access to quality medical products. This includes strong performance of the WHO RPQ investment (against below targets) and Unitaid's broader regulatory strengthening work: / • Proactive engagement to help develop the new WHO RPQ Strategic Framework by the end of 2025. / • Continued Unitaid leadership to strengthen RPQ capacity-building and the promotion of regulatory convergence and harmonisation / • Number of IVD/FPP/APIs prequalified: (12 IVD; 30 FPPs; 5 APIs - total of 47) / • Number of IVD/FPP/APIs prequalified at or below target time: 50% (IVD - 720 days; FPP - 720 days; API - 900 days)				Met Expectation (A) / In 2024, WHO’s Regulation and Prequalification (RPQ) programme prequalified 52 products for Unitaid-priority diseases (HIV, Hepatitis C, TB and malaria), exceeding the target of 47. This consisted of: / 11 IVDs (In-Vitro Diagnostics), just missing the target of 12. / 30 FPPs (Finished Pharmaceutical Products), meeting the target of 30. / 11 APIs (Active Pharmaceutical Ingredients), exceeding the target of 5. / For timeliness of prequalification, performance varied against the benchmark of 50% of products being prequalified at or below their target time, with the ongoing COVID-19 backlog of products and product complexity reported as contributing factors: / No IVDs met the 720-day target. / 76% of FPPs met the 720-day target. / 44% of APIs met the 900-day target. / 2024 saw important RPQ ‘firsts’ for Unitaid priority areas (e.g. first Hepatitis C self-test). Unitaid helped develop WHO RPQ’s Strategic Action Plan 2025-2028, which importantly included stronger aspects of environmental sustainability in regulatory standards - of significance to Unitaid’s climate and health work. There was positive progress on broader regulatory system strengthening through 2024 and 2025, including expansions of the WHO Collaborative Registration Procedure to include more authorities and vector control products (of relevance to Unitaid’s malaria portfolio).
Output 2.2 Demonstrated progress in planning for and investing in technology transfer and innovative supply models	Advance progress on the implementation of the Regional Manufacturing Initiative by mid-2025, leveraging Unitaid’s role as an influencer, pathfinder and investor to establish viable business cases and interventions for the local production of cost-competitive, quality health products in select LMIC regions.				Moderately exceeded expectation (A+) / Through 2024 and 2025, Unitaid moved from planning to early implementation of its regional manufacturing programme in Africa, successfully securing Executive Board approval in July 2025 for 2 multi-year grants with a combined value of ~$48m that look to catalyse regional production of Unitaid priority products across HIV, malaria and maternal health. The programme is holistic in seeking to address the various barriers to scaling up African health manufacturing, integrates well with Unitaid’s portfolio (including pandemic preparedness and climate and health), and is supported by a coherent approach to regional partnerships and convening.
Output 2.3 Knowledge increased, and evidence disseminated via peer-reviewed, published studies funded by Unitaid to support equitable access (with emphasis on evidence generated at a disaggregated level including gender disaggregation)	Strong demonstration that Unitaid-funded studies support equitable access by increasing and disseminating knowledge and evidence (with emphasis on evidence generated at a disaggregated level).				Met expectation (A) / In 2024 Unitaid continued to make valuable contributions to the global evidence base with 71 peer-reviewed publications supported by Unitaid funding. Most (83%) presented original research and new evidence. Gender-disaggregated data was included in ~45% of publications. Notable examples of this evidence base informing global policy and standards include Unitaid-funded studies on TB and HIV being referenced in updated guidelines by WHO and other regulatory bodies in 2024 and 2025.
Output 2.4 Products supported by Unitaid contribute to making health care greener and more conducive to sustainable development	Continued implementation of the Climate and Health strategy, including: / - climate smart health products advanced through a dedicated AfI and through integration into broader investments / - climate smart health products pathways promoted beyond Unitaid, through demonstrated partner engagement and at least one technical publication / - Political and financial will built to fund Unitaid for its climate smart health products approach, including through advancement of a Unitaid concept note.				Moderately exceeded expectation (A+) / Unitaid demonstrated continued, strong progress in its Climate and Health Strategy, with Executive Board approval of Unitaid’s first Climate and Health Area for Investment in December 2024, and an October 2025 $10m call for proposals on heat-stable health products. Dedicated grant investments have been pushed back following ODA cuts, but progress towards major climate financing from 2027 onwards is encouraging. Unitaid continue to be a thought leader and key convenor, including 2 studies in 2025 on the climate benefits and pathways of long-acting products, alongside leading on green supply chains as part of ATACH. Climate and health objectives are effectively and clearly being mainstreaming across the portfolio (e.g. regional manufacturing and maternal health).

Output 2.1: Demonstrated progress in planning for and investing in more rapid pathways to regulatory approval.

Unitaid’s grant to WHO’s Department of Regulation and Prequalification (RPQ) is a Unitaid ‘Enabler’ investment: a catalytic investment in a partner who’s uniquely positioned to implement work that addresses systemic access issues crucial for Unitaid’s overall mission. By pre-qualifying new health products (i.e. providing a global-level regulatory approval), WHO RPQ helps address gaps in regional and country-level regulatory capacities and standards, contributing to increased access to health technologies. This investment supports Unitaid priority products to meet the required levels of quality, safety and efficacy, thereby: charting an access and quality pathway for new innovations; fostering competition among high-quality product manufacturers; facilitating country registration (including collaborative registration); and strengthening the capacity of country regulatory bodies to review and approve new products themselves.

In 2024, WHO’s Regulation and Prequalification (RPQ) programme overall exceeded targets for Unitaid priority diseases across HIV, Hepatitis C, TB and malaria by prequalifying 52 products against a target of 47. Performance was strongest for Active Pharmaceutical Ingredients (APIs), more than doubling the target of 5 products to prequalify 11 products, meeting the target of 30 for Finished Pharmaceutical Products (FPPs), and just missing the target of 12 In-Vitro Diagnostics (IVDs) with 11 prequalified. Performance was more mixed for the timeliness of approvals against the benchmark of 50% of products being prequalified at or below their target timeline: with FPPs exceeding targets (76% prequalified within 720 days), APIs just missing the target (44% prequalified within 900 days), but IVDs substantially off-track (0% prequalified 720 days). This performance is similar to 2023 where FPPs and APIs met targets, while IVDs were off-track (again 0% meeting the 720-day target in 2023)– pointing to a clear need for RPQ to strengthen their approach to IVDs and identify targeted improvements.

The ongoing, legacy impact of COVID-19 delays is cited as a key contributing factor to delays, with products deprioritised until after the pandemic and now coming through the system. While no IVDs met the target, all of these were malaria RDTs (rapid diagnostic tests) and a G6PD test (for identifying glucose-6-phosphate dehydrogenase enzyme deficiency in patients and hence the right malaria treatment) which were submitted during the COVID-19 pandemic. This is understandable to some extent, but from 2025 onwards we would expect that this backlog is cleared and there should be improvements in performance, particularly for IVDs. It would be helpful for Unitaid to work with WHO RPQ to demonstrate a clear plan of action for addressing the backlog in cases, or to at least provide upfront amended expectations and a clearer overview if they’re already aware of a continued backlog which would be impossible to remedy. Submission complexity is also cited as a contributing factor. For example, the G6PD application had revisions to its intended use and required additional review rounds – RPQ would usually require a new application in this circumstance but exceptionally extended the original application to avoid further overall delays given the product’s importance for antimalarial treatment. This came at the cost of meeting target timelines.

Balanced against these timeliness issues are some important regulatory ‘firsts’ in 2024 that helped accelerate access in Unitaid priority areas. This consisted of RPQ prequalifying: the first Hepatitis C (HCV) self-test; the first mpox diagnostic via Emergency Use Listing (EUL) – strengthening outbreak readiness; and the first tafenoquine products with the companion G6PD test, supporting radical malaria cure and prevention. For TB notable ‘firsts’ included the first TB diagnostic test, the first dispersible rifapentine tablets for child-friendly TB prevention and treatment, and strengthening API security of supply for TB treatments with new sources of rifampicin, rifapentine and the first delamanid API.

Unitaid worked with RPQ and its other donors to shape the WHO RPQ Strategic Action Plan for 2025–2028. This multiyear action plan defines KPIs for prequalification processes and products, regulation and knowledge management. Importantly for Unitaid, the plan introduces stronger aspects of environmental sustainability in regulatory standards – for example through greener manufacturing practices, environmental risk assessments and sustainable packaging and labelling. This nicely complements Unitaid’s strategic initiative on Climate and Health (see output 2.4).

2024 and 2025 also saw progress on broader regulatory convergence and harmonisation as part of regulatory system strengthening. WHO’s Collaborative Registration Procedure (CRP) is a regulatory mechanism that uses the principles of reliance and improved regulatory coordination to accelerate the approval of new products: national regulatory authorities can use assessments and data from other trusted partners (Stringent Regulatory Authorities like the European Medicines Agency, MHRA, and WHO RPQ itself) rather than repeating a full review themselves. In 2024 8 new countries joined the Stringent Regulatory Authority CRP for a total of 65 participating national regulatory authorities (NRAs), while 3 additional NRAs joined the CRP for IVDs to reach a total of 35 NRAs. The total number of NRAs participating in the PQ CRP increased from 66 to 67. 194 new product registrations were achieved in 2024 through the CRP (a similar number to previous years), with the cumulative number of registrations reaching nearly 1500 to date – showing the CRP’s growing use and real-world impact in achieving global regulatory efficiencies. Of particular relevance to Unitaid’s portfolio was WHO expanding CRP in 2024 to include vector control products as a pilot, with Ghana registering the first vector control product through the CRP within 28 working days in 2024. Following this success, WHO moved from pilot to full CRP launch for vector control products in June 2025 – 6 countries were participating in the CRP for vector control products by the end of 2024.

However, looking ahead, 2025’s cuts to global health financing will likely impact WHO RPQ’s capacity. This may bring challenges for Unitaid’s RPQ investment and potential adjustments of expectations. It will be essential for Unitaid to consider how to best adapt this investment and Unitaid’s broader ambitions on regulatory system strengthening to wider landscape shifts. Unitaid will need to work closely with WHO RPQ, other RPQ donors, and national and regional regulatory bodies to clarify the role and ambition of WHO RPQ going forward, different actors’ roles and responsibilities as a result, and how the gains made to date can be best protected to ensure continued progress.

Output 2.2: Demonstrated progress in planning for and investing in technology transfer and innovative supply models.

Through 2024 and 2025, Unitaid moved from planning to early implementation of its regional manufacturing programme in Africa, successfully securing Executive Board approval in July 2025 of its two multi-year grants for 2025-2029: MADE (diagnostics manufacturing through PATH) and MedSuRe (therapeutics production through USP). With a combined value of $48m these grants aim to act as a set of catalytic blueprints for accelerating price-competitive, quality health product manufacturing in Africa across Unitaid priority products of antimalarials, malaria Rapid Diagnostic Tests (RDTs), HIV self-test and multiplex tests, HIV anti-retrovirals, and diagnostics and therapeutics for post-partum haemorrhage. It’s positive to see the integrated and aligned nature of this programme with the rest of Unitaid’s portfolio –with the focus on maternal health, malaria and HIV commodities synergising with other grants focused on improving access to innovations in each of these areas. There is also good integration of the strategic initiatives on climate and health and pandemic preparedness – for example the inclusion of injectable manufacturing capabilities for oxytocin and tranexamic acid for maternal health that could be flexed to other pandemic response products. While on climate and health, the grants will look to maximise opportunities for manufacturing climate-smart health commodities (e.g. heat-stable carbetocin for maternal health) and introducing decarbonisation opportunities into manufacturing processes. To fund this programme Unitaid are combining core funding (covering 30%) with specified funding (earmarked contributions from the EU, Gates and South Korea for maternal health and pandemic preparedness): a good model of how to best use the growing proportion of specified funding to advance Unitaid’s strategy and effectively mitigate against distortions to strategic priorities.

The comprehensive, coherent nature of the regional manufacturing programme is impressive, with the 2 grants together looking to address the range of barriers to increased health manufacturing in Africa:
- A cross-cutting regulatory and quality assurance budget for advancing national and regional regulatory infrastructure and harmonisation - with good opportunities to align with Unitaid’s WHO RPQ investment (see output 2.1).
- Technology transfer including dedicated funding to the Medicines Patent Pool.
- Technical assistance for supply and demand forecasting.
- Access to financing with targeted funds and capacity for establishing blended financing to bring in new funding from Development Finance Institutions and others.
- Building regional capacity for Contract Research Organisations (CROs) to provide bioavailability and bioequivalence services to manufacturers, reducing dependence on CROs outside Africa and strengthening regional pandemic preparedness (pandemics strain international CRO capacities).
- Building regional capacity to design processes and formulations of active pharmaceutical ingredient (API), like dolutegravir for HIV and pyronaridine for malaria, rather than relying on imported API.
- Regional biotechnology education and training programmes to establish platforms for workforce development (through African Society for Laboratory Medicine and the University of Cape Town).
While the programme is still in its inception phase and final manufacturing partners and workplans won’t be finalised until end 2025, from an FCDO perspective it is reassuring to see strong alignment with existing support to regional manufacturing in Africa. There is clear overlap between Unitaid’s priority countries and our regional ‘Manufacturing Africa’ technical assistance programme in Kenya, Senegal, and Nigeria. This includes opportunities for Unitaid to build on UK support to the Institut Pasteur de Dakar (IPD) in Senegal – the UK has a research partnership with IPD. Progress is promising with the diaTROPIX facility (IPD’s diagnostics facility) expanding its annual production capacity from 5 million to 75 million tests per year in late 2024 and early 2025 – building on UK support and a Unitaid partnership with FIND that included a technology transfer from GADx in the UK.

The way Unitaid have developed this set of grants through a stronger focus on co-creation with African partners is encouraging (and is a good example of the positive progress made for outputs 3.2 and 3.3). During grant development Unitaid convened a co-creation workshop in early 2025 in Geneva with Africa-CDC, AUDA-NEPAD, WHO and representatives from the Nigerian and South African governments and health agencies. There was notable engagement with Executive Board members, including African countries, NGO and Communities delegations, to ensure strong alignment during grant development. This aligns with feedback from South African manufacturer Kiara Health to FCDO during the December 2024 Executive Board visit – Kiara emphasised how Unitaid’s engagement felt different to other global health partners in that they were truly listening.

Unitaid’s convening and influencing role in aligning partners and different expertise and funding streams to support African health manufacturing was evident throughout 2024 and 2025. This included Unitaid working with UNFPA to support SADC (Southern Africa Development Community) develop its Pooled Procurement Services Business Plan – key for predictable demand to underpin local production. This built on Unitaid’s ongoing work as Chair of the Expert Panel for Africa CDC’s African Pooled Procurement Mechanism and Unitaid’s now formalised strategic partnership with Africa-CDC with an MoU signed in May 2025 (see output 3.3). Other important convening moments included Unitaid co-sponsoring the inaugural African Medicines Manufacturing Trade Exhibition and Conference (AMMTEC) in Tanzania in November 2024 and Unitaid presenting their grant programme portfolio at the WHO AFRO Regional Committee in August 2025. Unitaid plan to strengthen the impact of this convening work through targeted funding as part of MoUs with Africa-CDC and AUDA-NEPAD.

Output 2.3: Knowledge increased, and evidence disseminated via peer-reviewed, published studies funded by Unitaid to support equitable access.

In 2024 Unitaid continued to make valuable contributions to the global health evidence base, with 71 peer-reviewed publications supported by Unitaid funding. While this is a reduction in the total number of publications compared to the 97 publications reported for 2023, this is still an important and significant contribution. 83% of these 71 studies presented original research and new evidence, and nearly half (45%) included gender-disaggregated data (either in study results or participant characteristics). Research spanned over 42 low- and middle-income countries, with a strong focus on Africa (Cameroon and Uganda were the largest single-country contributors with 12 and 10 studies respectively).

Across the current strategic period 2023-2027, Unitaid has supported 168 publications – 97 in 2023 and 71 in 2024 – demonstrating sustained impact. In line with Unitaid’s mission of accelerating access for those who need it most, almost 75% of these studies focused on highest-risk and marginalised populations, including significant work on paediatric TB, MDR-TB treatment and HIV prevention (PrEP) among adolescent girls and young women, men who have sex with men and transgender women, particularly in South Africa and Brazil. In alignment with Unitaid’s multi-pronged approach to accelerating equitable access and informing how products perform in real-world settings, publication types in 2024 were broad in nature: 32% of the studies were implementation/feasibility studies; 21% research methods, protocols and recommendations; 17% technology evaluations and assessments; 15% clinical, pharmacokinetic and health-outcome studies; 6% economic or cost effectiveness studies; 1% genetics-focused studies and 7% other.

This evidence base is informing key global health guidance and policies, including WHO and other regulatory and standards bodies. Notable examples over 2024 and 2025 include the Unitaid-funded endTB clinical trial prompting a 2024 WHO Rapid Communication on drug-resistant TB treatment, later referenced by PAHO and subsequently incorporated into the 2025 WHO consolidated guidelines on Tuberculosis. Similarly, Unitaid-funded studies on HIV testing in rural Malawi and HIV self-tests in South Africa were cited in WHO’s consolidated guidelines on differentiated HIV testing services in January 2024 and referenced in 16 other policy and guideline documents published by WHO, the European Centre for Disease Prevention and Control and other regulatory bodies through 2024 and 2025.

Output 2.4: Products supported by Unitaid contribute to making health care greener and more conducive to sustainable development.

Through 2024 and 2025, Unitaid continued the strong trajectory of its Climate and Health Initiative, positioning itself as an early leader in laying the foundations for greener, more resilient health systems. In December 2024, Unitaid successfully secured Executive Board approval for its first Climate and Health Area for Intervention (AFI) – the first stage in Unitaid’s grant-making process, outlining the key areas and objectives of investment. However, with reductions in global ODA in early 2025, Unitaid pushed back the timelines of dedicated climate and health grants to better align with likely timing of potential future specified funding from a significant climate funder. While this is concerning given the pressing nature of the climate emergency, it is a realistic and sensible prioritisation of funding and protects the opportunity for dedicated Unitaid grants in the future when the funding situation allows.

In the meantime, Unitaid continued implementing its climate and health strategy, including launching a $10m call for proposals investigating the heat-stability of health products in October 2025, and continuing progress towards an expected funding submission to a major climate funder by March 2026 (including programme design work, priority interventions, priority country engagement and links to Nationally Determined Contributions). The front-runner nature of Unitaid’s work on climate and health is reflected in Unitaid being the only prospective health grant from this major climate funder focused on both mitigation and adaptation to the climate emergency.
Unitaid also continued effectively integrating climate and health across its portfolio. Climate adaptation using heat stable products was incorporated into pre-eclampsia and anaemia grants developed during 2025 and in the African regional manufacturing programme (see output 2.2). All calls for proposals for Unitaid grants are now scored against a climate criterion, and procurement processes require bidders to demonstrate sustainability commitments. A notable example of Unitaid embedding climate and health across its work was Unitaid supporting WHO to issue a Call for Action in December 2024 for a “Greener Pharmaceuticals’ Regulatory Highway”, linked to Unitaid’s RPQ investment (see output 2.1).
This aligns with Unitaid acting as a leading convenor in the climate and health ecosystem. Unitaid co-convened with WHO a global consultation on low-carbon, climate resilient supply chains in October 2024, which led to a joint position paper in Q1 2025, co-organisation of the ATACH Technical Meeting in May 2025, and a further ATACH-Unitaid online technical consultation on the heat stability of health products in September 2025 with over 70 experts. Other important thought leadership contributions included: a March 2025 study on decarbonisation pathways for first-line HIV treatments (including engaging over 20 manufacturers); a May 2025 study with the University of Liverpool on the dual climate benefits of long-acting technologies; and a co-authored paper with the Asian Development Bank and Health Care without Harm on low-carbon, climate-resilient products, models of care and supply chains. This which was later presented at Brazil’s Global Conference on Climate and Health in July 2025.
Unitaid have effectively strengthened their organisational capacity to take forward this climate and health work through filling two climate and health team roles in 2024 and onboarding a Sustainability Manager in April 2025 – this role is focused on mitigation, low-carbon product design and manufacturing, resilient supply chains and climate-smart market-shaping in Unitaid’s programmes. Unitaid have also identified a roster of Climate and Health experts to provide ad-hoc expertise for climate-focused investments to their Proposal Review Committee (an independent panel of expert advisers who help review grant proposals). However, it is concerning that Unitaid remains off-track for reducing its own organisational carbon footprint against its operational KPIs. Both travel and procurement-related emissions increased compared to 2023, meaning Unitaid is off-track for its admittedly ambitious interim target of reducing the Secretariat’s carbon footprint by 40% by 2025, ahead of its overall target of a 50% reduction by 2030. This is significantly related to the trade-off between impactful in-person engagement and reduced carbon emissions – with 2024 seeing a 27% increase in emissions from Unitaid partners (including Executive Board members like the UK) attending in-person meetings hosted by Unitaid. While this is concerning, the UK recognises that some factors including international travel are beyond Unitaid’s control and require broader global transformational change. However, given Unitaid’s organisational DNA for innovation, they should demonstrate stronger progress on reducing their footprint going forward.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following Unitaid-FCDO discussions in spring and summer 2025, minor adjustments were made to the wording of the milestone targets for Output Indicators 2.1, 2.2 and 2.4 to best assess the key areas of focus in 2024 and 2025. These updates are necessary given these output targets are mainly qualitative and not suitable for upfront, multi-year agreement. A similar exercise will occur in 2026.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Overall Unitaid are assessed as having partially responded to last year’s recommendation for this output. Progress has been made as reported below. Further dialogue with FCDO would be helpful for more clearly defining and articulating the upfront priorities and aims of the RPQ investment and Unitaid’s broader regulatory system strengthening approach and strategy. This is partly the result of turnover in the FCDO team overseeing Unitaid funding since the last RPQ grant went through Executive Board approval (in 2023), and FCDO’s policy work in the regulatory system strengthening space being nascent. This will likely be aided by the upcoming Executive Board review of the next RPQ grant investment, expected in early 2026.

Previous year’s recommendation(s)	Actions taken
Recommendation 2:1 / Unitaid should ensure that the key aims, activities and achievements of the WHO RPQ Enabler investment and their broader work on regulatory systems strengthening (RSS) are clearly defined and articulated in ongoing reporting and engagement with FCDO. Unitaid to provide ongoing updates to FCDO on how the RPQ investment and broader RSS work align with Unitaid’s strategic initiatives on regional manufacturing and climate and health (referenced in the 2023 RPQ cost-extension).	Unitaid have strengthened their reporting and engagement with FCDO through 2025 to better articulate the WHO RPQ Enabler grant’s activities and achievements and the links to Unitaid’s broader regulatory system strengthening. This has continued with a fruitful FCDO dialogue as global ODA cuts raise significant questions over regulatory system strengthening going forward. Unitaid have also demonstrated clear alignment of the RPQ investment and broader regulatory engagement with their strategic initiatives on regional manufacturing, and climate and health. However, Unitaid’s overarching strategy for the RPQ investment and regulatory system strengthening needs to be further clarified with FCDO.

Recommendations for the year ahead

Recommendation 2.1: global health financing changes in 2025 will likely impact on WHO RPQ’s capacity and workflow going forward. Unitaid should consider how to adapt their core RPQ Enabler investment, alongside how to best support the African Medicines Agency (AMA) as part of regulatory system strengthening. Unitaid will need to work closely with WHO RPQ, other RPQ donors, key global health partners, and national and regional regulatory bodies to clarify the role and ambition of WHO RPQ going forward, other actors’ roles and responsibilities, and how gains made to date can be protected and continued.

Output Title			3. Foster inclusive & demand-driven partnerships for innovation
Output number:				3	Output Score:		A+
Impact weighting (%):				25%	Weighting revised since last AR?		No
Indicator(s)		Milestone(s) for this review				Progress
	Output 3.1 / Partnership with the Global Fund supports faster and more equitable / access to innovation		I) Evidence of effective partnering with the Global Fund, e.g., based on Partner Survey feedback, broader recognition of Unitaid's contribution to help The Global Fund meet their objectives through the provision of key health products taken to scale, and collaboration within the context of NextGen Market Shaping work. / II) Collaboration with the Global Fund as they launch their next Investment Case and in the context of Global Fund's 2025 replenishment.			Moderately exceeded expectation (A+) / Unitaid and the Global Fund built on their 2024 3-year Strategic Framework through 3 structured pipeline-alignment reviews in 2025, producing clear workplans that outline their complementary roles. This will be institutionalised through bi-annual pipeline reviews every March and September with a rolling horizon to 2030. The example of lenacapavir highlights strong partnership, while showing the risks on communicating overlapping roles considering global health architecture reforms. Unitaid effectively represented the Partners Constituency on the Global Fund Board in 2025, contributing to GC7 and GC8 planning and the Global Fund’s 2025 Investment Case and 8th Replenishment with analysis on the role of Unitaid-supported innovation.
	Output 3.2 / Communities and civil society are effectively engaged in the development and implementation of Unitaid's portfolio		Proportion of programmatic priorities with a demonstrated engagement with communities and civil society across the operating model: / Baseline of 40% with good or strong engagement in 2022. / Progress towards 100% of priorities with a demonstrated 'good' or 'strong' engagement by the end of the Strategy (2027).			Moderately exceeded expectation (A+) / Continued progress with 77% of programmatic priorities demonstrating good or strong engagement in 2024 – Unitaid are on track to meet their target of 100% by end 2027. The 2025 Implementers Survey also shows improvements with a 13% increase to 71% of implementers agreeing that national communities and CSOs are involved in project design and implementation. In 2025 Unitaid undertook scoping work to further strengthen community and civil society engagement (CCSE) in their operating model: benchmarking their approach against other organisations’ models and preparing options for an enhanced CCSE approach for the December 2025 Executive Board (including better tracking and clearer targets for Unitaid funding going to CCSE).
	Output 3.3 / Low- and middle-income countries are effectively engaged in the development and implementation of Unitaid's portfolio		Demonstrable progress in advancing effective engagement with country stakeholders that leads to better alignment with country stakeholder needs and priorities for next investment cycles, additional partner agreements with Ministers of Health and Regional Bodies, and increased investments through low- and middle-income country institutions and manufacturers. / This includes, in the context of the workplan agreed as an outcome of the Functional Review process: / • At least one (and up to four) country agreement(s) (Memorandum of Understanding) by mid-2025 / • At least one (and up to two) flagship country visit(s), bringing together key stakeholders, by mid-2025 / • Increased investment in low- and middle-income country organizations (e.g., captured through diversification of the implementer base, linked to Organizational KPI F, and increased focus on regional manufacturing)			Moderately exceeded expectation (A+) / Unitaid signed 2 important MoUs in 2025 with South Africa and Africa-CDC on the back of active participation in key country and regional forums, including a notable Unitaid-African Ministers declaration from the 2025 WHO AFRO Regional Committee and active Unitaid involvement in UK-South African MP exchanges in 2025. This follows on from the MoUs also being negotiated with Kenya and Nigeria. Latin American partnerships have been strengthened through PAHO Enabler investments. 2 flagship Executive Board country visits were completed by end 2024 to strengthen partnerships: Kenya in February 2024 and South Africa December 2024. A now fully staffed Partnerships Team are actively developing options for enhancements to Unitaid’s operating model to go further on country engagement. Implementer diversity continued to improve with Global South partners constituting 23% of Unitaid lead grantees in 2024, although accelerated progress is needed to meet the 40% target by 2027.
	Output 3.4 / Unitaid effectively supports global health preparedness and emergency response [PPR]		Pandemic Preparedness and Response (PPR): / i) Document and publicise Unitaid's vision on Access for PPR to shape the evolving global PPR landscape, including R&D and nascent initiatives. / ii) Advance work in investments related to new business/supply models for therapeutics (small molecules, antibodies) and diagnostics that can enable equity needs in low- and middle-income countries for key countermeasures in the case of a pandemic, by 2025.			Met expectation (A) / Unitaid remain a leading actor for accelerating access to medical oxygen as a key pandemic treatment. Ongoing investments in East African production of medical oxygen, Vayu’s innovative oxygen tools for infant respiratory care and WHO’s Health Emergencies Program will soon be complemented by additional grants in new medical production and distribution technologies and sustainable business models for maintaining the major $1bn global C-19 investments in medical oxygen. Unitaid also continued to champion access considerations in key pandemic forums including the 100 Day Mission. The African regional manufacturing initiative (see output 2.2) will help strengthen regional supply of key diagnostics and treatments. However, resource constraints have paused a planned investment in monoclonal antibodies.

Output 3.1: Partnership with the Global Fund supports faster and more equitable
access to innovation

Through 2024 and 2025, Unitaid and the Global Fund sustained an effective, clearly defined partnership to support faster, more equitable access to innovation. The 3-year Strategic Framework signed in 2024 (reported on in last year’s Annual Review) has been operationalised in 2025 through three structured pipeline-alignment reviews. These reviews produced a refreshed shared pipeline and set of near-term priorities across aligned areas in the 3 diseases (e.g. next-generation TB diagnostics, African-manufactured HIV rapid diagnostic tests, anti-malarial drug resistance, long-acting HIV prevention options, long-acting depot buprenorphine and low dead space syringes (LDSS) for HIV co-infections etc). These structured pipeline-alignment reviews will be institutionalised going forward through bi-annual reviews every March and September with a rolling horizon to 2030. Together the Strategic Framework, pipeline reviews and associated workplans clearly outline how Unitaid and the Global Fund leverage each of their complementary strengths across the product pathway to accelerate scale-up of health innovations. Unitaid monitor the landscape, pioneer regulatory pathways and access conditions, and shape early markets, while Global Fund aggregate demand and translate policy into country-level scale through grants and procurement. This is nicely illustrated in the below joint Global Fund-Unitaid market-shaping workplan.

An encouraging example of this complementary partnership in action is the initial progress made in accelerating access to lenacapavir as a long-acting HIV prevention tool. As referenced in output 1.1, Unitaid are a leading early actor in addressing key access barriers for lenacapavir and shaping its early market for LMICs. Grants in pathfinder countries of Brazil, South Africa and Zambia are generating early lessons on the best delivery models, community acceptability, reaching vulnerable populations, and integration into existing HIV prevention programmes, alongside Unitaid’s work with generic suppliers to fast-track cheaper and more widely available supply. In tandem the Global Fund is working with Gilead and PEPFAR for the initial roll-out of Gilead’s originator product of lenacapavir; aiming to provide 2 million doses globally by end 2027 to 10 high-burden HIV countries, as part of clearing a pathway to global scale-up in the medium term. This commenced in November 2025 with the first shipment of doses being delivered to Zambia and Eswatini, albeit at a small-scale of 500 doses per country. While in its early stages, the example of lenacapavir demonstrates how Unitaid and Global Fund can complement each other’s work to promote equitable access.

However, this lenacapavir example also highlights the risks in the Unitaid and Global Fund partnership. While roles are complementary and different, the external language and framing of each organisation’s work – particularly for non-technical audiences not closely familiar with both organisations – demonstrates significant overlap and confusion with both organisations commonly cited as “accelerating access”, implementing key “market-shaping” initiatives, and driving innovation. Without greater clarity and distinction of each other’s roles and different market-shaping capacities and achievements, there are risks that Unitaid’s catalytic and access-focused market-shaping work is not sufficiently recognised. This has potential knock-on impacts not just for Unitaid’s brand recognition and resource mobilisation, but also for discussions on global health architecture reform and improved integration following major ODA reductions. Unitaid should use their strengthened strategic framework and market-shaping workplans with the Global Fund to better communicate each organisation’s different market-shaping roles and clearly distil why the Global Fund and the wider global health ecosystem needs Unitaid’s unique role. Unitaid should look to use the Lusaka Agenda discussions on shift 5 – the market-shaping and manufacturing shift – as an important route for this clearer clarification, and work with the Global Fund, other market-shaping partners and investors including the FCDO to map out the future of market-shaping and key roles going forward.

Beyond this, Unitaid continued to work closely with the Global Fund for its 2025 Investment Case and 8th funding Replenishment for Grant Cycle 8 (GC8) 2026-2029. A joint impact analysis in May 2025 (building on previous iterations for the 2019 and 2022 replenishments) continued to show their mutually supportive roles, highlighting that without the availability of innovative health products (predominantly supported by Unitaid) it would take the Global Fund an additional 3 years to achieve the same reduced level of HIV, TB and malaria deaths. Unitaid served as Global Fund Board Member for the Partners constituency in 2025, focused on innovation and equity in GC7 mid-term discussions and early GC8 planning and engagement.

Output 3.2: Communities and civil society are effectively engaged in the development and implementation of Unitaid's portfolio

Through 2024 and 2025, Unitaid built on past progress and further strengthened its engagement with communities and civil society as part of a shift to more inclusive, community-informed programming. The KPIs’ analysis of the programmatic priorities assesses engagement with communities and civil society (CCSE) against the following criteria: early engagement with communities and civil society organisations for better grant design; ensuring community voices are heard; having a CCSE activity plan and budget; establishing and supporting CCSE mechanisms that build capacity and ownership; and recognising specific community and civil society contributions to results. The 2024 results show that 77% of programmatic priorities have a demonstrated good or strong engagement: up from 75% in 2023 and on the right trajectory to meet the 100% target by end 2027 (compared to the 40% baseline in 2022). For the remaining 22% of programmatic priorities not demonstrating ‘good’ or ‘strong’ engagement, there was an increase in the proportion showing ‘moderate’ engagement from 5% in 2023 to 11% in 2024. The proportion showing no engagement has reduced from 10% in 2023 to 6% in 2023 - although this is also the result of 2024 portfolio closures of older investments predating the current strategy (e.g. HIV ART, COVID Test and Treat), it still indicates that new investments coming on board are more systematically integrating community and civil society engagement (the increased proportion in ‘moderate’, ‘good’ or ‘strong’). The proportion showing weak engagement remains similar at 6% compared to 5% in 2023.

Contributing factors and operating model changes explaining these improved results include:
- More consistent engagement at the start of the investment cycle, including in investment scoping, the articulation of areas for intervention, and calls for proposals with clearer CCSE language.
- Strengthened CCSE processes in grant selection and design, including all proposals undergoing a dedicated CCSE review and project plans requiring CCSE activities and budget lines.
- Stronger mainstreaming of CCSE across Unitaid, including CCSE inductions, a cross-Secretariat CCSE working group, and brown-bag exchanges and short case notes for future investments.
These improvements are reflected when triangulating against the below 2025 results of the Implementers Survey for CCSE questions:
- 89% agreed Unitaid engages with country-level civil society and communities through its grants (+2% from 2024)
- 71% agreed national communities and CSOs are involved in project design/implementation (+13%)
- 68% agreed such engagement contributes to achieving project outcomes (+7%)
- 61% agreed Unitaid facilitates collaboration with country stakeholders and partners (+24%)

Unitaid also administer a separate Partners Survey every 2 years focused on Partner Satisfaction, with a baseline in 2023 and a survey again in 2025. This survey assesses the extent to which Unitaid fosters inclusive, demand-drive partnerships for innovation that deliver impact. For 2025 the results were positive showing that 80% (4 out of 5) of community-based organisations and 77% of civil society organisations (7 out of 9) provided positive feedback – a strong improvement compared to 2023 results of 55% for community-based organisations (6 out of 11) and 50% for civil society organisations (12 out of 24).… However, these Partners Survey results must be taken with a pinch of salt given the relatively small sample size, with a low response rate in 2025 of just 18 partners responding – compared to 47 partners responding in 2023. While organisations not responding may indicate a weak relationship with Unitaid and poor collaboration, given that the survey was conducted in Q1 2025 it is more likely the result of the major global health challenges in early 2025 (as US ODA cuts were announced) stretching partners’ capacities to engage in activities like surveys (i.e. beyond their respective immediate priorities). Nevertheless, Unitaid should still pay attention to improving the response rate for the 2027 Partner Survey.

Despite these positive results and progress, there is more work to do. Unitaid’s Mid-Term Review highlights that community and civil society engagement remains uneven across regions and disease areas and that Unitaid often relies on implementing partners rather than direct relationships with communities on a grant-by-grant basis (linked to Unitaid’s HQ-only operating model with no country or regionally based staff). This aligns with mixed feedback from the NGO and Communities delegations to the Unitaid Executive Board – indeed in 2024 the Communities Delegation submitted a proposal aimed at strengthening community engagement and ownership in Unitaid investments. With the shifts in global health financing towards greater domestic funding and ODA reductions presenting existential threats to civil society organisations – particularly for the most vulnerable groups - it is even more important that Unitaid now goes further in taking forward people-centred, community-driven approaches across its portfolio. This will help protect equity in Unitaid’s delivery and improve the sustainability and legacy of Unitaid interventions. To that end it has been positive to see the Secretariat’s work through 2024 and 2025 responding to the Communities Delegation’s proposal and this need, including a benchmarking analysis of other global health partners’ approach to CCSE (including the Global Fund, the Robert Carr Fund etc.). The recognition of the need to do more is reflected in Unitaid’s staffing, with the addition in 2025 of a full-time staff member dedicated to CCSE. This workstream indicates a promising commitment to further changes, with consultations with Executive Board members over the summer of 2025 following the Benchmarking exercise. This has resulted in a set of proposals for how to further embed CCSE, including updated guidance, a stronger Secretariat staffing footprint, and clearer targets and better tracking of Unitaid funding going to CCSE activities. These proposals received positive feedback at the October Executive Board Committees – refining this into a clearer, agreed set of changes for implementation will be key.

Output 3.3: Low- and middle-income countries are effectively engaged in the development and implementation of Unitaid's portfolio

Unitaid have sustained the promising progress reported in last year’s Annual Review in working towards more effective and collaborative country engagement. The Secretariat’s dedicated Partnerships team being established in 2024 become fully operational as of spring 2025. Priority country and regional-level partnerships have been strengthened, firstly with an MoU signed with South Africa in March 2025 to support joint efforts on HIV, TB and cervical cancer on the back of the December 2024 Executive Board visit. South Africa is a key country partner for Unitaid, receiving the largest portion of Unitaid’s investments, and this close partnership was evident through South Africa’s 2025 G20 Presidency including a lenacapavir-focused event and visits co-hosted by Unitaid at the November 2025 G20 Health Ministers meeting, alongside Unitaid involvement in UK-South Africa MP exchanges as part of the Global Fund replenishment. Progress continues for other Unitaid priority country partnerships, with the Kenya MoU awaiting legal clearance and signature, and ongoing discussions for the Unitaid-Kenya 2026 workplan. Unitaid’s MoU with Nigeria has undergone technical review since 2024 and Unitaid are working towards approval, alongside discussions for the 2026 Unitaid-Nigeria workplan (e.g. building on Unitaid supporting Nigeria’s 2024 launch of the Cervical Cancer Taskforce)..

A notable step forward was Unitaid signing an MoU with Africa CDC in May 2025: establishing a joint action plan across medical oxygen, pandemic preparedness and innovation scale-up, including links to Unitaid’s regional manufacturing initiative. This is expected to be supported by dedicated Unitaid funding support. This focus on a strengthened African regional partnership was evident in Unitaid’s active participation at the 2024 and 2025 WHO AFRO regional committees in Brazzaville and Lusaka respectively. The WHO AFRO August 2025 meeting included a Declaration by Health Ministers on the principles of partnership with Unitaid. This declaration built on the Lusaka Agenda and 2025 Accra Initiative and had references to recognising African regulators globally (see output 2.1) and investing in regional production of health commodities (see output 2.2). It was a clear sign of the more prominent role of Unitaid in regional African health minister discussions and greater recognition of mutual goals, building on the African Health Ministers’ Platform for Unitaid launched in November 2024.

Unitaid also strengthened their regional partnership with Latin America and the Caribbean through Enabler grants and agreements with WHO PAHO to strengthen delivery on shared goals. This includes Unitaid Enabler investments of $0.8m for technical guidance and support linked to Unitaid’s ($25m) grant with PATH on the elimination of vertical (mother-to-child) transmission of HIV, hepatitis B, syphilis and Chagas disease; a $5m grant on advancing the regional HIV response; and a May 2024 MoU to intensify collaboration to end 30 communicable diseases by 2030.

This progress is partly reflected in the implementer diversity of Unitaid’s grants, with the proportion of Global South-based lead implementers increasing to 23% by the end of 2024. While sustaining progress against the 2022 baseline of 16%, this isn’t a major increase from the end 2023 figure of 21%. Further progress is needed to reach Unitaid’s target of 40% of lead implementers coming from the Global South by end 2027, which risks being off-track. While we can’t assume progress will be linear (likely coming in jumps as old grants close and new grants come online), Unitaid should roughly expect to be at 30% by end 2025 given it’s over halfway through the 5-year strategy. It’s promising to see that to date some key Global South partners have been confirmed as lead implementers in 2025 including CRID in Cameroon for malaria vector control, KELIN in Kenya for drug-resistant TB, and Fiotec in Brazil for lenacapavir.

Further progress on country engagement and partnership is needed, as highlighted by the African countries’ delegation bringing a proposal to the December 2024 Executive Board. Like output 3.2 on civil society and community engagement, Unitaid recognise this and took forward important work in the second half of 2025 to review options for strengthening Country Stakeholder Engagement in Unitaid’s operating model. This included consultations by the Secretariat’s partnerships team and country engagement lead with Executive Board members, particularly with the African delegation, and 3 options with different levels of ambition were proposed to the October 2025 Executive Board committees. Board feedback favoured the Secretariat developing a more detailed, fully costed proposal for a middle-ground ‘Enhanced’ option approach, which potentially included some regionally based staff in Africa to strengthen key partnerships. The necessary operating model changes need to be agreed, with a follow-up discussion at the upcoming Tokyo December 2025 Executive Board.

Output 3.4: Unitaid effectively supports global health preparedness and emergency response

Unitaid continue to be a leading global health actor for accelerating access to medical oxygen, a key drug for strengthening pandemic preparedness. Solid 2024 progress (August 2024 publication on the ‘Medical Oxygen Innovation landscape’ and launch of the East Africa Programme on Oxygen Access) has been followed by grant development through 2025 for introducing new medical production and distribution technologies and developing sustainable business models for maintaining COVID-19 investments, with grants due to be signed by the end of 2025. Unitaid also extended in 2025 their work with Vayu Global Health Innovations on their innovative bCPAP (bubble continuous positive airway pressure) and oxygen blender systems for non-electric, low-maintenance and affordable solutions for infant respiratory care, with an important focus on expanding access to oxygen in humanitarian and crisis settings (DRC, South Sudan, Yemen and Kenyan refugee camps). Thanks to Unitaid support, 260,000 newborns in 34 countries have been treated with bCPAP. Importantly this investment is linked to regional manufacturing and ensuring a more stable regional supply, with the bCPAP devices being manufactured by Revital in Kenya (and expanding to Indian production in 2026 with Gates Foundation support, helping also address Asian continental preparedness). Unitaid’s oxygen work has been complemented by a crosscutting $3m investment in WHO’s Health Emergencies Programme through 2024 and 2025 to provide country-level technical support coordination on oxygen access plans and guidelines, norms and standards - further joint work with WHO is being planned for 2026-2027. Unitaid’s combined efforts in market shaping and procurement have unlocked nearly 11 million Nm3 of oxygen annually across 23 LMICs, enough to treat nearly 290,000 severe COVID-19 patients. With further scale-up and domestic financing commitments in the future, this could make important contributions to future pandemic response.

Unitaid’s other contribution to pandemic preparedness has been their regional manufacturing in Africa programme, which has progressed to implementation. Output 2.2 contains further details. Unitaid also continued to make useful contributions to global pandemic preparedness forums. This includes delivering consistent messaging on access and the fragile therapeutics R&D chain to forums including the 100 Days Mission (e.g. advocacy for a multistakeholder therapeutics development coalition), the WHO/i-MCM-Net (interim medical countermeasures network), and supporting Africa-CDC and IAVI to convene a workshop on ‘Advancing a Sustainable Supply and Demand Ecosystem for mAbs’ (monoclonal antibodies) at the April 2025 Abu Dhabi World Local Production Forum. This influencing work has been supported by the addition of a dedicated pandemic preparedness Technical Officer recruited in March 2025.

However, Unitaid’s pandemic preparedness portfolio was dealt a setback with the pausing of a planned monoclonal antibodies investment in 2025. Monoclonal antibodies have major potential as treatment drugs in future pandemics given they can be designed and scaled relatively quickly (particularly compared to vaccines) once a pathogen’s structure is known – so potentially serving as an important stopgap measure before vaccines are widely available. This pause was the result of Unitaid’s funding prioritisation work from the 2025 ODA cuts and overall seems a sensible decision given constrained resources. While Unitaid retain the intention to take forward a pathfinding investment in mAbs, it reflects how pandemic preparedness as a strategic initiative has a more constrained ambition. Unitaid’s main contribution here for now is likely to remain through accelerating access to medical oxygen and helping scale African regional production of key health commodities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following Unitaid-FCDO discussions in summer 2025, minor changes were made to the wording of the milestone target for output 3.1 to best reflect the key areas of focus in 2025 (acknowledging the Global Fund replenishment and investment case for GC8). This was necessary given this output target is mainly qualitative (and was the case in 2024). A small addition has also been made to the milestone target of output 3.2 by FCDO during this Annual Review to ensure clarity to the reader on the area being measured and assessed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
No recommendations to report on from last year.

Recommendations for the year ahead

Recommendation 3.1: The Unitaid and Global Fund partnership is strong and mutually beneficial, but the external narrative and framing for newer, unfamiliar audiences risks confusion and ambiguity on their overlapping market-shaping work. Unitaid should use the strengthened partnership to clearly communicate their unique market-shaping role and the importance of Unitaid to the Global Fund. Discussions on global health architecture reform, the future of market-shaping and shift 5 of the Lusaka Agenda present an important opportunity to make this clearer. By working with the Global Fund, other market-shaping partners and investors including the FCDO, Unitaid should help map out key future roles and responsibilities in market-shaping.

Recommendation 3.2 (major): Unitaid should continue to work closely with the Communities, NGO and African countries’ delegations, alongside the rest of the Executive Board, to refine and agree a set of clear, realistic and costed changes to its Operating Model, to be piloted over the second half of this Strategy, which will help deliver inclusive, demand-driven partnerships with countries, communities and civil society. The current shifts in the global health ecosystem and the growing importance of domestic financing present important opportunities

Output Title	4. Unitaid governance, management and operational work is economical, efficient, and effective and embraces equity consistent with its Operating Model
Output number:		4	Output Score:		A+
Impact weighting (%):		25%	Weighting revised since last AR?		No
Indicator(s)	Milestone(s) for review			Progress
Output 4.1 Effective prioritisation enables development and implementation of the most impactful activities under the 2023-2027 strategy.	Demonstrable progress to ensure the effective prioritisation and implementation of the 2023-2027 Strategy through: / • Designing and implementing an organizational planning model, with clear Objectives and Key Results that are linked to Unitaid Strategic Objectives / • Strengthening of resource mobilisation activities and corporate communications / • Implementing a package of change initiatives related to grant making and grant management ways of working in order to increase efficiency and reduce workload / • Mainstreaming of strategic initiatives, including ensuring their inter-connectivity / • Secretariat to conduct a rigorous, evidence-informed and consultative Mid-Term Review process to support the development of recommendations related to the future implementation of the 2023-2027 strategy			Moderately exceeded expectation (A+) / Unitaid have been notably clear and structured in responding to 2025’s changes to the global health financing landscape with a well-communicated portfolio review and prioritisation process, including signalling encouraging principles on ways of working going forward (sustainability, integration, efficiency). This gave a clear outline on the priority, flagship areas of the portfolio to be protected and other areas to be paused, cancelled and rescoped. Overall, the Mid-Term Review met objectives and provides a set of recommendations, although these will need to be carefully prioritised and scheduled in line with Secretariat capacity. Resource mobilisation and communications continued to be strengthened, and Strategic Initiatives mainstreamed, although clarity on the Strategic Initiatives’ future will need to be given at the December 2026 Executive Board. Change initiatives to improve grant making and grant management are being implemented but will need to go further to help Unitaid become more agile.
Output 4.2 Unitaid Secretariat operations are efficient [KPI A Secretariat efficiency].	At least 95% met for Budget implementation rate per annum.			Moderately exceeded expectation (A+) / In 2024 the budget implementation rate was 97%, exceeding the 95% target and showing effective forecasting and budget management. Staff cost allocations were in line with expectations for a UN grant-making entity like Unitaid, with most staff-cost focused on grant portfolio and delivery (53%) and being leaner than comparative organisations on Corporate Functions staff-cost (12%). Investment Commitment and Disbursement ratios saw a drop compared to 2023 (from 13.3 to 5.2 and 13.1 to 11 respectively) – linked to output 4.3 with delays in grant-making.
Output 4.3 Unitaid manages the grant portfolio effectively and efficiently. [KPI D Speed of grant development]	KPI D – 6 months on average for grant development			Moderately did not meet expectation (B) While this KPI was not formally applicable for 2024 given that no eligible grants were signed (and so there are no timelines to report on), this itself reflects delays in Unitaid’s grant agreement development. 12 proposals entered the Grant Agreement Development process in 2024, 3 eligible grants were due to be reviewed and approved by the Executive Board, but none came to conclusion.
Output 4.4 Unitaid manages the grant portfolio effectively and efficiently / [KPI E Grant implementers' satisfaction]	KPI E – at least 75% overall positive feedback from grant implementers (i.e. combination of 'Positive' and 'Very Positive' responses from the scale of Very Poor, Poor, Neutral, Positive, Very Positive).			Substantially exceeded expectation (A++) / In 2025, KPI E reached a 93% positive score (“Positive” and “Very positive”) in the annual Implementer Survey, exceeding the 75% target.
Output 4.5 Unitaid secures sufficient and stable resources / [KPI C Resource Mobilisation]	KPI C.1: Demonstrated progress towards achieving targets for end of strategic period (US $1.5 billion committed resources) / KPI C.2: 70% (annual target) of funds secured against multi-year agreements (in value, annually) / KPI C.3: Demonstrated progress in gaining 3 new donors over the strategic period (cumulative)			Met Expectation (A) / KPI C.1 – US $527 million cumulatively committed by 31 May 2025. KPI C.2 –72% of funds secured via multi-year agreements in 2024 (target met). KPI C.3 – Four new donors to date (Canada, European Commission, Portugal, WHO Foundation), exceeding the target of 3.
Output 4.6 Unitaid manages risk, including PSEAH risk, effectively	Continued Secretariat efforts to sustain and raise awareness of and compliance with Unitaid's refreshed safeguarding requirements, both internally at Unitaid and for all grantees and sub grantees. Specific measures include reinforcement of incident reporting, its accurate and timely management, as well as clearer guidance and practice from WHO OIOS on how FCDO are kept up to date regularly on safeguarding cases. Unitaid and its partners to ensure that all allegations of SEAH are timely reported and investigated in accordance with victims/survivor-centred principles, in line with improved WHO Safeguarding policies.			Moderately exceeded expectation (A+) / Unitaid have strengthened their safeguarding approach, including internal awareness-raising by ensuring compliance with mandatory training and interactive theatre workshops on discrimination and unconscious bias. Unitaid have also enhanced the visibility of their safeguarding standards and reporting mechanism on their new website. BDO’s deep-dive review found Unitaid has significantly developed its PSEAH structure, implementer requirements, processes and documents, while identifying room for further improvements in strengthening formal case management of partner incident reports and stronger in-practice due diligence during grant agreement. Unitaid’s update of their safeguarding guidelines for implementing partners in 2025 and incorporating these into grant agreement and due diligence processes should help address this recommendation.
Output 4.7 Unitaid staff engagement and well-being / [KPI G gender equality]	KPI G – 45%-55% / of women in management positions (including senior leadership and middle management levels).			Met Expectation (A) / 45% of management positions were held by women by the end of 2024 (10 of 22), meeting the 45–55% parity target and improving from 40% (8 of 20) in 2023.
Output 4.8 Unitaid staff engagement and well-being / [KPI H1 staff satisfaction]	KPI H1 – at least 75% Unitaid Secretariat staff satisfaction reported in the annual staff survey.			Moderately exceeded expectation (A+) / Unitaid exceeded their target with 82% staff satisfaction reported in the 2024 annual staff survey. Although Unitaid need to carefully review and track a 9% drop in staff wellbeing (work-life balance) to 63%, alongside only 64% positive scores for psychological safety at work (safe to challenge, being comfortable discussing mistakes etc.).

Output 4:1: Effective prioritisation enables development and implementation of the most impactful activities under the 2023-2027 strategy

Through 2025 Unitaid continued to make progress across the 5 priority areas of this output. Most notably Unitaid were proactive, clear and structured in their response to the 2025 ODA cuts to the global health financing system and closure of USAID. Unitaid kept the Executive Board clearly appraised of their response to this radically altered funding environment through a series of meetings and written updates from March through to summer 2025 (initial ad-hoc sessions, then incorporations into scheduled Board sessions). It was reassuring to see Unitaid adopt a clear analysis and review framework (copied below) for this reprioritisation. This produced decisions on areas of the portfolio to be paused (for example monoclonal antibodies, post-discharge malaria chemoprophylaxis, some long-acting technologies), investments to be rescoped and right-sized for this changed context (for example core enabler cross-cutting investments related to regulatory strengthening and intellectual property), and investments to be prioritised as flagship high-impact work (e.g. lenacapavir, cervical cancer and antimalarial resistance grants). Beyond reviewing what work Unitaid would prioritise, it was positive to see Unitaid adopt a set of clear principles of how it would adapt going forward: focusing on co-creation with country and civil society partners (see outputs 3.2 and 3.3), efficiency and integration (see output 1.5), and sustainability of scale-up and alignment with domestic financing. These principles will be essential for achieving more with less funding.

Organisational planning matured with 2025 marking the second full year of the Secretariat’s planning approach using the OKR (Objectives and Key Results) methodology: setting critical, time-bound targets while remaining adaptable over the working year. The benefits of this more structured approach to planning and prioritisation appear to be paying off with the Secretariat showing an effective prioritisation of its portfolio (as described above). Teams collaboratively developed and reviewed annual plans, with regular Senior Management Team meetings to track progress, culminating in mid-year assessments that reinforced alignment with the 2023-2027 Strategy and the 2025 prioritised investment plan.

Resource Mobilisation efforts were strengthened through expanded staffing and strategic communications. Further detail is captured in output 4.4.

Overall, the strategic initiatives (partnerships, access, pandemic preparedness, climate and health, and regional manufacturing) saw solid progress, particularly for climate and health (output 2.4), regional manufacturing (output 2.2) and partnerships (outputs 3.1, 3.2 and 3.3). The focus for the access strategic initiative has been mainstreaming access across the Secretariat and its work. As reported for output 3.4, the long-term vision on the pandemic preparedness strategic initiative appears more constrained. For now, this appears to be an effective prioritisation of where Unitaid can have most impact, but a clear review is required for the end 2026 decision point on the future of the strategic initiatives. The initial phase 1 of staff recruitment to ensure adequate capacity for these initiatives was completed over 2024 and 2025 (with teams having more dedicated expertise e.g. on climate and health, pandemic preparedness, community and civil society). During December 2024’s Executive Board, the sensible decision was taken to extend this phase 1 (i.e. recruitment of the first 14 staff) beyond its original timeline until the end of 2026, while pausing on phase 2 (the recruitment of a further 12 staff). This has kept the staffing costs for these strategic initiatives within budget and provides additional time for enabling implementation and reviewing impact.

Finally, in 2025 Unitaid worked with consultants Agulhas Applied Knowledge to run a comprehensive and consultative Mid-Term Review of the 2023-2027 Strategy. Combined with the above-described prioritisation of Unitaid’s portfolio, this has provided a clear direction on the flagship, high-priority areas of the portfolio, while identifying other areas (e.g. pandemic preparedness beyond medical oxygen, further upstream R&D) where further scrutiny and consideration is required to ensure the right level of ambition and investment going forward. The Review coherently identified the successes (e.g. flagship investments, improved partnerships, expansion of portfolio into regional manufacturing, maternal health and climate and health, stronger resource mobilisation footprint) and challenges of the current Strategy (the need to go further on communities and country partnerships, grant agreement delays, clearer scalability engagement) and effectively linked these to the rapidly changing global health context in 2025. This has produced a wide-ranging set of recommendations for Unitaid Executive Board in December 2025. The key challenge for Unitaid will be prioritising these recommendations in terms of urgency and feasibility to implement changes in a sequenced, coherent fashion. To this end, the UK assesses that the Mid-Term Review would have been strengthened with a stronger focus on highlighting the most urgent and critical recommendations.

Output 4.2 Unitaid Secretariat operations are efficient (KPI A Secretariat efficiency)

In 2024 Unitaid’s budget implementation rate was 97%, exceeding the 95% target (and improving on 2023’s 92%) and demonstrating effective forecasting, planning and budget management. In terms of where staff costs and time is allocated, analysis shows that reassuringly most staff time is focused on Unitaid’s grant portfolio (i.e. delivering projects and programs): with 53% of staff costs identified as ‘Investment’, compared to 18% for ‘Management’, 16% for ‘Business development’ and 12% for ‘Corporate functions’. This spread is in line with expectations for a UN grant-making entity like Unitaid: doing better than expected for corporate functions (12% against 25-30% range), being in line with expectations for Management (15-20%) and investments or grants (53% against 40-50% range), while being slightly worse for business development (16% against 5-10% range). The 2024 Investment Commitment and Disbursement Ratios saw a drop compared to 2023, reducing from 13.3 to 5.2 for Investment Commitment and from 13.1 to 11 for Investment Disbursement. These ratios convey for every $1 of ‘Investment’ staff cost the amount of financial commitments or disbursements made in the calendar year. This reflects the fact that fewer new investment decisions were taken in 2024 and no grants signed in 2024 (see output 4.3).

Output 4.3 Unitaid manages the grant portfolio effectively and efficiently (KPI D – Speed of grant development)

While this KPI was not formally applicable in 2024 as no grants were signed, this itself reflects delays in Unitaid’s grant agreement development (GAD) process. 12 proposals entered the GAD process in 2024, including key investments in anti-malarial drug resistance, vector control, drug-resistant TB, monoclonal antibodies, and elimination of vertical transmission. The Executive Board was scheduled to review for approval the final proposals for 3 of these grants – with anti-malarial drug resistance and vector control grants facing repeated delays, and the timeline on drug-resistant tuberculosis slipping out of 2024. While these types of delays would have been more understandable in the context of the major changes in the global health financing system in 2025, the situation in 2024 is judged to have been more stable and without such clear, reasonable mitigating circumstances for delays.

In response, Unitaid conducted a structured review in early 2025 with all project teams involved in 2024 grant development to better understand the root causes of delays and identify opportunities for improvement. This identified external drivers of delay of partner validation requirements for proposed research approaches, proposal redesigns from unexpected clinical trial outcomes, and contracting and legal specificities of UN-to-UN engagement. Internal areas identified for improvement included earlier alignment with partners on scope, portfolio fit and budget parameters, and stronger continuity and coordination across project teams. Unitaid are now focusing on targeted improvements to address these issues, including clearer Unitaid expectations in an initial investment area (budget ceilings, theory of change) and clearer guidance in calls for proposals (including webinars targeting south-based partners). The complex, sometimes cumbersome and lengthy nature of Unitaid’s grant agreement development process has been identified as a key issue in the 2025 Mid-Term Review. There is therefore room for improvement, and this should be a priority for Unitaid to address – both for the remainder of this Strategy until end 2027 and then more fundamentally for the next strategic period beyond. In an increasingly fragmented global health ecosystem with a need to align more closely with country and civil society partners, it will be crucial for Unitaid to be more agile and move swiftly.

Output 4.4 Unitaid manages the grant portfolio effectively and efficiently [KPI E Grant implementers' satisfaction]

In 2025 Unitaid achieved a 93% positive score in the annual Implementer Survey, healthily surpassing the 75% target and reflecting strong overall partner satisfaction. The survey, conducted by IPSOS, highlighted key strengths as proactive risk management, effective communication, responsiveness and flexibility in grant management. Implementers also appreciated Unitaid’s emphasis on portfolio synergies, collaboration with country stakeholders (including communities), support for scale-up, integration with complementary programmes, Unitaid’s unique combination of Pathfinder-Investor-Influencer roles, technical expertise and helping build institutional capacity. The key areas identified for improvement all reinforce the findings under output 4.3 of challenges with Unitaid’s grant agreement development process and burdensome, complex proposal and reporting requirements. Partners identified the need for streamlining tools and templates (proposal review, GAD, reprogramming, reporting), improving timeliness of decisions and feedback, and enhancing expertise in Human Subject Research and Research Ethics Review Committee requirements. This last point on human subject research aligns with an emerging finding from the 2025 Mid-Term Review.

Output 4.5 Unitaid secures sufficient and stable resources [KPI C Resource Mobilisation]

Unitaid have continued to perform well on resource mobilisation through 2024 and 2025 in a challenging fundraising environment. With $527 million raised as of May 2025, Unitaid remain significantly off-track for their highly ambitious cumulative $1.5 billion target for the 2023-2027 strategy. But it is important to recognise that this fundraising target was made in the context of a 2022 COVID-19 related peak in ODA for global health. The $1.5bn target was a 50% increase compared to the total $1bn raised under Unitaid’s previous 2017-2021 Strategy, yet global ODA for health decreased by 40% in 2023 from its 2022 COVID-19 peak. This trend of declining global ODA for health has only strengthened since, with an estimated 6% decline in 2024 and an additional 14-29% reduction projected for 2025. ODA for health could drop to levels last seen in the mid-2000s under ‘higher cut scenarios’[1]. In this context, Unitaid are assessed to have done well by sustaining an increase in resources from $429 million in May 2024 to $527m by May 2025. In 2024, 72% of Unitaid funds received were secured via multi-year agreements, exceeding their 70% target, and surpassing 2023’s result of 63%, with key multi-year contributions from France, Spain, Norway, the Gates Foundation and the European Commission. This is a clear demonstration that Unitaid’s dual-track approach of protecting core funding while diversifying into greater specified funding is paying off, with Japan, South Korea, Brazil and the Gates Foundation all making major earmarked contributions in 2024. This is also an indication that Unitaid’s strategic initiatives and portfolio expansion into areas like regional manufacturing and medical oxygen (pandemic preparedness) are both delivering programmatic results (as shown in other outputs) and helping secure significant resources. Subject to WHO’s accreditation, the climate and health strategic initiative also holds significant promise for a major global climate finance specified contribution from 2027 onwards.
[1] https://www.oecd.org/en/publications/cuts-in-official-development-assistance_8c530629-en/full-report.html#section-d1e896

Unitaid have strengthened their approach to communications, brand and visibility. Unitaid launched a new and improved website in 2025 with a greater focus on human stories and photo and video content. 2025 reporting shows all communication channels had increasing viewers, mentions and followers. By September Unitaid had 366,000 active website users (a 227% increase compared to 2024), and they’ve benefited from a 60% increase in social media followers since 2023. Unitaid’s online media coverage in high-impact media has increased from under 50 stories mentioning Unitaid per quarter in 2022 and early 2023 through to numbers regularly exceeding 100 stories mentioning Unitaid per quarter since 2024. This reached an impressive peak in 2025 quarter 3 of over 400 stories mentioning Unitaid, with a potential audience reach of over 1 billion – likely thanks to the widespread media coverage of Unitaid’s landmark lenacapavir pricing deal in September 2025.

Unitaid also introduced in July 2025 a new published report ‘Reimagining global health: advancing people-centred solutions’ which effectively acts as a ‘Unitaid in numbers’ resource, summarising the results of their work, as well as providing a forward-look at the pipeline of game-changing innovations and nicely communicating the human stories of Unitaid’s successes. This serves as a useful advocacy tool and Unitaid would do well to regularly update this. Unitaid should replicate the good practice of other partners through an annual report for public consumption. This type of annual report could usefully combine this ‘Reimagining global health’ report with annual KPI figures. It could also serve as a vehicle for better differentiating Unitaid’s uniquely cross-cutting market-shaping work and access offer from other actors (see output 3.1 and recommendation 3.1).

Unitaid have responded effectively to Executive Board feedback to further diversify their funding base by reviewing options for more innovative financing. Working with consultants UN Advisory Alliance, Unitaid undertook a comprehensive review of 27 mechanisms and have coalesced around a triple-track approach of greater use of philanthropic fundraising platforms, expanding catalytic or blended finance approaches (building on the successes of partnering with MedAccess on medical oxygen), and exploring results-based financing (for example for the maternal health portfolio). Unitaid have adjusted this workstream to initial Board feedback and pending a December 2025 Executive Board decision would move to implementing this in a pilot-based and risk-adjusted manner from 2026 on. Success will likely require dedicated external expertise, a sustained push and effective risk-management to protect against adverse impacts on Unitaid’s core mission and ways of working.

Output 4.6 Unitaid manages risk, including PSEAH risk, effectively

To note that as per output indicator 4.6, despite the broader risk title, this output specifically focuses on Unitaid’s management of safeguarding risks (Unitaid’s broader risk management approach is covered in Section E). Overall Unitaid has continued to strengthen its safeguarding approach with further efforts to raise and sustain internal and external compliance with WHO policies on preventing sexual exploitation, abuse, harassment (PSEAH) and abusive conduct. In 2025 Unitaid worked with a Geneva-based theatre company to design interactive theatre workshops for staff on discrimination and unconscious bias in the workplace, following on the successes of working with the same organisation on gender discrimination in 2024. Combined with the introduction of anonymised 360 feedback (including external partners), an all-staff in-person workshop in October 2025 on a respectful workplace and culture, and informal socials, together this seeks to create a safe work environment conducive to reporting concerns. These workshops were partly in response to general staff feedback and requests for these sessions, alongside staff survey results showing that 15% of staff reported that they had witnessed or experienced harassment at Unitaid in the last 12 months, and 17% reported that they had witnessed or experienced discrimination at Unitaid in the last 12 months. While reports are not uncommon for organisations, this does not align with a zero-tolerance environment. Unitaid should prioritise understanding these scores and having a clear plan for ensuring a zero-tolerance approach is reflected in staff survey scores.

Importantly in 2025, Unitaid commissioned BDO (Unitaid’s external assurance provider) to undertake a comprehensive safeguarding and ethics review, showing a clear commitment to safeguarding standards with a focus on identifying areas for improvements. The review found “Unitaid has significantly developed its PSEAH structure, implementer requirements, processes and documents” since BDO’s last review in 2019 and had implemented all of its recommendations. This BDO deep-dive also found good completion of mandatory safeguarding training activities and evidence of the Executive Director highlighting the importance of this compliance to all staff. This reassuringly aligns with the 2024 staff survey finding that 90% of staff agreed or strongly agreed on ‘Familiarity with WHO reporting and how to report ethical matters” (and this may be linked to staff survey results on harassment and discrimination being higher than expected). Unitaid have also demonstrated their commitment to a strengthened approach to safeguarding with their Senior Legal Officer serving as Chair of WHO’s Global Advisory Committee on formal complaints of abusive conduct (GAC) since April 2023. The GAC reviews IOS investigation reports on allegations of abusive conduct and recommended action and has helped reinforce Unitaid’s expertise in WHO internal justice practices, while also strengthening working relationships with key WHO colleagues.

The Secretariat have undertaken significant efforts to strengthen external partners’ safeguarding compliance. In April 2025 Unitaid updated its “Guidelines on Prevention, Reporting and Management of Wrongdoing” and “Supplemental Guidance for Safeguarding” for implementing partners. These now include eight core safeguarding requirements for grantees, and these have been integrated into Unitaid’s Capacity Assessment Tool and onboarding workshops as part of grant agreement and development. Unitaid used the new website to enhance the visibility of their safeguarding standards, including a clearer and more actively promoted reporting mechanism and a dedicated safeguarding page (every project page on the website contains a link to this page). Coordination with WHO and the Global Fund PSEAH teams has also deepened, with technical training for Unitaid staff from the WHO focal point on accessing a shared database of PSEAH due diligence reports on implementers and increased engagement with the Global Fund’s safeguarding specialist.

The priority going forward for Unitaid should be translating this progress and strengthened approach into effective, widespread practice. BDO’s review found limited evidence of partners’ adherence to these standards being systematically sought or verified by Unitaid staff. However, it is important to recognise that BDO’s review only sampled projects from previous years, before Unitaid had updated their due diligence and capacity assessment tool in April 2025 to include the 8 core safeguarding requirements (as described above). Before the 2024 and 2025 changes, Unitaid’s due diligence of partners did not systematically consider the safeguarding capacity of all grantees, but it is too early to make clear conclusions on the implementation of these strengthened standards since April 2025. Unitaid should nevertheless prioritise BDO’s recommendation of requiring clear evidence of partners’ compliance with these 8 standards and ensuring routine project risk monitoring and evidence provision to support this in an ongoing fashion (e.g. training records, reporting mechanisms, policies). BDO also found that Unitaid lacked a formal case management tool for implementers’ reports of wrongdoing. There was evidence of good practice following a 2024 partner report of a safeguarding incident – including frequent dialogue with the implementer, tracking a set of management actions – but the lack of a formalised, consistent approach for handling such reports risks inconsistent management in the future. This aligns with concerns raised by FCDO, as per this year’s output indicator milestone, on the lack of a clear process for reporting implementing partners’ safeguarding incidents to FCDO or the Executive Board. We recommend that Unitaid address BDO’s recommendations of a formal case management tool for reports of implementer safeguarding standards, including regular reporting to the Unitaid Executive Board on a 6-monthly basis of any incidents (as Unitaid already do for financial wrongdoing).

Output 4.7 Unitaid staff engagement and well-being [KPI G gender equality]

Management positions are defined as UN P5-level or above (equivalent to UK Senior Civil Service level), with the target being the range around parity (45-55%). By the end of 2024, women held 45% of management positions (10 out of 22), with Unitaid meeting the strategic target and improving from 40% in 2023. This upward trend reflects the organisation’s commitment to inclusive leadership and equitable representation at senior levels.

Output 4.8 Unitaid staff engagement and well-being [KPI H1 staff satisfaction]

For 2024 Unitaid exceeded their 75% target for staff satisfaction based on the results of the latest staff survey (conducted by IPSOS at the start of 2025), with the average level of staff satisfaction reaching 82% - a solid improvement on 2023’s score of 75%. This level of staff satisfaction is measured from average scores against a composite of the below 5 questions in the survey – satisfaction is considered as met for any ‘Agree’ or ‘Strongly agree’ responses (while all ‘Neither agree nor disagree’, ‘Disagree’ or ‘Strongly disagree’ scores are considered as dissatisfaction).
- I feel proud to tell my friends and family about my work at Unitaid.
- Overall I like working at Unitaid.
- I would like to stay and progress at Unitaid.
- I would recommend Unitaid to friends as a good place to work.
- We have successfully managed to integrate and onboard new staff in the organisation.
The averages for each question all exceeded the 75% target, with the lowest scores being 79% for wanting to stay at Unitaid and recommending Unitaid. The highest performing response was for ‘feeling proud to work at Unitaid (as it was in 2023) at 87%, joint with people overall liking working at Unitaid. Notable gains included a 15% rise in recommending Unitaid as a workplace and a 19% increase in integrating and onboarding new staff. This is particularly encouraging given the expansion of the Secretariat since 2022 and following 2023’s more concerning score of 61%.

However, other areas of Unitaid’s 2024 staff survey show a drop in reported wellbeing. Unitaid missed their 75% target for staff’s self-assessment of being able to balance work and personal responsibilities while maintaining a healthy lifestyle, with only 62% positive responses in 2024 – a 9% reduction compared to 2023. Equally concerning are 64% positive scores for staff psychological safety and wellbeing – this is a composite average of questions on welcoming differences of opinion, valuing constructive challenge, sharing opinions without fear of negative consequences, being comfortable discussing mistakes, and work-life balance. Unitaid should invest time into understanding the barriers to a safe to challenge, open culture in the organisation, and how to address challenges for staff’s work-life balance. It will be important to factor these considerations into the end of 2026 recommendation to the Executive Board on the increased staff numbers following the Strategic Initiatives and Functional Review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following Unitaid-FCDO discussions in summer 2025, the wording of the milestone targets for both Output Indicator 4.1 and Output Indicator 4.6 was updated to best assess and reflect the key areas of focus in 2024 and 2025 (adding a milestone for the 2025 Mid-Term Review for 4.1, and increased visibility of implementing partner reporting of safeguarding incidents for 4.6). In line with changes to Unitaid’s own KPI reporting framework (given FCDO seeks to align with Unitaid’s KPI framework as far as possible), Output Indicator 4.2 no longer reports on the proportion (%) of Secretariat costs in relation to the value of Unitaid’s overall portfolio.

It is recommended for future reporting that FCDO formally includes Unitaid’s KPI H2 on staff wellbeing (scores on work-life balance) in Output Indicator 4.8 and explore the inclusion of the staff survey results on witnessing or experiencing discrimination or harassment – either as part of output indicator 4.8 on staff wellbeing or for output indicator 4.6 on PSEAH risk. Taken together, these changes are likely to provide a more comprehensive measure of staff wellbeing at Unitaid.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Unitaid are assessed as having effectively addressed last year’s recommendations.
Previous year’s recommendation(s)	Actions taken
Recommendation 4:1: Unitaid should use the 2025 Mid-Term Review to be on the front-foot and proactive for making strategic decisions on which parts of the portfolio maximise Unitaid’s impact and offer best value for money, in the context of constrained resources. This strategic prioritisation should consider the merits of continuing with the current broader portfolio approach versus backing certain thematic and programmatic areas much more substantially than others. The Executive Board should be engaged through 2025 on this, to inform both the rest of the current Strategic period until end 2027 and for the next Strategy beyond 2027. This exercise should consider the overall portfolio, rather than just reviewing the Functional Review’s 5 strategic initiatives.	The 2025 Mid-term Review with a dedicated focus on strategic prioritisation (Area 4) has engaged the EB throughout 2025 to ensure that decisions on portfolio optimisation are transparent and forward-looking. This process considers the merits of both a broader portfolio and more substantial backing of certain thematic or programmatic areas considering constrained resources. The exercise assessed the whole of Unitaid’s portfolio, and its main mission has been to inform both the remainder of the current strategy and the new strategy beyond 2027. The final outcomes and recommendations will be presented to the EB in December 2025, ensuring that Unitaid is well-positioned to maximise impact and value for money in the years ahead. Alongside this and as reported in output 4.1, Unitaid undertook a structured and clearly communicated prioritisation exercise of their portfolio in Spring 2025 in response to the rapidly changing global health financing environment.
Recommendation 4:2: Unitaid should develop a clearer vision on the role of other sources of financing and innovative financing, for example the role of Development Finance Institutions, in supporting their resource mobilisation efforts, including for supporting their strategic initiatives on regional manufacturing, pandemic preparedness (particularly medical oxygen) and climate and health.	As reported in output 4.5, Unitaid have undertaken a structured and comprehensive review of next-generation innovative financing solutions which could be appropriate and effective for Unitaid’s model. Unitaid partnered with the United Nations Advisory Alliance to evaluate 27 potential mechanisms – ranging from solidarity levies and carbon taxes to impact bonds and philanthropic platforms – against programmatic fit, political feasibility, and donor priorities. Consultations with Board members and partners, including the FCDO, helped refine a shortlist of promising options to advance Unitaid’s strategic objectives. A decision on the best options to take forward is expected at the December 2025 Executive Board. As of the October Executive Board Committee meetings, Unitaid were coalescing around a promising pilot-based, triple track approach of philanthropic funding, catalytic or blended financing and results-based funding to be introduced in 2026.

Recommendations for the year ahead

Recommendation 4.1 (major): Unitaid should prioritise addressing the Mid-Term Review findings on the administrative complexity, burden and delays in their grant agreement development (GAD) process. This should identify nearer-term fixes for the rest of this strategy (until end 2027) and more structural changes that could be introduced in the next strategic period. Increased agility will be valuable in an increasingly fragmented global health ecosystem with intensified funding competition and the need to align more closely with country and civil society partners.

Recommendation 4.2: Building on the successful donor country briefs and the June 2025 ‘Reimagining Global Health’ report, Unitaid should move towards a formal public annual report to bring a range of already available information into one clear document. This could usefully combine the ‘Unitaid in numbers’ approach of the Reimagining Global Health report with tracking of KPI progress. It could also serve to more clearly distinguish the unique nature of Unitaid’s market-shaping contributions (linked to recommendation 3.1), raise Unitaid’s profile, and be used as an advocacy tool by Unitaid champions (including the Executive Board).

Recommendation 4.3: Unitaid should prioritise addressing BDO’s recommendations in their 2025 Ethics and Safeguarding report. This includes ensuring systematic due diligence of partners’ safeguarding capacities during grant development and requiring ongoing reporting, building on Unitaid’s updated guidelines and standards for implementing partners since April 2025, as well as a case management tool for tracking and reporting partners’ safeguarding incidents to the Executive Board (or the Financial Accountability Committee) on a 6-monthly basis, as is done for financial wrongdoing. Unitaid should also prioritise understanding 2024 staff survey scores on experiencing and witnessing harassment or discrimination at work to ensure a zero-tolerance approach, alongside reviewing staff survey scores for staff psychological safety and wellbeing to ensure a safe to challenge, open culture that supports wellbeing.

UK funding to Unitaid continues to represent excellent value for money (VfM). Unitaid plays a critical role in bridging the gap between innovation and large-scale deployment of life-saving health technologies, thereby increasing the cost-effectiveness of domestic governments’ and other global health partners’ work and the availability of critical health tools. For the UK, our investment in Unitaid amplifies the impact of other FCDO bilateral, multilateral and research funding streams, particularly in HIV, TB and malaria, as well as in newer strategic areas such as local manufacturing and climate-resilient health products. For example, Unitaid enhances the reach and effectiveness of the UK’s Global Fund investment by accelerating the Global Fund’s roll-out of new and improved health commodities and technologies, often at significantly reduced prices in combination with the Global Fund’s procurement and buying power. As reported in output 3.1, joint Unitaid-Global Fund analysis for the Global Fund’s 2025 Investment Case for their Grant Cycle 8 (2026-2028) confirmed that without the availability of innovative health products (predominantly supported by Unitaid), it would take the Global Fund an additional 3 years to achieve the same reduced level of HIV, TB and malaria deaths.

As reported in our 2024 Annual Review, a comprehensive return on investment analysis by Cambridge Economic Policy Associates (CEPA) in 2024 estimated that Unitaid delivers a £46 return in health and socio-economic benefits for every £1 invested, and a 5:1 return using a cost-of-illness approach. These figures reflect Unitaid’s efficiency in leveraging resources for high-impact outcomes. Recent clear examples of Unitaid’s market-shaping work showing high value for money include securing 40–45% price reductions for cervical cancer diagnosis and treatment devices (thermal ablation devices), and 22–43% price reductions for medical oxygen in East Africa. At the midpoint of its 2023–2027 Strategy, Unitaid’s support for 16 key health products has averted an additional 86 million infections or cases and 930,000 deaths, with the most substantial contributions from optimal HIV treatments and seasonal malaria chemoprevention. Unitaid-supported products are projected to achieve global savings of $10 billion by 2030, primarily driven by price reductions in dolutegravir-based HIV regimens. With approximately 320 million people reached annually, including 53 million children, Unitaid’s performance reflects a robust alignment between resources deployed and health outcomes achieved.

E: RISK

As of Q4 2025, Unitaid is actively managing 25 organisational risks, a figure that has remained stable for two years. However, there has been a marked increase in overall risk exposure, driven primarily by:
- Geopolitical shocks: US ODA cuts and withdrawal from WHO disrupted funding streams for major global health actors creating ripple effects across health services, NGOs, and partnerships.
- Funding volatility: Reduced donor contributions and increased reliance on domestic financing in LMICs have heightened financial uncertainty.
- Fragmented global health architecture: Coordination challenges among multilateral actors and regional blocs have intensified.

The top five risks as assessed by Unitaid are now:
- Shortfalls in resource mobilisation.
- Unsuccessful grant transitions and scale-ups.
- Failure to deliver impact – especially in constrained funding environments.
- Loss of competitive advantage.
- Failure to adapt to external shifts, including geopolitical and climate-related changes.
Unitaid is actively mitigating these risks through strategic prioritisation of its portfolio and focusing on flagship investments (see output 4), intensified country engagement, reviewing overall partnerships approaches (see output 3), and exploration of innovative financing mechanisms (see output 4). As reported in output 4, Unitaid’s Mid-Term Review of their 2023-2027 Strategy will be important for longer-term risk mitigation and effectively guiding decision-making and prioritisation, ensuring resilience amid a rapidly evolving global health landscape.

Unitaid have also escalated several medium and medium-high risks:
- Harm to staff wellbeing and loss of key staff, due to operational pressures and leadership transitions.
- Ineffective partnerships with grantees, particularly in safeguarding and fraud reporting.
- Unintended market and patient outcomes, including risks of manufacturer exit from critical product markets.
- Misalignment with Board expectations, especially around strategic priorities and country engagement.
Unitaid is addressing these through flexible grant reprogramming, enhanced safeguarding protocols and improved internal communication. Notably, safeguarding against sexual exploitation and abuse has been elevated as a priority with updated guidelines and legal terms embedded in grant agreements. However as reported in output 4 there are recommendations to implement for case management tools and implementer reporting.

The FCDO’s overall risk rating for the programme remains at ‘Moderate’, with FCDO willing to accept activities that carry a moderate (cautious) degree of residual risk. Current major risks from an FCDO perspective are funding volatility of donor contributions impacting programme delivery and sustainability, and Unitaid failing to generate impactful transition and scale-up of its portfolio following grant implementation given wider changes in the global health system. As outlined in outputs 1 and 4, we assess that Unitaid are implementing effective, necessary mitigations in response to these risks and contextual changes.

In 2025, the FCDO conducted an updated Due Diligence Assessment (DDA) of Unitaid, following the previous FCDO DDA assessment in 2021, to provide assurance that Unitaid have the right capacity, capability and financial stability to deliver UK ODA funding effectively and efficiently, with outcomes and value for money achieved. Overall, Unitaid performed strongly across all 5 pillars of: governance and internal control; ability to deliver; financial management and stability; downstream delivery; and safeguarding. The DDA identified key risks related to:
- The impact of significant ODA funding reductions, potentially undermining scale-up pathways.
- Leadership transitions within the Executive Board and Senior Leadership Team positions over 2026 and 2027.
- Continued reliance on a small number of core multiyear donors and risks of not diversifying financing sources.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme Management

In 2024, Unitaid’s active portfolio contracted significantly from 63 investments worth US $1.3 billion to 43 investments worth US $1.0 billion. This reduction was driven by the closure of remaining COVID-19 related projects, closure of several large legacy investments, and delays in grant agreement development (as reported in output 4).

As reported in 2024’s Annual Review, Unitaid have shifted from grant-level to portfolio performance management, enabling stronger strategic oversight, clearer impact communication, and better identification of synergies and learning across investments. The introduction of Programmatic Priority Reports (PPRs), replacing individual grant summaries, supports this shift. These reports provide structured updates across six priority areas: HIV and co-infections, TB, malaria, women and children’s health, global health emergencies, and cross-cutting themes.

Through 2024 and 2025, Unitaid strengthened its Proposal Review Committee (PRC) to improve its grant selection and agreement process. The PRC is an independent group of experts that reviews grant proposals submitted to Unitaid for funding and provides recommendations to the Executive Board. The PRC is appointed by the Executive Board following a competitive application process. The PRC is composed of impartial members with expertise in specific areas relevant to Unitaid’s portfolio. The PRC therefore aims to ensure comprehensive, informed and independent evaluations of proposals submitted for funding.

Revised Terms of Reference for the PRC, endorsed by the Executive Board in December 2024, provide a better foundation for the PRC’s role as an independent, impartial advisory body. Members are now selected through a more transparent and structured recruitment process; the annual time commitment is more clearly defined (c. 20 working days) with clearer expectations for in-person and virtual meetings; and an updated performance management process enables more comprehensive peer feedback. To better align with Unitaid’s expanded programme portfolio under its 2023-2027 strategy and to accommodate growing proposal volumes, the PRC expanded from 15 to 18 members during its 2024/25 replenishment, incorporating new areas of expertise such as climate and health, gender and human rights, and local manufacturing. The replenishment process was also used as a timely opportunity to ensure that the overall PRC membership balances global North and South representation and gender balance, and that the recruitment process is more open and inclusive to applicants with a broader range of experience and expertise.

Formal processes for selecting the PRC Chair and Vice-Chair have also been introduced, alongside performance assessments for the PRC Chair and Vice-Chair, informed by benchmarking against comparable global health technical committees (e.g. Global Fund’s Technical Review Panel). Selection will be based on reviewing CVs and a letter of motivation against clear selection criteria (technical skills, risk of conflict of interest, strategic vision for PRC and its impartiality, proven leadership skills and experience), as well as now including PRC member peer assessment of the Chair and Vice-Chair.

Financial Management
Unitaid maintains a robust financial management framework grounded in international standards and supported by annual external audits. Unitaid’s 2024 financial statements received an unqualified audit opinion from the Controller and Audit General of India, confirming that Unitaid’s financial position and performance were fairly presented in accordance with the International Public Sector Accounting Standards. The audit assessed both financial and compliance dimensions, including the effectiveness of grant management and adherence to regulatory obligations. Internal controls were found to be generally effective, although the audit highlighted areas for improvement: i) inconsistencies in consultant contract terms and ii) delays in incident reporting by grantees. To address these findings, Unitaid has committed to strengthening its internal control mechanisms by aligning consultant deliverables and payment terms with WHO guidelines and introducing penalties or disallowances for delayed incident reporting.

The Executive Board’s Financial and Accountability Committee (FAC), chaired by the UK Board member, plays a central role in providing oversight and assurance to Executive Board members of Unitaid’s effective and comprehensive financial management. Reports on cases of implementer financial wrongdoing and loss are presented to the Executive Board and the FAC as part of overall risk reporting, with 2025 continuing the trend of a reassuring cycle of new cases under investigation and cases being closed. As of October 2025, 5 new cases were under investigation related to loss or theft in implementers’ projects. Each case update includes clear measures to establish responsibility, agree measures for minimising losses and agree relevant learning (e.g. changing procurement approaches, security action plans to reduce theft risks etc.).

For financial management of UK funds, Unitaid and FCDO continued to collaborate to ensure all use of funds was in line with the Donor Administrative Arrangement. In December 2025 a promissory note of £14m was made as the last contribution under the UK’s 20-year agreement up to March 2026. In 2025 Unitaid encashed three previous promissory note deposits for a total value of £61m (PN5 of £33m, PN6 of £14m and PN7 of £14m) – this was in line with Unitaid’s liquidity policy and FCDO rules on payments not being in advance of need.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
For this annual review, Unitaid and FCDO continued to align as far as possible with Unitaid’s own performance framework and KPIs to reduce reporting requirements and to promote Unitaid-FCDO joint monitoring and evaluation. As outlined in each output of this review, minor changes have been made to a subset of output indicators (output indicators 2.1, 2.2, 2.4, 3.1, 4.1, and 4.6) to include additional targets required for 2024 that were more directly relevant to that year’s activities.

2024 marks the first year of Unitaid reporting on the impact-level KPIs within the current strategic period (2023–2027). Unlike the previous 2017-2021 strategy’s approach of annual impact reporting, impact is now assessed twice: at the midpoint (end 2024) and at the end of the strategic period in 2027. Of course there also remains the strategic and operational KPIs tracking progress on an annual basis (and which the FCDO logframe mainly assesses through this Annual Review process).

Unitaid’s framework includes four impact-level KPIs:
- KPI 1: Public Health Impact measures the additional infections or cases and deaths averted through Unitaid-supported products. Current estimates indicate that the 16 products in scope have helped avert approximately an additional 86 million infections or cases and an additional 930,000 deaths (relative to the counterfactual). The largest contributors to infections averted are dual-active ingredient bed nets and Seasonal Malaria Chemoprevention, while deaths averted are primarily due to the scale-up of optimal HIV treatments (dolutegravir-based regimens) and Seasonal Malaria Chemoprevention for children.
- KPI 2: Economic Savings and Efficiencies is projected at US$10 billion by 2030, driven mainly by cost reductions in HIV programmes. This achievement stems from a significant price drop for dolutegravir-based HIV regimens—from US$75 in 2017 to US$37 per person per year—enabled by strategic market shaping, voluntary licences, and strong competition among generic manufacturers. These projected savings exceed original targets and have supported rapid scale-up of optimal HIV treatments. However, prolonged disruptions to HIV programmes from 2025’s major ODA cuts could jeopardise the ability to realise these savings.
- KPI 3: Return on Investment demonstrates the value of Unitaid’s interventions. For the 16 products analysed, ROI is estimated at 46:1 (range 28:1–61:1) using the intrinsic method commonly applied by global health agencies, and 5:1 (range 3:1–6:1) using a cost-of-illness approach. These figures underscore the efficiency and impact of Unitaid’s investments in health innovation.
- KPI 4: Accelerating the Global Health Response highlights the role of innovation in reducing mortality more quickly. According to Global Fund Investment Case modelling for 2027–2029, without innovative health technologies supported by Unitaid, it would take an additional three years to achieve the same reductions in HIV, TB, and malaria deaths. This acceleration is critical for meeting global health targets.
While these results are encouraging, they rely on forward-looking projections to 2030 and may vary if funding for healthcare in low- and middle-income countries declines. The Unitaid Secretariat will continue to monitor emerging trends and update impact estimates as needed. Additionally, there is a recognised need for more comprehensive analysis of economic efficiencies and cost-effectiveness to inform health system planning, particularly as countries face increasingly constrained budgets.

Learning
During this review period, Unitaid demonstrated a strong commitment to institutional learning by undertaking a series of targeted organisational development initiatives. As outlined in output 4.1, the 2025 Mid-Term Review (MTR) has been a pivotal learning exercise, enabling Unitaid to reflect critically on its strategic direction and operational effectiveness amid shifting global health dynamics. The Mid-Term Review’s findings and recommendations are still being finalised ahead of the December 2025 Executive Board. However, the overarching headlines are that Unitaid’s comparative advantage remains clear and Unitaid have made strong progress in implementing strategic initiatives (particularly for regional manufacturing and climate and health). Recommendations going forward include addressing delays in grant development timeline; potentially sharper prioritisation around flagship investments in a constrained funding environment; strengthened partnerships with communities and countries; and a combined internal change management approach to bring together different initiatives.
Alongside this, as reported in output 4.5, Unitaid have worked with the UN Advisory Alliance to review innovative financing mechanisms that could be incorporated into their operating model and resource mobilisation approach – with decisions due at the upcoming December 2025 Executive Board. Through this Unitaid seeks to strengthen its financial resilience, diversity funding sources and ensure sustainability in a rapidly evolving global health landscape.

Date of last narrative financial report	13 November 2025	Date of last audited annual statement	31 December 2024