## Poorest State Inclusive Growth (PSIG) Annual Review
Title: Poorest State Inclusive Growth (PSIG) Programme
Programme Value £ (full life): £65m		Review Date: 16 December 2020
Programme Code: 114293	AMP start date:	AMP end date:

Summary of Programme Performance
Year	2012/13	2013/14	2014/15	2015/16	2016/17	2017-18	2018-19	2019-20	2020-21
Programme Score	B	A	A	A	A	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate
DevTracker Link to Business Case:			https://devtracker.dfid.gov.uk/projects/GB-1-114293/documents
DevTracker Link to Log frame:			https://devtracker.dfid.gov.uk/projects/GB-1-114293/documents

Abbreviations	Full Form
BCFI	Business Correspondents Foundation of India
BCs	Banking Correspondents
DFID	UK Department for International Development
ESG	Environment Social and Governance
FCDO	UK Foreign, Commonwealth & Development Office
FCPD	DFID / FCDO Finance & Corporate Performance Division
FI	Financial Inclusion
FLWE	Financial Literacy and Women’s Empowerment
GoI	Government of India
GST	Goods and Services Tax
HMT	Her Majesty’s Treasury
IFV	Institutional Finance Vertical
MFIs	Micro Finance Institutions
MSMEs	Micro Small and Medium Enterprises
MUSP	Mahila Udyami Sashaktikaran programme
NAV	Net Asset Value
OSAFI	Odisha State Association of Financial Institutions
P&D	Promotion and Development (P&D) vertical, SIDBI
PSC	Project Steering Committee
PSIG	Poorest State Inclusive Growth Programme
RBI	Reserve Bank of India
SEDP	Skill and Entrepreneurship Development Programme
SF	Samridhi Fund
SFIF	State Financial Inclusion Forum
SFMC	SIDBI Foundation for Micro Credit
SHGs	Self Help Groups
SHPIs	Self-Help Promoting Institutions
SIDBI	Small Industries Development Bank of India
SRF	Swalamban Resource Facility
SRLM	State Rural Livelihood Missions
SVCL	SIDBI Venture Capital Limited
TA	Technical Assistance
ToC	Theory of Change
UPMA	Uttar Pradesh Microfinance Association

A. Summary and Overview

Description of programme

The Poorest State Inclusive Growth (PSIG) programme promotes Financial Inclusion through two components: Technical Assistance (TA) (£30 m) and Impact Investment (Samridhi Fund; £35 m) – implemented by Small Industries Development Bank of India (SIDBI) and its subsidiary SIDBI Venture Capital Limited (SVCL), respectively. The programme aims to support 13 million poor and vulnerable people, especially women, in the low-income states benefit from economic growth through better access to financial services and enhanced private investment. The programme is aligned to Government of India’s flagship schemes and priorities for financial inclusion.

Component 1, focused on policies and interventions for diverse financial services such as credit, insurance, savings, pension and financial literacy, ended in March 2020. It worked with a range of channels that include microfinance institutions (MFI), Self-Help Promoting Institutions (SHPI) and banking correspondents (BC) to reach the poor in four states – Madhya Pradesh, Uttar Pradesh, Bihar and Odisha.

The 2019 Annual Review discussed the progress under this component in detail. This Annual Review reports against the work done to set up an institutional mechanism within SIDBI to continue and build on the results of the TA components (referred to as PSIG legacy) and provides a summary overview for outputs 1, 2 and 4. The future Annual Reviews (2021 and 2022) will give an update on progress of PSIG legacy and not against outputs1, 2 and 4.

Component 2 promotes impact investments in eight low income states. FCDO is the majority contributor in Samridhi Fund with 78% interest in the Fund. The Fund provides risk capital to scalable enterprises which benefit the poor through job creation, increased earnings and reduced cost of goods and services. The Fund’s investment period is over as of March 2019 and the Fund has invested in a diversified portfolio of 23 companies.

Summary supporting narrative for the overall score in this review

The overall score for the programme is A+. Most log frame targets have been met or exceeded and the programme is on track to meet the outcome results. This was also confirmed by an independent end line evaluation for component 1[1], completed in October 2019 and midline evaluation/regular monitoring for component 2. The key findings and recommendations from the evaluation was disseminated in a DFID office wide meeting in February 2020.
[1] PSIG TA endline report

Component 1- Financial Inclusion
Amidst the dynamic policy shifts in the seven years of its active implementation, the component:
- Reached over 11 million women and improved their social and economic wellbeing - increased use of financial services (credit, savings, insurance); digital capability; increase in micro businesses; small but significant reduction in poverty levels; lower experience of violence; and more involved in decision making.
- Deepened the outreach in underserved regions (PSIG supported Micro Finance Institutions (MFIs) partners showed an annual growth of 26% against the average 10%). The end line noted a small but significant reduction in poverty rates (9 percentage points for the rural areas and by 13 percentage points for urban)
- Catalysed a more positive policy environment for microfinance; helped partners adapt to major policy shifts including demonetisation and “margin cap”; and helped industry and state associations (Uttar Pradesh and Odisha) become more effective in advocacy, outreach and governance.
- Focused on responsible finance, code of conduct and genuine gender focus.
- Demonstrated a cost benefit ratio of 1:11.
- Created an institutional mechanism[2] for SIDBI to continue to build on the TA interventions.
  [2] PSIG provided loans, guarantees and retail lending that allowed the MFIs to raise funds from the market and scale up their operations in underserved areas. These funds were returned during the life of the project. They are being used by SIDBI to continue the activities after the end of the contract in March 2020.
PSIG experiences and lessons are captured in three documents that were shared with diverse stakeholders including government departments (MSME; Skills Development; Social Justice; Financial services); Reserve Bank of India; Regional Rural Banks; State Livelihood Missions MFIs; NBFCs; civil society partners. The documents are also uploaded on SIDBI’s website.
- Poor 2Progressive: Decoding Learnings – highlighting PSIG approach and interventions within each state.
- Handbook for Promoting Women Entrepreneurship: important insights from our interventions where we provided 360 support to women – business development, personal capabilities, market accesses and access to finance.
- Sustainable Strategies: Finclusion to Swavalamban: describing implementation models that can be replicated/adapted.
Swalamban Resource Facility (SRF)

PSIG implementation started when MFIs were facing existential crisis as a fall out of the “AP crisis”[3] (2010 – 12).  Component 1 provided loans, guarantees and retail lending that allowed the MFIs to raise funds from the market and scale up their operations in underserved areas. SIDBI recovered the funds (loans, guarantees) - £11m and consolidated them into Swavalmban Resource Facility (SRF) to  build on the success of PSIG.
[3] Excessive lending, high interest rates and unscrupulous practices by a few MFIs in the Indian state of Andhra Pradesh. It led to severe backlash and criticism of the sector.

Swalamban Resource Facility (SRF), was launched in April 2020 and is aligned to SIDBI’s umbrella Mission Swavalamban (independent/self-sufficient) to promote entrepreneurship and is housed within the Promotion and Development (P&D) vertical of SIDBI.

SRF is envisaged as a catalytic facility to support social and economic inclusion of the poor. It supports microenterprise/livelihood development, and innovative pro-poor market-based solutions, especially targeting women. The geographic focus will extend to include North Eastern States and disaster-prone areas. It will continue to work with grassroots platforms – Livelihood missions, MFIs, BC networks, civil society networks and build on proven solutions. SRF will also support impact companies supported by FCDO and SIDBI to improve community outreach, business processes and ESG compliance. The initial time frame for SRF is five years.

The SRF team framework draws on the recommendations of the end-line assessment; and also on the 2019 report by the Reserve Bank Of India’s Expert Committee on MSME, specially on measures to strengthen the micro and small entrepreneurs.

The Steering Committee (SC), headed by the Deputy Managing Director, SIDBI, provides strategic oversight, approves work plans and monitors progress for SRF. FCDO is represented in the SC and in the Project Approval Committee. Two SC meetings were held this year – in January 2020 to agree the overall framework; and in June 2020 to review the progress and to update the work plan[4]. The FCDO Development team works closely with the SRF team[5], now fully in place, on developing projects under SRF. SIDB’s contribution also includes all programme management, administration and infrastructure support.
[4] Vault links to minutes; letter
[5] Five project staff – including gender and evaluation leads; four core SIDBI staff; headed by General Manager, P&D.

SRF is now an important vehicle for the division to have greater impact in unserved/underserved regions and sectors by building on PSIG’s successful interventions; and testing/validating new ideas and innovative approaches.  It is also an important aspect of our partnership with SIDBI, allowing us to co-create innovative solutions and influence sector wide policies. And helping our partners access SIDBI’s wider portfolio.

Progress: Since its inception in April 2020, SRF has  focused on covid recovery -  rebuilding livelihoods and supporting existing enterprises. In all  SRF has funded 11 projects (total amount sanctioned: Rs 22 cr/£2 m) till December 1, 2020. These include:

- Partnerships with  four State Rural Livelihood Missions (SRLM) – Assam, Odisha, Bihar, Jharkhand – for last mile financial services and microenterprise enterprise development for women.  Here is a glimpse of the work we are building on - Bank Sakhis in Bihar.
- Facilitate liquidity support by helping 10,000 small enterprises onboard the TReDs  platform for financing trade receivables; and 50,000 micro-entrepreneurs, especially women  to onboard PSBloans - an online platform to process loans in 59 minutes -  to access government schemes.
- Test new opportunities/new geographies: Sanitisation and Hygiene entrepreneurs  SHE; 360 support to communities to revive livelihoods/microenterprises in climate vulnerable (Sundarbans); and in remote areas (Leh).
- Support to  start-ups/impact companies under FCDO’s Samridhi Fund to strengthen business processes and deepen outreach; Assistive Technology Market Access Fund (ATMA; with Social Alpha) to support AT start-ups to be market ready; and the FinTech/rural tech incubator at IIM Lucknow.

Component 2 – Samridhi Fund

The social and financial results for the portfolio are promising. Samridhi Fund has met/exceeded expectations at the output level. The Fund has invested Rs 385 cr (£43m)[6] in 23 companies including financial services and Micro Small and Medium Enterprises (MSMEs) across sectors such as healthcare, agriculture & allied, water and clean energy.
[6] For component 2 (Samridhi Fund), all conversions done at the exchange rate of £1 = Rs 90.

The Fund has already overachieved its targets at the outcome level: increased employment income; reduction in cost of services; increase in earnings as producers.

MSMEs take time to mature as these are relatively smaller companies. COVID-19 impacted investee companies across various dimensions – revenue/business growth, cash flow issues, supply chain disruptions and delay in subsequent fund raise. Samridhi Fund (SF) has been continuously assisting and working closely with the portfolio companies to help them manage the crisis. Many companies repurposed their business models in face of the crisis. For e.g. Rite Water, which provides clean drinking water solutions has come up with disinfectant sprays/solutions to fight the virus. The portfolio is now showing signs of stabilizing compared with the initial months of the pandemic when there was higher level of uncertainty. Many companies are also restarting their fund raising efforts.

The independent evaluation of the Samridhi Fund (currently under way) will cover nine investee companies from the portfolio. These account for over 55% of the invested capital. The final evaluation report will be available by February 2021. Key takeaways from case studies are that Samridhi Fund’s capital is the first institutional investor in early stage companies and that it helped several investees improve access and affordability to goods and services to the poor. The midline evaluation[7] also noted that while Micro-finance sector has matured,the sector has been instrumental in reaching out and providing essential services to the most vulnerable. The FCDO team has also visited some of the investee companies in prior years and has verified the results and impact on the ground.
[7] Add link to the midline report evaluation - Joy

Despite COVID crisis which impacted growth and valuations, the Fund may deliver good financial returns. Based on September 2020 valuation report[8], the Net Asset Value (NAV) of the Fund for face value of Rs. 1,000 per unit was Rs. 1,331 per unit. COVID-19 has had an impact on the business of many companies and delayed fund-raising plans – the companies have requested for extensions in repayment time periods/lower interest etc which has been approved by the Investment Committee
[8] Done half yearly by an independent agency

The Fund has also made distributions to investors including FCDO in the past from part exit of an investee company and other income (e.g. dividends, interest) from investments in companies. The partial exit from Annapurna yielded substantial development impact in addition to the financial returns which has been given back to the UK Treasury. The exit story was also published in the media[9] highlighting the substantial double bottom benefits of FCDO’s investment.
[9] Exit story

Lessons learnt and recommendations

Component 1
Lessons
Covid highlighted the need for strong last mile delivery channels to support communities and highlighted the role micro finance institutions, SHG platforms, civil society networks play, to rebuild livelihoods and value chains. The crisis also highlighted the need to support women micro entrepreneurs to ensure that they can diversify their businesses and/or identify new opportunities. This support must include a combination of business, marketing and credit support.

PSIG successfully catalysed systemic change - significant in scale and sustainable beyond the timeframe of the program. Most community finance institutions do not have strong gender policies. Institutional commitment; practical action; women’s voices and team’s resilience ensured that the partners integrated gender and poverty lens as part of their core business. Partners also realised the need for greater client protection and relationship so as to retain the customer base in the face of coemption and crisis.

Recommendations
SRF should continue to identify innovative opportunities to build back better for the poorest households and enetrprises impacted by covid and help them access government programmes. SRF should also integrate a climate/green lens as part of the proposal review process.

SRF to develop an overall results framework, in consultation with FCDO. This will help in measuring progress and communicating the successes and the lessons better.

PSIG’s work on gender helped the sector become more client centred and inclusive. The programme generated a lot of important lessons for the sector around reaching the poor and the underserved geographies, product mix, client protection, and partnerships. SRF should develop a communication plan to share lessons and highlight ground experiences and implementation challenges regularly to different stakeholders.

Component 2
Lessons

Investment in companies is prone to external risks including regulatory risks – we have seen impacts on the portfolio due to demonetization, Goods and Services Tax (GST) and now COVID-19. The Fund has to closely work with investees during these times to mitigate the impact of such unforeseen instances. In the midst of current pandemic, the Fund has been closely monitoring the portfolio and working with investees on various initiatives e.g. cost reduction measures, helping with access to funding under government schemes, reorienting business strategies and connecting with intermediaries for subsequent fund raising.

Investments in small and medium scale businesses take time to mature including because these are relatively smaller companies. Technical Assistance (TA) support can help these companies in key areas such as Environment Social and Governance (ESG) framework and compliance, strengthening business processes, providing strategic and financial expertise to take their enterprises to the next level. SRF/SIDBI and SVCL have formalized agreement to use part of the funds (up to £0.4m in the first phase) for TA to Samridhi Fund and its investees.

While some investments do not perform as expected, the benefits from the ones which succeed can be substantial. Samridhi Fund had to write off some investments due to unsustainable business models. There are many investee companies who are showing good progress yielding both social and financial returns.

Recommendations

Samridhi team to focus on monitoring of the investees and working closely to help them tide over the current crisis and return back to growth. The focus of the Fund will also be to prepare for exit of the portfolio over the next 2 years.

The Fund and investee companies to develop TA proposals under the SIDBI-SVCL TA arrangement. This will focus on strengthening ESG compliance, supporting companies with financial and strategic advice to help them prepare for subsequent fund raising. The team has developed the first proposal under the TA agreement for an investee, Rite Water – which is expected to be operationalized in the coming few months.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change and any major changes in the past year(1/2 page)

The programme is based on the theory of change (ToC) that: a) access to finance protects poor households from economic shocks; b) catalytic donor support is needed to expand services to poor geographies; c) microfinance platforms can be leveraged to empower women; and d) there is an unmet need for investment in the poorer regions.

There were a lot of changes in the external environment that were unforeseen. PSIG adapted its interventions to respond to the for example to leverage digital platforms, deepen business correspondents (BC) network, make financial literacy more effective and support enterprise development. The focus on gender mainstreaming and women’s empowerment is directly related to the ToC. Very often such processes are undervalued, less invested in and in several cases not done at all. The end line has validated this focus.

Overall, the theory of change remained valid for component 1.

Samridhi Fund was designed on the hypothesis that there is an unmet need for capital in the poorest states, because of: (i) Investor preference for safer investments in known sectors and states; (ii) Untested business models which reach Base of Pyramid or provide basic and other services. It was expected that DFID’s investment will i) maximise the developmental impact of our investment and ii) to crowd in commercial capital into underserved segments; demonstrating additionality of FCDO capital. The theory of change remains valid for Samridhi Fund.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
Programme has met/is on track to achieve the outcomes (i) Improvement in targeting low income clients in PSIG states; (ii) Number of project clients accessing financial services (credit; savings & pensions; payments; and insurance) (iii) enhanced economic value generated as increased employment incomes by investments in enterprises; and (iv) Proportion of women who report being able to take decisions on household savings and investments.

For Component 2, the Fund has over-achieved its targets at the outcome level.
- 14,000+ jobs for men and women
- Reached over 5.8 million people with access to financial services
- Generated employment income of £43m and reduction in cost to poor consumer/ Increase in earnings to poor producers of over £900m
- Leveraged £100m in private equity capital.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Samridhi Fund is one of the key DevCap focused programme of FCDO India focused on delivering sustainable and inclusive economic growth in the low income states of India. It is important to deliver xHMG objectives on Entrepreneurship and Finance. The programme has a strong focus on cross cutting themes of fostering gender equality and supporting green growth projects. Besides creating substantial social impact, the Fund has returned approx. £5.7m to the UK treasury from financial returns from investments. The programme is in partnership with GoI and hence strengthens G2G relationships and influence.

Explain major changes to the logframe in the past year
Component 1 ended in March 2020. For component 2, there were no changes to the log frame this year.

Describe any planned changes to the log frame as a result of this review : None
## C: DETAILED OUTPUT SCORING(suggest 1 page per output)
Output Title		Policy and institutional environment that encourages provision of financial services to poor people in a responsible manner facilitated
Output number per LF			1	Output Score	A+
Risk:			Major	Impact weighting (%):	20%
Risk revised since last AR?			Y	Impact weighting % revised since last AR?	N
Indicator(s)	Baseline		Milestones March 2020	Achievements March 2020
Policy constraints to client-oriented need for financial services addressed by impacting policy on MF sector regulations and acts.	Establish a Think Tank with National & International experts on Inclusive Growth whose knowledge & neutrality is unquestionable and whose views will impact policy makers. / (A group was set up to provide advice on the programme. This is being referred to as “Think Tank”. This was discontinued in 2015).		a) Microfinance institutions seen as credible channels for financial inclusion providing diverse financial services / B) Strengthening Microfinance sector and enabling environment inclined to government policies/priorities / c) 8 policy papers prepared and 2 additional studies commissioned.	Achieved / A & B) MFIs recognized as key to financial inclusion by the regulator and borrowing limits raised in October 2019 to 1.25 lakhs for MFI clients, the limit was revised first time after 2015 / C) Overall 17[10] studies & 8 policy papers prepared and disseminated through various channels/platforms including SIDBI National Microfinance Congress. In addition, 13 policy level flyers for quick dissemination.
Number of Partnerships either directly or through assisted institutions for fostering innovations in financial inclusion and responsible financing e.g. / Business Correspondents; Branchless banking; Credit bureau; Technology etc.	0		16 partnership and 2 new partnerships and scale-up of at least one existing partnerships for capacity building	Exceeded. / 3 new partnerships; 30 in all
Synergise financial inclusion efforts at the state level	Establish a Senior State Level Multi-stakeholder Committee to feed into sectoral/state policy level issues. / (A multi-stakeholder forum was set up along the lines of the one at the centre).		a) 4 State Financial Inclusion Forum (SFIF) institutionalised and support in delivering at least 12 new inter-institutional partnerships / 2 State Associations functional; and explore further strengthen and replicating the association model in other states. / At least 4 fintech solutions tested and scaled up	Exceeded. / 10 partnerships overall. / SFIF were discontinued in 2016/17, based on the feedback received from the stakeholders. Focus shifted to strengthening State Associations in UP and Odisha - a more institutional and sector owned effort to promote responsible finance. / Business Correspondent Federation of India (BCFI), set up under the programme, advocates for better policies; capacity building of the BCs; and promoting a code of conduct. / The Sci-Fi fintech incubator with IIM, Lucknow, is incubating 9 solutions, one of which has successfully graduated from the programme. A strategic review of SciFI helped in revamping the incubation process and the industry connect. Support to SciFi will continue under SRF.
[10] https://www.sidbi.in/en/policy-advocacy-initiatives

Briefly describe the output’s activities and provide supporting narrative for the score.

The output has scored A+. When PSIG implementation started in 2012-13, MFIs were facing existential threats on account of the microfinance crisis in India. PSIG facilitated MFI funding, and worked with stakeholders to commission independent studies, convene neutral and topical forums and contribute to building national commitment and policy for microfinance and financial inclusion. Advocacy combined with direct support to MFIs (funding and capacity building) contributed to expansion of the sector in the PSIG states, with commitment to responsible finance.

In a changing policy landscape, PSIG adapted in innovative ways to support ideas and initiatives to be effective and relevant. These included contributing to the policy framework and MFI preparations for getting a Small Finance Bank licence or supporting MFIs, state and national level sector associations to deal with major policy shifts; and supporting small MFIs.

The National Microfinance Congress could not be held this year due to the pandemic. It is the only government led platform for the microlending sector. It brings together the MFIs, credit bureaus, e-commerce platforms, digital lenders, fintech start-ups, BC networks and SHGs. It must continue this critical role to identify and address key policies issues, emerging risks and opportunities for the sector to grow/revolve.

Current scenario: The MFI sector registered a growth of 30% from April 19 to March 20 [11], as against 40% for the previous year. The decline in growth rate is attributed to natural disasters in Odisha, Kerala and West Bengal, spread of misinformation and false rumours by vested interest political groups in certain districts of Assam and Karnataka, and the emergence of covid in the last quarter.
[11] Bharat Microfinance Report 2020:Sa-dhan

The crisis highlighted the need for MFIs to invest in building client relationships; use technology and provide finance and advise to revive livelihoods and microenterprises. There are signs of recovery but the growth is expected to be muted this year, with mid and small size MFIs more impacted due to the liquidity crunch. We continued to work with Sa-Dhan under another programme for ground level assessments including client feedback and to consult with a range of stakeholders for policy support to the sector during this period.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The policy impact of the programme has been high and well documented and fulfils all VFM considerations - of efficiency; economy, effectiveness and equity. . A programme level calculation of the cost benefit ratio based on the monetisation of estimated and/or imputed benefits both from economic and social uses of on-lending funds indicates very high benefits relative to cost (ratio of 11). PSIG cost-effectiveness ratios for reaching low income households at small, if not minuscule proportions of GNI per capita suggest a high level of efficiency for the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes. The TA component ended in March 2020. There will be no reporting on this output in subsequent ARs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The recommendations from previous ARs mainly centred around launching the legacy vehicle. This has been done.

Output Title	Institutions providing diverse financial services promoted
Output number per LF			2		Output Score		A+
Risk:			Moderate		Impact weighting (%):		20%
Risk revised since last AR?			N		Impact weighting % revised since last AR?		N
Indicator(s)		Baseline		Milestones / March 2020		Achievement 2020
Indicator 2.1 – / No. of MFIs reporting Improved Fund Flow 2.1.1 Increased exposure from banks; / 2.1.2 Diverse mechanisms of funds flow by securitisation, NCDs (non-convertible debentures), credit BC, External Commercial Borrowings (ECBs		Capacity Building Need Assessment (CBNA) reports of MFIs reflecting their current sources of funds		a) 25 MFIs report more than 25% increase in funding over baseline. / b) SFMC is a leading provider of long-term debt to microfinance sector / C) Promoting livelihood opportunities for bottom of the pyramids		Achieved / a) 25 MFIs reported more than 25% increase in funding over baseline. / b) PSIG has been administratively clubbed under the Promotion and Development (P&D) vertical. This has helped PSIG to integrate its focus and lessons better with SIDBI’s main programmes. / The SIDBI Foundation for Micro Credit (SFMC) is now merged with the Institutional Finance Vertical (IFV). IFV continues to provide equity/long term debt to MFI partners and is implementing the scheme “Prayas” that provides credit at a much lower rate. . / C) PSIG implemented / i) Skill and Entrepreneurship Development Programme (SEDP) with 7 MFI partners in 8 districts inclusive of 4 aspirational districts. The programme built business skills of 7000 entrepreneurs inclusive of setting/scaling up and credit linking 3500 women led micro enterprises / ii) The Mahila Udyami Sashaktikaran programme (MUSP) trained 15,500 women on business skills, created credit linkages for 9768 women and provided handholding support along with market linkages. / iii) 1,000 SHG members trained and onboarded as Banking Correspondents, now earning more than Rs. 6,600 per month.
Indicator 2.2 Number of MFI's with: / a) Improved/maintained credit rating; / b) Improvement in COCA (Code of Conduct Assessment); / c) using client targeting tool		Investment grade rating / of partner MFIs; / Agreed score of COCA		25 / 25		Achieved. / a&b): SIDBI developed a new tool combining code of conduct and rating. 25 MFI partners assessed. Rating of 15 MFIs improved, 7 maintained; 3 converted into SFBs. / 10 MFIs renewed COCA; rating was maintained / c)Progress Out of Poverty Index (PPI) 10partners used it.
Indicator 2.3 : Number of self-help groups (supported);		0.81m / a) TBD / b) TBD		2 million / Providing diverse financial services through strengthening SHG BC channel		Bank Sakhis supported under State Rural Livelihood mission of Bihar (Jeevika) providing financial services to their communities reaching out to 2.5m people in 20 districts of Bihar. Now the prog is being scaled-up by Jeevika covering 31 districts.
Indicator 2.4 Financial Products: Average Loans Size / Non-Credit Financial Services:		a) 4570		a)16,000 / 5 new MFIs associated to be taken to next stage / Non-Credit financial services		Achieved / INR 18,034 (Source- Bharat Micro Finance Report 2020. ) / 7 partners supported through a pilot programme to give higher ticket size enterprise loans along with entrepreneurship development services. / PSIG supported 34 MFIs. Out of which 24 continue to provide non-financial services even after PSIG support ended in 2018.
Indicator 2.5: No. Of MFIs supported for increasing the reach of affordable finance for graduating MFI clients.		0		Up to 2 MFIs catering to graduating clients in PSIG states.		3 PSIG partners onboarded under Prayaas Scheme. / SIDBI has rolled out Prayaas Scheme on Pan India basis catering to the graduating micro finance clients. Prayaas provides loans at affordable cost of 14-15%.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score is A+. The endline notes a substantial growth in the outreach of PSIG-supported partner Financial Institutions (PFIs) - a compound annual growth rate of 26.3% which is significantly higher than the 10-15% growth of outreach in the microfinance sector nationwide. (The evaluation does not consider the growth in 2012-13 in the recovery from the 2010 microfinance crisis).

The end line also noted that the PSIG interventions did not improve the cost of delivering the credit, partly due to the policy shocks and the margin cap[12]. However, as the National Congress 2019 noted[13] with new investment channels, and new business models, the cost of borrowing will come down. Many of the large MFIs have begun to reduce the interest rates[14].
[12] Margin cap refers to the net interest ceiling fixed by RBI - 10% for large MFIs(portfolio of over Rs100 crores) and 12% for others.
[13] Vision-of-Microfinance-in-India,
[14] More-mfis-to-lower-rates-as-borrowing-cost-falls

PSIG support enhanced the ability of small MFIs to expand outreach overall, manage growth, source commercial funds to facilitate that growth and to manage associated risks. PSIG also supported development of Stand-up India (now Udayamimitra) portal, a virtual marketplace to provide 'End-to-End' solutions for credit delivery and business counselling.

SIDBI has rolled out Prayas Scheme across India to provide higher ticket size loans starting from Rs 50,000 to Rs 5 lakh at affordable interest rates of 14% to graduating MFI clients and small entrepreneurs. This is a market maker scheme that brings down the cost of Microfinance in India. The scheme tied up with three PSIG partners in its pilot phase of implementation. SRF will support the capacity building and credit plus services for its partners and clients.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The value for money is high. PSIG had created assets on SIDBI’s books in the form of loans, guarantees and retail lending. This allowed the MFIs to raise funds from the market and scale up their operations in underserved areas. SRF, PSIG’s legacy vehicle, will use these residual assets to continue the activities after the end of the contract.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous recommendations focused on deepening the work on enterprise support; testing new products/vulnerable groups such as migrant workers and scaling up the Bank Sakhi model for last mile financial services in other states. The partner has progressed on all the recommendations and taking them further into SRF as well. SRF has formalised partnerships with four state rural livelihood missions (Odisha, Assam, Jharkhand and Bihar) to adapt the lessons from Bihar. Post covid, many of the projects are supporting migrant workers. Deepening its focus on disability, SRF will support four start-ups on Assistive Technology.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes. The TA component has ended and the subsequent ARs will not report on this output.

Output Title	Businesses that enable the poor to benefit as producers, skill providers and consumers, are promoted
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Cumulative Milestones Dec 2020	Progress December 2020
Enterprise investment strategy designed and implemented	NA	Impact Assessment	On Track / The Fund has completed investment in 23 companies. The Fund has a good portfolio and both the social and financial impacts will be met/exceed the expectations. The team monitors social indicators for all companies to assess the full impact. / The Fund has already returned £5.7m back to HMG from exit/other income from investments.
Results of investments in enterprises: / a) Number of total sustainable enterprises supported with risk capital /grant funds / b) Growth in turnover of these enterprises over the investment period	NA	a) 20-35 / b) 100%	Over-Achieved / a) The Fund has invested in 23 companies, out of which 50% is invested in MSMEs / b) The combined turnover of investee companies has increased over 300% over the investment period. The baseline revenue was Rs 923 cr (£103m[15]) which increased to Rs. 4,010 cr (~£445m) at the end of FY20
Development and Financial Returns on Capital from invested funds	NA	Gross portfolio IRR up to 8% + development returns TBC	Over-Achieved / The Fund has delivered well on development results. It has overachieved its development targets at the outcome level. The businesses it has supported has created an additional 14,000+ jobs for men and women. / Actual total financial returns will only be known at the closure/divestment of the Fund (based on actual exits). / However, based on September 30, 2020 valuation report, the Net Asset Value (NAV) of the Fund has increased from value of Rs. 1,000 per unit to Rs. 1,331 per unit.
[15] Arohan, Muthhoot, Sarvodaya and Ashirwad All INR-GBP conversions using exchange rate of 1 GBP = INR 90

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has scored “A+” as all output indicators have shown progress and most have over-achieved expectations.

The Fund has invested Rs 385 cr across 23 investments. As per regulatory requirement, the Fund has to invest 50% in MSMEs and 50% in financial sector (NBFC and Small Finance Banks). The Fund has built a diversified portfolio of investments spread across geographies, sectors (as shown below), size (amounts) and stages (start-ups, early-stage, growth).

The chart below shows the current Samridhi investments by value by sector.

Samridhi investments by sector

The Fund has achieved substantial development impact. For e.g. it has reached over 5.9m poor people with access to financial services; 1.6m with access low cost & quality healthcare; 1.5m people could access drinking water. (Refer to Annex 1 for more details).

At the outcome level, the Fund has overachieved its objectives. The companies supported by the Fund have generated employment income of £43m and reduction in cost to poor consumer/ Increase in earnings to poor producers of over £900m. The portfolio companies have also leveraged £100m in additional private capital (equity) up till now. This substantiates FCDO objective of leveraging in private capital into these companies that reach out to the poor.

During the current year, the portfolio was impacted due to the COVID-19 pandemic. The Fund has worked closely with the portfolio companies and they are now showing signs of stabilizing. Many MSMEs are showing good growth potential and are in the market to raise fresh equity.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The key cost factor for Fund investment is the fee paid to the Fund manager and the performance-related “carry” (i.e. share of the Fund manager in the profits of the Fund beyond a minimum return to the investors). The fees and costs to the Fund partners are in line with industry practices. In addition to social return, Fund investments generate a return on invested capital which is returned to the UK Treasury and can be further invested in other development projects.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There has been no change in this output during the past year. No changes are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations:

Recommendations	Progress
FCDO and SVCL to work together and close amendment to the legal documents	The amendment to the Samridhi Contribution Agreement was signed in August 2020
FCDO and Samridhi Fund to work together to produce case studies showcasing results (both social and financial returns) and capturing/disseminating lessons and impact created. FCDO and Samridhi Fund to also explore synergies, wherever possible, to make x-HMG connects	One of the companies, Glocal, which operates low cost hospitals and digital dispensaries in low income states of India, was named as Entrepreneur of the Year by the World Economic Forum’s Schwab Foundation in Sep 2020. / Companies such as Rite Water, Collateral and Glocal are developing solutions/offering services for COVID mitigation/treatment and these were highlighted in various forums. The teams also connected with DIT colleagues to discuss the healthcare portfolio of the Fund and explore synergies.
Samridhi team to focus on monitoring of the investees and start focus on value creation activities in the portfolio. The team to also get a TA agency on board to start implementing some of the planned TA activities e.g. Strengthening ESG monitoring and reporting, bringing in expertise at the investee level etc	During the current year, the portfolio was impacted due to the COVID-19 pandemic. The Fund has worked closely with the portfolio companies to reduce costs, increase revenues and prepare for subsequent fund raise. / The team has developed the first proposal under the TA agreement for an investee, Rite Water – which is expected to be operationalized in the coming few months.

Lessons learnt:

Investment in companies is prone to external risks including regulatory risks – we have seen impacts on the portfolio due to demonetization, GST and now COVID-19. The Fund has to closely work with investees during these times to mitigate the impact of such unforeseen instances.

Investments in small and medium scale businesses take time to mature as these are relatively smaller companies. Technical Assistance (TA) support can help these companies in key areas such as Environment Social and Governance (ESG) framework and compliance, strengthening business processes, providing strategic and financial expertise to take their enterprises to the next level.

Recommendations

Samridhi team to focus on monitoring of the investees and working closely to help them tide over the current crisis and return back to growth. The focus of the Fund will be to prepare for exit of the portfolio over the next 2 years

The Fund and investee companies to develop TA proposals under the SIDBI-SVCL TA arrangement. This will focus on strengthening ESG compliance, supporting companies with financial and strategic advice to help them prepare for subsequent fund raise.

Output Title	Women’s capacities to tackle financial and gender issues enhanced
Output number per LF				4	Output Score		A+
Risk:				Minor	Impact weighting (%):		10%
Risk revised since last AR?				N	Impact weighting % revised since last AR?		N
Indicators		Baseline	Target March 2020			Achievement March 2020
Indicator 4.1 / Number of women clients provided with training on financial literacy / x% of women achieve certification on financial literacy and gender trainings		0	Additional 200,000 imparted FLWE training institutionalised in association with government institutions. / 100%			Exceeded / Overall, 658,000 women trained and certified on FLWE Financial Literacy and Women’s Empowerment. / The FLWE is being continued by 10 partner institutions who have institutionalized FLWE trainings & content in their regular operations. / Achieved.
Pilot entrepreneurship development programme targeting women entrepreneurs / Association with livelihood missions for strengthening access to alternate banking and digital financial literacy		0 / 0	At least 5,000 women entrepreneurs trained / At least 300 women BCs trained and 20,000 provided Digital financial literacy			Follow up programme on Business Literacy and Entrepreneurship development for 9,000 women was implemented this year in UP to help women scale up and diversify their micro enterprises into viable small businesses that enhance their income and living standards. The programme trained 15,500 women on business skills, created credit linkages for 9,768 women and provided handholding support along with market linkages. The programme has helped to ground 9,000 women led enterprises. / Over 1,000 SHG members trained as Banking Correspondents in Bihar. These SHG members have become financially sustainable BCs earning more than Rs. 6,600 per month with cumulative transactions of Rs.15.61 crore across a range of services (such as savings, deposits, withdrawals and remittances). From 4 districts, the project was scaled up to 31 districts (out of total 38). / 61,867 SHG members were provided training on Digital financial literacy.
		Source				Minutes of meeting, Project MIS, End line Reports

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Output is A+. PSIG successfully catalysed systemic change - significant in scale and sustainable beyond the timeframe of the programme. More than 10 partners have institutionalized FLWE approach in their operations and 22 institutions have started to integrate a gender lens in their policies & products. Two of the largest livelihood missions of the Government – Bihar and Odisha - scaled-up PSIG demonstrated approaches of FLWE and deepening alternate banking services through Bank Sakhis. In its last two years, the programme also evolved to address the field demand from women to setup/improve/scale their livelihood opportunities.

Several institutions provide financial literacy. But layering it with modules on women’s empowerment helps women gain more self-confidence, be more risk aware; grow their business and be more involved in family decisions. Independent assessments of FLWE interventions also showed an increase in sharing of domestic chores between husband and wife.
From PSIG End line:

“The gender component of PSIG-Fin (Gender Integration in MFIs and Financial Literacy and Women’s Empowerment, FLWE) represents a very substantial effort on the one hand to introduce gender issues within MFI policies and operational practices, and also to demonstrate opportunities and methods to build financial and non-financial capacities of women clients.

Two thirds of clients said that things have improved. Significant reduction in violence; and improvement in women’s agency.”

PSIG’s microenterprise development programme for women has demonstrated the viability of scaling-up businesses of more than 9,000 “barefoot” entrepreneurs who often lack access to technical support and capital to expand and formalize. In partnership with Jeevika, Bihar, technical support was also provided for micro enterprise development for graduating clients with a special focus on kirana stores (small local retail/gen shop).

The National Microfinance Congress of 2018/2019 prioritised policy and sector issues identified by PSIG – doorstep access to financial services; women’s empowerment; client protection and enterprise financing. The endline too underscored the importance of a sustained approach.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The output has demonstrated systemic impact and unlocked state resources for scale up. The output satisfies all the VFMs and on gender. The overall cost benefit ratio for the programme is 1:11.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations centred around sustaining a focus on gender, credit plus services and support for women enterprises. SRF will continue to focus on underserved areas and provide 360° support to women micro entrepreneurs and also test different financing models; and launch targeted initiatives for young women. The SIDBI National Microfinance Congress should continue to put a spotlight on inclusion and support the sector to develop new products, services and organisational policies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes. The TA component has ended and there will be no further reporting on this output in subsequent ARs.
C: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The table below indicates the key risks and the mitigation strategy

Risk Description	Risk Category	Mitigation Strategies
Governance of PSIG Legacy Fund (Moderate)	Operational	A governance and operational framework for SRF, the PSIG legacy vehicle, is agreed. FCDO is represented in the PSC and the PSIG programme team works closely with the SRF team for programme development.
Loss of FCDO Capital (Major)	Reputational	The valuations show positive increase in the value of the units held by FCDO. The progress of companies is good and the Fund has already returned £5.7m to the UK Treasury
Reputational risk for DFID (Major)	Reputational	The Fund invests in small and medium enterprises in low income states where it takes time and effort to establish standard policies, governance etc. It can attract negative media on any incidents under investees. / Mitigation includes regular updates from the Fund managers, site visits to see the interventions on ground, ESG monitoring and TA support to strengthen capacity, policies and the processes. Samridhi Fund is represented on the Board of investee companies. Due diligence is done on the Fund level as well as investee levels. Independent audits are being done (ESG and Statutory). Exits to happen in next 1 -1.5 years and will also review KYC of buyers – to be then approved by IC. Counterparts (fund manager, other investors) are also Govt. entities and will have standard compliances in place. Endline evaluation presents lessons and value addition for the Fund management.
Adverse impact of Covid on investee companies (Major) and on SRF partners.	Delivery	Continuous engagement by the Fund with investee companies e.g. cost cutting work, close reviews of cash flow position, moratorium, resource support, funding tie-ups under government schemes /quick approvals for the same. / A similar approach followed by SRF to support partners.
Activities supported by the intervention lead to environmental pollution or unintended social consequences (Major)	Safeguarding	ESG assessment of investee companies by an independent consultant with recommendations for improvement / The TA agreement between SIDBI-SVCL will work with the investee companies and fund to strengthen ESG compliance
Development results are unmet/inflated (Moderate)	Reputational	Both the components have done well to achieve the development impact. / As per social indicators, development results are over-achieved/on-track. The Fund has shown good traction in both development and financial results.

D: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and FCDO, notably on commercial and financial issues

FCDO’s working relationship with SIDBI and SVCL has been collaborative. The SRF team - five full time project staff supported by three SIDBI core staff - is in place and is led by the General Manager, Promotion & Development (P&D) Department, SIDBI. This has ensured coherence and alignment with SIDBI’s institutional mandate.

SVCL is working with a small team and will be using the TA to strengthen support on portfolio management and strengthening its ESG reporting. With investment period over, SF team is focussing more on monitoring, portfolio management and exit strategy.

Financial Management: SIDBI is a public sector financial institution with strong financial management systems. The SIDBI team conducted periodic reviews of the projects against expected performance and spend. It achieved substantial savings by closing poorly performing activities/components of the programme and consolidating others.

The Fund undertakes valuation of its investments every 6 months, by an independent valuation expert. These reports are shared with FCDO’s Finance & Corporate Performance Division (FCPD) periodically. Fund finances are monitored regularly through monthly Investment Committee meetings. The Fund also provides a quarterly update on the investments undertaken and value creation activities for each investment. Current valuation shows an increased in the financial returns.

Monitoring and evaluation: Overall programme performance for both the components is measured against the log frame and previous year’s recommendations; regular meetings and field visits with beneficiaries and downstream partners to understand ground realities (restricted this year due to covid). Independent impact assessments have been commissioned for both the components. The baseline/midline and end line reports have informed the programme strategies and for component 1 the design of the legacy.

For Component 1, quarterly/bi-annual Project Steering Committee meetings helped review the progress and set strategic direction. SIDBI as a partner continuously reviewed ongoing activities during the year that helped in refining the design and delivery and scale up of interventions.

For Component 2, Investment Committee (IC) meetings - quarterly review Fund progress, portfolio updates and key risks. Fund Manager sends quarterly progress reports, six monthly valuation report and audited/unaudited statement of accounts. FCDO and SVCL monitor the results of the Fund regularly capturing essential social indicators (e.g. jobs created, beneficiaries reached) as well as financial performance (through the independent valuation report and tracking performance of investee companies).

Value for Money: As per the Endline assessment, a programme level calculation of the cost benefit ratio based on the monetisation of estimated and/or imputed benefits both from economic and social uses of on-lending funds indicates very high benefits relative to cost (ratio of 1: 11). PSIG cost-effectiveness ratios for reaching low income households at small, if not minuscule proportions of GNI per capita suggest a high level of efficiency for the programme.

The Samridhi Fund has delivered well on development and financial results. Though the total financial returns will only be known at the closure/divestment of the Fund, but based on September 30, 2020 valuation report, the Net Asset Value (NAV) of the Fund has increased from value of Rs. 1,000 per unit to Rs. 1,331 per unit.

Date of last narrative financial report(s)	For comp 1 – to be updated. / Latest Statement of Accounts received on 29 October 2020 / Latest financials for the Fund received on 8 Oct 2020
Date of last audited annual statement (s)	Annual Report for the Samridhi Fund received on October 1, 2020

Annexure I: Social Indicators for Samridhi Fund

Socio economic indicators	Incremental from baseline / (As on March 31, 2020)
Access to financial services	> 5.9 m
Access to low cost & quality healthcare	> 1.6 m
Access to drinking water	> 1.4 m people from approx. 3,506 water treatment plants
Access to services to farmers	>27,000
New employment generated	>14,000 People
Access to skill development training	Approx 1.25 lakh
	>70% are Women

* Note the above numbers are for the whole Fund
Source: Data collected from Investee Companies