Programme Completion Review

Title: Poorest State Inclusive Growth (PSIG) Programme
Final Programme Spend £ (full life): £65m	Review Date:	30/09/25 (as per AMP)
Programme Code: 114293	Start Date: 23/12/2008	End Date: 30/06/2025

Summary of Programme Performance

Year	2012/13	2013/14	2014/15	2015/16	2016 - 17	2017-18	2018-19	2019-20	2020-21	2021-22	2022-23	2023-24	2024-25	2025
Programme Score	B	A	A	A	A	A	A	A	A+	A+	A	A	A	A
Residual Risk Exposure Rating[1]	Medium	Medium	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate
[1] This document captures the risk rating from earlier Annual Reviews, the nomenclature of some of them have been changed in the AMP

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-1-114293/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.dfid.gov.uk/projects/GB-1-114293/documents

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved

The Poorest State Inclusive Growth (PSIG) programme was set up to promote Financial Inclusion and Inclusive Growth in India’s low-income states through better access to financial services and enhanced private investment. It was delivered through two components: 1) Development Capital Investment (Samridhi Fund (SF/Fund); £35 m), and 2) Technical Assistance (TA) (£30 m). The development capital investment component was delivered by SIDBI’s subsidiary SIDBI Venture Capital Limited (SVCL). The TA component was implemented by an Indian Development Finance Institution (DFI), the Small Industries Development Bank of India (SIDBI). A diagrammatic representation of the programme is shown below:

Flow of funds

The programme aimed to support 13 million poor and vulnerable people, especially women, in the low-income states (LIS) to benefit from economic growth. This aim is aligned to Government of India’s flagship schemes and priorities for inclusion. PSIG implementation started when microfinance institutions (MFIs) were facing an existential crisis as a fall out of the “AP crisis”[2] (2010–12).
[2] Excessive lending, high interest rates and unscrupulous practices by a few MFIs in the Indian state of Andhra Pradesh (AP). It led to severe backlash and criticism of the sector.

SF invested £35m in 23 enterprises across sectors including healthcare, education, agriculture, and clean energy, achieving financial returns and development impact. Complementing this, the TA component strengthened financial systems, supported women’s entrepreneurship, and laid the foundation for inclusive finance.

Development Capital Investments:

This component invested in enterprises with potential for high development impact in the eight low-income states[3]. These states find it difficult to attract entrepreneurs or impact investments due to their limited infrastructure and perceived limited growth potential. FCDO established the Samridhi Fund (SF) in 2013, with SVCL as the fund manager, to provide capital to scalable enterprises that benefit the poor in these low-income states.
[3] Rajasthan, UP, MP, Bihar, Chhattisgarh, Jharkhand, Odisha, West Bengal These states constitute 53% of India’s population with 61% below $3.1 per day income (source end line evaluation).

SF was one of the first Development Capital investments under the UK-India co-investment partnership model. It was also SIDBI/SVCL’s first Social Venture Impact Fund for low-income states. FCDO was the anchor investor, providing £35m of the total fund value of c.£43m (c.78% share of investment in the Fund). SIDBI and Indian domestic Government of India (GoI) owned insurance companies (Life Insurance Corporation (LIC) and United India Insurance (UII)) also invested in the fund. SF invested in 23 companies mainly across micro finance, healthcare, education, agriculture, water and clean energy sectors. SF investments enabled a 300% growth in turnover of investee businesses and mobilised £700m in follow-on capital, while enabling businesses to expand operations to underserved regions, promote gender equity, and generate development impacts.

Key development returns included:

  1. SF investment led to a substantial expansion in productive capacity of the investees leading to an average 5 times growth in the turnover. 35% investees have women promoters.
  2. Significant role of SF in transformation of finance companies to large micro-finance institutions and, in two cases, to small finance banks.
  3. The Fund supported each investee’s expansion to at least three low-income states and 14 enterprises to expand their operations from other states to low-income states
  4. In majority of the investments, SF was the first/ second institutional investor and had SF not invested, it is highly likely the enterprises would have remained undercapitalised.
  5. Investees raised 15x from market with overall increase in capitalisation by £700m (₹7,208 cr).

SF was to end in June 2024 but received an extension to April 2025 from the Indian Regulator, Securities and Exchange Board of India (SEBI), to allow SF to exit its investments in a more responsible way to maximise UK tax-payer value. Previous Annual Reviews reported on the fund exit process and financial returns. The timeline of the Fund is presented below:

June 2013
Samridhi Fund launched
2013 Contribution Agreement signed with SVCL
March 2017
Original end of committment period
March 2018 Extended end of committment period: SF fully invested in 23 companies
April 2021 external evaluation of SF completed (including development outcomes)
June 2022 Original end date of SF
June 2023 Extended end date of SF (agreed due to covid impacts on investees)
June 2024
Original exit period end date (per standard SEBI regulations)
2025 exit period completed (one-year extension to exit period agreed with SEBI)

Financial Inclusion:

This component provided technical assistance from 2012-2019 for policy support for the sector, improved governance and systems for partner Government institutions and for financial and digital literacy and micro enterprises for women.

The component has been a transformative initiative aimed at strengthening the microfinance ecosystem and empowering women in underserved regions of India. The Programme supported in catalysing inclusive growth to improve governance, and to enhanced access to financial and digital literacy. It provided support to lay a strong foundation for inclusive, responsible, and gender-sensitive financial systems in India.

FCDO through the TA provided loans, guarantees and retail lending that allowed the MFIs to raise funds from the market and scale up their operations in underserved areas. SIDBI recovered the funds (loans, guarantees) - £11m and consolidated them into Swavalmban Resource Facility (SRF) to build on the success of PSIG in 2020.

SRF played a pivotal role in undertaking three policy studies which have been adopted by Government of India. One was on identifying gaps and opportunities for private sector in grain silos and distribution to help reduce food wastage. The second one proposed optimal approaches and policy inputs to strengthen India’s biomining and bioremediation ecosystem for better waste management. The Central Pollution Control Board has adopted the recommendations of the report and cascaded to municipalities. The third one was a technical study to inform a national policy for reducing diesel generator emission.

SRF has helped to navigate investee companies scale up, employ sustainable business processes and generate larger social impact through technical support. These interventions included sessions on responsible investing in ESG and climate change investing. As a result, these led to improved business processes; community outreach and impact measurement in start-ups.

Major lessons learned, evidence generated and recommendations

There were certain programme level lessons which are discussed below. Component specific lessons are discussed separately in the section.

The programme generated wider benefits for FCDO and the UK, particularly through building a strong relationship with GoI via SIDBI. SIDBI is a strategically important organisation given the importance of the Small and Medium Enterprises (SME) sector to both GoI’s priorities, and FCDO’s objectives for the UK/India relationship. For example, the importance of disruptive/ innovative solutions from the SME sector in tackling climate change; the need to reduce emissions from the sector to achieve climate ambitions; and the role of SMEs in supply chains and UK growth). As FCDO’s first impact investment fund in India, the SF also raised FCDO’s visibility in the impact investment ecosystem in India. These factors have supported FCDO’s subsequent efforts to partner with the Government of India both on policy influencing objectives (e.g. NEEV investee PRESPL pushed for amending the biofuel policy to reduce emissions) and further development capital investment funds (e.g. Green Growth Equity Fund). Some SF investees have also partnered with UK firms as part of their supply chains or as joint venture partners, generating benefits for UK firms. These linkages require significant time and resources to track: for current/future funds under the wider portfolio, FCDO should consider how these benefits could be tracked in a more robust, cost-effective way.

Beyond the programme’s direct financial and development outcomes, there is evidence that it contributed to creating longer-term systemic impact. These were not captured in the external evaluation, as this took place before many of these impacts had emerged, and the evaluators struggled to find evidence for them within the timeframe. The overall impact objective of the fund was to increase investment flows to the poorest states by 4 times baseline (2013-2018). Although neither the evaluators nor this report have been able to source quantitative sources to confirm overall increase in state-level investment flows, there is anecdotal evidence that SF contributed to developments in the wider impact investment industry, including an increase in funds targeting challenging sectors or geographies and increased adoption of ESG standards. More directly, SF’s successful lobbying of the regulator – Securities and Exchange Board of India (SEBI) – to allow more flexibility in fund exit periods is likely to enable other impact investment funds to pursue more responsible exits.

Another key lesson from the programme is that technical assistance (TA) plays a vital role in complementing development capital investments by enabling enterprises to scale responsibly and deliver deeper impact. While capital provides the financial runway for growth, TA strengthens the institutional capacity of investees - enhancing governance, improving ESG compliance, and building systems for monitoring and impact measurement. In the case of PSIG, TA helped microfinance institutions and start-ups navigate complex regulatory environments, adopt sustainable business practices, and expand outreach to underserved populations. It also supported policy-level engagement and sector-wide reforms, amplifying the effectiveness of investments. This dual-track approach—combining capital with targeted technical support—proved essential for achieving both financial returns and systemic development outcomes, and should be considered a best practice for future programmes. However, in the 0.3% ODA world, FCDO should also explore other approaches for creating systemic impact: for example, requiring fund managers, other partners or investees to undertake policy/sectoral initiatives, fund technical assistance activities, or bring in requisite expertise to bridge the gap areas.

Development Capital Investments – Experiences and lessons learnt

The external evaluation and ARs of SF report extensively on the direct development and financial impacts of the Samridhi Fund. Therefore, this PCR focusses on broader impacts of the SF, including:
- Key success factors and challenges for SF
- SF’s contribution to systemic impacts at industry, sector, and organisation level
- Wider benefits to the UK generated through the SF
- How learnings from SF have been captured in subsequent India Capital programmes

At fund manager level, the approach to ESG assurance that FCDO instigated for the SF has influenced SIDBI and SVCL’s corporate ESG approach. At sector level, some investees scaled and emerged as sector leaders with potential to highlight sectoral opportunities/challenges and influence other actors. Some had a transformative impact e.g. Online PSB Loans which drove public sector banks to engage with a fintech platform for the first time and has onboarded 20+ banks, disbursed £6.2 bn. Other investees successfully lobbied for policy changes e.g. on agricultural exports. It is important to note that systemic impacts do not necessarily occur organically or as a result of a passive “demonstration effect”: they rely on active influencing through closer engagement, technical assistance, communications, and relationship-building.

Learnings from SF have already informed FCDO central guidance on development capital programmes, as well as subsequent programmes delivered by the British High Commission India Capital Team. This PCR recommends dissemination activity to ensure all lessons from the SF are captured and made accessible to wider FCDO.

One of the key learnings from SF is that impact investment requires a long-term view. Investments in small and medium businesses take time to mature as they are prone to external shocks including regulatory risks. This affects their fund-raising which in turn implies a delay in exits for the fund and its investors. The investors have to be patient during these times as the Fund works closely with the investees to mitigate the impact of such unforeseen instances. This may require extension of fund tenor to ensure responsible exits for all the investors.

In summary, the SF was an innovative initiative for both FCDO and SVCL (the fund manager). As such, there were several practical challenges throughout the lifetime of the fund, including the fund manager’s capacity vis-à-vis the number and size of investments, investments spanning multiple sectors impacted by evolving industry dynamics, and regulatory challenges that delayed the exit period. In addition, external shocks affected the fund, including demonetisation (2016), disorganised implementation of the Goods and Services Tax (GST) (2017), and COVID (2020). On the whole, FCDO and SVCL were able to work together effectively to overcome these challenges and ultimately achieve SF’s development objectives. Throughout, an essential success factor was FCDO having a seat on the fund’s investment committee and having sufficient staff with technical understanding to fulfil its role as an active investor. Another key learning could be that, for a fund of this size, focusing on 10–15 investments across 4–5 sectors might have helped maintain strategic focus and mitigated the exposure to sector volatility.

Additionally, a valuable insight was that FCDO and SVCL could have collaborated more closely to align on impact priorities. While commercial returns were important for SVCL, the fund’s overarching goal of delivering meaningful development impact required a shared understanding that impact should take precedence when trade-offs arose.

It was also recognised that not every investment succeeds, and a failure rate of around 20% was acceptable and outweighed by the successes. This reinforces the importance of a portfolio approach and realistic expectations in impact investing.

Financial Inclusion – Lessons learnt

Small amounts of TA can create valuable impact in India’s financial landscape by working with Government institutions. Using TA, the programme created robust systems within SIDBI and partner institutions for monitoring, evaluation and impact assessment. PSIG laid a strong foundation for development-focused investments and elevated financial institutions within the ecosystem, enabling them to better serve the diverse financial needs of the population.

Tailored and inclusive approaches are key to building resilient Entrepreneural ecosystem. Many initiatives targeted entrepreneurship building under SRF such as the ‘Level-up' programme’, Swavalamban Chairs, WE-Lead programme among others. These programmes have shown that targeted support can unlock latent potential in underserved demographics.

The TA had a special focus on integrating gender-sensitive approaches in financial services, enhancing women’s access to credit and entrepreneurship. This programme has played a pivotal role in advancing gender mainstreaming within the financial sector, fostering systemic change that is both sustainable and enduring.

Partnerships with Government can create systemic impact. Under the programme, more than 17 studies and policy papers were developed and disseminated through SIDBI platforms e.g. Micro Finance Congress among others. It has created policy level impact at ground level and amplified UK’s role in building the sector. Government stakeholders value the support and expertise UK has brought to this programme.

Recommendations for future programme:

This programme has helped to design new programmes with an inclusive approach, having gender and inclusion at the core. This has shown us a way to embed gender right at the start having a systematic approach. SRF has a strong focus on integrated financial inclusion strategies, women entrepreneurship, innovation through challenge funds and capacity building of youth.

SIDBI can continue investing in initiatives that bring about further systemic change, policy development and promote entrepreneurship in new-age sectors such as tech and climate. Learnings and experiences of PSIG can be disseminated to government, private sector partners and other DFIs.

How this report was conducted

This report is based on review of existing programme documents (including the programme evaluation and Annual Reviews), and virtual or in-person interviews with key stakeholders including FCDO management team, the fund manager, and investee businesses (see Annex for full list).

Actions following approval of this report

All outstanding programme management tasks were completed before this review. All outstanding transactions have been completed: no further payments are due from FCDO, and final distribution of returns from SF was received by the HM Treasury in April 2025. Audit statements have been received from partners, legal formalities and handover is complete.

We recommend further actions to record and disseminate lessons from SF contained in this report (summarised in Annex 3):

- Work with SIDBI to support other UK/India priorities (e.g. on SMEs, climate investment) for our future programmes on green enterprises, and with other teams in BHC to explore opportunities to use existing relationship with SIDBI. Opportunities for further collaboration within BHC / FCDO:
  - Discuss with PSCMD and PSD Cadre whether there would be appetite to more proactively share lessons from other centrally managed investment programmes and/or support similar funds in FCDO posts that want to move towards an investment partnership approach.
  - Strengthen two-way links between development capital programmes and other TA programmes within BHC. E.g. development capital programmes could identify policy/regulatory factors blocking investment or expansion of high-impact businesses, which could be a focus for dialogue and engagement with GoI.
- Explore how BHC development capital programmes can work together with PSCMD initiatives to promote better impact management in the impact investment sector (e.g. through encouraging other impact funds to adopt the Operating Principles on Impact Management). This could be informed by SF's success in embedding ESG management in SVCL and investee companies.
- Consider whether the social return methodology followed for SF would be useful for assessing impacts of other funds. This could involve support from central FCDO economics / evaluation teams.
- Disseminating lessons
  - Work with PSD cadre to disseminate lessons. Consider a product/event that compares experiences across different country-led development capital programmes.
  - Consider disseminating lessons publicly through relevant networks – e.g. through blog posts, articles or events.
- Recording lessons within FCDO
  - Feedback to central team to update the PrOF Guide on Development Capital (see Annex 3)
  - Ensure all final SF documents are saved on Devtracker including the final logframe and all relevant external documents e.g. evaluation reports
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£65m £30m - Technical Assistance Component £35m non-fiscal CDEL - Investment Component (Samridhi Fund)	£27.3 m – TA disbursed. / £43 m SF returned to FCDO
Timeframe	7 years 2012-2019	13 years 2012-2025
Outcomes	Benefits accruing as a result of investment in enterprises from / a) Employment Income (target by 2020 - £40m) / b) Reduction in cost to poor consumer/ Increase in earnings to poor producers (target by 2020 - £600m)	Generated employment income of £49m* / Reduction in cost to poor consumer/ Increase in earnings to poor producers of £1b[4].
[4] Based on regular monitoring by the fund manager. In addition, the final evaluation figures were extrapolated to reflect the user value attributed to the Fund’s investment in the enterprises.

Overall assessment of programme outcomes, sustainability and VfM

The PSIG programme was based on the theory of change (ToC) that: a) access to finance protects poor households from economic shocks; b) catalytic donor support is needed to expand services to poor geographies; c) microfinance platforms can be leveraged to empower women; and d) there is an unmet need for investment in the poorer regions.

Through its Financial Inclusion component, PSIG reached 13 million; deepened the outreach in underserved regions (PSIG partners showed an annual growth of 26% against the average 10%); catalysed a more positive policy environment for microfinance; helped partners adapt to the “policy shocks” including demonetisation and “margin cap”; and helped industry and state associations (UP and Odisha) become more effective in advocacy, outreach and governance. Its focus was on responsible finance, code of conduct and genuine gender focus. It supported transition of MFIs/NBFCs into SFBs.

The theory of change for the SF was that SF’s investee enterprises would use investments to raise further finance to expand operations, resulting in financial returns for the SF and development outcomes including more jobs, increased earnings of poor people, and reduced cost of goods and services. This would contribute to the overall programme objective of increasing the flow of capital to the eight poorest states in India.

SF achieved its output targets by the end of the programme: supporting 23 businesses, growing their turnover by 300%, and achieving both financial and development returns. The development returns are detailed in the external evaluation conducted in April 2021 and summarised in the 21/22 Annual Review. SF also achieved its direct outcomes as detailed above, within the original budget allocation. However, the fund duration was extended twice to allow sufficient time for investee companies to grow and provide responsible exits and financial returns to investors. This was caused by external factors (demonetisation and covid negatively affected investee operations, and regulatory challenges delayed the exit process) as well as internal factors (challenges with fund manager capacity which delayed the exit process).

Overall, the external endline evaluation calculated the SF’s “social return” at 41% over the 7-year period to 2020, with a projected increase to 67% for the 12-year period with Benefit Cost ratio of 9:1. This is calculated from the total value generated by SF investees over the fund lifetime, including: employee income, investee profits, and user value (reduction in cost of products or services, income benefit, or user satisfaction). NB: the fund’s social return was not included as a log frame target, and we have not been able to find comparable funds that have used this metric – making it difficult to put this result in context.

In addition, SF achieved some longer-term systemic impacts which should be noted, even though they were not reflected in the external evaluation (because they emerged after 2021) and cannot be easily quantified. There is anecdotal evidence that SF contributed to developments in the wider impact investment industry, including an increase in funds targeting challenging sectors or geographies and increased adoption of ESG standards. The Indian Impact Investment Council estimates that the impact investment industry as a whole had a compound annual growth rate of 26% during the period 2010-2019. More directly, SF’s successful lobbying of SEBI to allow more flexibility in fund exit periods is likely to enable other impact investment funds to pursue more responsible exits.

At fund manager level, the approach to ESG assurance that FCDO instigated for the SF has influenced SIDBI and SVCL’s corporate ESG approach. Drawing from their experience with SF, SVCL has launched further SME venture capital funds with the Governments of Maharashtra, Tripura, West Bengal, and Assam; as well as a fund (Ubharte Sitare) for export-oriented enterprises. SVCL is looking at mainstreaming ESG in the new funds. At sector level, some investees had a transformative impact e.g. Online PSB Loans which drove public sector banks to engage with a fintech platform for the first time and unlocked access to loans for micro, small and medium-sized enterprises (MSMEs) and individuals. Other investees successfully lobbied for policy changes e.g. on agricultural exports.

SF played a significant role in transformation of finance companies to large micro-finance institutions and, in two cases, to small finance banks. This means a shift from providing credit-only services to operating as full-fledged banks that provide a wider range of financial services to low-income and underbanked segments of society.

The SF also generated wider benefits for FCDO and the UK, particularly through building a strong relationship with SIDBI: a strategically important organisation given the importance of the SME sector to both Government of India’s priorities, and FCDO’s objectives for the UK/India relationship (e.g. climate and UK growth).

It is important to note that systemic impacts do not necessarily occur organically or as a result of a passive “demonstration effect”: they rely on active influencing. PSIG commissioned a report from sector expert Palladium on investment and technical assistance, which highlights the important role of industry networks and associations in “driving industry conversations, convening relevant stakeholders, [and] facilitating cross-learning". This report also notes that “combining investments along with technical assistance and their auxiliary activities, such as research, monitoring, network building, and the development of market infrastructure is critical”, and that “Investments and TA need to inform one another in bi-directional feedback loops. Fund managers are well positioned to provide input in the technical assistance interventions that aim to achieve changes at market level”. Evidence from the SF supports this view (as noted in the 2024/25 Annual Review). SF was able to draw some funds from SIDBI’s SRF facility to support the fund and investees – e.g. to strengthen compliances and standards, provide sector level policy support, showcase impact etc.

Another key learning is that for a fund of this size, focusing on 10–15 investments across 4–5 sectors could have helped maintain strategic focus and mitigated the exposure to sector volatility. More active engagement between the fund manager and the wider impact investment ecosystem – e.g. to disseminate results and findings – could have increased influence over similar investors/funds.

Finally, even though SF achieved its target outcomes, it is worth considering whether it could have generated even greater systemic impact – for the purpose of informing design of future programmes. Research for this report suggested that if the fund manager had been better resourced, it could have provided more support to investees and enabled them to achieve greater systemic impact, for example, by providing more support on sectoral/ policy matters, or on integration of ESG approaches or on building methodologies for achieving development impact. Also, if the fund manager had been able to allocate more resources to promoting the fund’s results within the impact investment sector, it may have achieved a bigger “demonstration effect” and encouraged more impact investment in the low-income states. Equally, while the need to extend the investment/exit period can be partially ascribed to the external shocks that occurred during the programme, the impact could have been reduced if the fund manager team had been better resourced. This could have generated development impact and financial returns sooner.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
The SF achieved its targets at the outcome level (noted in annual reviews): (i) generation of employment income, (ii) reduction in cost of goods and services to poor consumer, (iii) increase in earnings to poor producers, and (iv) employment generation (including for women). In addition, 10% of the investments (i.e. investments in solar water pumps and solar Engineering Procurement and Construction (EPC) services for rural areas) have contributed towards UK’s ICF commitments and contributed towards reduction in GHG emissions, access to clean energy and mobilization of climate finance. In terms of impact, UK’s capital helped in expansion of enterprises to low-income states, mobilised additional finance for investees (including from the private sector), and enabled enterprises towards scale and sustainability, with some emerging as market leaders to influence the sector’s trajectory.

On the whole, the assumptions in the programme’s Theory of Change did hold during implementation. The SF was able to build a portfolio of companies associated with the eight low-income states that had both potential to scale and generate financial returns, and achieve development impacts. It should be noted that many investees required support/technical assistance alongside equity investment to meet ESG standards and report development impacts. ICAI’s review of the India ODA portfolio noted the importance of technical assistance in development investment programmes as a driver of “value additionality”. In addition, the FCDO programme team’s active management approach was an important success factor (also noted in the ICAI review: “a more active management approach is associated with greater development impact”).

The outcome-level targets for increased employment income, reduction in cost and increase in earnings were achieved. This was verified by the external evaluation in 2021, although the evaluation noted that the ability of investees to reach poorer-than-average people in the SF states was mixed. About half the investees clearly targeted customers who were poorer than the general population. However, for several investees it was not possible to show specific targeting of poorer-than-average consumers (e.g. for clean energy production where energy feeds into the grid and is not targeted at poor consumers, or agricultural service companies working with farmers who are able to generate a surplus).

The Theory of Change, particularly the translation of outcomes into impacts, relied on SF and its investments providing a “demonstration effect” which could help other investors to better understand the risks and benefits of investing in low-income states, and therefore contribute to the impact objective (increasing investment in the low-income states). It is difficult to prove whether this “demonstration effect” actually changed behaviour of other investors. As the evaluation suggested, simply demonstrating success isn’t always sufficient to change behaviour: programmes may need to combine this with active dissemination and influencing. Even so, many other factors could continue to inhibit investment e.g. the low-income states’ poor infrastructure, lack of skilled workforce, state-level policies etc.

As noted above, there are case study examples of SF having other systemic impacts at the level of the fund manager, impact investment sector, and within investee sectors. However, it is possible that investing more time (and funding) to actively disseminate results and influence other market actors could have encouraged more investors to invest in low-income states.

Since the early funds, including SF, the Capital team’s approach has shifted away from geographically-targeted funds to sector-targeted funds. This shift related to broader strategic changes at the time, and was in line with other development actors (e.g. BII stopped state-level targeting around 2021).

There were many changes in the external environment that were unforeseen. PSIG adapted its interventions to respond to changes, for example to leverage digital platforms, deepen business correspondents (BC) network, make financial literacy more effective and support enterprise development. The focus on gender mainstreaming and women’s empowerment is directly related to the ToC. Very often such processes are undervalued, less invested in and in several cases not done at all. The endline evaluation has validated this focus.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output 1,2 and 4 ended in March 2020 and last reporting was done in December 2020 Annual Review. Since then we have only been reporting on Output 3 (Samridhi Fund).

Output Number and Title		Businesses that enable the poor to benefit as producers, skill providers and consumers, are promoted
Output Score		A
Impact weighting (%)		100%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved

3.2	Results of investments in enterprises: a) Number of total sustainable enterprises supported with risk capital /grant funds b) Growth in turnover of these enterprises over the investment period		20-35 / 100%	23 / Combined turnover increased over 300% during the investment period (to March 2021).
3.3	Development and Financial Returns on Capital from invested funds		Gross portfolio return up to 8% / The Fund Manager monitored the development returns by tracking socio-economic development indicators of investee companies. The overall development returns were calculated at the Endline evaluation (March 2021).	Gross return in GBP is 3.1% over the life of the fund. FCDO received 1.26 times our invested capital. / Development returns at March 2021 Endline evaluation included: / • Access to financial services – 5.9 million borrowers / • Access to low cost and quality healthcare – 1.6 million patients / • Access to drinking water – 1.4 million households / • Access to services to farmers – 29,000 farmers / • New employment generated – 22,000 / persons / • Access to skill development training – 125,000 (70% for women)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

SF invested in 23 enterprises, 74% of which were MSMEs. 22% were start-ups, 35% were early stage, and 43% were growth stage. SF was the first investor for 52%, and the second investor for 22%. Combined turnover increased 300% during the investment period to March 2021. Out of the 23 enterprises, 80% succeeded and 20% failed. The investments achieved a gross financial return of 3.1%, and development returns as detailed above.

The FCDO programme team monitored this output during the fund lifetime through regular fund valuation reports. Development returns were analysed in detail in the external evaluation report in March 2021.

Lessons learned through this output, and recommendations for future programming

Overall, these outputs were achieved – although (as noted in the previous section) the original timeline for the fund was extended.

Section A of this report covers many of the key success factors and challenges of the fund, which are also relevant to these outputs. An additional factor contributing to the fund’s financial return was its diversification across sectors. Spreading risk across different sectors and stages of business allowed the fund to achieve a financial return. Having a proportion of relatively lower-risk financial services investees was particularly important (35% investees, 56% of funds invested).

Measuring the fund’s development impacts was challenging. Both at investee and fund manager level, there was limited internal data tracking social/development impact. This is unsurprising given the novelty of the approach – combining financial and development impact targets.

Lessons from SF (both at output and outcome level) have already informed the Managing Public Money document, a standardised document for future investment programmes. As part of programme closure, the team should ensure these lessons are disseminated more widely within FCDO to inform capital investment programmes elsewhere. This should include incorporating lessons into central guidance (e.g. the Development Capital PrOF guide), as well as more targeted sessions with the PSD Cadre and with FCDO teams/posts interested in developing similar programmes. This could include some learning events/products that compare lessons across existing Development Capital programmes and Centrally Managed Programmes. The BHC team could also consider dissemination of lessons within the national and global impact investment ecosystem. This has potential to further increase SF’s “demonstration effect” and to encourage other investors towards opportunities in low-income states.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case
Development Capital Investments
The Samridhi Fund has delivered well on development, ESG and financial results. The VfM on defined parameters is discussed below:
Economy: The main cost drivers for the SF were the fund manager’s fees and expenses. The fee and profit structure was in line with industry standards. In addition, the FCDO team negotiated reductions in the fund manager’s fees as the fund reached exit phase, which improved programme economy. However, as already noted, the fund manager operated with a small team which may have affected its ability to generate additional systemic impact. For future funds, FCDO should explore how best to negotiate terms with the partners (including fees, team strength etc.) and whether in some cases it would be better value for money to deviate from industry standards to enable fund managers to hire larger (or more specialised) teams.

Efficiency: The fund manager invested all funds within the planned timeframe. However, the investment holding and exit periods were extended, partly due to the impact of external shocks on investee companies, and partly due to regulatory challenges during exit. The FCDO team negotiated a reduction in the fund manager’s fees during the exit period to incentivise efficient exit. [The portfolio has been able to return 1.26 times our capital on the gross basis generating a gross return in GBP of 3.1% over the life of the fund.]

Effectiveness: SF achieved its target development outcomes by 2021. The independent impact evaluation conducted in March 2021 calculated an overall 41% social return on investment, with a benefit:cost ratio of 9:1. SF also achieved its financial objectives: returning 1.26x FCDO capital; and enabling investee companies to mobilise 15x more capital after SF investment.

In addition, the SF contributed to systemic impacts at the impact investment industry level, sector level, and within SVCL/SIDBI. These are not quantifiable, but also contribute to the Fund’s overall effectiveness and value for money.

Equity: 35% SF investee companies had women as promoters or in leadership roles. SF's development impact targets included equity targets, including jobs created by investee companies (20% of 14,000 were women) and individuals reached with skills training (70% of 125,000 reached were women). Some investee companies had a specific focus on gender equality e.g. Caspian Debt adopted gender-lens investment principles and was selected as a 2X flagship fund.

Financial Inclusion

PSIG had created assets on SIDBI’s books in the form of loans, guarantees and retail lending. This allowed the MFIs to raise funds from the market and scale up their operations in underserved areas. The TA component has demonstrated systemic impact and unlocked state resources for scale up. The output satisfies all of the VFM parameters and on gender. SRF used the residual assets to continue with TA activities which benefitted both the Samridhi and NEEV funds and created much wider impact as summarised above. The vehicle has had a sustained focus on gender, credit plus services and support for women enterprises.

In addition, about three policy level studies to assist Government of India were undertaken. These were mainly in agriculture sector, waste management from biomining and recommendations for reduction in Diesel Generation emissions. The recommendations from these studies have been adopted by the govt and cascaded to different departments and states as appropriate.

As per the Endline assessment of TA, a programme level calculation of the cost benefit ratio based on the monetisation of estimated and/or imputed benefits both from economic and social uses of funds indicates high cost-benefit ratio of 1:11. PSIG cost-effectiveness ratios for reaching low-income households at small, if not minuscule proportions of GNI per capita suggest a high level of efficiency for the programme.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The whole PSIG programme (including the TA component and the SF) was rated at a higher risk for its first four years of operation 2012-2016, then reduced to “moderate” risk for the remaining nine years until closure in 2025. The higher risk at outset reflects the fact that the SF was FCDO’s first equity investment programme, requiring the FCDO team to build and maintain new specialist capabilities in investment management, as well as accessing technical expertise (legal, commercial, financial) from FCDO HQ. Although the fund manager was an established public financial institution, SF was the first time they had created a fund to invest in poor states. Finally, the fund was designed to invest in the eight poorest states which are challenging places to invest. Together, these factors led to elevated delivery, financial/fiduciary, and reputational risks.

Towards the end of the commitment period, the risk reduced to “moderate”. By this point, the immediate delivery risk had reduced (i.e. the fund manager was able to find companies in which to invest the funds), SVCL had demonstrated its capability as a fund manager, and fund governance was functioning effectively to mitigate risks (e.g. through FCDO’s seat on the investment committee and fund manager payment structure).

Three major external shocks occurred during the investment holding period which affected the programme’s risk profile. These were:
- Demonetisation (2016)
- Introduction of the GST (2017)
- COVID (2020)
In response to these events, individual risk parameters were adjusted in their respective years. Additionally, a new risk factor was introduced in 2021 specifically due to the prolonged effects of COVID-19. Despite these disruptions, the overall risk level of the programme remained “moderate” throughout the period.

The fund manager worked with the investment committee and investee companies to mitigate the impact of these shocks. On the whole, this was successful – investee companies valued the fund manager’s support during this period. The fund’s commitment period was extended by one year as a result of the disruption caused by demonetisation and GST, and the fund tenor was extended till April 2025 to allow investees to recover from the impact of covid and generate responsible exits. The value of the fund fell during demonetisation and covid, and while it did recover following the initial shock, SVCL thought these shocks could still have negatively impacted the final sale value of the companies at exit. For the extension to the fund end date, the UK and other SF investors negotiated terms with SVCL to safeguard investors’ interests, including a reduced management fee and recommendations on improved governance and showcasing impact. FCDO should ensure it captures lessons from how Samridhi responded to external shocks to support planning for future shocks across current funds.

Programme risk remained “moderate” until the fund had exited all its investments. The exit period brought new legal/regulatory risks, [which were exacerbated by resourcing challenges at SVCL.] Exiting from financial services investments was particularly challenging because it required approval from two regulators: SEBI and the Reserve Bank of India (RBI). The fund manager and FCDO successfully lobbied SEBI to extend the permitted time for the exit period by one year, which enabled SF to achieve more responsible, better value-for-money exits.

Financial risks were mitigated through SVCL’s robust internal policies and oversight of investees; strong governance of the fund, including through the investment committee; accountability of the fund towards the regulator, with periodic mandatory disclosures; and close engagement between the BHC team and FCDO central finance teams throughout the fund lifecycle. As part of assurance process, the programme team also conducted an independent financial review of the fund which did not highlight any red flags.

The residual risk after the mitigation measures remains within the tolerable limit of FCDO’s risk appetite.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

SVCL was the fund manager for the SF. SVCL was chosen because:
- SIDBI and SVCL had experience and networks throughout the poorest states that the SF focussed
- As a public sector financial institution, SIDBI and SVCL had strong financial management systems and capacity to deliver

However, the SF was the first time SVCL had managed a fund with investment from a foreign government, and the first time they had managed a fund focussed specifically on poor states. Including ESG standards as a core part of the fund’s design was also new for SVCL.

On the whole, SVCL was an effective fund manager, delivering the target financial returns and development impacts, despite external shocks that threatened both. As Government of India institutions, SVCL and SIDBI were better able to help resolve some of the legal/regulatory challenges faced during the fund’s lifetime (compared to a private fund manager); they also helped some investees to access state governments to resolve specific challenges. Working with a Government of India institution offered alignment of objectives, greater potential for scale and systemic impact: e.g. during the SF, FCDO worked with SVCL to incorporate ESG factors into its management approach, which has been rolled out more widely across SVCL and SIDBI funds. SIDBI and SVCL’s profile and credibility is likely to have been a key factor in securing co-investment from insurance companies, and could have helped investee companies to secure follow-on investments. Indeed, some investees noted the long process for making investments (up to 1.5 years from first engagement to funds being released): we think that was acceptable for an impact equity fund, as it allowed sufficient due diligence – which should also have conferred credibility on the investees and made it easier for them to secure follow-on investment.

Finally, the partnership also brought wider benefits for the UK. FCDO built a strong relationship with SVCL and its parent organisation SIDBI, thanks to the co-investment model and sense of partnership. This has proved valuable since, creating opportunities for further partnerships. As mentioned in the ICAI review of the India Portfolio; by working with government institutions, relatively small investments have the capability to influence investment practices of larger financial institutions. It also enables a systemic approach to addressing wider barriers to investment, e.g. policy/regulatory challenges. As already noted in this report, the SF generated systemic impacts at the fund manager level, particularly the mainstreaming of ESG assurance across SIDBI/SVCL, and its future investment funds in partnership with state governments (which were informed by their experience with SF). FCDO also continues to benefit from the relationship it built with SIDBI/SVCL through the SF.

[There were challenges to working with SVCL. Although staffing was adequate at the start, later in the investment and exit period the SVCL team was under resourced and this was not resolved despite the FCDO programme team escalating the concern. The FCDO programme team have reflected that for future fund management relationships, FCDO should consider including key staffing requirements into the management contract. ]

Otherwise, although there were some differences in approach between SVCL and FCDO, the design of the fund governance allowed the FCDO team to protect UK objectives. For example, during the exit period, FCDO wanted to exit investments by April 2025 and to do so responsibly (i.e. through sale to an investor that would support the long-term growth and impact of the investee companies) - even though the fund could have made larger financial returns by holding onto some investee companies for longer. FCDO was able to maintain focus on timely, responsible exits through FCDO’s seat on the SF Investment Committe, and by reducing SVCL’s management fee once the fund entered the exit period. FCDO also included financial incentives for SVCL to achieve ESG targets across the portfolio, which were effective.

SVCL was an important driver of the SF’s overall value for money, specifically the economy component (via SVCL’s management fees) and efficiency component (via SVCL’s ability to deliver.) SVCL’s management fees were structured to maximise economy and align SVCL’s incentives with FCDO objectives. [FCDO paid SVCL up to 1.5% management fee (this is in line with market standards).] As mentioned above, FCDO also included in the fee structure incentives to achieve ESG targets, and a reduction in management fee during the exit period to incentivise the team to complete exits by the desired date. During the final five years of the SF, the FCDO team commissioned an independent financial audit review of the fund manager’s fees and expenses, which did not identify any issues.

The SF programme ran for thirteen years, during which there were several staff changes in the FCDO team. Strong information management and thorough handovers were essential to maintain consistent programme leadership.

For the Financial Inclusion component, quarterly/bi-annual Project Steering Committee meetings helped review the progress and set strategic direction. SIDBI as a partner continuously reviewed ongoing activities during the term of the programme which helped in refining the design and delivery and scale up of interventions.

The SRF team – five full time project staff supported by three SIDBI core staff – led by the General Manager, Promotion & Development (P&D) Department, SIDBI. This has ensured coherence and alignment with SIDBI’s institutional mandate.

Programme-level approach to monitoring and evaluation

SIDBI is a public sector financial institution with strong financial management systems. The SIDBI team conducted periodic reviews of the projects against expected performance and spend. It achieved substantial savings by closing poorly performing activities/components of the programme and consolidating others.

To maintain effective oversight of the SF’s financial performance and development impact, the FCDO team received: quarterly unaudited accounts, half-yearly independent fund valuation reports; and annual audited accounts. The team also commissioned specialist audits including the financial audit mentioned above, and audits of investee ESG performance at baseline, midline and endline.

The Fund Manager supported investee companies to monitor and report their impact against the development indicators included in the SF log frame. The FCDO team reported these in Annual Reviews. The team also conducted field visits to investee companies.

The FCDO team commissioned an external evaluation of the SF, which produced its endline report in March 2021 and was published along with a management response from FCDO. Both the FCDO team and fund manager judged that the evaluation had not fully captured the Fund’s systemic impacts on the investment landscape in the focus states, or within the investee sectors. This is partly due to the timing of the evaluation, which was completed before the fund exit period, before many of the systemic benefits had arisen. However, it was also limited by the capability of the evaluation team to assess growth of the impact investment sector, and to assess poverty levels. As impact investment approaches have become more established in India, this capability should be more prevalent now.

However it is also worth noting other challenges to evaluating the SF. It is challenging to find robust data on state-level investment flows, which made it difficult to assess change over the lifetime of the fund. Also, the evaluation calculated the fund’s social return on investment. While this gives a useful single indicator of its total return, its utility is limited because few other funds (within FCDO or externally) have calculated this metric – making it difficult to contextualise or interpret this result. It is worth considering whether this is a useful approach for future evaluations of capital funds. In addition, the calculation involves various assumptions – although these are clearly explained in the evaluation report.

Date of last narrative financial report	June 2025	Date of last audited annual statement	March 2025

Annex 1: stakeholders consulted for PCR

BHC India
- Development Director
- Climate Team
- Capital Team
- SRO, PRO for Samridhi Fund

Fund Manager
- SIDBI
- SVCL

SF Investee Companies
- RiteWater
- Online PSB Loans

Annex 2: References

- PSIG Log Frame
- PSIG Annual Reviews
- SF Evaluation Report and Management Response
- BHC India Capital Funds Flipbook
- ICAI Review of FCDO India Portfolio (2023): https://icai.independent.gov.uk/html-version/uk-aid-to-india-review/#section-6
- FCDO/Palladium report: Investments and technical assistance together can strengthen India’s march to achieve the SDGs

Annex 3: Lessons learnt - Recommended updates to DevCap PrOF guides

Selecting the fund manager
- Consider the fund manager’s potential to support systemic influence and any wider benefits to the UK, in addition to their ability to deliver during the lifetime of the fund. E.g. in India, public investment banks and financial institutions have greater scale and capacity to influence than private fund managers.
- Consider trade-offs between the fund manager’s existing capability, and the additionality of the FCDO programme (e.g. in building the manager’s capacity or raising ESG standards).

Governance and delivery
- FCDO should plan an active role in engaging with Fund Managers for investments and policy
- Consider whether the investment fund would benefit from access to additional technical assistance, either at the fund manager level (e.g. to build their capacity), or for investee companies (e.g. to support them to implement ESG standards or create policy/sectoral impact). Also consider how investment programmes can inform or support FCDO’s wider influencing work (e.g. has the investment programme helped FCDO to build relationships with key stakeholders that could be useful for achieving other FCDO objectives? Can the investment programme inform or support FCDO’s wider technical assistance activities?)
- Consider how to avoid crowding-out private investment
- Start planning the exit period early

Fund manager incentives
- Consider how the fund manager’s remuneration could be structured to align incentives with FCDO’s objectives. E.g. a bonus rate for achieving ESG standards across the portfolio; reducing management fees during the exit period.
- Include clauses in the legal agreement with the fund manager to safeguard any factors that would be essential to the fund’s success. E.g. mandating a minimum team size or level of experience, key person clauses, level of experience

FCDO team / management
- FCDO team should have sufficient capability to fulfil its role as an active investor
- FCDO team should ensure they can manage the investment programme consistently throughout its lifetime, which can extend over 10 years. The team should have robust information management systems and record all key agreements with the fund manager. Where staff in key roles change, there should be thorough handovers.
- FCDO team must be able to access support from central financial accounting, commercial and legal teams.

External evaluation
- Consider conducting the final external evaluation after the exit period, to capture longer-term systemic impacts
- Ensure evaluators have capability to assess both the financial and development impacts of the programme
- Seek advice from Economic or Evaluation Advisers on which metrics to use for fund-level impact. Consider metrics that can be compared across funds or with external benchmarks, e.g. Social Return on Investment.

Systemic impacts
- Ensure the fund manager and/or FCDO team plans how to maximise the potential for systemic impacts from the fund’s activities. This could include:
  - Using industry networks and associations to communicate results/learnings and influence other actors to adopt or scale-up innovations
  - Ensuring that learnings from the investment fund can inform technical assistance activities (e.g. a fund could identify issues with specific regulations, which TA could help to reform), and vice-versa (e.g. analysis from TA projects could inform investment strategies).
- Ensure the fund manager and/or FCDO team have enough team resources to deliver this.
- Where setting targets for systemic impact (e.g. changes in volumes of investment to underinvested regions/sectors), consider what data sources are available and feasibility of measurement.
- Consider developing a standardised list of KPIs and outputs for a general development capital investment programme, including indicators of systemic impact. This would support the creation of an initial log frame and help align expectations from the outset.