## Annual Review Template

Title: Joint Global Health Trials Initiative
Programme Value £ (full life): £ 75,154,696.21 / Spend to Date: £70,510,568.99		Review date: Sep 2025
Programme Code: 201267-106/107	AMP start date: 19/07/2010	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A+	A	A	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logframe

A. SUMMARY AND OVERVIEW

Description of programme

The Joint Global Health Trials scheme (JGHT) is a joint funder initiative between FCDO, Wellcome Trust, the Medical Research Council (MRC) and the Department of Health and Social Care (DHSC). The Initiative was established in 2010 to address the need for large scale clinical trials in global health, supporting the best proposals to generate new knowledge about interventions that contribute to the improvement of health in developing countries. The scheme focuses on late-stage clinical and health intervention trials, evaluating efficacy and effectiveness. While the scheme is aimed at funding Randomised Controlled Trials (RCTs), other types of methodologies (such as economic evaluations and social science research) are encouraged alongside the RCT to explore implementation and operational issues. The scope of the scheme includes, but is not limited to, behavioural interventions, complex interventions, disease management, drugs, vaccines and hygiene and diagnostic strategies. The main health areas of focus are infectious diseases (including HIV, malaria, and TB), SRHR, maternal and newborn health, and child health.

The funding mechanism improved funding decision processes by establishing a bespoke group of experts who consider clinical trial applications in competition; increases the overall pool of funding dedicated to clinical trials by leveraging funding from a number of sources for research; and helps share the risk (both financial and reputational) between funders of supporting important but also likely to be high-risk clinical trials. Priority is given to proposals that are likely to produce implementable results and that are designed to address the major causes of mortality or morbidity in low- and middle-income countries.

The programme funds both full grants and development grants and has funded 149 grants in total since inception. Although the main programme finished funding new trials in 2020, one new trial (on the R21 malaria vaccine) was funded through the scheme in 2023 via the MRC’s Applied Global Health Research Board. Given the ongoing demand for large scale definitive clinical trials FCDO, MRC and NHIR are in discussions around developing a successor scheme.

Summary supporting narrative for the overall score in this review

This year the scheme has met or moderately exceeded expectations across all outputs and has scored an A. The scheme has made more than 120 awards and is continuing to deliver on its original aim to generate new knowledge to inform the delivery of health interventions and increase the actionable evidence base available to decision makers. Throughout the reporting period the scheme has funded a strong portfolio of trials in global health which are delivering results to influence and change policy.

Highlights from 2024/25 include:

- Very promising early results from a major trial of mass vaccination with the R21 malaria vaccine led by the London School of Hygiene and Tropical Medicine. This found that vaccinating all age groups (rather than just children) could have a huge impact with a possible 70% lower odds of infection across all ages and a higher effect in children under five (82% lower odds). These are potentially groundbreaking results suggesting that vaccinating all age groups leads to a substantial ‘mass effect’ leading to overall decreased malaria transmission. The results were presented at a the EDCTP international conference in Kigali in May 2025 and the team plan to present further results at the ASTMH annual meeting in Toronto in November.
- Results from a trial led by London School of Hygiene and Tropical Medicine informed the Ugandan governments updated Reproductive Maternal Newborn Child and Adolescent Health (RMNCAH) plan. Updated in October 2024, the plan includes the procurement of Kangaroo Mother Care (KMC) beds for all Emergency Obstetric and Newborn Care facilities. This recognises results on the impact of using KMC before stabilisation on low-birth-weight neonates in Africa, finding it more cost-effective than standard care, despite having no effect on neonatal mortality. The funding case for the care package in Uganda, which included support or immediate KMC, estimated that scale-up would avert 46,300 neonatal deaths by 2030.
- WHO updated guidelines on tuberculosis in September 2024 recognised findings from a trial led by Stellenbosch University which demonstrated the efficacy of preventive therapy in child and adolescent contacts of people living with multidrug-resistant (MDR) TB. Following a rapid communication, the updated guidelines recommend the 6-month regiment of levofloxacin be used as TB preventative therapy (TBT) for contracts of drug-resistant TB. The regimen has been adopted by at least 15 countries and the key trial publication reported in December 2024. In partnership with UNITAID, the novel MDR TPT is being scaled-up in seven high-burden countries, with the trial estimating that 5,620 cases in children could be prevented annually, saving 3,600 lives.
- A Randomized Clinical Trial into the immunogenicity of combined pertussis-containing vaccine (Tdap) for HIV-infected pregnant women and their newborns had key results published in January 2025. The trial found TdaP was safe and immunogenic in pregnant women living with HIV and their infants. The clinical significance of this finding remains unclear due to the absence of a correlate of protection against pertussis disease, but it is the only study of its kind conducted on women living with HIV and will be key to the SAGE discussions of the evidence for pertussis vaccines.
Major lessons and recommendations for the year ahead

Major lessons
The JGHT provides a single coherent funding route, reducing the administrative workload and sharing the risk of funding clinical trials. The scheme stopped making new awards in 2020 and has left a significant gap in the landscape for funding large scale definitive clinical trials. Typically, it is hard to get trial funding from individual funders, because the risk for any one funder is too great. Moreover, COVID19 highlighted the importance of establishing clinical trial networks in advance to respond to emerging threats. The recent cuts in US funding for global health research have further highlighted the risks of research groups relying on a single source of funding for large scale clinical trials.

Discussions around a possible successor scheme to the JGHT started during 2024 but were paused due to the 2025 Spending Review and then the UK announcement of a reduction in ODA from 0.5% to 0.3% of GNI. Following the conclusion of the SR, FCDO, DHSC, MRC and Wellcome have recently restarted discussions on a new scheme as part of efforts to strengthen alignment and coherence of ODA R&D funding for global health. Any new scheme will inevitably be dependent on long term budget availability.

In 2025, MRC undertook an evaluation of the Economic Impact of MRC funded research, but with only limited reference to global health research. As the JGHT scheme moves towards closure there is an opportunity to replicate this exercise and look at the potential longer term economic impacts of funded trials.

Summary of recommendations
1. MRC, FCDO, and DHSC to agree on a new approach to funding clinical trials (By April 2026)
2. As programme moves towards completion, MRC and FCDO to develop a comprehensive, aligned approach for disaggregating data across the programme lifespan to support final reporting, including a focus on work in specific thematic areas of health and vulnerable populations (By February 2026)
3. MRC to provide stronger capacity strengthening case studies. FCDO to support MRC develop a template for examples. (By May 2026)
4. MRC to consider evaluating the economic impact of JGHT funded programmes, alongside other co-funded programmes (By August 2026)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change is outlined below. The inputs continue to be delivered, with regular monitoring and reporting processes to ensure the research remains relevant to LMIC priorities; exemplified by journals articles having a geographic coverage predominantly located in LMICs (Output 3). The outputs on evidence creation and dissemination continue to contribute to growing the body of evidence, and the assertions which underpin them remain true.

The theory of change remains relevant and valid, and the scheme continues to provide good evidence of impact as demonstrated by a steady pipeline of impact case studies. The inputs continue to be delivered, with regular monitoring and reporting processes to ensure the research remains relevant to LMIC priorities; exemplified by journals articles having a geographic coverage predominantly located in LMICs (Output 3). The outputs on evidence creation and dissemination continue to contribute to growing the body of evidence, and the assertions which underpin them remain true. There have been no significant changes since the previous annual review. The programmes longevity has enabled an ability to track impact across a significant period of time to inform greater confidence in the continued relevance of the theory of change. This includes the relevance of research to LMICs, with Table 1 (below) mapping the location of LMIC research institutions represented in JGHT journal articles published in 2024, an indicator of location of work, with 60% of institutions represented in journal articles coming from LMICs.

Active Programmes in Country
1
19

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress against output and outcome indicators suggests the programme is delivering on expected work and achieving intended impacts, providing robust new knowledge on which health interventions work or do not work. During this reporting period seven new case studies were provided, beyond the milestone of three, of which, four were updates of earlier case studies and three were cases of new results, demonstrating how earlier funded research is continuing to change global policy and practice. For example, previous reviews highlighted the findings of the SHINE trial published in 2022, which evidenced that four months of antituberculosis treatment was noninferior to 6 months of treatment in children with drug-susceptible, non-severe, smear-negative tuberculosis. Most recently, the trial informed WHO guidelines from 2022, which led to the American Thoracic Society, U.S. Centers for Disease Control and Prevention, European Respiratory Society, and Infectious Diseases Society of America to update their clinical practice guidelines for TB treatment in children and adults in 2025.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue. Although now closed to new applications, programme continuation ensures that trials are completed and results reported, alongside enabling the monitoring of impacts from closed trials. The programme offers strong value for money through the production of new high-quality knowledge on the effectiveness of health interventions which continue to influence global policy. It is standard experience for clinical trials already funded to take one or two years to start after the funding decision and for scientific information to emerge only in the final stages of studies which can be up to 5 years in duration. Based on the analysis of outcome and output achievement to date, the programme represents good value for money for FCDO and has already achieved tangible outcomes and impacts by generating new knowledge about health interventions which will contribute to improving health in LMICs.

## C. DETAILED OUTPUT SCORING

Output Title	Trials which generate new knowledge about health interventions in developing countries.
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of full trials completed and reporting final results.	68 (cumulative)	Met expectations: 69
1.2 Number of development awards reporting main findings	67	Met expectations: 67

Briefly describe the output’s activities and provide supporting narrative for the score.

Output met expectations. Since the last review, six full trials and nine development grants have completed. As the programme moves into the final two years, 14 of the 82 funded full trials remain ongoing, whilst all 67 development grants having completed work; the scheme has funded 149 grants in total. The findings of JGHT funded research are often published in the highest-ranking medical journals highlighting the quality and robustness of the evidence produced.

Further examples of new evidence produced includes:

- Very promising early results from a major trial of mass vaccination with the R21/MatrixM malaria vaccine in The Gambia and Burkina Faso led by the London School of Hygiene and Tropical Medicine. The results were presented at a major international conference in Kigali in May 2025 and showed that vaccinating all age groups (rather than just children) could have a huge impact with a possible 70% lower odds of infection across all ages and a higher effect in children under five (82% lower odds). These are potentially groundbreaking results suggesting that vaccinating all age groups leads to a ‘mass effect’ leading to overall decreased malaria transmission. The team plan to present these findings at the ASTMH conference in Toronto in November.
- The Gastroenteritis: rehydration for children with severe acute malnutrition (GASTRO-SAM) trial found no difference in using intravenous rehydration strategies, compared to oral treatment, on the mortality at 96 hours of children with severe acute malnutrition (SAM) and gastroenteritis. Published in June 2025, the study demonstrated that severely malnourished children can be safely rehydrated intravenously, disproving international recommendations advising against this. The findings are expected to support evidence-based updates to global guidance in November 2025.
- Findings from a feasibility trial on the impact of prophylactic continuous positive air pressure (CPAP) in the delivery on neonates weighing less than 1500g in a low-resource setting changed national policy in Uganda, contributing to the recommendation of CPAP and delivery room CPAP in the Ugandan National Protocols for Care of the Small and Sick Newborn in September 2023. Findings are yet to be published.
- Funding high-risk clinical trials entail that negative results are also found: PRODIGITAL-D is a cluster randomised controlled trial (RCT) for late life depression in socioeconomically deprived areas of São Paulo. A second publication in October 2024 demonstrated that digital messaging psychosocial intervention did not help improve subthreshold depression symptoms amongst older adults, following a positive result published in March 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s review increased the number of main trials expected to complete from 45 to 68, with the programme continuing to perform ahead of target, we recommend updating the full trials milestone for the final year to 75, reflecting the 7 grants remaining to complete in the 12 months following September 2025. The implications of the grants completing earlier is in enabling outcomes and impacts from trials to be more accurately recorded within the programme work dates.

New recommendations
FCDO to update milestones and reduce the weighting slightly for this output from 50% to 40% (or lower) to reflect that the scheme is now no longer making new awards and to enable an increase in the weighting on dissemination.

Output Title	Rate of trials complying with WHO Joint Statement on trial transparency and registered in the public domain.
Output number:		2	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Percentage of trials complying with WHO Joint Statement on trial transparency and registered in the public domain. / 2.2. Including percentage who published within 2 years of trial completion.	100% of trials are registered in the public domain / At least 70% of completed trials have published their main result within 2 years	Met expectations: 100% of trials are registered in the public domain / Exceeded expectations: 81% of completed full trials have published their main result within 2 years

Briefly describe the output’s activities and provide supporting narrative for the score.
This output moderately exceeded expectations. The MRC requires all funded studies to make the study protocol, analysis plan and all relevant statistical analyses publicly available prior to the start of the study. For clinical trials, the protocol (or information about where to find the protocol) must be added to the registry entry within 12 months of the trial start. The MRC mandates that all study results (whether positive or negative) must be published or made publicly available within 24 months of the end of the study or trial. In 2025 81% of JGHT trials published their main result within 2 years which is just above the average of 65-70% for all MRC studies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A.

Output Title	Case studies or examples that show how trials have led to capacity strengthening at the institutional or individual level.
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Case studies showing how trials have led to capacity strengthening at the institutional or individual level.	At least two case studies on individual or institutional level capacity strengthening per year	Met. Two strong case studies provided

Briefly describe the output’s activities and provide supporting narrative for the score.

This output met expectations. Although capacity building is not an explicit objective for the programme, the scheme is continuing to use and strengthen existing research capacity in the South and strengthening partnerships with the UK universities. The mid term external review in 2019 found that 23% of all awards funded were led from institutions based in the south. The review also found that 65% of PIs from closed full-trials reported that the research had enhanced trial capacity at the trial sites, including through training in trial methodology and data management. The programme has continued its strong performance in building capacity in the Global South, whilst demonstrating UK-leadership in global health research in partnership with UK universities.

Two case studies demonstrate individual capacity strengthening. The IMPROVE and IMPROVE-2 large multi-centre multi-country trial, led by LSTM, built up a successful team whose members continue conducting trials in pregnancy gaining valuable experience, and the MICA trial team at the Makerere University Johns Hopkins University (MUJHU) are developing a pathway to policy for maternal vaccines in partnership with Africa CDC, the African Medicines Agency, and the Gates foundation.

JGHT trials have also developed institutional capacity. The ACT South Asia trial strengthened Nepal’s research environment significantly. Nepal has resultantly become a credible location for producing high-quality global health trials, having gained advanced infrastructure. Similarly, the EFFECT trial has strengthened trial sites and systems in South Africa and Tanzania.

Describe any changes to this output during the past year, and any planned changes as a result of this review
None

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Past reviews have commented on the need to strengthen the quality of case studies. There is an opportunity for the research groups funded through the JGHT to bid for funding through FCDO’s new impact fund which could help to strengthen the quality of capacity building case studies.

New recommendations
1. MRC to provide stronger capacity strengthening case studies. FCDO to support MRC develop a template for examples. (By May 2026)
2. MRC (with support from FCDO) to apply for FCDO impact funding opportunities. (By November 2025)
3. MRC website to consider including more impact examples from their global health work on their website. (By August 2026)

Output Title	Research findings communicated to academics and policy makers
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No.

Indicator(s)	Milestone(s) for this review	Progress
4.1. Number of research articles in high-impact peer-reviewed journals disaggregated by: % Open Access; % LMIC lead author; % International lead author	At least 1,300 publications (cumulative) / 95% Open Access, 30% LMIC-based authors, 45% International authors	Met expectations. / 1,344 cumulative publications / 90% Open Access (including bronze) / 55.2% LMIC-based authors / 96.2% International authors
4.2 Number of output and engagement activities per year for a non-publication dissemination	800+ engagement activities	Exceeded. 1,393 cumulative engagement activities
4.3. Number of databases produced by the trials. (cumulative)	65 databases	Exceeded. 93 databases.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output moderately exceeded expectations. The programme continues to perform strongly against output 4. As the majority of programmes have completed it is necessary that research findings are communicated and that policy uptake is prioritised to ensure that the programme outcomes are achieved. MRC have changed the tool to extract data on publications, informing a reduction to 1,344 cumulative articles in 2024, compared with 1,492 reported for 2023, this has also impacted the Open Access figure. In 2024 alone, JGHT published 85 journal articles, 11 reviews, and an editorial. The 97 publications represent research in 66 different countries, 60% of which were LMICs.

For output 4.2, JGHT continued to exceed expectations in the number of cumulative engagement activities delivered within the year, with 63 additional activities in 2024. Output 4.3 reflects 14 new databases produced in 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Recommend increasing the weighting on this output from 20 to 30%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

MRC continues to make efforts to improve the accurate tracking of research outputs, exemplified by the changes reported.

New recommendations

1. FCDO and MRC to review milestones before the programme enters its final year in 26/27.
2. FCDO to establish what tool will be used to extract publication data.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
The main cost drivers include the people required to carry out the research; their travel and subsistence, equipment and supplies, and the costs of data collection and analysis (and making data open access, although this cost is recouped when considering effectiveness /reach and equity).

All grantees are subject to the audit and management procedures of UK Research and Innovation (UKRI), and the MRC has robust VfM guidance during the peer review and panel stages. The programme is filling a critical gap in the world's research landscape and funding high-quality RCTs that will produce reliable evidence to guide health care in low- and middle-income countries across a wide range of priority health areas. This programme continues to perform well compared to the original VfM proposition in the business case.

The MRC attempts to reduce unit costs within trials whenever possible and keeps track of the costs and VfM of research initiatives throughout their lifespans. When deciding whether to grant costed extensions, the MRC takes into consideration VfM . Below is a summary of VfM factors to consider.

It is recommended the MRC provide further up to date examples of how the scheme leverages value for money. This was also a recommendation from last years report; however, no case studies were provided.

VfM performance compared to the original VfM proposition in the business case

	VfM Examples
Economy	Procurement: FCDO is leveraging funding from the other funders and using partners’ existing tried and tested mechanisms to ensure that the costs of managing applications and peer review processes to award funding are minimized.
Efficiency	Input maximisation: HMG departments working together minimises overlap and duplication and ensures relevant skills from each partner are leveraged to maximise the productivity of funds spent. / Effective dissemination strategy: including by use of leveraging new ways to encourage research uptake (including through blogs). / Cost-effectiveness: All grants are subject to value for money reviews and the funders carefully review budgets, making appropriate savings where costs are not considered appropriate. All projects receiving funding are required to report on outputs and impact annually and after the end of the project
Effectiveness	Quality of research: The Expert Panel feedback to individual applicants ensures that bidders strengthen proposals before they are funded, and for those that do not receive funding they are able to strengthen future applications. The portfolio of trials includes a range of different partners investigating issues across all areas relevant to health of the poorest. / Leveraging support: The partnership has performed well in terms of crowding in additional resources, both from other departments and from other funders (eg EDCTP).
Equity	Gender: Many of the research proposals promote equity through helping the most marginalised populations, such as women and girls. This includes research on maternal and newborn care and sexual health and reproductive rights. / LMIC participation: At least 60% of the studies involve institutions from LMICs, further strengthening the equity of fund distribution across the portfolio of studies.

Assessment of whether the programme continues to represent value for money
The programme represents good value for money through the joint model that leverages funding between FCDO, Wellcome, and MRC to improve efficiency and deliver greater output. Clinical trials are costly and high-risk in providing positive research outcomes, however the MRC’s diligence on cost effectiveness, including once a trial has started receiving funding, means that the research risk is offset by limiting the financial costs. However, the MRC could do more to provide evidence on the return on investment from global health research overall. The MRC website includes a useful document on the economic impact of MRC funded research but this did not include any global health examples. It is recommended that the MRC consider providing more public examples on the impact of their global work.

E: RISK

Overview of risk management

The overall risk of the programme is rated as Moderate during the reporting period. Although this is a high value programme compared to other programmes in the team’s portfolio, the sharing of risk with other funders, the diversification of risk across multiple projects, together with the MRC’s oversight means we are confident that the risks are mitigated and limited. MRC provides a biannual update of the overall programme portfolio of work, outlining overall progress of each project. Through the update, MRC retains a clear and constant dialogue with the FCDO that establishes any changes in risk for each specific project, alongside any expected actions or future action to be taken.

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Moderate	Moderate	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context – Major
We have increased the risk rating from Moderate to Major for two reasons. First the overall funding environment for global health R&D has changed significantly since the last review. Although there is no expectation that JGHT trials are directly affected, some partners received funding from the US and could be indirectly impacted. In addition, the UK ODA reductions may also have secondary impacts by limiting the extent to which funders can consider cost extensions to ongoing trials. Second, the MRC is undergoing a major strategy review which could impact their ability to support applied research in future. We are in close discussions with the MRC on the strategy process and any implications for the final stages of the JGHT scheme.

Policy and Programme Delivery – Moderate
As the programme progresses, there is an increased risk of trials needing cost extensions to ensure that the full body of research is completed. The cause of any such extensions does range between different projects following delays caused by internal or external factors. The MRC has developed clear procedures for reviewing each extension request on a case-by-case basis, including a formal endorsement by an independent Trial Steering Committee, with a business case submitted and approved at two levels within the MRC. The nature of clinical trials means that such risks are constant and unpredictable, having strong institutional approaches means MRC has developed effective systems for managing and overseeing these risks.

Public Service, Delivery, and Operations – Moderate - The MRC has in place a range of policies and procedures to maintain quality in the research it funds and to ensure an effective and efficient use of public funds. MRC are required to report spend to Treasury. MRC has a comprehensive grant management system which minimises the risk of fraud from any research grant. MRC only awards grants to institutions recognised as bona-fide research institutions and provided those institutions and award-holders are willing to adhere to MRC terms and conditions.

People – Minor - The MRC has good procedures in place to promote equity across programme activities.

Safeguarding – Moderate – Safeguarding of research participants is inevitably an issue in clinical trial research. The MRC undertakes regular due diligence and acts quickly and promptly on allegations of research misconduct.

Financial and Fiduciary – Moderate - The MRC undertakes regular due diligence and acts quickly and promptly on allegations of fraud/misuse. Overseas research organisations awarded funding through the JGHT scheme are subject to a jointly agreed finance monitoring process. The level of monitoring is proportionate to the financial risk posed to the joint funders. Determining factors include size of grant, duration of grant, existing relationship of funders with the research organisation and corruption index of the country in which the research organisation is based. For instance, research organisations which are deemed high risk are required to submit quarterly spend reports to UKRI. Underspends are closely monitored and if significant MRC will freeze payments until funds have cleared. MRC has a detailed fraud and error risk register, which is reviewed regularly by their Management Board. The risk of the MRC defrauding FCDO directly is zero.

Reputation - Minor - The research issues addressed by the scheme are not contentious. The MRC reviewed its risk management arrangements against the “Managing of Risk in Government” framework and confirmed no weaknesses identified.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery and Commercial
A monitoring report is provided each quarter, including updates of trials’ progress and key programme management information. Regular meetings see MRC provide updates on the risk of trials not achieving their desired impact or the expected end dates. Through these meetings, supported by additional offline updates where relevant, a clear narrative is established on the progress and performance of the programme delivery. Due to the well-established long-term partnership between MRC and FCDO, the intermediate dialogue addressing any programme management concerns remains open and transparent.

Financial Statements and Financial Management
MRC are consistent in their financial forecasting, providing regular updates and accurate forecasts. Financial forecasts are provided quarterly, whilst ad hoc requests for updated figures are responded to in a timely and accurate manner, supported by a consistent narrative to any deviations, or potential deviations, in expected figures.

Financial Performance
The programme continues to follow MRC financial management principles and procedures, and the MRC's Internal Audit Department conducts an annual audit of the programme's accounts. MRC has strict controls on fraud and corruption that are in line with the MoU's standards for the FCDO. At the beginning of every project, the MRC transfers assets to the research institution, so it is not necessary to submit an asset register for FCDO inspection every year. Transfers into or out of the equipment budget heading are not permitted since project equipment financing is ring-fenced.

Overall, JGHTs financial performance remains strong, having now spent just over 94% of their total budget, spending £70,510,569 out of the total budget of £75,154,696. The precision of MRC’s financial forecasting underpins their strong overall performance, whilst quarterly invoices are provided shortly after quarter end. In tracking the programme, a list of projects’ downstream partners and the funding received is effective in the process of monitoring MRCs financial performance.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The MRC monitor the progress of all awards and emerging issues are discussed with FCDO at the quarterly meetings. FCDO and MRC have a strong relationship in monitoring and managing grants, keeping in regular communication about the progress, or lack of for any grants that are off track. In addition, the FCDO is an observer on a number of trial steering committees.

The change in tool for extracting publication data has meant a less extensive coverage of articles. This includes lesser representation of publications from LMICs due to a more stringent criterion, similarly, impacting the reduced Open Access results. MRC expect the new tool to remain in use for the remaining years and data will be consistent with this review.

An external review of the scheme was published in 2019 and provided important new learning for the scheme and case study examples of how results from JGHT trials are leading to longer term impacts from the scheme. Overall, the review concluded that the initiative is delivering on its core aim to generate new knowledge on efficacy and effectiveness of interventions which are starting to contribute to improving health in LMICs.

Evidence
There have been no changes in the delivery of evidence from the programme. The evidence produced by JGHT remains at a high standard, demonstrated by the extent to which journal articles are published in high-quality impact journals. The evidence produced by JGHT also has a focus on vulnerable populations, with a number of grants researching issues where children or women and girls are particularly vulnerable. A small amount of JGHT grants focuses on people with disabilities.

Learning
JGHT has continued to increase the level of dissemination and learning from their research, described under output 4. It is recommended that MRC look at synthesising data on learning from across the programme as the final year approaches.

Date of last narrative financial report	June 2025	Date of last audited annual statement	n/a