Programme Completion Review

Title: Forest Governance, Markets and Climate (FGMC)
Final Programme Spend (full life): £280,025,544 / Budget: £250m in three tranches: / £79m, 2011-15; £84m, 2015-18; £87m 2018-21 / £30m budget extension to April 2023 / No cost extension to August 2024	Review Date: / 18/11/2024
Programme Code: 201724	Start Date: 18/08/2011	End Date: 18/08/2024

Summary of Programme Performance

Year	2012	2013	2014		2015	2016	2017	2018	2019	2020	2021	2022	2023
Programme Score	A	A	A		A	A+	A	A	A	A+	A+	A+	A+
Residual Risk Exposure Rating	M	M	M		M	M	M	M	M	M	M	M	M
DevTracker Link to Business Case (and any addendum):				DevTracker Programme GB-1-201724 (fcdo.gov.uk)
DevTracker Links to all logframes used during programme lifetime:				61390418.xlsx

A. Summary and Overview

Programme Description
The Forest Governance, Market and Climate (FGMC) Programme was approved in 2011 as a ten-year programme, as part of a global effort to tackle illegal logging and deforestation working with consumer and producer measures to curb the trade in illegal timber. It has been a flagship programme under the UK's broader initiative on international forestry and climate under the International Climate Fund.
The aim of the programme was to support governance and market reforms that reduce the illegal use of forest resources and benefit the poor (outcome), resulting in improved management of forests for poverty reduction, biodiversity conservation, and climate protection. (impact).
FGMC’s premise was that transparent and accountable forest stewardship is essential to stop deforestation, protect biodiversity and promote sustainable growth. It was designed to close international markets to illegal trade (supply side measures) and assist developing countries to comply with requirements for legal and sustainable timber (demand side measures). In turn, this would enable producer countries to sustain and grow exports.
The UK applied these principles to agree an EU-wide approach in 2003, known as the Forest Law Enforcement Governance and Trade Action Plan (FLEGT). FGMC was designed as the vehicle through which the UK would contribute to this endeavour. It aims to close UK and EU markets to illegal trade and help developing countries that are keen to reform their timber sectors so as to meet international market requirements for legal timber and secure supply chains.
Sixteen countries approached the EU to form Voluntary Partnership Agreements (VPAs) for this purpose. Together these countries represented 75% of the global tropical timber trade and approximately 25% of the tropical forest area. The VPA is a trade treaty that secures ready market access for timber products in the UK and EU market, coupled with nationally negotiated governance reforms to the forest sector. VPAs aim to a) guarantee that all exports from that country come from traceable, legal sources; b) clarify a definition of legal timber; and c) stop illegal logging and corruption. Since the UK exit from the EU, we have committed to transpose the policy and regulatory framework for the UK market and UK VPA.
FGMC partnered with six of these countries in four broad areas with government and non-government actors, seeking to:
- support reforms in developing countries to strengthen regulation and enforcement, secure rights, improve transparency and accountability in the management of forests and land use (supply measures);
- promote responsible business practices and demand for legal timber and other commodities such as palm oil in consumer markets (demand measures);
- help to shift global business norms to halt illegal timber imports by providing evidence and tools to support the legal timber trade and building global momentum for change,
- apply lessons from the timber trade to inform policy on commodities such as rubber and palm oil that put forests at risk, supporting efforts to combat illegal wildlife trade and informing international processes seeking to promote restoration of degraded lands and limit deforestation. Ensuring global coherence with other processes.
The UK through FGMC, led partnerships in Indonesia, Ghana, Guyana, Liberia, Republic of Congo and Burma/Myanmar[1]. These are referred to as FGMC focal countries. FGMC provided support to a wider set of countries by contributing to the European Forest Institute’s FLEGT Facility and by providing grants to civil society organisations (CSO). Beyond supporting producer country efforts, FGMC worked at the international level to shift global norms: providing dedicated support to encourage China to review its role as market and investor, generating evidence to inform measures aimed at halting illegal timber imports and fostering responsible business practices. It applied lessons from working with the timber trade to other commodity supply chains, notably rubber and palm oil. The map below illustrates FGMC’s footprint.
[1] Due to conflict, a decision was made by the Uk to cease working in Myanmar. The remaining 5 countries became the focus of FGMC

Programme Performance and Achievements

For more than ten years FGMC has been a high performing programme (scoring A and A+ in annual reviews, and A+ consistently since 2020). The Independent Commission for Aid Impact (ICAI) singled FGMC out for praise regarding its impact and operating model as one of the most successful programmes in the (HMG) forest and biodiversity portfolio of programmes. This PCR scores A+ based on the overall performance of output scores and against an assessment of the programme’s overall performance against outcome level indicators and the Theory of Change (set out in more detail in sections B and C).

Summary of performance/achievements against the outcome statement
The outcome statement as set out in the 2011 Business Case and results framework is “Governance and Market reforms that reduce the illegal use of forest resources and benefit poor people” and has remained unchanged throughout the programme lifetime. FGMC made excellent progress towards achieving its outcome objective demonstrating that transformational shifts are possible across the entire timber sector through changes to laws, policies and social norms combined with systematic monitoring.
The first decade+ of experience resulted in a simple and replicable delivery approach that uses deliberative[2] approaches to allow stakeholders to navigate the complex and political nature of forest land use to address their own national challenges together, as a result owning the outcomes making them more robust to challenge.
[2] Deliberation is a formal process of collective and reasoned decision-making, through which competing interests are mediated, and settlements are negotiated. Further explanation under Output 1 Section C
FGMC has demonstrated that long term dedicated and predictable support through partnerships can drive international systemic shifts. FGMC has supported: the delivery of significant reforms in at least 6 countries and strengthened NGO capacity and voice in 7 countries through championing of a multistakeholder deliberative approach, now the norm in all FGMC focal countries and adopted by other significant forest donor countries. The global community of practice that has developed around the forest governance agenda has successfully advocated for forest positive policy shifts at the international level, most significantly the EU Deforestation Regulation, UK Environment Act, US Lacey Act, and reforms in other markets such as Japan, S Korea, Australia and China. It has supported strong business-led operational standards in China addressing China’s significant forest footprint in producer countries and contributed to a significant shift towards legal timber trade.
FGMC has achieved these results by being a genuinely adaptive, locally led, and politically informed programme. It uses a range of instruments to tailor support to local contexts, focuses on outcomes over fixed activities, and allows flexibility to respond to changing opportunities. National stakeholders lead reforms, and the programme avoids unrealistic expectations by acknowledging political interests and incentives. These principles are shaping the design of FGMC2.

An Independent Commission for Aid Impact (ICAI) review of ICF forest and biodiversity programmes singled FGMC out for praise as one of the most successful programmes in the (HMG) portfolio, regarding its impact operating model noting its successful approach to delivering real change through patient and respectful partnership. ICAI said "it has been able to influence and shape demand for timber in major consumer markets in Europe and China, while supporting reforms in producer countries".

The review found "significant, visible and widespread evidence of FGMC's contribution to and influence on establishing new forest governance arrangements and market reforms at international, regional and national levels".
FGMC1 has extensive documentation of its achievements over the programme’s lifetime. In addition to Annual Reviews, these are captured in a series of end of programme reviews and lessons reports (produced in 2018, 2021 and 2023) and through several evaluative studies carried out by an outsourced Programme Evaluation and Learning Team (PELT). These reports, together with the outputs of more than 100 projects are archived in a FGMC Knowledge Management System. (Access will be made available on request).

FGMC took the theory of working with both demand and supply measures to influence and change national and global norms, and put it into practice with the following resulting key achievements:

First, enabling stakeholders to shape and engage in bilateral partnerships (VPA), FGMC experience demonstrates that trade incentives can leverage and strengthen governance reforms.
FGMC supported UK leadership in international efforts to strengthen forest governance and combat illegal logging, helping to forge bilateral partnerships with tropical forest countries, known as Voluntary Partnership Agreements (VPA). VPA are trade treaties between timber producer countries and the EU (and now the UK) that frame both governance and market reforms and link these to UK market access. The VPAs aim to eliminate illegal forest products from trade. VPAs comprise two essential elements: (i) a national system that assures compliance with their legal requirements (known as Timber Legality Assurance Systems[3] (TLAS)) and (ii) an EU (now UK) regulation that checks imports from these countries to ensure they accord with their TLAS. This reinforces national systems of control and provides a “green lane” for businesses importing to the UK in meeting their due diligence obligations. The promise of international market recognition and ease of export/ import procedures served as an important motivator for governance reform in all focal countries.
[3] national TLAS are being developed in Ghana, Liberia, Cote d’Ivoire, Cameroon, Gabon, Rep of Congo, Colombia, Peru, Guyana, Brazil, Honduras, Thailand, Laos, Vietnam, Indonesia, Malaysia
FGMC support has demonstrated best practice in supporting these processes to deliver improved governance through facilitated multi-stakeholder policy deliberation. Facilitated multi-stakeholder deliberation is now the norm in all VPA countries (with other donors adopting FGMC practices (e.g. AFD, GIZ, World Bank, Norway). It helped national stakeholders to shape the VPA and supported the governance reforms that are enshrined within them. The VPA provided the framework through which FGMC facilitated deliberations on policy and law and supported institutional capacity building to apply and enforce the reformed governance arrangements. This included the development and establishment of national-scale systems to ensure compliance (TLAS), these too have become the regulatory norm for timber.
FGMC’s 10-year commitment signalled a recognition of the challenges of tackling governance failures and coupling this to reforms in global markets. Partner countries have appreciated the sustained and long-term engagement afforded through FGMC. The combination of work at international and national levels, and with a diversity of actors created the political space to put local people at the heart of policy decision-making. The FGMC-facilitated VPA processes resulted in legal and policy change addressing concerns over rights, benefits, responsibilities and accountability in all five focal countries. It supported the re-tooling of regulatory functions in all five countries and enabled SMEs to improve their compliance with national standards and requirements. Other donors have been influenced by FGMC in their support of these processes.
Second, FGMC addressed market failure. Market reforms resulted in better regulated markets that designed to exclude illegal products and incentivise improved forest governance in producer countries.
Market regulation and other measures to shut out illegal material has become the norm in the majority of OECD countries, including the UK, EU, USA, China, Japan, Australia, Canada, Vietnam.
FGMC has helped to influence major consumer markets in Europe, the USA and China. FGMC was instrumental in shaping and putting into practice European policies and regulations to curb illegal logging and the timber trade. Information and evidence developed with FGMC support has resulted in prosecution of operators who imported illegal timber products into the EU and USA; and in China new regulation making it illegal to trade illegal timber products, and codes of practice and tracking systems that govern trade association member practices overseas.
FGMC partner-generated evidence, engagement and influence has over the years given confidence in due diligence as a key feature of market regulation. This was not the norm in many consumer market contexts. It now features in many consumer market regulations aiming to promote legal and sustainable supply chains aimed at stopping illegal logging and illegal deforestation. FGMC support has enabled practitioners to gain confidence in its application in practice, through shared learning, evidence, and new tools.
Many of the end of programme targets regarding compliance with the UK and EU Timber Regulation have been met, demonstrating a good level of understanding of EU/UKTR requirements by operators, suppliers, monitoring organisations, third-party certification schemes, and trade federations. Where operators have not been compliant or competent authorities have not been quick enough to act, civil society investigations and advocacy have shone a light on such cases Traceability and certification of timber supply chains to demonstrate compliance with requirements in source countries is the accepted business practice across most major markets.​
Information and evidence developed with FGMC support has also led to new regulation in the world’s largest timber market: China, making it illegal to trade illegal timber products, and helped to put in place codes of practice and tracking systems that govern trade association member practices overseas.
China shifting timber sourcing to countries with low risk of illegal logging demonstrates the influence of consumer market due diligence regulations. The question remains as to whether China in turn can become an important driver of forest governance reforms in producing countries. China is in a particularly influential position to lead a shift in the global trade paradigm away from illegally sourced timber products. However, despite its shift in sourcing from high risk to low risk and strong signalling of the need for Chinese enterprises to comply with the law in producer countries, mandatory import controls are not yet in place.[4] Although the concept of due diligence in timber supply chains has been established for transactions within China as a result of the Revised Forest Act (2020), it is not yet a mandatory requirement to extend this back to the source of imported materials.
[4] There has been a significant shift to sourcing from lower risk supply chains (with increased use of timber from domestic sources, US, New Zealand, France and Germany), demand for tropical hardwoods still exerts pressure on forests in countries with weak governance. PNG, a high-risk country for illegal timber, is now the largest source of hardwoods into China since the collapse of imports from Russia.
There is evidence of China’s growing recognition of the need to focus on legal frameworks and ESG principles in producer countries where Chinese businesses are active, and of Chinese business associations increasing willingness to engage in international processes. In terms of investment and trade in tropical timber, China is signalling to both enterprises and producer countries the importance of legal timber. Supported by FGMC, two Chinese trade associations, in consultations with their counterpart associations, are developing legality checklists which they can use to assess their members’ compliance with national standards in Liberia, Gabon, ROC, Cameroon, and PNG. Similar work is on-going with forest risk commodity supply chains, notably in palm oil, natural rubber and minerals with the development of due diligence and ESG guidance.
Third, FGMC demonstrated that sector wide transformations are possible across the entire timber sector at national scale in forest producer countries, through changes to laws, policies and social norms combined with systematic monitoring. The first decade of experience has resulted in a simple and replicable delivery approach that uses deliberative approaches to allow national stakeholders to navigate the complex and political nature of forest land use to address their own national challenges together, as a result owning the outcomes making them more robust to challenge.
For example, Indonesia, the world's largest producer of tropical timber has fully operationalised its timber legality assurance system known as "SVLK" system, developed with FGMC technical assistance (TA) support. This forest production and compliance monitoring system assures that all its forest product exports, including furniture and paper, now meet all legal requirements and illegal operators have been squeezed out. In 2011, by contrast, 80% of Indonesia's exports were considered illegal, produced in violation of Indonesia's own law. In 2016, it became the first country to issue licences, which provide access to a "green lane" for its exports to UK and EU markets. Since then, timber exports to the UK and EU have increased by 19% to over USD 1.4.
Indonesia credits the overall drop in its deforestation since 2016 (from 2.8% to 1.3% and more particularly the reduction in loss of primary forests from 1.1% to just 0.3%) in part to the improved compliance monitoring of the SVLK supported by FGMC.
All five focal countries supported by FGMC are on their journey to achieving fully functioning national sustainable forest management regulatory systems leading to (FLEGT) licenses for the export of all forest product exports, in particular to the EU and UK. Two countries have systems operational at national scale and are delivering export licenses: Indonesia and Ghana, with the remaining three at various stages in the process of rolling out these new systems (Guyana, Roc, Liberia).
Fourth, FGMC has shown that Transparency which fosters accountability is important for both demand and supply side actions.
The development of traceability and certification of timber supply chains to demonstrate compliance with requirements in source countries is the accepted business practice across most major markets, as reflected in the purchasing policies and guidance of the UK, EU, USA, China trade associations. National scale traceability and certification (like Indonesia’s SVLK) is being developed by many countries (much of tropical SE Asia and Central and West Africa)[1];Civil society organisation (CSO)-led independent forest monitoring (IFM) which is now well established as a means to assure markets and demonstrate national accountability, for example, across the Congo Basin, IFM reports are linked to WRI’s Open Timber Portal that provides international buyers with information on sourcing legal timber.
At an international level, FGMC’s support for innovative tools that aid transparency have helped to inform civil society third party monitoring of the private sector and have supported the private sector and consumer markets in decision making and reporting. Examples include:
- WRI’s Open Timber Portal[5] and Global Forest Watch initiatives[6]. Global Forest Watch made high quality data on forest resources and forest cover change accessible to all. It is now the go-to source of freely accessible information to track deforestation in many parts of the world and forms the basis for many tools used in real time tracking of illegal activity
  [5] The Open Timber Portal is an initiative by the World Resources Institute to incentivize the production and trade of legal timber.
  [6] Global Forest Watch is an open-source web application to monitor global forests in near real-time
- EU/UK Buyers and Governments are increasingly using transparency and disclosure tools incubated by FGMC such as Global Canopy Forest 500 initiative[7] and Trase[8] as part of their commitments and due diligence regulations. This includes nine EU member states using the data. The data has also been mobilised by the European Commission and Parliament. Notable use cases include France’s updated risk evaluation tool embedded in the country’s National Strategy against Imported Deforestation platform; Commodity Footprints, the nature impact dashboard launched by the UK Government’s Joint Nature Conservation Committee; and the mapping and visualisation of Germany’s imported deforestation.
  [7] Global Canopy's Forest 500 tracks the policies and performance of the 350 most influential companies and 150 financial institutions linked to deforestation in their supply chains and investments.
  [8] Trase is a supply chain transparency initiative that transforms our understanding of globally traded agricultural commodities. It empowers companies, governments, and others to address sustainability risks and opportunities by linking supply chain actors to production landscapes across the world.
- The Taskforce on Nature-Related Financial Disclosures, formally launched in June 2021, helped create substantial momentum around the crises facing nature and biodiversity. Versions were shaped by FGMC partners with improved provisions on transparency, impact reporting, IPLCs and public participation prior to launch.
Fifth, FGMC developed and supported inclusive stakeholder-driven processes that have helped to create legitimacy for resulting policy and regulatory reform with greater likelihood of sustaining these reforms.​
A hallmark of FGMC’s approach has been to encourage national processes led by national stakeholders, not international organisations and/or consultants. This is because the key assumption underlying FGMC is that genuinely inclusive and deliberative[9] decision-making will result in more sustainable, robust, and nationally owned outcomes (legal and administrative reforms) and contribute to benefits for both people and forests.[10]
[9] Deliberation is a formal process of collective and reasoned decision-making, through which competing interests are mediated and settlements are negotiated. Further explanation under Output 1 Section C
[10] ‘Sustainability’ manifests in three ways: ecologically (forests are replenished), socioeconomically (benefits of the forests continue), and institutionally (rules and systems are reinforced over time).
FGMC recognised that society (in any country) is heterogenous and made up of competing interests. FGMC experience showed that Inclusive and deliberative processes can help lead to resolution of sector conflicts that allow governments to put into law agreements and settlements that have been politically negotiated by representatives of stakeholders, and which are therefore widely held to be socially legitimate and therefore more likely to be followed.
Lastly, FGMC played a key role demonstrating that focusing on illegality and crime is an effective entry point to engage with governments, businesses and national stakeholders to bring about reforms. Illegal production and trade undermine legitimate business, reduces the benefits from forests and tarnishes country-wide reputation and trade. A focus on illegality and crime has helped to build common ground between local CSOs and businesses who commonly disagree over forest policy priorities. The focus on illegality in supply chains has also encouraged more consumer countries to adopt measures to control imports. This approach is now globally understood, and in many instances forms the basis for import measures to reduce trade in illegal commodities. This was not received wisdom in 2010/11 at the start of FGMC. It proved an important factor that has fostered regulations in China, Japan, Australia, Canada, USA in addition to the UK and EU.
Major lessons learned, evidence generated, and recommendations
FGMC has extensive documentation of the lessons learned throughout the programme’s lifetime. These are captured in a mid-term independent evaluation, a series of lessons learnt reports and evaluative studies carried out by an outsourced Programme evaluation and learning team (PELT).

Some of the key lessons of potential interest to other programmes are set out here and can be broadly categorised as those relating to the substance of the programme, the programme’s approach to working with stakeholders and delivering results, and the internal ways of working and managing delivery

Lessons learnt from our approach to forest governance reform:

At its core, FGMC is a governance programme. It recognises that the governance of natural resources is inherently political and that, more often than not, the challenges facing national stakeholders cannot be solved by technical solutions alone. Below is a summary of high-level reflections on what FGMC has learned about governance in the forest sector.[11]
[11] For a more detailed examination of FGMC as a governance programme, see Learning wider governance lessons from work on renewable natural resources: the case of DFID’s FGMC programme. As FGMC approached its mid-term review in 2017, FCDO examined on how the programme engaged explicitly on conventional governance challenges and extracted several lessons in relation to ongoing HMG governance policy concerns. These lessons remain relevant today, not only for governance advisers but for anyone interested in understanding the “politics of natural resources” beyond the narrow confines of ‘management’.

What did FGMC mean by forest governance?
For FGMC forest governance included:
- defining in law and securing the rights and responsibilities (formal or traditional) of all stakeholders, including Indigenous Peoples and Local Communities (IPLCs),
- agreeing forest management protocols, backed up by regulation legitimate in the eyes of stakeholders, and implemented in practice.

These are the governance foundations that help establish effective forest stewardship – as depicted in figure 1.

Strong Governance foundations and FGMC practices are influencing beyond programme bounds demonstrating the long-term sustainability of the partnerships and processes supported through the programme. The forest governance foundations supported through FGMC over the decade are enabling UK ICF programmes, other donor investments and developing countries themselves to build on the progress made. Forest countries are increasingly seeing the wider benefits of their efforts to strengthen forest governance. For example:
- Producer countries are increasingly calling for international market recognition of their national verification systems. Confident that they have built and established strong forest governance that provides evidence required by increasingly concerned consumers, producer countries are working to see their national systems recognised in international markets. Building from their experience with VPA, a coalition of producer countries have joined together to expand international market interest in their national-scale certification approach. So far, only the EU and the UK have committed to recognising these national systems through VPA and producer countries want to achieve greater appreciation and visibility for them. Launched at UNFCCC COP27, six countries (Indonesia, Cameroon, Ghana, Guyana, Liberia, and RoC) formed a Broader Market Recognition (BMR) Coalition to galvanise more ambitious action in producer countries and to see this valued and recognised in international consumer markets[12]
  [12] The BMR Coalition was launched at COP 27. https://timberdevelopment.uk/timber-development-uk-supports-broader-market-recognition-at-cop27/
- Experience from the timber sector has been tested with other forest risk commodities. Despite the differences in forest sector institutions and stakeholders compared with those engaged with agricultural forest risk commodities, some FGMC CSO partners have sought to apply the lessons learnt in VPA-processes to other national processes. Stakeholders in the cocoa sector in Ghana and Ivory Coast have been learning from the timber sector. Civil society (NGO and farmers organisations) have been able to actively engage in discussions on sustainable cocoa and the EU Deforestation Regulation supported by experiences from the VPA process through ‘clinics’ and research undertaken by FGMC partners.
- Investing in strong governance foundations can pay dividends, enabling countries themselves to build on work supported through FGMC. By investing in forest sector governance countries are able to demonstrate they are effective forest stewards. For example, Guyana acknowledged that the VPA process helped it build inclusive governance foundations that enabled it to secure a carbon deal under the high integrity ART TREES standard for a minimum of USD 750m (30% of Guyana’s forest credits for the period 2016-2030), of which 15% of proceeds will flow to indigenous and local communities.
- Progress in forest governance reforms are increasingly being seen as foundational for performance related payments. The Voluntary partnership Agreements that some tropical forest countries have embarked upon provide a useful hook for wider reforms and access to finance. Norwegian climate finance results-based payments in Guyana were contingent upon progress against the VPA, in RoC and Cameroon the Central Africa Forest Initiative references governance reforms and VPA progress within the formal Letter of Intent that forms the basis of the CAFI partnership. The IMF is referencing forest governance reforms as triggers for the release of payments under the Sustainability and Resilience Facility.
Trade is a strong incentive for reform if linked to governance outcomes. Stakeholders must first recognise that the deliberative process is the legitimate forum for deciding the rules and systems that govern how forest land is used and how its benefits are distributed. By linking outcomes to market-based instruments such as trade agreements, stakeholders with interests in forest land are incentivised to participate in the deliberative process because they understand this is how they can shape the rules and systems that will lead to their desired outcomes (e.g. market access). Some stakeholders, such as Indigenous communities, might be incentivised not by a trade agreement, but by the opportunity to shape the legal architecture in a way that supports their claims to land tenure rights. Conversely, the deliberative process can be undermined when stakeholders (particularly more powerful ones) are less incentivised to engage, either because they perceive the outcome as a threat to their position or because they feel they can continue to operate outside the process.
Climate and environment programmes can offer entry points to address ‘wicked problems’ in complex political contexts. In some countries, there is little appetite among government stakeholders to engage directly in democratic reforms. However, by focusing on seemingly apolitical topics where there might be opportunities to align incentives – for example, the economic case for climate reforms – external partners can help civil society to open a space to discuss governance challenges, such as transparency and accountability.
Informed representation and participation are critical if reforms are to be seen as legitimate and therefore sustainable. In the case of FGMC, this means that all relevant stakeholder groups interested in or affected by forest land reform were engaged in the deliberative process. The absence of critical interest groups reduces the legitimacy of the outcomes and can lead to the eventual agreement being undermined by those who have been excluded from or not participated in the process. Moreover, the actors participating in the process need to represent the breadth and diversity of their constituents and need to be seen as legitimate in the eyes of their constituents. Finally, representation is about more than being present in the process: it requires that all actors involved have the power, capacity, resources, and information to engage and negotiate on a level playing field.
The genuine inclusion of women and indigenous people in policy processes takes time and concerted advocacy and awareness raising effort., and longer still for policy reforms to translate into tangible impacts. The forest sector tends to be male-dominated where gender blindness remains the default setting for policy- and decision-making. Not all stakeholder groups are receptive to gender considerations, and it has often been through local CSOs that FGMC partners have identified opportunities and barriers. For instance, Legal Working Groups (supported by FGMC partners) have been a crucial medium not only for women to engage in legal reform process, but also for civil society and non-civil society actors to be further sensitised. However, experience has shown that gender-positive policies do not necessarily translate into changes in practice. Implementation is often hampered by the persistence of unconscious biases and resistances in light of the perceived feasibility, cost, and the political/ social desirability of changes. Nevertheless, FGMC made progress involving women and marginalised voices in deliberative policy processes and addressing gender and inclusion in legal frameworks and policy outcomes. For example, stronger women’s rights are secured in Liberia’s Land Rights Act, as a direct result of FGMC supported multi-stakeholder processes.
FGMC has not sought to drive agendas, but rather has focused on enabling informed stakeholders to do so, and to make informed decisions. Reforms covering the jurisdiction where decision making about the allocation of resources takes place are more likely to gain traction. National rules and systems – rather than internationally mandated ones – are typically seen as more legitimate because they are developed, owned, implemented, and enforced by the people directly impacted by them. This also means that the rules and systems agreed through a national deliberative process will be shaped by the country’s history, norms, and the evolution of its political settlement, and, similarly, can evolve to respond to social, political, and economic changes within the country. From FGMC’s experience in some countries, stakeholders felt that the national legal frameworks had been developed by international consultants and were therefore unworkable, or unsustainable. However, it is also recognised that external rules – such as market demands by trading partners – can establish the impetus needed to consider national-level reforms.
Governance reforms require strategic patience and long-term partnerships. The deliberative process has intrinsic value in that it increases stakeholder capacity and builds trust among different groups. But building trust takes time and occurs through repeated interactions. Moreover, deliberative processes are established progressively, replacing or retrofitting pre-existing non-deliberative processes that benefited powerful actors. These actors may not immediately see that a more balanced redistribution of influence is in their interest and, in reality, in some instances it may not be. FGMC ran for 13 years and did not operate in a typical projectised approach. This demonstrated long-term commitment to stakeholders engaged in the deliberative process and positioned the UK as a partner, rather than a donor.
Global networks of individuals can be powerful allies for reform. FGMC works through an extensive and evolving global community of practice. The FGMC community is made up of individuals embedded into existing organisations from across a wide spectrum – civil society, media, government, multilateral, private sector. This means that the programme’s influence is not restricted to FCDO or implementing partners.
Taken together, these lessons demonstrate that FGMC is a genuinely adaptive, locally led, and politically informed programme. It offers a configuration of instruments based on the local context (e.g. grants, technical assistance, facilitation). Implementation is guided by high-level outcomes, rather than predetermined activities or outputs, which allows it to test different approaches based on the context, start new activities where windows of opportunity open, and stop activities where they close. Reform processes are entirely led by national stakeholders. FGMC plays a supporting background role, for example, not publicising its work through a website. Finally, it recognises the prominence of interests and incentives, thus avoiding the common trap of optimism bias in many donor-funded reform programmes.

Lessons on influencing and shaping market/trade policies:

Coalitions working at national and international levels have helped to create momentum for change and will sustain the reforms put in place and support the drive for implementation.
Since 2012, FGMC1’s accountable grants have supported international not-for-profit organisations like FERN, Environmental Investigations Agency, ClientEarth to form coalitions with civil society organisations from tropical forest countries and other European NGOs advocating for action on the trade of commodities that put tropical forests at risk of deforestation. The FGMC coalition drew from their experience to advocate for import measures that would curb illegal tropical forest clearance and incentivise sustainable production. A decade ago, consumer governments relied on voluntary industry initiatives and non-binding policy measures. However, new evidence about the rising problems of illegal deforestation, practical experience with implementing import measures for the timber trade and combined with increased pressure from both business and NGOs has pushed governments to adopt binding rules.
In 2021, the EU Deforestation Regulation (EUDR) was proposed. The FGMC1 community of practice shared evidence, convened voices from tropical forest countries and shared ideas to improve the proposal, including strengthening enforcement provisions, transparency and reporting, protection of rights of IPLCs and advocated for greater voice from tropical forest producer countries. The finalised text of the Regulation, which enters into force in 2024, includes many of the suggestions proposed by the FGMC coalition. FGMC’s community of practice continues to provide inputs to EU authorities, businesses, producer governments and their stakeholders as the practical mechanisms for implementation are being established. They continue to press for greater attention to partnerships and cooperation with producer countries. The FGMC community of practice also worked closely with Defra in the development of UK equivalent legislation. The EUDR presents a significant success for the FGMC community of practice and demonstrates the significant return on investment of concerted and informed advocacy supported through FGMC accountable grants programme.

FGMC has facilitated dialogue and influence between producer country stakeholders and the consumer markets to which they export. Experience sharing between practitioners and stakeholders learning lessons from the process in their respective countries has also been an important source of motivation as to what is possible. Combined with the support of targeted technical assistance, learning between forest countries has been proved to be particularly successful.

Lessons learnt from FGMC’s ways of working:

Given the long term and political nature of the programme, it has necessarily evolved and adapted in terms of delivery mechanisms and approaches, with a lot being learnt before settling on the optimal approach to delivery. What started as a programme largely implemented directly by DFID evolved into a programme largely outsourced but with a unique approach to ensuring strong DFID/FCDO oversight and steer. Additionally, ways of working evolved considerably in response to an appreciation of delivery instruments and approaches that were not working as well as hoped until such time as an optimal approach was found. These include significant adjustments in management of the programme, from in-house to outsourced, an evolution in how MEL was conducted throughout the lifetime of the programme, and adjustments to the grants programme and our approach to working with other donors.
FGMC was highlighted in the ICAI review of HMG projects supporting action on forests as delivering strong policy influencing results at national and international levels supported by an adaptive approach that has helped build a strong coalition of practitioners.
Support to national reforms processes was delivered through various instruments depending on country context, ranging from direct Financial Aid to TA contracts procured directly by FCDO, through International Organizations, to projects managed by Posts. This diversity of instruments combined with an approach to “thinking and working politically” enabled the programme to tailor support to local donor and country context and advance quickly when needed or scale back if progress was not being made. The timescales to mobilise TA contracts were often a constraint when the political timing was opportune. FGMC evolved ways of engaging in countries with both strong forest expertise and post and in countries where there was no post at all. Section F provides detail of the management, delivery and commercial lessons learnt through the lifetime of the programme.

One of the practical challenges faced by FGMC as well as other donors, was securing advice and assistance in a way (at speed and with flexibility) to work with the positive political energy of the governance reform processes. In many instances, donor procurement processes have been slow (taking sometimes over a year to mobilise teams) and this has often frustrated processes on the ground. Through FGMC we worked with other donors to establish facilities with international organisations (FAO and EFI) to provide timely guidance and offer small grants to local organisations. In addition, some TA projects included mechanisms for small grants to local organisations to strengthen voices and understanding in the national policy dynamic.
Actions following PCR
Key conclusions and recommendations, and evidence generated from this programme review and the programme’s final annual review have informed the development of the approved FGMC2 Business Case (link D0005966.odt and its annexes D0006757.odt )
How this PCR was conducted
This PCR comprised a review of key experience and evidence which started during the preparations for the development of a new 10- year forest governance business case, and has included interviews with individuals and stakeholders associated with the programme over its lifetime as well as the review of key documents including all annual reviews (available on devtracker), a range of evaluative studies commissioned by FCDO and carried out by the Programme Evaluation and Learning Team (PELT).

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£250,000,000 at time of BC approval. / first tranche £79m approved 2011 / second tranche £84m approved 2014 / third tranche £87m approved 2018 / Addendum to BC and cost extension of £30,000,000 from2021 to 2023 – no cost extension to March 2024	Total budget through 3 tranches and several BC addendum: £ 280,025,544
Timeframe	Initially anticipated as 10 years at BC sign off (August 2011 – August 2021). / Two-year cost extension to April 2023. / One year no cost extension to April 2024. / Further extended to August 2024	August 2011 – August 2024 (including costed and no-cost extension)
Outcomes	Governance and Market reforms that reduce the illegal use of forest resources and benefit poor people” / Original indicators: / Forest policy and governance performance (against Chatham House index) / Quantity and value of illegally sourced timber and other commodities / Area and value of forests under non state rights.	The outcome statement held for the whole lifetime of the programme and strong evidence of achievement of this outcome statement exists to varying degrees across the focus countries. Outcome level indicators were modified in 2014 from being largely focused on quantifying in absolute terms on a country-by-country basis variables of governance, area under management, value of illegal timber traded, to a set of indicators utilised for the remainder of the programme which focused more on the processes behind the transformational shifts sought by the programme. A range of methodologies, including indices and score cards were developed to track progress.

Overall assessment of programme outcome and sustainability

Performance against the Programme Outcome

The outcome statement as set out in the 2011 Business Case and results framework is “Governance and Market reforms that reduce the illegal use of forest resources and benefit poor people” and has remained unchanged throughout the programme lifetime.

FGMC made excellent progress towards its outcome objective of forest governance and market reforms that reduce the illegal use and trade of forest resources, with positive impact for forests, people and economies.

Indonesia and Ghana provide “proof of concept” for the FGMC Theory of Change, achieving the outcome statement. Having seen the broader benefits that the governance reforms have brought to their forest sector, they are now taking this experience to other countries, building a coalition of tropical countries committed to establishing national scale timber governance known as the “Broader Market Recognition coalition”.

The following outcome level indicators were revised in 2014 and became the basis for all future assessment of performance against the outcome statement.:
- Progress towards self-sustaining, nationally owned, deliberative multi-stakeholder process in VPA countries
- Progress with adopting and implementing pro-poor forest sector governance reforms at national level
- Progress with pro-poor reforms that secure and safeguard forest and land rights, the interests of Indigenous Peoples, poor and forest-fringe communities
- Progress with market reforms addressing deforestation and forest degradation at national and international level
Achievements against the outcome indicators include:
Deliberative multi stakeholder processes have built strong local support for governance reforms. FGMC provided significant support to these processes to be inclusive and fair. Our assumption has been that these deliberations create legitimacy, and decisions agreed are more likely to be sustained than if policy had been made through edict. The 2017 independent Mid Term Review noted “one of the most significant achievements of FGMC has been facilitating the inclusion of key stakeholder groups … who often were previously unable to exercise any significant level of influence. Support provided by CSO grantees has shaped and strengthened the voice of civil society in national-level policy processes across all countries”. At the outcome level we expect to see these deliberative mechanisms functioning and being sustained. This target has been fully achieved for Ghana and Indonesia and is broadly on track for most other countries. A good indicator of the value that stakeholders place in these processes can be seen in Cameroon and Liberia, where despite deteriorating national governance situations, stakeholders continued to engage with forest governance reforms.
Pro-poor forest sector governance reforms: The legal and policy reforms supported by FGMC enhanced voice and representation in policy processes and through this we assumed, rights were protected, revenue shared with communities and regulatory challenges faced by small and medium enterprises supported. As such it was assumed that the many millions of people dependent on forests would benefit through reforms established through an inclusive process. However, establishing causal links between governance reforms and their impact on livelihoods is complex. Nevertheless, there are examples of governance reforms impacting positively on livelihoods.
In Ghana, ICAI found FGMC demonstrated an excellent understanding of national and local forest governance contexts noting good progress on strengthening forest governance and legal compliance over the past decade. Ghana now has a fully functioning timber legality assurance system (TLAS). Public access to its wood tracking data, developed with FGMC TA support, has improved accountability; reduced operational costs; made it difficult to introduce illegal timber into supply chains; increased revenue capture; and provides greater certainty for business. Social contracts between communities and logging companies are now honoured, resulting in more community benefits and reduced conflict. For example, revenue collection increased by 240% from 2010 to 2019 despite a reduction in the volume of trade. Legal reforms in all focal countries addressed rights such as free prior and informed consent, benefit sharing arrangements, and measures to support SME and community enterprises, examples of which are set out in section C.
Both from a rights and forest protection perspective[13], FGMC sought to ensure that forest governance reforms secured forest rights for IPLC. COP 26 raised the profile of IPLC’s culminating in the IPLC forest tenure joint donor statement. FGMC grantees advocated for enshrining the rights of Indigenous People in national legal frameworks. After many years of supporting the advocacy efforts of indigenous people’s organisations in DRC, and collaborating with many civil society organisations, international and national, an ambitious and potentially consequential new Indigenous People’s Law was promulgated by parliament in 2022. Many from the FGMC community of practice and their partners are now looking to the operationalisation of this law through secondary legislation, and its coherence across other important laws. A similar process was supported in RoC, with ongoing efforts to develop secondary legislation and ensure coherence across sectoral laws.
[13] There is a growing body of evidence demonstrating that forests under some form of IPLC tenure are likely to be better managed than elsewhere.
Market reforms are addressing deforestation and forest degradation nationally and internationally: With an increasing number of consumer countries regulating their timber markets, (particularly in the EU, UK, US and Australia) there is good evidence that this has stimulated increased controls over imported raw materials in key manufacturing countries. The assumption was that market regulation in consumer countries would signal to producers the need to improve forest and land use governance. China and Vietnam are good examples where the requirements of consumers in the US, EU and UK have driven shifts in timber import sourcing which have in-turn signalled to tropical countries their demand for legal timber.
In domestic (producer country) markets, public procurement policies and new regulatory requirements are impacting levels of illegality in local markets. Evidence of this is strong in Indonesia, growing in Ghana, and starting in Guyana. In RoC, the government has introduced a “product sharing” regulation which although unpopular with business, reflects the government’s determination to ensure a level playing field between international and domestic timber markets.
FGMC assumed that operators would require suppliers and third parties to provide better quality and more accessible information needed for them to comply with their due diligence obligations under the EU/UKTR and other market regulations. The sustained investment in tools and accessible up to date information has continued to grow, driven by the increasing reliance of different consumer markets on Due Diligence and risk assessment as a means of ensuring and demonstrating compliance.
The 2017 Mid-Term-Review (MTR) concluded that FGMC “has proved a highly effective model for addressing the complexities of trade, through mutually reinforcing actions relating to supply, demand and business measures. A key benefit of this approach is the ability to link different actors working at multiple levels, such as timber processors and exporters in producer countries and timber importers and Competent Authorities in European markets. Also, consistent support to China has been influential in enabling China’s shift, over the past decade, from its reluctance to acknowledge the problem of illegal timber trade to recent commitments to implement measures to address this problem in a manner aligned with the EU and other global markets. There is growing evidence of the influence of market measures in producer countries creating incentives for governance and trade”.
Mainstreaming gender in FGMC[14]:
[14] While recognising that gender must be seen as only one element of wider power relations and institutional structures that influence women’s access to land, natural resources and economic development, it was agreed that gender should continue to be considered as a separate programmatic strategy from other dimensions of marginalisation and exclusion. This aligns with the growing emphasis on gender within FCDO, including the 2022 International Development Strategy in which FCDO highlights ongoing inequalities faced by women and girls and commits to “work to ensure women’s voices are heard at all social, political and economic levels” (p 12).
As a policy programme, FGMC supported processes where the terms of engagement were set by national stakeholders and not by the programme. FGMC therefore supported local actors to build capacity of women’s representatives to engage in policy making processes, and to generate evidence to encourage a focus on women and marginalised groups such as IPLC. This resulted in significant shifts in legal frameworks, including benefit sharing rules.
Internationally, FGMC encouraged all partners to generate understanding and ideas for ways to ensure that women participated in and benefited from governance reforms and private sector investment in the forest and land use sectors e.g., one FGMC grantee supported IPLC women to participate actively in the creation and implementation of policies that affected their land and resource rights; and another FGMC grantee Proforest, connected private sector, communities and government to understand the important role that women smallholders play in productive landscapes, such as cocoa in West Africa, and how they can be differently impacted by policies and interventions.
Over the years FGMC has updated the programme’s Gender approach to respond to evolving DFID/FCDO policy and recommendations made by FGMC’s MEL process, most recently in 2022. The updated gender strategy has informed the design of the new forest governance programme Business Case recently approved by Ministers (August 2024) and will ensure that the future governance programme reports against the OECD DAC gender marker. In addition, FGMC has reflected on its approach to political inclusion drawing from 13 years of experience that is focused on the ways in which different interests are represented within inclusive deliberative processes. It identifies three critical elements for successful political inclusion, including: participation of often excluded stakeholder groups (such as IPLC), deliberative decision-making process, and forest stakeholders being incentivised (including influenced by external factors such as market signals) to participate.
Reflection on the sustainability of the programme
The FGMC approach that focused on systemic and institutional change has resulted in national scale shifts in BAU where the reforms and new institutional mechanisms have had time to be fully operationalised. In these instances, forest authorities and businesses as well as forest communities have changed management and harvest practices, regulatory procedures and strengthened independent monitoring by independent auditors as well as local CSO. Thus, creating the structures that will help sustain the reformed systems beyond the programme end. In Ghana and Indonesia, where national systems are fully operational, little external assistance is required other than to ensure that independent monitoring and external audits continue. Political challenges (e.g. instability, general elections, politically connected stakeholder lobbying) as well as external threats such as the Covid pandemic, have tested the sustainability and robustness of the governance reforms that are secured in the national Timber Legality Assurance Systems (TLAS) and the resilience of inclusive and legitimate multi-stakeholder deliberative platforms that continue to drive positive change. This provides confidence in the resilience and sustainability of the governance shifts.
The improved capacities, improved understanding has lasting impacts beyond the programme but clearly will require periodic investment and renewal. Some of the tools and innovations piloted by FGMC have grown into globally significant mechanism (such as Global Forest Watch), tools (e.g. national TLAS, global TRASE), ways of working, and norms (e.g. focus on IPLC tenure). The various communities of practice, whether at national level, or operating in international policy domains will continue to shape future engagement.
Reflections on the programme ToC
The FGMC Theory of Change (TOC) had at its heart, the proposition that a nationally-owned, multi-stakeholder deliberative process is fundamental for fair and enforceable public policy. As a result, institutional change and the establishment of comprehensive national systems in both consumer and producer countries are key for Transformational Change. FGMC’s TOC assumed that trade and other incentives or levers could transform markets, governance, forest and land stewardship and business practices, and that these changes would bring economic, environmental, and social benefits to promote economic growth, reduce poverty, secure ecological goods and services, and build stronger, fairer and safer societies.
FGMC operated on a global scale centred on actions that brought together trade policy (regulation to close the market to illegal timber or commodities grown on illegally converted forest land for example) with development assistance (support to address weak governance that allows illegal practice to flourish) to improve global business practices. It involved a mix of interventions that engaged in national and international policy processes to bring about institutional and governance reforms that changed the rules (laws, policies, regulations) governing forest management and trade in forest products in tropical countries.

Changes in Operational Context
FGMC was approved whilst the UK was a member state of the EU and in support of the implementation of the EU’s Forest Law Enforcement Governance and Trade action plan (EU FLEGT), at a time when illegal timber was one of the key drivers of deforestation. Since approval of the BC in 2011, the UK left the EU, timber trade volumes shifted significantly to Asia away from European markets, other commodities such as palm oil, soya, cocoa became more important drivers of deforestation along with mining and other extractive industries, and markets for carbon and other environmental services grew and evolved, with the Paris agreement in 2015 and the Glasgow Leaders Declaration on Forests at the Glasgow Climate COP in 2021 marking significant milestones internationally impacting on the profile of forests etc. The programme has adjusted to these shifts, seizing opportunities through its agile approach.
Other Important shifts in the global context include new regulations in the EU and UK (and US) aimed at curbing deforestation (in 2024), and the emergence of new incentives for governance reform leveraged through carbon, biodiversity and other ecosystem service payments. Since UNFCCC COP 26 these shifts have grown in importance and given rise to new threats and opportunities for forests, which reinforce the need for strong forest governance foundations.
Refinements of the ToC and results framework over the programme period
As expected of a long-term programme, the ToC has undergone a number of adjustments and revisions over the years in response to the changing context, lessons learnt through implementation, the 2017 Mid Term review, and Brexit reality. In 2021 and 2022, post Covid, and in preparation for the design of a future programme, a series of “deep dive” sessions with Posts and thematic discussions, explaining what FGMC did in a changing context helped to refine the TOC to better reflect the focus of FGMC's work in supporting and facilitating inclusive, national deliberative processes in the governance sphere and traced through the results of sector governance changes to both the sharing of benefits and to the incentives for better forest management.
FGMC utilised ToC for each country and for different policy domains. These were nested within the overarching theory of change and were regularly reviewed drawing on ongoing political economy analysis enabling the programme to respond to opportunities and pivot when needed.
ToC Assumptions over the lifetime of the programme:

As expected with a programme implemented over such a long-time frame, and over many countries some assumptions set out at the start of the programme in 2011, were not borne out. Examples include:
At the start of FGMC in 2011, there was considerable expectation of the potential transformative promise of REDD+ finance to bring about positive incentives for forest governance improvement. There was also an assumption that the focus on national REDD+ results-based payment schemes would foster coherence between FLEGT processes and REDD+. The creation of a REDD+ facility and a FLEGT facility in the European Forests Institute were a reflection of this assumption amongst EU donors, including the UK. In reality, the coherence that was expected did not materialise and for many years the processes and actors associated with REDD+ and FLEGT progressed in parallel to each other rather than in a complementary fashion. Within HMG, this was manifested in the separation of functions between (then) DFID covering the economic and livelihood aspects of forests, and (then) BEIS covering forest carbon. With the creation of the joint FCDO-DESNZ International Forest Unit in 2022, bringing together these two work streams within one unit, the opportunity has arisen to build greater synergy between these important processes. The design of the new FGMC2 programme places more emphasis on the underlying governance foundations required for successful REDD+ and has created greater opportunity than before to bring FGMC’s approaches to inclusive multi stakeholder deliberation and policy making into the forest carbon and REDD+ domains.
When FGMC was designed as the UK’s vehicle to deliver on the EU’s FLEGT action plan, it was assumed that the VPA structures in each country would provide an important framework for donor coordination and for the UK to work closely with other development partners including the EU, and Member State development cooperation departments such as GiZ and AfD. The expectation was that this would bring comparative advantages to partnering between development agencies and countries, would be cost effective and promote learning across delivery agencies. FGMC actively tested this approach in a number of countries co-financing actions in Ghana, Liberia, Vietnam and RoC. Whilst important, the experience proved to be extremely resource intensive. Learning from this experience has shaped the approach to partnering through MOUs with other donors envisaged under the new programme, where more straightforward cooperation agreements will be agreed rather than efforts at joint implementation.

Domestic and regional trade far exceeds the international trade in timber suggesting that there are limits to the assumed leverage and influence of external consumer market measures. A long-standing critique of FLEGT has been that it does not adequately address local and regional markets that are mostly supplied by unregulated chainsaw milled lumber. This chainsaw milling sector may have significant impact on forests and is often an important source of livelihoods to many people. In some countries however (Ghana, Guyana, Indonesia, Cameroon) by supporting SMEs to be able to comply with timber legality systems, combined with the incentive of public procurement policies that specify legal sourcing of timber, there is evidence that the % of illegal timber in domestic markets is decreasing. In Ghana the use of illegal timber in the domestic market has been reduced from 80% to less than 50% of total at the last check, through sustained action with the suppliers and vendors. Much still remains to be done to address illegality within the domestic and regional timber markets and will be a focus of the new forest governance programme, FGMC2.
A common concern within the context of FLEGT and land governance is that a push for legal compliance resulting from governance reforms may unintentionally criminalise the customary practices of communities upon which their livelihoods depend. A significant assumption in FGMC was that, where possible, interventions funded by the FGMC programme could anticipate and mitigate these possible side effects ensuring that the voices of communities were heard in deliberative processes and their rights recognised and respected. In Indonesia and Ghana, FGMC provided support to help SME associations comply with TLAS requirements, and in Indonesia the government introduced subsidies to lower the costs for SMEs, e.g. for audits, and providing self-declaration options on timber legality and provisions for group operations. ICAI’s 2021 review of HMG’s international forest and nature portfolio of programmes made a general point about the need to improve on the analysis of the potential “winners and losers” from programme supported interventions. Ensuring ex ante analysis to understand the potential winners and losers from any reform process, and exploring mitigation measures, is a key consideration in future programming.
Timeline of FGMC BC addenda, contracting and logframe amendments
- The original FGMC BC was approved in 2011 with a total value of £250 to run to 2021. The approval of the BC was accompanied by approval of a first tranche of £79m. At the stage the programme was managed directly by DFID.
- An Addendum to the BC was concluded in 2014 to seek approval of a second tranche of funding (£84m) and to agree outsourced management through an external supplier (KPMG) in 2015 – 2018
- An addendum to the BC for spending period 2018-2021 to request a 3rd tranche- £87m and outsourced management agreed with a new Provider - Pegasys from 2018-21
- Addendum to BC developed to provide a costed extension to cover period 2021-2023 – additional £30m
- Outsourced management with Pegasys from 2021-23 (contract extended)
- No cost extension to March 2024 (with final project closure August 2024) approved in 2022

## C: Detailed Output Assessment

Output Number and Title		1 Legal, legitimate and credible mechanisms of forest sector governance and management are in place in producer countries
Output Score		A+
Impact weighting (%)		40%	Impact weighting revised since last AR?	No

Output Indicator	Baseline		Final Logframe Target	Final Result Achieved
1.1 Inclusive public policy	The effectiveness of multi-stakeholder processes varies across countries. / Ghana has followed a very effective multi-stakeholder process and is a model for other countries, but problematic in implementation. / In Liberia, momentum lost for several reasons, including delays in getting DFID contracts in place. / In Indonesia it remains relatively strong, allowing civil society to influence the legality definition and LAS. / DRC has only been established quite recently. However, there are some limitations in representation and inclusiveness, as communities are not represented or, as yet, community level consultation is not as strong. / Guyana- very difficult, limited interactions between Govt and CSO, especially on IP rights / Burma: post conflict, limited engagement with CSO / ROC: strong stakeholder structures established in negotiations.		Functional mechanisms established with strong stakeholder constituency for deliberative approach to policy making; evidence of transformative policy change in 5 focal countries: Ghana, Liberia, ROC, Guyana, Indonesia. / Effective mechanisms are operational in 10 other VPA countries.	Indicator achieved / A+ Positive inclusive change sustained in 5 focal countries through difficult times illustrating the strong multi-stakeholder dynamic / 6 of 8 countries in the 2023 TCI assessment have improved scores since 2022 AR (Guyana, Indonesia, Ghana, Cameroon, RoC China). Declines for Liberia (deteriorating political context), Gabon (deliberation not successful and facilitation ended), and Vietnam (slight drop after the resurgence of last year). / Effective stakeholder deliberations result in decree for a SVLK upgrade enshrining legality and sustainability in Indonesia. / In Cameroon the multi-stakeholder dynamic improved, broader engagement through revamped National Monitoring Committee strong deliberative process is informing decision-making. Joint review of the TLAS (known as SIGIF2) planned with EU in 2023. / VPA negotiations between Guyana and EU ratified Dec 2022 / Increased sharing of benefits through establishment and operationalisation of legal and national scale systems (Liberia, Ghana, ROC in particular) / Deliberation in Burma were progressing positively at the time the programme withdrew because of the civil conflict
1.2 Effective facilitation of VPA processes	Not in place or agreements are being arranged to get facilitation units in place for DFID focal countries		Animating policy processes in all Focal Countries: Indonesia; Ghana, Liberia, ROC, Guyana, / Facilitator's mobilised in response to strong demand from key stakeholders and supporting wider FGMC engagement in Cameroon, Gabon, PNG. / Where appropriate, FGMC has encouraged and inspired facilitation support for other VPA countries including Ivory Coast, CAR, DRC, Vietnam, Laos, Thailand, Honduras.	Indicator achieved / A++ Facilitators sustain key dialogues across 5 focal countries Positive feedback demonstrates their contribution to national reforms, policy coherence, convening stakeholders, enhancing UK bilateral relations and supporting programme oversight. EU is emulating the approach, adopting the facilitation ToRs developed by FGMC. / Cameroon – facilitation credited with helping to bring CSOs into cooperation during challenging time of breakdown in VPA process due to poor relationship EU-MINFOF / Facilitation in non-VPA countries more challenging without VPA structured incentive for political dialogue, but positive indications of appetite for facilitation in PNG / Facilitation contract extension secured for Bridge period responding to strong in-country demand to sustain them
1.3 Progress in the design, development and full operation of a Timber Legality Assurance System (TLAS) / Scoring is based on action in focal countries.	By country: progress in establishment and institutionalisation of TLAS to improve regulation and enforcement indicated in developmental stages: (1) design; (2) develop; (3) test; (4) national roll-out; (5) operate; (6) licensing (7) self- sustaining (not project financed). / Ghana (2 – develop): problematic supplier contract yielded no result; second company engaged and working well. / Liberia (4 – national roll-out): functioning CoC system with SGS - design of upgrade to full legal compliance checking contracted / Indonesia (4 national roll-out): LAS designed, developed but not fully operational across all country or businesses / ROC – (1 – design) LAS system under design		Ghana, Indonesia, RoC fully established self-financing and operational, / Liberia fully operational LAS / Guyana LAS developed and controls upgraded across country / Cross-border transit and import processes established to lock out illegality and avoid leakage / In other VPA countries, systems are at advanced stages relative to its baseline	Indicator mostly achieved / A: Excellent results in some countries, slow in others. All TLAS stages improving relative to baseline: Indonesia 7, Ghana 7; Liberia 5; RoC 4; Cameroon 4; Guyana 2; Gabon 3. / In Indonesia and Ghana, systems have driven sector transformation & improved enforcement. Fully functioning systems. / Cameroon has rolled out its system (SIGIF2) and agree to review it with the EU later in 2023. Good private sector buy-in. / Sustained functioning of Libertrace in Liberia despite weak leadership and deteriorating political context. / Stalled roll out in RoC / Strong design process in Guyana drawing from best practice
1.4 Progress in monitoring and transparency mechanisms. On: / (a) legal compliance and forest crime; / (b) public information; / (c) VPA impacts.	By country; key milestones stages in mechanisms: designed, piloted, tested, operational / • Ghana: The process to develop an impact monitoring framework initiated. / • Liberia: Experience from Ghana will be used inform the development of systems in Liberia. / • Indonesia: Has developed and tested a livelihoods monitoring framework. This will be presented for adoption at the first Joint Implementation Committee (JIC) after ratification in 2014. Small producers are currently likely to suffer market access problems, and so the government, with FGMC support, is funding audits, streamlining processes and providing free training. / Guyana: n/a / ROC: not yet started / Non-lead countries: Impact monitoring studies will be undertaken in other VPA negotiation countries (Cote d’Ivoire, Honduras, Guyana, Vietnam, Laos and Malaysia) supported by EFI, and in Cameroon and Congo it will be developed in 2013/14.		All focal countries have fully operational and effective monitoring and transparency mechanisms. / Independent forest monitoring operational / Effective data management and transparency mechanisms operational without external project support in all DFID focal countries / EITI reporting established in Guyana, Liberia and RoC / Independent Forest Monitor mechanisms with finance mechanism identified for self-sustaining functions / All other VPA countries progress from baseline	Indicator mostly achieved / A+ Excellent progress with systems in place in all focal countries. / Monitoring systems for compliance and forest crimes are operational in all 5 focal countries. / Public information sharing: Good progress sustained in Indonesia and Ghana; information sharing mechanisms designed in Guyana, Gabon, Vietnam. / In Liberia – publishing of timber legality data has deteriorated but systems remain in place and environmental journalism is actively supported and holding government to account. / VPA impacts: Impact monitoring systems established in Indonesia and Ghana but are not fully functional. Weak demand for results / All focal countries have established CSO-led IFM, but sustainability remains key challenge. Indonesia is testing new IFM financing through a new Environmental Fund.

Tropical timber-producing countries can reduce the flow of illegal timber by implementing Timber Legality Assurance Systems (TLAS), underpinned by legal, regulatory, and governance reforms. However, FGMC recognises that for these systems and reforms to be legitimate, robust, and enforceable, they must be developed through a deliberative and inclusive process involving all relevant stakeholders. To this end, FGMC supports national processes through which countries negotiate and implement FLEGT Voluntary Partnership Agreements (VPAs) with the EU - and with the UK in the case of Indonesia. A core requirement of VPAs is that these processes are participatory. Once a country has implemented its TLAS and the broader reforms outlined in the VPA, it can begin issuing ‘FLEGT licences’ for verified legal timber exports to the EU and other markets.
FGMC’s actions under this output are guided by each country’s specific Theory of Change and the priorities set out in VPA annual workplans, which are agreed upon by national stakeholders. Progress is tracked across countries using indicators reported in the PMST Annual Progress Reports. [15]
[15] Available on request
To assess progress toward transformational change, PMST developed a tailored Transformative Change Index (TCI), which measures the quality of multi-stakeholder deliberation over time and across countries. The TCI provides an overall score per country based on dimensions such as inclusivity, alignment of incentives and national capacity, and the extent to which processes are informed by evidence. While individual country scores have improved significantly over the life of FGMC, the index reflects the non-linear nature of change, with fluctuations often tied to shifting political contexts over extended timeframes.[16]
[16] Country scores are not comparable between countries as the scores are influence by the context and expectations of each country.
At the programme level, the overall TCI score rose steadily from 4.1 in 2016 to a peak of 6.3 in 2023. The contribution of deliberative processes to the index has remained consistently high but has plateaued in recent years, reflecting the transition of many countries into the implementation phase of VPAs and the move toward internationally recognised licensing. Meanwhile, scores for other dimensions (such as irreversibility and innovation) have continued to rise, as systems in newer countries become more embedded and demonstrate increasing resilience.
The basic model used to measure transformational change – which relies on country-level scoring against pre-defined criteria - has been carried forward into the design of MEL processes under FGMC2. It will continue to inform the assessment of output and outcome indicators in the programme logframe. However, it is acknowledged that a more robust and independent scoring methodology will be required in the future.
Output 1.1 Inclusive public policy making: Status: Indicator achieved.
FGMC is successfully supporting national stakeholders to contribute to policy making and resolve contested issues around forest governance. National platforms providing political space to voice informed and organised stakeholder positions are functioning in all VPA countries as is capacity to engage effectively. Quality of engagement varies over time and in some countries, processes have slowed this year and inclusion has been weak. Examples of effective and inclusive public policy making are presented below from Indonesia, Ghana and Liberia.
Indonesia
In 2020, the Furniture and Craft Industry Association of Indonesia attempted to weaken the Sistem Verifikasi Legalitas Kayu (SVLK) - Indonesia’s timber legality assurance system, which ensures legal compliance across forest management, harvesting, transport, processing, and trade of timber and timber products. This effort was effectively countered by a coalition of FGMC partners, who leveraged their expertise, evidence, and networks to:
1. Provide targeted data and analysis to relevant government institutions, directly challenging the rationale for removing SVLK requirements on timber exports;
2. Coordinate international timber trade federations (from the UK, USA, Japan, Korea, Australia, and the EU-STTC) to issue public statements in support of SVLK;
3. Mobilise civil society to engage with the media and raise public awareness;
4. Engage with national timber associations to identify and strengthen internal support for maintaining SVLK.
FGMC’s formal collaboration with the Indonesian government through MFP4 - alongside its support to civil society and private sector actors - created the enabling environment for this coordinated response. Ultimately, these efforts contributed to the revocation of the regulation that threatened the integrity of the SVLK system.
Ghana
A major bottleneck in multi-stakeholder negotiations around the Ghana VPA was the conversion of existing logging permits into new Timber Utilisation Contracts (TUCs). In 2015-16, large-scale logging companies strongly resisted this transition, particularly opposing the payment of Timber Rights Fees required before conversion of leases can take place.
A second contentious issue was the use of “Special Permits” - harvesting permits issued directly by the Minister outside of standard tendering and contract award procedures. These permits were widely viewed as a loophole that undermined the VPA’s objectives of transparency, accountability, and legal clarity. Often associated with political patronage, Special Permits lacked transparency and ran counter to the VPA’s commitment to public disclosure, transparency and accountability.
Although the law permitted Special Permits prior to 2017, many stakeholders considered this provision a legal loophole. During VPA negotiations, it was ultimately agreed that timber sourced through Special Permits would not qualify for FLEGT licensing. Civil society organisations strongly advocated for these gaps to be addressed through a new legal instrument. Initially, the government proposed a working group to develop a ‘manual of procedures’ - a solution with limited legal weight. However, sustained lobbying and negotiation led the Ministry of Lands and Natural Resources (MLNR) to agree to draft a new legal instrument. This was jointly developed by the Forestry Commission, civil society representatives, and the Attorney General’s office, and was approved by Parliament in November 2017.
Interestingly, private sector actors increasingly aligned with civil society’s position. Many viewed the legal loopholes as enabling unfair competition and preferred a transparent, rules-based system for licence allocation. This shift catalysed greater organisation within the private sector, which had previously been fragmented and inconsistent in its engagement. The Ghana Timber Millers Association, for example, had often attended meetings but pursued separate lobbying efforts with government officials.
As discussions progressed, both large and small companies began advocating for a unified private sector voice. This led to the formation of the Forest Industry Association of Ghana (FIAG) - an umbrella organisation representing the full spectrum of private sector voices.
Liberia
The 2009 Community Rights Law provides a legal framework that empowers local communities located in or near forest lands to access, manage, use, and benefit from forest resources for sustenance, livelihood improvement, and community development. Community forest areas are managed by Community Forestry Management Boards (CFMBs), and the CFMB Union (representing CFMBs at the national level) was allocated three seats on the National Multi-Stakeholder Monitoring Committee (NMSMC).
Concerns have been raised by CFMBs and national and international NGOs working in Liberia regarding collusion between timber companies and community forestry leaders over company access to timber resources within community forest areas. In October 2018, Global Witness published a report titled “Power to the People?” [17] which highlighted how logging companies were seizing control of community forest areas by defrauding local leaders. Subsequent research by SDI and Global Witness indicated that many Community Forestry Management Agreements (CFMAs) were approved by the government without fulfilling all legal requirements in the mandated 9-step process. These agreements were often negotiated locally between companies and community leaders but failed to generate meaningful forest revenues for the affected communities.
[17] 2018. Global Witness. Power to the People? How companies are exploiting community forestry in Liberia.
These concerns have prompted significant discussions within the Joint Implementation Committee of the VPA. A CFMA working group was established to explore how CFMAs could be integrated into the legality matrix and the TLAS, ensuring they are subject to the same scrutiny as other commercial concessions. With support from ClientEarth, templates for Commercial Use Contracts (CUCs) were developed to guide communities and companies in negotiating such agreements.
Additionally, civil society has raised concerns about the unlawful granting of Private Use Permits (PUPs) and CFMAs. The irregular allocation of PUPs led to investigations and corrective actions, including a moratorium on the issuance of new PUPs and the suspension of operations under most existing ones. Further measures included an audit of the PUP issuance process by the General Auditing Commission (GAC), a review of all allegations by a Special Independent Investigative Body (SIIB) established by the President, the issuance of an Executive Order outlining additional actions, and the suspension of FDA officials pending prosecution.
Output 1.2: Effective facilitation of VPA processes. Status: Indicator achieved
A key aspect of FGMC’s support to producer countries has been the provision of FLEGT facilitators, whose role is to support and safeguard the multi-stakeholder deliberative process. FGMC has funded facilitators in several countries, though not always continuously. [18] These facilitators are independent and unaffiliated with any institution or interest group. Unlike EFI, which provides technical support, facilitators do not advise on specific technical aspects of the VPA. Instead, they play a vital role in brokering relationships among forest sector stakeholders.
[18] Countries supported include Ghana, Liberia, Guyana, ROC, DRC, Cameroon, Ivory Coast, Vietnam and Papua New Guinea
The FGMC mid-term evaluation described facilitators as “a valuable and effective investment in building inclusive, locally driven processes, ensuring equitable participation, facilitating communication between national stakeholders, supporting increased collaboration and coherence, and alerting external stakeholders when problems or bottlenecks occur.” [19]
[19] Tripleline. 2017. Forest Governance, Markets and Climate. Mid term review. Independent Review Team.
Cameroon, which until recently did not have a facilitator, experienced delays and stagnation in its VPA process. While this cannot be solely attributed to the absence of a facilitator - given other forms of support within the Ministry - it may have contributed, or at least delayed, the identification of issues. Facilitators have access to modest budgets to convene stakeholder meetings aimed at clarifying interests and representation (e.g., among national NGOs) and improving coordination among diverse actors involved in FLEGT.
Effective facilitation remains crucial to maintaining a constructive and engaged dynamic. Its value has been recognised to the extent that the EU is now funding facilitators in most EU-VPA countries, adopting FGMC’s terms of reference that emphasise the impartial, behind-the-scenes nature of the role. Positive feedback continues to be received, and country-specific examples of facilitator impact are presented below:
- Ghana: A key point of contention between Ghana and the EU has been the EU’s insistence that timber confiscated by the government cannot enter legal export supply chains. The European Commission cited a legal opinion as the basis for this stance but initially declined to share it, leading to a breakdown in trust and accusations of bad faith from Ghana. In September 2022, the facilitator was invited to a formal meeting of the Parties. With their support, the Parties agreed that excluding confiscated timber would not be a precondition for licensing. Ghana also committed not to export such timber to the EU once the EU Deforestation Regulation (EUDR) takes effect. The facilitator’s role as an impartial ‘honest broker’ was key to restoring trust and reaching consensus.
- Republic of Congo: After ratifying its VPA in 2013, implementation stalled. When the facilitator arrived in mid-2016, government oversight was weak, and there was little analysis of delays. Political tensions between the government and the EU delegation further complicated progress. The facilitator used the appointment of a new forest minister and changes at the EU delegation to reset relationships. She organised a retreat to revisit the VPA’s rationale, identify national priorities, and develop a theory of change. This led to the country’s first VPA work-planning exercise, resulting in a strategic plan (2018–2022), and frameworks for monitoring, evaluation, and communication. The facilitator’s coordination helped rebuild momentum and stakeholder engagement, enabling them to develop a shared vision and agree priority actions for the next five years.
- Guyana: In 2014, forest governance was a taboo topic, and tensions between the Guyana Forestry Commission/National Technical Working Group and an NGO representing Indigenous peoples had stalled progress. The introduction of a facilitator marked a turning point. Two seminars in 2014 and 2016 focused on forest governance, helping to normalise the topic and foster dialogue. Stakeholders - including non-state actors - were engaged in reviewing forest policy, and transparency improved significantly. Public access to forest sector information, including concession allocations, was expanded. The facilitator played a central role in ensuring stakeholders were informed and empowered to participate meaningfully in the VPA process.
- Liberia: Facilitation was critical in re-establishing dialogue between the Government and the EU after relations broke down due to the government’s failure to act on a widely known illegal logging case. No Joint Implementation Committee meetings had been possible for some time, and the facilitator helped reopen channels for engagement.
Output 1.3: Progress in design, development and operation of Timber Legality Assurance Systems Status: Indicator mostly achieved
Timber Legality Assurance Systems (TLAS) translate governance reforms into practice by establishing clear legal requirements, systematic controls, independent audits of supply chains, and enforcement mechanisms - culminating in the issuance of export licences. Progress in TLAS development across producer countries is tracked using a seven-level scoring system, with higher scores indicating greater effectiveness, institutionalisation, and functionality. Countries are at different stages of TLAS development: from design (e.g. Guyana), to testing (Gabon), roll-out (Republic of the Congo, Cameroon), operation (Liberia), licensing (Indonesia), and full national implementation (Indonesia and Ghana). Progression is often slow and non-linear, with processes sometimes stalling before restarting.
Country examples:
- Indonesia: The SVLK system has been upgraded to better reflect sustainability and legality, in response to evolving international due diligence requirements. MFP4 supported studies and recommendations to strengthen SVLK-certified products from social forestry areas and helped MoEF develop SVLK licensing at the Forest Management Unit level to improve local compliance.
- Ghana: The Ghana TLAS (GhTLAS) is now fully operational across the private sector and has become the standard for timber trading. The launch of the Ghana Wood Tracking System in December 2022 has boosted national pride and ownership, leading to improved company-level compliance and gains in the domestic market. NDF data suggests illegal timber on the domestic market dropped from 80% in 2016 to around 50% in 2022. This progress is linked to vendor registration efforts, legal sourcing apps, and public procurement reforms. Forest sector revenue rose by 640% between 2014 and 2017. With Parliament’s ratification of new concession agreements, the final barrier to FLEGT licensing has been removed.
- Liberia: It is noteworthy that the ‘Libertrace’ system remains operational at a national scale in spite of a deteriorating governance context. While enforcement is weak, continued stakeholder engagement reflects enduring commitment to the TLAS approach.
- Guyana: TLAS development is progressing well. With UK support via EFITAP, GFC’s head and field offices, main datacentre, and disaster recovery centre were upgraded. During Minister Zac Goldsmith’s visit in February 2023, the new IT systems - forming the backbone of TLAS - were officially launched.
- Republic of Congo: TLAS roll-out has stalled, partly due to delays in EU support, which is now resuming. FGMC, through EFITAP, continues to support the Ministry of Forest Economy in building capacity to manage the system down to district level, fostering a positive working relationship.
- Gabon: The forest ministry is developing an e-governance system to centralise forest-related information and create a single access point for both government and the public. This initiative is supported by GSEZ developers and EFITAP IT experts (until February 2023).
TLAS are demonstrating clear value to implementing countries. States such as Laos and Cameroon continue to invest in their TLAS and the broader VPA process, even as EU market incentives fluctuate or negotiations remain unresolved. This commitment reflects the perceived domestic benefits of TLAS, beyond access to EU markets. Evidence of this value comes from two main sources:
National presentations and independent assessments: Ghana and Indonesia have actively showcased the benefits of their TLAS - particularly in improving forest governance and increasing revenue - during the FACT dialogues. A 2022 CIFOR assessment further validated the VPA’s impact, highlighting improvements in governance, institutional effectiveness, reductions in illegal logging, and better forest conditions. While economic benefits such as increased revenues, improved livelihoods, and more secure rights are harder to quantify in the short term, they are also emerging.

Growing demand for international recognition: Producer countries are increasingly calling for global recognition of their national legality systems. At UNFCCC COP27, 6 countries (Indonesia, Cameroon, Ghana, Guyana, Liberia, RoC) launched the Broader Market Recognition (BMR) Coalition. Building on their VPA experience, they aim to promote more ambitious forest governance and seek recognition of their efforts in international markets (see Joint Statement[20]). The BMR Coalition is supported by global trade and business associations, echoing calls made in the Tropical Timber Accord (launched at COP26 by Timber Development UK and others) for international recognition of verified forest governance systems. To date, only the EU and UK have formally committed to recognising these national forestry systems through VPAs.
[20] https://forestgovernance.org/joint-statement/
Output 1.4 Monitoring and transparency[21]:
[21] To note that FGMC’s focus is on the establishment of the systems. Support for governments to actively follow up and implement enforcement actions based on the information provided by the monitoring systems, is not supported by FGMC.
Improving monitoring, reporting, and transparency is essential to sustaining governance reforms. VPAs introduce critical tools and open space for community and CSO-led surveillance, enhancing accountability, benefits, and impact. FGMC supports governments and civil society to establish accountability mechanisms—some of which are now institutionalised (e.g. Ghana, RoC) and potentially self-sustaining (e.g. Indonesia). Examples of strengthened transparency and accountability:
- Ghana: Article 20 of the Ghana–EU VPA commits to public disclosure of key forest sector information, including harvesting rights, designated areas, schedules, fees, and social responsibility agreements. This marks a significant improvement in sector transparency. CSOs can now request details of Timber Utilisation Contracts from the Forestry Commission (FC), enabling monitoring of community agreements. Civil society advocacy also contributed to the 2017 Timber Resources Management and Legality Licensing Regulation (LI 2254), which mandates timely public access to forest sector information, either via request or publication on the FC website.
- Liberia: Annex IX of the Liberia–EU VPA outlines transparency commitments, including public access to information on forest management, resource allocation, production, fees, law enforcement, and processing. The VPA has led to notable improvements in information sharing, including the publication of tax revenue reports on the FDA website - reportedly a first among VPA countries. CSOs credit the VPA, rather than the Freedom of Information Act, for enabling access to previously withheld data such as land rental fees. The FDA also developed the Interactive Forest Atlas of Liberia, a GIS-based platform that integrates forest allocation data with near-real-time forest cover and change data from Global Forest Watch. This dynamic tool supports forest management and land use planning and is regularly updated by FDA with support from WRI.
In most countries, Independent Forest Monitoring (IFM) led by local civil society remains a vital tool for oversight, and transparency-focused business practices continue to play an important role in strengthening forest governance. Examples include:
- RoC: A national IFM strategy, developed by CIDT and partners, now promotes stronger coordination between mandated and non-mandated IFM and enhances links to civil society advocacy.
- Indonesia: IFM is institutionalised through JPIK, a national body with a legal mandate to oversee the performance of Conformity Assessment Bodies (CABs) and report non-compliance. MFP4 has supported field-level IFM operations and helped JPIK develop a jurisdictional SVLK monitoring scheme in collaboration with three Forest Management Units (KPHs) in North Maluku and Central Kalimantan. Guidelines for jurisdictional monitoring have been produced for both IFM and KPHs and shared widely, serving as a reference for broader adoption.
- Ghana and Indonesia: Both countries recognise the value of IFM and its potential to be extended to other commodities. However, securing long-term sustainable financing remains a challenge. In Indonesia, the Environment Fund includes a designated window for supporting independent monitoring, though no funding has yet been allocated.
Lessons learned through this output, and recommendations for future programming
The multi-stakeholder approach supported through FGMC’s delivery mechanisms has been crucial to the resilience of the VPA process.
Despite challenges - including political transitions, private sector resistance, and lack of support from some stakeholders - momentum has been sustained through established multi-stakeholder structures. FGMC’s ability to mobilise data and actors across government, civil society, and the private sector, in both producer and consumer countries, has proven effective. This is well illustrated by cases from Liberia and Ghana.
- Liberia: Despite political and economic pressures, Liberia has built a credible forest sector under the VPA, centred on its TLAS known as Libertrace. In November 2019, the Independent Auditor flagged illegal logging linked to TSC A2. This triggered a forensic investigation by the Ministry of Justice and FDA Board, supported by civil society monitors. Bilateral discussions with the EU and UK helped maintain pressure. In March 2021, the government announced the revocation of these logging permits at the National Multi-Stakeholder Monitoring Committee. The TLAS structures enabled early detection and response, supported by evidence from the EFI FLEGT Facility and civil society, reinforcing Liberia’s commitment to good governance and international credibility.
- Ghana: The illegal logging of Rosewood became a national scandal following an EIA-US report questioning the effectiveness of the ban. Ghana’s engagement in the VPA process and its ambition to achieve FLEGT licensing prompted a swift government response: an independent investigation and reinforcement of the ban, which was made indefinite. EIA continued monitoring using global trade data, initially showing a drop in exports to China, though later data revealed a resurgence on its ‘Rosewood Revealed’ website. Civil society disclosures prompted further investigation. The VPA framework created the accountability and pressure needed for government action.
Without an external lever like the VPA, establishing a meaningful deliberative process is challenging due to the inherent mistrust between stakeholders.
In Gabon, a multi-stakeholder platform was launched in March 2022 with support from a facilitator, but in the absence of a VPA framework, it has been difficult to define clear objectives and secure genuine engagement. This experience highlights the importance of political space and structured incentives in fostering inclusive dialogue. Lessons from Gabon will be valuable as the programme considers expansion into non-VPA contexts, such as the Pacific region.
Timber Legality Assurance Systems (TLAS) have become a cornerstone of forest governance reform, driving significant improvements in legal compliance, transparency, and accountability across the sector.
Tropical timber-producing countries can curb illegal timber flows by implementing TLAS, supported by legal, regulatory, and governance reforms. However, FGMC emphasises that for these systems to be legitimate, robust, and enforceable, they must be developed through a deliberative, inclusive process involving all stakeholders. In Ghana, civil society has played a critical role in TLAS development and rollout. For example, NDF secured funding under its accountable grant to establish a transparency portal that provides public access to system-generated reports.
Key lessons from TLAS and wood tracking system implementation include:
- Government commitment and long-term vision are essential for success.
- Nationwide system development takes longer than expected, and local complexities (e.g. infrastructure, capacity) must be carefully considered.
- Sustained UK support has been vital, enabling governments to iterate and improve systems over time.
- Broad sectoral reforms, supported by change management strategies, increase the likelihood of successful national information systems.
- Ongoing dialogue with non-state actors is crucial for credibility.
- Public access to system-generated information enhances transparency and accountability.
- Building on existing control procedures improves user adoption and system integration.

Output Number and Title		2 Public policies and private business standards that tackle trade in illegal timber
Output Score		A+
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Baseline		Final Logframe Target	Final Result Achieved
2.1 EU/UK Timber Regulation: Compliance and understanding by operators, monitoring organisations, third-party certification schemes, and trade federations.	Minimal understanding and awareness of EUTR and consequently, low levels of compliance.		Widespread knowledge of UK and EUTR by EU-based economic operators / Widespread due diligence practice in business standard / SME operators and suppliers able to apply DD. / FGMC supported tools effectively helping companies address risk and requirements (uptake) / Widespread knowledge and appreciation of FLEGT licenses	A+: Fully achieved by EOP / Private sector shift to EU/UKTR compliance is widespread. / Widespread uptake of tools to aide compliance by businesses e.g., of WRI’s Open Timber Portal covering EUTR/UKTR and other regulations globally. A total of 23,809 new users since the OTP was released, exceeding target by 116%. / Awareness of EUTR increased amongst private sector operators in the UK, and across international trade federations in producer and consumer countries in partnership with TDUK
2.2 EUTR/UKTR Enforcement: Competent Authorities (CA) awareness of EUTR enforcement roles and responsibilities.	Limited understanding by Competent Authorities of the EUTR. / Systems in place to enforce it are not established across EU Member States.		Monitoring and public reporting by competent authorities on EUTR and UKTR compliance. / Increased successful enforcement actions against EUTR and UKTR infractions. / Competent Authorities are enforcing EUTR compliance across all EU member states and coordination with UK CA informed by FGMC-supported intelligence / UKTR in place post EU exit sustains UK commitment to FLEGT policy domain	A+: Achieved ahead of EOP / Establishment of the Timber Regulation Enforcement Exchange (TREE) facilitated by Forest Trends to strengthen the informal coordination of enforcement agencies to tackle import of illegal timber / Enforcement actions taking place regarding timber imports in contravention of sanctions regimes (Myanmar and Russia particularly in the spotlight). EIS and FT contributing important intelligence. / EUTR loopholes and inconsistencies are addressed in the EUDR, heavily influenced by FGMC partners, and enforceable from 2026
2.3 Market measures in other consumer markets: Consumer markets (notably China) implement measures to reduce consumption and trade in illegal timber globally.	Lacey Act in force, but no prosecutions. / No other market access measures by consumer countries. / Timber procurement policies adopted by 9 countries but limited take up. / China dominating global timber market; unclear interest in promoting legal timber trade; see it as the responsibility of national governments to regulate their own production; market measures not seen positively. China mainly interested in sharing lessons of its tenure reforms in promoting tree planting/ stewardship.		Regulators and other stakeholders across key timber processing and consumer countries implement coherent and coordinated measures to address illegal timber are working together to significantly shift global demand for timber to low-risk supplies. / Evidence of increased coherence in implementing anti-illegal logging measures across jurisdictions. / Market shift towards timber supplies with low risk of illegality. / FGMC-linked actions creating tools and information to inform implementation of demand side measures / China has import regulation/ measure in place / China overseas businesses adopt responsible and legal sourcing. especially in focal countries. / China-UK partnership promotes legal and responsible / China establishes mechanism to recognise FLEGT licences.	A: On track for transformational impact notably through guiding the interpretation of China’s forest law that makes it illegal to place illegal timber on the market (strong weighting given the transformational potential). / The revised Forest Law was adopted by the Chinese government in Dec 2019 and came into effect in July 2020. The amended forest law includes a ban on buying, transporting, and/or processing illegally sourced timber, and requires processing companies to establish a data record of raw materials and products (Article 65). / Chinese industry associations, CNFPIA and CTWPDA, developed legality standards for business, and legality checklists for 4 countries including Gabon and Liberia building linkages to other aspects of FGMC. / In Vietnam, stronger measures are taken to control the import of illegal timber (and the subsequent processing and re-export of timber products) following a trade dispute with the USA
2.4 Financial institution (FI) policies and practices adapted to mitigate risks of illegality through timber supply chains.	Minimal efforts on the part of financial institutions to address risks associated with illegal practices in timber supply chains. / Minimal awareness among regulators about the connection between illegal logging and regulatory and financial risks. / Limited awareness among financial institutions and regulators of tenure risks associated with company operations in community lands lacking formal legal recognition. Dominant land/resource sector business models do not take community land tenure rights and livelihoods into account.		Major financial institutions demonstrate understanding of the risk associated with illegal practices in timber supply chains, including risks associated with company operations in community land lacking formal legal recognition and contribute to the dialogue on these issues, adopt policies to address these risks, and are significantly changing their behaviour and practices in accordance with these policies. / Major financial institutions are transparent in how they manage risks associated with illegal logging, violation of land rights, and other illegal practices in timber supply chains.	A+: Excellent progress exemplified by strong focus on disclosure and assessment tools to de-risk finance & investment with increased support from financial institutions (FI) / All signatories to Race to Zero’s Commitment Letter on Eliminating Commodity-Driven Deforestation were assessed in 2022 to show progress and maintain accountability. / The Taskforce on Nature-related Financial Disclosures (TNFD), (supported by FGMC-grantee Global Canopy) released its fourth and final beta framework for nature-related risk management and disclosure in March 2023. This marks the fourth and final draft of the framework. / InFIT and FGMC grantees have supported Chinese Banks and financial institutions to develop risk assessment tools for deforestation and biodiversity.

Indicator 2.1: EU/UK Timber Regulation: Compliance and understanding by operators, monitoring organisations, third-party certification schemes and trade federations. Indicator fully achieved
Through accountable grants, FGMC has supported the development of tools that help EU-based economic operators and Competent Authorities strengthen their due diligence. These include ClientEarth’s Forest Logbook, WRI’s Open Timber Portal, ZSL’s SPOTT, and Forest Trends’ National Governance Indicators. FGMC has also supported Timber Development UK in engaging European member associations and UK-based operators to improve understanding of EUTR and UKTR requirements.
A recent Forest Trends assessment found that European operators are collecting and scrutinising more information from suppliers. Companies increasingly use a combination of tools, such as Transparency International’s Corruption Perception Index and FSC risk assessments, to evaluate risks of illegal timber entering supply chains. Risk assessments are helping flag high-risk countries and are accompanied by increased investment in mitigation measures, both human and financial. As a result, many companies report reduced imports of tropical hardwoods from high-risk countries (e.g. Brazil, China, CAR, Solomon Islands, PNG), while imports of licensed timber have increased.
The EU Timber Regulation (EUTR) has contributed to a decline in tropical timber imports from high-risk countries like CAR and DRC, with some substitution from lower-risk temperate sources. Conversely, the introduction of FLEGT-licensed timber from Indonesia has led to increased imports of tropical timber from that country.
In response to evolving market norms, producer countries with long-standing national legality verification systems, such as Indonesia, are now seeking greater international recognition beyond the European market which is widely seen as failing to provide positive incentives. Six tropical countries (Indonesia, Cameroon, Ghana, Guyana, Liberia, and RoC) have formed the Broader Market Recognition Coalition (BMRC) to develop a framework that incentivises national systems, building on VPA-FLEGT experience. FGMC has supported the coalition’s development and convened a series of meetings to help launch it.
Indicator 2.2 EUTR/UK Timber Regulation compliance and enforcement: Indicator fully achieved
While enforcement of the EU Timber Regulation (EUTR) increased - reflected in more fines and consignment seizures - challenges remain around consistency across EU/UK jurisdictions and evolving sourcing practices designed to circumvent enforcement. FGMC grantees such as EIA and Forest Trends (FT) have worked to identify these gaps. EIA engaged with multiple Competent Authorities (CAs) and uncovered circumvention routes through Italy and Croatia. In coordination with EIA’s exposé, FT published a blog highlighting additional high-risk entry points. These findings were shared with relevant CAs, triggering enforcement actions. Both organisations also responded to direct requests from enforcement authorities.
The Timber Regulation Enforcement Exchange (TREE), supported by FGMC and facilitated by Forest Trends, is an informal network of law enforcement agencies responsible for implementing demand-side measures (e.g. EUTR, UKTR, US Lacey Act). Initially launched to help European CAs share enforcement experiences, TREE has expanded to include jurisdictions such as the US, Australia, New Zealand, and Southeast Asia. It was particularly valuable in the early stages of EUTR implementation, when many enforcement officers were unfamiliar with the timber sector.
As CAs have gained experience and collaboration has improved, TREE’s added value has shifted. While it has no formal objectives, members widely regard it as a useful platform for sharing lessons, intelligence, and risk assessments. Meetings have proven especially helpful for enforcement staff needing networks and insights to assess risks from high-risk countries. An unexpected benefit has been the facilitation of joint enforcement operations. For example, intelligence about questionable timber (e.g. Myanmar teak) reaching one CA can be quickly shared with others - enabling coordinated action across jurisdictions without bureaucratic delays.
Indicator 2.3 Market measures in other consumer markets: Consumer markets (notably China) implement measures to reduce consumption and trade in illegal timber globally. Indicator on track for transformational impact
FGMC worked with several non-European consumer markets (primarily in Asia) to introduce or strengthen demand-side measures aimed at restricting imports of illegally harvested timber. The focus has been on China. An important breakthrough was the 2020 revision of China’s Forest Law, which now prohibits the purchase, transport, or processing of timber known to be illegally sourced (Article 65) and requires processors to maintain records of raw materials and products. Chinese trade associations are operationalising this through country-specific legality checklists for import assessments.
Additional action in other consumer countries includes:
- Japan: In 2012, Japan was the second-largest importer of tropical timber, much of it from high-risk countries. At the time, it lacked legislation to exclude illegal timber. Global Witness and partners campaigned for reform, engaging lawmakers and companies, and sharing lessons from the EU and US. This led to the Clean Wood Act in 2016, which introduced a voluntary due diligence system. Following a 2022 review, and with input from Forest Trends, the law was strengthened to make due diligence mandatory and introduced penalties for non-compliance.
- South-Korea: FGMC supported revisions to the 2018 Act on Sustainable Use of Timbers, which now includes provisions to exclude illegal timber from the market by restricting its import and processing.
- Vietnam: Vietnam’s TLAS initially focused on domestic legality, but concerns grew over the legality of imported timber. In response, Decree No. 102/2020/ND-CP introduced due diligence requirements for importers to prevent illegal timber from entering supply chains. Forest Trends, with FGMC support, played a key role in providing technical assistance and convening stakeholders.
FGMC has also worked to mitigate the negative impacts of Chinese timber trade in Africa, building on progress in China. InFIT supported the development of guidelines for Chinese timber traders operating in producer countries, covering legality, workers’ rights, and health and safety. In Gabon, FGMC helped create a platform that encouraged Chinese companies—representing 80% of Chinese forest investment in the country—to make sustainability commitments.
Indicator 2.4: Financial institution (FI) policies and practices adapted to mitigate risks of illegality through timber supply chains. Indicator demonstrating good progress
The Taskforce for Nature-related Financial Disclosures (TNFD) officially launched its recommendations for nature-related risk management and disclosure in September 2023, following two years of development supported by FGMC via Global Canopy (until December 2022). This included four prototype iterations and sector-specific guidance (e.g. forestry, financial institutions), as well as a discussion paper on the biodiversity footprint of FIs. TNFD’s launch signals growing recognition among financial institutions, companies, and other actors of the financial risks linked to nature loss and the need to integrate climate and nature priorities.
With FGMC support, the Interlaken Group (IG) - managed by RRI - engaged businesses, investors, financial institutions, and civil society to embed tenure considerations into corporate and investment practices. Over the course of FGMC’s support:
- 17 companies and investors were engaged to consider tenure issues or assess their portfolios/supply chains;
- 9 tested new approaches to managing tenure on the ground;
- 2 companies in Indonesia changed institutional standards or practices as a result of this engagement.
FGMC grantees have contributed significantly to the development of the EU Sustainable Finance Action Plan. In 2019, following advocacy by Global Witness (GW), the EU adopted the Disclosure Regulation, requiring investors to conduct due diligence and disclose mitigation measures for adverse impacts. GW continued to push for effective implementation. In June 2020, the EU Taxonomy Regulation was published, establishing a classification system for environmentally sustainable activities. GW, in coalition with European NGOs, helped strengthen the proposal. In September 2020, the European Parliament adopted a non-binding resolution urging the Commission to introduce due diligence rules for deforestation-free supply chains, including for financial institutions. GW had anticipated this move, publishing joint briefings with ClientEarth and the NGO Coalition to advocate for such measures.

Lessons learned through this output, and recommendations for future programming
Demand-side regulations are expanding and influencing global supply chains
According to Forest Trends’ 2020 review, 10 markets have introduced timber import regulations: the US, EU+EFTA, Australia, Canada, Indonesia, South Korea, Malaysia, Vietnam, Colombia, and Japan (via voluntary due diligence). Thailand is developing import controls, and Japanese Registering Bodies now advocate for mandatory due diligence. Enforcement in key markets - particularly the EU, US, and Australia - is driving increased scrutiny of raw material sourcing in manufacturing hubs like China and Vietnam.
In regulated markets demand is reducing illegal imports.
Vietnam’s forest product exports reached $14.5 billion (up 12% from 2020), but the country faces a timber supply challenge, relying heavily on imports from high-risk countries. US investigations into illegal timber imports in 2021 prompted trade tensions and potential tariffs. With support from Forest Trends, Vietnam committed to strengthening its TLAS and improving customs enforcement with high-risk source countries to maintain market access.
China’s evolving role is critical to global forest governance.
China is uniquely positioned to lead a shift toward legal and sustainable timber trade. While sustainability has historically been a low priority for Chinese importers, the 2020 revision of the Forest Law introduced a ban on sourcing illegal timber and mandated record-keeping (Article 65). CTWPDA, representing half of Chinese wood traders, is developing an online matchmaking platform and country-specific Legality Checklists to support legal sourcing. B2B pilots in Liberia and Gabon are testing these tools. As China is a major destination for timber from FGMC-supported producer countries, its growing demand for legal compliance offers a powerful incentive for continued governance reforms.

Output Number and Title		3 Increased knowledge, momentum and global policy engagement
Output Score		A++
Impact weighting (%)		20%		Impact weighting revised since last AR?		No

Output Indicator	Baseline		Final Logframe Target		Final Result Achieved
3.1 Availability and communication of evidence on governance, market and tenure reform	Evidence is produced and communicated via web sites and key events. / Limited strategic plan for research.		High quality research and evidence produced which is clearly communicated. / Research and evidence are being effectively used to progress policy and regulatory reform at global and national levels / FGMC experience informs future UK policy on climate, forests, forest-risk commodities and Trade.		A++ Fully achieved - Extensive evidence and analysis produced by community of practice informing policy processes in the UK, EU, USA, China, Japan as well as tropical forest countries, including more recently: / Important policy processes in the UK including Due Diligence regulations under the UK environment act, Timber Procurement policy update, FLEGT Policy review, Financial Services Bill / Significant contribution to COPs (climate and biodiversity)– the Biodiversity COP in December 2022, ensuring governance and the rights of IPLCs were front and centre. / Grantees such as Chatham House, Forest Trends, EIA, Global Witness, WCS provided evidence and opinion informing the US’ The Fostering Overseas Rule of Law and Environmentally Sound Trade (FOREST) Act
3.2 Size, diversity and influence of communities of practice	Approximately 200 participants at Chatham House stakeholder update meetings over the past decade. / Regional events in Africa, Asia, China (e.g. CIDT Africa; FAO/EFI Asia).		Diversity and scope of policy engagement, including CBD and UNFCCC COPs, / Community of practitioners responding to policy-shaping opportunities and sector governance challenges at national, regional and global levels		A++ Fully achieved. FGMC’s community of practice has engaged in a wide range of policy processes and through a range of media to ensure accessibility. / RRI’s Path to Scale platform has become the leading multi stakeholder platform for mobilizing and coordinating support to advance the rights of IPLCs. / FGMC grantees, partner countries, and the PMST have brought experience and expertise to the FACT dialogue – particularly the Trade and Traceability theme. / Forest Trends translated the EUDR, proposed US FOREST Act, New York and California Deforestation-free Procurement Acts, into Chinese resulting in awareness amongst relevant Chinese government agencies and business associations and processes for preparation put in place.
3.3 Communication and engagement to sustain political momentum	Effective communication and engagement with influential political decision-makers and in countries with a significant forestry sector (whether as producers, processors or consumers).		Effective engagement with UK, EU, global and business decision-makers, demonstrated by uptake evidence and engagement / Convening policy dialogues to inform decision making related to illegal timber and wildlife trades, forest risk commodities and sustainable production, investing in green and sustainable (investor policies and practices) / Policy dialogues in EU to protect and restore forests, future trade arrangements and green deal; in the UK actions in support of GRI and shaping future partnerships / Evidence contributes to 2021 Biodiversity and Climate COPs		A++ Fully achieved. / Sustained and influential engagement with the EUDR process, and other processes such as: / Chatham House annual global forum on forest governance with a special topical focus on the theme of conservation colonialism brought together audiences from across Central Africa to address governance challenges in the region with the conclusion that co-creation was needed – resonating with the FGMC deliberative MSH approach. / At CBD COP15, TNFD received widespread recognition as being the reference framework for reporting on nature-related risk and WCS made significant contributions to the Global Biodiversity Framework indicators Continuing years of advocacy supported by FGMC to promote a stronger focus on gender in climate and forest policy making, RRI contributed to an international advocacy tool: Our Call to Action, which motivated the creation of the Women in Global South Alliance for Tenure and Climate, launched at the COP-27

Output 3 is defined as “increased knowledge and momentum for change” and is, in a sense, an “enabling output” that contributes to achievement of Outputs 1, 2 and 4. It has three core activities:
1. Convening stakeholders and networks to explore or document new knowledge and best practices;
2. Generating evidence at national or international levels on key issues or themes;
3. Strengthening knowledge within the FLEGT community of practice.
Compared to the other outputs, Output 3 involves a more modest investment and scope. Its Theory of Change is based on the premise that high-quality knowledge products, when integrated into an informed and connected community of practice, can generate momentum for change through global networking and influence.
Indicator 3.1: Knowledge products. Indicator status: Fully Achieved
FGMC grantees have produced a wide range of high-quality knowledge products that document impacts, share lessons, and support FLEGT implementation across diverse country contexts. These outputs draw on grounded, field-level experience and contribute to the growing body of literature on practical approaches to tackling illegal logging and influencing policy reform. The improved information generated has informed decision-making at both national and global levels. Examples of evidence-driven policy and practice change include:
- Fern: Produced the first comprehensive communications on FLEGT VPAs, including reports, newsletters (e.g. Forest Watch, VPA Updates), and the LoggingOff online library. In 2020, Fern assessed VPA impacts on seven forest governance elements, finding improvements in most countries.
- Chatham House: Published influential synthesis reports (2010, 2015, 2022), country profiles, and thematic analyses that have shaped third-party assessments and policy discussions.
- Global Witness: Investigated illegal logging in Papua New Guinea, tracing timber through Chinese supply chains and prompting sourcing changes by major US and Chinese flooring companies. Other reports influenced Japanese parliamentary debate on timber import legislation and led to sustainable sourcing commitments from five major tyre companies in the rubber sector.
- Rainforest Action Network: Documented forest-related crimes in Indonesia and shared findings with law enforcement. This led to an anti-corruption investigation, and, in 2021, the revocation of concessions held by the company Korindo.
- Global Canopy and Trase: Provided data on EU and UK exposure to imported deforestation and the limitations of voluntary commitments. Their work has been instrumental in shifting policy thinking toward regulatory approaches. A senior European policymaker noted that “Trase has shaped the entire underlying system for policy development [on imported deforestation].”
In addition to formal reports, grantees have used blogs, websites, newsletters, brochures, and guidelines to broaden understanding of FLEGT. EFI, with FGMC support, has played a key role in providing up-to-date information on VPA progress and demand-side measures like EUTR implementation.
Indicator 3.2 Community of practice Indicator status: Fully achieved
A key activity under this output has been the facilitation of forums and platforms that bring together diverse stakeholder groups within the FGMC community of practice. Notable examples include:
- Chatham House Illegal Logging Workshops: Held throughout the early and mid-2010s, these forums convened government, NGO, and private sector representatives from both producer and consumer countries. Initially focused on practitioner-level exchanges, they evolved into venues for political announcements. An evaluation found them to be effective platforms for networking, knowledge sharing, capacity building, and accountability—enabling citizens to raise concerns directly with officials and strengthening cross-sectoral links.
- FGMC Annual Stakeholder Forums: These events foster exchange between countries and stakeholder groups involved in the programme and are highly valued by participants.
- EU “FLEGT Weeks”: Facilitated by the European Commission and partially supported by FGMC, these annual events in Brussels during the 2010s helped connect field-level voices with policymakers and negotiators.
Together, these forums have helped build relationships, strengthen capacity, and develop a broader community of practice - an important but often invisible asset of the programme. Discussions and learning at the international level have also influenced national processes.
Online platforms have further expanded the reach and diversity of this community:
- RRI’s Path to Scale has become a leading multi-stakeholder platform for advancing Indigenous Peoples’ and Local Communities’ rights in line with climate and biodiversity goals.
- WRI’s Global Forest Watch added 1.5 million new users, reaching a cumulative total of 6.4 million.
- ZSL’s SPOTT dashboard saw 51 new financial institutions join during the grant period, with seven new members added to the SPOTT Supporter Network, now totalling 22.
Indicator 3.3: Communication and momentum for political engagement. Indicator Status: Fully achieved
FGMC grantees have played a significant role in shaping international forest policy dialogues and outcomes through strategic advocacy and communications, particularly at UNFCCC COP26 & COP27 and CBD COP15. Organisations such as ClientEarth, EIA, Chatham House, Proforest, WCS, WWF, and others led events amplifying marginalised voices and promoting rights-based forest governance, sustainable landscapes, and supply chain due diligence.
These efforts contributed to major policy developments, including:
- The EU’s Forest Partnerships with five countries;
- The COP26 Forest Tenure Pledge;
- China’s Banking Initiatives for Nature and Climate;
- The launch of the Forest and Climate Leaders’ Partnership (FCLP) at COP27, following advocacy by ClientEarth, Chatham House, Global Witness, CIDT, WCS, ZSL, and Global Canopy;
- The $1.7 billion Glasgow Forest Tenure Pledge to support Indigenous Peoples and local communities, influenced by RRI advocacy;
- The creation of the Women in Global South Alliance for Tenure and Climate, launched at COP27.
Grantees also played a key role in advancing anti-illegal logging legislation:
- The UK Environment Act (adopted in November 2021), where ClientEarth, Fern, Global Canopy, Global Witness, EIA, Forest Trends, and WWF submitted detailed recommendations on secondary legislation;
- The EU Regulation on Deforestation-Free Products, proposed in November 2021 and agreed in December 2022, which includes key provisions advocated for by FGMC grantees - such as the inclusion of smallholders, civil society participation, gender considerations, and the use of GIS and earth observation tools.
Grantees continue to monitor and influence the implementation of these regulations, particularly regarding the readiness of sectors like palm oil and soy to meet new EUDR requirements.
Lessons learned through this output, and recommendations for future programming
Face-to-face engagement remains essential for building trust and momentum
While online meetings offer a cost-effective way to maintain dialogue, in-person events are critical for building networks, alliances, and informal connections. The 2022 FGMC Annual Stakeholder Forum in London, held in person despite COVID-related risks and costs, was instrumental in reactivating the community of practice. Participant feedback highlighted the value of informal interactions—during breaks and social moments—as key to strengthening relationships and collaboration. Future programming should continue to invest in strategic in-person convenings.
Informal coalitions can drive influence and policy change.
FGMC-supported networks have proven effective in mobilising coordinated advocacy. For example, around the EU Deforestation Regulation (EUDR), FGMC grantees (Global Witness, Fern, ClientEarth, etc.) collaborated with the Global Forest Coalition to advocate for inclusive reforms. Concerns raised included smallholder inclusion, tenure insecurity, illegality risks, and gender responsiveness. Joint policy briefs and a public letter (March 2022) helped shape the final regulation. Supporting such informal alliances is a valuable strategy for amplifying impact.
Southern academic institutions are vital contributors to national policy processes.
Recent partnerships with universities in Indonesia (UGM, IPB) and the University of Freiburg have demonstrated the value of engaging southern research institutions. These institutions are often trusted, credible, and well-positioned to inform national deliberative processes. For example:
  - UGM and Freiburg highlighted the benefits of the VPA for diverse stakeholder groups.
  - IPB, through a Chatham House grant, profiled challenges faced by SMEs and households in securing legality verification under SVLK.
Future programmes should prioritise partnerships with southern universities to strengthen evidence-based policymaking and ensure locally grounded perspectives are integrated into reforms.

Output Number and Title		4 Coherence with other global processes aiming to safeguard forests and combat deforestation
Output Score		A+
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Baseline		Final Logframe Target	Final Result Achieved
4.1 Policy alignment between international processes promoting responsible forest and land use	REDD+ generally not drawing on lessons from FLEGT deliberative processes to address forest governance issues in most DFID VPA countries.		New forest programmes and investments adopt learning from FGMC with regards to stakeholder-led deliberative processes in design and implementation whether at country or global levels. / Global policy processes, such as CITEs, EITI, adopt learning from FGMC with regards to stakeholder-led deliberative processes in dialogues at country levels / NDCs draw from FGMC to foster inclusive policy making	A+ Fully achieved: / Strong governance foundations understood to be critically important for delivering ambition in reversing forest loss and delivering sustainability in forest management. / Growing interest in governance foundations for benefit sharing as more focus on high integrity voluntary carbon markets and jurisdictional REDD+ instruments takes hold. (e.g. instruments like LEAF). Guyana reaped benefit of years of investment in governance foundations to meet standards and unlock carbon finance. / Indonesia and Ghana sharing experience with FACT dialogue, Indonesia as co-chair seeking to promote the broader market recognition of national TLAS. / FGMC grantees engaging with biodiversity agenda influential in agreement at CBD COP 15 securing Global Biodiversity Targets / Forests now integrated within EITI reporting in 4 countries (Cameroon, Liberia, RoC, Guyana) indicating a growing commitment to accountability and transparency
4.2 FLEGT practice informing measures to reduce the risk to forests from production of other commodities	Relevant research and analysis drawing lessons from FLEGT is being planned and produced by some FGMC grantees.		EU and other regional trade and investment measures that aim to minimise risks from production of other (non timber) commodities is informed by research and analysis of the lessons from FGMC; / UK development and policy measures that aim to minimise risks from production of other (non timber) commodities is informed by research and analysis of the lessons from FGMC, notably GRI / Lessons from timber related actions inform engagement in Indonesia, West and Central Africa on policy development for sustainable palm oil and other commodities / Partnership with China informs policy actions to reduce risks in Chinese FRC supply chains, notably natural rubber	A+ Fully achieved / Significant experience shared with EUDR, UK and US DD legislation captured in catalogue of FGMC knowledge products generated. / Community of practice continuing to engage and drive forward policy areas without FGMC finance from 2023 onwards. / Cocoa sector learning from deliberative processes in Ghana, Cote D’Ivoire and Cameroon / Indonesia learning from SME experience with SVLK to consider smallholder engagement with ISPO / China – experience from working with China on timber, translating into development of business standards for FRCs.
4.3 Business standards, legal compliance and investor behaviour to reduce deforestation	Business standards for avoiding deforestation in relation to forest risk commodities (e.g., Palm oil, soy, beef, leather, cocoa, rubber) do not adequately respect community rights over forest land and resources in accordance with customary and international laws. / Even where business standards are evolving, levels of business awareness, due diligence, and compliance in relation to these standards are low.		Tools and evidence informing business and investors linking deforestation risks to specific commodity supply chains. / Tools and evidence to improve accountability for corporate commitments to reduce footprint on forests from unsustainable production and investments; / Systems established by civil society and local communities to monitor and report on compliance with business standards. / Business standards such as RSPO are managed and monitored with respect to compliance of environmental and social requirements, especially with respect to community and Indigenous people's rights. / Greater proportion of smaller and medium global companies with standards for forest risk commodities. / Market share in each sector of businesses reporting on compliance has increased	A+ Excellent progress / UK Parliamentary group on deforestation calling for Amendment 91 to the Financial Services and Markets Bill / Nine of the ten Amsterdam Declarations Partnership signatory governments have now used Trase tools and data. / China has made notable progress on standards (e.g. mining, sustainable palm oil) / Version 0.4 of the TNFD Framework has now been launched for consultation prior to the full TNFD launch in September 2023.

Around 75% of tropical deforestation is driven by land conversion for export commodities such as palm oil, soy, cocoa, minerals, and timber - over two-thirds of which violates national laws and regulations. Infrastructure expansion into forest areas is also a contributing factor. FGMC’s experience is highly relevant to informing new policies and regulations that support legal and sustainable production and trade of forest-risk commodities (FRCs).
Producer countries stand to benefit significantly from improved legal compliance, with illegal deforestation estimated to cost governments over $17 billion annually in lost revenue. [22] However, initiatives promoting sustainable forest land use must be underpinned by strong sector governance to deliver meaningful results.
[22] https://www.forest-trends.org/wp-content/uploads/2018/06/Info-Brief-Costs-of-Illegal-Agro-Conversion_Final.pdf
Output 4 connects country-level work (in both producer and consumer/processing countries) to regional and international efforts that influence government and private sector practices. This work is essential to sustaining gains from national FLEGT processes, as many pressures on forest land now originate from outside the forest sector—driven by global commodity markets and international policy dynamics.

Much of the progress under Output 4 has been achieved through the FGMC community of practice, as described under Output 3, which has played a key role in linking field-level experience to global advocacy and policy influence.

Indicator 4.1 Policy alignment between international processes promoting responsible forest and land use. Indicator status: Fully achieved
Over the past five years, there has been a significant acceleration in the development of legislative frameworks in major demand-side markets to regulate trade in forest-risk commodities (FRCs). Since 2012, FGMC grantees such as Fern, ClientEarth, and others have highlighted that most tropical deforestation is driven by the expansion of commercial agriculture - often illegally - and have called for binding regulations in the EU and UK, which are among the largest importers of FRCs.
Until recently, regulatory action seemed unlikely, with governments favouring voluntary initiatives and non-binding measures. However, through coalition-building, technical input, advocacy, and evidence generation, FGMC grantees helped shift the political landscape. They drew on lessons from FLEGT and the EUTR to demonstrate how due diligence frameworks could be applied to agro-commodities.
Key milestones included:
- EU Deforestation Regulation (EUDR): Agreed in December 2022, just over a year after the Commission’s proposal.
- UK Environment Act: Adopted in November 2021, with secondary legislation under development.
- US FOREST Act: Introduced in October 2021, currently awaiting a Congressional vote.
All three frameworks introduce due diligence requirements to address deforestation and forest degradation linked to commodity supply chains. FGMC-funded organisations—including ClientEarth, EIA, Fern, Forest Trends, Global Canopy, and Global Witness—played a central role in shaping these laws through:
- Investigative reports substantiating the need for regulation;
- Advocacy amplifying Global South perspectives;
- Data and analysis (e.g. from Trase) to inform policy design.
The EUDR marks a shift from a legality-based approach (as in the EUTR) to a zero-deforestation standard, consolidating timber and other commodities under one regulatory framework. This has raised concerns among producer countries and private sector actors:
- Producer countries worry that their investments in national timber legality assurance systems (e.g. under FLEGT) may no longer be recognised or rewarded.
- Private sector actors, particularly in the timber trade, are concerned about the removal of the “green lane” for FLEGT-licensed timber, which now requires additional due diligence.
In response:
- Timber Development UK (TDUK) launched the Global Timber Accord at COP26, urging regulators to recognise national legality systems.
- Indonesia and other VPA countries formed the Broader Market Recognition Coalition (BMRC) to advocate for broader international recognition of their national systems.
At COP28, more than two years after the UK Environment Act was passed, the UK government announced the list of FRCs that will be restricted from import if linked to illegal deforestation, marking a key step in implementation.
Indicator 4.2 Forest Risk Commodities. Indicator status: Fully achieved
NGO grantees have produced influential research that has shaped policy and regulatory reforms, both in government and the private sector, particularly around land-based investments like palm oil. In April 2017, the European Parliament passed a resolution[23] calling for urgent action on tropical deforestation, including regulation of agricultural commodity imports. Forest Trends[24] (funded by FGMC) showed that nearly half of recent tropical deforestation was due to illegal clearing for commercial agriculture, driven by global demand for commodities such as palm oil, beef, soy, and timber. Fern’s research[25] (also funded by FGMC), also cited in the resolution, estimated that one-quarter of forest-risk commodities were destined for the EU.
[23] http://www.europarl.europa.eu/sides/getDoc.do?type=TA&reference=P8-TA-2017-0098&language=EN&ring=A8-2017-0066
[24] Forest Trends. 2014. Consumer Goods and Deforestation: An Analysis of the Extent and Nature of Illegality in Forest Conversion for Agriculture and Timber Plantations
[25] Fern, 2015. Stolen Goods: The EU’s complicity in illegal tropical deforestation
FGMC has helped strengthen linkages between FLEGT and REDD+ in countries like Liberia and Guyana by transferring lessons and promoting shared platforms for multi-stakeholder engagement. International agencies supporting REDD+ increasingly view FLEGT implementation as a valuable upfront investment that facilitates later REDD+ efforts. In Guyana, for example, FLEGT conditions were embedded in its performance-based REDD+ agreement with Norway, reinforcing governance reforms aimed at reducing deforestation. However, this integration is not universal. In Indonesia, inter-agency rivalry has kept FLEGT and REDD+ processes largely separate, despite clear synergies. FGMC has worked through the FCPF to bring together FLEGT and REDD+ focal points from multiple countries, raising the profile of governance within the Facility Management Team. Yet, country-level REDD+ readiness guidance still tends to focus on technical processes led by external contractors. Guyana’s inclusive forest sector reform (also supported by FGMC) has enhanced its credibility and helped secure long-term carbon reductions. In 2022, Guyana signed a carbon deal under ART TREES with Hess Corporation worth at least USD 750 million, with 15% of proceeds allocated to IPLCs.
The EU launched the Sustainable Cocoa Initiative in West Africa in 2020 to improve the sustainability of the cocoa supply chain and support producers in meeting due diligence requirements under the EUTR. Early assessments revealed a lack of shared understanding among stakeholders regarding the planned EU regulations. To address this, ClientEarth and local partners are analysing the legal frameworks for cocoa production in Ghana and Côte d’Ivoire to identify gaps between EU/UK deforestation and due diligence requirements and national laws. Fern and ClientEarth have also provided capacity-building and advocacy support to farmer-based organisations, enabling them to engage more effectively in national and international policy discussions. In both countries, CSOs and farmer groups are being supported to understand the implications of EU and UK regulations for smallholders. In Ghana, CSOs are drawing on the FLEGT VPA and the Ghana Wood Tracking System - seen as gold-standard multi-stakeholder processes - to inform the development of the Cocoa Management System.
In November 2021, the China Chamber of Commerce of Foodstuffs and Native Produce (CFNA) finalised the China Sustainable Palm Oil Consumption Guidelines to support Chinese companies in adopting more sustainable palm oil practices. These guidelines align with other CFNA sustainability frameworks and will be followed by the Sustainable Palm Oil Sourcing Guidelines, supported by WWF China and expected in 2022. WWF also co-launched the China Sustainable Palm Oil Alliance to mobilise private sector actors—including L’Oréal, Mars, HSBC, and Cargill—towards sustainability, eliminating illegal sources, and achieving zero deforestation in high conservation areas, with links to producer country actions. Alliance members and Chinese palm oil companies have begun implementing the guidelines. Regional and global engagement continued, including a China–Indonesia Dialogue in 2022, co-hosted by WWF China and CFNA, marking a first step toward aligning China’s guidelines with Indonesia’s ISPO standards.
In 2022, the China Chamber of Commerce for Metals, Minerals and Chemicals Importers and Exporters (CCCMC) revised its Due Diligence Guidelines for Mineral Supply Chains (prepared with support from FGMC) which were approved by the London Metal Exchange, marking the first Chinese mining standard to gain international recognition. Progress was also made on procurement policies in the tin and cobalt supply chains.
China further demonstrated leadership in environmental governance by launching the Kunming Biodiversity Fund during Phase One of CBD COP15, committing RMB 1.5 billion to support biodiversity conservation in developing countries. The Global Environmental Institute (GEI) played a key role in advocating for and researching the fund’s establishment. GEI also supported the update of China’s Guidelines for Ecological Environmental Protection in Foreign Investment Cooperation and Construction Projects, which led to the development of a sector-specific handbook for the banking industry.
Indicator 4.3 Business standards and compliance. Indicator status: Excellent progress
Co-managed by Rainforest Alliance and supported by FGMC, the Accountability Framework initiative (AFi), provides a global reference for ethical agricultural and forestry supply chains. It builds on international law and best practices in human rights and environmental protection. Following outreach and input from NGOs and supply chain actors - including in Cameroon, Ghana, and Liberia under FGMC - Version 1.0 of the Framework was launched in June 2019 at the Amsterdam Declarations Partnership meeting. Since then, AFi has gained traction among key stakeholders. By the end of RA’s project (Y3Q2), 57 entities (29 companies and 28 NGOs, peer initiatives, and policy platforms) had adopted the Framework, with broader engagement reaching 136 companies and 123 non-corporate actors. AFi’s definitions have informed the EU due diligence policy proposal and the UK GRI recommendations.
Global Canopy’s Forest 500 has become the leading dataset tracking deforestation and human rights commitments among the 350 companies and 150 financial institutions most exposed to forest-risk commodities. In 2014, only 10% of companies and 7% of financial institutions had comprehensive deforestation policies. By 2020, these figures rose to 29% and 11%, respectively. While some companies have responded to pressure with stronger action, Forest 500 highlights that voluntary efforts remain insufficient. Global Canopy uses Forest 500 data to engage policymakers and advocate for mandatory action and reporting to drive systemic change.

Lessons learned through this output, and recommendations for future programming

New demands from demand-side laws (EUDR, UKDD, US-FOREST) may create new incentives for greater transparency in supply chains for other commodities – but only if national rules are developed through an inclusive, multi-stakeholder process. These new laws place new requirements on operators importing commodities into their respective jurisdictions – including greater transparency and disclosure on their geographic origin and assurance that they are both legally sourced and not from areas recently subject to forest clearance. These new laws have the potential to create new incentives for increased transparency across a number of supply chains, including timber and forest products. However, experience from FGMC suggests that if these new measures are to succeed and gain real legitimacy within producer countries, national policy responses need to be developed through an inclusive, multi-stakeholder process, rather than being simply imposed in a top-down manner.
Evidence-based, targeted advocacy has been effective in shaping policy responses to the challenges posed by FRC supply chains. The legislations that the EU and the UK are in the process of equipping themselves with mark a sea change from a decade ago, with a shift in attention from just timber to other FRCs, and with regulatory action being given unprecedented prominence among the demand-side tools available to combat deforestation. Advocacy work by NGOs (including FGMC-funded organisations) must be credited for their key contribution to this profound change in mindsets. Over the past years, this work has broadly consisted of:
- Providing policymakers with clear evidence that voluntary commitments are not enough. Voluntary commitments were the backbone of the collective deforestation goals set for 2020 in initiatives such as the New York Declaration on Forests or the Consumer Goods Forum resolution – none of which could be reached, as evidenced in dedicated assessments such as Global Canopy’s Forest 500. The wealth of intelligence generated by FGMC-funded organisations over time in various forms (e.g., investigative reports, factsheets, policy briefs) has been key in further sensitising policymakers to the inherent limitations of too heavy a reliance on corporate commitments, and the need for regulatory measures to tackle deforestation in supply chains more consistently.
- Informing what demand-side measures should look like. FGMC-funded organisations in coalitions with other NGOs have played a critical role in pushing for the introduction of due diligence requirements for businesses in the EU and UK legislations, building on the innovations introduced by the EU Timber Regulation (EUTR) in 2013. Even though all their asks are not reflected in the legislations in their current forms, NGOs have succeeded in influencing policymakers’ ambitions to a certain extent (e.g., inclusion of rubber and leather in the scope of the EUDR).
Demand-side regulatory measures addressing commodity-driven deforestation are just in their infancy. Implementation, which is yet to begin, will tell whether the regulations’ ambitions and modalities are fit for purpose. Experience from the FLEGT Action Plan can be drawn here to highlight what elements will likely require specific attention in this testing and learning process:
- Enforcement must be consistent and sufficiently resourced. This has been a main shortcoming in the implementation of the EUTR, with penalty regimes and levels of human and financial resources varying across member states, thereby creating loopholes and opening routes for circumvention that severely hampered the regulation’s impact, in addition to questioning the value added of producer countries achieving FLEGT licensing.
- Political will and private sector adherence must be sustained. This will be key to ensuring the above and seeing to it that ambitions do not end up being watered down by further adjustments to the scope of the regulations. Such a risk remains, even though it is worth noting that so far, adverse private sector lobbying has had limited influence, and a growing number of industry actors have been supportive of mandatory due diligence requirements, on grounds that these will help establish a genuine level playing field in the FRC supply chain landscape.
- Reliable, fit-for-purpose, accessible evidence and data will continue to play a crucial role. In recent years, there has been a proliferation of innovative tools designed not just to assess policies and commitments in place, but also to help both governments and FRC supply chain companies identify risks and track progress. As the general context in demand-side geographies is transitioning towards implementing the nascent regulatory measures, there is going to be a sustained (or, arguably, strengthened) need for stakeholders to access relevant evidence and data: policymakers, to appreciate the impacts and shortcomings of the regulations and determine what adjustments are needed; companies, to demonstrate compliance with due diligence requirements, in addition to progress with voluntary commitments ; and civil society observers, to ensure transparency and accountability, and drive change where needed. Adequate resources will have to be mobilised for the continued generation of evidence and data.
- Constructive cooperation with producer countries and other demand-side geographies will be paramount. Demand-side regulations are expected to elicit, and be complemented by, policy responses in producer countries, essentially in the form of reform that aims at strengthening forest and land-use governance. Without this, progress will be partial at best. The need for support and cooperation has already been identified and is being worked on. This is indeed one of the main objectives of the FACT Dialogue, and the EU has made it a priority too by confirming that a strategic framework will be established to define the modalities for dedicated bilateral partnerships with producer countries. Much experience can be derived from the FLEGT Action Plan and the FLEGT VPAs to help shape cooperation in a way that fosters alignment of incentives and interests and brings all stakeholders to the table.
Despite their clear limitations, voluntary commitments will retain a key role in driving change. Those private sector players that have been most supportive of the regulatory agenda tend to also be those that have performed well in the voluntary space. As noted in a joint Fern/Forest Trends report published in 2018, voluntary action by companies helps to build “confidence that change is not an economic threat” and to create “consumer-country constituencies for regulatory action”. Faced with specific challenges, advanced companies may take up commitments that go beyond what is legally required at a given time – thereby also providing policymakers with a better understanding of what could be achieved through future revisions of existing regulation. This has been identified by NGOs as a potential route for closing gaps on, for instance, the consideration of human rights in the current UK and EU regulations. In jurisdictions where adequate laws are still not in place, voluntary commitments and guidelines (e.g., China’s sectoral guidelines on rubber, palm oil, and mining) are useful entry points to further drive impact and potentially sensitise to the need for regulation.
The FGMC midterm review argued that while the programme was delivering impact under output 4, this area of work lacked focus and a long-term strategy. It recommended that a more coherent approach be taken, including the development of a thematic theory of change and a decision whether this work will be consolidated or expanded in Phase 2. With this in mind, the second phase of FGMC has a much clearer focus on thematic areas such as FRCs, carbon, mining, biodiversity and other environmental services and the programme has been re-oriented to focus on the governance of forested land (rather than what was previously a narrower focus on timber with limited activities in other sectors).

D: Value for Money [½ - 1 page]

For over ten years, FGMC has been a high performing programme - consistently scoring A and A+ in annual reviews. The Independent Commission for Aid Impact (ICAI) review of the International Climate Finance (ICF) Forests and Nature portfolio (2021) singled FGMC out for praise regarding its impact and operating model, noting “FGMC offers a strong example of how to approach commodity-related deforestation and is one of the most successful programmes in the [HMG] portfolio, with lessons to offer other programmes in the sector, not least the value of sustained long-term relationship building and investment”.[26]
[26] ICAI 2021 International Climate Finance: UK aid for halting deforestation and preventing irreversible biodiversity loss, pp21,25

When looking at Value for Money (VfM), FGMC has performed very well. The programme has delivered on a wide range of fronts, demonstrating significant value for money through long-term investments in nationally owned and inclusive governance reform processes. These efforts have laid the foundation for other initiatives to build upon. FGMC has assisted in implementing Timber Legality Assurance Systems (TLAS) in multiple countries which have been key to delivering sector wide national scale transparency, increased revenue collection and more effective benefit sharing, improved controls and compliance checks with environmental requirements and social safeguards. The programme has resulted in better-regulated markets designed to exclude illegal products and incentivise improved forest governance in producer countries. It has supported national policies and regulations leading to increased transparency, accountability, and reduced illegal logging. The success of the programme has led to a transformational change in both consumer and producer countries. FGMC experience demonstrates that trade measures can leverage and strengthen governance reforms.

VfM is assessed using the 5E’s framework (Economy, Efficiency, Effectiveness, Cost-Effectiveness, and Equity). Cost-effectiveness, and the transformational case studies demonstrating this, are explained below.

Transformational change and cost-effectiveness:
Cost-effectiveness looks at VfM through FGMC’s ultimate impact relative to the inputs invested (the FGMC programme budget was £280m). Quantifying the value for money through the metrics used in the original Business Case is challenging due to the nature of the benefits and the extended causal chain linking FGMC inputs to impact. FGMC works towards systemic shifts in forest governance and markets at global and national scale, rather than in identified project landscapes. Therefore, it is not possible to attribute the impact of FGMC on the number of hectares protected, the number of emissions avoided, the number of livelihoods protected, or the number of incomes improved. FGMC can take a domain approach when looking at its impact; change has happened in FGMC countries and FGMC can be confident its actions resulted in consequential impacts contributing to this change, alongside domestic and other donor supported actions.

Country focus: Indonesia
Between 2016 and 2022, Indonesia was one of the few countries globally to reverse its deforestation trend. Tree cover loss in 2016 was 2.4mha (tree cover of 1.5%) and in 2021 it had reduced to 0.8mha (0.51%)[27]. Indonesia credits its improved record of controlling deforestation in part to the improved monitoring of its national (SVLK) TLAS, supported by FGMC. However, the rate of tree cover loss over the following two years did show a worrying increase reaching 1.4 mha in 2023 (0.87%), of which 0.3mha were in primary forest. This underlines the need to maintain support for forest governance efforts.
[27] Global Forest Watch

In 2019, Indonesia permanently banned the issuance of new licences to clear or convert primary natural forests and peatlands to agriculture or other uses. Sustained UK support for multistakeholder deliberation on Indonesian forest policy, prior to FGMC, resulted in increased focus on forest stewardship and was the basis for a 2-year moratorium in 2011 that prohibited issuance of new licenses to clear or convert primary natural forests and peatlands to agriculture or other uses. FGMC’s support contributed to the permanent implementation of this moratorium in 2019.

FGMC support was also a key factor in Indonesia becoming the first country to implement national scale licencing under its Voluntary Partnership Agreement (VPA) with the EU, and a similar post-Brexit agreement with the UK. This agreement allows traders to import timber products worth nearly £1.6 bn annually into the EU and UK, without needing to conduct due diligence on the legality of production[28]. This progress reflects a transformation since the early 2000s, when illegality was the norm and over 80% of Indonesia’s timber exports were judged to be illegally produced. Today, 100% of exports are controlled for full legal compliance and a robust assurance system backed by a stakeholder platform is in place[29]. Over 20.3 million hectares of forests are independently certified for compliance with Indonesia’s forest management standards, helping to drive a 10% increase in export values[30].
[28] https://www.gov.uk/government/publications/cs-indonesia-no12019-ukindonesia-voluntary-partnership-agreement-on-forest-law-enforcement-governance-and-trade-in-timber-products
[29] TCI PCI 2024 report
[30] Annex G of FGMC2 Business Case

As well as increased value from legal timber exports, FGMC’s work on enabling more efficient enforcement to meet VPA system requirements has led to an increase in forest revenues collected by the Indonesian government (increasing from £42.2 million in 2016 to a peak of £59.2 million in 2018)[31].
[31] PELT Briefing Note 1 2021

During the lifetime of the programme, FGMC spent £28m in Indonesia through grants and projects with Government Forest services, think tanks and local experts and CSOs[32].
[32] Comprising three phases of the Multistakeholder Forest Programme in Indonesia providing direct technical assistance to the Ministry of Forests

Country focus: Ghana
Investment in technology can be transformational, as exemplified in in Ghana where the full deployment of the Ghana Wood Tracking System has improved timber operator compliance to environmental, social and financial requirements as well as improving forestry decision making by businesses and government services. Such change of behaviour results from concerted enforcement efforts over a number of years, but the IT-based tracking technology has made the sector more transparent and more efficient at fee collection, which has contributed to significant increases in revenue.

From 2010-2019 total forest revenues increased from £6.1 million in 2010 to £20 million in 2018. FGMC supported Ghana in a range of ways to help improve the efficiency and effectiveness of tax collection. The increase was due to increases in stumpage fees[33], the imposition of export levies and improvements in systems for collection of fees and fines and levies. Increased harvesting of threatened rosewood meant that, in 2016, it contributed 28% of total tax and non-tax revenues.
[33] Forest stumpage fees are the payments made by timber harvesters to the landowner (often the government or a private entity) for the right to cut and remove standing timber from a specific area of forest land. These fees are typically based on the volume of timber harvested, with the price per unit of volume varying based on factors like timber species, quality, and location

This in turn has enabled the legally required redistribution of revenues to District Assemblies and Traditional Authorities. By law, 50% of stumpage fees are due to be paid to landowners and district councils. Between 2010-2019 approximately GH₵71m was distributed (roughly £3.5m)[34]. These resources can be utilised for community actions.
[34] Modelling carried out for FGMC2 based on PELT report:

Over this period there has been a growing level of compliance by timber companies (75% of them) against their legal obligation to sign Social Responsibility Agreements with communities and in so doing, securing benefits to forest dependent communities and reducing conflicts.

During the lifetime of the programme, FGMC spent £8.6 million in direct support to the Forestry Commission (and more through grants and other services).

Country focus: Guyana
The governance systems developed with FGMC’s support directly enabled Guyana to effectively demonstrate the high environmental and social integrity necessary for carbon credit markets. The FLEGT VPA process in Guyana strengthened the legal frameworks for sustainable forest management, developed transparent monitoring systems, and established inclusive mechanisms for national stakeholders – including Indigenous Peoples and local communities – to participate in forest governance decisions. These improvements directly addressed key requirements later needed for ART TREES verification, particularly around regulatory frameworks, forest monitoring capabilities, and environmental, social, and governance safeguards implementation.

In December 2022, Guyana became the first country in the world to issue jurisdictional forestry carbon credits under the Architecture for REDD+ Transactions (ART) TREES standard, with verification of approximately 33.5 million tons of carbon dioxide equivalent emissions reductions for the period 2016-2020. This achievement led to a landmark agreement with Hess Corporation to purchase carbon credits worth at least $750 million between 2022 and 2032, representing one of the largest private sector investments in forest conservation globally. 15% of the revenue from credit sales goes directly to Indigenous People for activities of their choice; 85% of revenue is used for land titling for Indigenous villages, low carbon development initiatives (e.g. renewable energy), repairing canals, and protecting against climate change.

In February 2024, ART issued 7.14 million 2021 TREES Credits to Guyana, and Guyana became the first government to report a corresponding adjustment to the UNFCCC for the associated emission reductions.

The Government of Guyana explicitly recognised the value of building on existing forest governance systems supported through the FLEGT VPA process when registering for the ART TREES standard.

Country focus: China
FGMC’s influence in China has been a success[35], with China joining international efforts to stamp out the illegal timber trade. China has moved from a position of total refusal to engage at the start of the programme, to active engagement with their private sector and trading partners to stop the trade in illegal timber and promote sustainable production of forest risk commodities, largely aligned with the EU and other global markets[36]. For example, the adoption of the 2019 Forest Law introduced due diligence obligations for Chinese companies importing timber products[37][38]. This increased import scrutiny and reduced unregulated trade. As an overall result, China is now importing less from “high risk countries” and more from “lower risk sources”. Senior Chinese policymakers emphasised FGMC’s crucial contribution to its recent national forest law reform, banning the purchase of illegally sourced timber; and to its development of standards and tracking systems that govern the mining, logging and palm oil practices of its trade association members’ overseas.
[35] "https://icai.independent.gov.uk/html-version/international-climate-finance-uk-aid-for-halting-deforestation-and-preventing-irreversible-biodiversity-loss-2/"International Climate Finance: UK aid for halting deforestation and preventing irreversible biodiversity loss - ICAI
[36] 2017 Mid-Term Review
[37] 2021 Annual Review
[38] International Climate Finance: UK aid for halting deforestation and preventing irreversible biodiversity loss - ICAI

Theme focus: tax revenue
Tax revenue generated from strengthened forest governance has also increased since the beginning of the programme. Globally, estimates of the market value of illegal logging activity range from $30-157 billion, with foregone tax revenue ranging between $6-9 billion[39]. These are vital resources and revenues that are being lost. FGMC’s support to reforms, timber legality assurance systems, and associated technical assistance aims to increase government revenues from the forest sector and the disbursement of benefits back into the sector and to the communities that depend on forests for their livelihoods and often share responsibility for their stewardship.
[39] Illegal Logging, Fishing, and Wildlife Trade: The Costs and How to Combat it (worldbank.org); https://www.forest-trends.org/wp-content/uploads/2018/06/Info-Brief-Costs-of-Illegal-Agro-Conversion_Final.pdf

At the programme level, a modelling exercise carried out in preparation for the new FGMC2 programme design based on data from FGMC studies carried out by PELT on the economic impacts of FGMC in 4 countries, estimated a potential increase in government revenue in the 16 existing VPA countries of £1.6 billion per year (assuming a 10% increase in efficiency of revenue collection due to the VPA[40]).
[40] FGMC PELT report, Summary of Key Results and outcomes relating to trade, behaviour change, economics and benefit sharing, and policy influencing. August 2021 -also published by Chatham House: https://www.chathamhouse.org/sites/default/files/2022-03/2022-03-18-forest-revenues-hoare-kanashiro-uehara_0.pdf

Theme focus: grants leading to innovation
A grant to World Resources Institute in 2014 was an important contribution to their development of Global Forest Watch (GFW), the most important resource in monitoring change in forest cover worldwide. GFW is a publicly available website that uses analysis of satellite imagery to estimate forest loss and gain and carbon results for all countries.

A grant to the NGO, Global Canopy, was instrumental in establishing the Task Force for Nature-related Financial Disclosures (TNFD). TNFD’s set of disclosure recommendations and guidance encourage and enable business and finance to assess, report and act on their nature-related dependencies, impacts, risks and opportunities. This initiative has now become a global standard. In the 18 months since the release of the TNFD recommendations, over 500 organisations, representing more than USD 17 trillion in assets under management, have committed to getting started with reporting on their nature-related issues.

FGMC was an early funder of RRI, which has built a coalition of 21 partners and over 200 rights holders’ organisations, advancing the rights of Indigenous Peoples, Afro-descendant Peoples, and Local Communities in tropical and subtropical countries. Between 2015 and 2020, communities supported by the coalition in Asia, Africa, and Latin America gained legal recognition to over 100 Mha of additional lands and now own more than 11% of the world’s land.

Theme focus: trade as a lever
FGMC has shown that transparency, which fosters accountability, is important for both demand and supply-side actions. FGMC has seen evidence of transformative policy change in focal countries including Ghana, Liberia, ROC, Guyana, and Indonesia, with effective mechanisms operational in other VPA countries[41]. Countries with VPAs now cover roughly 80% of the total global trade in tropical wood products, which is far more than the EU’s market share[42]. The effective facilitation of VPAs by FGMC has developed trust over years with VPA partner countries, and strong support for nationally owned processes constitutes excellent VfM, growing the UK’s reputation as a valued long-term partner[43]. A 2022 evaluation of the VPA impact by CIFOR concluded the VPA process has contributed positively towards a decrease in illegal logging and trade[44]. This has been achieved through an increase in the implementation of forest management plans thanks to a coherent legal and regulatory framework with regularly enforced and more credible sanctions, and greater transparency in the forest sector, all supported by FGMC partners and incentivised by more stringent market requirements.
[41] 2024 TCI PCI Report
[42] 2022 Annual Review
[43] 2023 Annual Review
[44] 2022 Annual Review

Lessons learned
A focus on efficiency can have negative implications for equity. Improved forest governance and trade may squeeze small family forest enterprises out of the market. This can be rectified by re-directing government revenues to social services and implementing systems for more equitable sharing of timber, revenues, royalties and fees among communities for activities of their choice. In Liberia, by law, 30% of land rental fees paid by timber concessions should be shared with adjacent communities. In total (2021), US$2.7 million had been released, resulting in much needed investments in remote and under-served areas of the country. Although this represented just 4% of the total owed by timber companies for land rental fees and therefore the need to continue prioritising equitable benefit sharing remains clear.
Equity needs to be assured, sometimes at extra cost. If benefit sharing of payments are captured by minority elites within communities or do not benefit women within communities, additional investment in independent monitoring and awareness raising can improve accountability, transparency and equity.  The 2017 mid-term review found that one of the most significant achievements of FGMC had been facilitating the inclusion of stakeholder groups who often were previously unable to exercise any significant level of influence in policy making, particularly representation of Indigenous Peoples and SME forest managers and processors. Analysis of the potential impacts of reforms on women, IPLC’s, small scale enterprises, has enabled FGMC to anticipate potential exclusionary impacts of reforms and to mitigate these[45]. This has included for example, supporting SMEs to associate, seek group certification to minimise the transaction costs of legal compliance, supporting the formation of SME associations to enable them to represent themselves in deliberative processes, and to enter arrangements with concession holders to access legal timber.
[45] FGMC PELT report – Private Sector, Government and CSO behaviour change 2021
Positive results on efficiency, effectiveness and equity requires sustained support and results will not linearly improve. Addressing deep seated governance issues requires multi-pronged approaches and consistent, long-term support.  Rather than transformational, structural change, policy development processes take place through incremental steps, each one allowing quick and visible gains, thereby demonstrating progress towards a long-term goal. The use of learning insights and well-timed knowledge products has been instrumental in this process. Ultimately, the success of FGMC is in part linked to the wider political context in country, with progress advancing and stalling over the course of the programme lifetime as the space for transparency and civil society scrutiny opens and closes – the design of governance programmes needs to take this into account and adopting an incremental approach that facilitates flexibility to adapt to changing contexts.
Assessing programme-wide VfM is difficult for a programme that works globally across a wide range of policy areas, in multiple countries and with different instruments. Whilst the notion of a single VFM cost-effectiveness metric may be appealing, it is also of questionable value in a programme such as FGMC given that the ultimate aim of the programme is to bring about change in individual countries with forest, all of which have context specific and different policy needs and costs associated with bringing about change. FGMC has therefore found it challenging to assess VFM across its lifetime. The approach taken has focused on shifts observed in specific countries, identifying how these changes have occurred, and then to assess the extent to which FGMC’s efforts have made a contribution to these shifts, amongst many other factors. Case studies, rigorous outcome harvesting, multiple country evaluations, country and thematic specific studies feeding economic models have all been tried, largely drawing on measures of perceived change.
Further work should be prioritised in FGMC2 to set out a VfM approach and methodology that can be quantitatively tracked at explicit points in the programme's lifetime. This is not straightforward, seen by the difficulties in assessing this in FGMC1, but could involve the combination of expert judgement on FGMC’s influence in a given country (an equivalent to the FGMC2 business case “policy impact factor”) and the FGMC2 business case modelling (which calculates impact based on deforestation trends and the implications this has on carbon emissions, ecosystem services and a reduction in conflict). A framework for this assessment should be set out in the inception phase of FGMC2 and feed into the independent evaluations.
The Value for Money section of this PCR draws from an aggregation of MEL material from FGMC focused independent analyses targeting aspects of policy influencing and sectoral shifts created over the past 12 years, as well as analyses drawn together to inform the development of a new successor programme Business Case. However, no independent end of programme review was commissioned. This exercise adds value by bringing views and examples together in one place to give an overarching understanding of FGMC’s VfM. This PCR benefitted from evaluations from the independent MEL team at the mid-term review and FGMC2 will benefit from a similar approach of independent evaluation at the mid-term as well as at the end of the programme.

E: Risk [½ - 2 pages]

The overall programme risk was rated as 'moderate' throughout FGMC's lifetime.

Over its 12-year duration (2011–2024), the FGMC programme maintained a substantial risk appetite in relation to political context and delivery challenges, while adopting a more cautious approach to operational, safeguarding, fiduciary, reputational, and personnel-related risks. These risks were carefully monitored throughout the programme’s lifetime.

At the time of the original Business Case approval in 2011, four key risks were identified as potentially affecting the programme’s ability to achieve its objectives. Each was accompanied by proposed mitigation measures. These early assessments reflect DFID’s risk management approach at the time. While risk frameworks have evolved significantly since then, the analysis of these four risks offers valuable insight into the programme’s strategic thinking and the lessons learned through implementation.

Risk A: Shifting dynamics in the illegal timber trade

Nature of risk: The illegal timber trade has evolved, increasingly targeting less-regulated consumer markets and domestic markets within producer countries. A growing share of illegal wood enters Europe indirectly via processing hubs such as China, Vietnam, and Thailand. As some countries strengthen enforcement against illegal logging, there is a risk of displacement, where illicit activities shift to regions with weaker governance.

Proposed mitigation (2011): FGMC aimed to apply demand-side pressure to influence market behaviour. Key strategies included:
- Promoting consumer and procurement legislation.
- Building alliances and facilitating knowledge exchange with emerging economies.
- Coordinating with NGOs to raise awareness of reputational risks.
- Supporting up to 10 country-level forest governance agreements.
- Encouraging regional cooperation, particularly in areas like the Mekong Basin.

Actual experience: Initially focused on programme delivery, FGMC quickly recognised the importance of understanding broader geopolitical dynamics. Rapid growth in Asian timber markets, driven by economic expansion and construction booms, outpaced European demand, challenging assumptions that tighter regulations in traditional markets (Europe, US, Japan, Australia etc) were the primary driver of trade shifts. FGMC’s engagement with China became pivotal as its influence in forest-producing countries expanded. Similarly, Vietnam’s role as a major processor of tropical timber from West and Central Africa opened new avenues for engagement, despite its relatively low regulatory oversight compared to Europe.

Risk B: REDD+ finance potentially undermining forest governance

Nature of risk: Global anticipation of large-scale REDD+ finance raised concerns that carbon-focused funding might overshadow efforts in forest law enforcement, governance, and trade. There was a risk that countries failing to address illegal logging could still benefit from REDD+ finance, undermining credibility and incentives for reform.

Proposed mitigation (2011): FGMC aimed to:
- Advocate for forest governance as essential to credible REDD+ outcomes.
- Promote coordination between FLEGT and REDD+ strategies at EU and national levels.
- Leverage synergies between legality, tenure, and governance to support long-term REDD+ success.

Actual Experience: The anticipated REDD+ finance did not materialise at scale. Instead of convergence, REDD+ and FLEGT developed in parallel, with separate architectures and limited integration. FGMC struggled to gain traction in the REDD+ space, especially as responsibility shifted across UK departments (DFID → DECC/BEIS/DESNZ). This fragmentation persists, with forest management for carbon and for productive use still treated separately. However, emerging carbon markets are beginning to demand “high-integrity” forest carbon, which may incentivise stronger governance frameworks - an area where FGMC’s legacy could be influential.

Risk C: Agricultural expansion driving deforestation

Nature of the risk: Rising global demand for agricultural land for domestic consumption and export, has become a dominant driver of legal and illegal deforestation.

Proposed mitigation (2011): FGMC planned to:
- Apply demand- and supply-side measures similar to those used in timber legality.
- Leverage growing awareness of deforestation links in agro-commodity markets.
- Engage with voluntary certification schemes and consumer country initiatives.

Actual Experience: Commodity agriculture emerged as the leading cause of deforestation many forest regions. This includes Asia, with growing footprints in source countries such as China, Vietnam, Indonesia amongst others, as well as growing regional markets in Africa, such as Nigeria, and increasing domestic markets. In the latter years of the programme mining in forest areas has also become a growing risk to forests.

FGMC successfully adapted its timber governance approach to forest-risk commodities (FRCs), notably in Ghana’s cocoa sector and Indonesia’s palm oil industry. However, progress was hindered by fragmented, commodity-specific standards driven by private sector interests rather than national frameworks. FGMC supported tools like Forest 500, Trase, and TNFD, which became industry benchmarks for ESG performance. Yet, most finance linked to deforestation remains outside these instruments, and behavioural change is largely limited to Western companies. Promisingly, FGMC’s work with Chinese Chambers of Commerce to raise ESG standards among member businesses could be transformative, given China’s global footprint.

Risk D: Managing a large, geographically dispersed programme

Nature of the risk: Expanding FGMC’s geographic scope risked reducing its flexibility, responsiveness, and coherence (qualities that had been central to the success of earlier DFID programmes).

Proposed mitigation (2011): FGMC was designed with:
- Oversight from xHMG Steering Committee (DFID, Defra, DECC, Forestry Commission), to secure coherence across int’l and domestic forestry and climate policy
- Input from a non-government reference group (private sector, civil society).
- Strong emphasis on consultation, partnership, and political engagement.
- Formal reporting to EU FLEGT bodies, including European Council Working Party on Forests and the FLEGT-REDD Donor Working Group.

Actual Experience: The programme’s global reach required deep contextual knowledge and coordination across diverse regions (e.g. consumer markets in Asia and producer countries in Africa). DFID’s small central team could not manage this complexity alone, leading to the establishment of an outsourced programme management support team in 2014. This model evolved and proved highly effective, supported by robust monitoring, evaluation, and learning systems (see management section).

FCDO’s approach to and assessment of risk has evolved substantially since 2011, broadening beyond operational context to encompass a wider range of geopolitical and institutional risks. By 2019, during the Business Case addendum process, risks were reframed to reflect the fragile and often post-conflict environments in which tropical forests are located. These include: (a) armed conflict; (b) forest access controlled by secretive regimes without regard to the rights of indigenous people or communities; (c) institutionalised corruption; (d) conflicts of interests; (e) and the instability of weak political regimes, economic and health crises.
FGMC mitigated these risks at country level primarily through inclusive, multi-stakeholder processes that brought together government, civil society, and the private sector. In some cases, targeted technical assistance was provided to strengthen regulatory and enforcement capacity. Across the portfolio, risks were managed flexibly through broad networks, grounded intelligence, and the ability to scale activities in response to political shifts and emerging opportunities.
Safeguarding, particularly in relation to environmental defenders, became a critical focus. Several implementing partners developed advanced expertise in this complex area, going beyond basic duty of care.
Given the duration of the programme, it has also experienced adaptations to changing UK centric factors such as Brexit, which clearly impacted a programme designed to work towards an EU wide policy objective, and also to internal changes including the merger of DFID and FCO in 2020, the creation of the joint International forest Unit with DESNZ in 2021 and changing development priorities and budgets. Throughout these contextual changes, the adaptive and flexible design of the programme has enabled it to adjust and evolve remarkably well.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

The Programme’s Management arrangements: Over its 12-year duration, FGMC Phase 1 was led by a Senior Responsible Owner (SRO) and Programme Manager, supported by advisory roles and strategically placed programme-financed positions in the EU, Indonesia, and China.

Initially, DFID directly managed all accountable grants, MOUs with international organisations, and supplier contracts providing technical assistance (TA) to forest countries. However, as the programme expanded, the limited human resources within DFID made direct management unsustainable. Consequently, some projects were delegated to Posts with greater capacity (Beijing and Jakarta).

A key change occurred in 2014 with the introduction of an outsourced Programme Management Support Team (PMST). Working alongside FCDO, the PMST enhanced operational efficiency, managed over 20 accountable grants, ensured coherence across delivery partners in alignment with the programme’s ToC (ToC), and led and vastly improved monitoring, evaluation, and learning.
The PMST was instrumental to FGMC1’s success. By relieving FCDO staff of administrative burdens, it enabled more strategic oversight and increased capacity for political and international engagement. A strong working relationship with FCDO allowed significant delegation to the PMST, while decision-making authority remained with FCDO.
Comprising five technical experts, the PMST provided specialist advice and grant management, supporting governance reform processes and aligning grants with broader programme objectives. This improved learning, coherence, and influence. The continuity of dedicated professionals throughout the programme fostered trusted relationships with partner governments, further strengthening FGMC’s impact. In addition, a pool of on-call experts provided rapid, targeted support in response to emerging requests for policy advice. This flexible expertise significantly strengthened FCDO’s oversight and informed strategic decision-making.
By leveraging this outsourced advisory and management service, FCDO was able to effectively oversee a complex and wide-ranging programme across multiple regions and geographies with a small internal team, ensuring strategic coherence, operational efficiency, and sustained impact.
Multiple levers and delivery instruments: linking national and global action
FGMC deployed a diverse set of delivery instruments tailored to specific national contexts. These mechanisms supported policy engagement, technical and governance reform, facilitation of inclusive national processes, and the generation of evidence, knowledge, and capacity - enabling stakeholders to drive systemic change across forest governance landscapes. These included:

Instrument	Purpose	Key Features	Key stakeholders
Long-term Technical Assistance	Support partner governments’ development of national timber legality systems	Provided through supplier contracts; capacity building; system establishment; technology investment	Partner governments
Short-term Technical Assistance	Rapid response to country needs and analysis for global policy engagement	Delivered via MOU with EFI[46]; specialised analysis and advice; flexible and responsive support	Partner governments; FCDO & international policy stakeholders
Facilitation Service	Enable inclusive multi-stakeholder national policy and regulatory reform	Impartial support; ensures diverse voices (women, IPLC, small-scale actors); fosters national dialogue	Partner governments; nat’l private sector, civil society & IPLCs
Accountable Grants Programme	Advance rights advocacy, transparency, and legal trade	Community of practice; CSO-led investigations; evidence generation incl from producer countries; influence int’l policy processes	CSOs, global advocacy and policy groups and platforms; int’l policy platform
Delegated Cooperation Agreements	Strengthen donor coordination and country-to-country connections	MOUs with donors like AFD & GIZ to build on existing actions; links producer and consumer markets	Partner governments; donors, private sector & market actors
[46] In this context, EFI is the European Forest Institute’s International Partnership Facility.

Reflection on the “multi-pronged” approach:
FGMC1’s Business Case proposed four outputs designed to combine the UK’s international influence with targeted support for change in forest-producing countries - recognising that no single approach would be sufficient to drive systemic reform. The programme’s success hinged on a multi-pronged strategy embedded in its ToC, which integrated the following core elements:

- Legality and law enforcement to reinforce national sovereignty and institutional integrity.
- Market leverage to shift incentives, recognising that indiscriminate markets perpetuate poor governance.
- Inclusive, multistakeholder processes to address entrenched governance challenges and build coalitions and momentum for sustained reform.
- Formal legal frameworks, including bilateral treaties and an international (EU) action plan, to uphold the credibility and durability of measures.

This integrated approach of linking demand- and supply-side market measures, proved effective in promoting trade in verified legal timber and discouraging illegal practices, as evidenced throughout the programme’s implementation and reflected in the ToC section of this report.

Key lessons from programme delivery / FGMC’s range of delivery instruments enabled the programme to adapt to varying country and local donor contexts and respond rapidly when opportunities arose. The timescales to mobilise TA contracts were often a constraint when the political timing was opportune. Key lessons are set out below and it is worth noting that FGMC2 has proposed to continue these approaches: / Instrument diversity builds resilience of forest governance reform processes: In Indonesia (2020), an attempt by the business faction to undermine the timber legality system was successfully countered by a coalition of FGMC partners leveraging their networks and expertise. / Rapid response mechanisms essential to capitalise on political momentum: The European Forest Institute’s Technical Assistance (TA) facility enabled swift mobilisation of support aligned with political momentum, with beneficiary-led approaches contributing significantly to impact. / Donor coordination boosts effectiveness: In Liberia, DFID pooled resources from the EU and Norway through FGMC action; in RoC and Vietnam, collaboration with AFD and GIZ strengthened governance and market linkages. While administratively complex for donors, this model worked well for partners. / Locally owned processes drive change: In Indonesia, long-term support for stakeholder-led reforms led to significant shifts in forest production practices. / Accountable grants foster innovation, accountability and reach: The accountable grants programme built a global community of practice, linking national efforts to international initiatives. CSOs played a vital role in exposing illegal timber activity, prompting reforms and prosecutions, while offering independent, constructive challenge to FGMC team. / Facilitators enhance inclusion and intelligence: Dedicated facilitators provided impartial, cost-effective support, enabling greater participation by IPLCs and marginalised groups. Their trusted insights improved FCDO’s understanding of national dynamics and coordination. The shift to a multi-country Facilitation Service further strengthened adaptability and cross-country learning.

Management lessons:
FGMC Phase 1 (“FGMC1”) demonstrated the value of a lean, strategically focused FCDO team supported by outsourced programme management. Initially led by an SRO and Programme Manager, the team adapted as the programme scaled. The introduction of the Programme Management Support Team (PMST) improved efficiency, coherence, and oversight, allowing FCDO to focus on strategic engagement and policy influence. This model was key to FGMC1’s success in building a strong practitioner coalition and delivering impact, as recognised in the ICAI review of HMG projects supporting action on forests.

The following lessons will be carried forward into FGMC Phase 2 (“FGMC2”): / Further streamlining for scale: FGMC2 will retain the outsourced programme management model and further streamline FCDO’s role by outsourcing administration of most technical assistance contracts. This will allow FCDO to maintain strategic focus while expanding delivery capacity. / Technical expertise and responsiveness: The PMST’s technical team and expert pool provided timely, specialist support for shaping grants and responding to governance and policy needs. FGMC2 will build on this model with enhanced skill sets and expert capabilities. / Donor collaboration amplifies impact: Joint delivery with donors (e.g. EU, Norway, Germany, France) improved coherence and scaled impact. FGMC2 will continue this approach and establish an independent forest governance hub to support donor coordination and provide a source of impartial advice and analysis. / Clear roles and accountability support delivery FGMC1’s success was underpinned by well-defined roles, strong complementarity between FCDO’s policy engagement and partner delivery, and robust accountability mechanisms—all of which will remain central to FGMC2.

Country-level engagement and coordination: Lessons from FGMC1

FGMC1 developed flexible approaches to country engagement, adapting to contexts where there was strong UK forest expertise at Post and those with no resident diplomatic presence at all.

Indonesia: FGMC benefited from strong UK engagement and an established presence in the forest sector. A formal MOU with the Ministry of Forest and Environment set out governance arrangements for co-steering a multistakeholder programme, including grants and technical assistance. This was chaired by the UK Ambassador and Forests Minister, supported by an in-country FGMC adviser and programme manager (G6 and HEO). Accountable Grants enabled independent support to civil society and the private sector. A regularly updated ToC, informed by political economy analysis, ensured strategic alignment across delivery partners. The FGMC-funded advisory post was key to maintaining trusted relationships and keeping Post well-informed.

Republic of Congo (RoC): In contrast, FGMC operated without a resident diplomatic presence, with coordination led by the UK Post in DRC and no programme-financed position in-country. Despite these constraints, Post engaged where feasible, focussing on developing a forest sector roadmap outlining shared UK–RoC ambitions. Initial collaboration with French cooperation partners proved cumbersome, prompting a shift to more flexible support via the EFI Facility. FGMC’s work was formalised through an MOU with the Ministry of Forest Economy and overseen by a high-level steering committee co-chaired by the FGMC SRO and the Minister. A country-specific ToC guided delivery, supported by a country-based facilitator who played a key role in convening stakeholders, supporting inclusive policy dialogue, and ensuring coordination among delivery partners.

Across all countries, regular coordination meetings between FCDO and delivery partners - including PMST, long-term TA providers, and the Facilitation Service - proved essential for surfacing issues, tracking progress, and maintaining strategic coherence. The European Forest Institute’s Technical Assistance Project (EFITAP) provided flexible, high-quality support, including rapid expert analysis during key moments such as COP26.

The PMST, delivered by KPMG and later Pegasys, was central to FGMC’s adaptive management. Its ability to synthesise real-time political economy insights, alongside intelligence from facilitators and grantees, enabled the programme to remain responsive and strategically aligned across diverse country contexts.

Asset Management

Suppliers maintained asset registers, reviewed regularly by FCDO. During delivery, assets were owned by FCDO, but at programme closure, most assets used by contract suppliers and grantees (PMST, long term TA projects, accountable grants) were transferred to local partners to support long-term sustainability. Retrieval was deemed impractical due to low residual value and high repurposing costs. Capital assets formed a small portion of the FGMC budget and were generally low value, except for vehicles and IT equipment in Liberia, RoC, and Guyana, which were formally signed over to the management of the respective governments.

Commercial
At inception in 2011, FGMC’s commercial strategy combined direct and indirect procurement. The programme required DFID to directly:
- Procure a lead facilitator (EU-based) to oversee programme operations.
- Establish facilitator-managed frameworks to deliver forest governance and trade expertise.
- Co-finance the EFI-hosted EU FLEGT Facility in partnership with the EU.
- Support country/regional work via delegated arrangements or joint funding with the EU Commission and EU member states.
- Issue calls for proposals from non-profits - managed by the facilitator and approved by DFID - to strengthen monitoring, evidence, and local institutions.

By the 2014/15 Annual Review, FGMC transitioned to a partially outsourced model for managing accountable grants and providing technical support. KPMG was awarded the contract, bringing strong sectoral understanding and robust grant management. This marked the start of the PMST, procured via the procurement framework arrangement that was deployed for ICF at the time – this shortened the procurement process as it drew from a pre-screened group of service providers. However, this also introduced challenges for some of the FGMC contracts where we wanted to retain and extend long-term expertise with extensive networks but found that the pricing model of since the framework promoted a fee-discounting approach for long term contracts, limiting our ability to retain specialist staff with long term trusted relationships.

In 2018/19, a business case addendum extended the programme for a further 3 years. The PMST contract was re-tendered and awarded to Pegasys International, ensuring a smooth transition and continuity through to the no-cost extension ending March 2024. The financial and programme management handover during this process was very ably managed by both contractors.

Performance
Suppliers used Monthly or Quarterly Financial Reports to confirm actual spend, which was compared against forecasts to identify and investigate variances before payments were made. Supplier performance was managed through contract-defined Key Performance Indicators (KPIs) and milestones, covering areas such as facilitator mobilisation, reporting quality, financial administration, safeguarding, and cross-country learning.

Key Performance Indicators (KPIs) and milestones were used to manage supplier performance and were set out in their respective contracts. These ensured that the suppliers demonstrated high standards in programme management, including mobilisation of experienced facilitators, timeliness and quality of reporting and finance administration, safeguarding, and cross-country learning. While most KPIs were seen as useful - particularly for financial management - some were viewed as mere formalities.

Overall, supplier performance and compliance were strong. No financial penalties were issued for failed KPIs during the reporting years, and the 2023 Annual Review confirmed all suppliers met their contractual KPIs. As part of an HMG transparency initiative, performance against the top three KPIs for FGMC contracts over £5m was published on GOV.UK, with all suppliers receiving the maximum mark ‘good’.

Financial management
FCDO and the PMST maintained strong oversight of financial risks, requiring implementing partners to report any fraud allegations immediately. In 2025, two such cases by a downstream partner organisation in the Congo region were promptly reported to the FCDO Fraud Unit, with funding suspended pending investigation. An independent investigation determined that £3,078 of FGMC funds disbursed to the sub-grantee were ineligible and thus returned to the FCDO. Both cases were closed in line with FCDO procedures, and the overall fraud risk level remained stable through the end of the programme.

The 2011 Business Case prioritised Output 1 - supporting forest producer countries - with 74% of the budget. The remaining funds were distributed across Outputs 2–4 and programme facilitation, reflecting a more limited scope:

Output	Purpose	Budget Allocation
Output 1	Create effective multi-stakeholder institutions and operational VPAs or timber legality assurance systems in up to 10 FLEGT producer countries	74%
Output 2	Develop public policies and private standards with compliance in consumer and processing countries	2%
Output 3	Generate evidence, knowledge & momentum for change	20%
Output 4	Strengthen coherence between programmes on forests and deforestation (national and international levels)	2%
Facilitation, M&E	Programme support & oversight	2%

As the programme evolved the split rebalanced as follows:

Output	Focus	Budget Allocation
Output 1	FGMC provided support throughout the programme to 10 forest countries: Cameroon, China, Gabon, Ghana, Guyana, Indonesia, Liberia, Laos, Republic of Congo, and Vietnam.	68%
Output 2	Engagement with Chinese think tanks, chambers of commerce, and other consumer markets exceeded initial expectations.	15%
Output 3	Accountable grants and the broader community of practice were central to amplifying and sustaining programme results.	10%
Output 4	International engagement expanded significantly in the latter stages, particularly around forest-risk commodities, forest carbon, and global policy influence driven in part by COP26 and its commitments.	7%

This allocation struck the right balance, aligning effort with priorities and opportunities, while keeping the core focus on forest governance in producer countries. The breakdown of the spend across programme is as follows:

Year	Spend (GBP)
2010–2011	£102,345.23
2011–2012	£3,937,614.88
2012–2013	£17,921,856.02
2013–2014	£18,881,016.82
2014–2015	£25,725,151.27
2015–2016	£30,499,760.43
2016–2017	£30,586,791.78
2017–2018	£28,941,693.31
2018–2019	£20,004,610.44
2019–2020	£27,569,487.85
2020–2021	£25,234,259.07
2021–2022	£21,106,572.15
2022–2023	£23,630,278.01
2023–2024	£5,764,532.43
2024–2025	£36,380.48
Final Programme Spend	£280,025,544.44

Monitoring and Evaluation

FGMC1 tried and tested different approaches to programme MEL throughout implementation. These can be summarised in the Figure below:

Figure 1 - Evolution of MEL in FGMC1

Evolution of MEL in FGMC:

2012-2013 – mainly in-house MEL
In the initial phase of FGMC, MEL was managed internally by two DFID staff who compiled reports from grantees, projects, and international partners such as EFI and FAO. Monitoring was largely logframe-driven and fragmented, with limited strategic learning. External reviews were occasional, and support for learning and strategy was minimal. The burden of synthesising diverse inputs for annual reviews highlighted the need for a more robust MEL structure.

2013-17 – outsourced MEL
As the programme’s complexity grew, DFID outsourced MEL to an Independent Review Team (IRT). This brought dedicated expertise, reduced pressure on DFID staff, and ensured independent assessment of performance. The IRT conducted country-level and thematic reviews, including a mid-term review in 2017. However, the need for deeper contextual understanding led to a shift toward integrating MEL into routine programme management.

During this period, DFID collaborated with MEL specialists and researchers to develop methodologies for ICF KPIs. A key challenge was attributing impact in a policy-focused programme operating at national scale. In response, the Programme Management Support Team (PMST), formed in 2015, developed the Transformational Change Index and later the Policy Change Index - tools that became central to FGMC’s MEL framework and were retrospectively applied from 2013 onward. FGMC2 plans to expand these tools to better track gender and inclusion.

2015–2021: Strengthening MEL Structures
To address limitations of outsourced MEL, FGMC established the Programme Management Support Team (PMST) in 2015. PMST managed grants, coordinated monitoring, synthesised reporting, and provided strategic advice. It ensured adaptive delivery and supported learning through lessons-learned reports, annual reviews, and stakeholder engagement. From 2019 to 2021, PMST collaborated with the Programme Evaluation and Learning Team (PELT), which focused on formative evaluation. PELT conducted analytical studies on governance outcomes - such as behaviour change, policy influencing, benefit sharing, and revenue generation - and explored how FGMC support contributed to these results. Evaluative studies also assessed performance on gender, inclusion, and conflict sensitivity. While PELT added valuable insights, clearer mechanisms for approving contested findings would have improved the process. After PELT’s contract ended in 2021, PMST absorbed many of its functions, commissioning studies through its expert pool. This integrated model - combining internal MEL capacity with targeted external evaluations - is now recommended for FGMC2

Key lessons learned on MEL during FGMC / Beyond outputs: Monitoring project-level outputs is essential, but understanding the broader political and governance context, especially in producer countries, is equally critical. / Political economy insight: Regular engagement with in-country facilitators, political economy analyses (PEAs), trade studies, and grantee interactions helped track shifting governance drivers and barriers. / Policy influence is complex: Measuring FGMC’s contribution to policy change is challenging, especially when outcomes result from coalitions and collective action. / Communicating impact: FGMC struggled to articulate its influence on harder-to-measure achievements, prompting the development of qualitative tools to better capture policy contributions. / Formative vs. Summative Evaluation: While external summative evaluations are important, formative approaches - like those used by PELT - offered deeper insights into systems, behaviours, and governance dynamics. / Time for Reflection: More structured opportunities to reflect on analytical findings and integrate them into strategy would have strengthened learning and adaptation. / Dissemination gaps: PELT findings were not always effectively communicated; clearer strategies for sharing insights across the community of practice are needed. / Evolving Theories of Change: These have been vital tools for guiding design, implementation, and evaluation. Developed through stakeholder workshops, they adapt to changing contexts and help align partner workplans.

Date of last narrative financial report	Last reports prior to bridging period: / PPMST Final Report - April 2024 / MFGAP Final Report - February 2024 / Facilitation Final Report -February 2024 / EFITAP - February 2024 / Bridging Period: December 2024	Date of last audited annual statement	EFI, June 2024

## List of primary documents consulted for this PCR:
FGMC1 generated extensive documentation of its achievements over the programme’s lifetime. Key documents included Annual Reviews, a series of end of programme reviews and lessons reports (produced in 2018, 2021 and 2023), several evaluative studies carried out by an independent Programme Evaluation and Learning Team (PELT). These reports, together with the outputs of more than 100 projects are archived in a FGMC Knowledge Management System. (Access will be made available on request). Several ICAI reviews were also consulted.