Programme Completion Review

Title: REACH Improving Water Security for the Poor
Final Programme Spend £ (full life): £22,500,000	Review Date:	June 2025
Programme Code: GB-1-201880	Start Date: / 24 January 2015	End Date: / 31 March 2025

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019	2020	2021	2022	2023*	2025 (PCR)
Overall Output Score	A	A+	A+	A+	A+	A++	A+	A+	A+	A+	A++
Risk Rating	Major	Medium	Major	Major	Major	Major	Major	Major	Major	Moderate	Moderate

## *2024 Annual Review deferred to streamline reporting at end of programme.
DevTracker Link to Business Case (and any addendum):	4128518
DevTracker Links to all logframes used during programme lifetime:	D0001186

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]
REACH was a global research programme initially designed to improve water security for 5 million poor people in Africa and Asia from 2015 to 2020, using a risk-based framework to develop and promote an integrated systems level approach to water security. It aimed to provide robust and accessible evidence for governments, practitioners and the private sector in Africa and South Asia, on how to improve water security and manage the trade-offs associated with investments at scale, as well as capacity building and partnerships to ensure the research delivered impacts.
The programme was competitively procured in 2014 and a £15 million contract was awarded to the University of Oxford in January 2015 for 7 years to May 2022. In May 2020, FCDO approved a scale-up extension for REACH to continue the programme with £7.5m of new funds for a further two years up to May 2024 bringing the total contract value to £22.5 million. This impact and value for money focussed extension sought to double programme impact, increasing the target for the number of poor people with improved water security from 5 million to 10 million and. REACH was subsequently given a no cost extension (NCE) to continue until March 2025, to catch up on delays due to political instability and Covid-19 and maximise impact. The focus for the last 18 month has been on impact activities to help support scale up and scale out of the REACH programme as outlined in the Exit Strategy (2023). REACH closed on 31 March 2025, having exceeded the target of improved water security for 10 million poor people in South Asia and sub-Saharan Africa.
REACH priority countries were Bangladesh, Ethiopia and Kenya where over 10 years a civil war, an overthrow of a Prime Minister, major terrorist attacks, the COVID-19 pandemic, and multiple environmental shocks have created challenging conditions to design, execute and deliver the programme. Critical to the programme’s resilience and success in this context, was an inclusive, patient and respectful science-practitioner partnership supported by a long-term, well-funded local teams with international partners, including UNICEF, IWMI, IFRPI, RWSN and excellent academic leads in each priority country. This approach of localising research in “observatories” has led to an impact and legacy that was not envisaged at the outset of the programme.

Table 1 – Initial set of Observatories established by REACH

Country	Theme
Bangladesh	Coastal water security (dynamics between poverty, growth & infrastructure investment (Khulna)
	Water security for an urbanising river (rapid industrial growth including garment industry (Dhaka)
	Universal drinking water security and institutional design in rural Bangladesh (Matlab)
Ethiopia	Sustaining growth through water security (trade-offs around promoting growth in the Awash basin)
	Water security in fragile environments (impacts of sustainable land management (SLM)
	Small town pathways to water security (implications of government WASH/growth programmes – Wukro)
Kenya	Building water secure institutions (including FundiFix, mitigating rural water insecurity risks in Kitui)
	Small towns in fragile environments (risks and institutional responses in Turkana)

Following an independent mid-term review, work in Matlab (Bangladesh), sustainable land management in the Abbay Basin (Ethiopia) and Wukro (Ethiopia) was phased out, with efforts refocussed around clear pathways to impact that emerged as work and partnerships matured.

The conclusion of the final external programme review Impact and value-for-money of the REACH programme highlights the value of the Observatory model adopted by REACH.
“it is clear that the REACH programme has performed very highly. It has reached beyond its target of 10 million beneficiaries, is set to benefit several times this number in future and has exceeded its leveraged funds target by 100%. It has also leveraged other research funds to contribute to REACH’s objectives. The VfM analysis which drew on selected efficiency indicators also demonstrates that a high degree of value for money was achieved by the REACH programme. Much of this would not have been achieved with a traditional research programme, especially one of a short time duration. Indeed, the close relationships developed with practitioners in the programme countries and the funding of a ten-year research programme to allow research to be translated into policies and programmes on the ground – were strong enabling factors for REACH to achieve and surpass its targets.”

Achievements and highlights

REACH achievements can be categorised into three interconnected areas; research; capacity and impact.
- World class science – While REACH has been driven by a focus on impact and beneficiary numbers (with milestone payments by results), foundational science has underpinned the policies, institutional design and priority activities to improve water security. Over 10 years REACH has published 146 peer reviewed scientific journal articles as well as over 200 working papers, policy briefs and other products. The global impact of this evidence base will only be fully known in years to come as REACH has become a defining resource for water security with over 3,600 citations in academia, policy and practice communities by May 2025.
- Research capacity –strengthening capacity in partner institutions, particularly national academic partners, has been a key impact area providing a legacy beyond the programme. Central to this goal was to create and support the next generation of water leaders to emerge with the skills, knowledge and commitment to improve water security for decades to come. In total, 324 years of training were delivered by in the programme with over 80% to partners in the Global South and over 50% to women. The value of the science-practitioner partnership approach embedded in REACH design was recognised in a paper published in Nature last year “Science-practitioner partnerships for sustainable development” and underlines our focus on the importance of localisation.
- 10 million and more beneficiaries – surpassing the target to improve water security for 10.4 million vulnerable people is an enormous achievement. Independent estimates suggest that emerging developments and programmes applying and expanding the work, are expected to lead to improved water security for more than 120 million more vulnerable people in the years ahead. An Impact Fund has been created within the University of Oxford 100 million Initiative to sustain, scale up and scale out REACH’s most promising work in line with the Exit Strategy published in January 2024.
The highlights within these categories over 10 years have been extensive and varied including:
- Drought and floods in the Horn of Africa are now better understood, shaping policy and investments for 25 million people.  In Ethiopia, REACH’s research on river basin management is being scaled up through a new €45 million investment by the Government of the Netherlands. In Kenya, a major scientific breakthrough has improved understanding of regional climate systems affecting 25 million extremely water insecure people in the region. This will improve the accuracy of UK Met Office (and other) climate models by providing understanding of the “East African Paradox”
- River pollution affecting 20 million residents in Dhaka, Bangladesh, is now being addressed through evidence-based understanding of seasonal risks, and the government is using REACH research to guide USD20 billion of infrastructure investments to sequence and prioritise water treatment for Dhaka’s rivers.
- Results-based funding models to ensure safe drinking water for rural people have been tested and are now being taken up by governments, including the governments of Zambia and Bangladesh . In the coastal zone, the government has made a 6-year national budget commitment to co-fund safe drinking water services in clinics and schools through a co-designed REACH results-based contracting model. Collaboration with social enterprise, Uptime, has enabled results-based funding contracts to expand to 16 countries benefiting over 5 million rural people. This includes addressing water quality issues which are often overlooked in rural areas but have major impacts on the health, education and welfare of children, the sick and the old.

The way in which the wide range of new research has led to impacts across SDGs for is summarised in Figure 1.

Figure 1: PATHWAY TO WATER SECURITY FOR 10 MILLION VULNERABLE PEOPLE IN AFRICA & ASIA

Scaling out to
100 million people

People beneﬁting from improved water security
Improving water security through Sustainable Land Management in Ethiopian Highlands
Fit-for-purpose labs for monitoring and managing rural water supplies in rural Nepal
Building drought resilience in Ethiopian river basins
Dhaka river water quality modelling

Scaling up results-based funding for rural water services
Sustainable	Turkana Jet
management of	research sedimentation risks in	unlocks new coastal rivers in	understanding southwest Bangladesh	of East African
droughts to improve climate models
A risk-based approach to deliver	SafePani model for rural
urban water security for the poor	drinking water service
in the Greater Dhaka Watershed	delivery in Bangladesh
The FundiFix model – smart pumps and performance-based ﬁnance to improve rural water security
Protecting groundwater for climate resilience and water security in Turkana, Kenya
Making water safe	Progress to deliver safe for maternal and	drinking water services to neonatal care in	100 million rural Bangladeshi hospitals	people by 2030

2016
2017
2018
2019
2020
2021
2022
2023
2024
Looking ahead
Success stories published with VfM analysis
1	2	3	5	10	15	20	25	30
10 million

REACH has been scored A++ to recognise excellent performance, an innovative approach to delivering groundbreaking multidisciplinary research and impressive independently verified impact and Value for Money. In addition to exceptional performance at output level, REACH has substantially exceeded outcome indicators as well as ambitious impact target, leading to improved water security for over 10 million poor people and a legacy which is projected to reach an additional 100 million people. This impact achieved is double what was envisaged at the outset of the programme, and was achieved with a only 50% increase in programme value. The focus on outcomes and legacy has built strong sustainability and capacity which further justifies the Output based scoring of A++.

Major lessons learned, evidence generated and recommendations [1/2 page]

Building and sustaining effective government partnerships is critical for impact at scale, that can be sustained to create a legacy. From inception REACH integrated the critical role of government partners and boundary organisations, like UNICEF, to make research relevant to key policy targets and political priorities. Fostering of science-practitioner partnerships has increased research impact and reduced time taken to progress from piloting to policy and practice. REACH adopted a risk-based framework that helped to focus metrics and models on decisions government was making and in a language they could relate to, increasing confidence amongst decision-makers to act upon data. REACH’s pathways to impact at scale have all engaged government partners in design and implementation, progress (to 100 million beneficiaries) will continue beyond the end of the programme through these partnerships. One of the critical aspects in developing strong relationships has been time.

Long term and interdisciplinary Observatories have enabled space to design, test and scale water security interventions. Long term investments have supported strong government partnerships, with value for money increasing over time as relationships with practitioners strengthen and as research translates into policies and programmes on the ground. This justifies the funding of research projects for a longer period of time to support the uptake of the findings into policies and programmes. The observatory model has fostered interdisciplinarity and trans-disciplinarity as researchers build relationships with each other and practitioners over time. Longer funding periods help to ensure research institutions can attract, retain and promote outstanding staff. This approach will underpin the design of FCDO’s new water and nature research programme RENEW.

Sustained focus on aligning high quality research with impact for the most vulnerable is needed. The drive from senior researchers across the programme to ensure excellent research outputs that would support career development for themselves, and their teams, has enabled REACH to deliver high quality research across the observatories. Practitioner partners welcomed opportunities to engage in high profile publications to support their own career goals. The interdisciplinary approach through the observatories and the architecture provided by the risk-based framework focusing on the role of how inequalities are reproduced across scales helped to ensure research excellence was applied towards supporting the vulnerable.

A clear and ambitious project goal backed up by resources over the long-term drives impact at scale. REACH was designed to meet an ambitious target to achieve water security for 5 million – a defining and collective goal, informing choices of research topics, partners and locations. Pragmatic and flexible management of the programme directly contributed to the impact achieved, facilitating the ability to shift investments to where impact was emerging. The scale of the programme also helped to manage risks, from political instability, conflict and the pandemic. A portfolio of eight interdisciplinary Observatory sites in core countries spread risks and increased chances of success. As results emerged, promising observatories were supported and less promising locations retired or relocated. And when research was not possible, efforts could be refocused to other sites. However, there are trade-offs in delivering impact at scale, with less focus on delivering gains for smaller marginalised groups.

A strong gender strategy is needed to support all aspects of programme delivery. An explicit and consistent focus on prioritising gender in all programme activities is required from the outset to challenge established norms which are difficult and slow to change in all contexts. Female leadership in water security is limited in Africa and Asia. The annual gender strategy provided critical reflections on the uneven progress and often unsatisfactory outcomes. This detailed, regular monitoring of equity indicators helped stimulate debate on how equity targets can be achieved, challenging leadership teams and advisory staff to create and test novel solutions. Demand for gender research from governments and donors was widely stated but rarely actioned. REACH success in female early career researcher recruitment, REACH-WISER research (Water insecurity, Equity and Resilience partnership) and women-in-water workshops (Kenya) illustrate what can be achieved when principles of equity are considered from the outset. Reflections on the Gender Strategy are included as Annex H of the REACH 2025 Programme Completion Report.

Partnership Funding provided a mechanism to address gaps in the original programme designs. Gender was identified as an obvious gap and external funding through competitive research calls allowed strong partners to be recruited producing high-quality outputs. Although this provided a helpful pathway to support demand led co-designed research delivered through the Observatories, integration into the core programme was limited. In addition, the transaction costs of managing small grants awarded through partnership funding to smaller organisations, were disproportionate and rarely represented good value for money.
Evidence generated

Over the course of a decade, the REACH Programme has generated extensive evidence demonstrating its work and impact. The REACH website acts as the home of all programme outputs. This platform provides over 200 publications including: published articles, policy briefs, reports and Stories of Change, the last of which offer concise case-studies of research impact and success. This is complemented by availability of over 30 datasets from the programme’s partner observatories in Ethiopia, Kenya and Bangladesh. This data, which is available to download, includes information on river water quality, household WASH surveys, water service infrastructure audits and more.

Whilst the REACH website will be maintained until 2030, all REACH research outputs have also been uploaded to the Oxford Research Archive (ORA) provided by the University of Oxford Bodleian Libraries to ensure that future researchers will be able to access and utilise insight gained from across the programme. REACH has promoted this resource via LinkedIn and the final REACH country dissemination events, aiming to create awareness amongst social and natural scientists of various datasets from which they could develop future research. A full list of outputs and permanent links is provided as Annex F of the Annual Report 2025 and is also available on the FCDO K4D website.
### REACH website: www.reachwater.org.uk

Recommendations
1. Design long term programmes with break clauses that do not prohibit hiring or losing high quality staff, supporting developing capacity and strong partnerships with practitioners. Ensure budgets and design can support career progression and salary growth for outstanding research staff.
2. Establish long term, place based, instrumented and interdisciplinary observatories that support strong engagement between researchers from different disciplines and between researchers and practitioners to respond to need and opportunity for impact. Plan to pilot scalable interventions with government support to chart a pathway to scale.
3. Strengthen national FCDO partnerships so there is greater cohesion and impact in programme design. Exploit FCDO’s significant network of partners, including MDBs, to create greater value for money, and leverage soft power to advance gender norms with stakeholders.
4. Gender equality in research and practice is extremely challenging requiring protected resources and supported strategies to influence donor and government behaviours. REACH’s Inclusive Conferences Guide provided a range of simple but effective measures to mitigate power imbalances and gender inequalities which equally can apply to workshops and meetings.
5. An Exit Strategy which is published well in advance of programme close, provides a framework to support a transition to sustain, scale up and scale out impacts in current and new geographies.

How this report was conducted [1 paragraph]

This report is drawn largely from the REACH programme completion report May 2025 and two independent assessment reviews on REACH impact and value for money, which were carried out by Innate Values in 2024 and 2025. This report consolidates success stories and learning from a range of activities including the final programme conference which was held in Oxford in 2024 and brought together a wide range of stakeholders, experts and partners, as well as a wealth of knowledge, learning, evidence products developed over 10 years.

Actions following approval of this report [1-2 paragraphs]

The programme was a payment by results programme. All milestones have been met or exceed with milestone payments fully paid. All assets have been disposed of during the life of the programme, transferred to local observatory research partners to support their continued capacity to deliver their research agendas and sustain the impact of the programme. The research outputs have all been published, with all (bar a couple of exceptions) in open access journals, with links also available via R4D. As above, the website will remain live until 2030, but all documents on the website have been added to the Bodleian library archive to provide a permanent record and access beyond 2030. An impact fund has been established by Oxford University with remaining profit from the contract, which arose as a result of the nature of the milestone payment structure. This wil be used to continue scale out and scale up activities as set out in the Exit Strategy increasing lifetime VfM substantially. FCDO will continue to be part of the management board overseeing use of the fund, but no further actions are pending.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£15,492 million	£22,492 million
Timeframe	7 years	10 years
Impact	Improved water security for 5 million poor people	Improved water security for 10 million poor people. / i.e. a 50% increase in programme funding (additional £7.4 million) to double programme impact / Final achievement: 10.4 million verified beneficiaries with projected future beneficiaries 120 million
Outcomes	National & global sector actors improve the way they plan, implement or monitor in order to improve water security for the poor at scale for multiple users (including women, children, marginalised; industry, households, farmers; etc. / Indicators / 1. Evidence of REACH catalysing change on barriers to water security for poor women, men and children / Target for 2022: 12 documented “Stories of Change” quantifying pathways to impact from sets of research activities / 2. Leveraged funds: New or existing investments influenced by REACH programme in research agendas and implementation / Target for 2022: £30 million	Local, national & global sector actors improve the way they plan, implement or monitor, and demonstrate greater collaboration, in order to improve water security for the poor at scale for multiple users (including women, children, marginalised; industry, households, farmers; etc.) / Indicators / 1. Evidence of REACH catalysing improvements in the design, planning & budgeting, implementation and monitoring of water security interventions that incorporate climate science and are responsive to the needs of poor women, men and children / Target for 2024: 30 “Stories of Change” / Final achievement: 37 ”Stories of Change” / 2. Leveraged funds: New or expanded investments influenced by REACH programme in research agendas and implementation / Target for 2024: £55 million / Final achievement: £131.4 million / Outcome indicators were revised, in line with recommendations of a theory of change review in 2021, to encourage greater collaboration between sector actors, and ensure water security interventions incorporated climate science and delivered global scale outcomes.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

REACH has met or exceeded (mainly substantially) all logframe targets over the entire programme period from 2015-2025, including meeting a 10-million beneficiaries impact target by May 2024. Each year FCDO has reviewed and increased selected outcome and output targets to maintain stretch and increase ambition alongside ongoing success. It has not been necessary to reduce any milestone target, even in the context of exceptional externalities including the Covid-19 pandemic, political instability and conflict as well as FCDO funding uncertainty.

In addition to exceptional performance at output level, REACH has substantially exceeded outcome indicators as well as an ambitious impact target, leading to improved water security for over 10 million poor people. This impact is double what was envisaged at the outset of the programme, and was achieved with 50% increase in programme value. The focus on outcomes and legacy has built strong sustainability which further justifies the Output based scoring of A++.

Additional outcomes this year include:

Catalysing Change (Indicator 1)
- On 20th January 2025, the Safepani contract was signed by the Government of Bangladesh and the Uptime Catalyst Facility to contract safe drinking water services for 1,174 schools and clinics in Khulna District. This represents formal investment by the Government of Bangladesh in the REACH designed professional service delivery model, SafePani.
- An MOU signed with four ministries (water, education, health and local government) in Zambia and Uptime Global for a SafeManzi pilot adapted from the SafePani work in Bangladesh.
- After piloting the results-based framework for water safety designed with REACH in 2024, Uptime have incorporated water safety for all results-based contract for partners in 16 countries.
- REACH has handed over assets to partners in country to support their on-going implementation and monitoring of water security, including monitoring boreholes in Lodwar, Kenya, and weather station equipment to Kenya Meteorological Department.

Leveraged funding (Indicator 2)

REACH has also been remarkably successful at influencing other funders. The Strategic Impact Review (2023) provides a more detailed assessment, reporting £91 million of leveraged funds, which is well above the £55 million target. Since then, one additional major project – the BRIGHT project (Basin Management Support for Resilient Inclusive Growth and Harmonized Transformation) – has been leveraged in Ethiopia, which is worth £39 million. The addition of BRIGHT brings the total leveraged funds to £131 million, more than twice the target amount, and the cost per £ leveraged is £0.15 instead of the target £0.41. In other words, £1 of REACH spending has leveraged £7 from other funders, directed towards both research and water investments. This benefit comes on top of £0.49 per beneficiary reached and with no extra cost. The leveraging excludes national authorities taking over FCDO funding, or enhancing funding for scale up. An example of the former is the shift in support for FundiFix from 81% donor (FCDO) in 2017 to 14% donor in 2021, due to the transition to funding from the Kenya Water Services Maintenance Trust Fund. An example of funding for scale up is the SafePani expenditure that has been formally approved by the Bangladesh Planning Commission from 2024 to 2030 for Khulna district.

Research continues to influence new or expanded investments in research agendas and implementation. New additions over the final year of REACH include:
- REACH research informing the review of indicators for global monitoring of climate resilient WASH (USD 200k) by WHO/UNICEF Joint Monitoring Programme (JMP) and Global Analysis and Assessment of Sanitation and Drinking-Water (GLAAS) initiative.
- REACH research informing the Asian Development Bank Asian Water Development Outlook Report Key Dimension 1 on Rural Water Security (USD 225k).
- Funding from US foundation for Uptime to support the implementation of the SafeManzi model in Zambia (USD 350k).
UNICEF has been a global, regional and national partner since inception. A key hypothesis was to build on UNICEF’s close and long-term government collaborations through science-practitioner partnerships. This has proved effective in some cases though fragile in part due to the key role of the individual in the post of national Chief of WASH in Bangladesh, Ethiopia and Kenya. In most cases, these key staff (men in all 8 appointments) have shown interest in the programme, though a couple have been indifferent or, in one case, actively opposed to work on operational sustainability. In UNICEF headquarters (NYC) and regional offices (ESARO, ROSA), there has been active sharing of information with particular interest in climate resilience, affordability research, and professional service delivery models. One of the major achievements of REACH has been the SafePani model co-designed with UNICEF in Bangladesh; this was driven actively by one national UNICEF staff committed to the model and not subject to international rotational disruptions. The success of the UNICEF partnership in REACH is captured in this Story of Change.

The REACH Oxford Management team has consistently highlighted that while adaptive programme management is standard practice for FCDO, the assumption that it is possible to continuously improve on agreed outcomes has in some cases lowered morale and confused partners. This became a major concern during COVID, as mental health issues affected many staff in extremely difficult circumstances. The team has been frustrated that there are no clear criteria for assessing whether milestones have been substantially exceeded and that the process does not take into account the nature or ambition of targets, resulting in an overall score that is therefore subjective.

Sustainability of outcomes is a key challenge. Three strategies will increase the probability of success beyond the end of the programme:
- National academic partners are well-respected and engaged with government programmes. This is evidenced in all three countries, for example, work on river pollution in Dhaka is a long-term Bangladesh University of Engineering and Technology (BUET) area of engagement and progress, and a similar story on river basin management by Water and Land Resource Centre (WLRC) in Ethiopia.
- Several impact pathways have been codified into national law, local bylaws or budgets. Examples include groundwater protection in Turkana, SafePani results-based payments in national budgets from 2025-2030, professional service delivery models in the 2016 National Water Act (Kenya), inclusion of cleaning the tap in the WHO’s sanitary inspection guidance.
- Wider collaboration with the World Bank is providing larger scale funding opportunities, including Payment for Results programmes in Kenya and regionally in East Africa. In recent months, pathways to sustainability of impacts have been undermined by wider rapid and indiscriminate cuts across the sector resulting in closure of effective programmes (e.g. STAWI in Kenya) and damaged relationships.
FCDO country offices have shown varying levels of interest but no aligned funding or operational commitment to the programme. While REACH has actively tried to illustrate shared interests, the nature of centrally managed global research programmes has been a constraint. There have been regular technical exchanges, but the potential to extend impacts through country office collaboration has never materialised. Regular rotation in country office staff has contributed to this situation.

Value for Money is covered fully in Section D below.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The Business Case made provision for an Inception Phase to develop the Theory of Change (ToC) following the competitive procurement process. The theory of change (ToC) developed by REACH is captured in the statement “REACH aims to improve water security for 10 million poor people in Africa and Asia by 2024 through new thinking, models, policies and technologies which can potentially benefit many millions more.” which encapsulates the requirement to deliver an optimal combination of multiple outputs to generate an outcome, based on an understanding of the pathway to scale. The ToC is reviewed in full in the independent assessment “Impact and Value for Money of the REACH programme”, February 2025, carried out by Innate Values Ltd.

The business case envisaged a programme that would fund new and innovative approaches to water research which cut across traditional siloes and look for the inter-linkages between different parts of the water system and the sectors which depend upon it. It sought not only a research programme that would generate a number of ‘traditional’ outputs (e.g., evidence and knowledge papers) but also an effective research into use strategy which engages end-users from the start to ensure research findings are integrated into policies and investment decisions.
REACH was therefore designed as a multi-faceted programme taking novel and innovative approaches proposed and reflected by the theory of change. This necessarily required unproven assumptions and carries with it risks, not all of which could be predicted at the start of the programme. For this reason, the theory of change has been regularly reviewed regularly including the mid-term impact review (2018), the Global Strategy (2020-2024), and the external Theory of Change review (2021). The logframe was updated in 2022 to reflect recommendations, better align with the Global Strategy and increase ambition following several years of strong performance.
Overall, the ToC has been proven to be an impactful one, and the explicit nature of the underlying assumptions has helped the programme to identify and mitigate risks. Assumptions in REACH’s initial theory of change (ToC) and its 2020 update have been confirmed, with high quality outputs delivering outcomes and impacts within the timescale of the programme and beyond. The ToC and logframe have proven helpful to drive impact and to monitor progress towards it. A key success factor has been the programme’s ability to engage and build strong relationships with a range of stakeholders at different levels, which has contributed to the continuity of its research and influence even in the face of political and social instability. Decision makers have been strongly influenced by the credibility of research conducted through the observatories, local ownership, strong communications, as well as support and influence of international partners engaged by REACH

REACH was designed to enable adaptive programming, with flexibility to explore a range of research themes through many partners and take forward those that held most promise. Several course changes were made during over the 10 years. Three of the first-wave observatories were phased out: Matlab - when Bangladeshi policy determined that the Matlab District was sufficiently researched, the research programme shifted to more vulnerable and less researched regions; Wukro was closed down in 2021 due to the escalating conflict in Tigray, Ethiopia; and the Abbay basin work was phased out as per original work plan. REACH also adapted programming though the development of research collaborations, with contracted partnerships evolving through the programme to match impacts required or specific research needed. The proportion of catalyst and larger grant budget that was allocated to partners outside the original consortium (92% against a target of 80%) indicates how REACH developed new partnerships to succeed.

Theory of Change for REACH (from May 2021)

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Strengthened technical capacity in the design, delivery and monitoring of water security interventions that promote both water security and equity by policy-makers, practitioners and change makers in Africa and Asia.
Output Score	A++
Impact weighting (%)	40%	Impact weighting revised since last AR?	N

Indicator(s)	Starting target to 2022 (where applicable)	Final / target	Final Result Achieved
1.1 Knowledge sharing events organised by REACH / a) # of events (disaggregation by country) (annual) / b) % of attendees that are women / c) % of events that are in developing countries / d) % of attendees that are early career researchers / e) % that specifically address gender / f) % that specifically are cross- sector or cross-disciplinary / g) % that include knowledge exchange / h) % that are co-organised with practitioner / i) % where women are visibly involved in the leadership / j) % where researchers from developing countries are visibly involved in the leadership / Final results and targets for Indicator 1.1 are to May 2024 (ie not including final year of targeted NCE)	5 / 40 / 80 / 30 / 50 / 25 / g- j added in 2022	(a) 5 / (b) 40 / (c) 70 / (d) 30 / (e) 50 / (f) 75% / (g) 50% / (h) 50% / (i) 70% / (j) 70%	Exceeded / borderline substantially exceeding / 7 / 40% / 78% / 37% / 94% / 94% / 100% / 61% / 100% / 100%
1.2 Training for researchers (cumulative) / a) # of years of training for researchers (disaggregated by nationality, experience) / b) # of years of training for women researchers	a) 70 / b) 30	a) 225 / b) 113	Substantially Exceeded / a) 324 / b) 168
1.3 Policy and practice briefing materials produced (cumulative) / a) # produced / b) # that specifically address gender / c) # that are co-authored or co-badged with practitioners	a) 20 / b) 10 / c added in 2022	a) 50 / b) 25 / c) 13	Substantially Exceeded / a) 74 / b) 29 / c) 35
1.4 Inclusive digital engagement: / a) % of blog authors that are (1) women; (2) ECRs; and (3) from the Global South; / b) Examples of REACH digital activities successfully supporting dissemination and uptake of REACH's research	n/a / significantly revised in 2022	a1) 40% / a2) 40% / a3) 40% / b) 3	Exceeded / a1) 60% / a2) 40% / a3) 90% / b) 3
1.5 Concrete examples of positive interactions between the REACH research team and practitioners in UNICEF, government, CSOs and industry (cumulative)	21	40	Substantially Exceeded / 69
1.6 Number of local, national and global actors with improved knowledge of and/or skills in identifying and responding to water security challenges, taking account of the need for climate resilience and equity of access (disaggregated by gender). (annual)	new indicator in 2022	50	Substantially Exceeded / 105

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
This outcome aimed to measure the strengthening of technical capacity in the design, delivery and monitoring of water security interventions that promote both water security and equity by policy-makers, practitioners and change makers in Africa and Asia. It has been scored as A++ with performance substantially exceeding expectations over the course of the programme for most indicators. This score also reflects the fact that the most important and valuable indicators have been substantially exceeded, despite increasing the targets every year to reflect success and ensure ambition (documented in Annual Reviews). The sustained benefits delivered through partnerships building capacity and learning, leading to substantive changes and a committed cohort of future water leaders, are unusual in a research programme and merit an overall A++ score.
Across the 10-year programme REACH delivered 324 years of research training, leaving a legacy of early career researchers who it is estimated have over 9,500 years left in their careers. REACH delivered a wide range of events that ensured visibility of women and researchers from developing countries to support their career development, and that were designed to integrate across sectors embedding gendered aspects, with practitioners, to create events that foster pathways towards water security. Practitioner engagement was integrated more formally into the logframe for reporting in 2022, with reporting on co-creation of outputs, training, and positive interactions.
REACH’s ECR provide a cohort of dynamic and motivated professionals, 50% of whom are women. They are leading in writing papers, representing over 60% of first authors in peer reviewed publications since 2015, and attracting funding from competitive grants. They are also taking on an active role in disseminating REACH’s work in international conferences and in stakeholder events with policy makers and practitioners. The success in creating a legacy of water leaders is captured in a Story of Change: Building the next generation of water security leaders.
Their ongoing impact was reflected by Dr Meron Teferi Taye, this year invited to speak at the "Hydrology in the 21st century: challenges in science, to policy and practice" event organized by and held at the Royal Society, London. She spoke on the need for transdisciplinary research in hydrology based on the REACH funded Awash flood work.

Highlights over the last year (24/25) include:
- Ministry of Mass and Primary Education using a Lessons Learned summary on the SafePani programme for scale-up of SafePani nationally in primary schools in Bangladesh. Oxford is also now partnering with Gov of Zambia and Uptime to scale-out the SafePani model, adapting and implementing in rural Zambia in the SafeManzi programme. Collaborations for further locations within Zambia with UNICEF, the World Bank, the EU and GIZ have also been identified.
- Support to The World Bank regional office in East Africa on design of a multi-country programme on Payment for Results, including components on professional service delivery models from REACH research.
- On-going engagements with Kenya Water Services Regulatory Board’s (Wasreb) acting CEO and staff from monitoring; advocacy and public education; internal audit; corporate services; and ICT departments, have led to publishing of a discussion document on rural water regulation in Kenya co-authored with Wasreb. The formal hand-over of the weather station to the Kenya Met Department was one of several assets successfully transferred to local partners to support the sustainability of the research.
- Discussions with Water Resources Planning Organisation (WARPO) in Dhaka and sharing the REACH dataset on Dhaka river water quality, with opportunities to collaborate through the water quality monitoring project taken forward. Through engagement with ADB, REACH is leading the development of the rural water security indicator for the Asian Water Development Outlook Report 2025, and ADB is hosting the Fair Water exhibition in Manila in May 2025.
Throughout the programme, REACH has made the most of social media channels to disseminate findings and engage the wider network of people working on water security worldwide. In the final year there has been huge growth in LinkedIn engagement, with REACH Water Security page followers quadrupling since February 2024. REACH used YouTube for dissemination throughout the programme, with 64,617 views of the 155 videos on the channel to March 2025, with the recent REACH Impact video series receiving 5,049 views.

It is not possible to summarise lifetime results from this output here, but REACH has updated and released the REACH Stories of Change. These present key scientific findings and reflections on policy implications in short form, demonstrating the pathway from research to uptake and impact. They have supported policy engagement and have been shared widely online and in print. There have been over 1,800 views of the Story of Change resource pages on the REACH website this year. The most downloaded Stories of Change from the REACH website were: Fit-for-purpose labs for monitoring rural water supplies; Protecting groundwater for climate resilience and water security in Turkana; and The SafePani model -delivering safe drinking water in schools and healthcare centres in Bangladesh. Selected Stories of Change have also been translated into Amharic, Swahili and Bangla for use by country partners and a full pack of print-ready copies of these briefing materials have been shared with all partners.

 Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

The areas where targets have been particularly important are on challenging norms in leadership and engagement. This includes women, early career researchers, and researchers from developing countries. Having these targets helped raise awareness that the shifts during the pandemic were changing who was engaging in the research events and how the research was being presented due to changes in delivery mode and the gendered impact of lockdowns.
While the shift towards online events has increased potential engagement across a more diverse group of people, in reality not all groups have equal access to these meetings. A key barrier to delivering on gender equity remains the challenge of how a research programme can shift gender bias in stakeholder groups, where there is no control over recruitment and often power asymmetries in the relationship. The proportion of women attendees from stakeholders were always very restricted, with REACH researchers the majority of women in many spaces, except the Women in Water workshops. Equity and gender are discussed further in Section D.

Output Number and Title	Establishment of science-practitioner partnerships that demonstrate improved collaboration in the design, planning, implementation and monitoring of water security interventions, supported by water security observatories that drive and generate globally outstanding science to inform improved policy and practice.
Output Score	A++
Impact weighting (%)	40%	Impact weighting revised since last AR?	N

Indicator(s)	Starting target to 2022 (where applicable)	Final / target	Final Result Achieved
2.1 Concrete evidence of strengthening partnerships with practitioners, government, CSOs, industry and community members	new indicator in 2022	10	Substantially Exceeded / 21
2.2 Cumulative number of open access peer reviewed articles, and working papers published (disaggregation by gender, nationality and experience of lead author and co-authors)	60	90	Substantially Exceeded / 146
2.3 # of papers in which gender is part of the analysis	30	40	Exceeded / 48
2.4 # of papers co-authored with practitioners (disaggregation by gender and nationality)	new indicator in 2022	9	Substantially Exceeded / 28
2.5 Citation of REACH research in academic literature & policy documents	100	1000	Substantially Exceeded / 3654
2.6 Concrete evidence of REACH gaining influence in areas of water security (disaggregated by gender, nationality and experience where relevant)	new indicator in 2022	30	Substantially Exceeded / 38
2.7 Evidence of collaborative working among key stakeholders in each of REACH’s programme sites demonstrating sharing of information/knowledge; co-design-planning & budgeting, and / or co-implementation of projects/research/studies	new indicator in 2022	9	Substantially Exceeded / 18
2.8 Number of knowledge sharing and dissemination events (not organised by REACH) / a) # of events; / b) % presenters that are women; / c) % presenters that are ECRs; / d) % presenters from the global south; / e) % of presentations that address gender	new indicator in 2022	a) 30 / b) 40% / c) 30% / d) 40% / e) 40%	Substantially Exceeded / a) 71 / b) 76% / c) 47% / d) 47% / e) 53%

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

This output sought to measure the progress towards improved collaboration in the design, planning, implementation and monitoring of water security interventions, supported by water security observatories that drive and generate globally outstanding science to inform improved policy and practice. This output captures two areas: how REACH has gained importance and influence in the sector, a key to driving uptake of research into policy; and the strong relationships that have been developed with practitioners, both of these areas have been underpinned by the delivery of rigorous cutting-edge science. Across the output, the programme has substantially exceeded its targets and is scored A++.

Science-practitioner partnerships are characterized by a process of co-designing research priorities and locations, collaborative interdisciplinary data collection, and identification of investment priorities based on scientific evidence moderated by political feasibility. These partnerships were present from the initial design of the programme, with UNICEF and governments, and have expanded across the programme. However, the strength and utility of these partnerships has always been challenging to track and communicate, and indicators were revised in 2022 to reflect these challenges, for example indicator 2.4 on co-authorship with practitioners. Co-authorship and co-creation of outputs has strengthened practitioner engagement in the research as REACH developed and piloted approaches with government. A range of outputs have captured narrative reflections on these processes and the importance of the partnerships to impacts and outcomes, most notably the REACH Stories of Change.

An article “Science-practitioner partnerships for sustainable development” was published in Nature (June 2024), co-authored with UNICEF, the World Bank, IWMI, and local partners, drawing on many years of collaboration. This provides peer reviewed evidence of how a patient, outcome-based approach, rooted in localisation and long-term partnerships has delivered sustainable impact on water security; and sets out how science funding could be better leveraged to sustain progress towards global development goals.

In 2024, REACH was also awarded the Research Engagement prize in University of Oxford Vice Chancellor awards, for enriching research through engagement for the benefits of wider society, with REACH ethical fieldwork guidelines highly commended (there were 250 applications from over 1,000 staff).

Production of world class research, with targets for academic outputs substantially exceeded. Wide ranging peer reviewed publications across the observatories and themes now total 146. The quality and impact of this research is demonstrated by the very high level of citations which substantially exceeds norms and 54 high profile papers receiving more than 20 citations. A full list of publications has been provided with permanent open access links and uploaded to K4D. There is a wealth of research over the course of the programme, but a few highlights include:

Smart handpumps and results-based financing for rural water services: Smart handpumps were developed by Oxford University under the DFID UpGro programme, which use low-cost accelerometers mounted in pump handles to sense when the pump fails and alert local mechanics via the local mobile network. Continuation of work under REACH found this cut the average repair time from over a month to less than three days, with the result that villagers were prepared to pay five times as much for water leading to design of a results-based funding model to improve the reliability of rural water supply services in Kenya. The Water Services Maintenance Trust Fund has tested this model and attracted new sources of results-based funds to guarantee rural water services in two counties in Kenya. The WSMTF has informed the work of the Uptime Catalyst Facility which has issued results-based contracts guaranteeing reliable drinking water for over 4 million rural people in 12 countries in 2023 and is set to achieve its target of 100 million by 2030. This work was widely picked up in the UK media including by the BBC and Economist in 2017.

Monitoring and modelling river water quality to protect Dhaka’s river system: Industrial pollution particularly from the Ready-Made Garment (RMG) industry in Dhaka, Bangladesh, together with domestic waste, damages rivers, estuaries and coastal waters with serious impact on the health and livelihoods of people who live nearby. REACH has created river system models to evaluate domestic and industrial effluents in Bangladesh and Ethiopia; and supported the development of a new water quality monitoring network in Dhaka. The models have also been used to assess mitigation measures for river clean-up, both for a government-led USD 20 billion mitigation scheme in Dhaka, and for industry, to inform potential investment in water treatment measures. Since 2019, Primark, the Alliance for Water Stewardship (AWS) and the Partnership for Cleaner Textiles (PaCT) representing many of the major international RMG companies, have been collaborating with REACH to understand and respond to pollution from their factories. Publications and video here. Proof of concept for use of mobile biosensors to measure metals, contaminants and toxicity in this Observatory led to in new spin-out company, Oxford Molecular Biosensors, to use state-of-the-art science in partnership with government and industry.

RIFTjet Project unlocks new understanding of East African droughts: The Turkana Jet is a high-speed low level wind which carries water vapour from the Indian Ocean across East Africa to Central Africa, influencing the regional climate system and rainfall patterns (The invisible rivers implicated in African drought). A field campaign co-led by University of Oxford and University of Nairobi staff with the Kenya Meteorology Department to produce 24-hour data on the jet led to new scientific insights published in Nature in March 2023 (Valley formation aridifies East Africa and elevates Congo Basin rainfall), showing that strength of the Turkana Jet is severely underestimated in current weather and climate models hampering their ability to predict drought. The work is used as a benchmark for UK Met Office forecasting models for East Africa, providing much-needed evidence to improve current modelling and predictions. Seven publications from this work were published in high impact journals, including Nature and Geophysical Research Letters. A key output is a unique observational dataset of the Turkana Jet, which can be used by all for African and dryland climate systems research.

The credibility and influence of REACH research is reflected by an exceptionally high level of citations, particularly in policy documents, with researchers valued nationally and globally. New tools helping to track citations in policy literature beyond the partnerships and influence has been captured each year in Annual Reviews. Notable examples include:

- Climate resilience, COP26 and the IPCC: A synthesis of REACH climate research published in advance of COP26, generated 55,000 impressions and 5,368 video views on Twitter, as well as five media engagements including on Sky News. The report highlighted gaps in IPCC’s understanding of the gendered impacts for the poor and was discussed extensively through media in the UK and globally. REACH research was cited multiple times throughout the Intergovernmental Panel on Climate Change (IPCC) WGII 6th Assessment Report in 2022 – with one paper (Grasham et al 2019 "On considering climate resilience in urban water security: A review of the vulnerability of the urban poor in sub‐Saharan Africa”) featured as a graphic on “Factors contributing to the progression of vulnerability in African contexts considering their socioeconomic processes, resource access and livelihood changes, and intersectional vulnerability among social groups”. Professor Daniel Olago (University of Nairobi), funded by REACH, was invited to be lead author for the Africa chapter, framing water insecurity and poverty as the two ‘key risks’ (9-18, p.18).
- Multiple REACH outputs are cited on the Wikipedia page on water security: https://en.wikipedia.org/wiki/Water_security. This has been undertaken through partnership with RWSN to build the legacy of REACH ensuring outputs are available to broader audiences and on platforms that will outlast the programme.
Multiple citations in the influential report by The Global Commission for the Economics of Water Security Review and Findings in 2023 (The What, Why and How of the World’s Water Crisis)

Some further examples of citations within policy documents in 2024-2025 include:
- Societal and institutional context of the Asian Development Bank’s new conceptual framework for gendered water security (presented in the 2024 report on Gender Equality and Water Security: A Conceptual Framework and Practical Strategies to Accelerate Progress
- the World Cities Report 2024: Cities and Climate Action, United Nations Human Settlement Programme on November 4th 2024 and in the World Drought Atlas published by the European Commission Joint Research Centre and United Nations Convention to Combat Desertification.
- The World Bank book “Inequalities in Sub-Saharan Africa” cites Hope and Ballon (2021) in a section about factors that explain regional variations in access to basic services.
- The International Monetary Fund’s June 2024 report Promoting Gender Equality and Tackling Demographic Challenges includes evidence from Sarah Dickin et al (2021) relating to the importance of improving women’s decision-making power when taking measures such as investing in electricity, water and sanitation infrastructure to reduce unpaid work by women and enhance female education, health and labour force participation.
- The United Nations Framework Convention on Climate Change’s Bangladesh Country Diagnostic - Climate Resilient Food Systems (CRFS) Alliance cites Lázár et al. (2020) on development trajectories for coastal Bangladesh.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Many of the reflections from the programme were captured in the working paper on Creating an enabling environment for research impact. A key lesson that was brought out there and in the report by the external reviewer was the importance of time to develop partnerships, and to weather the interruptions to relationships and to operations within partners.
Over the 10 years of REACH, the programme has experienced considerable political disruptions, ranging from major changes in government such as the Bangladesh Revolution in 2024, civil wars, elections, and the usual turnover in many civil service positions, political positions and partner international organisations. To manage these risks, partnerships had to be founded broadly, with multiple entry points in an organisation to enable collaboration to continue and avoid political affiliations and have time to rebuild after significant change. The signing of the SafePani TAPP by the new Bangladeshi government in early 2025, a commitment made at the UN Water Conference in March 2023, is an indication of how long processes to change policy and practice and how REACH has been able to successfully navigate them despite political upheaval.

Output Number and Title	Effective management of the consortium
Output Score	A+
Impact weighting (%)	20%	Impact weighting revised since last AR?	N

Indicator(s)	Starting target to 2022 (where applicable)	Final / target	Final Result Achieved
3.1 Functioning of Global Advisory Panel (GAP) and Science Board (SB) including commissioned research. / (a) # from developing countries on the GAP & SB. / (b) # of women on the GAP & SB / (c) # gender specialists on the GAP & SB	3 southern representatives on each of the SB & GAP / 3 women on each of the GAP & SB / At least one gender specialist on the SB & GAP	3 southern representatives on each of the SB & GAP / 3 women on each of the GAP & SB / At least one gender specialist on the SB & GAP	Exceeded / 3 southern representatives on each of the on GAP and SB. / Women: 6 of 11 on GAP and 3 of 15 on SB / 3 gender specialists on the GAP & 2 on SB
3.2 Effective management of Partnership Funding measured by: / (a) # examples from each completed Partnership funding project contributing to the programme’s output, outcome and impact level indicators; and / (b) Proportion of catalyst and larger grant budget allocated to partners outside the original consortium	Added in 202?	1 success story per Partnership Funding contract / b) 80%	Exceeded / a) at least one success story per completed partnership funding contract / (b) 92%
3.3 Value for money, including cost analysis per impact success story to baseline Value for Money for REACH programme, disaggregating core and leveraged costs.	10 success stories	a) 25 Stories of Change	Exceeded / 25 Stories of Change plus full independent VfM assessment across programme with full disaggregation.
3.4 Monitoring country research groups and evaluation of activities / a) # of engagements of country teams with practitioners / b) # women in observatory management groups / c) £ value of research proposals submitted for funding and approved / d) % of research projects completed on time	(a) new in 2022 / (b) 6 / (c) £4,000,000 / (d) 50%	a) 10 / b) 6 / c) £4,100,00 / d) 50%	Exceeded / (a) 118 / (b) 6 / (c) £4,342,892 / (d) 73% (27/37)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
The final output relates to effective management of the consortium to ensure delivery of the research, impact and outcomes at scale. The output has been scored as A+ because indicators were all met and moderately exceeded where the nature of the indicator allows. However, this scoring does not fully recognise the level of commitment of the Oxford University management team, and their centrality to the enormous success of the programme,, both through the partnerships supported and the quality of research delivered. There have been major challenges across the 10 years of REACH, from funding uncertainty and contract delays due to FCDO, conflict and political instability in focus countries as well as a global pandemic. Highly effective and responsive programme administration and management has been vital through all these to ensure continued delivery, morale and results.
The indicators tracked the advisory group compositions, country partners, partnership funding and VfM, and showed steady progress throughout the programme. As highlighted in the external review report, the diversity on the GAP with representation from developing countries, women, and of gender specialists was a key element of the success of REACH, especially their strong engagement in the early years of the programme.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

The requirements around Partnership Funding were an initial challenge to Oxford to develop the governance systems to implement but provided flexibility to expand the programme to address key gaps in expertise and were a critical role in the success of the programme. The direct oversight of the funding by academics, and close relationships to researchers leading the work, enabled rapid decisions to be made to accelerate successful pathways to impact. These Partnership Funding grants developed into longer term collaborations, for example with work developing an empowerment index in WASH being used in the REACH-WISER programme. They also supported the development of women in the sector, with several women citing them as supporting their promotions

D: Value for Money [½ - 1 page]

 VfM performance compared to the original VfM proposition in the business case
 The VfM proposition in the Business Case was based around 3 areas:
- innovation in water resources research which is commissioned in an open and transparent manner
- bespoke mechanisms to specifically target research into use and therefore uptake of findings into a broad range of water related policies and investment decisions
- clear focus on monitoring and evaluation with funding flexibility to scale up successes

A full external independent VfM assessment was carried out in 2024 by Innate Values Ltd with VfM assessed across the “5 Es”: cost-effectiveness, effectiveness, equity, efficiency and economy. The report, Impact and Value for Money of the REACH Programme, concluded that the programme performed well against the VfM markers in the Business Case, in most cases exceeding expectation. VfM analysis is a core metric across the logframe, tracking effectiveness through leveraged funding and demonstrated uptake leading to change. In summary from the full assessment:

Cost-effectiveness
The most meaningful VfM metrics assessed here are the cost per beneficiary and the cost per £ leveraged from other funders, which are compared with the actual spending to 30 April 2024, of £19,023,248. Figure 2 (left-side) shows that the VfM performance of £1.82 per beneficiary is better than the target of £2.25 per beneficiary, due to higher number of actual beneficiaries and lower actual costs. VfM was increased by the 2022 extension and budget uplift, with target beneficiaries were doubled from 5 million to 10 million, with only 50% increase in budget. When projected future beneficiaries (28.64 million) are included, cost reduces to £0.49 per beneficiary, which is less than one-quarter of the target amount, and if the updated future projected (2025 update) 91.5 million beneficiaries are counted, the cost is £0.17 per beneficiary.

Figure 2: Cost-effectiveness of the REACH programme (Hutton, 2025)
Cost per beneﬁciary (already impacted) over time (GBP)
£27.52
£15.06
£8.32
£4.95
Target £2.25
£3.81
£2.61 £2.35
£1.82
2017 2018 2019 2020 2021 2022 2023 2024

Cumulative Annual
Cost per	Cost per	Cost per	Cost per beneﬁciary – beneﬁciary – beneﬁciary – beneﬁciary – target	already	including	including
impacted	projected	adjusted
future	future beneﬁciaries beneﬁciaries
Comparison of VfM outcomes Target versus actual (GBP)
£0.17

£0.49

£1.82

£2.25

Efficiency
Impact and outcome indicators not captured in the cost-effectiveness assessment – but which are a critical part of the pathway to impact – are the achievement of 30 Stories of Change and 32 examples of catalysed improvements in the design, planning & budgeting, implementation and monitoring of water security interventions that incorporate climate science and are responsive to the needs of poor women, men and children. The successes described in the Stories of Change and catalysed improvements are down to several factors which combine to have a greater overall impact. These include:

- The Oxford ‘label’ is a globally recognised brand and has helped open doors and have greater impact.
- The adoption of best practice M&E, as demonstrated by the annual monitoring of a considerable number of indicators in the logframe, and the biannual financial reporting, which furnished ample opportunity to assess and fine-tune the programme as it evolved.
- Opportunities for refinement of the programme approach were also created at critical points including: REACH impact review report and response (2018); Research Into Action (RIA) strategies of 8 Observatories (2018); the Theory of Change review (2020) review which led to several output indicators being added to the logframe; Global Strategy (2020-2024) to strengthen the overall strategic focus of REACH; Gender Strategy revisions (2021); Exit Strategy (2023); and Strategic Impact Review (2023).
Equity
Gender equality has been a core focus of the programme from the outset. Detailed, regular monitoring and reporting against equity indicators in the Gender Strategy has helped stimulate debate on how equity targets can be achieved, challenging leadership teams and advisory staff to create and test novel solutions. Equity and gender are embedded in the logframe through 6 output indicators and REACH has generally exceeded targets monitoring inclusion and visibility of women as well as communicating innovative work around gendered aspects of water security. Annex H of the 2025 Programme Completion Report provides a useful reflection the challenges around the Gender Strategy.
Equity was not a familiar theme for many of the team at the start but was strengthened across the programme with targeted use of partnership funding, and a focus on intrahousehold dynamics under REACH-WISER research (Water insecurity, Equity and Resilience partnership) in the later phases. Water management remains a highly patriarchal male dominated area, with female leadership in water security very limited in Africa and Asia. Gender bias in the initial team has been addressed over the years through hiring and training an exceptional cohort of female scientists who offer opportunities for future change.
REACH has also worked to illustrate and feature the quality and value of gendered research, including creating space and opportunities for women to participate in, and later lead, workshops and events. A modest but important early step was the Inclusive Conference Guide which has had wide uptake to counter the inherent biases marginalising women. Demand for gender research from governments and donors was widely stated but rarely actioned. REACH success in female early career researcher recruitment and women-in-water workshops (Kenya) illustrated what can be achieved although there has been limited action taken by government stakeholders. A key barrier to delivering aims on gender equity remains the challenge of how a research programme can shift gender bias in stakeholder groups, where there is no control over recruitment and often power asymmetries in the relationship. The proportion of women attendees from stakeholders were always very restricted, with REACH researchers usually constituting the majority of women, except the Women in Water workshops.

Setting a research agenda around gender, inequality and climate resilience: REACH has published 66 peer reviewed papers and policy/practice briefs on gender and inequality related aspects of water security.

- Research on the need for gendered approaches for building climate resilience was highlighted within IPCC WGIII and widely cited in the report.
- REACH-WISER research helped to understand and mitigate the impact on women and girls of crises and shocks, and is now being further developed under PALMTREEs (A Pan-African and Transdisciplinary Lens on the Margins: Tackling the Risks of Extreme Events (PALM-TREEs), 2023-26) funded by FCDO’s CLARE programme.
- Research on water quality in hospitals in Bangladesh has targeted maternity and neonatal investments addressing risks for women and girls at a key life stage. This research, with UNICEF Bangladesh, ICDDR,B and the Government of Bangladesh will inform investments in hospital water safety to reduce the spread of infectious disease and anti-microbial resistance.
- The SafePani model has grown from 4 pilot unions to a further 4 unions and now 68 unions across the coastal region, improving water security for over 300,000 girls and boys in schools, as well as vulnerable patients in healthcare facilities
- Research on climate resilience and urban water security informed the societal and institutional context elements of the Asian Development Bank’s new conceptual framework for gendered water security (presented in the 2024 report on Gender Equality and Water Security: A Conceptual Framework and Practical Strategies to Accelerate Progress). The work is also referenced in the World Cities Report 2024: Cities and Climate Action, United Nations Human Settlement Programme and in the World Drought Atlas published by the European Commission Joint Research Centre and United Nations Convention to Combat Desertification.
- The International Monetary Fund’s report Promoting Gender Equality and Tackling Demographic Challenges (2024) includes REACH evidence on the importance of improving women’s decision-making power when investing in electricity and WASH infrastructure to reduce unpaid work by women and enhance female education, health and labour force participation.
Other notable gender publications include

- Redefining the connections between WASH and gender - Measuring women's empowerment in WASH to support policy and practice
- The Water Diaries, R. Hope & S. Hoque, documents the daily struggle of 350 families in Kenya and Bangladesh providing a unique insight into their lives and the decisions they must make to survive on the frontline of the global water crisis. Published February 2025.
- Blog: https://reachwater.uk/what-kind-of-a-man-are-you-that-cannot-even-provide-water-on-the-table-unpacking-the-gendered-nature-of-water-conflicts-at-the-household-level-in-arid-and-semi-arid-lands-i/Unpacking the gendered nature of water conflicts at the household level in arid and semi-arid lands in Kenya

Disability has not been specifically tracked or targeted within the programme, however the Strategic Impact review (2023) concludes that the 10.42 million beneficiaries achieved by REACH until 30 April 2024 are highly likely to be poor and vulnerable people or communities, as are the projected 28.6 million future beneficiaries. People with disabilities will benefit from research focussed on equity and inclusion. REACH-WISER included work around specific challenges associated with WASH for example, looking at water access challenges and coping mechanisms of people with disabilities and women at different stages of life.

How the lack of inclusive waterpoints creates challenges for vulnerable people in coastal Bangladesh - REACH: Improving water security for the poor
.
Economy aspects of VfM are covered in Section F under Programme Management.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]
REACH has carried a major risk rating, to reflect the challenges of working on a complex, multidisciplinary research programme across fragile states. Risks have decreased significantly as the programme nears completion and has already delivered most of its impact. Risk rating was downgraded to moderate in the 2023 Annual Review to reflect this. The risks for the duration of the programme were identified in the REACH risk register and remained within organisational and departmental risk appetites at all times. The risk register has been maintained by the programme management team and updated to reflect additional risks and mitigating actions each year. Within FCDO, staff sickness resulted in a lack of programme management support for REACH for much of the programme. Aspects of compliance related to the contract were managed by PCD, but this staffing issue reduced the level of scrutiny possible for some aspects of the programme at key times, and significantly increased risk. Risk was assessed as within tolerance, due to the credibility and openness of Oxford University as a trusted partner and the rigorous programme management systems the programme put in place.
Two key challenges to the impact and legacy of the programme have been the Bangladesh political upheaval in July 2024, and the cuts to international development funding during the Covid-19 pandemic. The risks during political upheaval in Bangladesh were managed firstly to limit any personal harm to researchers, adapting travel and research plans, and secondly by managing relationships with stakeholders. These risks were effectively managed, given the subsequent sign-off of SafePani by the Government of Bangladesh.
The risk posed by the close of USAID will have long term ramifications for many partners implementing REACH research, including UNICEF and WHO. Notable impacts include UNICEF-Bangladesh withdrawing from work on the government WASH in healthcare facilities strategy due to internal cuts; and the immediate closure of the USAID STAWI programme which has had major impacts for FundiFix which had been awarded a major grant for four years.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]
REACH programme administration and management by the University of Oxford contributed vitally to the success of REACH. On finances, REACH had a dedicated financial manager within the Oxford central programme management team. Financial management followed University of Oxford procedures, included auditing, and FCDO received a twice-yearly financial report that provided transparency over costs, despite the milestone based contract not requiring this. Prior to the country agreements, the University of Oxford conducted a due diligence review of partner organisations. There was effective planning, reporting and auditing of country programmes. While sufficient funds were released to the Observatories to enable cash flow and activities to be implemented according to the plan, undue financial risk was avoided by releasing funds based on spending and on meeting milestones, which incentivised good performance. Non-financial risks were minimised through having a solid Theory of Change and explicit assumptions (see previous section), and issues arising were dealt with in a timely way. The strength of REACH’s monitoring and evaluation system has been covered above. Through having a comprehensive set of impact, outcome and output indicators that were regularly monitored and reviewed – and whose targets were all met and, in many cases, exceeded – and having at least six different strategic review processes in just six years it could be concluded that REACH has achieved ‘best in class’ in terms of its monitoring and evaluation.
The REACH programme is run through a contract with Oxford University, with biannual payments (May and October) based on approved delivery of fixed milestones linked to log-frame performance. The REACH contract was also a “Silver Contract” under the previous Cabinet Office contract management initiative and reported quarterly against agreed KPIs through this process. REACH provided financial statements in advance of invoicing with a breakdown of the actual expenditure compared to the amount forecasted for the same period, explaining the main variances. This gave FCDO sight of the actual delivery costs despite this not being required under the contract and this enabled FCDO to work with Oxford to agree further in the final year to support the programme’s legacy. Progress against delivery targets is monitored through the logframe and against the respective country workplans. The REACH management team meet monthly with the FCDO SRO.
As expected, expenditure grew noticeably from 2022, as COVID-19 related restrictions were lifted. The most substantial increase was in REACH partner costs, with the contracting cycle (call-down) 2022-2024 starting in mid-2022 and activities ramping up in scale. Similarly, although to a slightly lesser extent, partnership funding grants reached pre-pandemic levels at this time. REACH remained within the limits of the programme’s overall budget headers and the Programme Management team continued to follow financial management best practice. This year, the management team prioritised reviewing and fine-tuning REACH’s expenditure outlook for the remainder of the programme, factoring in the pandemic years' unavoidable slowdown and the need and potential for research activities to bounce back post-COVID. This was at the basis of the discussions with FCDO and successive approval of a no-cost extension of REACH until March 2025, which focused on ensuring the remaining research projects (Turkana Jet) could be concluded despite delays while also focusing on activities to scale REACH’s impact (Contract Amendment 2, approved in April 2023).
Key cost drivers and VfM performance on economy are shown in the table below, which analyses the expenditure in specific budget headers against the total expenditure in 2015 to March 2025.

Key costs	% total budget	Cost drivers	Actions to manage key costs
Staff	24%	Oxford staffing: research, administration, faculty, and DPhil bursaries	The University of Oxford salary and grading structure is in accordance with the National Pay Spine and comprises employee salary, national insurance and pension. Salaries are uplifted in line with sector-wide national agreements on an annual basis. Funding from alternative sources has also been secured. / REACH Oxford researchers have secured some separate grants in 2023 (DEFRA, MRC PHIND, PALM- TREEs and Hygiene Futures), allowing staff cost sharing.
Partnership Funding / (grants awarded through competitive call outside of consortium)	22%	Staffing, research costs, meetings / / training events, institutional overheads	A budget and payment schedule are agreed in advance for all partnership funding grants awarded. Each grant holder is required to provide financial statements of expenditure at defined intervals. For most contracts, the final payment is based on actual costs incurred, where the grant holder is responsible for any overspend, whilst any underspend is retained by REACH.
Partner Costs	31%	Staffing, research costs, meetings / / training events, institutional overheads	Budgets are prepared and approved at the start of each call-down agreement. Economies of scale are applied where possible. Local staff are / employed wherever possible to minimise travel and subsistence (T&S) costs. Overheads are negotiated ahead of contracting.
Travel and subsistence costs	3%	Flights, accommodation	Travels are planned to be multi-purpose where possible to minimise flight costs, or combined with complementary projects so that costs can be / shared. Wherever possible, flights are booked with a cancellation option to ensure that costs can be refunded.

Programme-level approach to monitoring and evaluation [1/2 page]
REACH continued to systematically monitor activities, outputs and expenditure through a process of 4-monthly reporting by our country partners against logframe indicators, workplan and budgets, and mid-term and end-of-project reporting all grant holders. Workplans and deliverables were agreed with partners, and these linked to and informed their budgets and payments.
Monitoring and disposal of assets
FCDO approved the transfer of all assets (primarily water quality monitoring equipment and fixed weather station equipment) to local REACH research partners to enable the partners to continue to deliver the services and research approaches developed under REACH. One low value meteorology device was destroyed during the Tigray war and following investigation was written off according to FCDO’s requirements. The Programme Management Office maintained an asset register for all items of REACH equipment in accordance with the contract throughout. This has been updated, finalised and included as Annex C of the REACH PCR confirming transfer and disposal of all assets.
Programme Closure
The programme has been closed in line with all PROF rules. All invoices have been paid.

Date of last narrative financial report	May 2024	Date of last audited annual statement	Published mid- Dec with supporting letter of comfort at REACH Programme Completion Report 2025 Annex B