## Sheet1
PROJECT TITLE | Global Agriculture and Food Security Programme
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
Planned
| Household income (production-based approach (revenues minus costs) | Achieved | [10 empty] | Please see narratives in the data note file | PuSW: Please refer to the Slides on individual project's achievements on Tier 1 indicators PrSW: Please see narrative in the data notes file | PuSW: Please refer to the slides on individual project's achieviment on Tier 1 indicators. | PuSW: Please refer to the slides on individual project's achievements on on Tier 1 and outcome indicators
Source
Impact Evaluations
Rural communities in the poorest countries have improved incomes and food security | Impact Indicator 2 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
Planned
| Food Insecurity Experience Scale | Achieved | [10 empty] | Please see narratives in the data note file | PuSW: Please refer to the Slides on individual project's achievements on Tier 1 indicators PrSW: Please see narrative in the data notes file
Source
All public sector window projects and a sample of private sector window projects
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
|  | Planned | [14 empty] | Target is to raise crop yields by 25 percent in countries where productivity gains are an explicit objective
| Crop Yields | Achieved | [10 empty] | Please see narratives in the data note file | PuSW: Please refer to the Slides on individual project's achievements on Tier 1 indicators PrSW: Please see narrative in the data notes file | PuSW: Please refer to the slides on individual project's achieviment on Tier 2.1 outcome indicators. | PuSW: Please refer to the slides on individual project's achievements on on Tier 1 and outcome indicators
Source
Projects where productivity is a specific goal
Men and women in rural areas have increased incomes, productivity and improved food security and nutrition. | Outcome Indicator 2 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
Planned
| Food Consumption Score, Minimum Dietary Diversity | Achieved | [10 empty] | Please see narratives in the data note file | PuSW: Please refer to the Slides on individual project's achievements on Tier 1 indicators PrSW: Please see narrative in the data notes file |  | PuSW: Please refer to the slides on individual project's achievements on on Tier 1 and outcome indicators
Source
Projects which have explicit nutrition objectives
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
| Outcome Indicator 3 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
Planned
| GAFSP Tier 1 Outcome: Number of farmers whose livelihood has become more resilient to shocks | Achieved | [12 empty] | PuSW: Please refer to the data note
Source
Projects which have explicit nutrition objectives
| Outcome Indicator 4 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
Planned
| GAFSP Tier 1 Outcome: Institutional capacity of supported organizations measured by capacity index | Achieved | [12 empty] | PuSW: Pleas refer to the data note
Source
Projects which have explicit nutrition objectives
OUTPUTS 1 (Public)AND 4 (Private) | Output Indicator 1.1 (PuSW) and 4.1 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
Grant based (1) and investment and advisory (2) activities to improve livelihoods | Number of beneficiaries reached | Planned |  |  |  | Estimated Target Value (PuSW): 2,330,996 | Estimated Target Value (PuSW):2,966,312 | Estimated Target Value (PuSW): 3,106,159 | Estimated Target Value PuSW: 3,252,599 (35% women) | Estimated target value: PuSW: 4,189,895 (35% women) PrSW: 1,158,000 | Estimated target value: PuSW: 12,451,160 (34.4% Women) PrSW: 1,300,000 (13% women) | Estimated target value: PuSW: 12,516,323 Estimated target PrSW: 1,223,727 farmers; 157,072 female (13%) | Estimated target value: PuSW: 13,506,607 Estimated target PrSW: 1,648,626 farmers; 166,720 female (10%) | Estimated target value: PuSW: 13,992,845 Estimated target PrSW: 1,486,910 farmers; 211,282 female (10%) | PuSW: 17,509,282 (39% women) Estimated target PrSW: 4,100,827 farmers; 545,126 female (13.3%) | Estimated target: PuSW: 22,714,150 (9,525,108 women) PrSW: 4,240,606 farmers; 559,271 female (13.2%)
|  | Achieved |  |  |  | PuSW: 4,027,857 | PuSW: 6,564,784 | PuSW: 8,617,472 | PuSW: 9,731,102 (40% women) | PuSW: 11,149,493 (43% women) PrSW: 1,168,071 (152,878 women, 13%) | PuSW: 15,059,219 (39% Women) PrSW: 1,193,880 (13% women) | PuSW: 16,021,393 (38.3% women) PrSW: 1,290,522 (161,864 women, 12.5%) | PuSW: 17,662,586 (41% women) PrSW: 1,443,602 (205,128 women, 14%) (please see explanation in the data note file) | PuSW: 18,547,651 (43% women) PrSW: 1,987,858 (327,031 women, 16.5%) | PuSW: 19,509,282 (42% women) PrSW: 2,119,308 (351,761 women, 16.6%) | PuSW: 24,820,185 (10,424,478 women) PrSW: 2,510,733 (340,254 women, 13.6%)
Source
|  | Total programme, cumulative. Source: GAFSP Annual Report and Portfolio Review | [11 empty] | All the PuSW estimated targets are estimated by pro-rating the disbursement ratio of the total allocation. Projects may not always update the targets during implementation, which CU is working with SE to ensure targets would be updated accordingly in the reporting system.
| Output Indicator 1.2 (PuSW) and 4.2 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Number of smallholders receiving productivity enhancement support. | Planned | • Baseline value (PuSW) = 0 trainees (17 projects) • Baseline value (PrSW) = 0 trainees (8 projects) • TOTAL: Baseline value is 0 |  | PuSW: 220,994 trainees (17 projects) (35% women) PrSW: 23,157 trainees (8 projects) (7% women) Total: 244,151 trainees (33% women) | • Estimated Target value (PuSW) = 367,459 trainees (17 projects) in 2015 (35% women) • Estimated Target value (PrSW) = 23,157 trainees (8 projects) in 2015 (3% women) • TOTAL: Estimated Target value is 390,616 trainees (33% women) | • Estimated Target value (PuSW) = 281,226 trainees (35% women) • Estimated Target value (PrSW) = 15,630 trainees (2% women) • TOTAL: Estimated Target value is 296,856 trainees (33% women) | • Estimated Target value (PuSW) = 294,485 trainees (35% women) | Estimated Target Value (PuSW): 308, 368 | Estimated Target Value PuSW: 397,230. PrSW:19,465 (644 women, 3.3%) | Estimated Target Value: PuSW:2,312,102 (39 % Women) PrSW: 31,818 (2,155 women, 6.8%) | Estimated Target Value: 2,737,117 (39% women) Estimated target PrSW: 41,818 participants; female participants: 4,405 (10.5%) | Estimated Target Value: 3,123, 580 (50% women) PrSW: 47,603 (4,405 women, 9.3%) | Estimated PuSW Target Value:4,316,831 (50% women) PrSW: 59,656 (4,980 women, 8.3%) | PuSW: 5,743,567 (Women = 2,078,890) PrSW: 71,958 (10,543 women, 14.7% women) | PuSW: 6,672,248 (2,440,642 women) PrSW: 66,500 (11,838 women, 17.8%)
| (For PuSW: Data for years 2013-2016 is Number of clients reached to raise agricultural productivity provided to scientists, extension agents, agro-dealers, farmers, community members etc (disaggregated by gender)) | Achieved |  | 21,091days | PuSW: 606 PuSW PrSW: 22,000 (4% female) Total: 22,606 | PuSW: 211,544 trainees (25% women) PrSW: 23,242 trainees (3.5% women) Total: 234,786 trainees (23% women) | PuSW: 445,959 trainees (25% women) PrSW: 23,681 trainees (3.5% women) Total: 469,640 trainees (24% women) | PuSW: 456,178 trainees (35% women) | PuSW: 488, 515 (35% women) | PuSW: 570,779 (43% women). PrSW: 27,225 (8,517 women, 31%) | PuSW:2,939,512 (39 % Women) PrSW: 36,059 (11,140 women, 31%) | PuSW: 4,850,981 (41.2% women) PrSW: 33,295 (10,653 women, 32%) | PuSW: 7,202, 418 (35% women) PrSW: 52,570 (14,044 women, 27%) | PuSW: 8,446,510 (37% women) PrSW: 59,402 (14,408 women, 27%) | PuSW: 6,699,770 (2,424,460 women, 36%) PrSW: 81,428 (20,831 women, 25.6%) | PuSW: 6,789,096 (2,461,387 women) PrSW: 85,565 (22,650 women, 26.5%)
|  | Source | [12 empty] | PuSW: Please note that the reported figure is lower compared to the previous period. Kindly refer to the attached data note explanation for more details.
|  | PuSW: Burkina Faso, Bhutan, Cambodia, The Gambia, Haiti, Honduras, Liberia, Malawi, Mongolia, Nepal, Nicaragua, Senegal, Tajikistan, Togo, Uganda, and Zambia PrSW: Bangladesh, Cambodia, Côte d'Ivoire, Ethiopia, Haiti, Honduras, Liberia, Madagascar, Mali, Nepal, Nicaragua, Pakistan, Kenya, Rwanda, Senegal, Sierra Leone, Solomon Islands, and Uganda | [9 empty] | PuSW: This reports a combination of a pre-2017 indicator (Number of farmers who have adopted the technology being promoted (Total)) and a post-2017 indicator (Number of smallholders receiving productivity enhancement support). |  | PuSW: This reports a combination of a pre-2017 indicator (Number of farmers who have adopted the technology being promoted (Total)) and a post-2017 indicator (Number of smallholders receiving productivity enhancement support). | PuSW: Both the results and targets reflect the combination of the two indicators. | PuSW: Both the results and targets reflect the combination of the two indicators.
|  | Source | [14 empty] | RISK RATING
| Output Indicator 1.3 (PuSW) and 4.3 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Number of farmers receiving inputs or service on climate resilient or sustainable agriculture practices (farmer) Disaggregation: Of which, female farmers Disaggregation: Of which, number of farmers adopting technologies or practices received | Planned | [8 empty] | PrSW: 64,283 (1,970 women, 3.1%) | PrSW: 1,686,360 (7,924 women, 0.5%) | PrSW: 1,692,115 (9,244 women, 0.5%) | PuSW: 818,379 (52% women, and 69% adoption) PrSW: 2,139,200 (361,297 women, 16.9%) | PuSW: 818,379 (52% women, and 69% adoption) PrSW: 2,184,420 (358,157 women, 16.4%) | PuSW: 2,511,307 (1,248,078 women, 18% adoption) PrSW: 2,296,199 (348,467 women, 15.2%)
|  | Achieved | [8 empty] | PrSW: 126,960 (16,489 women, 13%) | PrSW: 440,361 (3,776 women, 0.9%) | PrSW: 171,209 (8,229 women, 4.8%) | PuSW: 1,030,188 (44% women, 0 adoption) PrSW: 637,595 (156,570 women, 24.6%) | PuSW: 1,517,639 (42% women, and 6% adopted the technologies being promoted) PrSW: 767,604 (160,025 women, 20.8%) | PuSW: 2,123,565 (828,190 women, 7% adopted the technologies being promoted) PrSW: 1,004,888 (136,835 women, 13.6%)
| Output Indicator 1.4 (PuSW) and 4.4 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
|  | Planned | 0 |  |  | 69720 people | 286309 | PuSW: 299, 806 people | PuSW: 313,941 people | PuSW: 359,494 (people) | PuSW: 492,943 (people) PrSW: 390 organizations | PuSW: 3,413 producer-based organizations (PBOs) Estimated target for PrSW: 446 | PuSW: 2641 producer-based organizations (PBOs) Estimated target for PrSW: 531 | Estimated target for PuSW: 4470 Estimated target for PrSW: 639 | PuSW: 22,656 PrSW: 1,260 | PuSW: 25,033 PrSW: 2,471
| Number of producer-based organizations supported | Achieved |  | 35,988 people | 94865 people | 105284 people | 314644 people | PuSW: 337,301 people | PuSW: 353,881 people | PuSW: 389,191 (people). PrSW 269 organisations | PuSW: 441,156 (people) PrSW: 435 organizations | PuSW: 13,502 PBOs PrSW: 614 organizations | PuSW: 17,326PBOs PrSW: 375 | PuSW: 18,959 PBOs PrSW: 1489 | PuSW: 23,897 PBOs PrSW: 1727 | PuSW: 26,196 PrSW: 2,536
| (Indicator 2013-2016 is number of targeted clients who are members of an association including producer association, cooperative, water user association etc) | Source | [8 empty] | PUSW: 10 projects (here the indicator used is actually number of targeted clients who are members of an association including producer association, cooperative, water user association etc). | Since this indicator is asking about number of organizations, so we will report on organizations here from now on instead of number of people. This is a combination of pre-2017 indicator (Number of operational water user associations) and post-2017 indicator (Number of producer-based organizations supported) | The higher target (3413 PBOs) reported in June 30, 2021 was lower because it was not pro-rated then. |  |  |  | RISK RATING
Bhutan Cambodia Ethiopia Ethiopia Mali Niger Tajikistan Timor Leste Togo_WB Togo_IFAD
| Output Indicator 1.5 (PuSW) and 4.5 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
|  | Planned | • Baseline percentage (PuSW) = 0% • Baseline percentage (PrSW) = 0% |  |  | • Estimated target percentage (PuSW)= 58% (18 projects with nutrition focus) • Estimated target percentage (PrSW)= 10% (3 projects with nutrition focus) • TOTAL: Estimated Target value is 34% of projects in the GAFSP portfolio with nutrition focus in 2015 | • Estimated target percentage (PuSW)= 59% (23 projects with nutrition focus) • Estimated target percentage (PrSW)= 8% (3 projects with nutrition focus) | • Estimated target percentage (PuSW)= 62% (24 projects with nutrition focus) | Estimated target percentage (PuSW) = 52% (25 projects with nutrition focus) - The Target is revised down because the base has been increased from 39 to48, with new GAFSP projects evaluated | PuSW: 52% of projects have a nutrition focus. PrSW: 10% of projects have a nutrition focus. | PuSW: 1,056,942 people PrSW: 21% for investment projects and 18% advisory service projects | PuSW: 2,473,920 PrSW: 17% for investment projects and 19% for advisory service projects | PuSW: : 2,786,817 PrSW: 16% for investment projects and 17% for advisory service projects | Estimated PuSW target: 2,192,114 PrSW: 15% for investment projects and 18% for advisory service projects | PuSW: 5,657,541 (Women = 2,709,840) PrSW: 16% for investment projects and 17% for advisory service projects | PuSW: 6,331,982 (3,063,132 women) PrSW: 16% for investment projects and 16% for advisory projects
| Number of people receiving improved nutrition services and products, disaggregated by gender & age | Achieved |  | Not available | PuSW: 15 projects PrSw: 0 project Total: 15 projects | PuSW: 59% (19 projects with nutrition focus) PrSW: 15% (2 out of 30 projects approved) Total: 33.8% of projects in the GAFSP portfolio with nutrition focus PuSW: 59% (19 projects with nutrition focus) PrSW: 15% (2 out of 30 projects approved) Total: 33.8% of projects in the GAFSP portfolio with nutrition focus | PuSW: 51% (20 projects with nutrition focus) PrSW: 6% (2 out of 30 projects approved) | PuSW: 62% (24 projects with nutrition focus | PuSW: 79% (38 out of 48 projects have explicit or implicit nutrition focus) | PuSW: 79% of projects (38 of 48) have a nutrition focus. PrSW: 21% for investment projects (14 of 66 projects) and 18% for advisory service projects (13 of 71 projects) | PuSW: 1,224,269 people 17% of GAFSP public sector funding is targeted to nutrition activities. $193M across 24 countries are invested in nutrition-sensitive agriculture and nutrition specific non-agriculture. (New projects approved in 2019 and 2020 have not been accounted for because they are still under preparation so we do not have their PADs) PrSW: 17% for investment projects and 19% advisory service projects | PuSW: 4,610,861 people 17% of GAFSP public sector funding is targeted to nutrition activities. $193M across 24 countries are invested in nutrition-sensitive agriculture and nutrition specific non-agriculture. (New projects approved in 2019 and 2020 have not been accounted for because they are still under preparation and so we do not have their PADs) PrSW: 16% for investment projects (13 of 81 projects) and 17% for advisory service projects (15 of 88 projects) | PuSW: 4,967,322 17% of GAFSP public sector funding is targeted to nutrition activities. $193M across 24 countries are invested in nutrition-sensitive agriculture and nutrition specific non-agriculture. An analysis of the design documents of 23 GAFSP projects is currently underway to update the portfolio-level nutriton analysis and account for new projects approved in 2019 and 2020. PrSW: 15% for investment projects (13 of 84 projects) and 18% for advisory service projects (17 of 95 projects) (Please see explanation in the data note file) | PuSW: 6,260,890 33% of GAFSP public sector funding are considered as nutrition sensitive (in terms of $ value) while 68% of projects have nutrition sensitive activities. The nutrition sensitive agriculture anaylsis has been updated to include COVID AF (2020), Six Call projects. PrSW: 16% for investment projects (14 of 89 projects) and 17% for advisory service projects (17 of 101 projects) | PuSW: 5,959,760 (women = 2,997,126) PrSW: 16.1% for investment projects (15 out of 93 projects) and 16% for advisory projects (17 out of 106 projects) | PuSW: 6,427,344 (3,217,898 women) PrSW: 15.8% for investment projects (15 out of 95 projects) and 14.2% for advisory projects (16 out of 113 projects) | RISK RATING
|  | Source | [11 empty] | There is a significant increase on this indicator as projects from fourth and fifth Cal entered into the mid-term or later stage of the implementation, driving up the results. | PuSW: Please note that the reported figure is lower compared to the previous reporting period. Kindly refer to the attached data note explanation for more details.
| Output Indicator 1.6 (PuSW) and 4.6 (PrSW) |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
|  | Planned | [7 empty] | PrSW: 6,178 (2,659 women, 43%) | PrSW: 16,459 (44.5% women) | PuSW: 56,395 (49% women) PrSW: 17,937 direct jobs direct jobs to women: 7,485 (41.7%) | PuSW: 77,372 (54% women) PrSW: 18,254 (7,511 women, 41.1%) | PuSW:83,022 (54%) PrSW: 28,663 (7,571 women, 26.4%) | PuSW: 306,508 (Women = 101,615) PrSW: 30,210 (7,654 women, 26.3% women) | PuSW: 301,438 (98,971 women) PrSW: 30,684 (7,657 women, 25%)
| Direct employment provided, gender disaggregated-number of full time equivalent jobs | Achieved | [7 empty] | PrSW: 11,925 (5,617 women, 47.2%) | PuSW: 125,140 (36,557 women) PrSW: 6,682 (53.1% women) | PuSW: 262,721 (142,066 women) (54% women) PrSW: 24,121 (9,298 women, 39%) | PuSW: 271, 094 (145,970 women) (53% women) PrSW: 34,656 (13,330 women) (38% women) | PuSW: 405,152 (53% women) PrSW: 35,487 (13,735 women, 39% women) | PuSW: 286,496 (Women =107,260) PrSW: 38,909 (15,426 women, 39.6%) | PuSW: 287,522 (109,778 women) PrSW: 42,998 (15,614 women, 36.3%)
|  | Source | [8 empty] | 5 projects (Benin, Ethiopia AGP 2, Haiti_PITAG, Liberia, Zambia). | 12 projects report on this | 12 projects report on this (Benin, Burundi, Cambodia, Ethiopia AP, Haiti_PITAG, Kenya_SIVAP,Liberia_SAPEC, Mali, Niger, Tanzania_TANIPAC, Zambia) | 17 projects report on this ( Benin AFDB, Burundi IFAD, Cambodia ADB Rice, Ethiopia 1 WB, Kenya AFDB SIVAP, Liberia AFDB SAPEC, Mali AFDB, Niger AFDB, Senegal AFDB, Zambia AFDB,Mali IFAD, Bangladesh FAO, East Africa IFAD, Tanzania AFDB, Haiti IADB PITAG, Ethiopia 2 FAO, Ethiopia 2 WB | PuSW: Please note that the reported figure is lower compared to the previous reporting period. Kindly refer to the attached data note explanation for more details. |  | RISK RATING
OUTPUT 2 | Output 2.1 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
Performance of GAFSP as a funding mechanism | Public and Private Sector Windows working effectively together - number of projects with joint activities across PuSW, PO, BIFT and PrSW, also as a % of total projects | Planned | Initial results framework currently in place | Both windows have their own results framework | 80% of results can be disaggregated by gender | Mid 2015; aggregated results assessed as part of DFID's project completion report process which can be disaggregated by gender. Emerging findings from MTR acted on. | DFID and GAFSP to agree on the new results framework as per the recommendations outlined under outputs 1-5 of the 2015 annual review. This will include gender disaggregated data and be he basis of future DFID performance reviews of GAFSP | M&E Plan Finalised and made public, work to define and measure indicators in progress with Ses | M&E plan implemented and results being tracked using new indicators, with read across to results from pre existing projects | A qualitative assessment by DFID of whether the Public and Private Sector Windows are working effectively together
|  | Achieved |  |  | Results frameworks are in place across both windows. There are still issues with data collection and indicator definitions, which have hampered DFID’s ability to assess progress for this annual review. Gender indicators are in place, but uptake of some remains low. The mid-term review has undertaken an initial assessment. Phase two will help inform the GAFSP steering committee of precise measures to improve performance. | Monitoring and Evaluation groups have been set up to reform GAFSP’s existing results framework. Alongside these initiatives, the public and private sector window have been working more closely together in two countries. Gender reporting in the PrSw is still below expectations. | GAFSP's M&E Plan has been updated based on inputs from across GAFSP's SC. A revised M&E Plan document, which will guide SEs will be shared for SC endorsement by the end of 2016 |  |  | Specific PrSW advisory project examples: AMRU Rice, Rwanda Grain Markets, Ethiopia Agribiz Development | Specific PrSW project that worked together: Mercon Coffee (IFC and WB_PAIPSAN in Nicaragua). | Specific PrSW advisory project examples: (i) Haiti Horticulture project, (ii) Nicaragua Mercon Coffee project | PuSW/PrSW coordination advisory projects: (i) Haiti Horticulture (ii) Nicaragua Mercon Coffee (iii) Côte d'Ivoire AfDB Women-led Coops (please see explanation in the data note file) | PuSW/PrSW coordination advisory projects: (i) Haiti Horticulture (ii) Nicaragua Mercon Coffee (iii) Côte d'Ivoire AfDB Women-led Coops (please see explanation in the data note file) | PuSW/PrSW coordination advisory projects: (i) Haiti Horticulture (ii) Nicaragua Mercon Coffee (iii) Côte d'Ivoire AfDB Women-led Coops (please see explanation in the data note file)
Source
| Output 2.2 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
|  | Planned | [5 empty] | PuSW follows the definition of World Bank Corporate Score Card to report on Disbursement Ratio. Disbursement ratio (%): Disbursed amount for lending operations as a ratio of undisbursed balance in a Fiscal Year. There is no GAFSP target set for Disbursement Rate/Ratio. Target: Indicatively, the WB uses a target of 20% in its corporate reporting for all lending projects. A higher Disbursement Ratio better is the quality of the portfolio (inverse of speed of disbursement) | [9 empty] | The speed of disbursement/time-elapsed, which can be estimated by the number of months between approval by SC and disbursement by SE is a fairly static number. If needed, we can report on this by cohort, which should be rational approach to presenting the data - as below
| Disbursement Rate (The number of months between approval by the Steering Committee and disbursement by a supervising entity) | Achieved | [5 empty] | PuSW - 45% - this is based on the average disbursement rate of the projects that are under implementation. |  |  | Overall Avg. Speed of Disbursement: 21.5 months (21.55 months is the average for the 46 projects that have completed disbursed and those that are currently disbursing. These are the 20 closed projects and 26 projects currently disbursing. Projects with under-preparation and/or with expected dates of disbursments are not included in the calculation.) | Overall Avg. Speed of Disbursement: 23.8 months (23.8 months is the average for the 55 projects that have completed or are currently under disbursement. Projects that are under preparation or approved but not disbursed yet are not included in the calculation. | Overall Avg. Speed of Disbursement: 24.5 months (23.8 months is the average for the 55 projects that have completed or are currently under disbursement. Projects that are under preparation or approved but not disbursed yet are not included in the calculation. | Overall Avg. Speed of Disbursement: 25.35 months | The overall average time-elapsed between project approval and first disbursement is 21.5 months, based on data from 41 completed and 31 ongoing projects. Projects that are still under preparation or have been approved but have not yet started disbursement are excluded from this calculation. | The overall average time-elapsed between project approval and first disbursement is 23.5 months, based on data from 46 completed and 67 ongoing projects. |  | Avg. Speed of Disbursement Grant allocation_June 2010: 22.1 month Avg. Speed of Disbursement Grant allocation_Nov 2010: 26 month Avg. Speed of Disbursement Grant allocation_Nov 2010: 26 month Avg. Speed of Disbursement Grant allocation_May 2012: 24.7 month Avg. Speed of Disbursement Grant allocation_Sep 2013: 25.1 month Avg. Speed of Disbursement Grant allocation_Nov 2014: 22.3 month Overall Avg. Speed of Disbursement: 24.4 months
Source
The improvement is mainly due to the significantly shortened timeline from the 7th Call Country-led projects.
| Output 2.3 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
|  | Planned | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
| Leverage ratio- the extent to which GAFSP funding has been instrumental in mobilising funds from other sources. | Achieved |  | GAFSP PrSW funding to Total Project Size: 1:10.1 GAFSP funding to IFC Investment: 1:1.8 (For FY13) | GAFSP PrSW funding to Total Project Size: 1:4.5 GAFSP funding to IFC Investment: 1:1.9 (For FY14) | GAFSP PrSW funding to Total Project Size: 1:5.1 GAFSP funding to IFC Investment: 1:1.7 (For FY15) | GAFSP PrSW funding to Total Project Size: 1:4.8 GAFSP funding to IFC Investment: 1:1.2 (For FY16) | GAFSP PrSW funding to Total Project Size: 1:4.5 GAFSP funding to IFC Investment: 1:1.6 (For FY17) | GAFSP PrSW funding to Total Project Size: 1:6.9 GAFSP funding to IFC Investment: 1:2.1 (For FY18) | June 2019 PrSW achieved GAFSP to total project value 1:7.6 for 2019 GAFSP to IFC funding 1:1.0 for 2019 | GAFSP PrSW funding to Total Project Size: 1:6.1 GAFSP funding to IFC Investment: 1:2.0 (This is the leverage ratior for FY20) | PuSW: 2.1 ($1 of GAFSP attracted $2.1 from other sources). This is a combination of primary co-financing, mobilized co-financing, and additional co-financing. GAFSP PrSW funding to Total Project Size: 1:16.3 GAFSP funding to IFC Investment: 1:3.6 (This is the leverage ratior for FY21) | PuSW: 2.5 ($1 of GAFSP attracted $2.5 from other sources). This is a combination of primary co-financing, mobilized co-financing, and additional co-financing. GAFSP PrSW funding to total project size: 1:2.8 GAFSP funding to IFC investment: 1:1.2 (This is the leverage ratio for FY22) | PuSW: 2.48 ($1 of GAFSP attracted $2.48 from other sources). This is a combination of primary co-financing, mobilized co-financing, and additional co-financing. PrSW: GAFSP funding to total project size Investment: 1:2.0 GAFSP funding to IFC Investment: 1:1.4 (For FY23) | PuSW: 1.86 ($1 of GAFSP grant attracted $1.86 from other sources). PrSW: GAFSP to total project size 1:6.3 GAFSP funding to IFC Investment: 1:3.0 (For FY24) | PuSW: 1.92 ($1 of GAFSP grant attracted $1.92 from other sources). PrSW: GAFSP funding to total project size 1:6.1 GAFSP funding to IFC investment 1:3.6 (for FY25)
|  | Source | [14 empty] | RISK RATING
| DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
| Output 2.4 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Number and value of projects committed (Private Sector Window and BIFT only) and disbursed | Planned |  | in FY13 it is expected to commit between US$ 4-5million for advisory services | in FY14, GAFSP targeted US$4million in advisory services | AS pipeline for FY15 was estimated at 10-15 Advisory Services projects for US$4 million. | in FY16, GAFSP planned to support 10 to 15 Advisory Services projects for US $6.3 million | For FY17, the advisory pipeline included 10-12 projects for US $4.5million | FY18 ADVISORY pipeline included 10-12 Advisory Services projects for US$10.6 million. FY18 INVESTMENT pipeline included 12-14 new investment projects for a approximate investment amount of US$70.5 million. | FY19 Advisory pipeline included 5 – 17 Advisory Services projects for US$9 million. FY19 INVESTMENT pipeline included 10-12 new investment projects for an approximate investment amount of US$50 million | FY20 ADVISORY pipeline included 17 projects for US$ 7.1 million. FY20 INVESTMENT pipeline included 10-12 new investment projects for an approximate investment amount of US$50 million | FY21 Advisory pipeline included 16 projects fro US$ 10.74million. FY21 INVESTMENT pipeline included 10-12 new investment projects for an approximate investment amount of US$50 million | FY22 Advisory pipeline included 14 projects for US$10.41 million. FY22 INVESTMENT pipeline included 8-10 new investment projects for an approximate investment amount of US$40 million | the FY23 pipeline for AS included 14 projects for US$5.3 million. FY23 INVESTMENT pipeline included 8-10 new investment projects for an approximate investment amount of US$50 million | AS Pipeline for FY24 was 13 projects for US$8.2 million. FY24 INVESTMENT pipeline included 7-9 new investment projects for an approximate investment amount of US$50-60 million | The ADVISORY pipeline for FY24 was 12 projects for US$3.7 million. FY24 INVESTMENT pipeline included 7-9 new investment projects for an approximate investment amount of US$50-60 million
|  | Achieved |  | in FY13, GAFSP approved 11 Advisory projects for US$3.2 million | In FY14, GAFSP approved 21 advisory projects for funding US$4.9 million | in FY15, we approved 14 new advisory services activities totaling $2 million. | In fiscal year 2016, GAFSP’s Private Sector Window approved 9 advisory services projects with a total funding of US $1.17 million. | FY17 ADVISORY - 10 projects had been approved for a total funding of US$5.2 million. | FY18 ADVISORY, 20 new projects were approved with a total funding of US$8.7 million FY18 INVESTMENT - 8 new projects were committed for a total funding of US$ 46.33 million; 10 disbursements made to new projects and US $43.12 M in total disbursements to GAFSP PrSW investment projects | FY19 ADVISORY, 9 new projects were approved, and 4 projects received additional support for a total funding of US$8.1 million. FY19 INVESTMENT - 6 new projects were committed for a total funding of US$ 21.05 million; 5 disbursements made to new projects and US $5.53 M in total disbursements to GAFSP PrSW investment projects | FY20 ADVISORY, eight new projects were approved, and three projects received additional support for a total funding of US$3.12 million FY20 INVESTMENT - 7 new projects were committed for a total funding of US$ 23.62 million; 7 disbursements made to new projects and US $33.09 M in total disbursements to GAFSP PrSW investment projects | In FY21 ADVISORY, GAFSP PrSW approved nine new advisory projects and provided additional funding to nine existing projects, with a total funding of US$6.28 million FY21 INVESTMENT – 4 new projects were committed for a total funding of US$ 18.5 million; 4 disbursements made to new projects and US $16.93 M in total disbursements to GAFSP PrSW investment projects | In FY22 ADVISORY, GAFSP PrSW approved seven new advisory projects and provided additional funding to eight existing projects, with a total funding of US$7.92 million FY22 INVESTMENT – 5 new projects were committed for a total funding of US$ 25.03 million; 5 disbursements made to new projects and US $15.89 M in total disbursements to GAFSP PrSW investment projects | In FY23 ADVISORY, GAFSP PrSW approved six new AS projects and provided additional funding to four existing projects, with a total funding of US$4.88 million FY23 INVESTMENT – 6 new projects were committed for a total funding of US$ 26.82 million; 4 disbursements made to new projects and US $10.35 M in total disbursements to GAFSP PrSW investment projects | In FY24, GAFSP PrSW approved five new AS projects and provided additional funding to four existing projects, with a total funding of US$1.33 million FY24 INVESTMENT – 4 new projects were committed for a total funding of US$ 35.12 million; 6 disbursements made to new projects and US $39.38 M in total disbursements to GAFSP PrSW investment projects | In FY25 ADVISORY, GAFSP PrSW approved seven new AS projects and provided additional funding to two existing projects, with a total funding of US$2.9 million FY25 INVESTMENT - 2 new projects were committed for a total funding of US$12.7 million; 9 disbursements made to projects and US$30.5 M in total disbursements to GAFSP PrSW investment projects
Source
| Output 2.5 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Volume of financing that is 2.5.1 climate related 2.5.2 gender sensitive 2.5.3 nutrition related | Planned | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Achieved | [7 empty] | PrSW: CLIMATE: In FY19, 20% of PrSW’s investment portfolio, comprising US$2.89 million was listed as climate smart. On the AS side, 20% of FY19 approved projects qualified in part or whole under climate smart agriculture. GENDER: This fiscal year, GAFSP Advisory Services approved seven projects with gender components NUTRITION: During FY19, the GAFSP AS portfolio approved four projects with a nutrition component and increased equity investments in one IS project. | PrSW: CLIMATE: As of June 30, 2020, a total of at least 24 PrSW investment projects have been classified as climate smart. In total, US$113 million of GAFSP financing has supported these 24 climate smart projects, accounting for 30% of total GAFSP PrSW investments. In FY20, 5 investments were tagged as climate smart, adding up to a total investment amount of US$29.4 million (or 55% of the FY20 approved volume). On the AS side, 2 new projects supported, sought funding under the climate smart agriculture theme, and an additional 3 AS projects were flagged for their work in climate. Historically, AS projects under the climate smart agriculture theme represent 14% of all AS work, amounting to US$4.6 million. GENDER: GAFSP funded five AS projects with gender components in FY20. As of June 2020, 19 active projects in the portfolio that are gender tagged. NUTRITION: Based on the new nutrition-tag framework, 13 projects received a Nutrition tag within GAFSP PrSW overall portfolio. One new project was approved under the theme in FY20. As of June 2020, 12% of the total cumulative GAFSP PrSW investment amount can be categorized under this theme. | PrSW: CLIMATE: As of June 30, 2021, a total of 26 PrSW investment projects have been classified as Climate as per IFC definitions. Taking into account which element and how much of these 26 projects are Climate, a total of US$146 million of GAFSP financing is Climate. During FY21, on the investment side, two investment projects approved are under the climate cross-cutting theme, amounting to US$32.9 million, or 65% of the FY21 approved investment volume. On the AS side, one new project and one existing project falls under the climate cross-cutting theme, with a total approved amount of US$2.09 million, or 33% of the FY21 approved AS volume. GENDER: In FY21, GAFSP funded five AS projects with gender components. NUTRITION: No new investment projects approved with a nutrition tag | PrSW: CLIMATE: As of June 30, 2022, a total of 26 PrSW investment projects have been classified as Climate as per IFC definitions.13. Taking into account which element and how much of these 26 projects are Climate, a total of US$146 million of GAFSP financing is Climate. During FY22, on the investment side, no investment projects are under the climate cross-cutting theme. On the AS side, three new projects and two existing projects fall under the climate cross-cutting theme, with a total approved amount of US$4.0 million, or 51% of the FY22 approved AS volume. GENDER: In FY22 advisory supported 4 new projects and 5 existing projects that are working on Gender. NUTRITION: As of June 30, 2022, a total of 14 GAFSP-supported investment projects have received the Nutrition tag based on IFC’s nutrition framework. In FY22, there were no new investment projects approved under the nutrition cross-cutting theme. However, on the advisory side, three new projects were approved focusing on delivering food safety practices to IFC clients. | PuSW: • 47.5% of the or $668.97m allocated to climate co-benefits. • 41% of project beneficiaries are women. • 68% of projects have nutrition contributions, equal to 22.5% of the funds or $399.9m. PrSW: CLIMATE As of June 30, 2023, a total of 27 PrSW investment projects have been classified as Climate as per IFC definitions. A total of US$192 million of GAFSP financing is Climate. During FY23, on the investment side, two investment projects are under the climate cross-cutting theme, amounting to US$16.5 million, or 56% of the FY23 approved investment volume. On the AS side, three new projects and one existing project that received additional funding in FY23 fall under the climate cross-cutting theme, with a total approved amount of US$1.3 million. GENDER: In FY23, 90% of approved project count and 95% of funding allocation of AS projects were gender flagged. Since inception, 50% of AS project count and 69% of AS project allocations have been gender flagged. Additionally, due to the new gender flagging process for investment projects, we can report that in FY23, 60% of investment project count and 40% of investment volume were gender flagged. NUTRITION : As of June 30, 2023, a total of 14 GAFSP-supported investment projects have received the nutrition tag based on IFC’s nutrition framework. In FY23, there were no new investment projects approved under the IFC’s nutrition framework | PuSW: • 91% of all projects have climate co-benefits, equal to 49% of funds or about $880m. • 42% of project beneficiaries are women. • 78% of all projects have nutrition contributions, equal to 31% of funds or about $550m. PrSW: CLIMATE: As of June 30, 2024, a total of 32 investment projects have been classified as climate as per IFC definitions. A total of US$240 million of GAFSP financing is climate-tagged. For invetsment, US$30.4 million, and for advisory a total approved amount of US$1.01 million. GENDER: In FY24, 67% of approved project count and 57% of funding allocation of AS projects were gender flagged. NUTRITION: US$8.8 for investment (Pearl Dairy), nothing on Advisory | PuSW: • 91% of all projects have climate co-benefits, equal to 49% of funds or about $880m. • 42% of project beneficiaries are women. • 78% of all projects have nutrition contributions, equal to 31% of funds or about $550m. PrSW: CLIMATE: As of June 30, 2025, a total of 37 investment projects have been classified as climate as per IFC definitions. A total of US$240.6 million of GAFSP financing is climate-tagged During FY25, no new investment project is climate-tagged; for advisory, four new and two existing projects that received funding in FY25 were climate tagged GENDER: For AS in FY25, 67% of approved projects and 89% of the funding amount were gender flagged NUTRITION: No new advisory or investment projects
|  | Source | [11 empty] | PuSW; The results are based on projects from 1st to 5th Calls for Proposal | PuSW; The results are based on projects from 1st to 7th Calls for Proposal. Kindly, refer to the data note for further details. | PrSW: The climate-tag project count has been updated as part of routine data quality checks
OUTPUT 3 (PrSW only) | Output 3.1 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025) | Assumptions
Performance of private sec investment and advisory mechanism | Leverage ratio (covered by 2.3 above) | Planned
Achieved
Source
| Output 3.2 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Percentage of projects rated successful on development outcome | Planned |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | Achieved |  |  | PrSW: 1 positive out of 1 total | PrSW: 2 positive out of 2 total | PrSW: 2 positive out of 2 total | PrSW: 3 positive out of 4 total | PrSW: 4 positive out of 6 total | PrSW: 5 positive out of 9 total | PrSW: 8 positive out of 13 total | PrSW: 9 positive out of 17 total | PrSW: 11 positive out of 25 total | PrSW: 15 positive out of 33 total | PrSW: 25 positive out of 45 total | PrSW: 26 positive out of 52 total
Source
| Output 3.3 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Product distribution of projects—debt, equity, guarantees, advisory services | Planned | [7 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Achieved | [6 empty] | PrSW (US$) Loan = 14.1 million RSF = 14 million Partial Credit Guarantee = 1.3 million Advisory = 8.7 million | PrSW (US$) Loan = 7.9 million Equity = 11.6 million Advisory = 8.09 million | PrSW (US$) Loan = 31.6 million RSF = 11.2 million Equity = 10 million Advisory = 3.12 million | PrSW (US$) Loan = 42.9 million RSF = 7.5 million Advisory = 6.28 million | PrSW (US$) Sub Loan = 11.2 million RSF = 1.4 million Advisory = 7.92 million | PrSW (US$) Loan = 12.8 million Sub Loan = 14 million RSF = 2.5 million Advisory = 4.88 million | PrSW (US$) Loans = 19.4 million Equity = 2.5 million Sub-Loan = 8.5 million Advisory = 1.33 million | PrSW (US$) RSF = 12 million Swap Rate Buydown = 0.7 million Advisory = 2.9 million
|  | Source | [14 empty] | RISK RATING
| DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
| Output 3.4 |  | Baseline | Milestone 1 (June 30th 2013) | Milestone 2 (June 30th 2014) | Milestone 3 (June 30th 2015) | Milestone 4 (June 30th 2016) | Milestone 4 (June 30th 2017) | Milestone 4 (June 30th 2018) | Milestone 5 (June 30th 2019) | Milestone 6 (June 30th 2020) | Milestone 7 (June 30th 2021) | Milestone 8 (June 30th 2022) | Milestone 9 (June 30th 2023) | Milestone 10 (June 30th 2024) | Milestone 11 (June 30th 2025)
| Country distribution of projects—percentage of projects in fragile and conflict-affected states | Planned | [6 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Achieved | [6 empty] | PrSW IS: 70% of approved volume PrSW AS: 7.5% of approved volume | PrSW IS: 20% of approved volume PrSW AS: 22% of approved volume | PrSW IS: 63% of approved volume PrSW AS: 33.6% of approved volume | PrSW IS: 55.7% of approved volume PrSW AS: 9.67% of approved volume | PrSW AS: 12.25% of approved volume | PrW IS: 44% of approved volume PrSW AS: 17% of approved volume | PrSw IS: 28% of approved volume PrSW AS: 56.6% of approved volume | PrSW IS: 0% of approved volume PrSW AS: 37.9% of approved volume
Source
Note on M65: Shijie Yang: Noted that not all projects have targets on this indicator, though there are actual achievements.
Note on L69: Shijie Yang: Since there is absence of target/planned values for Ethiopia and Haiti, the total planned value is not entered.
Note on L70: Shijie Yang: Benin, Liberia, and Zambia did not report gender disaggregated data)
Note on L76: Shijie Yang:  Mercon Coffee This project will build up /collaborate with two World Bank projects: the first one (PAIPSAN) was funded by GAFSP’s Public Sector Window. PAIPSAN provided 600 producers in the Caribbean Coast with Robusta seedlings and technical support from the National Institute for Agricultural Technology (INTA) and the Ministry of the Family, Community, Cooperative and Associative Economy (MEFCCA). While PAIPSAN ended in 2019, between March – September 2020, a technical assessment carried out with GAFSP funding interviewed 342 PAIPSAN beneficiaries (# farmers surveyed shown in map) and identified potential and interest for integration into Mercon’s supply chain. Activities to support linkage are included in the recently approved US$ 1.3 million GAFSP PrSW project with Mercon. A second collaboration is being pursued with the Land Administration Project PRODEP II (P121152). This WB project has an on-demand land titling window that is overseen by Nicaragua’s Attorney General’s Office. IFC and Mercon have established dialogue to have Mercon’s farmer suppliers (and potential PAIPSAN participants) included in the program for 2021. Access to land titling could help Mercon provide financing to integrate new farmers or provide additional support for existing suppliers.
Note on M76: Shijie Yang: See the attachment for two examples
Note on B79: Maddison Alexandra Abboud: N/A for PrSW