Annual Review

Title: Global Innovation Fund
Programme Value £ (full life): £75,600,000		Review Date: May 2026
Programme Code: 202604	AMP Start Date: 30 June 2013	AMP End Date: 31 March 2027

#### Summary of Programme Performance
Year	2013- / 2015	2016- / 2017	2017- / 2018	2018- / 2019	2019- / 2020	2020- / 2021	2021- / 2022	2022- / 2023	2023- / 2024	2024-2025	2025-2026
Overall Output Score	A	A	A	A	A	A+	A	A	A+	A	A+
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/5435489.odt
DevTracker Link to results framework:

# A. SUMMARY AND OVERVIEW
## Description of programme
Innovation is an important driver of inclusive economic growth and climate resilience, with the potential to deliver strong social impact and value for money through the mobilisation of private capital. However, Many promising innovations fail to scale after early validation—the “valley of death”—because funding, support, and investor appetite are often misaligned. This is especially true in low- and middle-income countries, where fragmented markets and reliance on short-term grants limit pathways to sustainable finance. Strategic intermediaries are therefore needed to help bridge public and private capital and support transitions to viable, market-based models.
The Global Innovation Fund (GIF) addresses this gap as an impact‑led investment vehicle focused on scaling evidence‑based solutions to inclusive economic and climate resilience challenges, while contributing to the global evidence base on what works. Supported by a coalition of donors—including the UK Government, the Swedish International Development Cooperation Agency (Sida), and other philanthropic and private sector partners—GIF uses a venture‑style approach to deploy flexible capital at early and growth stages, de‑risking innovations, strengthening business models, and catalysing follow‑on private finance. This mandate aligns closely with UK priorities on modernising development finance, strengthening equitable partnerships, and mobilising private capital. Headquartered in London with offices in Kenya, Singapore and Washington, GIF delivers on its mission primarily through three core objectives:
1. Building investable innovations
   Back high‑potential solutions with risk‑tolerant capital and active portfolio support to help them become viable, scalable and attractive to mainstream investors.
2. Creating pathways to scale
   Design and operate investment approaches and vehicles that connect proven innovations to larger pools of public and private finance, enabling sustained growth and expansion.
3. Generating and applying evidence
   Produce and share robust evidence from the portfolio to inform investment decisions, improve delivery models, and influence policy and market practice.

FCDO has supported and helped design the Global Innovation Fund since its inception in 2014. The current business case, running to March 2027, positions GIF as an evidence‑led vehicle that delivers strong value for money by blending public and private finance through its Growth fund to address market failures and support innovations to scale, occupying a distinct position between upstream innovation funding and later‑stage development finance. The programme focuses on underserved and vulnerable populations, particularly women and girls, aligning closely with FCDO’s objectives on inclusive and sustainable economic development, with continued effort required to strengthen performance on gender outcomes, particularly women’s leadership. To date, FCDO has invested £73m in GIF. This longstanding UK support has played a catalytic role in establishing GIF’s credibility and helping to crowd in £93m in co‑investment from partners including USAID, Sida, DFAT, Global Affairs Canada (GAC), and philanthropic and corporate funders. In 2025/26, GIF secured additional commitments from GAC and Sida totalling £8.3m.

GIF has made 81 investments, with at least 40% progressing to scale[1], the majority in Africa. Capital has been deployed through a strategic mix of instruments designed to ensure the right level of concessional capital to foster innovation, while positioning ventures for follow on investment. Approximately 56% of GIF’s innovation funding is delivered as grants and 44% as risk capital. In recent years, GIF has deliberately increased its use of risk capital and strengthened its focus on climate and gender innovations, which now account for around 45% of the portfolio. This reflects a portfolio‑level shift towards scalable, market‑based models designed to crowd in follow‑on capital and deliver inclusive economic and climate outcomes at scale.
[1] “scale” is defined as directly benefiting at least 300,000 people or indirectly benefiting at least one million people

To address persistent financing gaps between early‑stage innovation and commercial investment, GIF launched GIF Growth in 2024/25 as a dedicated blended finance vehicle. GIF Growth is designed to deploy flexible, risk‑adjusted capital to support companies transitioning from grant‑supported validation to commercially investable scale, with an ambition to raise and deploy $100m.

Summary of performance for the reporting year

Apart from three sub‑indicators, GIF met or exceeded its output, outcome and impact targets for the year, with a number of indicators performing above target.

This year marked a transition point for GIF, with a maturing portfolio, increased use of returnable capital, and the first deployment of dedicated growth‑stage blended finance. Key achievements reflect this shift from broad innovation support towards more targeted scale and capital mobilisation.

- GIF impacted the lives of over 63.5 million people in 2025. This year’s figures are driven by the scale‑up of mature, platform‑based investments such as Viamo, which operate at population level and enable action through access to information or services. As the portfolio matures, more investments also have robust impact models in place, strengthening understanding of the depth of impact delivered. This reflects GIF’s design, which supports innovations from early validation through to scalable delivery.
- GIF‑backed innovations mobilised approximately $80 million in public and private follow‑on finance in 2025, bringing cumulative follow‑on investment across the portfolio to just under $1.49 billion against total commitments of $131 million to date[2]. This capital mobilisation reflects GIF’s strong venture support, delivered through active portfolio management including shared due diligence, ESG and risk oversight, governance engagement and targeted technical assistance, which reduced information and transaction costs for subsequent investors. For example, Mafisa secured a $2.5 million follow‑on grant in 2025, with the follow‑on investor noting in written feedback to FCDO that engagement with GIF was “invaluable” in informing their assessment and investment decision.
  [2] GIF’s follow-on finance methodology is aligned with OECD-DAC blended finance principles
- GIF Growth maintained delivery momentum and advanced fundraising despite significant volatility in the external funding environment. The fund completed its first investment, built a diversified investor pipeline, and secured targeted technical assistance to support gender outcomes. During the year, GIF Growth reconfigured its financing package towards more concessional public capital, including commitments from Global Affairs Canada and Sida, increasing deployment flexibility in higher‑risk, lower‑income contexts in line with FCDO development finance objectives, with FCDO’s early engagement playing a catalytic role in sustaining investor confidence.
- In late 2025, GIF approved a new five‑year organisational strategy, providing a clear framework for its future role in the development and innovation finance landscape. The strategy strengthens alignment with FCDO’s 2030 objectives by sharpening GIF’s focus on underserved and climate‑vulnerable populations, prioritising climate change and inclusive economic opportunities, concentrating resources in a smaller number of countries across Africa and Asia, and adopting a more explicit systems‑level approach to scaling innovation. A central shift towards commercial pathways and market‑based solutions establishes a more unified approach across GIF’s financial instruments and clarifies GIF’s comparative advantage as a provider of catalytic, risk‑tolerant capital alongside active portfolio support.
- GIF made seven new investments applying a systems‑focused approach to climate adaptation and resilience, deploying catalytic capital to address market failures across food, agriculture and natural‑resource systems. Investments targeted high‑leverage system chokepoints rather than stand‑alone technologies: Agros, Mati Carbon and Toothpick address soil health, land‑use incentives and smallholder productivity; Keep it Cool reduces post‑harvest loss through cold‑chain infrastructure; and Green Teams and Blue You focus on strengthening natural and urban systems by enabling locally delivered environmental services and waste and resource management models in underserved settings. By concentrating investments in these system‑critical functions, GIF reduced the risk of fragmented, project‑level interventions and strengthened pathways to scale, aligning with FCDO priorities on climate resilience, food security and locally led development, and demonstrating the effective use of catalytic public capital to unlock durable adaptation outcomes.
- GIF, in partnership with PATH, launched Thrive, a climate–health investment platform addressing scale barriers for early‑ and growth‑stage technologies in low‑ and middle‑income countries. Thrive made its first investment through a $1m risk capital investment in Blackfrog Technologies, demonstrating early execution of the platform’s strategy. The launch of Thrive positions GIF as a credible originator of blended finance platforms aligned with FCDO’s climate, health and systems‑level objectives.
- In 2025, FCDO’s catalytic participation in GIF Growth as an anchor public investor helped GIF Growth to secure a CAD $10m (c.$7m) investment commitment from Global Affairs Canada, alongside the Korean International Cooperation Agency (KOICA) support for targeted technical assistance. Further investors are expected to close in the first half of 2026 subject to market conditions, following which deployment will accelerate across Africa and Asia. GIF Growth made its first investment in 2025, backing Green Teams and has established a credible pipeline of investors expected to close in 2026, subject to market conditions. However, for 2025 this has not yet translated into broader diversification, with GIF missing both fundraising and new donor targets in 2025/26 (US$10.4m vs US$12m; one donor vs three), reinforcing a long‑standing reliance on a small number of anchor funders

Major lessons and recommendations for 2026

	Lessons for the year ahead	Recommendation
1	Attempts to diversify GIF’s funding base were less effective where the underlying proposition lacked sufficient focus, while the clearer, more targeted proposition of GIF Growth enabled stronger fundraising outcomes. This reinforces the need for a more coherent and compelling offer for GIF Core to reduce reliance on its anchor donors.	GIF should consolidate and sharpen its core offering by defining a small number of priority themes and product propositions under the new strategy, drawing directly on the fundraising experience of GIF Growth. This should result in fewer, clearer propositions for GIF Core, with defined target funder segments, articulated additionality, and clearer links between thematic focus, capital instruments and learning outputs. Progress should be evidenced by improved quality of donor engagement and a reduced concentration of reliance on anchor funders over time.
2	As GIF’s portfolio has scaled, reliance on fragmented and manually intensive systems has constrained operational effectiveness, creating reporting delays, limiting portfolio insight, and absorbing disproportionate management time. This experience indicates that further growth without more integrated systems is not sustainable, particularly given growing donor expectations around technology‑enabled efficiency.	GIF should implement an integrated systems upgrade to automate deal management and impact reporting, drawing on appropriate digital and AI‑enabled solutions. This should enable more timely portfolio insight, reduce manual reporting burden, and strengthen compliance readiness as GIF diversifies its donor base. For FCDO, this would improve assurance, transparency and the quality of portfolio‑level oversight as delivery scales.
3	As the global funding environment tightens and grant‑dependent models become less attractive to major donors, the ability to generate credible learning, evidence and ecosystem insight has become a core determinant of funding relevance. This year showed that while GIF’s learning and systems‑level insights are increasingly valued by partners and funders, they are not yet consistently embedded in the operating model. Key learning outputs—including toolkits, articulation of GIF’s scale model and portfolio‑level synthesis—were delivered largely through time‑bound consultancy support, creating a risk that critical learning functions remain episodic, externally driven and insufficiently anchored to core investment decisions, rather than a sustained source of competitive advantage.	GIF should articulate a revised investment strategy that defines a clear grants approach aligned to an indicative 70/15/15 allocation of resources—explicitly embedding learning, evidence and ecosystem insight as a core function for maintaining funding relevance. Approximately 70% would be deployed through direct investments (using grants alongside risk capital to de‑risk innovations for impact, scale and capital mobilisation), 15% through grant support to address system‑level barriers to scale, and 15% through grants dedicated to learning, evidence generation and portfolio‑level insight, consistent with the new corporate strategy.
4	While GIF has strengthened its internal learning, analysis and articulation of its strategic value‑add, this has not yet translated consistently into external influence within the wider ecosystem. Experience this year shows that learning outputs have primarily informed internal strategy, rather than being systematically converted into externally usable evidence, insights and influence with partners, funders and peers.	GIF should establish a structured influencing plan to translate its decade of track‑record data and portfolio learning into externally usable intelligence, embedding learning and toolkits at defined points in the investment cycle. Progress should be evidenced through a small number of clearly defined learning and influencing products produced annually, their systematic use in fundraising and investment decision‑making, and demonstrable uptake by funders and partners, supporting GIF’s positioning as a credible thought partner within the development finance and innovation ecosystem.
5	GIF’s experience shows that its value to donors and the wider impact investing ecosystem increases when it is explicit about its role as a scale enabler within the development capital continuum. Where GIF’s early‑stage investments have contributed to mobilising downstream capital at lower risk and cost, this has provided a clear signal of GIF’s additionality, but this role has not yet been articulated consistently or systematically to external partners.	GIF should more clearly position its portfolio as a feeder into larger pools of development finance by formalising partnerships and co‑investment arrangements with DFIs and other actors across the capital continuum. This should include structured engagement and MoUs that demonstrate GIF’s role in de‑risking high‑impact innovations for subsequent investment, supported by deeper regional partnerships led by its Nairobi and Singapore teams, strengthening GIF’s recognition as a trusted vehicle for preparing innovations for larger‑scale development capital.
6	GIF’s evolution from an open innovation funder towards a more strategic early‑growth stage investor is not fully reflected in the current theory of change and logframe. As a result, parts of GIF’s delivery model, incentives and contributions are misaligned with the results framework, at times under‑representing its role in de‑risking innovations for scale and capital mobilisation.	As part of any future business case or programme refresh, FCDO and GIF should review GIF’s Theory of Change and logframe, ensuring alignment with GIF’s evolved role as a strategic early‑growth stage investor. This should reflect GIF’s current investment approach, including the integration of GIF Growth, recent strategic shifts, and evolving donor requirements, to establish a coherent and proportionate results framework against which performance can be assessed.

GIF Growth’s first investment supports the scaling of air quality monitoring to strengthen climate and public health policy in Indonesia

Indonesia faces a severe environmental health challenge, with fine particle air pollution (PM2.5- harmful microscopic particles which penetrate the lungs) exceeding World Health Organization guidelines by more than seven times, disproportionately affecting low‑income communities and driving significant health and economic costs. While air quality regulations exist, limited access to reliable, real‑time environmental data has constrained effective enforcement, with early‑growth providers struggling to scale monitoring infrastructure.

Green Teams addresses this gap by providing air quality monitoring systems and laboratory services to government and industry, embedding reliable data into environmental policy and compliance processes.
Operating in a policy‑dependent market, the company faces high upfront capital costs and slow procurement cycles. GIF Growth has provided a USD $1 million loan to support expansion of monitoring infrastructure and position the business for larger public and commercial contracts.

The investment is expected to deliver:
• expanded access to reliable air quality data;
• improved regulatory enforcement and environmental management; and
• a scalable model for monitoring and compliance in high‑pollution markets.

2025 investment overview
Capital: USD $1 million loan (GIF Growth)
Focus: Expansion of monitoring infrastructure and services
Market: Government and industrial clients in Indonesia

.

# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
## Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case
GIF’s original Theory of Change focused on two main pathways to impact: scaling innovations through blended support and influencing the wider development ecosystem.
While the current Theory of Change captures core outcomes, it does not fully reflect GIF’s evolution towards a more strategic early‑growth-stage investor. In particular, it under‑represents the role of GIF Growth, the reduced emphasis on open innovation, the intensity of portfolio management, and the effort required to de‑risk investments for scale, impact and capital mobilisation. As a result, the framework no longer fully reflects GIF’s operating model, the changing funding environment, or its potential contribution to addressing system‑level barriers.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact progress (on track)

FCDO assesses that GIF remains on track to deliver its expected social and economic impact. Portfolio performance is strong across all headline indicators, with results meeting expectations and evidence of continued scaling among more mature innovations.

Performance is being driven by established, high‑impact investments, which continue to generate sustained social returns, alongside a growing contribution from newer investments beginning to reach scale. Projections indicate that this trajectory is expected to strengthen further as a larger share of the portfolio matures and transitions into scaled delivery.

Impact:
Impact	Indicator	Milestone	Progress	Supporting Text
1. GIF has a social and economic impact which benefits millions of people	Achieved net present value (net social benefits) created from GIF-supported innovations.	3.1 - 3.5bn	Met expectation: 3.35 bn	Social Rate of Return (SROR) has been maintained at $3.35bn, reflecting GIF’s conservative valuation approach: returns from mature, high‑impact investments have been sustained, while additional portfolio growth has not yet been monetised until impacts are fully realised and evidenced.
	Cumulative Achieved Person Years Income	10m – 16m	Met expectation: 14.5m	At portfolio level, GIF has achieved an estimated 14.4 million cumulative Person Years of Income (PYI), within the expected range. This reflects income gains generated by a subset of more mature innovations that have sustained delivery at scale, combined with incremental contributions from a growing number of newer investments. PYI estimates are updated annually using investee reporting and established proxies
	Projected risk-adjusted PYI/year at 10 year horizon)	6m – 10m	Met expectation: 8.2m	The projected 8.2 million PYI per year at the Year‑10 horizon is a risk‑adjusted estimate of annual impact once GIF‑supported innovations are expected to have reached scale. It is calculated using Practical Impact methodology, which combines projected reach at Year 10, income‑equivalent depth of impact (PYI), and a probability‑of‑success adjustment reflecting delivery and scale risks. The higher projected annual PYI reflects portfolio maturation and a greater share of investments expected to be operating at scale by Year 10, rather than any change in underlying assumptions or methodology.

Outcomes (largely on track): FCDO assesses that GIF is largely on track to deliver its expected outcomes on innovation scaling, evidence‑informed decision-making, and portfolio value growth. At least 40% of investments have demonstrated demand for scale, based on the most comprehensive track‑record assessment undertaken to date, and cumulative additional finance mobilised has reached $1.48bn, including $83m secured in 2025, primarily from private-sector sources. Evidence continues to inform scaling decisions, with 15 of 26 investments actively using rigorous research, alongside 25 innovations currently undertaking new evaluations. The risk-capital portfolio increased in value by US$4.3m, with $9.8m returned since inception. Performance against funder diversification targets was below expectations, with GIF missing both targets during the period. While the challenging funding environment and the timing of renewals (with several agreements concluding soon after period end) provide some context, FCDO expects GIF to prioritise accelerating conversion of recent commitments, broadening its donor base, and strengthening links between scaling performance, evidence, and downstream capital mobilisation in the year ahead.

Outcomes
Outcome	Indicator	Milestone	Progress	Supporting Text
1. Innovations are on a path to scale	Cumulative additional finance (raised subsequently), attracted to innovations ($)	1.4B - 1.6B	Met: 1.49bn	The cumulative mobilisation of additional finance reflects increasing portfolio maturity, with more innovations demonstrating the commercial or policy traction required to attract subsequent investment. This supports the assessment that GIF‑backed innovations are on a credible pathway to scale rather than remaining dependent on grant or early catalytic finance.
	For Test & Transition and scale investments at 5+ years since GIF investment, cumulative proportion that have demonstrated demand for scale[3].	30%	Exceeded: / 40%	Portfolio analysis undertaken this year indicates that 40% of Test & Transition and scale investments, five or more years after initial GIF support, have demonstrated demand for scale. This assessment draws on a revised and more consistent scaling rubric applied across the portfolio.
2. Learning and evidence generated by GIF is being shared and is influential	Cumulative proportion of innovations in GIF portfolio conducting rigorous research	30%	Met: 32%	By end‑2025, 26 of 81 GIF‑supported innovations (32%) had conducted rigorous research, meeting the target. This reflects GIF’s continued emphasis on embedding robust evaluation—such as RCT‑quality designs—within innovation pathways to test effectiveness, reduce uncertainty, and strengthen the evidence base available to inform future scaling and investment decisions.
	Cumulative proportion of innovators using rigorous evidence to drive scaling decisions	50%	Exceeded: 58%	Of the innovations generating rigorous evidence, 15 of 26 (58%) are actively using findings to inform scaling decisions, exceeding expectations. Where evidence is not yet being used to scale, this typically reflects evaluations still underway, or cases where findings have been used to pause, adapt or pivot delivery models rather than scale prematurely—consistent with GIF’s evidence‑led, adaptive approach to innovation.
3. GIF’s returnable capital investments are sustainable	Change in value of GIF’s risk capital	Tracked	Capital value is tracked annually.	In 2025, the gross value of GIF’s risk‑capital portfolio increased by US$4.3m year ‑on ‑year (pre-‑impairment), compared with an increase of US$2.2m in 2024. Net portfolio value remains subject to impairment review. Since inception, GIF has returned approximately US$9.8m through exits, loan repayments and interest. The indicator is tracked rather than targeted to reflect the inherently uncertain and exit‑dependent valuation of early‑stage impact investments, and to avoid incentivising financial performance at the expense of impact.
4. GIF’s model for funding and scaling innovation is credible and influential	Additional $ pledged to GIF during reporting years (Core and Growth)[4]	$12m	Below expectation: $10.4 m	Performance was below expectations at the reporting cut‑off, with US$10.4m secured against a US$12m target. While GIF Growth benefited from a clear, thematic and product‑focused offer, the core proposition has not yet been repositioned with the same specificity. Funding secured comprised US$3m from Sida and a signed US$7.4m agreement with Global Affairs Canada, reinforcing the case for applying the successful Growth fundraising model more consistently to GIF Core.
	Annual increment in # of new donors to GIF (Core and Growth).	3	Below expectation: 1	In 2025/26 GIF secured Global Affairs Canada as an investor into the Growth fund.
[3] When an innovation reaches the five year mark the deal lead reviews that deal against the following criteria: *for RC - market demand seen as growth of sales *for Grants - adoption through replication or public sector scale up *for both Grants and RC tangible scale 5 years post GIF *impact thesis still benefits GIF target population Deals that meet all three criteria are included in the scoring as ‘demonstrated demand for scale’.
[4] Pledge = commitment to contribute funds, not a signed contract

TURNING CLIMATE DATA INTO CLIMATE ACTION: SYSTEMS AND SCALE POTENTIAL OF KOMUNIDAD / Local governments in the Philippines face frequent climate hazards, but the constraint is often not the availability of forecasts—it is the ability to translate climate data into timely, local action. Risk information is frequently delayed, insufficiently localised, or weakly embedded in municipal decision‑making, limiting last‑mile preparedness. Komunidad addresses this gap through a digital climate‑risk intelligence platform that embeds high‑resolution data directly into local government workflows, including Pre‑Disaster Risk Assessments (PDRA) and public advisories. By operationalising climate data within institutional systems—rather than relying on ad‑hoc interpretation—the platform enables consistent, repeatable decision‑making that can scale across municipalities and persist beyond individual staff. / Operating through a B2G/B2B subscription model, Komunidad responds to clear operational demand but faces structural constraints typical of policy‑dependent markets, including slow procurement cycles and early revenue volatility. GIF Growth has supported Komunidad with a $500,000 credit facility, providing patient early‑growth capital to de‑risk expansion and demonstrate a scalable model for digital climate‑resilience infrastructure. / The investment delivers a triple dividend: / reduced service disruptions, emergency response costs and asset losses for public institutions; / improved preparedness and early action for climate‑vulnerable communities; and / strengthened institutional use of climate information through a scalable digital resilience model. / 2025 impact metrics / Capital: $500,000 GIF credit facility / Growth: 52% projected Compound Annual Growth Rate (2023–2026) / Reach: Over 2 million residents across major urban centres / Engagement: 181,000+ unique web‑app visits; 248 municipal users (50% women) / Confidence: 94% of disaster‑response staff report improved decision‑making confidence versus national forecasts / Sectoral integration: High‑resolution climate monitoring embedded in PhilRice’s 2026 wet‑season planning / Portfolio Insight / Within the same FCDO innovation portfolio, GSMA and the Global Innovation Fund supported Komunidad across the capital continuum: GSMA provided time‑bound grant funding to prove and deploy the early warning system through implementation support, training and partnership brokering, while GIF subsequently supplied repayable finance to strengthen liquidity and enable operational scale and continuity in government‑facing markets, including via working‑capital advances against public‑sector invoices.

## Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The Global Innovation Fund (GIF) should continue, as it has consistently demonstrated strong performance and value for money while filling a distinct gap in the FCDO portfolio. GIF addresses a clear market failure by supporting high‑potential innovations that are too risky for conventional finance, coupling this with robust evidence generation and a proven ability to catalyse follow‑on investment. Its strong alignment with FCDO priorities on climate, gender and private‑capital mobilisation, and the introduction of GIF Growth to extend support into mid‑stage scale position GIF within FCDO’s broader shift from grant-based funding towards an investment-led approach, using risk capital to support scaling and mobilise additional finance. In a constrained fiscal environment, GIF’s blended‑finance model amplifies UK ODA by crowding in external capital, complements upstream innovation programmes without duplication, and directly supports Ministerial priorities on modernising the UK’s development offer through partnership with the private sector, which provides a strong case for continuation.
# C: DETAILED SCORING OUTPUT

Output Title	GIF makes diverse innovation investments at an appropriate pace
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Cumulative number of innovations ever supported	80	Exceeded expectations. 81 .
1.2: New transactions this year	7-8	Exceeded expectations: 9 deals: 7 new deals and 2 follow-on investments.
1.3: Proportion of innovations in past year where investee’s primary headquarters is in a developing country	33%	Exceeded expectations: 78%. 7 out of 9 investments have the investee’s primary headquarters in a developing country.
1.4: Proportion of new innovations led by women or in senior decision-making roles.	50%	Below expectations: 43%. 43% (3 out of 7) were either led by women or had women in senior decision-making roles.

Briefly describe the output’s activities and provide supporting narrative for the score

Output 1 is scored A+, reflecting strong overall performance against the majority of indicators. GIF exceeded expectations on investment volume and pace (new and follow‑on deals), significantly surpassed the target for investees headquartered in developing countries—continuing a clear shift toward locally led innovation—and further increased reach into fragile contexts, with 61% of investments in fragile states, up from 50% last year. Taken together, these results demonstrate delivery beyond expectations on scale, localisation and portfolio reach.
However, GIF did not meet the target for the proportion of new innovations led by women or with women in senior decision‑making roles, although the shortfall was relatively narrow. This indicator is of high importance to FCDO as a core inclusive‑growth and value‑for‑money measure and should therefore be clearly acknowledged as an area requiring continued management attention. Performance reflects the challenges of operating in high‑risk, early‑stage markets—particularly in climate and deep‑tech sectors—where female leadership pipelines remain constrained, rather than a lack of intent. Nonetheless, strengthening origination, screening and selection approaches to improve performance on women’s leadership over time remains a priority, and progress against this indicator will continue to be closely monitored.
Name of Innovation	Sector	Headquarters in developing country	Women-led or senior roles
Agros	Agriculture	No	50%
Blackfrog	Public Health	Yes	0%
Blue You	Climate	No	0%
Green Teams	Climate	Yes	0%
Keep it Cool	Food chain	Yes	50%
Mati Carbon	Climate/Agriculture	Yes	0%
Toothpick	Climate/Agriculture	Yes	75%

A MARKET TRANSFORMING INNOVATION: BOOMITRA / Carbon finance can incentivise regenerative agriculture, but for smallholder farms and heterogeneous rangelands the cost of measuring soil carbon has historically outweighed the value of the carbon itself, making projects commercially unviable. / Boomitra addresses this constraint through an AI‑enabled platform combining selective soil sampling with satellite remote sensing, dramatically reducing measurement costs and unlocking investable soil‑ and grassland‑carbon markets. / Operating in an emerging and fragmented market, the business faced early commercial barriers, including high verification costs and uncertain demand for carbon credits. In 2024, GIF provided USD $500,000 in risk capital at a pivotal pre‑commercial stage, extending runway as the company transitioned from validation to first issuance. / Results followed rapidly. In April 2025, Boomitra issued its first soil‑carbon credits in India, working with over 6,000 smallholder farmers across c.25,000 acres. It subsequently signed a five‑year agreement to supply 625,000 Article 6 credits to Singapore, while its Northern Mexico Grassland Project became the world’s largest Verra‑verified soil‑carbon initiative, issuing 3.03 million credits across 4 million acres. / The investment demonstrates: / the viability of low‑cost, technology‑enabled soil carbon measurement at scale; / the creation of new carbon market opportunities for smallholder farmers; and / the potential to channel climate finance into land restoration and rural livelihoods. / 2025 investment and impact snapshot / Capital: USD $500,000 risk capital (GIF Core) / Stage: Pre‑commercial to first issuance / Scale: 6,000+ farmers; 25,000 acres (India); 4 million acres (Mexico) / Market: Voluntary and Article 6 carbon markets / Milestone: First issuance of soil‑carbon credits and large‑scale verified projects

## Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation (2025)	Progress
GIF to build learning objectives into its investments with a view to understanding alternative scale pathways for climate adaptation innovations	Partially Met: GIF has made early progress in embedding learning objectives into its investment approach. In 2025, all new investments included learning sections, and draft learning KPIs have been developed. In early 2026, GIF presented a new climate approach paper to its Development Policy Subcommittee, including proposals to focus more explicitly on climate scaling pathways and allocate dedicated resources. However, learning KPIs remain in draft form and evidence of systematic use to inform investment or scaling decisions is still emerging. As such, the recommendation has not yet been fully met.
GIF will raise the profile of the value of its offering and additionality through its communication products for knowledge sharing, fundraising and investment sourcing.	Achieved and on-going: GIF has strengthened the visibility of its value proposition and additionality through a more proactive communications and engagement approach. This included improvements to its website, new fundraising collateral, and delivery of an Asia-‑focused climate adaptation webinar targeting potential donors. GIF also increased its profile through scaling workshops and moderated panel discussions, contributing to increased website traffic, growth in LinkedIn followers, higher subscriptions to its newsletter (The Innovator), and more frequent speaking invitations. These activities demonstrate that the recommendation has been met and remains an ongoing area of delivery.

Lessons Learned and 2026 Recommendations

Clarifying the climate investment approach
Lesson: GIF’s emerging climate strategy highlights the need to make clearer, more deliberate choices about how funding is allocated between direct innovation investments and systems‑level interventions. It also reinforces the value of prioritising front‑runner innovations that are actively reducing reliance on grant funding and moving toward sustainable, market‑based models.
Recommendation: Implement the new climate allocation framework explicitly across the portfolio, with clear criteria to balance direct and systems‑focused investments, and prioritise support for scalable front‑runners demonstrating pathways to financial sustainability.

Strengthening how climate impact is measured
Lesson: A narrow focus on beneficiaries reached risks understating the value of climate investments where impact is driven by avoided losses, resilience gains, or timeliness of support. For example, insurance or anticipatory finance may deliver limited income effects but provide critical protection at moments of shock.
Recommendation: Expand climate impact measurement to a triple‑dividend framework, as outlined in GIF’s refreshed approach to climate.

Improving performance on women’s leadership and decision‑making
Lesson: While GIF’s climate investments increasingly reach high‑impact and frontier markets, progress on the proportion of innovations led by women or with women in senior decision‑making roles has been uneven—particularly in climate‑focused sectors. This reflects structural pipeline constraints but remains a core inclusive‑growth priority for FCDO.
Recommendation: Strengthen origination, screening and selection processes to improve performance on women’s leadership, including more proactive sourcing of women‑led innovations, clearer incentives at investment decision points, and closer monitoring of progress over time.

Output Title	GIF generates and disseminates high-quality evidence
Output number:		2	Output Score:	A +
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1: Cumulative number of peer-reviewed papers or studies publicly disseminated	28-30	Exceeded expectations: 38
2.2: Proportion of innovations with basic data on IATI	100%	Met expectations: 100%
2.3: Growth rate in followers across GIF's digital communication channels (LinkedIn and email) (New indicator for 2025	20% / (Baseline data 1 Jan 2025 total: 32685 / GIF email newsletter subscribers: 9805 / LinkedIn: 22880)	Exceeded Expectations: 30% / (Growth of 40.7% for GIF newsletter subscribers and 25% growth in LinkedIn followers

## Briefly describe the output’s activities and provide supporting narrative for the score
GIF exceeded expectations on this output, demonstrating not only strong evidence production but increasing movement towards practical influence on decision‑making.

Cumulatively, 38 peer‑reviewed papers or studies have been publicly disseminated, well above the target range, reflecting sustained investment in rigorous evaluation and learning across the portfolio. In 2025 alone, GIF and its investees published 26 reports, including peer‑reviewed studies and working papers that directly informed investment, scaling and partnership decisions.
Beyond volume, there is growing evidence that learning is being used to shape behaviour. Portfolio‑level scaling analysis and additionality frameworks have been applied to investment decision‑making and fundraising discussions, while investee‑level evidence has informed decisions to scale, adapt or pause delivery. Although the translation of evidence into external influence remains uneven, the foundations for more systematic uptake by funders and partners are now in place, justifying the A+ score while reinforcing the need for further consolidation
## Describe any changes to this output during the past year, and any planned changes as a result of this review.
## 2.3 - These metrics are treated as indicators of reach rather than influence, with future reviews expected to place greater emphasis on how digital engagement translates into use of evidence in funding, policy or investment contexts.
## Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation (2024)	Progress
GIF should expand its evidence generation toolkit by incorporating a variety of high-quality methodologies, such as lean data and quasi-experimental designs. This diversification will enhance the robustness of findings and provide a more comprehensive understanding of the impacts of its investments.	Partially Met: GIF has taken initial steps to broaden its approach to evidence generation. During the period, GIF amended its internal rubric on what constitutes good evidence and developed a draft framework to guide evidence use, which has been applied in its recent scaling analysis. GIF also reports increased use of quasi-experimental approaches across its portfolio. However, new methodologies are not yet fully integrated, and changes remain at a developmental stage rather than systematically embedded in investment or reporting processes. As such, progress is evident, but the recommendation has not yet been fully met.
Review and update GIF’s learning strategy, to incorporate macro-level research and insights; examining trends, patterns and interactions aggregated at portfolio-level, develop learning themes which GIF linked to new learning products and embed learning objectives within its investments.	Partially Met: GIF has made partial progress in strengthening its learning approach. Draft toolkits on scaling and additionality have been developed, and a scaling workshop was convened in March 2026 with FCDO participation. GIF has also begun embedding learning objectives into selected new investment agreements. However, a revised, consolidated learning strategy incorporating portfolio‑level analysis, defined learning themes, and clear links to learning products has not yet been finalised. Further work is required for full delivery of this recommendation.

Lessons Learned and 2026 Recommendations
Strategy clarity has outpaced external communication.
Lesson: GIF’s new strategy has clarified its competitive strengths, ecosystem role and strategic shifts, but these are not yet consistently reflected across the website, communications products and learning outputs, contributing to a perception gap and under‑utilisation of GIF’s evidence and track record.
Recommendation: Develop and embed a unified messaging framework aligned to the new strategy across communications channels, ensuring a consistent, authoritative external narrative that reinforces GIF’s distinctive value and evolving mission.

Learning activity is strong, but influence is insufficiently structured.
Lesson: While GIF has invested significantly in learning (including toolkits, track‑record papers and portfolio evidence), the current learning strategy is too narrowly focused on investment‑level learning and lacks a clear pathway from evidence to influence, limiting its impact at ecosystem level.
Recommendation: With the unified messaging framework (see previous recommendation), establish a clear influencing plan for GIF, setting out the changes it seeks to drive, and the target stakeholder groups it seeks to influence. This will be supported by targeted insights, blogs, synthesis products and presence at critical convenings.

Learning and impact are not yet tracked or communicated at portfolio level.
Lesson: GIF generates rich evidence across investments, but this is not yet consistently aggregated, tracked or communicated in a way that demonstrates portfolio‑level learning, influence and impact.
Recommendation: Integrate learning into the investment cycle and reporting and develop a concise portfolio‑level dashboard covering impact, evidence and learning to strengthen accountability, donor confidence and external engagement.

Output Title	GIF accounts for gender, the poorest and most marginalised in its strategy and investments
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
3.1: Proportion of people reached living on less than: / $8.30 PPP/day / $4.2 PPP/ day / $3.0 PPP/ day / Only for GIF core, not GIF Growth. Previously this was a tracked indicator. Separately, the thresholds have been increased this year, bringing them in-line with World Bank thresholds	Maintain proportions with previous years. / Higher tier: 84% / Middle tier: 54% / Lower tier: 28%	Exceeded expectations: / 93% under $8.30 PPP/day / 68% under $4.20 PPP/day / 48% under $3.0 PPP/ day / 30.2m people reached under $3 PPP/day.
3.2: Proportion of live portfolio innovations compliant with gender disaggregated reporting	75%	Exceeded expectations: 86%
3.3 Number of people supported by GIF innovations to better adapt to the effects of climate	10% increase on previous year (21.8m)	Exceeded expectations: 32.7m
3.4 The number of clients that are considered 2X Eligible Enterprises (specifically for RC Deals)	60%	Did not meet expectations. 50% (2 out of 4 deals, only risk capital deals are eligible.)

## Briefly describe the output’s activities and provide supporting narrative for the score
## Output 3 meets expectations, with strong performance on poverty and climate reach despite some mixed indicators. Delivery is supported by clear evidence of reach to women, poorer populations, and climate‑vulnerable groups.
## GIF applies a consistent portfolio‑wide approach to gender, poverty and climate inclusion, supported by systematic screening, use of gender and climate markers, and expanding sex‑ and poverty‑disaggregated reporting. Strong performance on poverty and climate reach reflects the scale‑up of large, digital and infrastructure‑based climate solutions, particularly in lower‑income Asian markets, which have enabled GIF to reach poorer and more climate‑vulnerable populations at scale.
## However, performance on women’s leadership and 2X eligibility[5] has been more mixed, reflecting structural constraints in climate‑focused and early‑stage markets, and GIF’s limited ability to influence senior leadership composition as a minority investor in returnable capital deals. Taken together, this supports an overall score of A: delivery is strong against poverty and climate objectives, while gender‑related indicators remain an area requiring continued, targeted effort rather than being treated as settled.
[5] “2X eligibility criteria” refers to the global standard for gender-lens investing, requiring investments to meet minimum ESG standards and demonstrate measurable contributions to women’s economic participation (e.g. leadership, employment, or access to finance)
KEEP IT COOL: DELIVERING CLIMATE TRIPLE DIVIDEND IMPACT / GIF has invested $500,000 in Keep It Cool (KIC), a Kenyan‑led pioneer in sustainable cold chains, to support the scale‑up of its network and reduce post‑harvest losses. KIC combines solar‑powered cooling hubs, a fleet of electric motorcycles and hybrid trucks, and a digital logistics platform to radically reduce the cost and emissions intensity of cold‑chain infrastructure. This model attracts commercial investment, supports adoption of improved harvesting practices, and provides a reliable revenue pathway for producers. This builds on earlier grant funding from the Ayrton Fund, illustrating GIF’s additionality in providing follow‑on risk capital to support scale in markets where concessional funding alone is insufficient. / Operating across aquaculture, wild‑catch and poultry value chains, KIC demonstrated significant scale in 2025—handling 477.9 million tonnes of produce while keeping post‑harvest losses below 2%, compared with a regional benchmark exceeding 50%. KIC’s network now serves 5,642 active retailers, 45% of whom are women‑owned businesses, providing consistent access to high‑quality, temperature‑controlled protein. / 2025 climate triple‑dividend outcomes / Mitigation: Solar‑powered operations avoided 65.5 MT of CO₂ in 2025. By preventing 166.3 MT of fish and poultry from spoiling, KIC also avoided substantial methane emissions associated with food waste. / Adaptation and resilience: By dramatically reducing spoilage, KIC ensures that the same volume of catch feeds more people, delivering 1,194,857 nutritious protein portions to underserved communities and increasing food access for 88,784 people in low‑income areas. This also reduces economic pressure to over‑fish and strengthens resilience to climate and price shocks. / Social and economic inclusion: KIC’s model is intentionally designed to support women across the supply chain. Solar‑powered freezers convert daily spoilage into stable micro‑enterprise income, while the company’s solar ice plants sell ice at 30–40% below market rates, increasing resilience for women traders across the wider region.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on recommendations
Recommendation (2024)	Progress
GIF should actively seek out and source new climate and/or gender focused innovations that prioritise both gender equality and climate outcomes. / GIF will generate a lessons learned and knowledge paper on gender outcomes through climate adaptation investments.	In progress: GIF has made credible progress in strengthening its pipeline of climate‑focused investments, with climate remaining a central organisational priority. In 2025, six of seven new deals entering the portfolio were climate‑focused, demonstrating continued emphasis on climate adaptation and resilience. All new investments were assessed using GIF’s gender marker and passed through both the climate and gender working groups, ensuring systematic consideration of these dimensions at design stage. Performance on gender integration remains robust at a minimum standard, with all new deals assessed as at least gender neutral. This reflects effective institutionalisation of gender screening processes across the investment cycle. However, while screening and assessment processes are strong, evidence of proactive sourcing of innovations explicitly designed to deliver combined gender‑transformative and climate outcomes remains more limited. / In parallel, GIF has initiated work to synthesise lessons on gender outcomes within climate adaptation investments. Progress has been made towards developing an external product, with a blog currently in draft. Delivery has been slower than anticipated due to competing priorities. As a result, the intended lessons‑learned product has not yet been completed in full.

Lessons learned

Progress against the 2X investment target has been constrained by a limited pipeline of qualifying deals, reflecting structural market scarcity rather than weaknesses in programme delivery. Without proactive pipeline development, there remains a material risk of underperformance against the target.

Recommendations

GIF should focus on improving gender performance across its portfolio over time by combining selective upstream origination with stronger, instrument‑appropriate levers at investee level. This should include targeted technical assistance, governance engagement, and support for investees to strengthen gender practices and progress towards 2X qualification where feasible, while maintaining realism about pipeline constraints in early‑stage and climate‑focused markets.

Output Title	GIF provides a satisfactory service and attracts diverse applicants/investees
Output number:		4	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1: Proportion of applications with GIF response within 60 days of the application window closing (new language)	60%	Exceeded expectations 73% (1,816 out of 2,493 reviewed and replied to within 60 days)
4.2: Investees’ Net Promoter Score on question: “How likely are you to recommend that a fellow innovator apply to GIF for funding?”	0% (-100% to 100% range)	Exceeded expectations 75%

## Briefly describe the output’s activities and provide supporting narrative for the score
Output 4 has exceeded expectations, demonstrating that GIF continues to provide a responsive service and attract a diverse applicant and investee base, despite rising application volumes and changes to its operating model.
In 2025, GIF closed a time‑limited open application window focused on climate innovations and moved away from a permanently open window. Despite a higher volume of applications requiring assessment, GIF responded to 73% of applications within 60 days. While this represents a decline from exceptionally high performance in 2023–24, it remains a strong result given the scale of applications handled and the more intensive review process adopted. 87% of applicants to the window were headquartered in developing countries, supporting inclusivity objectives.
DERISKING A NON PROFIT BEYOND GRANT DEPENDENCE - SIMPRINTS
 For people without formal identification, biometric systems can be critical to accessing essential services such as vaccinations and healthcare—meaning the four million people reached by Simprints include individuals who may otherwise have been excluded from life‑saving interventions.
GIF supported UK‑based Simprints, headquartered in Cambridge, through staged financing that enabled the organisation to move from product development to scale. GIF initially provided a US$200,000 grant to support the development and deployment of Simprints’ open‑source mobile biometric hardware and software, funding the establishment of a sustainable delivery model in Bangladesh and Nepal for GIF’s target beneficiaries. As Simprints scaled, GIF provided follow‑on risk capital in the form of a £2.1 million revolving credit facility, helping ensure the organisation could continue servicing contracts and managing cash flow during growth.
By 2022, this support had enabled Simprints to reach over two million people across programmes including neglected tropical disease treatment in Ethiopia, HIV patient tracking in Zimbabwe, maternal and child health services in Bangladesh, and immunisation delivery with Gavi. By 2025, Simprints had reached over four million people globally, launched a randomised controlled trial in Ghana to assess the impact of biometrics on child immunisation coverage, and its Operation Sight programme in Ethiopia was recognised as SDG Programme of the Year at the Development 2030 Awards. Simprints also formed a strategic alliance with Gavi, CIFF and ARM to deploy AI‑enabled biometric solutions from birth to help ensure children are counted in immunisation systems.
The organisation’s leadership has received international recognition, with CEO Dr Toby Norman named a 2025 UK Goalkeeper by the Bill & Melinda Gates Foundation, and Chief Scientific Officer Dr Alexandra Grigore awarded the 2025 Gates Cambridge Impact Prize for her contributions to digital identity.

Year	Number of Applications	Response within 60 days
2025	2493	73%
2024	4990	88%
2023	5525	93%
2022	2500	76%
2021	2266	2%
2020	3624	65%
2019	2263	60%

Investees report very high levels of satisfaction, with a Net Promoter Score of 75%. All respondents indicated that GIF met their expectations in 2025, and the majority reported being satisfied or very satisfied with the support received. Number of applications received vs response from GIF within 60 Days (2019 – 2025).

## Describe any changes to this output during the past year, and any planned changes as a result of this review
## Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on recommendations

Recommendation (2024)	Progress
GIF should conduct a review to explore how AI and other technology can enhance their internal systems and processes. This initiative is vital for improving team productivity and streamlining operations, ultimately leading to a more efficient and effective support system for their investees. By identifying and implementing innovative technological solutions, GIF can optimise workflows, reduce administrative burdens, and enhance the overall quality of their offerings, thereby driving greater impact and success for both the organisation and its partners.	In 2025, GIF updated its AI policy and delivered an internal workshop to support consistent and responsible use of AI across the organisation. An internal AI working group has been established, and AI tools are being used for basic operational functions, such as meeting note‑taking. / GIF has also begun piloting the use of AI to support aspects of impact and financial due diligence, including automation within the Practical Impact forecasting model and elements of financial analysis, with the aim of reducing staff time spent on repetitive tasks. In parallel, GIF conducted an internal systems audit and has since allocated a dedicated budget for AI and systems improvements.

Lessons Learned

GIF has sustained high levels of responsiveness and investee satisfaction despite increased application volumes and changes to its operating model, demonstrating strong operational resilience. However, existing indicators primarily capture speed and satisfaction, and are becoming less well aligned to measuring predictability, transparency, and quality of applicant engagement as the model evolves.

Recommendations

# D: VALUE FOR MONEY
## VfM performance compared to the original VfM proposition in the business case
## Overall, GIF continues to represent good value for money for FCDO across economy, efficiency, effectiveness and equity. Costs remain controlled relative to the complexity and risk profile of GIF’s blended‑finance model. Efficiency is improving as application processes, systems and portfolio management mature. Effectiveness is evidenced by sustained scale outcomes and catalytic capital mobilisation rather than delivery alone. Equity objectives are consistently addressed through strong poverty reach, climate resilience outcomes and systematic gender screening. Taken together, these factors support the conclusion that the VfM proposition set out in the Business Case remains valid.
## GIF provides strong value for money particularly because of its equity focus and evidence of its effectiveness.
## GIF continues to demonstrate a strong people‑centred approach to impact, with investment design and scale definitions linked to improvements in wellbeing and underpinned by active impact management. Its sustained focus on women and girls—through gender screening, 2X reporting and targeted technical assistance—remains a core strength of the portfolio.
## GIF’s use of patient capital supports clear attribution between its funding and the additional capital mobilised through active portfolio management, with cumulative mobilisation now approaching $1.5bn against $130m of commitments. Overall, the value‑for‑money case set out in the Business Case remains valid, with evidence that the partnership continues to deliver strong returns relative to resources deployed.
	VfM supporting narrative
Economy	GIF has demonstrated active cost discipline over time, adjusting its operating model and staffing mix in response to funding conditions while maintaining delivery capability, rather than allowing fixed overheads to drift upwards as the portfolio expanded. / Financial governance and assurance: GIF demonstrates strong financial governance and cost control. Independent FCDO due diligence (2025) and a Sida‑commissioned EY audit both found GIF to be well‑structured, effectively managed, and free of material weaknesses in financial management, safeguarding, or fiduciary controls. Budgeting and cost‑forecasting have also been strengthened, improving identification and tracking of key cost drivers. / GIF demonstrates strong financial governance and cost control. Independent FCDO due diligence (2025) and a Sida‑commissioned EY audit both found GIF to be well‑structured, effectively managed, and free of material weaknesses in financial management, safeguarding, or fiduciary controls. Budgeting and cost‑forecasting have also been strengthened, improving identification and tracking of key cost drivers. / Staffing and operating model: GIF manages costs through a flexible staffing model, including short‑term and time‑limited contracts, avoiding growth in fixed overheads. Improved cost attribution—separating direct investment, indirect support, and portfolio management costs—has strengthened oversight of resource allocation. GIF operates with 27 staff, including a seven‑person investment team, supported by a targeted international footprint in Kenya (5), the United States (2), and Singapore (2), aligned to portfolio activity. / Procurement and use of resources: Procurement and operating costs are proportionate to GIF’s investment model, with improved understanding of cost drivers supporting stronger cost control and value‑for‑money decisions. For example, under the new strategy, three suppliers were reviewed for alignment, suitability and cost‑effectiveness, with approval and contracting completed in line with procurement policy—ensuring competitive terms while maintaining delivery quality.
Efficiency	Pipeline and application management: GIF demonstrates efficiency in pipeline management despite high and fluctuating application volumes. In 2025, GIF processed over 2,400 applications and responded to 73% within 60 days under a more selective, time limited application window model—exceeding the agreed performance threshold. This reflects the organisation’s ability to adapt processes while maintaining service standards. / Service quality and investee experience: Efficiency gains have not come at the expense of service quality. In 2025, GIF recorded a Net Promoter Score of 75%, indicating high levels of investee satisfaction with the support received. / Systems and Process Improvement: GIF has undertaken a systems audit and is piloting the use of automation and AI to reduce staff time spent on routine tasks such as due diligence, analysis, and administrative processes. These initiatives are intended to improve internal efficiency as the portfolio scales.
Effectiveness	GIF’s effectiveness is best understood in catalytic terms: its contribution lies in derisking, evidence generation and investability at transition points, rather than sole attribution for downstream outcomes or capital mobilisation. / Catalytic impact and leverage: GIF plays a recognised catalytic role in the innovation and development finance ecosystem, supporting high risk early stage innovations to progress towards scale and enabling access to follow-on finance. In 2025, this included mobilisation of $83m of follow on investment, from majority private sector sources. This catalytic function is central to GIF’s value proposition and differentiates it from delivery only programmes. / Learning and Influence: This year saw credible steps forward in how GIF’s impact frameworks and evidence approaches have influenced other funders and practitioners, supporting broader system learning beyond GIF’s own portfolio.
Equity	Equity performance reflects deliberate prioritisation of scale and reach to poor and climate‑vulnerable populations, with ongoing effort required to deepen gender‑transformative outcomes in more constrained early‑stage and climate‑focused markets. / Gender and climate integration: Gender and climate considerations are systematically embedded across GIF’s investment lifecycle, supported by dedicated working groups and screening tools. All investments are assessed at pipeline stage, ensuring equity considerations inform decision making from the outset. / Poverty targeting and reach: GIF increasingly disaggregates impact data by poverty status, with evidence that a significant proportion of beneficiaries live below international poverty thresholds aligned with World Bank standards. In 2025, 87% of applicants were headquartered in developing countries, supporting accessibility to LMIC based innovators. / Disability and Inclusion: Disability and inclusion considerations are incorporated within GIF’s ESG and safeguarding frameworks.

# E: RISK
## Overview of risk management
The overall risk rating for GIF is major. In 2014, the programme was rated medium to high. Following a change in the risk rating categories in 2016, GIF was rated as major and that rating has remained unchanged. Top 3 programme risks currently as follows:

Risks and Description	Probability (H, M, L)	Impact / (H, M, L)	Mitigating Actions
Changes in donor priorities and funding availability may affect the renewal of existing commitments and slow diversification of GIF’s funding base, increasing reliance on a smaller number of core funders	High	High	GIF undertakes scenario planning to assess financial resilience under different funding scenarios. / Cautious approach to signing new downstream contracts, including use of break clauses. / Regular and open communication with the FCDO programme team on funding outlook. / Development and implementation of a revised funding and diversification strategy. / FCDO supports GIF to explore new bilateral, philanthropic, and private funding sources.
Growth Fund fundraising and scale‑up risk – The current global funding environment may slow progress in capitalising the GIF Growth Fund, affecting its ability to scale as planned.	Medium	High	GIF actively monitors market conditions and investor appetite. / Regular progress updates provided to FCDO on Growth Fund fundraising. / Joint FCDO–GIF engagement to leverage bilateral relationships and encourage private and DFI participation. / Staged deployment and flexible timelines to manage market uncertainty.
Delivery capability and organisational capacity risk – As GIF evolves its strategy and scales activity, there is a risk that systems, processes, and management capacity require continued strengthening to ensure they remain aligned with the organisation’s growing scale and complexity.	Medium	Medium	Organisational and portfolio risk registers reviewed regularly by the Audit and Finance Committee. / Findings from FCDO due diligence highlight areas for continued improvement while confirming no material weaknesses. / Systems audit completed and dedicated budget allocated for systems and operational improvements. / Ongoing FCDO oversight through delivery meetings and annual reviews

The programme team continually monitors risk and reviews and assigns mitigating actions for any risk on a quarterly basis. The Programme Team meets at least once a month. Discussions between the FCDO and GIF continue to be open and collaborative, whilst providing a good level of challenge.
# F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
## Summarise the performance of partners and FCDO, notably on commercial and financial issues

Financial Metric	Value	Notes / Coverage
Total approved programme value (lifecycle)	£75,600,000	Approved value across full programme lifetime
Cumulative disbursements to date	£33.6m	Total disbursed since programme inception
Disbursements in reporting year	£2.2m	Total disbursed in the current reporting year
of which: Grants	£ 0	High level grant disbursements only
of which: Returnable Capital	£2.2m	High level RC disbursements only
FCDO share of Opex coverage - reporting year	£2.3m; ~49%
FCDO Share of Opex coverage - to date	£27.1m; ~47%
In year budget variance	[-4 ]%	Variance against approved annual budget
External audit status	Unqualified	Most recent annual audit
Financial oversight arrangements	In place	e.g. Audit & Finance Committee, donor oversight

GIF has an approved programme budget of £75.6M across its lifetime, with £69.9m disbursed as of March 2026.

Financial performance is monitored jointly by FCDO and GIF, with regular forecasting and scenario planning reflecting the volatility of the external funding environment and GIF’s hybrid grant and returnable ‑capital model. In ‑year budget performance during 2025 remained within agreed tolerances, with no material variances requiring re‑profiling.

GIF demonstrates strong financial governance. A refreshed FCDO due diligence review in 2025 and an external audit conducted on behalf of Sida both concluded that GIF is a well-managed and professionally run organisation, with no material weaknesses identified in financial controls or safeguarding. Annual external audits provide continued assurance, and findings are overseen by GIF’s Audit and Finance Committee.

FCDO continues to view its relationship with GIF as transparent and constructive, with timely financial reporting,

In 2025 50% of £4.5m FCDO funding contributed towards ~ 49% of GIF Opex.

GIF’s 2025 operating expenditure was concentrated in core, value-adding functions, with 89% allocated to investment, fundraising, and governance activities, directly supporting delivery and accountability. These functions are predominantly staff-driven: of this core expenditure, personnel costs are the primary component, representing 71% of total operating expenditure and enabling portfolio management, deal sourcing, and governance oversight. The remaining 11% (USD 0.8 million) comprised indirect costs, mainly IT and office expenses, reflecting a lean operating model with limited overheads. Overall, this expenditure profile demonstrates a strong focus on directing resources toward frontline delivery and oversight, supporting value for money.
# G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Summarise monitoring activities throughout the review period
During 2025, monitoring was undertaken through a combination of FCDO oversight and GIF-led portfolio engagement. FCDO participated in Quarterly Board meetings and held structured quarterly review meetings with GIF senior leadership to assess progress against agreed outputs, financial performance, and implementation of recommendations. These engagements provided regular opportunities to challenge performance, review risks, and ensure alignment with strategic objectives.

FCDO also complemented desk-based monitoring with direct engagement. This included in-person visits to GIF investees where feasible, as well as virtual interviews with investees, Board members and other key stakeholders as part of the Annual Review process. These activities provided qualitative insight into delivery, impact pathways, and operational challenges at the portfolio level.

At the portfolio level, GIF undertook targeted field monitoring visits to Keep it Cool and 4G Capital in Kenya. These visits included engagement with senior management and end‑users, providing insights into evolving business models, identification of new impact pathways, and refinement of impact KPIs as the enterprises scale. The visits also supported identification of key operational and digital scaling risks requiring ongoing monitoring.
In December 2024, GIF’s Managing Director of Investments relocated to the Nairobi office, enabling more frequent and direct engagement with the Africa portfolio. This has strengthened day‑to‑day oversight and board‑level engagement, including at Mr Green Africa, where GIF holds a board nominee role.

As part of its toolkit and scaling work, GIF conducted structured interviews with over ten investees, complemented by portfolio handover and review meetings across the investment team. These activities further supported active portfolio management and monitoring throughout the year.
Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond FCDO). If there is an evaluation linked to this programme provide an update on findings (if not covered elsewhere in the AR).
This Annual Review (AR) provides an in-depth assessment of GIF’s progress, impact and strategic direction. It draws on extensive research and analysis, including:
1. Previous Annual Reviews, programme log frames, risk registers, and delivery plans
2. GIF’s 2024 Impact Report, website, and quarterly financial statements
3. Interviews with GIF’s grant and risk capital investment portfolio organisations
4. Consultations with GIF Board members, senior leadership, and FCDO Programme Managers.

The findings, lessons learned and recommendations presented in this review are shaped by this comprehensive evaluation process, offering key insights to inform future investment and policy decisions.
Delivery chain mapping: GIF’s delivery chain is monitored as part of FCDO’s rules on delivering programmes. FCDO receives a comprehensive view of all partners receiving FCDO funding through GIF’s quarterly reports and through access to their investment spreadsheet. An updated delivery chain map, identifying and capturing the names of all GIF investees is recorded on FCDO’s Aid Management Platform and the information is also used to establish which countries benefit from UK ODA through GIF contributing to the country footprint information available on FCDO programmes.
Assets: GIF’s physical assets mainly consist of computer equipment and an updated list of IT equipment and phones is held in the Delivery Plan. All assets are bought or rented on short-term agreements, and the value is deemed immaterial to GIFs overall assets.
Date of last narrative financial report	Jan 2025	Date of last audited annual statement	December 2024