Programme Completion Review

Title: Investments in Forests and Sustainable Land Use (IFSLU)
Final Programme Spend £ (full life): £138.2m		Review Date: 31 October 2025
Programme Code: GB-1-202745	Start Date: 09/12/2014	End Date: 31/03/25

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024
Score	A	A	A	A+	A+	A+	A	A+	A+	A+
Risk	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case and addenda:	Business case; Addendum 1; Addendum 2
DevTracker Link to logframe:	Log frame

A. Summary and Overview

Programme description and impact
Forests are central to addressing the widely recognised challenges of climate change and degradation of nature. Well over 1bn people depend on forests for elements of their livelihoods, with greater dependency among women and in poor and marginalised groups. Around 2.5bn small farmers also benefit in a range of ways from forests and trees in landscapes, and forests play a critical role in the water cycle and generation of rainfall upon which agriculture depends. Land use change, primarily deforestation, contributes around 20% of global greenhouse gas emissions, and forests hold around 80% of terrestrial biodiversity.

Land clearance to grow a small number of agricultural commodities, including palm oil, soya, cattle, coffee, cocoa, is the single largest cause of deforestation in developing countries. These commodities are critical to national economies and to the livelihoods of the farmers who depend on them. For example, around 70% of global cocoa production is produced by 2m smallholders in West Africa; and 2.6m smallholders produce around 40% of palm oil in Indonesia.

A new approach to development is needed urgently, to balance agricultural production, and the growth, jobs and livelihoods which that provides, with protection and restoration of forests to maintain the environmental services which sustain life on earth.

Investments in Forests and Sustainable Land Use (IFSLU) started operations to address this set challenges in 2014, before the severity and urgency of the nature crises was widely acknowledged, working with the private sector and other partners to demonstrate and scale up new approaches to doing business in support of private sector-led development and mobilisation of investment into sustainable agriculture, forest protection and restoration.

Results achieved over the programme lifetime include £1.35bn of private investment mobilised; 8.65m hectares of land under sustainable land use management; and 326,969 direct beneficiaries. These figures demonstrate the scale of impact and excellent value for money achieved through the intervention, which translate into a ratio of £11 of private finance for every £1 of public finance invested in the programme. These results, and wider transformational impacts which are summarised in this review, provided the foundations for a second phase which is now operational.

The programme was centred around Partnerships for Forests, a flagship bilateral intervention which worked directly with entrepreneurs, front-running businesses and other private sector and civil society partners to deliver direct impact on the ground in countries where the programme operated. Over the course of the programme, additional initiatives focused on knowledge and evidence, convening, and mobilising action at greater scale were also supported, to complement and enhance P4F impact. The complete set of initiatives supported over the programme lifetime comprise:

Partnerships for Forests (P4F) (£120m, 2015-24), implemented through a contract with Palladium, which provided grant funding and technical assistance to catalyse investment into sustainable agriculture and forest management enterprises.

P4F Independent Evaluation and Learning Manager (£1.4m, 2017-21), implemented through a contract with LTS International / Niras, supporting evaluation, learning and adaptive management for Partnerships for Forests.

The Tropical Forest Alliance (TFA) (£6m, 2015-24), a public-private initiative hosted by the World Economic Forum (WEF), which mobilised over 170 companies, governments and NGOs to tackle deforestation associated with agricultural commodities, including palm oil, soya and beef.

The Food and Land Use Coalition (FOLU) (£1m, 2019-22), implemented through a grant to the World Resources Institute (WRI), which supported countries to develop and implement plans which balance food production, agriculture, land use and nature protection.

Just Rural Transition (JRT) (£9m, 2020-25), implemented through grants to the World Bank, Meridian Institute and Sustainable Development Solutions Network (SDSN), which established a set of partnerships focused on helping countries to align agricultural policies and support with climate and nature goals.

Partnerships for Forests (P4F) commenced in 2015, operating in West and Central Africa, East Africa and Southeast Asia, with funding from the Department for International Development (DFID). The Department of Business, Energy and Industrial Strategy (BEIS) joined the programme in 2018, committing £19.3m in funding to extend operations to the Amazon region in Latin America. DFID confirmed a £33.5m extension in September 2018, extending operations in the initial three regions to 2023. BEIS confirmed £16.2m in 2020 to extend programme operations in Latin America over the same period. Funding for all regions transitioned to FCDO in 2021 and a no-cost extension was confirmed in 2023, extending operations to April 2024, with total funding of £120m over the lifetime of the programme.

P4F worked with companies, entrepreneurs and investors to demonstrate and scale-up new approaches to business, which created growth, jobs and livelihoods while protecting and restoring forests. It supported collaboration and pre-competitive action in global agricultural commodity industries, encouraging and supporting companies to take action to address deforestation risks associated with the production and trade in agricultural commodities, and it supported policy change to strengthen market signals and the wider enabling environment for sustainable business practices.

Alongside the direct impact figures, the programme contributed to wider mobilisation of corporate action across global agricultural commodity industries and supply chains, supported progress towards adoption of regulations to address deforestation associated with agricultural commodity production, and created the foundations of a partnership to support countries repurpose agricultural subsidies. These less tangible results, which contribute to longer-term and more diffuse impact, are equally critical for the transformational change at scale that is required to address the challenges presented by the climate and nature crises.

Agricultural subsidies illustrate this importance. Governments currently provide around US$700bn annually in public support to agriculture, much of which results in harmful practices destructive to nature. Standalone funding for nature and climate is minor by comparison, and repurposing agriculture support to provide greater benefits for climate and nature is a critical step to be taken. Through programme funding to the World Bank, countries began to receive technical support to develop repurposing plans, while the JRT secretariat worked to engage other stakeholders – particularly farmers’ organisations – in this agenda. This promising area of work, set up through IFSLU, has secured strong endorsement by the World Bank and is being taken forward at greater scale through the UK’s Just Rural Transition Support Programme (£65m, 2024-2029).

Major lessons learned, evidence generated and recommendations
IFSLU was a pioneering programme which generated important lessons and evidence about use of public funds to catalyse and support private sector action at scale, a critical area of learning for International Climate Finance (and ODA, as public funding diminishes). Learning was synthesised and disseminated through in-programme monitoring, independent evaluation, a broad programme community of practice and partner networks, and well-designed and targeted communications and knowledge products. Major areas of learning include:

Mobilising private sector action and investment: Partnerships for Forests provides a leading example of how public funding for climate and nature can deliver impact through partnership with the private sector. This is reflected in the programme legacy, with the delivery team responding to requests for consultation and training on strategies, business models and approaches from numerous interested parties, including development finance institutions, government aid programmes, private sector businesses and other nature-based development initiatives from the UK, EU, US, Australia and the tropical forest regions in which P4F operated.

Inclusive business practices and smallholder livelihoods: Important lessons and evidence were generated around inclusive business practices, ways of working with private sector partners to deliver benefits at greater scale to poor and vulnerable farmers, and creation of stronger incentives to protect and restore forests in ways that benefit local communities. This is reflected in results which include 327,000 direct beneficiaries, and further prioritisation of this theme in a Phase 2 programme.

Transformational change in the land sector: Independent evaluation, which ran alongside P4F, generated valuable lessons around identifying, measuring and monitoring transformational change in the land sector. The final evaluation product, which assessed evidence and potential for transformational change in P4F landscapes, was awarded a prestigious industry prize for Evaluation in Support of Transformation.
[note] The award competition is sponsored by the Independent Office of Evaluation of the International Fund for Agricultural Development (IFAD) and the Independent Evaluation Group (IEG) of the World Bank Group, and is hosted and managed by the International Development Evaluation Association (IDEAS).AWARD Results 2022 | IDEAS (ideas-global.org)

Novel partnerships to enable action at scale: Many of the challenges associated with tackling the climate and nature crises require cooperation between different actors and new models for partnership to enable that. Programme support helped to establish innovative platforms for collaboration, such as the Tropical Forest Alliance (TFA). At its outset, this was a novel form of collaboration between companies operating at different levels of supply chains, and between state and non-state actors, enabling engagement from all actors required to make progress with addressing a complex problem.

Policy reform: The programme generated important lessons about support for policy reform, through strengthening evidence, building coalitions, providing catalytic resources and technical assistance to help governments and companies enact and implement policy change, which contributes to transformational impact at scale.

Actions following approval of this report
The programme has fully concluded, with a second phase of work now underway. Phase 2 draws extensively on Phase 1, with this learning and evidence set out in detail in the Phase 2 programme business case. Phase 1 learning will continue to be drawn upon to inform the set-up and mobilisation of Phase 2.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£60m	£138.2m
Timeframe	Sep 2015 – Dec 2020 (5 years)	Sep 2015 – Apr 2024 (8.5 years)
Outcomes	Increased private investment in forestry and ‘reduced-deforestation’ agriculture support economic growth, improved livelihoods and reduced poverty. / Investment mobilised = £150m / Land under sustainable management = 1m ha / Beneficiaries = 3 case studies	Increased private investment in forestry and ‘reduced-deforestation’ agriculture support economic growth, improved livelihoods and reduced poverty. / Investment mobilised = £1.3bn / Land under sustainable management = 8.6m ha / Beneficiaries = 327,000

Overall assessment of programme outcomes and sustainability
The programme was highly successful. Headline results achieved through Partnerships for Forests comprise mobilised investment of £1.35bn into sustainable agriculture, forest protection and restoration, against a final target of £183m. This ensured sustainable management practices across 8.6m hectares of land, against a target of 1.2m ha, bringing benefits to an estimated 326,969 people, mainly small farmers and communities living adjacent to forest areas, against a target of 80,000. Investment was mobilised at a ratio of £11 of private investment to every £1 of public funds at the programme outcome level, offering exceptional value for money on the UK ODA commitment of £120m to finance P4F.

Results clearly exceeded logframe targets and with hindsight initial targets look overly cautious when compared to final outcomes. This caution reflects great uncertainty at the outset and the novel nature of the theory of change and approach. This centred on using ODA funds to catalyse private sector investment in the land sector, and faced a degree of challenge as the programme worked through initial approvals. Even relatively far into delivery, there was uncertainty about the likely extent of outcomes, and revised targets of £183m investment, 1.2m ha land under sustainable management, and 80,000 beneficiaries were held in place through to the end of the programme.

At the next tier lower down in the logframe, targets for Outputs (see below) were either met, or only moderately exceeded, and the difference between targeted and actual Outcome-level results reflects an under-estimate (and lack of certainty) around the level of private funding which it is feasible to mobilise through catalytic public finance.

The sustainability of results is assessed to be strong, a result of the P4F approach to working with companies and enterprises that have a viable underlying business model, and helping them to attract private commercial investment and become financially self-sustaining. Programme support was targeted, short-term and catalytic, with an exit point for public funding embedded in the business incubation process around which P4F delivered support.

Post-programme, many businesses supported through P4F will continue to grow and thrive, working through value chains, market links, and products that did not exist in a viable form before P4F interventions. As a result of this support, former subsistence farmers are now running agroforestry enterprises; indigenous communities are earning an income from their intimate knowledge of their forests; and UK consumers can purchase products like Ethiopian forest coffee in their local supermarkets. These examples – and many more like them – would not have occurred without P4F support, but will continue to develop and grow following closure of the programme.

The sustainability of interventions to facilitate collaboration, convening, partnerships and policy change is harder to attribute. These interventions – referred to as enabling conditions within the programme theory of change – are essential to achieving policy change, sharing learning, mobilising action at scale, and securing transformational change. The changes these initiatives seek to deliver are long-term and diffuse. While impact has been achieved during the programme lifetime, sustaining this kind of work without public funding is more challenging.

Platforms that bring together a wide range of stakeholders involved in a value chain or industry (small farmers, cooperatives, local authorities, trading companies, manufacturing companies, retailers, financiers) are a public good with limited prospects of achieving financial sustainability. P4F explored potential cost-sharing models with private sector companies that benefit from the public good, but this proved to be unfeasible to apply in practice. Up front consideration of post-project sustainability and conditional match funding requirements may help to address this challenge in future. It may also be the case that public support to this kind of intervention is an ongoing and legitimate priority, but risks of building donor dependency and supply-driven interventions need to be mitigated by continued scrutiny of impact and additionality.

Timelines to achieve impact are a further important consideration. Most Outcome-level results were recorded after the initial five-year duration of the programme. A three-year extension was approved based on potential identified in the portfolio, to ensure full delivery of benefits. If the programme had stopped after only five years, significant success in delivering results on the ground, as well as the learning, replication and wider legacy would have been foregone. Holding course for that length of time required commitment, clarity of purpose and relatively strong risk appetite for programme teams (within the UK government and delivery partners), as well as navigation of significant risks and challenges as external events led towards shifting UK policy and priorities for international development.

Headline results at Outcome level obscure significant variation between the impact of different interventions and trade-offs between different outcomes. The programme operated in a diverse set of regions and countries comprising Latin America (Brazil, Colombia, Peru), West Africa (Sierra Leone, Liberia, Cote d’Ivoire, Ghana), East Africa (Ethiopia, Kenya, Tanzania, Uganda, Madagascar), and Southeast Asia (Indonesia).

Strategies to support forest-positive economic development were tailored to each region, supporting a range of business opportunities identified across the forest transition curve (Figure 1).

Figure 1: Forest-positive business archetypes on the forest transition curve

Results achieved through these different strategies are summarised in Figure 2. Highest levels of investment mobilised were associated with projects associated with creating value from forest growth, reflecting both the high costs of restoring forests and degraded land and also the relatively higher attractiveness to investors in restoration over protection. However, these interventions had more limited impact on protecting standing forests, which have a higher carbon and biodiversity value, and were of moderate significance in generating jobs.

Interventions focused on protecting standing forests mobilised relatively low levels of investment, reflecting the importance of small-scale, low volume, high-value products based on sustainable use of non-timber forest products in this broad archetype. Although small scale, these nevertheless bring about significant changes to incentives for forest protection and are effective at protecting large areas of forest and reaching large numbers of beneficiaries in cost-effective way.

Produce-protect interventions, which balance agricultural production and forest protection, attracted relatively high investment and were moderately effective at supporting forest areas and livelihoods. This reflects the value and large flows of investment within established agricultural commodity industries operating at forest frontiers, including palm oil, cocoa, coffee, soya and cattle. While interventions impact only modest areas of forest, halting deforestation at the forest-agriculture frontier is essential to protect standing forest beyond the frontier.

Figure 2: Investment mobilised by business archetype

Trade-offs across these different intervention types are also evident in regional results. Results in Latin America are skewed by a shorter period of time for programme operations. Nevertheless, business partnerships in the region demonstrated the potential to strengthen incentives for the protection of large areas of forest through relatively modest investments in the bioeconomy, capturing value from biodiversity and non-timber forest products.

The portfolio in West Africa, focused on collaboration with established operators in the cocoa and palm oil industries, mobilised a large amount of investment into climate resilient and deforestation-free production, with good potential to protect significant areas of forest and support jobs and livelihoods.

Figure 3: Impact by region

Interventions in East Africa focused heavily on protecting forests around smallholder livelihoods through coffee and agroforestry. These successfully mobilised significant levels of investment and benefited large numbers of people, but with more limited impacts on forests.

In Southeast Asia, the portfolio reflected a balance of work with incumbent commodity industries (rubber, palm oil) and smaller scale bioeconomy businesses, with high levels of investment mobilised to protect forests and benefit significant numbers of people.

Overall, no one strategy or approach emerges as stronger than others, and balanced portfolios which reflect regional and local needs and deliver varying results across the three metrics offer the best approach. Scale of intervention does not correlate to greater impact, as demonstrated by the relatively small investments required to protect standing forest. It is important to note that conserving standing forests is the most cost-effective solution to reducing greenhouse gas emissions. Lessons from the portfolio offer valuable insights that are relevant for future strategies to curb deforestation, highlighting the need to focus on local livelihoods and incentives as an effective solution.

Theory of change and results framework
IFSLU worked to shift private sector incentives and practices, with Partnerships for Forests as the major element of those efforts. Changing business-as-usual practice in land use is challenging. The programme theory of change (Figure 4) was focused on shifting private sector incentives and practices through market-driven approaches and engagement at all levels of markets and supply chains. The programme provided grant financing and technical assistance in the following areas to deliver against the theory of change:

Demand-side measures: to accelerate public and private commitments to create a more valuable market for timber and agricultural commodities from sustainable sources.

Enabling conditions: to improve the business environment for investments in sustainable forestry and agriculture (policies, regulations, standards).

Partnerships and investments: to develop public-private partnerships and investments in sustainable forestry and in sustainable agriculture.

Leadership, collaboration and learning: to accelerate replication and scaling-up of successful sustainable business models.

Legacy: to sustain and scale-up efforts to increase private investment into sustainable land use beyond the life of the programme, building on the successful approach developed through P4F.

Figure 4: P4F summary theory of change

The steps in the theory of change, and the way in which those were reflected into the results framework, proved to be valid and effective over the lifetime of the programme, with Output-level results leading clearly towards the desired Outcome-level results. A strong focus on learning and evidence within the P4F delivery team, alongside input from the independent evaluation and learning manager, ensured that the programme generated a strong body of evidence in support of the theory of change.

Following the logical chain of the intervention from Outcome to Impact is more challenging, a challenge shared by all actors and interventions focused on halting and reversing the loss of forests. In the logframe, the targeted Outcome is: Increased private investment in forestry and ‘reduced-deforestation’ agriculture support economic growth, improved livelihoods and reduced poverty; leading to an Impact of Reduced deforestation leading to reduced greenhouse gas emissions, reduced poverty and conservation of biodiversity. While successful interventions such as IFLSU deliver important development benefits and forest protection and restoration within their immediate spheres of influence, tracking this up to an Impact that demonstrates influence over global rates of forest loss is more challenging.

FAO data on forest loss, published over a long time series, shows a declining rate of global forest loss. However, rates in key tropical countries remain high. Forests are also increasingly vulnerable to the effects of climate change, with increased rates of fire and disease adding to pressures from land clearance for agriculture, infrastructure, mining. Continued efforts are required to build the capacity, address governance and policy challenges, and ensure flows of finance, investment, trade and production are aligned with forest protection and restoration, through models that support national development goals and aspirations, meet local needs for jobs and livelihoods, and ensure forest protection and restoration.

## C: Detailed Output Assessment

Output Title	Demand-side measures: An enhanced market for sustainably sourced products through public and private commitments to sustainable sourcing
Output number:		1	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N

Indicator(s)	Starting Target	Final Logframe Target	Final Result
1.1 cases where P4F has supported demand side policy change and development, at public (sub-national, national or international) or multi-corporate level, that enhance forests and sustainable land use investment.	2 cases by 2018	7 cases by 2024	Exceeding target: 10 cases
1.2 cases where P4F has supported demand side policy change and development at the individual corporate level that enhances forests and sustainable land use investment.	N/A	15 cases by 2024	Exceeding target: 17 cases
1.3 cases where P4F has contributed to value or commodity chain change with regards to enhanced forests and sustainable land use, through supporting market linkages within or for FPs.	1 case by 2019	8 cases by 2024	Exceeding target: 9 cases

Overview
This output is focused on building stronger markets for sustainably produced agricultural commodities. A limited level of funding was provided for this Output, which accounted for around 6% of total grant funding. This reflects a strategy focused on specific and targeted packages of support to catalyse shifts in consumer markets which provide market-based incentives for implementation of sustainable practices on the ground.

Changes targeted included public policy reforms, such as procurement and due diligence measures, and private sector policy reforms, such as the implementation of sustainable sourcing commitments and practices. The initial focus of support was on broad interventions influencing wider market signals in UK and European markets. This evolved towards a later focus on regional and domestic demand and market signals in producer countries.

P4F interventions included private sector sustainable sourcing commitments for palm oil and soya in the UK market; UK and EU policy (the UK was an EU Member State for the first half of this programme) for sourcing of agricultural commodities including palm oil, soya, cocoa, coffee, rubber; and sustainable sourcing of beef in Brazil. It is not possible to cover all interventions over the course of an 8.5-year programme on this scale, so a flagship example is provided in Box 1.

The TFA also reflected the importance of demand signals in catalysing change in markets, with this initiative initially founded around a commitment by the Consumer Goods Forum (CGF), an industry association for retail and manufacturing companies, which pledged in 2015 to remove deforestation from supply chains for palm oil, beef, leather and paper & board. This created a powerful market signal, with the TFA convening other players in the supply chain, governments and civil society groups, to mobilise collective action aimed at realising those commitments.

Support provided to these initiatives encompassed policy engagement (e.g. supporting partners to help to shape key policies); technical support (e.g. supporting development of materials and provision of specialised advice to assist policy development on themes including demand, production and trade, traceability & transparency, market access & inclusion, and landscape governance); and convening, coordination and engagement (e.g. supporting stakeholder mobilisation, dialogue processes and meetings between industry, NGOs, public sector, and local communities).

Changes generated through demand-side measures are important for the longer-term sustainability of interventions and for wider transformational change, as they shape norms, practices and rules in markets and provide the demand signals which other market participants respond to. However, as P4F came to an end, so too did public support to these initiatives, raising questions about how to continue this important work in the absence of public funding, and the related need to develop sustainable funding models which avoid a full dependency on public funding. Phase 2 will consider how to address this challenge.

Lessons identified
Policy reform takes time to achieve, with work by many actors required to build consensus, gather evidence, demonstrate feasibility, and support development, particularly on novel and contested issues. Support to enable this needs to be committed for the long-term, with intelligent and adaptive capability. Individual actors can’t achieve transformational change working alone, and collective action is essential to make progress. The role of trusted, neutral and skilled facilitation is crucial in enabling partnerships and mobilising collective action, often by actors that are not used to working with each other. Finally, while demand-side policy provides a critical market signal, alone it is not sufficient to generate change, and needs to be complemented with supply-side engagement for successful outcomes and transformational change.

Recommendations
Secretariats, technical assistance and facilitation support are critical to the success of partnerships and platforms for collaborative action. Sustaining this support over time can be challenging but gaps in funding can lead to the loss of critical skills, capability and momentum. In future work, it will be important to continue looking for ways to maintain financial and technical support over time on a sustainable basis that mitigates the risks which public funding cycles present to the continuity of work. While public funds are likely to be needed – and can be justified – diversifying sources of funding is clearly needed for sustainability and resilience over time.

Box 1: Flagship demand-side interventions
___________________________________________________________________________________________

The United Kingdom has one of the largest deforestation footprints in Europe, with demand for palm oil, soy, cocoa, coffee, cattle products and rubber linked to around 36,000 hectares of tropical forest loss and 13 million tonnes of carbon dioxide emissions in 2022. These figures show how consumer markets in high-income countries continue to shape land use far beyond their borders, highlighting the urgency of aligning market sourcing practices with policy aimed at halting and reversing deforestation. This was a key objective of P4F demand-side interventions.

Support was initially focused on a palm oil roundtable, working in support of a collective pledge to ensure that all UK palm oil imports were from certified sustainable sources by 2015. A soya roundtable was established in 2017, learning from the approach taken to palm oil. These were later merged into the UK Sustainable Commodities Initiative (UKSCI), established as an industry-led platform facilitated by Efeca, a partner in the P4F consortium. UKSCI brings companies, civil society, and policymakers into the same forum to work towards the goal of sustainable, resilient commodity supply chains that have a positive impact on people and planet.

The impact of these interventions has been striking. Over the past decade, UK commodity supply chains have shifted in measurable ways, with certification rates climbing steadily year-on-year. In 2010, only 16% of palm oil imports were RSPO certified. By 2023 that figure had risen to 92%. Soya followed a similar trajectory, moving from 16% in 2017 to 74% in 2023. These changes point to a coordinated effort across refiners, feed companies, and retailers that reshaped the market in a relatively short time.

Growth in participation tells a parallel story. What started as 15 associations working on palm oil has expanded into more than 130 companies and organisations covering food, feed, shipping, and retail. This widening base has given the platform greater legitimacy and allowed conversations to reach sectors that had previously operated in silos.

The quality of monitoring has also deepened. By combining company submissions with national trade statistics, Efeca’s annual reports now serve as a trusted reference in government consultations and international dialogues. Because the same data underpin both policy and industry planning, progress can be tracked with a consistency that earlier voluntary efforts often lacked.

Alongside the UKSCI, P4F supported the Global Resource Initiative (GRI) Task Force, a panel of independent experts set up in 2018 to identify actions across supply chains to improve the sustainability of products and reduce deforestation. Efeca formed the GRI secretariat, facilitating the work of the task force and leading to publication of final recommendations for the UK government in March 2020.

A central recommendation focused on the need for mandatory due diligence, to ensure that agricultural commodities imported into the UK had not caused deforestation in the country of origin. This recommendation led on to the inclusion of a due diligence measure in the Environment Bill, which was passed into law in October 2021.

P4F – through Efeca – also provided technical assistance and expert advice to support the development of the secondary legislation required to support implementation of the measure. Secondary legislation had not been implemented at the time of programme closure, but the primary legislation nevertheless provides an important market signal and sets market expectations and direction of travel in policy.
___________________________________________________________________________________________

Output Title	Enabling conditions: Improved business environment for investments in forests and sustainable land use
Output number:		2	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	N

Indicator(s)	Starting Target	Final Logframe Target	Final Result
2.1 number and description of cases where P4F has supported national / international multi-partner initiatives designed to enable private investment in forests and sustainable land use.	3 cases by 2020	18 cases by 2024	Exceeding target: 20 cases
2.2 number and description of cases of Forest Partnerships that have benefitted from an enabled business environment as a result of P4F support.	7 cases by 2020	21 cases by 2024	Meeting target: 21 cases

Overview
This output is focused on strengthening the conditions required to enable sustainable private investment, addressing challenges such as the need to create conducive policy and regulatory frameworks, develop standards and tools to support sustainable practices, and facilitate pre-competitive collaboration. Approximately 20% of overall grant funding was allocated to this output. Interventions under Output 2 are important for the programme theory of change, helping to link individual business partnerships with wider transformational impact across markets, industries and finance.

The portfolio was developed through a mixture of opportunistic and strategic interventions, with an initial focus on sector-wide, regional and national issues, shifting to a later focus on interventions more closely aligned to business partnerships supported under Output 3.

Interventions addressing enabling conditions at a broad scale across sectors or regions are important for generating change at scale. Often these kinds of initiatives have a high degree of political visibility, offering an opportunity to align political engagement and programme support. For example, the Cocoa and Forests Initiative (CFI), a partnership formed by companies representing 80% of the global cocoa and chocolate industries, and the governments of Ghana and Cote d’Ivoire representing around 60% of global production, was launched in 2018 with support of HRH the Prince of Wales (now HM King Charles). P4F then engaged with technical and financial support, helping to catalyse change at scale throughout the industry.

Interventions at a more targeted scale generally had less visibility, but supported a clearer line of progression through the logframe and theory of change. For example, support to establish a regulatory framework for bioeconomy investments in Colombia allowed progress to be made by partner businesses, generating more investment and greater impact on the ground. It is not possible to cover all interventions over the course of an 8.5-year programme on this scale, so a flagship example of an enabling conditions intervention is provided in Box 2.

Whether at broad or more defined scale, supporting multistakeholder processes was a consistently important theme under Output 2, bringing different interest groups together to build consensus and agree policy change, regulatory standards, and support policy implementation. Eight years of delivery has generated substantial data, which was reviewed in the final phase of operations to generate insights and management information to guide future work.

The analysis drew on input data across six cost categories of support provided to multistakeholder processes, comprising human resources, travel, operations, workshops, communications and knowledge products, and other costs. The analysis assessed the support required, based on a sample of 23 initiatives implemented in all five programme regions (four in East Africa, eight in West and Central Africa, one in Southeast Asia, six in Latin America, and four Global). Human resource costs were the main required input (68%), with a significant proportion of budgets also falling under the Workshops category (11.6%) and Communication category (5.3%).
Figure 4: Cost category expenditure for multistakeholder initiatives

Lessons identified
High demand for human resources – and associated costs – reflects the need for capacity building and technical assistance in the sector, as well as the resource-intensive requirements associated with facilitating pre-competitive collaboration and multistakeholder partnerships. While these interventions are important for mobilising action at scale, there is a need to consider the efficiency and explore alternative approaches – such as grantee capacity building or streamlining project delivery – to optimise resource utilisation, improve cost effectiveness, share risks and costs with other participants, and enhance sustainability. Similar challenges were noted under Output 1.

Despite these challenges, programme experience shows that enabling conditions interventions have high impact potential at global, regional, national and local levels. There is also strong demand for this kind of support, which is generally underfunded across the sector. In this context, long-term public funding brings added value and can be important in helping to catalyse action and drive change. However, it is important to ensure clear objectives, milestones and exit strategies for any public support committed.

Aligning enabling conditions support with the business partnerships portfolio brought strong added value, facilitating specific investments, enabling scaling and replication, and establishing a clearer results chain within the programme. Technology and information infrastructure have also been identified as important areas of potential future support, with some initial support around these themes demonstrating striking potential for rapid scaling of action.

Recommendations
Future support should continue to prioritise enabling condition interventions, drawing on lessons identified in Phase 1. Specific issues to focus on include human resource costs, sustainability, avoiding dependency on public resources. A strategic approach, focused more closely on synergy between business partnerships and enabling conditions, offers an opportunity to strengthen the results chain in the theory of change and enhance programme impact.

Box 2: Flagship enabling interventions
___________________________________________________________________________________________

The Africa Palm Oil Initiative (APOI), established as the first signature initiative of the Tropical Forest Alliance (TFA) in 2016 and one of the first and longest-running partnerships supported through P4F, is a regional initiative focused on decoupling deforestation from palm oil supply chains. It was established in support of a vision for a prosperous palm oil industry which brings jobs and wealth to local communities in a way that is environmentally and socially sustainable and protects the rich tropical forests of the West & Central Africa region. Ten countries (Cameroon, Central African Republic, Côte d’Ivoire, Democratic Republic of Congo, Gabon, Ghana, Liberia, Nigeria, Republic of Congo and Sierra Leone) joined the initiative, which was launched at COP16 in Marrakesh.

Support focused on the development and endorsement of the regional principles; establishment of a regional platform to facilitate sharing of lessons and experience on progress in the ten participating countries; agreement on national principles and actions; establishment of national multistakeholder platforms to coordinate and support implementation of the principles and actions; enhanced knowledge of sustainability tools and approaches such as the Roundtable on Sustainable Palm Oil (RSPO), Free Prior and Informed Consent (FPIC), High Conservation Value (HCV) and High Carbon Stock Approach (HCSA); and integration of these tools and approaches into national laws and regulations.

Continuous engagement with governments through multistakeholder processes has resulted in much greater commitments to the responsible development of the palm oil sector across the region. This is beginning to provide tangible outcomes in areas such as smallholder productivity, the adoption and implementation of FPIC compliance requirements in land allocation, the adoption of smallholder inclusion in oil palm development, and the integration of tools and approaches such as FPIC, HCV, HCSA. A wide range of impacts on policies, regulations and practices has been documented throughout the region, creating a much stronger enabling environment for a sustainable palm oil industry in the region.

At the UNFCCC COP27 in Egypt, participating countries agreed to relaunch APOI as the Africa Sustainable Commodities Initiative, applying lessons and a related single set of principles to the responsible production of all agricultural commodities. This now puts producer countries in Africa at the forefront of defining the principles for the sustainable development of cocoa, rubber, palm oil, coffee and other commodities in a way that improves livelihoods and protects natural resources, including forests.
___________________________________________________________________________________________

Output Title	Partnerships and investments: Partnerships between private sector, public sector and communities that deliver investment in forests and sustainable land use
Output number:		3	Output Score:	A+
Impact weighting (%):		60%	Weighting revised since last AR?	N

Indicator(s)	Starting Target	Final Logframe Target	Final Result
3.1 number of concept notes that are accepted into the programme.	35 by 2019	67 by 2022	Exceeding target: 98
3.2 number of partnerships with a partnership agreement as a result of P4F support (Decision Gate 1).	17 by 2020	39 by 2022	Exceeding target: 49 agreements
3.3 number of partnerships with a business plan as a result of P4F support (Decision Gate 2).	15 by 2020	31 by 2022	Exceeding target: 44 business plans
3.4 number of partnerships ready and prepared for a pilot as a result of P4F support (Decision Gate 3).	10 by 2020	28 by 2024	Exceeding target: 32 pilots or trials
3.5 number of partnerships prepared for commercial scale-up as a result of P4F support (Decision Gate 4).	7 by 2020	27 by 2024	Exceeding target: 32 ready to scale-up
3.8 number of partnerships scaling-up investment and operations as a result of P4F support. (Decision Gate 5)	N/A	11 by 2024	Exceeding target: 12 scaling-up
3.6 number of interventions with new or enhanced stakeholder engagement planning (including gender and social inclusion) as a result of P4F support.	6 by 2020	13 by 2024	Exceeding target: 16 cases
3.7 number of interventions that have contributed to greater gender equality.	N/A	8 by 2024	Meeting target: 8 cases

Overview
This output is focused on incubating ‘Forest Partnerships’, businesses with commercial potential to mobilise investment and deliver strong development, climate and nature benefits. Grant funding and technical assistance were used to move partnerships through a managed process of incubation, leading from agreement of an MoU between parties (Decision Gate 1 (DG1) MOU), through the development of a business plan (DG2 Business plan), pilot testing (DG3 Pilot), readiness for commercial scale-up (DG4 Readiness for scale-up) and scaling-up investment (DG5 Scaling-up investment).

This output, with the highest weighting in the logframe, accounted for 75% of overall grant funding. This reflects the principal programme focus on turning corporate commitments into positive development impacts on the ground in forest landscapes. Over the course of the programme, 98 forest partnerships were supported, with around 200 grants issued to drive forward business incubation. It is not possible to cover all interventions over the course of an 8.5-year programme on this scale, so flagship examples are provided in Box 3. Output targets relating to incubation have all been exceeded (Figure 5).

Figure 5: Incubation support

An initial approach to sourcing partnerships through open calls proved to be ineffective, resulting in overwhelming numbers of poorly aligned proposals which absorbed disproportionate amounts of team time to sift and manage. Learning from this, the approach evolved into a mixed strategy of direct solicitation with co-design, and an online portal with screening to accept unsolicited applications and ensure that the programme was accessible to all potential partners. This led to a significant increase in the quality of proposals and better use of team time.

Learning and adaptive management was applied to the incubation process over time, resulting in more streamlined and efficient business processes. This evolution was supported by the Independent Evaluation and Learning Manager, through a review which assessed approaches applied by a sample of private and publicly funded business incubators operating across a range of sectors. This led to recommendations for improved pipeline management, greater efficiency in processing applications and reduced project development time. However, balancing the need to move quickly and support innovation with the need for effective risk management was an ever-present tension that required constant management oversight to ensure the right balance.

The high number of ideas assessed before acceptance into the programme was also striking, and reflected the lack of maturity in the sector and the novel approach taken by P4F, focused on working in a structured and targeted way with businesses, rather than issuing longer-term grants to civil society organisations, which is a more common form of delivering donor support to the sector.

Over 775 potential ideas were identified and screened, leading to 98 partnerships entering the incubation process, a high rate of attrition which reflects relative immaturity and low capacity in the sector and the importance of careful screening to maximise quality in the portfolio.

Out of the businesses which entered into incubation, around 43% entered at DG1, of which only 4% reached the DG5 of the incubation process (Figure 6). A higher share of partnerships which entered the programme at a greater stage of maturity, for example to start testing scale-up ideas at DG3, reached DG5. This reflects generally long timelines to maturity in the sector, significant needs to build capacity in start-ups operating at earlier stages of the business development process, and greater risk and uncertainty associated with engaging businesses at an earlier stage of the incubation process.

Figure 6: Incubation pathways

Lessons identified
The portfolio generated vast learning, which has been widely shared and disseminated. The approach to business incubation, and the progress and impact metrics associated with that, provided a strong framework which ensured consistency and clarity of purpose across all regions, while at the same time enabling very different, locally grounded approaches tailored to different countries and regions and delivering impact in very different contexts.

The business incubation and decision gates were also effective for tracking progress, enabling adaptive management and ensuring a ‘fail fast’ approach. However, failing is never easy and losing unsuccessful partnerships from the portfolio always proved to be difficult. On the few occasions where businesses supported by the programme failed, the decision to end support resulted in shortfalls in expected results, gaps in regional portfolios, actions to mitigate consequences and related communications, and a need to reassess regional strategies. Careful screening upfront helps to mitigate this risk, but can also lead to caution in supporting more early stage, risky and innovative ideas. Overall portfolio management required constant management of these risks, tensions and trade-offs.

Support for business incubation works for a wide range of businesses, from start-ups through to multinational businesses. Different businesses need very different kinds of support, and the programme generated significant learning to support a better understanding of how public support can be used to catalyse and scale-up business-led development. For example, a start-up may need support to build internal capacity, undertake product research and development, legal support for contracts and offtake agreements, trial-runs of production, testing of market appetite; whereas established multinationals hold all of that internal capability and required resources, but may need help in other areas, such as community engagement, landscape governance, partnership to access networks and expertise outside core business interests, and partnership support to mitigate risks of trialling new approaches and innovations.

The right partners and the right partnership models are important factors underlying success. Support to build partnerships can be a significant element of the added value provided through a programme like P4F, which holds skills and expertise in identifying needs and building partnerships. External stakeholder engagement and issues of equity and inclusion are also an important element of successful partnership development, with the programme also providing valuable advice and guidance on these issues.

Recommendations
Draw on Phase 1 learning to design a Phase 2 portfolio with potential to achieve impact at scale, with enhanced poverty, biodiversity and gender equity benefits where opportunities arise.

Box 3: Flagship forest business partnerships
___________________________________________________________________________________________

East Africa: Community livelihoods and forest protection incentives
Coffea arabica is indigenous to Ethiopia, where it grows naturally in highly threatened forests. P4F support focused on partnerships to strengthen the value chain and build a premium market for wild coffee, providing poor rural communities with enhanced income and strengthened incentives for forest protection and restoration. Interventions focused initially on capacity building, improvements to harvesting, post-harvest processing and marketing, followed by scaling up with private sector partners.

Interventions contributed to sustainable expansion of the specialty forest coffee market, with £18m invested, protecting 150,000 ha of forest across threatened forest landscapes including the Yayu, Kafa and Sheka Biosphere Reserves. Interventions also helped to establish a more inclusive value chain while boosting productivity and incentivising protection and restoration of forests. Around 17,000 smallholder farmers benefited, with farmgate prices increasing from an average of £2.6/kg to between £4.6-5.4/kg through productivity and quality improvements, branding and direct market linkage, leading to a 30% increase in income at farmgate level and a 35% increase in export prices.

Interventions to ensure post-programme scaling and sustainability included cooperation with the Ethiopian Coffee and Tea Authority (ECTA) to strengthen the policy enabling environment; and establishment of a wild coffee platform to continue and expand value chain development and forest protection systems post-programme, with estimated potential to protect nearly 500,000 ha of forest and benefit over 1.1 million farmers by 2032.

Southeast Asia: Developing markets for ecosystem services
In Indonesia, P4F worked with Lestari Capital to develop a market for ecosystem services, raising long-term private sector finance for conservation and restoration. Lestari Capital matches buyers and sellers of ecosystem services to create a market, raising long-term finance through providing an effective solution for companies to act credibly and transparently on their sustainability commitments, and providing communities with a source of finance for conservation and management activities.

P4F worked with Lestari from a formative stage of development, supporting establishment of the company, design and testing of an initial product offering, and engagement to secure investment and partnership with palm oil companies and conservation projects. This support led to the development of two products, the Rimba Collective and the Sustainable Commodities Conservation Mechanism (SCCM). The former channels payments from companies in the palm oil supply chain to conservation and restoration projects, under their commitments to zero deforestation palm oil production. The latter helps companies to manage liabilities for historic deforestation under the RSPO certification scheme, and channel mandatory compensation payments to conservation and restoration projects.

By the end of the programme, four companies had invested in the Rimba Collective, committing approximately £52m, and three companies had invested with SCCM, committing more than £17m. Together, these investments provided funding to protect a combined area of over 41,000 ha of forest over a 25-year period. P4F also strengthened the supply of projects generating services for this new market, supporting eight forest communities to develop business plans for selling ecosystem services through Lestari to private sector counterparties. The schemes have continued to scale since the end of the programme, with Rimba currently supporting 300,000 ha of forest under management with a clear pathway to grow further in coming years.

West Africa: Landscapes for livelihoods and conservation
Cocoa is vital for economies and farmer livelihoods in West Africa, but faces threats from climate change and environmental degradation. Working through a business partnership with Touton, a leading cocoa trading and processing company, P4F supported the piloting and scaling-up of an approach to growing climate resilient and deforestation-free cocoa in the Bia Juaboso landscape in Western Ghana.

The landscape faced several challenges, including encroachment into forest reserves for agriculture activities, logging, uncontrolled hunting, farming within buffer areas and unsustainable agricultural practices. Smallholders in the landscape had limited technical knowledge, low incomes, coupled with no incentives for forest protection.

Touton, motivated by shifts in end consumer markets and the requirements of buyers (e.g. chocolate companies) selling into those markets, was focused on increasing its ability to supply deforestation-free cocoa at scale to its clients. P4F support was focused on scaling action across the landscape, through establishing, piloting and scaling up a sustainable produce-protect model, with collective and organised smallholder farmers and strengthened forest protection mechanisms. Key areas of support included set-up of landscape governance arrangements and forest protection committees, promotion of sustainable cocoa productivity improvements for smallholder farmers, and creation of incentives and income diversification for smallholder farmers.

Prior to P4F support, Touton was working with farmers across 7,000 ha, producing 3,000 MT of cocoa. With P4F support, this had risen to 46,000 ha producing 26,000 MT by 2022, benefitting 50,000 farmers. Other results include catalysing £97m in supply chain finance and an increase in farmer income by over 50%; protection of the Krokosua forest reserve (48,161 ha) and Bia Conservation area (30,600 ha), which provides habitat for critically endangered species including chimpanzee, forest elephant and white colobus monkey. Post-programme scaling and replication has been ensured through a strong business case for action (Touton documented an increase in profits from the landscape through embedding more sustainable practices), wider changes influencing market practices (including the pending introduction of mandatory due diligence for deforestation impacts in the EU), and wider industry collaboration through the World Cocoa Foundation (WCF).

Latin America: Transparency and traceability to incentivise sustainable practice
In Brazil, P4F worked to support the development of Conecta, a monitoring tool to strengthen transparency and accountability in the Brazilian livestock chain, working with Safetrace, Amigos da Terra​ and CPQD. Conecta allows abattoirs to make an informed decision to purchase from ranchers that comply with the Forest Code and enables compliant ranchers to assure their social and environmental situation. The platform rapidly reached scale with programme support. Work to develop it began in 2021, when the partnership behind Conecta formed with P4F support. By the end of the programme in 2024, it was monitoring socio-environmental impacts of 28.7k farms in 20 Brazilian states, covering a total area of 23.4 million hectares. This represents a rapid and phenomenal rate of growth.

Ordinarily this impact would meet the verification criteria required for inclusion in Outcome-level reporting for area of land under sustainable management. A decision was taken not to include this within final reported results, as the vast area covered would have had a distorting impact on other programme results. However, this example does illustrate the potential for scale which technology-based interventions have under the right circumstances, and raises some interesting lessons for future scaling strategies. Rapid uptake of the tool during the programme clearly points towards strong potential for post-programme sustainability and continued growth.
___________________________________________________________________________________________

Output Title	Leadership, collaboration and learning: Models, learning and leadership that support collaboration and investment in forests and sustainable land use
Output number:		4	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N

Indicator(s)	Starting Target	Final Logframe Target	Final Result
4.1 annual report demonstrating understanding of portfolio dynamic and progress through decision gates.	5 by 2020	10 by 2023	Meeting target: 10 reports
4.2 number and description of P4F knowledge products published and communicated	20 by 2020	57 by 2024	Exceeding target: 72 products
4.3 number and description of initiatives with enhanced or high value collaboration from P4F	20 by 2020	19 by 2023	Exceeding target: 20 initiatives
4.4 number and description of events with a distinct contribution from P4F	30 by 2020	73 by 2024	Exceeding target: 94 events

Overview
This output drew from experience of delivering impact on the ground, and used that to support learning, collaboration and leadership, with the principal aim of sharing programme knowledge to accelerate replication and scale-up of successful approaches. Engagement across this output encompassed learning from the portfolio, business incubation processes, knowledge products, initiatives and events.

Portfolio learning drew upon eight years of portfolio data and management information, which was used to enhance understanding of the types of business which deliver the greatest impacts for investment, land area and people, regional distribution of impacts, rates of success and timelines within the incubation process, as well as case studies and a rich set of lessons on key pillars of the programme approach, such as support for demand-side measures and enabling conditions, monitoring, evaluation and learning, and legacy.

Knowledge products encompassed a wide range of interventions, including reports, case studies, video case studies, social media output and broadcasting. In all cases, knowledge products had to be guided by the aim of capturing learning, supporting action or adoption of recommendations, with dissemination to target audiences. An important principle behind knowledge products was to ensure promotion of the projects and the business models, rather than promotion of the programme.

Video case studies, hosted on a YouTube channel, were particularly effective in documenting programme impacts in an engaging way. LinkedIn was found to be the most effective platform for engagement on social media, allowing the programme to reach a smaller but more informed community of practice than other more generic platforms and prioritising the ‘quality’ or ‘actionability’ of the audience, over quantity.

Initiatives comprised ongoing, collaborative programmes of work with other organisations, with a distinct contribution from P4F over a minimum period of six months, and a focus on issues such as strategy development and resolution of challenges.

Events were the final element in this Output, focused on events produced with a ‘distinct contribution’ from P4F (i.e. not just participating as an attendee). The annual highlight, and a major platform to support other forms of leadership, collaboration and learning, was the P4F Annual Forum, which brought together partner businesses, with other programme stakeholders, to facilitate learning, collaboration, problem solving, marketing, connections to investors and communications (Box 4).

Lessons identified
Sharing knowledge to support the scaling and replication of sustainable approaches through markets, industries and supply chains is an important element of the programme theory of change. However, sharing knowledge in ways that are accessible and actionable can be challenging. A range of approaches helped to address this, including more interactive engagement through initiatives, face-to-face collaboration over multiple years to build trust, engagement and work through a range of media.

Recommendations
Apply lessons from leadership, collaboration and learning to inform Phase 2 strategy.

Box 4: Flagships leadership, collaboration and learning engagements
___________________________________________________________________________________________

The annual P4F Forum was a key focus of leadership, collaboration and learning. The final forum, held in conjunction with a series of events over three days in May 2023, drew together a groundbreaking global community of experts working on issues relating to sustainable business and investment in the land use sector.

The series opened with the Amsterdam Declarations Partnership annual multi-stakeholder meeting, drawing together international experts from government, business, civil society, farming organisations and communities to sustain momentum and catalyse action in the transformation of agricultural commodity markets and industries, and address challenges and opportunities relating to the implementation of mandatory due diligence measures.

This was followed by the Partnerships for Forests Forum, the annual meeting for P4F programme partners. The forum was organised with a greater scope, scale and ambition than any previous event. Taking place as the programme entered its final year, it offered an unparalleled opportunity to share the vast experience gained during eight years of delivery, profile success – including the launch of a video celebrating the £1bn investment milestone – and continue driving forward the agenda.

Day 1 was a focused session on Investing in Forests and Sustainable Land Use, held in conjunction with FMO, the Netherlands’ development finance institute, and the UK’s Mobilising Finance for Forests (MFF) programme. Day 2 was the P4F Exhibition, offering an opportunity to P4F partners to showcase their businesses, products and innovations, and providing an opportunity to connect to buyers, investors and other project developers, as well as running a series of panels, roundtables, and networking opportunities.

The target audience for the forum was investors, including those working in the finance sector, government representatives with a nature finance focus, and businesses. A key part of the audience strategy was targeted at those on the outside or periphery of the nature finance sector, as well as those already highly engaged with forests and sustainable land use. The format for the exhibition and content for side sessions was planned with this in mind.

The depth of experience held by the programme, expertise in the wider P4F partner network, and the global action which this community of practice was engaged in delivering, represented a phenomenal achievement, as well as reflecting strongly on the UK government’s commitment to this agenda through funding the programme.
___________________________________________________________________________________________

Output Title	Leadership, replication and transformational change: extending P4F approaches to drive investment in forests and sustainable land use.
Output number:		5	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Starting Target	Final Logframe Target	Final Result
5.1 number of leadership and replication initiative idea notes approved by PAC.	N/A	16 by 2023	Exceeding target: 18 notes
5.2 number of leadership and replication initiative outcome assessment reports approved by PAC.	N/A	16 by 2024	Meeting target: 16 cases
5.3 number and description of cases of leadership or replication with a distinct contribution from P4F.	N/A	9 by 2024	Meeting target: 9 cases

Overview
This output is focused on the external replication and scaling of models, approaches and learning from within the programme, to ensure P4F knowledge and experience of supporting public-private partnerships helps others to engage effectively in similar efforts. It was formally introduced to the programme logframe through a contract amendment finalised in 2022.

Results were achieved through sharing programme expertise, rather than provision of funding, and it is designed to extend the approach to public-private collaboration and leverage the knowledge of private sector engagement and delivery of impact through sustainable business incubation which the programme has pioneered since 2015. This tapped into growing interest in sustainable investing and mobilising private investment into sustainable land use, and helped to ensure that the P4F experience informed and helped to accelerate this trend.

Engagements were demand-driven based on requests and targeted at external replication of P4F programme approaches and design. No grants were provided under this Output, with an emphasis instead on technical assistance inputs from the P4F team. Engagements were set up with public, private and civil society partners, with the aim of contributing towards transformational change and building the P4F legacy. Specific themes around which interventions were structured included programme design and strategy, business incubation, pipeline development, project selection strategies and investment mobilisation. An example of a flagship intervention is provided in Box 5.

Lessons identified
The approach taken under Output 5 proved to be a structured and effective way of sharing programme experience, drawing on the wide partnership network held in the team. While it was introduced as a new Output late in the programme cycle, there may be opportunities to take a similar approach from an earlier stage in Phase 2 and ensure an even stronger legacy from the outset. This could include greater attention to building capacity for incubation and pipeline development within programme operating regions, to diversify sources of support and mitigate risks of dependence on a donor-funded incubator as the sole source of support, as well as continuing to engage with other partners around specific opportunities identified through a new portfolio.

Recommendations
Consider the approach to leadership, replication and transformational change from an early stage in Phase 2, drawing on Phase 1 experience and demonstrated ability of the programme approach to deliver change.

Box 5: Flagship leadership, replication and transformational change interventions
___________________________________________________________________________________________

The Global Gateway is a major EU strategy, launched in 2021, which aims to narrow the investment gap in smart, clean and secure infrastructure. It aims to mobilise €300bn in investments that support sustainable and high-quality projects, addressing the needs of partner countries and ensuring lasting benefits for local communities by 2027.

The European Fund for Sustainable Development Plus (EFSD+) is a major programme launched as part of the Global Gateway. It includes a €366m Carbon Sinks Guarantee for European development finance institutions and co-investors, to de-risk investments in nature-based carbon projects in emerging and developing countries. The facility aims to mobilise up to €4 billion in investments in nature projects such as reforestation, regenerative agriculture and blue carbon, generating high-quality carbon credits and substantial environmental and social benefits.

DEG, the German development finance institution, is working with FMO and Finnfund, to manage and implement the guarantee. Alongside the guarantee, the development finance institutions aim to establish a €32m technical assistance facility to develop project pipeline.

DEG requested P4F support to inform the set-up of the technical assistance facility, with this advice focused on pipeline development, project selection, portfolio management, incubation, performance and success measurements. This offered an opportunity to draw upon core programme learning to inform the strategy and approach under a major new drive to scale-up investment in nature, using expertise held within the programme team and sharing experience and learning around developing a portfolio of investable nature-focused businesses that deliver positive development impacts.
___________________________________________________________________________________________

D: Value for Money

VfM performance compared to the original VfM proposition in the business case
Partnerships for Forests generated £1.35bn in private sector investment, at a ratio of £11 of private investment to every £1 of public funds at programme Outcome level, offering exceptional value for money on the UK commitment of £120m to finance the programme. This greatly surpassed initial value for money assessments in the 2014 business case, which modelled a conservative estimate of £0.28 of private investment for every £1 of public funding.

Disaggregated data provides important insights into the different types of finance and investment which has been mobilised, supporting learning and informing future strategy (Figure 6). The total investment of £1.35bn of investment breaks down into £765m of direct private investment (for example, funding for a new plantation development), £368m in supply chain finance (for example, offtake agreements for deforestation-free cocoa or coffee), and £220m of investment by development finance institutions (public funds offered on commercial terms). P4F also helped to mobilise £120m in public funding, through instruments such as the Green Climate Fund (GCF), providing additional finance to scale-up initiatives incubated through the programme.

Figure 6: Disaggregated investment data

The methodology for reporting results against the UK’s ICF Key Performance Indicator 12 (KPI 12) on mobilising private investment did not allow for the full set of programme results to be counted in ICF reporting for most of the programme cycle. The KPI 12 approach to defining causality required public funds to be co-invested in commercial transactions and so effectively excluded results achieved through preparatory grant funding and technical assistance interventions put in place to prepare commercial investments.

Over time, this methodology – and underlying OECD guidance – evolved to recognise the important role that technical assistance plays in mobilising private finance. Revisions to the KPI 12 methodology, introduced in the final year of the programme, mean that future ICF KPI reporting will better capture the impact of technical assistance programmes like P4F. Recognition of the importance of technical assistance aligns strongly with P4F experience in delivery, where the early stage and risky nature of many potential businesses operating in the sector means that preparatory support is essential to creating investable projects and mobilising investment.

When the updated ICF KPI 12 methodology is applied retroactively, eligible results from the programme generated from 2015-24 would be £804m in mobilised investment. This retroactive reporting has not been included in the ICF KPI results reporting to maintain methodological consistency in past years, but a greater share of results under Phase 2 will be included in future reporting.

Only results corresponding approximately with what was categorised as supply chain finance (mobilisation of revenue through supply chains) in P4F reporting remains outside the scope of the revised ICF KPI 12 methodology. Supply chain finance is still critical in the specific context in which the programme operates and will remain an important results area to target in Phase 2. The market signals generated through supply chains are vital to incentivise sustainable practices in production landscapes and drive the transformational change which the programme seeks to achieve. Investment and offtake agreements set up around supply chains also provide the principal source of revenue for partner businesses working to scale-up sustainable practices and are key to their ongoing viability.

The programme’s success in mobilising investment and surpassing Outcome level targets was achieved due to a high degree of Effectiveness in programme interventions, and the rate at which outputs were transformed into desired outcomes and impacts. IFSLU worked to shift private sector incentives and practices, and catalyse investment in forests and sustainable land use. Changing business-as-usual practice in land use is challenging. The programme theory of change focused on shifting private sector incentives through a complementary set of interventions comprising demand-side measures; enabling conditions; partnerships and investments; and leadership, collaboration, learning and partnerships. P4F worked across this set of interventions to catalyse action, accelerate replication and drive the scaling-up of successful sustainable business models. The programme offer of grant funding and technical expertise, set around well-evidenced strategies and portfolios, provided an effective means to shape and influence private sector incentives and practices.

A strong focus on Equity sits alongside the core elements of the theory of change and is material to the success of the programme. Companies operating in remote landscapes depend on good relations with local communities to retain their licence to operate. Often, production models linked to global supply chains depend heavily on smallholder farmers. Implementing measures to build resilience and sustainability in production requires farmers’ active participation, and the programme worked through these supply chain and market relationships to deliver livelihood and income benefits which incentivise good practice and forest protection and restoration. Overall, the programme reached 327,000 direct beneficiaries, mainly small farmers and local communities in remote forest landscapes. Beyond direct beneficiaries, there is potential to reach many more people indirectly through wider adoption of practices that place a strong emphasis on equity as companies work to mitigate the impact of their operations on climate and nature, and look for new and sustainable business opportunities that protect and restore forests.

A commonly used metric for the Cost-Effectiveness of ICF interventions is the aggregate rates for cost per tonne of CO2e abatement. Partnerships for Forests reported results for ICF TA KPI 5, which measures the emissions reduced or avoided which have been supported by ICF technical assistance, but not directly attributed to ICF funding. P4F reporting shows that from 2016-24 programme interventions contributed to reduced or avoided emissions equivalent to 86.9MtCO2e, with total impact projected to reach 161.3MtCO2e on a risk-adjusted basis by 2044, accounting for an estimated 20-year horizon for investments supported through the programme. This implies an HMG carbon abatement cost of £1.38/tCO2e for interventions within the programme lifetime, compared to an estimate of £5.07/tCO2e in the programme business case, published in 2014.
[note] This cost estimate references results achieved through the Partnerships for Forests component of the programme, with the estimated HMG carbon abatement cost calculated by dividing programme funding to P4F (£120m) by the estimated volume of reduced or avoided emissions during the programme lifetime (86.9MtCO2e).

A strong approach to Economy helped to drive these results. Delivering the programme required specialised expertise that blended development impact and private sector engagement skills, applied in the forests and agriculture sector and with specialised regional and market knowledge. Engaging this expertise was one of the main cost drivers, and this was provided through the programme and by third parties. Costs relating to the former were managed through an output-based contract; and costs for the latter managed through competitive procurement, negotiation of rates, and sourcing of expertise in local, rather than international markets. Overall results achieved justify these costs.

These aggregate inputs were converted into desired outputs with a high degree of Efficiency. Many output indicators exceeded targets and linked strongly to outcome level impacts. Efficiency was further enhanced through match funding, which helped to cement a high degree of partner ownership and commitment, and ensure that costs and risks were shared fairly between the programme and the partners. Under the match funding policy, P4F grantees were encouraged to match at least 25% of project costs. Partner funding commitments surpassed expectations and at the end of the programme match funding had met 41% of project costs, or a ratio of 1:0.69. This means that grantees and their partners are contributing £0.69 for every £1 provided by the UK government through P4F, equivalent to a total of £39.4m due across the lifetime of the programme.

A focus on additionality further strengthened the value for money framework. Each project considered for support was reviewed against additionality criteria. Additionality was defined as the ‘net positive difference that is expected to result from a P4F supported partnership. The extent to which activities (and associated results) are larger in scale, at a higher quality, take place quicker, take place at a different location, or take place at all as a result of a P4F intervention’. Evidence to support additionality was documented for each partnership and broader analysis of this data used to help to improve the design and targeting of assistance more effectively.

Lessons identified
The programme demonstrated that a clear focus on using ODA to mobilise private finance offers strong value for money. Lessons were also identified around the important role that technical assistance interventions play in mobilising investment and generating enhanced value for money. A monitoring framework and consistent use of practical and effective indicators allowed for very close tracking and reporting of impact and provided an enhanced understanding of how to maximise results and value for money over the lifetime of the programme.

Challenges in reporting programme impacts against ICF KPIs meant that the full impact of the programme was not captured in headline ICF KPI 12 results. Early versions of the KPI 12 methodology did not reflect the essential need for technical assistance to help projects reach the point at which they become investable. Programme learning demonstrated that this was particularly important in immature, risky and relatively poorly understood markets like sustainable land use and nature investments. Over time, this learning contributed to revision of the KPI methodology, ensuring that results from technical assistance interventions will be better reflected in future reporting.

E: Risk

Overview of programme risk
The operating context in the forest sector is relatively high risk, with activities taking place in remote regions, where weak governance, contested resources, poor infrastructure, challenging environmental and climatic conditions, and high costs create a difficult operating environment, with enhanced risks around conflict, safeguarding, delivery and associated reputational issues.

Good risk management systems helped to ensure that risks within 98 partnerships and 200 associated grants were well managed throughout the lifetime of the programme. This is a considerable achievement which was central to building trust and confidence in the approach taken by P4F, delivering results, securing extension and scale-up, and retaining a licence to operate over a period of 8.5 years.

Risk categories which required continuous management oversight included risks associated with programme delivery and meeting results targets; provision of support to incubate start-up businesses and the fair sharing of associated risks; and political and reputational risks associated with supporting private sector-led innovation. Management oversight was focused on ensuring the programme maintained the right balance between innovation, delivery of results and risk management, and holding the tension between these objectives.

This provides many lessons in risk management that will carry over into Phase 2. Key Phase 1 delivery risks that will remain central to risk management in Phase 2 include delivery risks relating to the political economy and operating environment for forest and land use investments in developing countries. These can be mitigated through building a broad portfolio of partnerships, encompassing different types of businesses, commodity value chains, countries and regions; as well as through good due diligence and partnership management processes within the portfolio.

There were also reputational risks associated with private sector collaboration which required continuous monitoring and mitigation, particularly around the need to avoid providing an excessive subsidy for private sector activity, ensuring the right balance in sharing of risk and up-front costs, and demonstrating additional value arising from the use of public funds.

Systems were designed to ensure that fiduciary risk remained low, with funds disbursed through an external service provider applying strong due diligence and financial management systems and a zero-tolerance policy for fraud.

Risk mitigation included due diligence; the integration of gender and social equity considerations into appraisal and decision-making, to ensure that partnerships deliver strong development benefits; and a programme focus on developing shared value through public-private-people partnerships. Realising shared value is a vital element of sustainable business models, which retain a social licence to operate, in remote, rural regions of developing countries.

Safeguarding was a continuous focus of risk management. This was managed through due diligence procedures which encompassed a focus on safeguarding, including partner organisations’ internal policies, such as codes of conduct, grievance mechanisms and whistle-blower policies, questions on contractual equity (such as contracts between companies and farmers), as well as safety, security and duty of care.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Performance of partnerships
Partnerships for Forests was managed by a consortium led by Palladium, working with Systemiq and Efeca in sub-contracting arrangements. The consortium worked effectively to deliver the programme, offering a blend of development expertise and sustainable business advisory services. Palladium and Systemiq managed regional teams, which were responsible for identifying partnerships with the potential to contribute to programme outcomes. Efeca’s role in the consortium was as provider of specialised advice on demand-side policies.

An effective and collaborative working relationship between FCDO and the Partnerships for Forests management team was an important factor behind the programme’s strong performance, assisted by regular strategy workshops, management meetings, joint outreach and engagement with partners, field visits, and collaboration around key events.

Implementation was supported through strong programme management provided by Palladium. Grant management, due diligence, financial management and risk management were delivered to consistently high standards. Narrative and financial reporting was submitted in a timely fashion and to high quality, including a final narrative report submitted in April 2024.

Contract KPIs were met consistently and almost without exception throughout the lifetime of the contract. Financial forecasting improved as the programme portfolio matured, assisted by greater understanding of the portfolio dynamics which affect the rate of spending. This lead through to programme closure on schedule and on budget in April 2024, with a final underspend of £18.7k, representing 0% variance against a total budget of £120m over an eight-year period. At programme close, grant funding of £57.1m has been drawn down through Partnerships for Forests and £62.8m had been invoiced for programme milestones and expenses. This is an excellent outcome reflecting the diligent work undertaken by the programme management team on financial forecasting, budgeting and management to close the programme efficiently.

A final annual audit of P4F was conducted by an independent auditor at the end of the programme, covering the period 01 April 2022 to 30 April 2024. Other programme interventions follow separate auditing cycles, in line with their respective grant agreements. This final report ensures that the entire delivery of P4F has been subjected to an external audit. Audits were undertaken annually except for the final report, which was held back to cover the final full year of operations and additional months of no-cost extension. The audit provided assurance of compliance.

Funding to the Tropical Forest Alliance was blended with other donor money to deliver an agreed work plan. The alliance worked through a significant leadership change in 2023, with impacts running through into 2024. Improved governance is gradually being put in place to guide the activities, but further work to improve engagement of the TFA partner network, fill vacancies in the team, and improve the flow of information is still required. A new phase of funding, drawn from the IFSLU2 programme budget, was agreed with Norway and the Netherlands as co-donors and will be reported on in the IFSLU2 annual review.

Support to the Food and Land Use Coalition (FOLU) was provided through a grant to the World Resources Institute, blended with funding from other donors, notably Norway as the anchor donor in the partnership. Recommendations emerging from FOLU’s flagship global report led towards the establishment of the Just Rural Transition initiative and efforts to strengthen action to repurpose agricultural subsidies. The JRT Secretariat was managed through an accountable grant to Meridian Institute, with the UK managing the grant according to standard grant management practices. Support to countries for technical support to repurpose agricultural subsidies was delivered through the World Bank’s Food Systems 2030 Trust Fund, with the UK taking a seat on the partnership committee to steer this work. All of these partnerships functioned effectively during the course of work undertaken through the programme.

Programme-level approach to monitoring and evaluation
An effective monitoring framework was implemented across all P4F activities, providing management information to inform the development of regional strategies and portfolios, support adaptive management, and learning.

To complement in-programme monitoring, FCDO and the programme Senior Management Team held rolling weekly portfolio review meetings with regional teams (equivalent to one monthly meeting per region) to maintain an overview of activities, provide steers and input to portfolio development, manage risks and address challenges. Monthly meetings were also complemented by quarterly SMT regional visits to teams, partners and field sites.

An Independent Evaluation and Learning Manager also operated from 2015-22. Evaluation products included reviews of business incubation processes, KPI methodologies, baseline and thematic studies of elements of the portfolio. The continuous approach added considerable value, supporting learning and evaluation over time, comparing situations at the start and ends of the programme in a consistent way, accompanying the programme through its delivery cycle and supporting adaptive management over this time.

The final evaluation product was an assessment of evidence and potential for transformational change in a selection of landscapes where the programme operates. The differing contexts in which the programme operates, and the diversity of findings, made it challenging to draw broad conclusions from the assessment of transformational change. However, it clearly identified evidence of impact across all pathways, supporting the theory of change (Figure 7).

For example, in the cocoa sector in West Africa, evidence of transformational change was relatively strong, as multiple actors begin to collaborate to address the challenges of resilience, productivity and sustainability which threaten the sector. P4F support has focused mainly on developing the landscape governance system. The in-depth study of this cluster notes that it has strong transformative potential, with impact on issues including increased cocoa production, agroforestry pilots and cocoa rehabilitation, cocoa farmer income diversification; organising smallholder cocoa farmers in community and landscape governance; development of the national Ghana Climate-Smart Cocoa Standard; development of a service delivery model which provides a bundle of services to smallholders; increased stakeholder collaboration and the development of a landscape governance system; and the development of a cocoa management model.

Figure 7: Independent assessment of theory of change and evidence in associated impact pathways

Date of last narrative financial report	April 2024	Date of last audited annual statement	November 2024