## Annual Review

Title: Innovative Ventures and Technologies for Development (INVENT)
Programme Value £ (full life): £39.9m		Review date: July 2024
Programme Code : 202927	AMP start date: / 04.09.2013	AMP end date: / 31.03.2027

Summary of Programme Performance

Year	13/14	14/15	15/16	16/17	17/18	18/19	19/20	20/21	21/22	22/23	23/24
Overall Score	B	A	A	B	A	B	A	A	A	B	A
Risk Rating	Moderate	Major	Major	Moderate	Moderate	Major	Major	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3881771.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/56629110.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

INVENT India aims to address the lack of private sector investments in technological and/or process innovations in the low-income states of India. The objective of INVENT Global was to support transfer of India’s affordable innovations to Africa and South Asia for development impact. The objectives of INVENT India align with India-UK comprehensive strategic partnership and future relations which talks about “Exploring partnerships with joint investment to enable the growth of technology-enabled innovative businesses and increasing the number of start-ups and MSMEs growing and scaling-up internationally, for example in relation to climate and the environment, med tech devices, industrial biotech and agriculture, and sustainable development, helping to achieve the Global Goals by 2030”.

INVENT is now in the last quarter of its programme life cycle. It was approved in August 2013 to invest up to £38 million to support technological and business innovations for the benefit of the poor in the low-income states of India and in developing countries in Africa and South Asia. The allocation was subsequently increased to £39.9m. The programme has two elements; INVENT India and INVENT Global. The allocation of INVENT India is £27 million and that of INVENT Global is £12.9 million.

This is the eleventh annual review of the programme.

INVENT India (£27m) has two main components:

1. TA component of £9m: Of this £8m was allocated for an incubation programme to support capacity building of incubators and creation of a pipeline of investible projects in Low Income States of India. Delivered through the Technology Development Board, this programme provided capital to over 160 early-stage enterprises. This intervention was completed in 2019. About £3m of this allocation remained unspent. Further, an amount of £950k has been used towards compliance costs.
2. An investment component (£18m) that provides equity support to enterprises implementing technological or process innovations. This is being implemented through three Alternate Investment Funds (investment vehicles regulated by India’s Securities and Exchange Board of India). These are:
  1. Tara Fund IV (TARA) (committed £9m- spent £7.91m)
  2. Rajasthan Venture Capital Fund (RVCF) (committed £5m – spent £4.29m) and
  3. The Banyan Tree Fund (BT) (committed £4m – spent £2.03m)

INVENT Global £12.9m

Global invent was implemented through different approaches – A grand challenge to support Indian innovations which are interested in transfer to new geographies (called the Millennium Alliance – implemented by FICCI). This supported 53 enterprises and benefitted Afghanistan, Nepal, Bangladesh, Sri Lanka, Kenya, Uganda, Ethiopia, Tanzania, Rwanda, Burkina Faso, and Malawi. A grand challenge programme in Tuberculosis control implemented by IKP which supported three enterprises and benefitted Afghanistan, Uganda, Myanmar.

INVENT global was closed last year due to lack of progress in the only operational component. No further progress is reported for this Annual Review.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

During the period under review, only one output under INVENT India’s investment component (output 2 i.e. Supporting the scale up of innovative enterprises in low-income states) is operational with 100% weightage. The investments in this programme are being managed by three fund managers. Two of them (RVCF and TARA) are in an exit stage where they are returning back invested capital. They are proactively looking for opportunities to exit from the portfolio companies. RVCF has in the review period managed a good exit from one of the investments and are actively working with other investee companies for exit. TARA recently shared a secondary sale proposal, for the sale of entire portfolio of investments, which is under consideration of investors. BT, invested through UK India Development Cooperation Fund (UKIDCF), was initially slow in understanding INVENT’s investment thesis and hence slow in investing. During the period under review, they made progress and UKIDCF agreed two investments. UKIDCF’s investment period for BTIII closed in March 2024 and will not be committing towards any new investments. Follow-on investments, if any, in existing portfolio companies will be to continue to protect the investments and to help grow the innovative companies. BT made a successful exit from one of its earlier investments.

Of the three indicators for this output – expectation was met on one (number of investments made); moderately missed on one (Numbers of exits) and exceeded on one (return proceeds from exits). Based on this progress, it is assessed that the project has met expectations for the period under review, thus scored an A.

Output 1 and Output 3 have been closed in earlier years. The progress made against indicators of these two outputs is captured under the output section.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons Learnt INVENT India:

1. Differences with one of the fund managers, on aligning investments with INVENT’s strategy showed the need for watertight contracts to address such situations. It takes up a lot of staff time to manage such differences. Lesson is to ensure a clear agreement on investment strategies upfront and to have systems in place to ensure the fund manager stays aligned with project objectives all through. Shared values and principles matter and it is better not to proceed with a partnership in case of doubt.
2. Exits from investments depend on market conditions and growth of companies. These involve long drawn negotiations with new investors who are willing to buy the fund’s stakes in investee companies. This has proven to take longer than anticipated for both TARA and RVCF, though the one exit by BT fund was achieved earlier than expected. Proper follow-up with fund managers helps in expediting the process.
3. 7 of the total 32 investments made under the programme have been written off. Risk of failures in innovative programmes is expected and should be highlighted while designing the investment strategy to strike the right balance with capital preservation expectation of the instrument. There will be cases of companies failing to grow and scale up.
Lessons Learnt INVENT Global:
It has proven to be difficult to recover unspent money (£523,095) and unevidenced expenditure (£29,246) from a project partner. The team remains in close contact with them for the refund of unspent money though funds pertaining to unevidenced expenditure have now been refunded. For the refund of the unspent money, the partner will need to seek requisite permissions from Ministry of Home Affairs under relevant FCRA (Foreign Contributions Regulation Act) provisions. The partner has initiated this and is awaiting a response from the Ministry.
Recommendations for next year:
1. Feed in lessons from this programme to strengthen the investment contracts.
2. Continue the rigorous follow up on priority for the recovery of the unspent funds (~ £ 523 k) from a project partner under INVENT Global.
3. Closely monitor and support exit plans of TARA and RVCF.
4. Closely monitor BT investments through UKIDCF for any follow-on actions needed to support their growth trajectory.
5. The incubation programme was closed in October 2019. GoI carried out an evaluation at the close. Consider a follow up evaluation to know the extent to which the intervention made a difference and whether the supported companies were able to sustain post closure.

Progress against recommendations of last AR
Propose an extension to the programme by four years (i.e covering the duration of next SR) to allow for planned and effective exit from the investees of TARA, RVCF and BT. Update the log-frame and milestones suitably [Action: PRO by November 2023]	The project end date has been extended to March 2027 to allow for planned exit from investments by all three funds. No new investments are envisaged during this extension (except where there is need for follow on funding). Log frame and milestones have been updated.
Consider evaluation of the Development Capital portfolio including RVCF and TARA and apply the learnings from the exited investments for the existing investments and future programmes. (Action: SRO to coordinate with Results Advisor)	The bid for evaluation of India DevCap portfolio was not successful. However, learnings have helped review of the terms of our investment contract.
Continuous engagement with Fund Managers for progress on investments and exits. Actively engage with BT Fund Manager to ensure their pipeline aligns with INVENT’s development mandate. (Action: SRO)	Significant efforts were put in to align BT’s investment pipeline with INVENT’s development mandate. This resulted in the acceptance of two proposals and one being excused. / Follow up with both TARA and RVCF has resulted in some progress e.g. TARA has proposed a secondary sale of its active portfolio. RVCF has exited from one portfolio company and has shared a structured plan for exit from other portfolio companies.
Proactively pursue opportunities for visit of senior stakeholders and to communicate success stories. (Action: SRO/PRO)	Although the team visited many investees under the three funds, there were no opportunities for a visit by a senior stakeholder during the period under review.
XHMG collaboration to ensure coherence and synergy with country plan priorities and with other programmes. (Action: SRO/PRO)	INVENT’s investment objectives are coherent and aligned with roadmap 2030 and country plan priorities. This is also a continuous action and feeds into the KPIs on British Investment Partnership and Science, Innovation and Tech as relevant.
Feed in the lessons from INVENT into FCDO Private Sector Team at HQ to strengthen the Operations Guidance on Fraud and Corruption in programmes using the Financial Transactions instrument [Action: PRO by Dec 2023]	A guidance note for tackling fraud in FT programme has been developed in consultation with India FLO, Private Sector and Capital Markets Division (PSCMD) and Control and Assurance Unit.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Initial Theory of Change

Inputs
Outputs
Outcome
Impact
UK funding

Output1: Identify, pilot and nurture inclusive innovations in Low Income States (LIS) & Low-Income Countries (LICs)
- Pilot and test new solutions in LICs
- Supporting startups graduate from pre-incubation to incubation in LIS
- Support start-ups graduate from incubation support to first round of investments in LIS
Output2: Support the scale up of innovative enterprises in LIS
- Make patient risk capital investments.
- Strengthening ecosystem for inclusive innovations & impact investments
Output3: Support Knowledge sharing on inclusive innovations between India and LICs
Collect evidence base, undertake impact assessment
Increased technological & entrepreneurial innovative solutions that benefit the poor in LIS and LIC

- Scaled up pilots
- Improved access to affordable and efficient basic services & products in India and in LICs
- Contribution to global knowledge on transfer of innovative solutions from India to LICs
- Job creation
- Securing additional finance
Improved economic opportunities and quality of life for poor in LIS in India & LICs

- Increased impact Investments in LIS & LICs
- Increased Local multiplier effect in the economy in LIS & LICs
Activities
Support Grant Challenge funds & Incubators

Equity investments in enterprises

Support knowledge sharing platforms
Changes made:

1. Output 3 and output 1 have been closed, post completion of activities.
2. Output 2 is operational to allow for exit from investments. The project period was extended to March 2027.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Progress against outcome and impact indicators is as below:

Outcome statement: Increased technological & entrepreneurial innovative solutions that benefit the poor in Low Income States and Low-Income Countries
Outcome Indicator	Target	Achievement as of July 2023			Milestone July 24	Achievement July 24
		Incubation project	Investments programme	Total	Covering Investment programme
No. of piloted projects that are scaled up to become viable businesses in Low-income states of India	80	50	28	78	25	25
Jobs supported
Men		5,268	4,247	9,515		4,586
Women		4,582	1,277	5,859		1,418
PwD		72	5	77		5
Total	12,500	9,922	5,529	15,451	5,700	6,009
Finance raised (At fund and investee levels)	INR 10 billion (~£100 m)	INR 16.52 billion (~£165.2m)	INR 9.74 billion (~£97.4m)	INR 26.26 billion (~£262.6m)	INR 10 billion (~£100m)	INR 11.6 billion £110m
Numbers of beneficiaries (suppliers and customers) reached through supported companies	10m	13.77m	8.63m	22.4m	9m	8.29m

Notes:
(i) Targets for outcome indicators are based on proposals from an independent study but moderated by the programme team based on its own assessment.
(ii) Break up of 78 projects that became viable businesses: 19 (RVCF) + 8 (Tara) + 1 (BT)+ 50 (Incubation pilot). During the period under review the achievement has reduced by 3 as these investments were written off due to closure of company operations.
(iii) Additional Jobs created are numbers of direct jobs created by enterprises supported under both incubation and investment programmes.
(iv) Additional Finance secured is in terms of Equity / Debt or any other sources of funds raised by investee companies and start-ups supported under Incubation project. Exceptional fund raising by two start-ups supported under incubation during the previous AR periods have helped surpass the target.
(v) Numbers of lives touched is the number of people reached through the entire value chain of investee / supported companies. Major contribution to this number comes from the continuing impact of incubation project which otherwise closed in October 2019.

INVENT India’s operational component has delivered the targeted development impact. The incubation component was closed in 2019 and the investment programme continues to secure financial returns for the UK and has generated lessons which are helpful for the wider development capital portfolio. It is essential for INVENT India to continue its progress to its logical closure by completing exits at the most opportune time.

The 3 funds under the investment component have completed their investment period. The funds are now in value-addition phase for their respective portfolio of investments and planning the exit from each of these investments. It is prudent to continue this program to receive the financial returns of the investments while continuing to deliver the development impact as intended. Whilst the market plays an important role in determining exits, a planned and proactive approach can help protect the value of our investments and help manage the risks.

INVENT India is aligned with the priorities identified in the roadmap 2030 for India-UK future relationship. It supports several xHMG priorities – Climate & Clean Energy, Technology, and Inclusivity -gender and Disability inclusion, inclusion of people from low-income states and low-income groups.

INVENT Global: The Global element of INVENT was terminated in 2022. It no longer contributes to the milestones and targets. Progress achieved against outcome indicators till 2022 is as follows: -

Outcome Indicator	Target by End of Programme	Achievement as of July 2022
No. of piloted projects that are scaled up to become viable businesses in low-income countries	12	8
Additional individuals/households obtaining significantly improved access to affordable and efficient basic services and products in agreed priority sectors in LICs	250,000	246,500

Invent Global component has been closed. Global Innovation Partnership programme (GIP), the successor to Invent Global has started implementation and is engaged in pre-procurement activities. GIP builds on the lessons learnt from Invent Global.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Outputs 1 and 3 have been closed in earlier years.

For records:
Output 1 i.e. Identify, pilot and nurture inclusive innovations in LIS & LICs was closed last year with following results:

Indicator(s)	Progress
Pilot and test new solutions in LICs (approaches or technologies) to tackle global/local problems in key sectors	Achieved 30 against a cumulative target of 37.
Numbers of Business ideas/ early-stage start-ups graduating from Pre-incubation support to receive Incubation/ Acceleration support in LIS	Total of 215 (161 via Technology Development Board and 54 via Start-up Wave) were supported (Target of 150.)
No. of Business ideas/ early-stage start-ups graduating from incubation support to receive first round of investments in LIS	Overall, 50 supported start-ups received the defined follow-on funding (Target:50)

Output 3 Support Knowledge sharing on inclusive innovations between India and low-income countries (global component) two years back with following results: -

Indicator(s)	Progress
Evaluation studies/ Operational Research Studies undertaken.	An evaluation of the global component was carried out which is available on FCDO’s devtracker.
New Partnerships for replication, / adaption and adoption of inclusive / innovations developed in developing countries	A total of 7 new partnerships were formed.
No. of innovators targeting BoP, / receiving business development / services (BDS) and technical / assistance in developing countries	BDS was provided to 10 African enterprises through Sankalp Africa

Progress against the operational output 2 is as follows: -

Output Title	Support the scale up of innovative enterprises in low-income states of India
Output number:		2	Output Score:	A
Impact weighting (%):		100%	Weighting revised since last AR.	Yes, Up

Indicator(s)	Milestone(s) for this review	Progress
Number of new Investments	2	2; Met expectations.
Number of exits	3	2, Moderately did not meet expectations
Return proceeds from exits	£1m	£2.3 m; Exceeded expectations
UK financial inputs
Cumulative UK contributions	£14m	£14.5m Moderately exceeded expectations

1. Given the progress, the output is assessed to have met expectations for the review period (score A).
2. Investments:

  1. The milestone for two fresh investments for this review period was set at the last AR.
  2. INVENT makes investments in innovative enterprises through three funds. Of these, two i.e TARA and RVCF are direct investments while Banyan Tree Fund III is through the UKIDCF platform.
  3. TARA and RVCF completed their investments before this review period investing in 10 and 19 enterprises respectively.
  4. During the period BT presented three investment proposals. UKIDCF excused from one (due to lack of development impact) and committed to the other two. Although BT has not completed its investment programme, UKIDCF’s commitment period has ended in March 2024. With the two new investments, UKIDCF had a portfolio of three investments through BT, of which BT has exited from one. Going forward UKIDCF will only be paying for management fees or for follow on funding, if there is any.
  5. Overall INVENT made 32 investments through the three funds.

Exits & Returns:

  1. During the period under review RVCF exited from one of its investments in a Fintech company that provides innovative digital payments solution to banks, financial institutions, and merchants. The company has built a multi-layered solution for a cashless economy. RVCF exited at a Multiple of 12.8x on invested capital yielding an IRR of 197% on the investment. Listed on the National Stock Exchange’s SME market, this company provided jobs to over 260 persons (~17% women) and reached over 3 million people (~25% women) with the services it provides.
  2. BT exited from one of its investments at a multiple of 1.8x yielding an IRR of 24%. This investment catered to customers (mostly women) in tier 2 / tier 3 cities. The company’s strong ESG and regulatory compliance framework developed after BT’s investment allowed it to sustain six month long multiple agency diligence carried out by the pharmaceutical behemoth that took over this business.
  3. Before this review period TARA Fund IV had exited from one and written down four of its investments. It has proposed a secondary sale of its balance portfolio of five active companies. This is being analysed by the investors. A decision will be made in the coming months.
  4. RVCF has partly/ fully exited from 4 investments before this review period and has written down one. It now has an active portfolio of 15 companies.
  5. Gross returns during the review period at £2.3m exceed the milestone set for this indicator at the last review. Total gross reflows (capital and gains) are c£5.3m as of the date of this AR.
The output weightage changed to 100% as other two outputs of the project now stand closed. The milestones for the output indicators were set at the last AR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Refer to the summary sections for progress against recommendations from previous AR, Lessons learnt and Recommendations for next year.

Milestones for next year:
Number of Exits – 3
Return Proceeds – £0.5 m.

D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

Economy: The key cost drivers of this investment programme are (i) Management Fees and (ii) Carry (i.e.) the share of the Fund Manager in the profits from the investments. The average negotiated Management fees is 1.5 - 2% pa on committed / invested amounts. Carry is directly related to profitability incentivizing the fund manager to maximize financial returns of investors, while delivering the strategic development objectives. The management fees and Carry compare well with the industry average of funds of similar nature and size. To ensure responsible and development-oriented investment, FCDO has linked a part of the management fees to Fund Managers’ performance in ensuring environmental, social and government (ESG) related progress of the investees. An ESG assessment of Tara and RVCF investees indicates moderate to substantial progress against ESG benchmarks.

Efficiency: INVENT has been able to deliver on its main objective of supporting private sector innovations using relatively moderate allocation. It has so far disbursed about £14.5m for investments supporting about 32 small and medium enterprises, which is about £453k per company. The incubation and investment programmes together have made significant contributions in strengthening the ecosystem for innovating enterprises.

Effectiveness: INVENT has achieved the milestones on job creation, additional finance leveraged and numbers of people benefiting from basic service provisions through investee companies. Overall, the portfolio is in positive territory in terms of valuations. (See output and performance of project partner sections for details). The incubation project provided a very useful pipeline of investible projects. For example, RVCF has invested in Krimanshi Technologies and Fabriclore Pvt Ltd that were supported under the incubation programme.

In terms of Equity the project has a pro-poor approach as its focus is on supporting investees in Low Income States of India. It has done better than national average in providing jobs for women and people with disabilities.

Assessment of whether the programme continues to represent value for money.

INVENT India: The project has delivered the outcome targets. Planned investments in innovative enterprises have been completed. No new capital assets will be created. Going forward, the programme focus will be on planning and execution of exits from portfolio investments. Exit planning is linked to market conditions and is managed by the investment committee of respective funds. SEBI rules and guidelines allow for an extension of up to 2 years for funds to manage exits. Old funds are allowed to migrate to AIF structures with additional timeline equivalent to original timelines. Fund managers will use any agreed extension to work out profitable exits. The valuation of the three funds broadly indicates that, overall, the original value of investments will be protected. The programme should remain open to allow completion of exits from investments. UKIDCF completed its investments through BT during the review period. The programme end date has been extended to March 27 to facilitate exits in order for HMG to receive back our invested funds. The end date for TARA is extended to January 26. RVCF end date is December 24. They may seek an extension of the fund end date by two years to complete exits. Going forward, funding will only be needed to pay for management fees and for any follow-on support that the new investees of BT fund may need.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk of the programme is ‘Moderate’.

INVENT India:
The overall risk of the India component has fluctuated during the review period. A case of alleged financial impropriety in one of the funds, capacity issues, conflict of opinion between FCDO and fund manager leading to slowdown of investments, have all been resolved during the review period. The risk was ‘Major’ and brought down to ‘Moderate’ after the resolution of the above issues. The programme team will continue to monitor the risks closely in view of the issues arisen but covered in the review period. The team will also monitor closely the exits from two of its funds as the risk over the next review periods could be delay in exits.

Key risks and mitigation measures in place are highlighted in the table below:

Risk Description	Mitigation Strategy	Residual Risk
Risk of exits within the Fund tenure leading to direct holding by UK and loss of UK Capital	FCDO team to actively engage with fund managers to keep a close view on exit plan and progress and seek legal opinion where required to ensure we are able to explore feasible options.	Major
Conflict of opinion leading to slowdown of Investments through Banyan Tree Fund III and could lead to litigation.	This risk has been resolved and closed during the review period.	Major
Supported investees do not perform well commercially leading to loss of capital.	Jointly agreed and monitored investment strategy that balance development impact and financial returns	Major
Cancellation of RDEL budgets leading to unavailability of funds for policy support for the investment component and inability to carry out evaluations.	Collaborate with XHMG teams and use common pool of funds to support evaluations as possible.	Moderate
HERA issues leading to default in payments and breach of legal agreements.	Escalating promptly if there are any issues.	Moderate
Reputational risks related to investments (India) including financial frauds, safeguarding and ESG related.	Careful examination of investments by the programme team / Investment Committee / development framework before every approval, continuous monitoring and timely action in case of any incident.	Moderate
Slowdown of investments and exits due to attrition /other operational issues in partner entities	Closely work with partners and recruit replacement / identify a new partner in a timely manner. All three funds are stable currently.	Moderate
Fund managers diverting money for other purposes	Quarterly management reports and annual audited statement of accounts are mandatory from partners. Regular touch with investee companies. Hurdle rate and performance linked incentives for Fund Managers and for their employees.	Moderate

INVENT Global:

Default by partners in returning balance funds after closure of Global component.	Escalated the issue to the senior most leadership at FCDO and at the partner level. Continuous follow up ongoing. / To consider involving the High Commissioner if required.	Moderate

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

TARA Fund IV:

The fund is managed by Kois India Investment Advisers Private Limited. They took over from IL&FS Investment Manager Ltd (IIML) in 2021. Kois has tried its best to make the transition work for the investors through value protection for investees thereby arresting the financial losses, that could have arisen. One exit in the past yielded positive returns. Post that Kois has been proactive in supporting the growth of balance portfolio of investee companies. Despite their best-efforts investments in two companies had to be written down. Efforts to exit from the other five active investments have not been successful as the companies were not able to scale to investible levels. As a result, there have been no exits or investments during the review period. They have now proposed secondary sale of its balance 5 investments. FCDO and other investors are reviewing and exploring options.

TARA’s current investments have created 1689 net direct jobs (of which 639 are women and 3 PwD) and 383 indirect jobs (of which 79 women). Eight of the investee companies have been able to raise follow on funding in equity/debt or both. Total follow-on funding raised is about INR 7,814 m (~£78.14mn). The Fund has achieved a good equity as women constitute about 38% of direct jobs offered by its investees, which is higher than the national average. The ESG score for TARA investees has improved from an average of 1.59 at Due Diligence stage to 2.86 at Mid Term. As of December 2023, the reported value of balance units in TARA fund was INR 819 mn (against its book value of INR 614 mn) (unaudited valuation).

Secondary benefits are being generated for UK companies through TARA Investees. Two examples are Panacea, which imports critical equipment for its imaging product from E2V Teledyne of UK and Lilac Insights, which has accreditation from Fetal Medicine Foundation (FMF) and gets it audited by United Kingdom National External Quality Assurance Services (UKNEQAS). Disprz (Heuristix) has a presence in UK to provide HR solutions.

Date of last narrative financial report	March 2024	Date of last audited annual statement	March 2023

RVCF III:
RVCF is manged by Rajasthan Asset Management Company (RAMC) which is promoted by the Rajasthan government. The fund has invested in 19 companies, partly exited from 2 and fully exited from 2. The fund manager has been proactive in completing its investments. Exits during the period have been slower than expected. Update provided by the fund manager indicates regular and close monitoring of investee companies by the Fund Manager. They have shared required information regularly and supported visits as and when needed. They have been diligent in complying with regulatory and statutory requirements.

Four exits have been made so far, one during this review period giving us a return of 12.8 x. All exits have made commercial gains. As of Review date supported companies have been able to raise about INR 4,099 million(~£41m) by way of Equity /Debt/Others for their operations.

66% of RVCF portfolio companies have been started by first time entrepreneurs. 32% have women founders / promoters. 59% have RVCF as their first institutional investor. Fund’s investments have created 3,677 direct jobs (of which 681 women and 2 PwD); 19,123 indirect jobs (of which 1,243 women and 17 PwD). The fund’s equity performance continues to be good with women constituting about 20% of the direct jobs offered by the investees. This is significant given that most of these companies operate in the low-income state of Rajasthan where women participation in workforce is very minimal. The ESG score of investee companies has improved from an average of 1.05 at Due Diligence stage to 1.92 at Mid Term. The NAV of each unit of RVCF III as at March 2024 is INR 172,455 (face value 100,000).

Success stories of RVCF Investees

Inficold granted a patent for solar	Code Vidya promoting gender
powered cold storage	diversity

Date of last narrative financial report(s)	March 2024
Date of last audited annual statement (s)	March 2023

Banyan Tree Growth Fund III:
This investment is managed through the UKIDCF platform. UKIDCF has three investments through BT. BT has exited from one. Value of the two remaining investments is INR 46 m (~£0.46m). The investments till date have helped create 33 direct jobs, 105 indirect jobs and have provided benefits to 150,000 people. The valuation of the units as of March 24 is reported to be £0.54m

UKIDCF had strong difference of opinion with BT during the review period. This pertained to the additionality of investments proposed by the fund manager. This led to various rounds of discussions and difficult conversation but have been now resolved. We made two new investments during the review period. UKIDCF has exercised its excuse right for one of the investments proposed by the Fund Manager during the period under review. UKIDCF’s investment period in BT ended in March 2024 and will not be making any more new investments, it can still make follow-on investments in existing portfolio companies.

Date of last narrative financial report(s)	March 2024
Date of last audited annual statement (s)	March 2023

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

This Annual Review is informed by monitoring activities throughout the year and is based on information provided by Fund Managers.

Monitoring activities during the review period: -

All Funds
1. Each Fund Manager submits (1) a quarterly progress report providing an update on activities and status of their investment portfolio and (2) a valuation report of its portfolio at least once a year.
2. Programme team has discussed and obtained an assurance on management processes related to Fraud, safeguarding, personal data protection, visibility statement and risks.
RVCF III
1. Meetings with RVCF III fund Manager (for exit discussions) and with senior leadership of RIICO (anchor investor of RVCF) and visit to Future Cure and Code Vidya (RVCF investees) – October 2023
2. Meetings with RVCF fund manager on 24th April and XX July to discuss exit plans.
3. RVCF has shared media coverage of portfolio companies.

TARA Fund IV
1. Meetings with TARA IV fund Manager and visit to Lilac (TARA investee company) in April 2024.
2. Discussion with the Fund Manager for a review of their secondary sale proposal.
3. Several calls with co-contributors (LIC, SIDBI, SFPI) to gather views on TARA’s secondary sale proposal.
4. Working with co-contributors to seek independent valuation of TARA IV portfolio to help inform a decision on the secondary sale proposal.
UKIDCF/BT
Several meetings/calls with UKIDCF and BT III fund manager to ensure alignment of investments with INVENT objectives.

Evidence on progress and lessons learnt during the period are captured in other sections above.