Annual Review Template

Title: Innovative Ventures and Technologies for Development (INVENT)
Programme Value £ (full life): £39.9m		Programme Value £ (full life): £39.9m
Programme Code : 202927	Programme Code : 202927	Programme Code : 202927

Summary of Programme Performance

Year	13/14	14/15	15/16	16/17	17/18	18/19	19/20	20/21	21/22	22/23	23/24	24/25
Overall Score	B	A	A	B	A	B	A	A	A	B	A	A
Risk Rating	Moderate	Major	Major	Moderate	Moderate	Major	Major	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3881771.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/56629110.xlsx

## A. SUMMARY AND OVERVIEW

Description of programme

Approved in August 2013, the INVENT programme has consistently delivered on its mandate to catalyse inclusive growth through innovation. Now in the final quarter of its lifecycle, INVENT was designed to invest up to £38 million—later increased to £39.9 million—to support technological and business innovations benefiting underserved populations in India, Africa, and South Asia. The programme comprises two components: INVENT India (£27 million, including £18 million for investments and £9 million for technical assistance) and INVENT Global (£12.9 million), each structured to address distinct regional and developmental priorities.

INVENT is strongly aligned with the UK’s Vision 2025 and the Foreign, Commonwealth & Development Office’s (FCDO) strategic priorities, particularly in fostering inclusive economic growth and innovation-led development. INVENT India was designed to address the critical gap in private sector investment in technological and process innovations across low-income states in India. By supporting early-stage enterprises, the programme has contributed to building a more vibrant innovation ecosystem in underserved regions.

INVENT Global complemented this approach by facilitating the transfer of India’s affordable and scalable innovations to developing countries in Africa and South Asia, thereby amplifying development impact across geographies. INVENT global component was closed in 2023 due to lack of progress in its singular operational component. No further progress is reported for the component since then in this review.

These objectives are closely aligned with the UK India Comprehensive Strategic Partnership goals, which envisions deeper collaboration through joint investments to support the growth of technology-enabled innovative businesses. INVENT’s focus areas viz. climate and environment, med-tech, biotechnology, agriculture, and sustainable development contribute to the delivery of Global Goals by 2030.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This is the twelfth annual review of the programme. The current report covers the investment component (£18m) that provides equity support to enterprises implementing technological or process innovations over the last reporting year.

During the review period, only one output under INVENT India’s investment component (output 2 i.e. supporting the scale up of innovative enterprises in low-income states) is operational with 100% weightage. The investments in this programme are being implemented via three Alternate Investment Funds (AIF) (investment vehicles regulated by India’s Securities and Exchange Board of India (SEBI)). These are:

  1. Tara Fund IV (TARA) [committed £9m- spent £7.91m]
  2. Rajasthan Venture Capital Fund (RVCF) [committed £5m – spent £4.29m] and
  3. The Banyan Tree Fund III (BT) [committed £4m – spent £2.03m]
Of these funds, two i.e TARA and RVCF are direct investments while Banyan Tree Fund III is through the UKIDCF platform.

Addressing Gender and Disability:
INVENT is supports mainstreaming of disabled persons in the workforce which is a challenge in India. The efforts are helping create an inclusive environment in businesses supported under the programme and setting examples for others to follow.

While INVENT has completed making any new investments, the programme offers a strong example of how targeted innovation support can integrate gender and disability inclusion. Its experience in enabling over 6,000 women and 80 persons with disabilities to access employment in early-stage enterprises can serve as a valuable reference for future programmes aiming to build inclusive innovation ecosystems, especially in underserved regions.

Both RVCF and TARA are in the exit phase and actively pursuing strategies to return invested capital back to investors. RVCF, with a portfolio of 19 companies has successfully exited one investment during the review period. We have now received 100% of invested capital and expect to receive profits from future exits – indicative gains for HMG. The fund continues to work toward exiting the remaining 15 companies. Five of these businesses has raised funds from private markets in the reporting year, indicating successful scale up.

TARA, managing five active portfolio companies, has fully exited one and partially exited another business during the review period. To enable a complete exit by January 2028, the INVENT Task Team is engaging actively with the fund manager and other investors. This involved facilitating dialogue, aligning expectations, and navigating regulatory considerations, ultimately leading to TARA’s application to migrate from the Venture Capital Fund (VCF) regime to the Alternative Investment Fund (AIF) regime under SEBI regulations.

In addition to direct investment outcomes, TARA’s portfolio has generated Growth opportunities for the UK. For instance, Panacea – one of the investees – has trade links with a UK-based business (E2V Teledyne); another investee (Lilac Insights) has tied up with a UK based accreditation agency (Fetal Medicine Foundation) and audited by UKNEQAS. Similarly, Disprz (Heuristix) has established a presence in the UK to deliver HR solutions. The portfolio has created direct and indirect growth opportunities for both countries.

Case Study | Strategic Migration of TARA Fund to AIF regime

Background
TARA Fund was established in 2015 under SEBI’s VCF regime, with IL&FS Investment Managers (IIML), subsidiary of IL&FS (earlier known as Infrastructure Leasing & Financial Services Limited), as the fund manager for a 9-year term. However, following the financial and governance crisis at IL&FS, the fund’s Limited Partners/investors (LPs) took decisive action in 2021 to replace the fund manager with Kois India Advisors Private Limited (KOIS). In January 2024, on the request of the fund manager, the investors extended the fund’s term by two years to allow time for value recovery.

Challenges
- Legacy Issues: The IL&FS crisis and subsequent reputational damage created uncertainty around fund operations and the focus on management of portfolio companies was not there.
- Delayed Exits: The COVID-19 pandemic further compounded challenges, delaying portfolio exits and impacting fund performance.

Secondary Sale Proposal
In May 2024, KOIS suggested selling the fund’s portfolio to a new investment fund, supported by new and a few existing investors. KOIS would continue managing the fund, which raised concerns about a conflict of interest. The proposed sale was at a much lower value than the last valuation, which would have caused major losses for key investors, including FCDO.

Strategic Response:
The programme team believed in the long-term potential of the portfolio. They worked with like-minded investors to oppose the deal. The proposal was ultimately rejected, protecting the fund’s value and reinforcing investor trust and alignment.

Regulatory Breakthrough
In July 2024, SEBI introduced a regulation allowing Venture Capital Funds (VCFs) to migrate to the AIF regime, offering greater flexibility in fund tenure and exit strategies.
Key Insight: Although the decision to migrate rested solely with the fund manager, the programme team proactively engaged with other investors to influence KOIS to pursue migration. This collaborative advocacy was instrumental in aligning the fund’s structure with long-term value realisation.

Outcome & Impact
- Value for money: By blocking the discounted secondary sale, LPs avoided premature value erosion, offering better value for money.
- Benefiting from regulatory changes: Migration to the AIF regime enabled a more flexible and investor-aligned exit timeline.
- LP collaboration as a Force Multiplier: The case underscored the critical role of LP coordination in shaping fund strategy and protecting investor interests.

Key Takeaways
- Proactive engagement with other investors can significantly influence fund outcomes, even in manager-led decisions.
- Regulatory awareness and timing are crucial in unlocking strategic options.
- Collaboration over concession: Unified LP action can counter suboptimal proposals and drive better outcomes.

BT, investing through the UK India Development Cooperation Fund (UKIDCF), initially adopted a cautious approach as it sought to fully understand and align with INVENT’s investment thesis. This led to a slower pace of capital deployment.  UKIDCF’s investment period for BT-III closed in March 2024, therefore will not be committing any new investments. BT is closely monitoring the two new investments made before the investment period closed and their performance is on expected lines. Follow-on investments, if any, will be made in existing portfolio companies to protect the investments and to help grow the innovative companies.

Based on the progress reported above, we propose a rating of A for the Annual review – indicating that the programme has achieved its milestones.

Output 1 and Output 3 have been closed in earlier years and details are captured in Section C.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons learnt:

1. Systemic Impact: Strategic fund structuring and coordinated investor action can drive systemic change in early-stage innovation ecosystems, particularly in underserved geographies. INVENT’s model demonstrated how catalytic capital, when paired with disciplined portfolio oversight, can unlock long-term development value.
2. Policy Influence: Proactive engagement with regulatory developments—such as SEBI’s AIF migration policy—can open new pathways for fund sustainability and exit. INVENT’s experience underscores the importance of regulatory awareness and timing in shaping investment outcomes.
3. Gender Inclusion: intentional design and monitoring of gender outcomes can create impact even in early-stage, high-risk investments. INVENT’s support for over 6,000 women in employment demonstrates that gender inclusion is achievable and impactful when embedded in fund strategy. Such approaches can demonstrate successes for others to replicate in the industry.

Recommendations for next year:
1. Review of milestones in the logframe for the outer years and evaluate new outputs that can be tracked in the final quarter of the programmes (action SRO by November 2025).
2. Closely monitor and support exit plans of RVCF and TARA (action SRO – ongoing).
3. Share learnings from the TARA fund on navigating complexity of regulation to achieve UK objectives (action Programme team by December 2025).
4. Connecting fund managers and portfolio companies with DBT to evaluate possible UK linkages (action Programme team by February 2026).
5. Review and follow up on the proposals given in Development scorecard and monitor progress (action Task Team – ongoing).
6. For the incubation programme, conduct a follow up evaluation to know the extent to which the intervention made a difference and whether the supported companies were able to sustain post closure (action PRO – December 2025).
7. Active engagement on Gender has yielded positive results. It is important to continue to engage at investee levels to understand challenges on ground. This approach has led to higher accountability towards the gender mainstreaming agenda. (action Inclusion lead to engage deeper with investees to improve gender mainstreaming).
8. Conduct a governance due diligence on the funds under the programme (action PRO – March 2026)

Progress against recommendations of last AR
Feed in lessons from this programme to strengthen the investment contracts.	Completed. Lesson learnt incorporated as part of standard documents used for future programmes and selection procedures.
Continue the rigorous follow up on priority for the recovery of the unspent funds [~£523,000] from a project partner under INVENT Global.	This issue of recovery has been escalated to the highest level in the organisation of the partner and at high levels within GoI. FCDO is co-ordinating with Ministry of Home Affairs for a one-off waiver of the FCRA rules to enable them to return money to FCDO. Senior FCDO visitors have also raised the issue during their visit. Team is working with the partners to resolve the outstanding issues and secure repayment.
Closely monitor and support exit plans of TARA and RVCF.	The team continued to closely monitor through quarterly updates, regular interaction with the Fund Managers and site visits.
Closely monitor BT investments through UKIDCF for any follow-on actions needed to support their growth trajectory.	The team is closely monitoring through regular updates with UKIDCF. The team did not undertake any field visit in the last review period and will prioritise it for the next review period.
The incubation programme was closed in October 2019. GoI carried out an evaluation at the close. Consider a follow up evaluation to know the extent to which the intervention made a difference and whether the supported companies were able to sustain post closure.	The decision to undertake the evaluation of the incubation programme has been reconfirmed. While the process experienced delays due to budget constraints and the prioritisation of Official Development Assistance (ODA) exercises, the availability of funds now allows for procurement to proceed. The evaluation will assess the programme’s performance and impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The ToC was reviewed and found valid for the current reporting period. The Initial Theory of Change is as under:

Inputs
Outputs
Outcome
Impact
UK funding

Output1: Identify, pilot and nurture inclusive innovations in Low Income States (LIS) & Low-Income Countries (LICs)
- Pilot and test new solutions in LICs
- Supporting startups graduate from pre-incubation to incubation in LIS
- Support start-ups graduate from incubation support to first round of investments in LIS
Output2: Support the scale up of innovative enterprises in LIS
- Make patient risk capital investments.
- Strengthening ecosystem for inclusive innovations & impact investments
Output3: Support Knowledge sharing on inclusive innovations between India and LICs
Collect evidence base, undertake impact assessment
Increased technological & entrepreneurial innovative solutions that benefit the poor in LIS and LIC

- Scaled up pilots
- Improved access to affordable and efficient basic services & products in India and in LICs
- Contribution to global knowledge on transfer of innovative solutions from India to LICs
- Job creation
- Securing additional finance
Improved economic opportunities and quality of life for poor in LIS in India & LICs

- Increased impact Investments in LIS & LICs
- Increased Local multiplier effect in the economy in LIS & LICs
Activities
Support Grant Challenge funds & Incubators

Equity investments in enterprises

Support knowledge sharing platforms

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Progress against outcome and impact indicators is as below:

Outcome Indicator	Target	Achievement as of July 2025
		Incubation project	Investments programme	Total
No. of piloted projects that are scaled up to become viable businesses in Low-income states of India	80	50	28	78
Jobs supported
Men		5,268	4,882	10,150
Women		4,582	1,418	6,000
Disabled		72	8	80
Total	12,500	9,922	6,308	16,230
Finance raised (At fund and investee levels)	£100 m)	£165.2m	£135m	£ 300 m
Numbers of beneficiaries (suppliers and customers) reached through supported companies	10m	13.77m	8.33m	22.1 m

Notes:
(i) This is the last reporting year for tracking developmental outcomes under the INVENT programme. Focus on the future years would be on responsible exits and efficient reflows.
(ii)Targets for outcome indicators are based on proposals from an independent study but moderated by the programme team based on its own assessment.
(iii) Break up of 78 projects that became viable businesses: 17 (RVCF) + 8 (Tara) + 3 (BT)+ 50 (Incubation pilot).
(iv) Additional jobs created are numbers of direct jobs created by enterprises supported under both incubation and investment programmes.
(v) Additional Finance secured is in terms of Equity / Debt or any other sources of funds raised by investee companies and start-ups supported under Incubation project. Exceptional fund raising by two start-ups supported under incubation during the previous AR periods have helped surpass the target.
(vi) Number of lives touched is the number of people reached through the entire value chain of investee / supported companies. Major contribution to this number comes from the continuing impact of incubation project which closed in October 2019.

INVENT India’s operational component has delivered the targeted development impact. The incubation component was closed in 2019 and the investment programme continues to secure financial returns for the UK and has generated lessons which are helpful for the wider development capital portfolio. It is important for INVENT India to continue progressing toward a timely and well-managed closure, ensuring that portfolio exits are executed at the most opportune moments to safeguard and maximise the value of public funds.

All the 3 funds under the investment component have completed their investment period. The funds are now in value-addition phase for their respective portfolio of investments and planning the exit from each of these investments. Whilst the market plays an important role in determining exits, a planned and proactive approach can help protect the value of our investments and help manage the risks.

INVENT India remains well aligned with the priorities outlined in the UK-India Vision 2035 and the Comprehensive Strategic Partnership (CSP), contributing to cross-HMG objectives in Technology, and Social Inclusion. The programme has demonstrated meaningful impact across gender, disability, and participation from low-income states and groups, reinforcing its relevance to both UK growth and bilateral development goals.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Outputs 1 and 3 have been closed in earlier years.

For records:

Output 1 i.e. Identify, pilot and nurture inclusive innovations in LIS & LICs was closed in 2022-23 with following results:

Indicator(s)	Progress
Pilot and test new solutions in LICs (approaches or technologies) to tackle global/local problems in key sectors	Achieved 30 against a cumulative target of 37.
Numbers of Business ideas/ early-stage start-ups graduating from Pre-incubation support to receive Incubation/ Acceleration support in LIS	Total of 215 (161 via Technology Development Board and 54 via Start-up Wave) were supported (Target of 150.)
No. of Business ideas/ early-stage start-ups graduating from incubation support to receive first round of investments in LIS	Overall, 50 supported start-ups received the defined follow-on funding (Target:50)

Output 3 Support Knowledge sharing on inclusive innovations between India and low-income countries (global component) was also closed in 2022-23 with following results: -

Indicator(s)	Progress
Evaluation studies/ Operational Research Studies undertaken.	An evaluation of the global component was carried out which is available on FCDO’s DevTracker.
New Partnerships for replication, / adaption and adoption of inclusive / innovations developed in developing countries	A total of 7 new partnerships were formed.
No. of innovators targeting BoP, / receiving business development / services (BDS) and technical / assistance in developing countries	BDS was provided to 10 African enterprises through Sankalp Africa

Progress against the operational output 2 is as follows: -

Output Title	Support the scale up of innovative enterprises in low-income states of India
Output number:		2	Output Score:	A
Impact weighting (%):		100%	Weighting revised since last AR.	No

Indicator(s)	Milestone(s) for this review	Progress
Number of new Investments	NA	NA
Number of exits	3	3; Met expectations
Return proceeds from exits	£0.5 m	£1.1 million; Exceeded expectations

Given the progress, the output is assessed to have met expectations for the review period (score A). The output weightage changed to 100% as other two outputs of the project now stand closed. The milestones for the output indicators were set at the last AR.

Investments:

TARA, RVCF and BT completed their investments before this review period investing in 10, 19 and 3 enterprises respectively by March 2024, which is the reason for this indicator is not applicable. Overall INVENT has made 32 investments through the three funds.

Exits & Returns:

The following returns are reported in the current review period:
  1. Gross returns during the review period at £1.1m exceed the milestone set for this indicator at the last review. Total gross reflows (capital and gains) are £6.3 m as of the date of this AR.

  1. RVCF
    1. Exited from an investment in Woddenstreet which supports a network of local skilled craftsmen and artisans and supplies innovative and customised furniture to its clients. The company has over 100 stores across India with R&D capability centres in Rajasthan. RVCF had earlier, in 2023, exited part stake and has now exited the balance stake.
    2. Through this exit, RVCF has achieved a multiple of [~16x] on it’s invested capital in Woodenstreet. Woodenstreet provided jobs to over 1250 persons (~15% women) and reached over 1 million customers.
  2. TARA
- The fund has fully exited its investment in Caliper, a global provider of supply chain logistics management services. Caliper offers a Software-as-a-Service (SaaS) platform that supports supplier onboarding, procurement, planning and optimisation, and payment solutions. Despite its potential, the company faced significant challenges due to intense market competition and internal conflicts among its founding team, which led to a loss of strategic focus. While the investment did not yield full capital recovery, the fund manager successfully negotiated an exit that returned a substantial portion of the invested amount, mitigating further downside risk.
- Partly exited from its investment in Infinite Uptime (IU) achieving a multiple of [~4.5x] on its invested capital in the company. IU is an Industrial Internet of Things (IIoT) solution provider for predictive maintenance in the engineering and processing industries, which reduces energy consumption

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Please refer to section A. Progress against last year recommendation, lesson learnt and recommendations for next year covered in detail.

Milestones for next year:

Milestones for next year:
Number of Exits – 4
Return Proceeds – £2 million.

## D: VALUE FOR MONEY

Key cost drivers and performance

A significant cost driver for the fund continues to be the management fees charged by Fund Managers. These fees apply to both directly managed funds and those managed through the UK India Development Cooperation Fund (UKIDCF) and are essential to cover the operational costs associated with running the fund. It is typical for management fees to reduce over time as the fund matures and begins to exit from its portfolio investments.

Currently, the reported inputs pertain solely to the UKIDCF-managed funds. This is because the directly managed funds, overseen by the Foreign, Commonwealth & Development Office (FCDO), are utilising their reflows to cover associated costs.

In the current year a fraud was reported that was on similar lines to the one submitted in 2023. This was reported to the internal fraud team. Not enough evidence was found against the anonymous allegations and it is expected to be closed soon.

VfM performance compared to the original VfM proposition in the business case

Economy: The key cost drivers of this investment programme are (i) Management Fees and (ii) Carry i.e., the share of the Fund Manager in the profits from the investments. The average negotiated Management fees is 1.5 - 2% pa on committed / invested amounts. Carry is directly related to profitability, incentivising the fund manager to maximise financial returns of investors, while delivering the strategic development objectives. The management fees and Carry compare well with the industry average of funds of similar nature and size. To ensure responsible and development-oriented investment, FCDO has linked a part of the management fees to Fund Managers’ performance in ensuring environmental, social and government (ESG) related progress of the investees. An ESG assessment of Tara and RVCF investees indicates moderate to substantial progress against ESG benchmarks.

Efficiency: INVENT has been able to deliver on its main objective of supporting private sector innovations using relatively moderate allocation. It has so far disbursed about £14.5m for investments supporting about 32 small and medium enterprises, which is about ~£453,000 per company.

Effectiveness: INVENT has achieved milestones on job creation, additional finance leveraged and numbers of people benefiting from basic service provisions through investee companies. Overall, the portfolio is in positive territory in terms of valuations with one of the funds already returning the capital invested in it. (See output and performance of project partner sections for details).

In terms of Equity the project has a pro-poor approach as its focus is on supporting investees in Low Income States of India. It has done better than national average in providing jobs for women and people with disabilities.

Assessment of whether the programme continues to represent value for money.

INVENT India: The project has delivered the outcome targets. The programme is currently focusing on planning and execution of exits from portfolio investments. Exit planning is linked to market conditions and is managed by the investment committee of the respective funds. Fund managers use the agreed extension to work out profitable exits. The valuation of the three funds broadly indicates that, overall, the original value of investments will be protected. Necessary approvals from the development director has been taken to ensure return of the capital invested. RVCF end date has been extended to December 2026 to facilitate exit from the portfolio companies. Working on TARA end date post their migration to the AIF regime. TARA has submitted an application to migrate to the AIF regime which will enable it to extend the fund life till January 2028 and if necessary, further till 2033. Going forward, funding will only be needed to pay for management fees and for any follow-on support that the new investees of BT fund may need.

E: RISK [½ to 1 page]

Overview of risk management

The overall risk of the programme is ‘Moderate’.

Global Component: This component has been closed. The outstanding risk pertains to the recovery of any unspent balance. This is being actively monitored, and appropriate follow-up actions are underway to ensure resolution.

INVENT India Component: The component has remained generally stable throughout the review period. A significant risk emerged when one of the Funds initially declined to explore migration to an Alternative Investment Fund (AIF) structure (explained in detail in the case study).

Key risks and mitigation measures in place are highlighted in the table below:

Risk Description	Risk category	Mitigation Strategy	Residual Risk
Selection and monitoring of investments by Fund Manager /IC Committee the supported investees might not perform well commercially, leading to loss of capital.	Policy and Programme Delivery	Jointly agreed and monitored investment strategy between with the Fund Managers and FCDO, due diligence of investees and regular monitoring.	Major
Reputational risks due to financial frauds, safeguarding issues and lack of progress on ESG.	Reputational	Careful examination of investments by the programme team / Investment Committee / gender lead of capital/ development framework before every approval, continuous monitoring and timely action in case of any incident.	Minor
Fund managers diverting money for other purposes.	Financial & Fiduciary	Quarterly utilisation reports, annual audited statement of accounts are mandatory from partners. Delivery chain mapping and regular touch with downstream partners also ensures this. Hurdle rate and performance linked incentives for Fund Managers and for their employees.	Minor
Slowdown of investments and exits due to attrition /other operational issues in partner entities.	Policy & Programme Delivery	Closely work with partners and monitor their resource management ensuring timely replacements. All three funds are stable currently.	Moderate
Lack of appreciation for a heightened risk appetite by the internal stakeholders for the inherent failure rate in innovation investments (including economic returns) and consequent critique for the project not delivering.	Policy & Programme Delivery	Risk of failure will be clearly mentioned in the project documents. A well-diversified portfolio of projects to avoid failure due to issues in a particular sector; competitive bidding process was undertaken to select a suitable Fund Manager with requisite expertise for delivering the objectives; Regular communications including meetings with Fund Manager to monitor the investment strategy.	Moderate

INVENT Global:

Default by partners in returning balance funds after closure of Global components.	Financial & Fiduciary	Close follow up with delivery partner and insisting on returns, using high level engagement; including VIP visits to raise the issue with MEA.	Moderate

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

TARA Fund IV:

The fund is managed by Kois India Investment Advisers Private Limited (Kois). They took over from IL&FS Investment Manager Ltd (IIML) in 2021. Kois has tried its best to make the transition work for the investors through value protection for investees thereby arresting the financial losses, that could have arisen. During the review period, they were able to negotiate some value from the one written off investment and one profitable partial exit achieving gross yearly financial returns (IRR) of 24.9% [and 4.5x Multiple on Invested Capital (MOIC)]. During the last review period they had proposed secondary sale of its balance 5 investments. The proposal was not supported by some of the Investors, including FCDO, and was not passed. FCDO was keen that they explore other options and consider migration to AIF. During the current review period, TARA has filed it's application with SEBI for migration to the AIF regime.

TARA’s current investments have created 1,712 net direct jobs (of which 576 are women and 3 PwD) and 373 indirect jobs (of which 111 women). Eight of the investee companies have been able to raise follow on funding in equity/debt or both. [Total capital mobilised (equity and debt) till date is about £105 m]. The Fund has achieved a good equity as women constitute about 34% of direct jobs offered by its investees, which is higher than the national average. The ESG score for TARA investees has improved from an average of 1.59 at Due Diligence stage to 2.86 at Mid Term. [As of March 2025, Net Asset value (NAV) of the balance units in TARA fund is £9 m) (against its book value of £5.5 m unaudited valuation)].

Date of last narrative financial report(s)	March 2025
Date of last audited annual statement (s)	March 2024

RVCF III:
RVCF is manged by Rajasthan Asset Management Company (RAMC) which is promoted by the Rajasthan government. The fund has invested in 19 companies and fully exited from 4. The fund manager has been proactive in completing its investments. Exits during the period have been slower than expected. Update provided by the fund manager indicates regular and close monitoring of investee companies by the Fund Manager. They have shared required information regularly and supported visits as and when needed. They have been diligent in complying with regulatory and statutory requirements.

Four exits have been made so far, one during this review period giving us a multiple of ~16x. All exits have made commercial gains and the fund has now returned our total invested capital. As of review date, RVCF supported companies have been able to raise about ~£30 million by way of Equity /Debt/Others for their operations.

66% of RVCF portfolio companies have been started by first time entrepreneurs. 32% have women founders / promoters. 59% have RVCF as their first institutional investor. Fund’s investments have created 1,482 direct jobs (of which 349 women and 3 PwD); 22,030 indirect jobs (of which 1,851 women and 6 PwD). The portfolio companies are driving meaningful impact in low-income states, directly advancing the programme’s core objectives. While their corporate headquarters are based in Tier 1 and Tier 2 cities, the heart of their operations and their transformative impact lies in Tier 2, 3, and 4 cities across the country (see map below).

The fund’s equity performance continues to be good with women constituting about 20% of the direct jobs offered by the investees. This is significant given that most of these companies operate in the low-income state of Rajasthan where women participation in workforce is very minimal. The ESG score of investee companies has improved from an average of 1.05 at Due Diligence stage to 1.92 at Mid Term. [The NAV of each unit of RVCF III as at March 2025 is £1383 (face value £903)].

Map: showing the impact of RVCF III fund across the low-income states.

Date of last narrative financial report(s)	March 2025
Date of last audited annual statement (s)	March 2024

Banyan Tree Growth Fund III:

This investment is managed through the UKIDCF platform. UKIDCF made three investments through BT. BT has exited from one. UKIDCF made two new investments in March 2024. Value of the two remaining investments is ~£0.46m. The investments till date have helped create 110 direct jobs, 107 indirect jobs, and have provided benefits to 150,000 people, out of which 65% were women. [The valuation of the units as of March 25 is reported to be £1.3 m].

UKIDCF’s investment period in BT ended in March 2024 and will not be making any more new investments, it can still make follow-on investments in existing portfolio companies and pay for the management fees and expenses.

Map: showing the area of operation of the Banyan Tree investees – Groovy and Microbe across India.

Date of last narrative financial report(s)	March 2025
Date of last audited annual statement (s)	March 2025

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

This Annual Review is informed by monitoring activities throughout the year by the implementing team and is further substantiated through information provided by respective Fund Managers.

Monitoring activities during the review period: -

All Funds

Each Fund Manager submits:
  1. A quarterly progress report detailing updates on activities and the status of their investment portfolio.
  2. An annual valuation report of their portfolio.
  3. Annual audited financial statements of the fund

The Programme Team has periodically engaged with Fund Managers to obtain assurances on key management processes, including:
- Fraud prevention
- Safeguarding
- Personal data protection
- Visibility commitments
- Risk management
RVCF III
1. In person meetings with RVCF III fund Manager and with senior leadership at the RVCF office in Jaipur (January 2025) to discuss updates and exit strategies
2. Site Visits to investee companies Kirana King and Freshokartz (RVCF investees) – January 2025.
3. Quarterly virtual meeting with the Fund Managers – most recent held in July 2025.

TARA Fund IV
1. Quarterly meetings with TARA IV fund Manager – last one on 30th May 2025.
2. Multiple discussions with the Fund Manager regarding the fund’s migration to an AIF structure.
3. Several consultations with co-contributors (LIC, SIDBI, SFPI) to gather perspectives on the migration process.
UKIDCF/BT
1. Quarterly meetings/calls with UKIDCF – last one in May 2024.
2. Quarterly/6 monthly call with BT III fund manager for update on the two new investments – last one in June 2025.

Evidence on progress and lessons learnt during the period are documented in the relevant sections above.