## Annual Review Template

Title: IFC Global SME Facility – Small Medium Enterprise Initiative
Programme Value £ (full life): / Originally: £75 million Fiscal CDEL (2012 – 2031) / In Jan 2021, FCDO withdrew £10 million / Net Programme Value: £65 million		Review date: July 2025
Programme Code : 202935	AMP start date: 28/02/2012	AMP end date: 31/03/2031

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	B	A	A	A	A	A	A+	A+	A	A+	A	A+
Risk Rating	Med	Med	Med	Med	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod

DevTracker Link to Business Case:	3716779.odt
DevTracker Link to results framework:	DevTracker Programme GB-1-202935 Documents

Description of programme

The Global Small and Medium Enterprises Finance Initiative (GSMEF) is a blended finance partnership managed by the International Finance Corporation (IFC) since 2012, which aims to bridge the gap in financing underserved small and medium-sized enterprises (SMEs), especially in more challenging environments and market segments. This includes operating in fragile and conflict-affected states (FCAS), addressing climate challenges, and supporting women-headed businesses. The delivery modality is a multi-donor trust fund managed by the IFC, part of the World Bank Group, and funded by the UK and the Netherlands.

The GSMEF works across Sub-Saharan Africa, Middle East and North Africa, South-East Asia, and Latin America through two complementary workstreams:

1. Investment Services (IS): direct funding lines (concessional loans), risk-sharing facilities[1], and performance-based incentives[2] with a view to changing behaviour of bank and non-bank financial institutions (partner financial institutions, or ‘PFIs’) in lending to SMEs in the target geographies and segments; and
  [1] Risk sharing facilities such as Interest Rate Buy-downs and First Loss Guarantees.
  [2] Bonuses linked to meeting specific performance targets to encourage PFIs to grow SME portfolios.
2. Advisory Services (AS): capacity building of the PFIs to better understand the needs of SMEs and price the risks of lending to SMEs, with specific focus on underserved segments including women-owned SMEs. In addition, it supports the establishment and strengthening of financial market infrastructure (credit reporting bureaux, secured transactions, and collateral registries) to address more systemic constraints on SME financing in the target countries.
In aggregate this helps PFIs lower the pricing they can offer on their loans, improve risk management, embed digital tools, and develop and “right size” financial products to increase their lending to SMEs, leading to improved livelihoods through jobs and income generated by these SMEs.

The total GSMEF Trust Fund is $153m, with a total current UK total contribution of £65m (initially £75m was invested, however £10m was withdrawn in 2021). IFC have reported that all UK funds have been invested at least once[3]. However, the UK still has a light-touch involvement and ongoing interest in the operations of GSMEF as investment reflows (matured investments, returns and interest) are recycled through the programme, in line with priority areas. Since inception, the Facility has committed a cumulative total of $157m (Investment Services was $108.2m while Advisory Services was $48.6m) to 211 projects (127 Advisory Services projects, and 84 Investment Services projects). GSMEF’s projects have been implemented in 46 countries, of which 83% have been International Development Association (IDA, which supports low-income countries) countries, and 28% of all projects have been in FCAS countries.
[3] FCDO funds are ringfenced and tracked separately within the Trust Fund

As of June 2024, $16.6m had been committed but not yet disbursed (all FY24 blended finance commitments were supported by the UK), $13.5m of funding for Investment Services was uncommitted, and there remained an uncommitted cash balance of $9.13m in the Advisory Trust Fund. GSMEF has a strong pipeline of project proposals whose demand exceed available funding. Investment Services has pipelines of $26.8m (pre-concept), and Advisory Services has pipeline of over $9.1m. Despite the risk profile of GSMEF’s investments, it has generated $2.64m of reflows to support GSMEF Advisory Services.

Since all FCDO funds have been committed at least once, the FCDO now conducts a lighter touch Annual Review process of GSMEF, in line with FCDO Programme Operating Framework requirements. Additionally, FCDO continues to actively monitor progress through quarterly updates and annual meetings.

In 2024 GSMEF outperformed its targets, sometimes doubling the targets set for the Fund. It managed and mitigated the project risks despite its extended work in fragile states and has helped IFC and World Bank deploy significant additional sums through its broader investment portfolio. However, there is still more work to be done especially mainstreaming gender and capturing its gender reach. It achieved an A+ score in this Annual Review, with risk assessed as Moderate.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The programme’s theory of change remains broadly unchanged for the components that remain active (Output 1: Risk Capital’ and ‘Output 2: Advisory Services’), with blended finance and advisory components complementing each other to increase lending to SMEs.

The FCDO has now endorsed the inclusion of a new blended finance product, known as the ‘Swap Rate Buydown’ to maximise leverage and local currency access with a capital market angle. This addition reflects the Facility’s evolving capacity to innovate and respond to market needs, enabling PFIs to broaden their outreach and deepen their impact on SMEs.

The programme’s log frame was last revised early 2024 to ensure the results framework maintains ambition within an ever-changing environment. This follows from the programme’s cumulative impact targets revision in April 2021 (following a previous revision in June 2019).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The GSMEF continues to perform well, maintaining high impactful results across both remaining outputs. As of June 2024, all targets were exceeded except for the number of PFIs supported with risk sharing and funding mechanisms. However, this was under target by only one PFI and if Dutch-only funded projects were included in the results framework, the target would have been achieved from a programme perspective.

A total of $157 million was committed to 211 investment and advisory projects in 46 countries in this reporting period, with 28% of projects conducted in FCAS regions. The Fund is expanding its footprints in fragile countries such as Iraq where GSMEF provided $2.3 million Interest Rate Buydown to support IFC’s $20 million loans to the National Bank of Iraq to strengthen its SME lending. This has resulted in $94 million of loans, reaching 1,245 SMEs.

Activity throughout this reporting period and across all projects has supported an estimated 1.3 to1.9 million jobs. The programme is on track to deliver its intended outcomes and impact, with continued growth in portfolio size and strong performance in supporting women headed businesses (WSMEs.) GSMEF continues to make meaningful progress, with portfolio growth aligned to expectations and strong results in supporting WSMEs.

The pipeline for next year is strong with demand exceeding funds for both investment and advisory services.

	Outcome description	Target Yr13 (annual / cumulative)	Actual
Number of SME loans outstanding	Participating Financial Intermediaries
	Number of new SME loans	154,545	267,992
	Number of new Women-owned SME loans	17,066	58,156
	Number of SME loans in FCAS Countries	38,636	140,367
	Financial Market Infrastructure
	Number of new SME loans	550,139	523,194
	Number of new Women-owned SME loans	36,578	38,477
	Number of SME loans in FCAS Countries	137,535	98,914

Volume of SME loans outstanding	Participating Financial Intermediaries
	Volume of new SME loans (£)	7,583 million	9,682 million
	Volume of new loans to WSMEs (£)	420 million	806 million
	Volume of new SME loans in FCAS (£)	1,896 million	5,861 million

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Risk sharing mechanism(s) to catalyse investments from DFIs in the selected PFIs for scaling up SME financing on commercially sustainable basis in the 15 target countries, including in the high-risk environments of fragile/conflict affected countries.
Output number:		1	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Cumulative number of Partner Financial Institutions (PFIs) supported with risk sharing and funding mechanisms.	93	92
1.2a: Increase in volume of outstanding principal of SME loans made by PFIs under the investment component. / Volume of additional funding mobilized for SMEs through PFIs under the investment facility component (concessional funding). (£)	4,781 million	5,477 million
c) share of fragile countries and frontier markets in (a)	30%	39.6%

Output Title	Capacity of partner banks and Non-Banking Financial Institutions (NBFIs) strengthened through well-targeted technical assistance to partner financial institutions in risk management, product development, and improvement in of business processes, and support for development of financial market infrastructure such as credit bureau and collateral registry in the identified.
Output number:		2	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1a: Cumulative number of PFIs and financial infrastructure projects covered with advisory services and activities.	86	91
2.2a: Volume of SME loans generated by PFIs / financial infrastructure covered by advisory services plus IFC's non-concessional financing.	4,781 million	6,145 million

Briefly describe the output’s activities and provide supporting narrative for the score.

GSMEF has delivered impactful results across this review period and has continued to make commitments on both the Investment and Advisory side. GSMEF continues to expand its geographic presence with new countries, Morocco, Egypt and Vietnam, added to the portfolio in FY24. The Facility has the largest presence in Africa with 68% of all projects (including solely Dutch funded) completed across the continent, followed by 16% in South Asia, 8% in the Middle East, 7% in East Asia & the Pacific and 1% in Latin America.

Investment Services: GSMEF committed $16.6m f funds to 9 new Investment projects. This included:

1. A commitment of a$3m Pooled First Loss Guarantee to support an IFC Risk Participation Facility for Supply Chain Finance (SCF) in Vietnam. This is the first support of SCF in the GSMEF portfolio and was funded solely by FCDO funds.
2. The programme committed Interest Rate Buy-downs (IRB) totalling $4.6m to two banks in Egypt (Banque Misr and Banque du Caire) to increase their lending to SMEs, especially to women-owned SMEs.
3. GSMEF used, for the first time, a $0.7m IRB to support IFC Risk Share Facilities with Banque Centrale Populaire (BCP) in Morocco. To have greater climate impact, the facility encouraged SMEs to adopt water-saving and energy-saving technology.
4. The Facility, with a $1.8m IRB, supported Jordan’s first Sustainability Bond.
5. The programme committed a $6.5m concessional senior loan to the Bank of Palestine, in the West Bank & Gaza, supporting a $100m investment by IFC and other investors.
6. GSMEF’s support to the Bank of Africa Group was expanded to include 3 additional countries (Burundi, Democratic Republic of Congo, and Rwanda.) IFC assumed additional risk without requiring additional Donor support, due to GSMEF’s successful track record. As in stands, 13 Bank of Africa affiliates are now covered, which expects to reach 3,000 SMEs.
Advisory Services: The Facility committed GSMEF funds to 6 high impact advisory service projects across Laos, Benin, Guinea, Bangladesh and multiple West African countries. The projects include digital banking, RSF implementation support, SME banking and risk management.
1. Phongsavan Bank, Lao: the Facility is supporting in the implementation of key strategic initiatives of PSVB to meet its business objectives, mainly in the areas of risk management, People & Culture, sales and delivery, products, digital, and supply chain finance.
2. NSIA Banque, Benin: the Facility is assisting in improving the Banks capacity to serve its SME clients, focusing on areas such as the banks business sales and delivery channels, frontline capacity building, and credit management and products. The development and implementation of appropriate banking solutions and development of a local expertise for the staff will help sustain access to finance for SMEs in the region.
3. NSIA Banque, Guinea: the Facility will (i) help the bank grow its SME loan portfolio, (ii) strengthen the bank’s Enterprise Risk Management, (iii) strengthen the SME Business operating model, products and services, customer value proposition, sales, and delivery model; and (iv) provide staff capacity building through targeted training of frontline staff.
4. Bank of Africa, Niger, Mali, Senegal, Benin, Burkina Faso, Togo, Tanzania, Cote d’Ivoire, Madagascar, and Ghana: The Facility is assessing the needs of Bank of Africa affiliates and capacity and rolling out SME, Financial Management, and IFC RSF training programmes.
5. Commercial Bank of Ceylon, Sri Lanka: The Facility is supporting strategic alignment and agreement with key stakeholders on the Banks supply chain finance business model, to build a successful SCF proposition and execute implementation plans for all key pillars, to grow the portfolio on a sustainable basis, and to support in enhancing the inclusion of women entrepreneurs in their portfolio.
6. Prime Neo, Bangladesh: the Facility is supporting the establishment of a digital banking unit, a ‘Neo Bank’ division within the existing Prime Bank built. The project will be a greenfield project with completely independent platforms and processes, integrated via API into Prime Bank and within the Bangladesh Bank regulatory reporting framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on previous recommendations:

1. Mainstream Gender and increase the reported disaggregated outputs and outcomes: The Facility has exceeded its original gender targets and currently has a Gender Advisor on the management team. A discussion was held between FCDO and IFC to encourage a stronger focus on gender inclusion and further discussions will be held to ensure increased impact for those with vulnerable characteristics.
2. Reporting requirements: IFC is working with PFIs to improve data collection, especially through advisory services. IFC has launched a Banking on Women Global Sex Disaggregated Data program to strengthen the capacity of strategic financial institutions to collect, track, monitor, and analyse portfolio data.
3. Evidence based: There are a number of different initiatives ongoing on the analytical agenda to better understand the impact of financing on end-beneficiaries, specifically SMEs. The GSMEF was acknowledged in a recent ‘reverse gender gap in SME finance’ report. There is also an ongoing research program to quantify the impact of financing on key MSME outcomes with 14 financial institutions involved. The IFC team are currently putting together preliminary insights from the data collected from this exercise.
4. Systemic Change: The Facility assesses projects beyond project level impacts, and market transformation potential in support of SMEs is a key consideration. The GSMEF has invested $15.8 million across 24 financial Infrastructure projects to support systemic change.
5. Field Visits: A field visit was arranged in June 2024 to Kenya (Bank of Africa) and Tanzania (CRDB) where FCDO colleagues met with leading banks as well as SME owners. The trip proved to be very insightful and further field visits are to be arranged.

Programme Management: Delivery, Commercial & Financial performance.

Reporting
FCDO and IFC teams maintain regular formal and informal engagements throughout the year with an annual donor steering committee and quarterly pipeline updates. IFC engage on results framework amendments and respond to ad hoc requests for information.

Financial performance
FCDO has disbursed all its original funding commitment to this programme with no further disbursements planned. Programme resources now largely draw on the amount of reflows generated from FCDO’s original £75 million commitment. Reflows will remain within the Facility and will not return to the FCDO.

The key cost drivers for both investment and advisory services relate to:
1. Overall programme management,
2. Implementation of individual projects and transactions, and
3. Monitoring and evaluation activities.
The delivery model emphasises partnerships between global and regional teams of IFC. The IFC global team leads the overall coordination and work closely with regional managers, who drive the programme at country level, to select and approve projects. By leveraging IFC’s extensive regional presence and relationships, this model helps ensure cost efficiency for FCDO. IFC Investment and Portfolio Officers manage all investment projects, with the SME Initiative global team offering portfolio-level supervision, oversight, and reporting to FCDO. Most investment costs are funded by IFC or by project fees thus reducing the cost of deal origination and execution for FCDO. The operating expenses for investment and advisory services components are complemented by contributions from PFIs, and in the case of investments, other IFIs and investors.

Performance against Value for Money (VfM) metrics

The Business Case considered VFM under the specified components listed in the table below. Overall management fee paid to IFC has remained unchanged and competitive at 4.6% of the overall programme cost, including a 3% centrally mandated Trust Fund Management Fee paid to the World Bank for providing back-stop and trust fund account management support. IFC management fees are set forth in the administration arrangements between FCDO and IFC. Technical amendments to the administration arrangements relating to management fees were made in June 2019.

The GSMEF continues deliver strong mobilisation figures for every £ of funding provided by FCDO with latest figures presented in the table below. In particular, the GSMEF’s use of Performance Based Incentive instruments delivers high leverage figures, because they consist of small GSMEF investments (typically USD 100k – 400k per PBI) that crowd-in typically USD 5m to 50m (though occasionally USD 100m+) for SME finance.

VfM Indicator	Results (June 2024)
1) Volume of investment (£) from DFIs for every £ of funding from FCDO.	$19.30 ~ £15.25
2) Volume of lending to SMEs by PFIs (£) for every £ of concessional funding from FCDO.	$190.40 ~ £150.42

Key lessons and challenges
1. There are strong advisory linkages with 70% of PFIs receiving advisory support also received investments. Advisory support improved risk management, product design, and operational efficiency, directly contributing to better investment performance and reinforcing the value of combining technical assistance with capital.
2. GSMEF has done well to be more inclusive through an increase in the number of projects in FCAS (28%) and IDA regions (83%), as well as an increase in the support to Women owned SMEs. This strategic targeting should continue to ensure inclusive development. The current Advisory pipeline already notes the inclusion of new FCAS countries and is working to improve reporting on gender-disaggregated data.
There is a need for local currency solutions support and financing mechanisms to mitigate FX risk. Going forward IFC will deploy the swap rate buy-down to maximise leverage and local currency access with a capital market angle.

Recommendations for the year ahead:

1.The FCDO and IFC programme teams should liaise more often to ensure increased alignment, including with the FCDO Post Network and IFC Regional Managers. This will improve strategic coordination, avoid duplication, and ensure information is disseminated accordingly.

2. The Facility should continue to increase targets and inclusion of vulnerable characteristics, including gender, to further support the reduction of systemic barriers to accessing finance and opportunities. There is still a need for better reporting on gender disaggregated data and improved reporting mechanisms would be beneficial ahead of the next annual review.

Date of last narrative financial report	30th June 2024	Date of last audited annual statement	N/A