## IMPACT Programme Annual Review

Title: IMPACT Programme
Programme Value £ (full life): £157.9m		Review date: Feb 2024
Programme Code: 202939	AMP start date: Dec 2012	AMP end date: Dec 2035

 Summary of Programme Performance
Year	1	2	3	4	5	6	7	8	9	10	11	12 (2025)
Overall Output Score	A	A	A	A	A	A	A	A+	A	B	A	A
Risk Rating	M/H	M/H	M	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod

DevTracker Link to Business Case:	Link here
DevTracker Link to results framework:	Link here

A. SUMMARY AND OVERVIEW

Description of programme
The IMPACT programme is set up to catalyse the market for impact investment: investments that aim to create beneficial social or environmental effects while also generating financial gain.
Through strengthening the impact investing sector, there can be more effective allocation of capital which will increase direct impacts of investments and also overcome key market barriers for the private sector to address the world’s social and environmental challenges, as set out by the Sustainable Development Goals (SDGs).
The IMPACT programme’s coordination with key market stakeholders on impact management will increase the coherence and effectiveness of the impact investment sector to drive solutions to achieve the SDGs (e.g. investing in renewables) and to support private sector activity that positively impacts stakeholders and communities – including through improving access to affordable goods and services and creating income-generating opportunities. During the previous reviews we reported on:
Market-building grants, which have previously been delivered in partnership with Palladium and the Good Economy. The final phase (“Phase II”) of the Palladium partnership included market-building grants (2019 – 2023).
And
CDC Plus: a technical assistance (TA) portfolio managed within what is now British International Investment (BII) that included:
Impact and value creation in BII portfolio companies (‘within portfolio’), available to the whole BII Investee portfolio – firstly to other Catalyst investees for core business grants, then to Catalyst and Growth investees for catalysing impact grants). In 2021 the programme agreed a £39.8 million concessional capital allocation (“Kinetic” pilot).
Impact and value creation beyond BII portfolio companies (‘beyond portfolio’), allowing BII to test solutions that address systemic issues affecting multiple BII investees in the markets in which BII operates, and ecosystem level challenges that investors face.

The CDC Plus element of the programme, which sits within BII, is no longer funded by FCDO and is no longer part of the IMPACT Programme.
The IMPACT programme currently consists of market-building grant partnerships managed directly by the FCDO Impact Investment Team. Whilst this re-structuring of the programme has increased pressure on internal resources (e.g. developing and implementing new internal systems for managing grantees directly), this has eliminated external fees to a delivery partner, allowing the policy team to use a higher proportion of our reduced budget to fund grant activities and to have more direct relationships with partner organisations.
UK Overseas Development Assistance Budget
For FY24/25, the IMPACT programme budget has been £2m.
Summary supporting narrative for the overall score in this review.
Over the reporting period the IMPACT programme has met expectations and has scored an A, with a risk rating of moderate.
This year, the programme team conducted a Call for Proposals (CfP). The approach of inviting a broader range of organisations to participate was taken to encourage a more diverse set of ideas and value for money through competition, refined with input from FCDO policy teams, as well as key partners in the impact investment sector (with a focus on consulting other funders to avoid a conflict of interest for potential applicants). The CfP resulted in 20 quality bids and an increase of active accountable grants to 8 (from 5, last year). This represents a considerable increase in engagement across the impact investing sector and has broadened the adoption of impact management[1] for EMDE investing. The CfP was structured to:
[1] Impact management here refers to the process to which an enterprise’s identifies, measures, discloses and acts on positive and negative impacts of activities on enterprise, people & planet.
1. Increase the breadth of Environmental, Social and Governance (ESG) issues (defined as financially material information) and sustainability standards guidance and assistance across EMDE countries
2. Consolidate and improve the quality of impact management, i.e. planning, measuring, monitoring and optimising impact and investment strategies for use by development and private sector actors. This includes advancing critical private capital mobilisation agendas – for example promoting investment approaches which take into account system-level impacts (beyond the firm level) and increasing the practical application of more inclusive investment strategies to underserved markets or market segments such as Small, Growing Businesses or Small and Medium sized Enterprises (SMEs).
3. Pioneering investment structures that deliver for underserved businesses.
The CfP resulted in 20 applicable applications, with 8 new proposals selected to receive grant funding. Further details of activities are described in this year’s annual review outputs section, with a summary of the 8 partnerships outlined below:

Grant Partner	Headline description	Grant value (up to)	Progress this FY
Collaborative for Frontier finance (CFF)	Supporting EMDE Local Capital Providers (LCPs) to deliver finance to small and growing businesses; supporting LCP Convening and networking to build capacity. / This specifically supports the development of new instruments to address the large financing gap for small, growing businesses in EMDEs, which are vital for employment and economic growth	£200,000	Grant agreed (to complete end-March 2025) / Launch+ Facility has been established as a Technical Assistance vehicle / Support of the Collaborative for Frontier finance network, 2025.
Financial Sector Deepening Africa	Supporting the FSDA programme on International Sustainability Standards Board (ISSB) adoption roadmaps (Ghana & Nigeria) and testing ESG reporting for Insurers (Kenya, Uganda, Nigeria, Ghana). / This will test new approaches to supporting sustainability disclosures in EMDEs, in order to encourage PCM into these markets	£272,000	Grant agreed (to complete end-March 2025) / Working with regulators in Nigeria and Ghana has begun. / Bespoke training with Insurers/reinsurers and pilot sustainability and ESG reporting has begun.
GSG Impact	Establishing centres of expertise for sustainability reporting and convening of Development Finance Institution (DFIs) SME working group. / This will enhance the voice of EMDEs in sustainability reporting, support adoption and promote local solutions to financing gaps. / Supporting local networks in Ghana, Nigeria and Zambia to establish impact investment facilities to deliver for underserved groups.	£300,000	Grant agreed (to complete end-March 2025) / Development of Sustainability disclosure hubs in key networks has begun / Support on DFI – SME financing working groups completed / Development of input papers and research for sustainability disclosures and capital mobilisation in EMDEs.
Impact Frontiers	Impact Performance Norms for EMDEs (Impact Frontiers). / This will advocate for further standardisation of impact reporting globally, in addition to enhancing its applicability to emerging markets in order to increase impact investment volume and quality	£182,000	Grant agreed (to complete end-March 2025) / Preparation for the Development of Impact Norms with participation in Africa (Pan-African Venture Philanthropy Alliance, AVPA) and Asia (Asian Venture Philanthropy Network, AVPN).
Joint Impact Model Foundation (JIMF)	Building capacity for ISSB-aligned climate-related financial disclosures in Bangladeshi financial sector (JIMF). / This intervention is seeking to provide solutions to determining carbon in financial institution portfolios and create system to identify opportunities to raise climate finance.	£191,000	Grant agreed (to complete end-March 2025): / Sector assessment (with central bank) has begun / Capacity and technical input into climate risk system integration has been planned
University of Cape Town	Standards, tools, and training to increase systemic impact through investment. / This will create the right incentives in funds and enterprises to deliver beyond-the-firm impacts – increasing the impact of development finance allocators.	£220,000	Grant agreed (to complete end-March 2025) / Preparation of standards toolbox materials / Preparation of training course materials and training materials
Operating Principles for Impact Management (OPIM) – Ongoing from last FY.	Promotion and development of impact principles in EMDEs. / These principles, will support the standardisation of impact management across investors to increase PCM	£197,000	Grant agreed and ongoing. / Engaging emerging markets with OPIM and development of draft case studies of utilising the principles
International Financial Reporting Standards Foundation (IFRSF)	Road Map Development Tool (RDT) and interactive workshops. / This will lay the groundwork for the adoption of ISSB in emerging markets – and encourage collaboration across TA partners.	£104k	Grant agreed (to complete end-March 2025) / Development of a Web-based development tool / Technical assistance and workshop for implementor organisations which support ISSB adoption in EMDEs. / Continued work with Pan-Africa Federation of Accountants (PAFA) to develop a strategy for International Sustainability Standards (ISSB) implementation across Africa with member accounting organisations.

In addition to grant deliverables, the findings and learning from partners’ work are expected to contribute to:
(i) international policy discussions at events, such as UN Fourth International Conference on Financing for Development (FFD4) and London Climate Action Week (LCAW), including on areas such as financial inclusion, financing for growth businesses and sustainability disclosures and standards in EMDEs.
 (ii) The advocacy and development of standardised impact management tools – this can feed into UK domestic growth priority issues with an EMDE context, such as the work of the newly established Transition Finance Council[2]. The disclosing and management of an enterprises climate pathway will support financial markets participants to allocate capital to fund this trajectory or manage associated risks and opportunities.
[2] https://www.theglobalcity.uk/sustainable-finance/opportunities/transition-finance/transition-finance-council
Progress on recommendations in the previous annual review
      1. As global impact disclosure and measurement systems develop, the IMPACT programme team should consider how we best support this - balancing the extensive work across supporting adoption of disclosures represented in the portfolio with more 'frontier' initiatives looking to further advance the robustness of impact measurement. This could be supporting the development of new disclosure and measurement tools that fit as additional (perhaps voluntary) impact resources to ISSBs disclosure drafts.
In progress. The IMPACT programme has used its network of impact investors and grant agreements to test how best to support long-term implementation ISSB., for example, by using grants with FSDA, IFRSF and GSG Impact, all of whom have worked through existing local network and relationships with key local stakeholder (e.g. governments, regulators, thought leaders). This will enhance probability of effective ISSB adoption that better serves local needs. In the Call for Proposals, the programme was able to identify new partners delivering new disclosure and measurement approaches, including Impact Frontier and the University of Cape Town. While delivery is not yet finalised, both partners have confirmed appetite from stakeholders to further deepen work on impact disclosure and measurement.

      1. The Programme team should consider how evidence on the impact of disclosures and standards in relation to gender can be aggregated from delivery partners – and inform other FCDO programmes. The team can draw on the expertise of the newly appointed impact and equalities adviser.
Complete. The IMPACT programme, via the GSG Impact grant, is exploring frontier social disclosures and standards (encompassing gender). Consolidation of feedback on the inclusivity of grants occurs quarterly and will inform our prospective grant pipeline and wider programming as relates to targeting Gender outcomes.

      1. The programme team have developed an effective programme management system to provide oversight to each of the grants, reflecting the new in-house management. A formal, integrated, guide could be developed for use by the programme team and delivery partners – increasing the efficiency with which each grant moves across the delivery lifecycle: proposal development, due diligence, legal agreement, financial disbursals etc. Specific timelines could be agreed for each decision point. This can be used to set expectations with internal and external partners throughout the programme cycle.
Complete. Through the Call for Proposals, the team consolidated advice to partners on applying for grant funding, undergoing due diligence, delivering outputs and processing payments. This has been integral to managing 8 independent grants effectively, though has not yet been developed into a structured ‘guide’. The team will consider how to fine-tune engagement with prospective grantees again during any future calls for proposals.
      1. Replacement of output 4 - The programme team should consider other indicators or more effective way of determining the impact / engagement of published products.
In progress. After review, output 4 has remained. However, the team have removed indicators 4.3 and 4.4 on unique views of publications and grantee feedback on programme events, respectively. Both are no longer relevant as the programme is no longer managed by an external supplier. The team will continue to reflect on how to track the engagement on products either through individual grantees or through re-establishing a programme communication channel (e.g. on gov.uk or LinkedIn).
      1. Ahead of the next round of grants, the programme team should consider how to attract a range of proposals for interventions from a broad set of potential delivery partners, as well as improving knowledge sharing and engagement among programme partners and with other stakeholders in the impact investment field. The programme team should consider developing a stakeholder engagement plan.
Complete. As discussed in the summary, this year the team conducted a publicly accessible Call for Proposals – which ensured a broad set of applications were considered. Leveraging these partnerships, the IMPACT programme has been able to coordinate working across grants – increasing mutual impact.
      1. The programme team should leverage IMPACT to deliver discrete projects across the broader FCDO teams and model best practice for internal management and delivery of grant portfolios, improving value for money.
Complete. The programme has utilised programme management expertise to improve the efficiency of its grant allocation, and shared learning internally. The programme has consulted across the department, but did not identify demand for support in delivering discrete projects in partnership with other teams or supporting other policy areas. However, engagement across the wider private capital mobilisation (PCM) agenda indicates potential synergies of the programme’s focus on robust impact management, with other FCDO programmes’ ambition to i) grow the evidence base around key barriers to PCM as well as ii) ways to evidence the impact of private finance mobilised. The programme team should follow the PCM agenda closely in the following reporting period and establish whether there is demand for longer-term collaboration on producing this evidence.
Major lessons and recommendations for the year ahead
Being fit for purpose and responsive to need: The programme should continue to balance work across areas of ESG disclosures and more ‘frontier’ impact measurement to ensure it is able to respond to market demand across the spectrum of impact reporting (from managing ESG risk to measuring and reporting positive/negative impact). In addition, in work relating to delivering financial or investment products (Output 3), the programme team should consider options around providing appropriate types of finance (e.g. grant versus development capital investment) to help promising new vehicles to launch.

Contribute to data collection, evidence and learning. The programme team should consider:

  1. how to consolidate learnings and outputs from grantees in the portfolio to support collaboration and learning.
  2. where the products that are published can add most value e.g. to fill knowledge or data gaps, to strengthen the theory of change and inform policy development (Output 4), and whether this should form set milestones in the programme’s logical framework or tracked more informally
  3. opportunities for IMPACT to contribute data and evidence that will help develop the private capital mobilisation agenda. This could include connecting wider PCM programming to existing impact management frameworks, or directly supporting evidence generation around the impact of private finance mobilised.

Continual monitoring of delivery model. This includes ensuring effective and efficient future CfP deliver effective and efficient engagement with prospective grantees and onboarding of successful applicants. The team should continue to assess its own capacity constraints in working with new partners and find ways to manage these effectively, drawing in additional support where needed. Given established grant delivery patterns, the team should seek to make recommendations to the Head of Department regarding changing the reporting timeframe to May-June in order to allow for grants to deliver in full before Annual Reviews are submitted.

In response to an evolving policy landscape and private sector around ESG and impact investment, where mainstream institutions are started to regulate and adopt ESG frameworks into financial accounts and regulate sustainability investment, the team should consider whether any amendments to the Theory of Change are needed – especially to evaluate whether support delivered through FCDO to grow the impact investing market is still likely to achieve outcome and impact objectives.

While past engagement for the programme has often focused on private impact investors, the programme team should consider how it can better engage development finance institutions around uptake of new impact management standards.

The programme team should continue to work closely with our impact and equalities adviser to consider how evidence on the impact of disclosures and standards as well as new financing vehicles in relation to gender can be aggregated from delivery partners – and inform future interventions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
There has been no change in the Theory of Change – and it remains valid for the objectives of FCDO and PSCMD..

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to deliver towards the outcome- and impact-level objectives.
(1) (4) Through grant support for the GSG Impact network, the programme will continue to use its grants to enable EMDE voice on impact investment and ESG by building networks in EMDEs and showcase evidence here in international fora (such as G20 and FFD4). Further, within the impact investing community, we have continued to create efficiencies through the consolidation of principles and guidelines for reporting, managing and disclosing impact – increasing interoperability of data and strengthening impact pathways between market participants. A more efficient process should encourage more investors to allocate more effectively.
(2) The IFRS Foundation established the ISSB in 2021 to develop standards that will result in a “high-quality, comprehensive global baseline of sustainability disclosures focused on the needs of investors and the financial markets”. The widespread adoption of ISSB across countries has enabled the mainstreaming of ESG into the financial analysis and reporting (of who). IMPACT has provided grants directly to IFRS Foundation to consolidate a technical assistance and guidance offer on implementation in EMDEs. Further, the programme explored new avenues for supporting effective ISSB implementation directly in EMDEs – for example, partnering with FSDA to support African regulators in adoption of standards. The programme team will continue to support coordination between implementation partners, beyond the grant recipients. Progress can only be made with joint understanding of the challenges, opportunities and barriers to ISSB adoption across key market actors (regulators, governments and standard setting bodies)
(3) The programme has enabled organisations developing impact investment standards to engage a broad range of market participants (asset owners, asset managers, investees) in building consensus on, for example, structuring impact reporting (Impact Frontiers) and gathering impact data efficiently (JIMF). Socialising impact management, particularly in EMDEs, could become increasingly important to inform decision making as aid budgets are more constrained.
However, given the mainstream adoption and formalisation of impact investment and ESG, with a number of market actors and governments revising investment priorities, the programme team should evaluate the Theory of Change in the next reporting period and assess whether any amendments should be made.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The Impact Investment ecosystem is a small but vital segment of global capital markets. The grants under the IMPACT programme demonstrate how ODA funding can be deployed to shape standards and decision-making that integrates ‘impact’ within the global financial system and help to define impact in investment analysis and management. This is vital for financial sector actors to make investment decisions which can have societal and environmental benefits in EMDEs. There is opportunity to derive further value from this programme if the research and (financial) product development can be used to support development actors in targeting key market barriers to private sector development. Engaging local capital markets, supporting pragmatic sustainability regulations and offering thought leadership on mobilising capital to deliver impact.
With increased risks around ‘ESG’ ‘backlash’ and uncertainty surrounding donor grant funding it is vital that the IMPACT programme provides strong evidence and clarity on the value of the impact investing ecosystem. The programme plays an important role in combatting impact washing (where institutions make false or unsubstantiated impact claims) and ensuring constrained developmental finance maximises growth opportunities in developing countries and the UK.
## C. DETAILED OUTPUT SCORING

Output Title	Development of standardised methods and techniques for managing impact
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: # of grantees creating, improving, or increasing the usage of methods of measuring and managing impact	6	6 – OPIM, GSG Impact, FSDA, JIMF, Impact Frontiers and University of Cape Town.
1.2: % of grantees that use any formal impact measurement and management framework, or recommend that their users do	100	100%

Briefly describe the output’s activities and provide supporting narrative for the score.
The aim of this output is to develop standardised methods and techniques for managing impact and targets.
Indicator 1.1 addresses the lack of an accepted framework for the collection of impact data to enable comparison of impact performance and give confidence to investors on achieved impact. We have made substantial progress across this indicator. Last year, the programme team took a comprehensive approach to impact management, adoption and learning – for instance, supporting and amplifying the voice of emerging markets in the development of sustainability disclosures (e.g. with GSG Impact network) and funding for the IFRS Capacity Building Partnership Framework, which brings together donors on support for these standards.
This year, the team built on this evidence to deliver on specific challenges related to the implementation of standardised impact management practice. Collectively, each of these grants will continue to build consensus (including EMDEs) and collective actions on impact data management and reporting:
- Financial Sector Development Africa (FSDA) is supporting Ghana and Nigeria to adopt ISSB, leveraging the FSDA network to work with key African regulators. FSDA have hosted multiple workshops with regulators and capital market actors to consider application of the standard across the economy – including ensuring that risks and opportunities presented by the standard are considered. FSDA are also working closely with the IFRS ‘Partnership Framework’.
- GSG Impact is developing impact transparency and measurement learning hubs across its network private sector impact investment hubs (National Partners) – spanning over 50 countries. Building on the market engagement last year, the resources and guidance that were produced are being consolidated and offered more formally to a network of participant countries to engage with further.
- Impact Frontiers (IF) is developing a standardised framework for impact reporting from asset managers to asset owners. Work delivered under the IMPACT grant is helping engage a range of market participants across the value chain in the framework’s development. IF is reporting increased engagement from asset owners in demonstrating impact in their portfolios – vital in effort to support international investment into EMDE – including, for example, engaging on workshops with the Pensions for Purpose group (and underlying asset owners).
- Operating Principles for Impact Management (OPIM): are expanding the adoption of investment principles in EMDEs, through in-person and remote engagement in Africa and Asia– enhancing the credibility of impact investment strategies to deliver on development objectives. Further, through engagement with British International Investment (BII) OPIM are leveraging best practice across UK development network to inform the management principles further. In the past year BII have partnered with OPIM in delivery of workshops in Africa (Nairobi).
In addition to building consensus, our grants that will also address specific issues in impact data:
Joint Impact Model Foundation (JIMF) – is addressing a critical issue of data management, disclosure and analysis of carbon emission and risk through the banking sector. JIMF is working in Bangladesh with the central bank to embed data management systems to collect and determine carbon intensity of underlying banking portfolios. Measuring and forecasting carbon emissions across a large portfolio of investments and assets is a key issue with emerging disclosure regulations on carbon (for instance, within ISSB). Tackling data challenges will enhance the usefulness of emerging regulation. It is expected that demonstration of the tool in Bangladesh will result in further uptake in Asian countries.

University of Cape Town (UCT) – Whilst there has been a sustained improvement in direct impact measurement, there is a need for development actors to consider the broader and transformational aspects of an investment or investment strategy. UCT, in coordination with Agora Global are developing a toolkit to measure and target systemic impact in investments. The grant will develop this toolkit and test it with key development actors. This is coinciding with increased policy work on systems and market led approaches to development finance[3].
[3] Driving market-level changes in impact investing - British International Investment
Describe any changes to this output during the past year, and any planned changes as a result of this review.
None.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The past AR recommended that the programme team evaluate where the IMPACT programme could promote progress on more, new, frontier impact measurement. As described above, the IMPACT programme met this recommendation by using last year’s evidence and partnership development to deliver on specific issues relating to impact management – particularly with grants with Impact Frontiers (standard framework from reporting), OPIM (principles for impact investors across investment and management), University of Cape Town (standards for systemic investment indicators).
Recommendations for next year:
Given grantees’ rapid progress in developing new impact measurement and management methods, the programme team should consider how it can further leverage FCDO’s network in the UK and at Post to engage key market actors including development finance institutions as well as impact investors within or with a specific focus on EMDEs.

Output Title	Development and/or adoption of tools and services for use by ecosystem actors
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1: # of grantee's tools or services in development or in market	6	6: JIMF, OPIM, GSG Impact, CFF, University of Cape Town, IFRS Foundation
2.2: % of grantee's whose tools and services are demonstrating progress toward uptake by users and/or the public, as predicted in their milestones	100%	100%

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicator 2.1 focuses on tools or services in development or in the market. During the period under review, the programme was able to finalise grant agreements with six grantees.
Of particular significance are the ‘Reporting Norms’ under the Impact Frontiers grant. Here, for the first time, how impact reports are described, presented and compared are to be standardised across the industry. We consider this vital for the formalisation of impact management – and to raise the opportunities for stakeholders (including investors) to more effectively scrutinise results (driving up performance).
Likewise, OPIM has continued to promote the principles for impact management across its members and with new potential signatories and continued to see further adoption from fund managers. Further, emerging market participants have been engaging with the delivery team and use-case examples have been developed – ready for further engagement and publication later this year.
IFRS Foundation’s work developing an ISSB Roadmap Development Tool (under development), is building on experience and evidence gathered in jurisdictions adopting ISSB standards early, to identify practical ways to support adoption in new markets, especially targeting regulators in EMDEs.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes expected to this output
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
No recommendations have been made for the year ahead under this output

Output Title	Adoption and/or development of new financial or investment products for investors and investees
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1: # of grantee financial or investment products in development or in market	1	1 - Collaborative for Frontier Finance (CFF)
3.2: % of grantees developing financial or investment products, who are making progress toward capital raise and disbursal as predicted in their milestones	N/A	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focuses on the development and/or adoption of financial or investment products for investors and investees and has seen one grant delivering on this output.
New impact investing products facilitate an increase of the volume of impact capital flowing towards high-impact businesses in sub-Saharan Africa and South Asia. The IMPACT programme has focused on underserved sectors and/or the creation of prototype investment products and vehicles which have the potential for scale or widespread replication.
Indicator 3.1 focuses on the number of grantees with financial or investment products under development or in market.
One grant project is linked to this output – with the Collaborative for Frontier Finance (CFF). CFF engages via its network of local capital providers (LCPs) and impact funds to design effective support for LCPs to build capacity and attract both local and international finance. In this reporting period, CFF, using IMPACT grant assistance, has established a technical assistance vehicle for LCPs with an accompanying fund administrator, LAUNCH+. The combined legal, accounting, technical and impact services delivered through the technical assistance facility will work to enhance the ability of funds to raise capital – and are expected to begin provision to LCPs in 2025.
There is also an additional operating line of credit being established under LAUNCH+. This could be an opportunity to help LCPs build track record and, again, increase the likelihood of investment. Stakeholder engagement exercises indicate positive feedback from development finance institutions (DFIs) – potentially enabling DFIs to get exposure to smaller, growth businesses which are vital to economic development in EMDE, particularly Africa. This was described extensively as part of the GSG Impact grant segment which brought together a DFI working group on SME financing – outlining that local capital providers could act as useful intermediaries useful to increase SME and growth business financing.
IMPACT programme will continue to assess the ability of LAUNCH+ facility, and its underlying funds, to attract development finance.
Linked to this indicator, 3.2 assesses the percentage of grantees developing financial or investment products, who are making progress toward capital raise and disbursal as predicted in their milestones. As the grants are at the initial stages of project preparation we have not scored at this stage. We expect progress on this, as the LAUNCH+ facility becomes established.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to the output
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In light of early evidence on interest in new financial vehicles supporting LCPs, the programme should consider what type of future support would be most appropriate to help vehicles launch, evaluating the merits of grant/technical assistance as well as the possibility of development capital investment.

Output Title	Knowledge and learning from grants
Output number:		4	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Indicator 4.1: # of Programme learning engagements held (including those held with other funders, sharing lessons learned, or generating evidence on market-building interventions in the sector, and including the annual grantee learning event)	6 (14*)	6 (14*)
Indicator 4.2: # of Programme learning publications (including grantee case studies / success stories / knowledge products / thought pieces)	5	5

* Expected outputs by the end of FY (end of march)
Briefly describe the output’s activities and provide supporting narrative for the score.
The output focuses on the knowledge and learning dissemination from the programme grantees. For many of the grants the programme engagements are often situated at the end of the grant period – which runs to end of March 2025. We would therefore expect to report on these in the next AR period, February 2025 - February 2026.
For output 4.1: Four programme learning engagements were held during this reporting period –Joint Impact Model Foundation’s (JIMF) Financial institutions engagement, FSDA roundtables with African Regulators and a draft of the Collaborative for Frontier Finance network survey on local capital providers. This missed the expected target of 6 – however, 14 learning engagements are expected to be delivered by March 2025.
CFF survey – expected (upcoming)
CFF has an initial result reported for its annual survey of the local capital providers in its network. This data will provide evidence for DFI and impact investors to utilise this type of intermediary to extend finance to small and growing businesses. In addition, this is part of formalising the asset class for broader capital markets – where use of financial institutions is most prevalent form of financing for SMEs. FCDO will continue to engage directly and with other development actors – such as Financial Sector Deepening Africa Investments (FSDAi)
FSDA roundtable on ISSB implementation roadmap
One roundtable has taken place in Kenya Nairobi in January – bringing together regulators, and ministries. The aim of roundtable engagements is to assist in establishing an implementation pathway for ISSB standards. Further details will be provided at the end of the grant period – include next steps/actions.
JIMF – 2 completed
The Joint Impact Model Foundation conducted two key workshops engaging financial institutions in Bangladesh. Boosted by the MoU established between FCDO, JIMF and the Bangladeshi Central Bank there was strong engagement; all of the major banks in Bangladesh attended (60) and over 35 non-banking. The JIMF team will follow up for specific work on 7 of the banks portfolios – which will occur over the next annual review period. Participants in the workshops and detailed analysis were motivated by how the reporting could attract climate and adaption finance – this could be explored by green finance policy teams.
The workshop has also created demand in nearby jurisdictions in NE India and Sri Lanka.
GSG Impact
As part of the GSG Impact grant a working group was established between Development Finance Institutions, Public Development Institutions and other key stakeholders including thought leaders to share experiences and challenges related to SME finance mobilisation. With the aim to co-create solutions. Two of these workshops have occurred and have resulted in the development of a) data sets which outline investment into SMEs using information from DFIs and b) a set of success factors which development actors can use to support mobilisation for SMEs. It is likely that this will be leveraged in a form of commitment to use over the course of next year and inform policy objectives related to development conferences – such as UN Financing for Development.
For output 4.2: The 5 scored under this indicator was a result of grants awarded during the previous reporting period finalising and publishing reports within this reporting period.
GSG delivered a landmark report “Impact Transparency from the ground up”. This report outlines the key challenges across jurisdictions in Africa and Asia – using private sector engagements from the GSG Impact network hubs. This will inform policy makers, including FCDO, on the impact financial regulations related to impact reporting in EMDEs.
This was presented to the G20 Sustainable Finance Working Group to incorporate voice of EMDE and particularly SMEs to consider how regulatory and policy changes could increase challenges for these businesses.
GSG also submitted position papers into consultations and working groups related to impact standards: G20, Impact Weighted Accounting Standards and ISSB.
Finally, CFF had published last year’s survey of local capital providers. This presented evidence for CFF’s work delivered this year to develop a vehicle to support local capital providers (LAUNCH+).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The programme team have decided not to make changes to output 4.1 & 4.2.
However, the team have removed indicators 4.3 and 4.4 on unique views of publications and grantee feedback on programme events, respectively. Both are no longer relevant as the programme is no longer managed by an external supplier. The team will continue to reflect on how to track the engagement on products either through individual grantees or through re-establishing a programme communication channel (e.g. on gov.uk or LinkedIn).
No changes expected to this output for next review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
As recommended in the previous Annual Review the programme team have removed indicators 4.3 & 4.4, as their use in determining engagement is not necessarily causal, and data collection would be disproportionately burdensome considering the programme is no longer managed by a single supplier. Other examples, using more attributable behaviour or investment change, should be explored with care to understand the practicality of establishing causality between grant delivery (e.g. learning products published, engagements held) and behaviour change. Programme learning events for all grantees (under indicator 4.1) are unlikely to directly feature in any upcoming grant agreements. Any partner convening organised by the programme team will be delivered based on demand from partners and can be highlighted in future Annual Reviews.

## D: VALUE FOR MONEY

Key cost drivers and performance
The key administrative cost driver during the period is internal resource (financed by operating costs, not IMPACT programme spend) and this is now likely to continue to be the case. This will include a programme manager (50% FTE) plus leadership and oversight of an impact investment policy advisor (50% FTE). Grants are continuing to be committed with partial or full spend associated this financial year. The IMPACT programme delivers good performance from an overall cost-benefit perspective.
VfM performance compared to the original VfM proposition in the business case
The impact programme has leveraged previous relationships with grantee partners whilst also conducting a call for proposals – capturing more applicants for funding – this has driven the VfM, breakdown below:

Economy: The programme continues to have no external delivery fees. This year, the programme team conducted a call for proposals and established 8 new accountable grants, assessing prospective grantees’ strategies for achieving economy (as well as efficiency, effectiveness, equity). The programme is managed in-house which drives economy and enables more programme budget to be used to fund grantees’ outputs.

Efficiency: The call for proposals, this year, allowed the programme team to consider and compare a broader range of potential interventions, and onboard partners within a relatively short timeframe following confirmation of budgets. Having some grants with existing partners allowed for strengthening of relationships and ongoing conversations around future interventions, as well as timely delivery of outputs (though new grantees also delivering to agreed timelines). Despite the challenges associated with a small window of time to secure Accountable Grant Agreements, the programme is expected to fully utilise its budget this FY. The programme team will continue to consider how to make the process for onboarding new partners as efficient as possible, given the likelihood of another one-year budget cycle for FY 25/26.

Financial forecasting: During the review period there has been a reduced variance on financial forecasts compared to previous years. This is a result of broader sourcing of new grant agreements and a full call for proposals to the market – which supported better allocation of budget across priority objectives.

Effectiveness: The IMPACT programme has continued to make significant progress on establishing relationships with key market stakeholders. Funding provided through IMPACT has often enabled partners to leverage support from other donors (governments, foundations) and catalysed delivery of outcomes. The programme’s focus on assessing impact of regulatory and voluntary standard setting in EMDEs has provided FCDO useful evidence and insight into key enablers and barriers to private capital mobilisation. Similarly, work on understanding the needs of local capital providers is building evidence on ways to deepen financial markets in EMDEs, mobilise capital and ensure this is generating intended impact. Most projects within this FY have had relatively short delivery timeframes (6-7 months), and the programme team should therefore continue to consider where future funding or engagement around outputs could contribute to delivering outcomes.

Equity: The Programme considers gender equity in all grant proposals. However, similarly to last year, as many of the grants are interventions at a systems level, they do not focus specifically on gender inclusivity. The Programme team should consider engaging with delivery partners on evidence building on the accessibility of capacity building or market building in relation to gender. The programme team will review the selection criteria for grant proposals with the gender and inclusion advisor over the next reporting period.
Assessment of whether the programme continues to represent value for money
The year under review saw good progress on establishing a quality pipeline of grants and forming protocols to manage the portfolio effectively. The programme represents good value for money.
We expect the value for money to further improve over the coming review period as the programme team will likely have an opportunity for either a call for further proposals much earlier in the financial year or grant extensions which will ensure that the IMPACT programme will partner with ecosystem actors best placed to deliver on the objectives. As the number of grants has increased while increase in internal resources (staff time) is unlikely, the programme team will explore options to see how they can streamline grants, for more efficient management.

E: RISK
Overview of risk management
The programme has a risk rating of “moderate” and the programme has been able to deliver within the Department’s risk appetite. The increased budget, compared to last year, has allowed for more grants, however, ongoing uncertainty from the fiscal environment has resulted in continued risks to public service delivery & operations, and policy and programme delivery.
This review period saw establishment of new grant agreements through in-house programme delivery. Key risks to highlight include:
Risk Category	Level of risk	Risk Appetite	Description and Mitigation Strategy
Public Service Delivery & Operations	Major	Cautious	There is a continued risk on the uncertainty over programme budgets, inhibiting the establishment of long-term partnerships. This is managed by establishing budgets early within organisational parameters and clearly communicating these to prospective partners. / There is also another continued risk that reliance on in-house programme management can slow programme delivery when resources are stretched, or capacity is reduced at FCDO. We continue to mitigate this by ensuring the programme is appropriately staffed and drawing on advisory input from across PSCMD. Further, continually reviewing the balance of in-house or outsourced programme management.
Strategy & Context	Major	Receptive	A continued risk is that an incoherent set of interventions increases the number of competing non-financial standards and poses challenges to interoperability of domestic taxonomies or does not align effectively with domestic policy objectives. This is continually managed by engaging in domestic implementation of standards and utilising the policy expertise for impact reporting frameworks.
Reputational	Moderate	Minimal	There is a new risk of an ‘ESG backlash’ – an abandonment of ESG strategies by investors, in favour of a renewed focus on short-term financial performance. There could be a misunderstanding between sustainability disclosures and political objectives which could undermine programme interventions. This risk is mitigated by ensuring that both FCDO and the programme team communicate clearly the objectives of grants, as well as the value of ESG and impact investment approaches in terms of social/environmental as well as financial and economic objectives. / There is also a continued risk that due to programme activities focusing on investment and the private sector activities, this could lead to criticism related to spend that delivers on the ODA mandate. This is managed by maintaining transparency around all grants and seeking appropriate ODA approvals at right levels. / Additionally, as delivery is in-house, there is a risk of perception of bias towards selecting grantees who have existing relationships with FCDO. The programme has established governance protocols, agreed by Head of PSCMD, to ensure robust internal processes for selecting grants and regularly engage with commercial teams.
Policy & Programme Delivery	Moderate	Cautious	There is also a continued risk that the grants are ineffectively managed. The risk has been managed by establishing a Programme Team with adequate Programme Management processes in place. This includes clear deliverables attached to prospective payments under the Accountable Grant Agreements.
Financial & Fiduciary	Moderate	Cautious	There is a continued risk that as the programme funds short-term grants for 1-2 years, this could result in poor value for money and reduced effectiveness in achieving results. This is effectively managed by following value for money guidance and ensuring best allocation of resources. Further, policy evidence and grant products are reviewed prior to new grants executed – to ensure the funding is always additional and meeting the IMPACT programme objectives. / There is also continued risk that programme funds are inadvertently channelled to disreputable organisations and that the grantees do not use the funds for the intended purposes. However, robust due diligence processes are completed, and regular reporting is embedded in the agreement to mitigate this risk.
Safeguarding	Minor	Minimal	As the programme may involve service providers working with vulnerable people, there is a risk that service provider staff behave inappropriately and cause harm to children and consequently reputational risk to FCDO. Additionally, there is also a risk that the programme fails to effectively implement the 'Do No Harm' principle by not giving adequate consideration to safeguarding principles. / These risks are managed by abiding by and implementing FCDO safeguarding guidance and ensuring that all partners have their own processes in place. Due diligence is conducted to test robustness.
People	Minor	Minimal	There is a continued risk that programme staff capacity is low and is not effectively staffed with experienced staff who aware of the broad needs of programme delivery. Through proactive recruitment and appropriate training, this risk has been mitigated as there is an established Programme Team in place. Further, we continually review the suitability of in-house approach and outsourcing of policy expertise programme support.

The risk register on AMP is monitored regularly and updated quarterly to ensure compliance with the PrOF rules.
F: PROGRAMME MANAGEMENT:
DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise performance of partners & FCDO, notably on commercial/financial issues
The IMPACT Programme is delivered internally, using FCDO programme management systems, budgetary tracking and procurement.
To manage a portfolio of grants at varying stages of delivery we continue using the series of specific protocols, developed last year, to ensure sufficient oversight of the spend and interventions under the Impact Programme, these include:
- Due Diligence pack approved by PRO and SRO
- Standardised Project support Document – Approved by SRO
- Standardised Accountable Grant Agreements – Approved by SRO
- Supplier application (to central FCDO) – following Call for Proposals through the International Development Funding site
- Projected deliverable and spend trackers
Out of 8 funding agreements, 5 are to delivery partners for whom this is the first direct financial contribution from the programme, demonstrating the broadening of the pool of potential partners to the programme, as well as strengthening relationships with existing collaborators.
The reporting systems for the grantees in place are: quarterly meetings with partners and additionally on an output-by-output basis, set alongside payment requests – to ensure quality assurance of products prior to making payments. The quality of this reporting has been good, however the programme team will look to take a more standardised approach – as we continue to expand the number of grants.
The Impact Programme team has performed well, particularly in light of significant new responsibilities and spending pressures. This has resulted in several active grants – with prospective grants into the next FY.
Effectiveness of programme management
Compliance with the Supply Partner Code, drawing on advice from Commercial Directorate. Compliance with the new cost and transparency requirements, highlighting any profit variance and challenge and use of Open Book Accounting
No longer relevant to this programme, as there is no longer a contracted delivery partner.
Performance of Partners, including summary of the Strategic Relationship Management scorecard assessment for each delivery partner
No longer relevant to this programme, as there is no longer have a contracted delivery partner. We should consider further measures to manage grantee relationships, now in-house.
Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

[1] https://www.impact-taskforce.com/reports
[2] https://www.theimpactprogramme.org.uk/resources/