## Annual Review Template

Title: IMPACT Programme
Programme Value £ (full life): 150.5m		Review date: May 2026
Programme Code: 202939	AMP start date: 18/12/2012	AMP end date: 31/12/2035

Summary of Programme Performance
Year	1	2	3	4	5	6	7	8	9	10	11	12	13 (2026)
Output Score	A	A	A	A	A	A	A	A+	A	B	A	A	A
Risk Rating	M/H	M/H	M	M	M	M	M	M	M	M	M	M	M

DevTracker Link to Business Case:	Link here
DevTracker Link to results framework:	Link here

A. SUMMARY AND OVERVIEW

Description of programme
The IMPACT Programme aims to catalyse the market for impact investment, the practice of deploying capital to deliver measurable social and environmental outcomes alongside financial returns. By strengthening the impact investing ecosystem, the programme supports more effective allocation of capital towards development priorities and helps address market barriers that limit private sector contributions to the Sustainable Development Goals.
The programme works by making grants to organisations which develop impact management standards and approaches to sustainability disclosures, provide capability training, practical tools and technical assistance to impact investors, and which develop innovative financial models to support impact investments.
These interventions help improve how impact is defined, measured and managed (known as IMM – Impact Measurement and Management), while also seeking to improve the conditions for capital to flow to Emerging Markets and Developing Economies (EMDEs) through better impact investment data, stronger standards and more coordinated engagement across investors, financial institutions and market actors. The reach of the programme includes impact investors, asset managers, development finance institutions (DFIs), regulators, banks and the wider investment eco-system including regulators and standard setting bodies.
Most, if not all, of the grantees this year were previous grant recipients of the programme following a Call for Proposals during the last reporting period and were chosen where this year’s proposals represented an evolution of their work.
Summary supporting narrative for the overall score in this review
The programme has performed well at output level during the review period. Two outputs are assessed as meeting expectations, one moderately exceeds expectations and one is moderately below expectations. The strongest delivery has been in the development of standards, practical tools, guidance, technical assistance and learning activities that help investors, financial institutions and other market actors define, measure, manage and report impact more effectively. Progress has been slower on the development of new financial vehicles: the new investment fund platform (see Output 3) has reached an important regulatory milestone, but is not yet operational, and another potential initiative is at an early stage.
However, the review did not find evidence being captured of meaningful changes in investor decision-making, capital allocation or the flow of finance, possibly because the programme does not have the right evidence gathering methods to survey the investors being reached by the work of the grantees over a relevant period of time. It also found that some of the most promising activities now operate beyond pure impact investing, for example, by engaging banks, regulators, DFIs and wider market actors on disclosure, data, standards and market readiness. This raises a strategic question about whether the programme should still be focussed on being a purely impact investing focussed programme, or whether it has become a broader market-shaping instrument for capital mobilisation into EMDEs.
Major lessons and recommendations for the year ahead
Overall, the review found strong evidence of delivery at output level, including indications of uptake of impact standards, readiness and harmonisation, but less evidence that this has translated into changes in financial decision-making. Getting from standards, tools and partnerships to changed investment behaviour is complex and would require more detailed surveys or follow up of participants, for example, to establish a causal link. The reduction in budget and the recent shift from a delivery partner to in-house management makes this more challenging to undertake. Additionally, while the financial vehicle development work provides useful learning on domestic capital mobilisation, it also appears more exposed to delivery risks than the work developing standards, tools and partnerships.
The programme team should consider three actions:
- First, complete a strategic stocktake of the last two years of delivery, identifying which interventions have shown the strongest evidence of uptake, where there is real market demand and how the programme best fits with wider FCDO work on private capital mobilisation. This may lead to a revised vision for the programme’s role and a revised Theory of Change.
- Second, adjust the results framework so output indicators become better proxies for outcome achievement, for example, by tracking whether standards or tools are formally adopted by target actors, used in investment, disclosure or due diligence processes or generate follow-on engagement or funding without further programme support.
- Third, review whether financial vehicle development should remain part of this programme. Since the objective of the programme is to promote financial innovation, future support may be better channelled through other instruments with tried and tested appraisal and risk management capability. This would allow the IMPACT programme to focus on the standards, data, evidence and partnerships that are needed to help deploy capital more effectively.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s Theory of Change is unchanged from the previous Annual Review.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

For Outcome 1, the programme shows evidence of investors, financial institutions and asset managers adopting or beginning to integrate programme-supported tools and standards, but not yet of significant changes in capital allocation or financial decisions, or at least, the causal links are not yet being captured. For Outcome 2, the strongest evidence is around harmonisation, shared standards, improved data and better alignment between market actors; development of financial vehicles/instruments remains narrower and less advanced, with one initiative not yet operational and another at an early stage. For Outcome 3, the programme is contributing to awareness and emerging practice among targeted networks and institutions, especially through training, technical assistance, publications and convening, but there is not yet evidence of widespread change across the wider impact investing market.
Given the long Theory of Change, reduced future budget and relatively small grant portfolio, achieving the original outcomes and intermediate steps towards longer-term development looks increasingly challenging. In the year ahead, the programme should use the stocktake recommended in Section A to clarify its future role, tighten the results framework and prioritise activities with the clearest route to practical use by investors, intermediaries or financial institutions. No significant changes to expected outcomes on gender equality or protected characteristics have been identified.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue, subject to the stocktake recommended above. It is delivering well at output level, particularly on standards, tools, data, learning and partnerships that improve how market actors assess and manage impact. In the context of the wider portfolio, the programme remains relevant because it supports priorities on mobilising private capital, particularly on delivering impactful outcomes, strengthening domestic capital markets, improving data and evidence and supporting regulation. To improve portfolio fit, the programme could prioritise work that complements this most clearly: evidence and tools that can be used by investors, supporting standards and data that reduce barriers to investment and building partnerships that connect programme learning to wider policy and investment work. Financial innovations such as new vehicles or instruments may be better done by other FCDO instruments with stronger commercial appraisal and risk management capability.

## C. DETAILED OUTPUT SCORING

Output Title	Development of standardised methods and techniques for managing impact
Output number:		1	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
Indicator 1.1: # of grantees creating, improving, or increasing the usage of methods of measuring and managing impact	6	6
Indicator 1.2: % of grantees that use any formal impact measurement and management framework, or recommend that their users do	100	100

Briefly describe the output’s activities and provide supporting narrative for the score.

Impact standards and norms are essential in IMM because they create consistency, credibility, and comparability across a rapidly growing but still fragmented field. Without them, it becomes difficult for investors, policymakers, and organisations to make informed decisions or scale impact effectively. Since IMM involves multiple actors (investors, DFIs, foundations, governments etc), each historically using different definitions of “impact”, stakeholders often talk past each other, making alignment and collaboration harder without a common accepted language.

Six grantees delivered clearly against this output during the reporting period:
- Impact Frontiers published Version 2 of its Impact Performance Reporting Norms as an Exposure Draft (a draft for wider stakeholder consultation) establishing a standardised, open-access framework for how investors report on impact. The Norms are designed to enable comparability across asset classes and geographies, with tailored adaptations developed for DFIs, asset owners and public markets investors. A global pilot engaged 211 organisations in testing and refining the framework, with 92 signing up as Founding Adopters.
- Joint Impact Model Foundation (JIMF) developed an International Sustainability Standards Board (ISSB)-aligned methodology for measuring GHG emissions and climate risk across financial institution portfolios, working with Bangladesh Bank. The approach goes beyond disclosure toward linking emissions data to climate finance opportunities, representing a significant methodological evolution from measurement to mobilisation.
- University of Cape Town (UCT)/Agora Global produced the Systemic Impact Investing Standard (SIIS), a codified framework for applying a systems lens to investment decision-making. The standard was validated through technical assistance engagements with asset managers and has been published in the Stanford Social Innovation Review, contributing to the academic and practitioner evidence base.
- Global Impact Investing Network (GIIN) continued to refine and build consensus around the Operating Principles for Impact Management (OPIM), with a focus on expanding adoption among EMDE-based investors and fund managers. Engagement with British International Investment (BII) supported alignment between the Principles and UK development finance practice.
- GSG Impact advanced impact transparency methodologies across its network, contributing to global standard-setting processes including submissions to the G20, International Sustainability Standards Board (ISSB) and Impact Weighted Accounting Standards consultations. GSG's work on the Global Impact Economy Index provides a cross-country benchmarking methodology for impact investment ecosystems.
- International Financial Reporting Standards (IFRS) Foundation continued to develop its approach to supporting ISSB implementation in EMDEs, building on the Capacity Building Partnership Framework. The Foundation's technical assistance methodology draws on early-adopter experience to identify practical pathways for jurisdictions considering adoption, contributing to the standardisation of sustainability disclosure methods globally.
The available evidence suggests this output is on track. The evidence suggests that the quality and maturity of methods being developed has improved since last year, with several partners moving beyond framework design into implementation support and early adoption. The main evidence gap across partners remains at the outcome level: while methods and standards are being produced and taken up, evidence that these methods are changing actual investment decisions or capital allocation remains limited and early-stage.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes to indicators or milestones are proposed, however, the team may wish to consider whether the indicator framing (which counts the number of grantees active rather than the depth or quality of methods produced) remains the most useful measure of progress, given that several partners are now moving from method development into implementation and adoption.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year's review recommended that the programme leverage FCDO's network to engage DFIs and EMDE-focused impact investors in the uptake of new impact management methods. There has been meaningful progress on this. Impact Frontiers engaged 20 DFIs and MDBs (including British International Investment (BII), International Finance Corporation (IFC), European Bank for Reconstruction & Development (EBRD) and Proparco) in developing its Reporting Norms, and GIIN co-delivered regional workshops with BII in Africa. JIMF's work in Bangladesh was conducted in partnership with the central bank, engaged substantially with DFIs and engaged all major domestic banks. The Private Infrastructure Development Group (PIDG)-funded secondment into the EMDE Investor Taskforce has also created a channel for connecting programme-funded standards work to institutional investor engagement at a senior level. Collectively, these represent a step-change in DFI and institutional engagement compared to previous years.
The most significant lesson from this year is that methodology and standard development, while necessary, is not sufficient to change investment behaviour. Several partners have identified that the gap between producing tools and influencing capital allocation requires active intermediation: structured technical assistance, follow-on engagement with adopters and mechanisms to link disclosure to financing decisions. This "disclosure-to-finance" gap is a recurring finding across the portfolio and has implications beyond the programme, including for FCDO's wider private capital mobilisation agenda. For the year ahead, the programme team should consider how to systematically capture evidence on whether the methods funded under this output are being used in practice by investors and intermediaries, e.g. via light-touch qualitative follow-up with key adopters. This would significantly strengthen the evidence base for future outcome-level claims.

Output Title	Development and/or adoption of tools and services for use by ecosystem actors
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
Indicator 2.1: # of grantee's tools or services in development or in market	6	6
Indicator 2.2: % of grantee's whose tools and services are demonstrating progress toward uptake by users and/or the public, as predicted in their milestones	100	100

Briefly describe the output’s activities and provide supporting narrative for the score.

Six grantees have tools or services in development or in market, meeting the indicator 2.1 milestone. On indicator 2.2, six of six are demonstrating progress toward uptake:
- IFRS Foundation delivered a web-based Roadmap Development Tool (RDT), an interactive platform that helps jurisdictions plan and sequence ISSB adoption. The tool has been tested through workshops with EMDE regulators and standard-setting bodies. All deliverables were met.
- JIMF deployed its GHG and climate risk tools across 11 Bangladeshi financial institutions, with data now actively being generated and fed into central bank reporting processes. This is one of the clearest cases of demonstrated uptake in the portfolio: tools are in daily operational use rather than at pilot stage.
- GIIN delivered regional workshops, use-case materials and practical guidance supporting EMDE fund managers and investors in applying the Operating Principles. Engagement events in Africa and Asia, including sessions co-delivered with BII, supported continued adoption.
- GSG Impact consolidated its impact transparency hubs into a structured service offer available across its network of National Partners in over 48 countries. GSG also produced a capital mobilisation how-to guide and country-level action plans for several EMDEs, providing practical tools for local actors.
- UCT/Agora Global deployed its toolkit to audit asset managers' investment processes and make recommendations for applying the SIIS. The training course functions as a service in its own right, with two cohorts delivered, oversubscribed 10:1, and TA recipients beginning to fund follow-on engagement independently. Plans to offer the course on a paid basis indicate a pathway to sustainability.
- Collaborative for Frontier Finance (CFF) developed an assessment framework for evaluating fund managers entering the LAUNCH+ platform and delivered a structured TA programme producing practical tools for five fund managers. The tools were well received and represent a functioning service offer for emerging fund managers. The broader LAUNCH+ platform through which these services are intended to be delivered at scale is discussed under Output 3.
This output meets expectations. The quality of uptake evidence varies across partners, from daily operational use (JIMF) and independently funded follow-on engagement (UCT/Agora Global) to network-level adoption (GIIN, GSG), but all six grantees are demonstrating progress.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes have been made to the output indicators or milestone targets. The composition of grantees contributing to this output is unchanged from last year. No changes are proposed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations were made under this output in the previous annual review.
The main lesson from this year is that the quality of uptake evidence varies significantly across partners. At one end, JIMF's tools are in daily operational use across 11 banks, and UCT/Agora Global’s TA recipients are independently funding further engagement, both representing strong uptake. At the other end, some partners report adoption through network membership or workshop attendance, which is a weaker signal. For the year ahead, the programme team should encourage grantees to report uptake evidence that distinguishes between awareness (e.g. event attendance, downloads), adoption (e.g. organisations formally committing to use a tool or standard) and integration (e.g. evidence that a tool is being used in ongoing investment or reporting processes). This would strengthen the evidence base for indicator 2.2 and provide a clearer picture of where the programme is genuinely influencing practice.

Output Title	Adoption and/or development of new financial or investment products for investors and investees
Output number:		3	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
Indicator 3.1: # of grantee financial or investment products in development or in market	2	1
Indicator 3.2: % of grantees developing financial or investment products, who are making progress toward capital raise and disbursal as predicted in their milestones	0	0

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on the development and adoption of financial or investment products for investors and investees. Only one grantee is delivering against this output:
- CFF's core product is LAUNCH+, an integrated platform structured as a Mauritius VCC that combines shared services, technical assistance and catalytic capital to support emerging fund managers investing in small and growing businesses in Africa. The platform is designed to centralise key operational functions, such as fund administration, legal compliance, governance and LP reporting, while also providing targeted capacity building and access to capital facilities (e.g. lines of credit). The assumption is that by reducing the cost and complexity of reaching institutional readiness, LAUNCH+ can help fund managers access available capital and that this would lead to increased access to finance for small businesses in frontier markets. After extended delays, CFF received formal Mauritian Financial Services Commission approval in March 2026 and secured certificates of incorporation and licences for both the umbrella vehicle and its first sub-fund. An assessment framework for evaluating and selecting fund managers has been developed, covering eight dimensions from investment strategy and fund economics to governance and capital readiness. CFF is currently identifying two fund managers for onboarding onto the platform under a cost-share model. LAUNCH+ can therefore be counted as one product in development, though it is not yet operational and no fund managers have been onboarded or begun receiving platform services.
- CFF also established a strategic partnership with NSSF Uganda during the reporting period, with a joint initiative ("Project Shujaa") to mobilise domestic pension capital into small business finance through a Fund of Funds structure targeting a first close of USD $35–50 million. This is at concept stage with no formal commitments, term sheets or binding agreements in place. It is not yet sufficiently advanced to be counted as a product "in development" for the purposes of this indicator.
- Against indicator 3.1, the milestone of two products is therefore partially met at one. For indicator 3.2 no capital raise was expected during this period. On balance, this output is moderately below expectations. The LAUNCH+ regulatory milestone is a genuine achievement after a protracted process, and the development of a structured assessment framework represents meaningful progress in platform design. However, the platform has not yet begun onboarding fund managers or delivering services, which last year's review anticipated would begin in 2025. The Project Shujaa partnership is promising but does not yet constitute a countable product.
Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes have been made to the output indicators. The milestone for indicator 3.1 increased from one (2025) to two (2026), but the evidence currently supports only one product in development. The programme team should review whether the milestone of two remains realistic given current delivery and clarify which products are expected to contribute. More broadly, the team should consider whether this output remains well suited to the programme's focus and delivery model (see recommendations below).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year's review recommended that the programme consider what type of future support would be most appropriate to help vehicles launch. CFF's experience this year sharpens this question. The focus on establishing a commercial financial vehicle sits increasingly apart from the programme's core strengths and strategic direction, which centres on standards, measurement frameworks and ecosystem-level approaches and tools. The programme's delivery model of selecting and funding a small number of strategic partners works well for this work, where the distribution of benefits is wide and risk of market distortion is low. It is worth assessing whether this approach is suited to choosing a financial vehicle to back in a nascent market without competitive sourcing, independent due diligence or structured investment processes (e.g. as employed in FCDO’s MOBILIST or FSDAi programmes). The concentration of Output 3 on one delivery partner, which is simultaneously the platform operator, the selector of participating fund managers and the FCDO grantee, amplifies these concerns. If FCDO wishes to continue supporting financial vehicle development for EMDE small business finance, this may require a different delivery approach, with stronger independent evidence of the market failure being addressed, a more open process for identifying the right intervention and coordination with DFIs and other instruments better positioned to bear the commercial risks involved.

Output Title	Knowledge and learning from grants
Output number:		4	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
Indicator 4.1: # of Programme learning engagements held (including those held with other funders, sharing lessons learned, or generating evidence on market-building interventions in the sector, and including the annual grantee learning event)	36	~50
Indicator 4.2: # of Programme learning publications (including grantee case studies / success stories / knowledge products / thought pieces)	5	~20

Briefly describe the output’s activities and provide supporting narrative for the score

This output focuses on the knowledge and learning generated and disseminated. The 2026 milestone for indicator 4.1 is 36 learning engagements; for indicator 4.2 it is 5 learning publications. This includes evidence key to priority areas of focus on private capital mobilisation, such as the potential impact on the financial sector of major climate risks, the systemic nature and severity of which could precipitate financial crises; and policy tools and interventions that could deliver more systemic economic, social and environmental value.
On indicator 4.1, the programme has generated a substantial volume of learning engagements across the portfolio. The most significant contributions include:
- Impact Frontiers delivered 12 monthly global pilot webinars on using the Impact Performance Reporting Norms, an open-access public good that outlines shared expectations for how investors report impact results. Four webinars for EMDE participants, regional events in London, Berlin and Tokyo, a year-long pilot with 45 Japanese investors, a learning cohort with 15 European VCs and over 35 Office Hours sessions with individual investors.
- JIMF conducted structured engagement workshops with 11 banks and over 35 non-banking financial institutions in Bangladesh, as well as central bank engagement sessions and a joint MDB meeting on how to implement climate related disclosures (ISSB IFRS S1 and S2-aligned disclosures)
- The EMDE Investor Taskforce (supported by a PIDG secondment and IMPACT-funded academic) held a Ministerial-led event at the World Bank Spring Meetings (40 participants), a roundtable with 10 investment consultants, Leadership Group meetings and multiple bilateral engagements with pension funds and asset owners.
- GSG Impact convened DFI-SME working group sessions, Coalition of the Ambitious convenings and global policy gatherings.
- CFF delivered TA group sessions and masterclasses across four pillars, peer learning exchanges among fund managers, and strategic meetings with NSSF Uganda. The Community of Practice’s first convening took place in April 2026, just outside the reporting period.
- UCT/Agora delivered two training cohorts and ecosystem engagement sessions with AVPA and other networks.
- GIIN held workshops and conference engagements, including events co-delivered with BII.
- IFRS Foundation delivered TA workshops with EMDE regulators and standard-setting bodies.
A conservative estimate, excluding bilateral sessions such as Impact Frontiers' Office Hours, puts the total at approximately 50 learning engagements, comfortably exceeding the milestone of 36. Impact Frontiers, JIMF and the Taskforce-related grants collectively account for the majority.
On indicator 4.2, the portfolio has produced a strong body of learning publications: Impact Frontiers published four Implementation Guides, three Case Studies, a White Paper on the standards landscape and co-authored research with Pensions for Purpose. The EMDE Investor Taskforce produced seven publications across its workstreams. GSG Impact published its Impact Economy White Paper and continued development of the Impact Transparency State of Play report. CFF produced a CoP Master Briefing Paper, a TA Deliverable Report and a pre-event briefing note. UCT published in the Stanford Social Innovation Review. The milestone of 5 is comfortably exceeded.
This output moderately exceeds expectations. Both milestones are exceeded, reflecting the maturing portfolio and the breadth of engagement and knowledge production across partners.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes have been made to the output indicators. The milestone for indicator 4.1 increased from 14 to 36, reflecting the expanded number of active grantees and the inclusion of planned engagements from each partner in the logframe assumptions. Indicators 4.3 and 4.4 (unique views of publications and grantee feedback on programme events) were removed in the previous review and have not been reinstated. No changes are proposed, though the programme team should note that the current definition of "learning engagement" is broad and encompasses activities of very different scale and reach. If the milestone continues to increase, a clearer definition or tiering of engagements (e.g. distinguishing major convenings from bilateral sessions) would help ensure the indicator remains a meaningful measure of progress.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year's review noted that indicators 4.3 and 4.4 had been removed and recommended exploring more attributable measures of engagement impact, while acknowledging the difficulty of establishing causality between learning outputs and behaviour change. Progress on this has been limited. The programme does not yet have a systematic approach to tracking whether publications or engagements lead to changes in practice. However, several partners have begun generating stronger evidence of engagement quality. Impact Frontiers reported an 83% satisfaction rate from EMDE-focused webinars and tracked repeat participation in its global pilot. UCT/Agora Global's course oversubscription (10:1) and high ratings (4.7/5) provide clear demand signals. These are useful signals that go beyond simple counts.
The key lesson from this year is that the programme's strongest learning contributions come not from standalone publications or events but from sustained engagement models, e.g. JIMF's bank-by-bank capacity building, Impact Frontiers' year-long global pilot, the EMDE Taskforce's structured workstream approach, where learning is embedded in ongoing relationships rather than delivered as one-off products. For the year ahead, the programme team should consider whether the current indicators (counts of engagements and publications) adequately capture this distinction. A light-touch qualitative assessment of the programme's three or four most significant learning contributions each year would add more value than increasing the numerical target further.

## D: VALUE FOR MONEY

Key cost drivers and performance

The main cost driver remains the grant portfolio, with programme management delivered in-house rather than through an external delivery partner. This supports economy by avoiding external delivery fees and allowing a higher share of programme resources to be used for grant activity. However, the in-house model also places significant demands on staff time.
VfM performance compared to the original VfM proposition in the business case

The programme continues to represent good value for money, but there is some variation across the value for money criteria:
Economy: The programme continues to benefit from having no external delivery partner fees. This is important given the relatively small annual budget and means a greater share of programme resources can be directed to grants and partner delivery.
Efficiency: The in-house delivery model remains efficient from a direct cost perspective but is a significant draw on staff time. Keeping the portfolio on track requires substantial PRO time for partner management, reporting, payment processing and delivery oversight, alongside input from the SRO and additional programme management support. Whether this is proportionate depends on the effectiveness of the programme’s activities, and on whether learning, evidence and partnerships are leveraged across the department’s wider priorities, including private capital mobilisation, data, standards and domestic capital markets. Having a strong focus on disseminating and embedding the learning from the programme across relevant FCDO teams would deliver more VfM than a focus primarily on the impact ecosystem-wide changes. This echoes the previous review’s recommendations to consolidate learning across grantees, use programme evidence to support wider private capital mobilisation work and continue monitoring whether the delivery model is efficient and adequately resourced.
Effectiveness: The programme is effective at output level, with the review assessing the overall output score as A. Its work on standards, tools, data, guidance and learning is important because these provide the foundations upon which later changes in investor behaviour, disclosure, due diligence and capital allocation can build. However, the review also raises a question about whether the current indicators are sufficiently demanding measures of progress along that pathway. Several outputs capture production, engagement, uptake or early use, but are still some distance from capturing the intended outcome-level changes in financial decision-making and flows of finance. This does not undermine the positive output assessment, but it does suggest that future effectiveness would be strengthened by tracking a clearer progression from development of standards and tools to adoption by target institutions, to practical use in investment, reporting or due diligence processes.
Equity: The programme continues to consider equity through its grant design and management processes, although many interventions operate at market or system level and do not directly target specific groups. The current review has not identified significant changes to expected outcomes on gender equality or protected characteristics.
Assessment of whether the programme continues to represent value for money
On balance, the programme continues to represent good value for money. It is economical to run, generates good outputs and has built partnerships and evidence that are effective and relevant to the department’s wider portfolio. The case for continued value for money depends on whether the programme can sharpen its focus and ensure its work is actively leveraged across the portfolio, including through more dissemination of the learning.

E: RISK

Overview of risk management
The IMPACT programme has an overall risk rating of “Moderate”. All risks are assessed and managed within the FCDO Risk Management Framework by the team using a risk register which is regularly reviewed.

This year there are 2 “major” risks that continue to be monitored and managed:

- Public Service Delivery & Operations: Resources – towards the end of the reporting period the programme experienced a significant resource reduction with the SRO, PRO and programme manager leaving in quick succession. While temporary cover arrangements are in place, any protracted delays in recruiting successors may impact delivery and pose a reputational risk. Recruitment is being planned as part of broader FCDO restructuring.
- Strategy & Context: global interest in Impact investing could potentially be undermined by competing geopolitical objectives and tensions - the risk of an ‘ESG backlash’ – an abandonment of ESG strategies by investors, in favour of a renewed focus on short-term financial performance, was added last year. This year this has been escalated to a major risk. The programme has sought to manage this risk through clear communication of policy with external stakeholders - emphasising that ESG-related information can be financially material and is therefore relevant to investors’ understanding of risk, supporting the case for disclosure standards such as ISSB. This is distinct from impact investing, which may also incorporate values-based considerations into investment decisions alongside financially material information.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

The IMPACT Programme is delivered internally, using FCDO programme management, financial and procurement systems

Management of the programme involves regular meetings between the PRO and Programme Manager to review progress across the programme, agree any updates to the risk register, and track continuous improvement actions. The SRO attends these internal meetings once per quarter and represents the IMPACT programme at the quarterly Private Sector & Capital Mobilsation Department’s (PSCMD) Programme Board (which reviews delivery of all PSCMD programmes). The PRO escalates risks, issues, and decisions to the SRO at any time if they exceed the PRO’s financial delegated authority or the programme risk appetite.

The programme had been fully resourced until Q3 when the SRO left, followed by the PRO and programme manager in Q4. The programme is being managed on a temporary basis by an interim SRO and some programme management support from elsewhere in PSCMD until recruitment is completed under new FCDO structures.

On financial management, as the programme operates on a payment on delivery basis, with the majority of final reporting on deliverables being submitted just before the end of the FY. As a result of the staff changes, the interim team have been prioritising the relevant payment processes in order to enable payments to be authorised and made, once delivery against the relevant Accountable Grant Agreements have been assured.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Monitoring across the portfolio occurred through quarterly and ad hoc engagement with the grantees, and participation in their stakeholder and governance meetings. For example, GSG Impact, IFRS and Impact Frontiers hold regular meetings with their stakeholders to update on their work which the team attended.

Evidence
On Evidence, all grantees provide reports and updates on the progress of their work and interventions, which are generally comprehensive and to a high standard. The programme team follow up where additional information or clarification is required, particularly at year end ahead of final payments becoming due. However, there is a lack of consistency of reporting formats and in future, the team should consider a baseline of KPIs, including standardised reporting against deliverables, potentially as part of AGAs.

Additionally, as set out in the “Major lessons and recommendations” section above, the programme team should complete a strategic stocktake of the last two years of delivery, identifying which interventions have shown the strongest evidence of uptake, where there is real market demand and how the programme best fits with wider FCDO work on private capital mobilisation. This may lead to a revised vision for the programme’s role and a revised Theory of Change to more accurately reflect a causal link between the outputs and the programme’s objectives, in other words, whether and to what degree investor decisions and capital allocation are being influenced by the work being funded by the portfolio.

Learning
The work covered by the portfolio has resulted in some rich learnings from the grantees, for example considerations for driving more systemic impact investment into EMDEs both structurally (e.g. through policy levers) and through proper implementation of IMM via standards and frameworks, through to examples of supporting domestic capital market development by working with domestic pension funds to invest in SME finance. These learnings, as observed earlier, are not only relevant to impact investing but more generally to the work the FCDO undertakes to mobilise more impactful private capital. At the time of writing, some reports were still being finalised but the programme team should consider how to disseminate this knowledge and learning more broadly across the teams responsible for capital mobilisation within FCDO. This will help to ensure the work is not developed in isolation from the rest of the mobilisation agenda, and will facilitate more cross-team and sector learning on enabling more systemically impactful investments in the deployment of development finance.