## Annual Review

Title: Macroeconomics Research in Low-Income Countries (MRLIC)
Programme Value £: 21.68m		Review date: July 2025
Programme Code : 202960	AMP start date: Feb 2012	AMP end date: March 2026

Summary of Programme Performance
Year	2020/21	2021/2022	2022/2023	2023/2024	2024/2025
Overall Output Score	A+	A+	A+	A	A+
Risk Rating	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/56217735.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005186.xlsx

A. SUMMARY AND OVERVIEW

Macroeconomic Research in Low Income Countries (MRLIC) is a long-standing partnership between FCDO and the International Monetary Fund (IMF) aiming to promote macroeconomic stability and growth in LICs through improved IMF engagement in those countries. It seeks to achieve this by:
1. producing high quality, policy relevant research on macroeconomic issues affecting LICs.
2. ensuring that research products are used by IMF country teams and partner governments.
3. shaping high-level IMF policy positions and strengthening engagement by senior IMF policymakers on LIC issues.
4. widening the field of academics and policymakers working on these issues.
  [note] In 2022, the logframe was revised and streamlined. Output 4 was removed, with some indicators subsumed under other Outputs.
Macroeconomic stability is critical for economic development. Low Income Countries (LICs) are particularly vulnerable to shocks leading to economic instability, such as rising debt or high inflation. Instability deters private investment, reduces growth and can lead to deeper poverty and greater risks of conflict. Though macroeconomic stability is not sufficient to guarantee growth, it is a foundation from which growth is more likely to take off.
[note] Macroeconomic instability refers to high inflation and large currency fluctuations, or important swings in growth rates. For a brief explainer see how the IMF Promotes Global Economic Stability
[note] Macroeconomic stability, investment and growth in developing countries - ScienceDirect

MRLIC’s research is produced mostly by economists in the IMF Research Department, with some commissioned from external academics. It aims to push the frontier of the global understanding on macroeconomics in LICs, a typically under-researched field. MRLIC research also aims generate policy and practice change. The main channel through which this research uptake occurs, is via IMF country missions. The programme also delivers training for Fund staff, and government officials as well as focused engagement with the IMF Board. Linking the IMF Research Department (RES), the Strategy, Policy and Review (SPR) Department and the Institute for Capacity Development (ICD) helps ensure that the research agenda is relevant to the Fund’s policy and is disseminated effectively.

Working with the IMF is an efficient route for supporting macroeconomic policy in the countries where FCDO works. It helps the FCDO achieve breadth and leverages the IMF’s comparative advantage in providing macroeconomic policy advice and analysis.

MRLIC started in March 2012. A fourth phase (£5.1m) was approved in 2019. A no-cost programme extension was approved in 2021, reprofiling disbursements and extending the end date to March 2025. In September 2024 a further extension was approved taking the programme up to March 2026 and adding an additional £1.84m of budget.

Summary supporting narrative for the overall score in this review

This annual review scores an A+. At the output level, two outputs score A+ and one scores A. The review covers April 2024 to March 2025. During this 13th year of operation, MRLIC demonstrated excellent performance, exceeding ambitious targets while maintaining the high quality and policy relevance that has characterised the programme throughout its lifetime.

During this annual review period, the programme produced 18 working papers and secured 5 publications in peer-reviewed journals (Output 1: A+). Research uptake remained strong with 236 country applications and 59 training courses delivered (Output 2: A+), exemplified by the successful conclusion of Ghana's multi-year monetary policy framework transformation and widespread adoption of Debt-Investment-Growth and Natural Disasters (DIGNAD) model across Resilience and Sustainability Facility (RSF) programmes. Senior IMF engagement with LIC issues continued at high levels (Output 3: A), with MRLIC research featured prominently in the April 2024 World Economic Outlook (WEO) and shaping policy discourse from Board papers to speeches by senior officials.

The successful securing of a one-year extension with £1.84m additional funding provides welcome stability and enables strategic planning for the programme's future. While the programme excels in producing and disseminating high-quality research, there remain opportunities to strengthen systematic tracking of policy impacts and enhance digital dissemination strategies to expand reach and value for money, areas that can be addressed within the remaining programme period to further strengthen an already exceptional track record.

It should be noted that the logframe targets were not refreshed following last year's review, resulting in some Year 13 milestones being less stretching than appropriate given previous achievements. However, the output scores remain valid based on strong annual performance, for example, with 18 working papers produced compared to 13 in the previous year, demonstrating sustained programme momentum rather than simply meeting cumulative targets. Going forward, annual milestone setting will ensure targets are appropriately ambitious based on prior year achievements.

Major lessons and recommendations for the year ahead

Key lessons from Year 13:
The programme's thirteenth year reinforced several important lessons. Sustained high-quality research combined with active dissemination and capacity building can achieve significant policy influence, as demonstrated by Ghana's monetary policy transformation and the widespread adoption of DIGNAD in climate resilience planning. However, the year also highlighted persistent challenges in systematically tracking how research translates into policy reforms and the need for more innovative approaches to increase reach and impact in an evolving digital landscape.
Major recommendations for the year ahead:
1. Prioritise knowledge synthesis and accessibility: In the year ahead, develop comprehensive technical syntheses and policy briefs that synthesise 13 years of MRLIC research on critical topics (climate resilience, debt sustainability, gender and inclusion, structural transformation). The policy briefs should be designed for time-constrained policymakers and include clear, actionable recommendations. This will create lasting value from the programme's extensive research base while demonstrating cumulative impact to support considerations about future phases.
2. Leverage the November 2025 conference for strategic positioning: Use the conference showcasing pathfinding papers as a platform to: (i) convene potential co-funders and build a coalition for continued LIC macroeconomic research, (ii) demonstrate MRLIC's unique value through an "impact showcase", and (iii) facilitate discussion on future research priorities and delivery mechanisms. Ensure key stakeholders from FCDO, IMF, other donors, and partner countries are engaged at senior levels.
3. Develop multi-donor funding strategy In the year ahead, actively develop partnerships with other bilateral donors, multilateral development banks, and foundations interested in macroeconomic stability and LIC development. Create a compelling investment case based on the external evaluation findings, demonstrated impact, and alignment with global priorities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

This programme was initiated in 2012. The Theory of Change is summarised below. Successive Annual Reviews have provided evidence from the output and, to some extent, the outcome stage. However, the Theory of Change assumption that the greater visibility of MRLIC among IMF seniors would increase the probability of IMF funding LIC research itself has not been fully validated. The Theory of Change should be revised to reflect the limitations in achieving universal uptake of research through existing IMF channels. The impact of the programme would be multiplied by engagement with other agencies with a comparative advantage in areas which can facilitate better uptake by policy makers in LIC.
[note] The original Business Case did not specify a formal Theory of Change (ToC) however the implicit ToC for the program is summarised in its logical framework and subsequent Annual Reviews.

OUTPUT 1	High quality, policy relevant research on macroeconomic issues affecting LICs produced.
OUTPUT 2	IMF research products (policy analysis, practical and operational tools and frameworks) produced under this project used by IMF country teams and partner authorities.
OUTPUT 3	Engagement by senior IMF policymakers on issues affecting LICs strengthened through this project.
OUTPUT 4	IMF strengthens research capacity, by expanding the network of researchers and policy makers working on LIC macroeconomics

OUTCOME	Better engagement by IMF policymakers on LIC-specific macroeconomic issues, leading to improved policymaking in specific project thematic areas.

IMPACT	Better macroeconomic policymaking in LICs leading to faster economic growth, job creation and poverty reduction.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to meet its expected outcome: Better engagement by IMF policymakers on LIC-specific macroeconomic issues, leading to improved policymaking in specific project thematic areas. The outcome indicator shows strong performance with 22 thematic areas of IMF policy influenced and made LIC-specific, meeting the target. Year 13 demonstrated substantial evidence of this improved engagement across multiple channels.

Key research outputs have been integrated into IMF's highest-level policy documents, including a full chapter in the April 2024 World Economic Outlook on medium-term growth prospects with specific analysis of LIC convergence challenges. MRLIC tools, particularly DIGNAD, have become integral to IMF country operations, with applications in 10 countries during Year 13 alone, directly shaping climate resilience strategies and RSF programme design. The successful conclusion of the multi-year FPAS project in Ghana exemplifies how MRLIC research translates into fundamental improvements in country-level monetary policy frameworks. Furthermore, the continued strong demand for MRLIC training—with 59 courses delivered and consistently positive feedback—indicates that both IMF staff and country authorities value these tools for practical policymaking.

At the impact level, while direct attribution to economic growth, job creation, and poverty reduction remains methodologically challenging, there are encouraging signs at outcome level. Countries implementing MRLIC-supported reforms, such as Ghana's enhanced monetary policy framework, are better positioned to maintain macroeconomic stability—a crucial foundation for sustainable growth. The widespread adoption of climate resilience planning through DIGNAD potentially helps countries avoid costly economic disruptions from natural disasters. Research on gender complementarities and distributional impacts provides evidence base for more inclusive policies that can enhance growth while reducing inequality.

Box 1: Case Studies of MRLIC Outcome level Policy Impact

Case Study: Ghana's Monetary Policy Transformation
The Bank of Ghana's transformation through MRLIC-supported technical assistance demonstrates lasting institutional change. Over several years, MRLIC products have supported IMF technical assistance with BoG to develop a sophisticated Quarterly Projection Model that now sits at the heart of monetary policy decisions. The project built deep technical capacity among BoG staff, enabling a shift from backward-looking analysis to forward-looking, model-based policymaking. By 2024, the QPM routinely informs interest rate decisions and inflation forecasts, strengthening Ghana's ability to navigate economic challenges. This represents an improvement in national monetary policy capability.

Case Study: DIGNAD Mainstreaming in Climate Planning
DIGNAD has evolved from research tool to operational cornerstone of IMF climate work in LICs. In 2024/25, applications across ten countries shaped national climate strategies and RSF programme design. In Tanzania, DIGNAD demonstrated that climate-resilient infrastructure could reduce post-disaster GDP losses by 2 percentage points while improving debt sustainability—analysis central to their RSF arrangement. Beyond individual countries, DIGNAD has achieved institutional mainstreaming: it features in Executive Board discussions, IMF training curricula, and is independently applied by trained officials. This demonstrates how MRLIC research can shape institutional practice.

However, sustaining and deepening these outcomes faces uncertainty without confirmed Phase V funding. The positive trajectory of IMF engagement with LIC-specific issues, built over 13 years, risks losing momentum if the research pipeline diminishes after March 2026. For the year ahead, several strategic actions are planned to consolidate achievements and position for continued impact:

- External evaluation completion: An independent evaluation, launched in early 2024, will provide systematic assessment of MRLIC's outcomes and impact over its lifetime, offering evidence and lessons for future programming.
- Pathfinding papers and conference: Five commissioned papers across core themes will identify emerging macroeconomic challenges for LICs and research priorities. The November 2025 conference will convene key stakeholders to discuss findings and build consensus on future directions.
- Knowledge synthesis: As recommended, the programme will prioritise creating accessible summaries of research findings on key topics, ensuring the 13-year knowledge base remains available and influential beyond the current phase.
- Strategic engagement: Leveraging high-level conferences and the external evaluation to engage potential co-funders and build coalition support for continued LIC macroeconomic research, whether through another phase or alternative mechanisms.

These actions aim to maximise impact in the remaining period while creating strong foundations for sustaining the programme's contribution to improved macroeconomic policymaking in LICs.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue through to its current end date of March 2026. Strong performance in Year 13, with targets met or exceeded across all outputs, justifies completing the approved extension period. The remaining year provides opportunity to maximise impact through knowledge synthesis and dissemination while the external evaluation and pathfinding papers will position FCDO to make an informed decision about potential future programming

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	High quality, policy relevant research on macroeconomic issues affecting LICs produced.
Output number:		1	Output Score:	A+
Impact weighting (%):		34	Weighting revised since last AR?	[If Yes, up or down?]
Indicator(s)		Milestone(s) for this review		Progress
1.1 Number of priority research papers produced, on the five research themes of the MRLIC		H (200 papers) / M (196 papers) / L (190 papers)		209
1.2 Number of research papers accepted for publication in appropriate high-quality peer-reviewed journals		H (117 papers) / M (115 papers) / L (113 papers)		118

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses the performance of the programme in producing high quality, policy relevant research on macroeconomic issues affecting LICs. In this review year it scores an A+, though this reflects differential performance across the two indicators. Indicator 1.1 exceeded its high target with 209 papers against a target of 200, representing strong continued productivity. However, indicator 1.2 achieved 118 published papers against a high target of 117, which while meeting the stated target represents a decline from 8 papers published last year to 5 this year, indicating performance at expected rather than exceptional levels. It should be noted that the logframe targets were not updated following last year's review, which would have set more ambitious benchmarks. The overall A+ rating reflects the sustained high quality and policy relevance of outputs, with 18 working papers produced in Year 13 maintaining the programme's strong research productivity.

Output 1.1 -- Working Papers
MRLIC maintained strong performance across all five research themes. Notable contributions include work on monetary policy frameworks, with papers developing Ghana's Quarterly Projection Model for forward-looking policy analysis and examining the pass-through of global price shocks in spatial models of low-income countries. Research on macro-financial linkages explored financial reform contagion and dominant currency pricing in services trade. The programme made significant contributions to building resilience, with four papers examining fiscal tools for disaster resilience, foreign aid responses to shocks, and the macroeconomic benefits of resilience-building in disaster-prone countries. Structural change research was particularly productive with ten papers covering topics from middle-income traps to knowledge diffusion through FDI and the implications of geoeconomic fragmentation. Several papers employed innovative methodologies, including machine learning applications for nowcasting and spatial general equilibrium models.

Output 1.2 -- Published Papers
The programme achieved 5 papers accepted in peer-reviewed journals, meeting expectations. These included papers in the European Journal of Political Economy on political institutions and output collapses, the Journal of International Economics on changing global linkages amid geopolitical tensions, and a forthcoming paper in Feminist Economics on gender complementarities in production functions. A paper on financial reform contagion is forthcoming in International Economics Review, and another on connector countries bridging geopolitical fragments will appear in AEA Papers and Proceedings. These publications demonstrate the programme's ability to place research in influential journals while maintaining policy relevance for low-income countries. While this represents a strong performance in terms of publication quality, the decrease from the previous year’s 8 publications indicates natural variability in academic publication timelines.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Output 1: Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The 2024 review recommended that the programme seek to more specifically demonstrate how research outputs influence IMF policy positions and programming decisions as well as the thinking of policymakers in LICs. Good progress has been made on this front. The Year 13 report provides stronger evidence of policy influence, including research integration into WEO chapters that shape global policy discourse, citations in speeches by senior officials such as Gita Gopinath (IMF First Deputy MD) and the Bundesbank President, and direct country applications such as Ghana's monetary policy framework transformation. The programme has better documented these pathways of influence.

Given the limited time remaining in the current phase, recommendations focus on maximising impact and preparing for transition:

Recommendation: In the final year, prioritise synthesis of the substantial body of research produced over 13 years into accessible policy briefs or evidence summaries on key topics, particularly on topics which are not covered by the path finding papers. This would create lasting resources for policymakers while demonstrating the cumulative policy value of MRLIC research, supporting the case for donors to support future research.

Output Title	IMF research products (policy analysis, practical and operational tools and frameworks) produced under this project used by IMF country teams and partner authorities.
Output number:	2	Output Score:	A+
Impact weighting (%):	33	Weighting revised since last AR?	[If Yes, up or down?]
Indicator(s)	Milestone(s) for this review		Progress
2.1 Application and use of tools and frameworks by country authorities and country teams.	H (233) / M (230) / L (227)		236
2.2 Courses offered to country authorities and IMF staff	H (53) / M (51) / L (49)		59

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses the IMF research products produced under MRLIC which are used by IMF country teams and partner authorities as well as training courses to upskill end users. The output scores an A+. While both indicators exceeded their stated high targets (indicator 2.1 achieved 236 applications against 233; indicator 2.2 delivered 59 courses against 53), these milestones were not updated from last year's review when performance was already above these levels. The A+ rating is justified not by surpassing these understated targets but by the strong quality and impact of the programme's tools and capacity building, particularly the widespread adoption and influence of DIGNAD and the impact on country-level policymaking capacity, particularly the use of MRLIC in the technical assistance mission with the Bank of Ghana.

Indicator 2.1: Applications by IMF country teams and country authorities

The DIGNAD model continued to be widely applied across multiple countries, particularly in the context of Resilience and Sustainability Facility (RSF) programmes. Applications spanned the Democratic Republic of Congo, Republic of Congo, Côte d'Ivoire, Guinea, Madagascar, Maldives, and Tanzania, with the model helping countries assess the macroeconomic benefits of climate adaptation investments. A particularly notable success was the conclusion of the multi-year IMF technical assistance mission with the Bank of Ghana which utilised MRLIC-supported products, significantly strengthening Ghana's macroeconomic forecasting capabilities through the development of a modern Forecasting and Policy Analysis System (FPAS). The enhanced Quarterly Projection Model now plays a central role in the Bank of Ghana's monetary policy formulation and communications.

Country teams provided strong positive feedback on these applications. The Palau team noted that DIGNAD "provided an invaluable framework to discuss the medium-term fiscal anchor and policies with the authorities." In Rwanda, Executive Board discussions welcomed the use of DIGNAD alongside the Debt Sustainability Analysis as important inputs for RSF programme design. The MIMMI app continued to demonstrate its value in distributional analysis, with applications in Guinea assessing the macroeconomic and social impacts of the Simandou mining project, helping authorities understand the importance of complementary policies in education and infrastructure.

Indicator 2.2: Courses for IMF country teams and country authorities

MRLIC delivered seven high-quality training events reaching diverse audiences across IMF staff, government officials, and academics. The DIGNAD toolkit training received consistently positive feedback, with the November 2024 IMF staff course rating 4.73/5. Participants praised its practical value for operational work. Regional training through partnerships with institutions like the Africa Training Institute proved particularly effective, with the Climate in Macroeconomic Frameworks course in February 2025 bringing together representatives from 36 countries and receiving a 4.7/5 rating.

There are examples of the impact of training extending beyond immediate learning, as demonstrated by a Reserve Bank of Zimbabwe staff member who, following a February 2024 DIGNAD training, independently calibrated the model to Zimbabwe's economic conditions in a policy paper. The workshop at MathWorks Finance Conference expanded reach beyond traditional audiences, attracting approximately 1,400 registrants and showcasing MRLIC tools to private sector and academic communities. Participants consistently highlighted the hands-on nature of the training and its direct relevance to their policy work, with many expressing interest in applying the tools to their country contexts.

Notably, the MRLIC team strengthened engagement with FCDO by delivering a DIGNAD training event for FCDO staff and actively collaborating with FCDO teams working on debt sustainability issues, demonstrating the programme's direct value to FCDO's operational work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2024 review noted that while the programme demonstrates academic impact and broader interest, it could more systematically capture shifts in IMF positions or policies based on MRLIC output. Limited progress is evident on developing structured measurement of policy impact. While Year 13 shows strong examples of uptake (Ghana's FPAS transformation, widespread DIGNAD adoption in RSF programmes), these remain illustrative rather than systematically tracked.

Recommendation: External evaluation to assess policy influence pathways and impacts. This should include: (i) systematic follow-up with a sample of training participants to track tool application, (ii) brief surveys of IMF country teams using MRLIC tools to document policy changes influenced, and (iii) creation of a simple database of policy reforms linked to MRLIC research. This would provide evidence for potential future phase design while being achievable within the remaining timeframe.

Output Title	Engagement by senior IMF policymakers on issues affecting LICs strengthened through this project.
Output number:		3	Output Score:	A
Impact weighting (%):		33	Weighting revised since last AR?	[If Yes, up or down?]
Indicator(s)		Milestone(s) for this review		Progress
3.1 High level policy conferences attended by senior IMF staff reflect findings of research papers funded under this project.		H (60) / M (59) / L (58)		60
3.2 Results of the research reflected in IMF Board discussions and papers such as IMF Policy Papers, Staff Discussion Notes, policy memos to management etc.		H (67) / M (65) / L (63)		66

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses how the level of engagement by senior IMF policymakers on issues affecting LICs is strengthened through this project. It scores an A. Indicator 3.1 met the high target exactly with 60 policy conferences, while indicator 3.2 achieved 66 instances of research reflected in IMF policy papers, exceeding the medium target of 65. The programme continued to influence high-level policy discussions and shape IMF positions on critical macroeconomic issues affecting LICs.

Indicator 3.1: High level conferences

MRLIC organised and contributed to four high-level conferences that advanced macroeconomic research and policy dialogue for LICs. The "Rethinking Economic Policy: Steering Structural Change" conference in April 2024 explored how policy can navigate structural transformations while ensuring inclusive benefits, with particular relevance for developing economies. The AERC-IMF Visiting Scholars Workshop in September 2024 brought together six researchers from Sub-Saharan Africa for presentations and one-on-one mentorship with IMF economists, fostering regional research capacity. The November 2024 conference on "Transforming Industries for Growth in a Fragmented World" disseminated findings from MRLIC's major research on economic diversification strategies in developing countries.

A particularly prominent achievement was the ASSA 2025 session on "Policy Uncertainty and Economic Activity," co-organised with Stanford University. This well-attended session featured four papers analysing global trade and fiscal uncertainty, including applications of the World Uncertainty Index, demonstrating MRLIC's contribution to cutting-edge policy debates at premier academic venues.

Indicator 3.2: Research reflected in IMF Board discussion and other IMF policy papers

MRLIC research achieved visibility in high-level IMF policy documents. The April 2024 World Economic Outlook featured a full chapter on "Slowdown in Global Medium-Term Growth: What Will It Take to Turn the Tide?" analysing key drivers of slowing productivity and growth with important implications for LIC convergence. The WEO also included two MRLIC-contributed boxes on distributional implications of growth prospects and trade fragmentation effects. Additionally, MRLIC research on financial flows to developing countries was prominently featured in the Board paper on the 4th Financing for Development Conference.

The policy influence of MRLIC research extended beyond formal publications, with findings cited in speeches by senior officials including IMF First Deputy Managing Director Gita Gopinath and Bundesbank President Joachim Nagel. This high-level uptake demonstrates how MRLIC research continues to shape global policy discourse on macroeconomic challenges facing LICs, from geoeconomic fragmentation to growth prospects and development financing.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2024 review recommended revising indicators to focus more clearly on exposure and engagement of senior IMF officials to MRLIC research and capturing how research influences IMF policy. While the indicators remain unchanged, the programme has improved documentation of influence, with clearer examples of how MRLIC research shapes Board papers, flagship publications, and senior management positions on LIC issues.

Recommendation: For the extension period, leverage the high-level conferences and pathfinding papers to strengthen senior stakeholder engagement for a potential Phase V. Focus on: (i) ensuring pathfinding paper authors include influential policy voices who can champion continued LIC macroeconomic research, (ii) using the November 2025 conference to convene senior IMF, FCDO, and potential co-funding partners, and (iii) developing a concise "impact showcase" highlighting 13 years of policy influence to support resource mobilisation efforts. Enhanced digital dissemination of these materials could amplify reach to senior audiences at minimal cost.

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The MRLIC programme continues to deliver good value for money across all dimensions of FCDO's value for money framework. The programme's ability to produce high-quality, policy-relevant research at competitive costs while achieving substantial policy impact demonstrates strong overall cost-effectiveness.

Economy: The programme maintains robust governance on procurement processes through IMF systems and guidelines. All contractual employees undergo competitive selection processes, and the Fund's established procurement procedures ensure cost-effective acquisition of inputs. Travel and conference costs continue to be managed efficiently within IMF guidelines. The one-year extension, including resources for an external evaluation and pathfinding papers, represents prudent investment in ensuring the programme's future strategic direction delivers maximum value.

Efficiency: The programme demonstrates efficiency in research production. The updated figures for Year 13 show the cost per working paper at approximately $70,000 (£53,000), a slight decrease from the previous year's $72,000, while the cost per published paper remains stable at approximately $124,000 (£93,000). Both figures remain significantly below FCDO's benchmark of £150,000 per paper. This efficiency is particularly noteworthy given the programme has maintained high quality standards, with 118 papers published in peer-reviewed journals over 13 years, many in top-tier publications.
## Cost per Working and Published Paper during Years 1-13
Total Staff/Contractual/VS Costs1	$19,489,336
Research Paper Costs	$14,617,002
Country Applications Costs	$4,872,334
Working Papers2	209
Cost Per Working Paper	$69,938
Published Papers2	118
Cost per Published Paper	$123,873

1 Estimated as the sum of the first two lines of Table 3. Note that the first line of Table 3 includes both IMF staff salary and travel expenses. Thus, the estimates we have calculated for working and published paper costs likely overestimate the true cost of research time.
2 These include commissioned papers.
However, the programme's cost allocation between research papers (75%) and country applications (25%) remains based on estimates rather than detailed time tracking. More granular cost analysis could identify opportunities for further efficiency gains and better demonstrate where resources create the most value.

Effectiveness: The programme's effectiveness is evidenced through multiple channels of impact. In Year 13, DIGNAD applications were implemented across 10 countries, directly informing climate resilience strategies and RSF programme design. The high citation rates (86.3% of publications cited, averaging 23.4 citations per article) and extensive downloads (average 962 per working paper) demonstrate strong academic influence. Moreover, the direct uptake by policymakers—such as Ghana's transformation of its monetary policy framework through MRLIC-supported FPAS development—illustrates tangible policy impact.

While these outputs are well-tracked, there remains scope to strengthen the systematic measurement of how research translates into actual policy changes in LICs. Developing a more robust framework to track and attribute policy reforms to MRLIC research would provide stronger evidence of effectiveness. Additionally, while training is delivered to country officials and IMF staff, more systematic follow-up on how participants subsequently apply tools and knowledge could both improve impact and strengthen the VfM evidence base. The external evaluation underway presents an opportunity to develop such tracking mechanisms.

The programme could enhance its effectiveness through improved knowledge synthesis. Creating more accessible policy briefs or evidence summaries that consolidate findings across multiple studies into digestible formats could increase uptake among time-constrained policymakers at relatively low marginal cost. Similarly, while the programme maintains good traditional dissemination through conferences and quarterly newsletters reaching 1,500+ subscribers, there is potential to amplify impact through enhanced digital strategies. The relatively modest social media engagement compared to the quality of outputs suggests untapped potential for broader reach.

Equity: MRLIC's continued focus on inequality and inclusion enhances its value proposition. Year 13 outputs included groundbreaking research on gender complementarities in production functions, suggesting that gains from gender inclusiveness are substantially larger than standard models estimate. The programme's tools, particularly the MIMMI app, enable detailed distributional analysis of policy impacts, as demonstrated in Guinea's Simandou project assessment. Research on topics ranging from food insecurity to the distributional implications of global growth slowdowns ensures that equity considerations are embedded in macroeconomic policy advice for LICs.

Overall cost-effectiveness: Working through the IMF continues to provide leverage for FCDO resources. The programme benefits from IMF infrastructure, expertise, and convening power while maintaining direct costs at approximately 1% of budget for programme management. The breadth of country coverage (spanning most LICs) and depth of engagement (from research to country applications to capacity building) would be difficult to replicate through alternative delivery mechanisms at comparable cost.

Looking forward, the external evaluation and pathfinding papers commissioned for the extension period represent strategic investments in sustaining and potentially enhancing value for money. These exercises provide opportunities to address identified areas for strengthening VfM evidence, including developing better impact attribution mechanisms and exploring more cost-effective dissemination strategies. However, with Phase V funding uncertain, maximising future value will require concerted efforts to crowd in funding from other donors and development partners. The programme’s strong track record of delivery, demonstrated impact, and alignment with global challenges such as climate change and inequality position it well to attract complementary funding, potentially multiplying FCDO's investment impact through leveraged resources.

The consistently strong performance over 13 years, combined with the programme's ability to adapt to emerging challenges while maintaining cost discipline, confirms that MRLIC continues to represent excellent value for money in addressing critical macroeconomic research gaps for low-income countries. The identified opportunities for improvement would further strengthen an already robust value proposition.

E: RISK

Overview of risk management

The overall risk remains minor. The risk register is regularly updated and was last updated in April 2025. The programme has continued to demonstrate resilient delivery despite the global economic challenges, with MRLIC successfully meeting or exceeding most output targets. The approval of a one-year extension to March 2026, with additional funding of £1.84m, has provided welcome stability and reduced the immediate funding uncertainty that was a key concern in the previous review period.

The main risks for the programme continue to be managed effectively:
- External context: Most research is carried out at IMF headquarters using secondary datasets, maintaining limited exposure to context in LICs. The programme has adapted well to global challenges including geopolitical tensions and economic uncertainties. MINOR
- Delivery: Established delivery systems continue to demonstrate high performance over the extended programme period. Demand for MRLIC outputs remains strong, with continued uptake by IMF country teams and national authorities. MINOR
- Operational: Experienced management teams remain in place at both FCDO and IMF, ensuring continuity and effective programme oversight. MINOR
- Fiduciary: All funds continue to be spent directly by the IMF and are subject to extensive IMF financial management controls, providing strong fiduciary assurance. MINOR
- Reputational: Research activities and topics continue to pose little or no reputational risk, with outputs maintaining high academic standards and policy relevance. MINOR
Safeguarding: Programme activities rarely involve contact with vulnerable persons, and external researchers continue to be managed in accordance with IMF procedures. MINOR

The December 2021 Central Assurance Assessment (CAA) of the IMF confirming its position as a low-risk partner remains valid. The light-touch due diligence conducted in July 2023 continues to provide appropriate assurance, with no material changes to the IMF's operating procedures or the MRLIC programme's implementation approach.

Climate and environment risk assessment: In alignment with the Paris Agreement, climate and environment risks within the programme remain low. The programme actively contributes to climate resilience through research on natural disasters, climate adaptation, and the development of tools like DIGNAD that help countries assess climate-related macroeconomic risks. This work directly supports LICs in building resilience to climate change.

Equalities considerations: The programme continues to meet its obligations under the Gender Equality Duty and Public Sector Equality Duty. Research on gender and inclusion remains a core theme, with outputs including work on gender complementarities in production functions and the macroeconomic impacts of gender gaps. No adverse impacts on protected characteristics have been identified, and the programme actively contributes to evidence on reducing inequalities.

Due diligence status: All due diligence assessments remain current and valid. The IMF's robust internal controls and governance structures continue to provide appropriate assurance. No material changes have occurred that would require a refresh of existing assessments.

Looking ahead, while the one-year extension to March 2026 provides near-term stability, the programme continues to face medium-term funding uncertainty. The planned comprehensive external evaluation and commissioned pathfinding papers during the extension period will be crucial for shaping a potential Phase V and ensuring the programme's continued relevance and impact. The evolving global context—including geoeconomic fragmentation, declining development assistance, climate change, and rapid technological change—presents both challenges and opportunities that will need to be carefully considered in future programme design.

Overall, the programme continues to operate comfortably within risk appetite across all categories, with effective risk management enabling the delivery of high-quality, impactful research that supports macroeconomic policymaking in LICs.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The partnership between FCDO and the IMF continues to demonstrate strong performance in programme delivery and financial management. Both partners have maintained effective collaboration throughout the thirteenth year of implementation, ensuring the programme continues to meet its objectives efficiently.
Financial management and reporting: The IMF has maintained high standards in financial reporting, with timely submission of both narrative and financial reports. As of April 2025, $27.5 million has been drawn from the subaccount against the total approved budget of $29.5 million, reflecting appropriate budget utilisation as the programme approaches its conclusion in March 2026. The programme continues to benefit from the IMF's robust financial management systems, with all expenditures subject to the Fund's stringent internal controls.
Programme delivery and coordination: Regular coordination between FCDO and IMF teams has been maintained through regular progress meetings and output summaries. The programme has successfully delivered against its targets, meeting or exceeding high targets for six of seven output indicators. This strong performance demonstrates the effectiveness of established delivery systems and the continued high demand for MRLIC research products.
The approval of the one-year extension to March 2026, including additional funding of £1.84m, was managed efficiently by both partners. This extension has provided valuable continuity for ongoing research projects while creating space for strategic planning for a potential Phase V.

Value for money: The programme continues to demonstrate excellent value for money, with the average cost per working paper at approximately $70,000 (£53,000) and per published paper at $124,000 (£93,000), both remaining well below FCDO's benchmark of £150,000 per paper. Direct project management costs remain minimal at approximately one percent of the total budget, ensuring maximum resources are directed to research outputs.
Quality of outputs: The IMF has maintained rigorous quality control processes, with all outputs meeting Fund publication standards and many achieving publication in high-ranking peer-reviewed journals. The continued strong uptake of MRLIC tools and research by IMF country teams and national authorities demonstrates the sustained relevance and quality of programme outputs.
Areas of strong performance:
- Consistent delivery against ambitious output targets
- Maintenance of low per-paper costs while ensuring high quality
- Effective adaptation to evolving LIC needs and global challenges
- Strong institutional knowledge retention despite funding uncertainties in previous years
Partnership effectiveness: The relationship between FCDO and IMF remains collaborative and productive. The IMF team has been responsive to FCDO priorities while maintaining the academic rigour necessary for credible policy influence. Both partners have worked effectively to position the programme for future success through the planned external evaluation and pathfinding papers that will inform potential future phases.
As this is a grant arrangement rather than a commercial contract, standard commercial contract provisions such as KPIs, Supply Partner Code compliance, and Strategic Relationship Management scorecards are not applicable. The programme continues to operate under IMF policies and procedures, which provide appropriate governance and accountability frameworks.
This evaluation was carried out by the FCDO programme team demonstrating continued strong oversight and engagement from FCDO in programme management.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The IMF MRLIC team reports annually to FCDO regarding the outputs included in the log-frame. In addition to this formal reporting requirement, the MRLIC team provides quarterly updates to on the programme’s website which hosts up-to-date information on research and progress and open publicly. The team sends out quarterly e-newsletters that reach an audience of more than 1500 academics, policymakers, central bank staff, and government representatives, among others. These e-newsletters are posted on the programme website. All publicly available working and published papers are uploaded to the R4D portal on the FCDO website. To further ensure public access to all outputs produced through the grant, “Gold access” is assigned to journal publications. The IMF and FCDO project members routinely conduct video conference calls to discuss the programme as needed.

Evidence
FCDO conducts a yearly evaluation of the program. In addition, there is an ongoing external evaluation of the program by Shanta Devarajan (Georgetown University) and Stephen A. O'Connell (Swarthmore College), which is expected to be completed before the end of 2025.

Date of last narrative financial report	May 2025	Date of last audited annual statement	August 2024

Annex A: Summaries of working papers and publications under output 1

## Output 1.1 – Working Papers
Topic 1. Modelling and understanding policy choices
1. Quarterly Projection Model for the Bank of Ghana: Extensions and Applications
2. Transport Frictions and the Pass-Through of Global Price Shocks in a Spatial Model of Low-Income Countries

Topic 2. Understanding macro-financial linkages
1. Global Contagion of Financial Reforms
2. Bilateral Trade in Services and Exchange Rates: Evidence of Dominant Currency Pricing

Topic 3. Building resilience
1. The Macroeconomic and Welfare Benefits of Building Resilience in Disaster-Prone Developing Countries
2. Foreign Aid and (Big) Shocks: Evidence from Natural Disasters
3. Foreign Aid and Conflicts: The Effects of 9/11 on Donor Behavior
4. The Urgency of Conflict Prevention – A Macroeconomic Perspective

Topic 4. Promoting structural change and institutional development
1. At the Threshold: The Increasing Relevance of the Middle-Income Trap
2. Dynamic Development Accounting and Relative Income Traps
3. Productive Capacities, Economic Vulnerability and Growth Volatility in Sub-Saharan Africa
4. Economic Diversification in Developing Countries: Lessons from Country Experiences with Broad-Based and Industrial Policies
5. Knowledge Diffusion Through FDI: Worldwide Firm-Level Evidence
6. Changing Global Linkages: A New Cold War?
7. Can Mobile Technologies Enhance Productivity? A Structural Model and Evidence from Benin Food Suppliers
8. Regime-Switching Factor Models and Nowcasting with Big Data
9. Shocks and Shields: Macroeconomic Institutions During Commodity Price Swings
10. State Capacity and Growth Regimes

Topic 5. Enhancing inclusion
We have no working papers under this topic this year.

## Output 1.2 – Published Papers

Topic 1. Modelling and understanding policy choices
We have no publication under this topic this year.

Topic 2. Understanding macro-financial linkages
Policy Contagion: What Do We Learn from Financial Reforms?
 International Economics Review, forthcoming

Topic 3. Building resilience
We have no publication under this topic this year.

Topic 4. Promoting structural change and institutional development
Political institutions and output collapses
 European Journal of Political Economy

Changing global linkages: A new Cold War?
 Journal of International Economics

Changing Global Linkages: Bridging Geopolitical Fragments
AEA Papers and Proceedings

Topic 5. Enhancing inclusion
The Armistice of the Sexes: Gender Complementarities in the Production Function
Feminist Economics, forthcoming

Annex B: Details of Country Applications under Output 2

## Output 2.1 – Country Applications by authorities and IMF Country Teams

FPAS framework - no publication under this topic this year.
1. Ghana – Technical Assistance mission to develop FPAS processes at the Bank of Ghana
2. Ghana – Technical Assistance Report-Report on Developing the Forecasting and Policy Analysis System (FPAS) at the Bank of Ghana (BOG)

Diversification – no publication under this topic this year.
DIG/DIGNAR/Investment scaling up/Debt sustainability – no publication under this topic this year.

Natural disasters/DIGNAD
1. Democratic Republic of Congo – Democratic Republic of Congo: Requests for an Arrangement Under the Extended Credit Facility and an Arrangement Under the Resilience and Sustainability Facility-Press Release; Staff Report; and Statement by the Executive Director for the Democratic Republic of Congo
2. Republic of Congo – Republic of Congo: Selected Issues
3. Côte d’Ivoire – Côte d’Ivoire: Request for an Arrangement Under the Resilience and Sustainability Facility-Press Release; Staff Report; and Statement by the Executive Director for Côte d’Ivoire
4. Guinea: 2024 Article IV Consultation and Request for Disbursement Under the Rapid Credit Facility-Press Release; Staff Report; and Statement by the Executive Director for Guinea
5. Guinea – Guinea: Selected Issues
6. Madagascar – Republic of Madagascar: Request for an Arrangement Under the Extended Credit Facility and Cancellation of the Current Arrangement Under the Extended Credit Facility and Request for an Arrangement Under the Resilience and Sustainability Facility-Press Release; Staff Report; Staff Supplement; Staff Statement; and Statement by the Executive Director for Republic of Madagascar
7. Maldives – DIGNAD results are presented to country authorities
8. Tanzania – United Republic of Tanzania: Third Review Under the Extended Credit Facility Arrangement and Request for Extension of the Extended Credit Facility Arrangement and Rephasing of Access, and Request for an Arrangement Under the Resilience and Sustainability Facility-Press Release; Staff Report; and Statement by the Executive Director for the United Republic of Tanzania

Income and Gender Inequality
1. Guinea: 2024 Article IV Consultation and Request for Disbursement Under the Rapid Credit Facility-Press Release; Staff Report; and Statement by the Executive Director for Guinea
2. Guinea – Guinea: Selected Issues

Food insecurity
Sierra Leone – Sierra Leone: Selected Issues

## Output 2.2 – Courses to authorities and IMF Staff
1. Workshop: Modelling Climate Risks and Policies – July 2024.
2. Workshop: Macro-Climate Modelling with DIGNAD – July 2024.
3. Course: Compilation of Macro-Relevant Environment and Climate Change Statistics – August 2024.
4. The DIGNAD Model: Applications and a New Toolkit - MathWorks Finance Conference 2024 -October 2024
5. Course: DIGNAD: User’s Guide to the Model and Toolkit – November 2024
6. DIGNAD Training in Palau – November 2024
7. Course: Climate in Macroeconomic Frameworks – February 2025

Annex C: Engagement by senior IMF policymakers on issues affecting LICs

## Output 3.1 – High-level Policy Conferences Attended by IMF Senior Staff
1. Rethinking economic policy: Steering structural change – April 2024
2. Workshop: AERC-IMF Visiting Scholars Workshop 2024 – September 2024
3. Transforming Industries for Growth in a Fragmented World – November 2024
4. Session ASSA 2025: Policy Uncertainty and Economic Activity – January 2005

## Output 3.2 –Results of the research reflected in IMF policy papers such as Board papers, SDNs, policy memos to management
1. Chapter: World Economic Outlook: Slowdown in Global Medium-Term Growth: What Will it Take to Turn the Tide?
2. Box: World Economic Outlook: Distributional Implications of Medium-Term Growth Prospects
3. Box: World Economic Outlook: Fragmentation Is Already Affecting International Trade
4. The 4th Financing for Development Conference-Contribution of the IMF to the International Financing for Development Agenda
## Outcome Indicator 1 – Thematic areas of IMF policy influenced and made LIC-specific
Relationship between foreign aid, big shocks, and conflicts.

## Other Outputs

E-newsletters
1. June 2024 Newsletter
2. September 2024 Newsletter
3. December 2024 Newsletter
4. March 2025 Newsletter

Blogs/Article/Press/Other
1. VoxEU Blog – May 2024: Global gender gaps may never close on their own
2. F&D Article – September 2024: Back to Basics: Total Factor Productivity
3. F&D Article – September 2024: Eliminating the Productivity Drag

External presentations
The paper 'Changing Global Linkages: A New Cold War' was presented at
- Peer-to-Peer Workshop for Central Bank Practitioners in CCAMM (June 2024).
- Conference on Globalization and Fragmentation in Manila, Philippines (July 2024).
- Workshop on Fragmentation in Trade and Financial Flows at the US Federal Reserve Board (September 2024).
- BIS/WTO/PIIE Conference on Fragmentation (October 2024).
- European Commission’s Annual Research Conference (November 2024).
- 2024 Global Challenges Workshop on Industrial Policy and Trade Disruption at Bocconi University (November 2024).
- The Annual Meetings of the Southern Economic Association (November 2024).
- The American Economic Association Annual Meeting in San Francisco (January 2025).
The paper 'Do Capital Inflows Spur Technology Diffusion? Evidence from a New Technology Adoption Index' was presented at
- The Barcelona School of Economics Summer Forum (June 2024).
- George Washington University Economics Department Seminar Series (October 2024)
- LACEA/LAMES Annual Meeting (November 2024).
- The Annual Meetings of the Southern Economic Association (November 2024).
- The American Economic Association Annual Meeting in San Francisco (January 2025).
- The Research Institute for Development, Growth and Economics (RIDGE) Forum (December 2024)
1. The country application 'Toward a New Revenue Strategy for Vanuatu: The Role of Income Taxes' was presented at the poster session at the IMF Small Developing States Week (November 2024).
2. The Bilateral Trade in Services (BiTS) database was presented to FCDO staff (November 2024).
3. The paper 'Knowledge Diffusion Through FDI: Worldwide Firm-level Evidence' was presented at the
- European Commission’s Annual Research Conference (November 2024).
- The American Economic Association Annual Meeting in San Francisco (January 2025).
1. The forthcoming working paper ‘The Allocation of Talent and Income Differences Across Countries’ was presented at the CREI 30th Anniversary Conference (November 2024).
2. The country application ‘Scaling Up Investment, Enhancing Growth, Debt Sustainability, and Climate Resilience in Senegal’ was presented at the IMF’s Institute for Capacity Development, and as part of the African Department Seminar Series (February 2025).
3. The country application “Evaluating Saving-Investment and Resilience Building Strategies for Palau” was presented at the Small Development States Analytical Seminar (March 2025)