ADDENDUM TO BUSINESS CASE FOR PHASE 5
SUMMARY INFORMATION
Project Name	Macroeconomic Research in Low Income Countries
Country or region targeted	Global – Low Income Countries
Type of extension (if applicable)	New Phase (Phase 5)
Original project budget	£21.68 million (phases 1, 2, 3, 4 & bridge extension)
Original project start and end dates	March 2012 – March 2026 (phases 1, 2, 3, 4 & bridge extension)
Phase 5 value	£4.0m (revised programme total is £25.68m)
New project end date	March 2030

INFORMATION
What is the project's purpose?
Macroeconomic Research in Low Income Countries (MRLIC) is a strategic partnership between FCDO and the International Monetary Fund (IMF). FCDO has provided £21.68m over 14 years to the IMF to undertake and utilise research into critical macroeconomic issues affecting low-income countries (LICs). The aim of MRLIC is that "Better macroeconomic policymaking in LICs leads to faster economic growth, job creation and poverty reduction in LICs". This is delivered through four core activities: / Producing high quality, policy relevant research on macroeconomic issues affecting LICs. / Ensuring these research products are used by IMF country teams and partner authorities. / Strengthening engagement by senior IMF policymakers on issues affecting LICs. / Expanding the network of researchers and policy makers working on LIC macroeconomics. / The overarching objective of the project has been to improve understanding of the macroeconomics of LICs with a view to improving development outcomes. A key intermediate objective is to increase the profile of LIC work at the IMF, but also to influence the broader academic community, attract new researchers into the field and ultimately enable stronger macroeconomic policymaking in LICs. / High-quality research to guide sound macroeconomic policymaking in LICs remains scarce. These countries face extraordinary challenges: rising debt burdens, limited fiscal space, vulnerability to global shocks and natural disasters, compounded by structural constraints such as narrow export bases and weak institutions. Yet, LIC-focused macroeconomic research remains limited due to capacity constraints in governments and central banks, weak academic engagement, and lack of quality data—leaving a critical gap that a global research partnership is needed to fill. / Macroeconomic stability is critical for economic growth. LICs are particularly vulnerable to shocks that cause periods of macroeconomic instability, low growth and deeper poverty. In the aftermath of the Covid-19 pandemic and the global economic impacts of the war in Ukraine, many LICs have experienced acute macroeconomic pressures compounding persistent longer run vulnerabilities. More than half of all LICs are now in or at high risk of debt distress and the share of government revenue required to service external debt has risen rapidly. / The challenges facing LICs are different to those faced by richer countries. The current uncertainty around global growth poses significant risks to LICs, many of whom have vulnerabilities from worsening debt and face limited fiscal space. Emerging structural changes to the global economy including climate change, automation and artificial intelligence, increasing trade fragmentation, and an unstable geopolitical environment are resulting in new macroeconomic and policymaking challenges for LICs. There is a need to develop a deeper understanding of these challenges and design sound macroeconomic policies based on dedicated research and analysis. MRLIC’s core objective is about unlocking long-term economic development. The programme supports LICs strengthen domestic revenue mobilisation efforts, improve debt sustainability and build economic resilience. With more stable macroeconomic foundations, LICS are better able to: / Build institutional capacity and core economic systems. / Unlock private investment and mobilise finance, enabling greater participation in global trade. / Support women’s economic participation and their access to essential services. / By elevating the profile of LIC macroeconomic issues within the IMF, MRLIC helps drive ongoing reform of the international financial system to be more responsive to, representative of and effective for LICs. / The programme aligns well with the strategic direction of the ODA R&D portfolio. MRLIC delivers global impact through the IMF by focusing on high-level macroeconomic issues. The UK also benefits strategically with the ability to directly fund and influence the direction of the IMF’s LIC research in-line with UK’s objectives.
What is the objective of Phase 5?
Phase 5 of the MRLIC programme (April 2026 to March 2030) will sustain momentum from previous phases and address emerging challenges facing LICs. Phase 4, which will end in March 2026, has advanced research on modelling policy choices, understanding macro-financial linkages, building resilience, promoting structural change and institutional development, and enhancing inclusion. Yet, further work is needed to sharpen policy advice and respond to new priorities. Phase 5 will deepen research in these areas and expand into critical emerging issues. / Research in Phase 5 will be guided by the path-finding papers commissioned by the FCDO and the recommendations of the recent independent review, alongside the policy priorities of the IMF, FCDO, and LICs. The path-finding papers outline five strategic themes for future research: (i) debt, financing and macro-fiscal issues, (ii) growth and trade in a new global environment, (iii) building resilience, (iv) leveraging microdata for better macro policies, and (v) enhancing inclusion. / In line with the independent review's recommendations, Phase 5 will also prioritise adapting analytical frameworks to current LIC challenges—such as debt restructuring and fiscal consolidation—while strengthening risk analysis, incorporating political economy considerations, and improving data transparency, particularly on debt. / Phase 5 also aims to deepen the financial sustainability of the programme by broadening the donor base and securing additional sources of co-funding. This includes engaging new bilateral donors and multilateral development banks and exploring wider income-generation opportunities, such as support from philanthropic sources. / Main Topics During Phase 5 / The following 5 topics represent the core research priorities for FCDO-backed research. With additional funding from a broader donor base, the programme would be able to expand upon these topics into related themes. / Topic 1: Debt, Financing and Macro-Fiscal Issues / This topic focuses on the critical debt challenges facing LICs, where public debt levels have been rising since the mid-2000s and rose further during the COVID-19 pandemic. Work will include: / Establishing updated stylized facts for LICs on the debt-investment-growth nexus, quantifying debt used to finance consumption vs. investment. / Research on sovereign debt defaults and restructurings, building an empirical restructuring 'playbook' dataset and developing quantitative frameworks for sovereign bargaining. / Creating a new database of narrative fiscal actions and fiscal multiplier estimates at country level, with a user-friendly toolkit for tailored fiscal advice. / Building a comprehensive dataset on LIC financing sources and terms, covering creditor composition, currency denomination, maturity, and collateralisation. / Developing a news-based 'debt barometer' to measure debt vulnerabilities in real time. / Topic 2: Growth and Trade in a New Global Environment / This topic addresses the increasingly fragmented global trading environment and its implications for LIC development: / Development of ECLIPSSE (Endogenous Capital-Labor-Imbalance Policy Simulator for Steady-State Equilibrium), a novel quantitative trade model for assessing impacts of tariffs and trade barriers. / Research combining theoretical development with empirical analysis on trade, industrial and fiscal policy interactions in LICs. / Establishing a research agenda on services trade for development, anchored by the Bilateral Trade in Services Research Dataset (BiTS). / Building a multisector long-term growth model to decompose structural change into various drivers and provide long-run scenario analysis. / Topic 3: Building Resilience / This topic continues extensive work on how countries can build resilience to natural disasters, climate change, volatile capital flows, and conflict: / Extensions and applications of the DIGNAD model, including a new Energy Security Module and analysis of distributional impacts of natural disasters and adaptation investments. / Development of a macro-climate model with private sector adaptation to slow-moving climate risks in the agricultural sector. / Research on the macroeconomic consequences of conflicts, contributing to the April 2026 IMF World Economic Outlook chapter. / Building a news-based database of social unrest to expand coverage of lower income countries. / Topic 4: Leveraging Microdata in LICs for Better Macro Policies / This new topic addresses the underrepresentation of LICs in microdata research that informs macroeconomic policy: / Creating and extending a structured DataHub to collaborate with LIC authorities using national administrative micro-datasets. / Providing capacity building and technical assistance to help LIC institutions develop expertise in microdata research. / Strengthening integration of research insights into policy work of IMF country teams, covering areas such as monetary policy transmission, remittances, and distributional effects. / Topic 5: Enhancing Inclusion / This topic examines issues related to growth and inequality, distributional consequences of macroeconomic policies, and talent misallocation: / Research on the joint evolution of inequality, structural change and their underlying drivers through heterogeneous agent models. / Building a practical toolkit for analysing distributional impacts of shocks and policies in LICs. / Using state-of-the-art models and micro data to compute female labour-market barriers at occupation level across economies. / Building a semi-endogenous growth model to understand how migration, knowledge diffusion and remittances interact. / The programme produces impact and influence at the IMF itself, as well as directly with policymakers in LICs. / The IMF is a significant and respected player in macroeconomic discussions in LICs worldwide. Therefore by supporting LIC research that enhances the evidence-base and the IMF’s capability, the IMF is better able to serve and influence macroeconomic policymakers within LICs. / Via the dissemination of programme research and products, the programme also meaningfully contributes to the deepening of understanding of LIC macroeconomies – a vital yet neglected, and increasingly challenging area of economic research. / The IMF has unique channels through which it can feed evidence into policymaking discussions, including annual Article IV surveillance missions and reform programmes that countries agree when they take out IMF programme loans. Outputs from the MRLIC programme such as research products and policy toolkits helps to shape what flows through these channels.
What is the additional and total support the UK will provide?
The proposed support for Phase 5 is up to £4.0m over four years (April 2026 – March 2030), bringing the total programme cost to £25.68m. / This project has received the following funding from FCDO to date: / Phase 1 (2012-2015): £4.14m / Phase 2 (2015-2017): £5.47m / Phase 3 (2017-2020): £5.13m / Phase 4 (2020-2024): £5.1m + no cost extension to 2024 / Bridge Extension (2024-2026): £1.84m / The rationale for the additional FCDO contribution is as follows: / MRLIC is a high performing programme with strong independent review findings: The programme has maintained annual review scores of A and above across all previous phases. A recent independent external review commissioned by FCDO concluded that MRLIC "exceeded all expectations" and "is unquestionably a highly successful project." The review found that MRLIC produced over 200 working papers, more than 110 published papers, 16 toolkits, and 52 training courses—filling a global research void as LIC-focused work declined elsewhere. / MRLIC continues to build influence in the IMF: The output of the programme allows FCDO to influence the IMF to increase focus on LIC priority areas. MRLIC research informed over 120 IMF country reports and several Board papers. Tools such as the Debt-Investment-Growth (DIG) model and Forecasting and Policy Analysis System (FPAS) are now standard in LIC policymaking. / MRLIC fills a clear gap in the macroeconomic field: Few macroeconomists work on LICs; few development economists work on macroeconomics; and central banks and other macroeconomic institutions in LICs face capacity constraints. The IMF—given the skills of its staff and their role in making policy recommendations to governments—are ideally placed to fill this gap. / IMF would not undertake this work without FCDO support: The IMF's mandate is mainly about systemic challenges to the global financial system. LICs do not present a systemic challenge. While supporting LICs is part of their mandate, resources available for policy-relevant research on LICs are insufficient. Other IMF Executive Board members view the funding of LIC-focused research at the Fund as a UK comparative advantage. / MRLIC helps demonstrate UK global leadership on LICs: Results of MRLIC research feed through into IMF country programming, Board discussions, presentations and papers, and policy papers. This demonstrates the UK's leadership on, and commitment to, understanding and addressing LIC issues, providing additional authority at the IMF. / MRLIC delivers global public goods: The MRLIC partnership advances the mandate of both FCDO and the IMF in supporting LICs. MRLIC contributes to the FCDO's goal to promote economic development and prosperity in the developing world, and the IMF's mandate to help LICs build and maintain strong economies.
What are the expected results?
MRLIC's expected outcome is to engender "Better engagement by IMF policymakers on LIC-specific macroeconomic issues, leading to improved policy making in specific project thematic areas." The key indicator in tracking progress against this outcome will be evidence of improved IMF policymaking and integration of LIC-specifics in MRLIC thematic areas. This will be achieved through the following outputs over the full phase: / i. High quality, policy relevant, open access research on macroeconomic issues affecting LICs produced: / Working papers (40) / Peer-reviewed publications (20) / ii. IMF research products used by IMF country teams and partner authorities: / Application and use of tools and frameworks by country authorities and country teams (36) / Courses offered to country authorities and IMF staff (16) / iii. Engagement by senior IMF policymakers on issues affecting LICs strengthened: / High level policy conferences attended by senior IMF staff reflect findings of research papers funded under this project (8) / Results of the research reflected in IMF Board discussions and papers such as IMF Policy Papers, Staff Discussion Notes, policy memos to management etc. (12) / The programme has consistently demonstrated strong value for money (VfM). Cost per working paper and publication sit well below FCDO’s benchmarks, and administrative management costs are highly competitive. / A key VfM priority for Phase 5 will be to better integrate metrics that track utilisation and impact. Qualitative testimonials in particular will be a new and important component in capturing how influential and impactful MRLIC’s outputs are in country. The programme will aim for two to three qualitative impact assessment cases studies in each MRLIC annual report, with data collected from 1. mission chiefs and IMF country team members on influence and impact of MRLIC products used in Article IV work, and 2. country authorities on the usefulness of MRLIC research and tools, and what influence this had on country decisions.
What is the approach to implementation?
On approval of Phase 5, we will formalise our agreement by revising the existing Letter of Understanding (LoU) between FCDO and the IMF. We plan to release funds via annual disbursements. As before, the project would be administered under the UK FCDO Fund Activities Subaccount at the IMF. The LoU is signed by both FCDO and the IMF. Execution would follow the existing policies and procedures of the IMF and FCDO. / The Research Department (RES) will lead the project during Phase 5, collaborating with the Strategy Policy and Review (SPR), the Institute for Capacity Development (ICD) and the Fiscal Affairs Departments (FAD). Consultations with area departments will be strengthened through regular in-reach events to increase awareness of programme outputs and seek views on the analytical needs of country teams and authorities. / Many of the research officers and economists hired from outside the IMF to work on the project will stay on past March 2026—hence Phase 5 will have the benefit of starting with an experienced core team. / There are no concerns on management or implementation of the project from the IMF; the programme has been high performing to date. FCDO and the IMF leads will continue to have quarterly reviews of progress with regular updates of upcoming publications, papers and events. There will continue to be detailed annual reporting and review of the programme at FCDO annual reviews. The IMF will provide a regular 'forward look' document with upcoming publications, papers and events. / Financial sustainability efforts may see MRLIC’s donor base broaden, bringing additional implementation requirements. Where possible, new contributions would be channelled through FCDO’s existing arrangement with the IMF, and programme management structures aligned through consolidated processes. / Gender Equality / MRLIC has performed especially strongly in this area. The 'enhancing inclusion' theme focuses strongly on macroeconomic issues around gender equality. Phase 5 will continue this work, including using state-of-the-art models to compute female labour-market barriers at occupation level and examining talent misallocation. The programme will also explore extending frameworks to examine other dimensions of inclusion, such as labour market barriers for minority ethnicities. / Terrorism Act / The risk of programme resources being used to fund terrorism is extremely low and acceptable. The IMF is an established partner. We will continue to ensure that all implementation partners are aware of HMG policy and funding rules to counter terrorist financing.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
Several key changes and developments inform Phase 5: / 1. Independent Review Findings / A comprehensive independent external review was conducted by Shantayanan Devarajan (Georgetown University) and Stephen O'Connell (Swarthmore College), commissioned by FCDO. The review concluded that MRLIC "exceeded all expectations" across all five dimensions assessed: strategic alignment, management, output, policy impact, and sustainability. Key findings include: / MRLIC's agenda is tightly matched to LIC needs / The programme produced over 200 working papers, 110+ published papers, 16 toolkits, and 52 training courses / MRLIC research informed over 120 IMF country reports and several Board papers / Multiple tools developed by MRLIC are now standard in LIC policymaking, including the Forecasting and Policy Analysis System (FPAS) for supporting development of modernised monetary policy frameworks, and the Debt-Investment-growth (DIG) models, for evaluating non-concessional borrowing in LICs. The review found that these frameworks have in many cases been successfully adopted by LIC Governments. The review recommended adapting analytical frameworks to current LIC challenges, strengthening risk analysis, incorporating political economy considerations, and improving data transparency on debt. / 2. Leadership Transition / The Research Department (RES) will lead Phase 5, continuing the arrangement from the one-year bridge extension. This maintains collaboration with SPR, ICD and FAD departments. / The IMF’s Low-Income Countries Consultative Working group will form an internal advisory committee, meeting 2-3 times a year to discuss LIC-related issues, and to provide advice towards and judgement on MRLIC’s outputs. / In addition, a new external advisory committee comprising a small group of experts (e.g., top representatives from FCDO, IMF, academia, thinktanks and policy institutes) will provide independent, non-binding advice to the programme, meeting once a year. / 3. New Topic Area: Leveraging Microdata / Phase 5 introduces a new topic on leveraging microdata in LICs for better macro policies. This responds to the increasing availability of granular administrative data and its potential to transform empirical analysis, while recognising that LICs remain severely underrepresented in microdata research. / 4. Extended Programme Duration / Phase 5 covers four years (April 2026 – March 2030), providing a longer planning horizon to develop and implement comprehensive research agendas and build sustained partnerships with LIC institutions. / 5. Path-Finding Papers / FCDO commissioned path-finding papers that outline five strategic themes for future research, which directly inform the Phase 5 research agenda. These papers identify gaps in existing literature and emerging global economic trends that MRLIC needs to address.
List of Annexes: / Annex I: Budget details

Annex I: MRLIC Phase 5 Summary Budget
Description	Amount in U.K. pounds (preliminary)	Amount in U.S. dollars (preliminary)*
Peer to peer engagement	266,200	355,191
Field based work	50,000	66,715
Development of general CD technical materials	2,044,549	2,728,044
Development of CD tools	187,451	250,116
Development of training courses or other learning materials	136,918	182,690
Interactive learning and workshops	253,400	338,112
CD Project Management	799,800	1,067,174
Sub-Total	3,738,318	4,988,042
Trust Fund Management Fee (7.5%)	261,682	349,163
TOTAL	4,000,000	5,337,205

* The currency conversion is based on the exchange rate as of December 8, 2025 (1 U.K. pound = 1.3343 U.S. dollars).
Note: The budgeted amounts are expected to be spent evenly over the four years of Phase 5, though plans are subject to change should circumstances alter in an unforeseen manner.

Annex II: FCDO IMF MRLIC_Phase 5 Proposal.pdf