## Annual Review Template

Title: Jobs and income for Women Research Programme
Programme Value £ (full life): £49.85m		Review date: September 2025
Programme Code: 203050	AMP start date: 27/02/2013	AMP end date: June 2030

Summary of Programme Performance

Year	July 2014	July 2015	July 2016	July 2017	July 2018	July 2019	Sept 2020	Aug 2021	Sept 2023	Sept 2024	Sept 2025
Overall Output Score	A	A	A+	A+	A	A+	A	A+	A+	A	A+
Risk Rating	Low	Minor	Minor	Minor	Minor	Minor	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/S20305017.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007418.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Jobs and Incomes for Women Research Programme aims at understanding and generating high-quality evidence on “what works, what does not and why” for government, donors and the private sector to address gender inequality and boost women’s economic and social empowerment. Its research focuses on six main themes: agriculture, private sector development, property rights, social norms, youth employment, and social protection.

This is delivered through three core activities:

1. Delivering high-quality, policy-relevant impact evaluations on how to close the gender gap in the five thematic areas.
2. Dissemination of knowledge of effective gender policies and engagement with policy makers to influence policy demand and uptake.
3. Support in the uptake and design of innovative, cost-effective and scalable initiatives that can improve the social and economic opportunities of women and girls.

The programme is implemented by the World Bank Africa Gender Innovation Lab (AGIL), that sits in the Africa Chief Economist Office. FCDO support began with a commitment of £11.58 million in 2013 (Phase 2 of AGIL) to implement the findings of the World Development Report 2012 on Gender Equality and Development. FCDO provided a further £8.18 million in 2017 (Phase 3), following a commitment made during the High-Level Panel on Women’s Economic Empowerment. In June 2018, the British Embassy in Ethiopia signed a direct contribution to AGIL (of up to £1.03 million) to undertake an evaluation of an SME finance project. In March 2023, a two year extension of up to £2 million was approved to create additional knowledge products which increase awareness and dissemination of rigorous evidence amongst researchers and policy makers on AGIL’s key activities. In September 2024, a further extension was approved for £28.1 million (giving a revised programme total to £49.85 million) until June 2030. In addition to the core activities, this extension will support activities through the East Asia Pacific Gender Innovation Lab (EAPGIL), the Living Standards Measurement Study (LSMS), the South Asia Regional Gender Innovation Lab (SARGIL) and Women, Business and Law (WBL). The extension also promotes a helpdesk service to share evidence, provide advice and expertise to FCDO country and policy teams to expand understanding, inform their analysis and policy engagement, and shape future programming.

FCDO funds are provided through the World Bank-led Umbrella Fund for Gender Equality (UFGE). Over time AGIL has attracted funding from other donors (UFGE includes: Australia, Canada, Denmark, Finland, Germany, Iceland, Latvia, the Netherlands, Norway, Spain, Sweden, Switzerland, United States, the Bill and Melinda Gates Foundation and other World Bank trust funds), with FCDO’s share of overall financial contributions falling from 60% of the total over 2013-2017 to 19.7% in 2024/25.

Summary supporting narrative for the overall score in this review

This Annual Review reflects the programme’s achievements in the period between June 2024 and June 2025. The programme has scored an A+ overall moderately exceeding expectations. The programme is surpassing the annual impact, outcome and output targets for the reporting period.

AGIL’s influence on development spending continues, for instance through its influence in shaping the design of major regional Bank projects. Examples include the Chad Digital Transformation Project, Ethiopia’s Financial Sector Strengthening Project, Additional Financing to Nigeria’s Community Action for Resilience and Economic Stimulus (CARES) Program for Results, and Zambia Girls' Education and Women's Empowerment and Livelihoods for Human Capital Project. These projects have all integrated evidence-backed programming based on engagements with and contributions from AGIL. Moreover, new efforts to track the number of beneficiaries reached by AGIL-influenced programming revealed that, upon completion of ongoing projects, over 43 million beneficiaries are expected to benefit from evidence-improved adolescent girls’ programming due to AGIL. As a testament to AGIL’s success in not only advancing the knowledge frontier, but also ensuring that its evidence translates into policy action, the 2025 World Bank Independent Evaluation Group report, “Learning in World Bank Lending”, highlighted the Africa GIL as one of the three standout examples of World Bank units that have effectively embedded knowledge into Bank operations in a systematic way.

While our support for EAPGIL, LSMS, SARGIL and WBL is at an early stage, these partners are already demonstrating strong signs of positive influence and high-quality reach leading to impact. This year SARGIL demonstrated compelling influence through three World Bank operations, totalling $277 million in development spending and two new examples of policy influence in Pakistan and Bhutan. EAPGIL has influenced $10 million of development spend over the last year, including a new World Bank operation in Cambodia and a new government regulation in the Philippines. During the reporting period LSMS reported influencing $1.2 billion of development spend including projects on human capital projections in Burkina Faso and governance modernisation in Ethiopia, while WBL reported directly influencing commitments through the G20 process on removing legal barriers to women’s economic participation.

Major lessons and recommendations for the year ahead

The programme has performed well during a time of uncertainty. To build on the success of this year the programme should implement the following recommendations:

- Now that the programme represents research from multiple regions and partners it would be useful to have an integrated research uptake strategy, and one which explicitly targets external stakeholders alongside those within the World Bank structure.
- Given the overachievement against all indicators, the programme should revise the logframe targets to reflect realistic but stretching future levels of delivery, while also taking into consideration potential budget challenges.
- The programme should build on the lessons from this year’s reporting process to formalise consistent reporting structures, governance and templates including for value for money metrics (especially for LSMS).
- The programme should build on the success of this year’s Helpdesk advice and capitalise on the push within FCDO to mainstream gender and women’s economic empowerment. FCDO and the programme team should finalise a joint strategy to that effect included agreed helpdesk protocols.
- As the programme partners are leading centres for research into Women’s Economic Empowerment FCDO is keen to ensure it pulls together global evidence on key topics to influence policy. Therefore, going forward there should be an increased focus on synthesis products and dissemination.
- The programme should seek to strengthen its measures of cost-effectiveness.
In addition, one recommendation from the 2024 Annual Review should be retained:

As the regional report on Adolescent Girls Economic Empowerment has been completed, FCDO and AGIL will work together to engage FCDO country offices on the findings and implications for policy and programming.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change was revised during the business case extension and approved in September 2024. Three ways in which the current theory of change is different than previous ones are:

- A more evolved strategy for engaging with policymakers and influencing policy and programs. This includes specific strategies for engagement at three distinct levels: the global dialogue, project-level, and country-level.
- Incorporating work on measurement, where needed, due to unavailability or inadequacy of existing measures.
- Supporting the roll-out of high-quality nationally representative surveys, that help build the evidence base.

Good data and good measurement tools help us identify and prioritise gender gaps and constraints to women’s economic empowerment. They also help us evaluate the impact of interventions. Finally, high-quality nationally representative survey data that shows the breadth and depth of gender gaps are incredibly valuable for informing discussions with policymakers, national policy dialogues, and selection and targeting of interventions.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact achievements

The impact objective of the programme is “to increase government, donor, and private sector uptake of effective policies that can address the underlying causes of gender inequality in Africa”, particularly in terms of women’s economic and social empowerment, and through that promote development, poverty reduction, and growth.[1]
[1] AGIL’s research uptake strategy has three parts: i) Bringing ideas together and getting them into the global discussion; ii) Changing the discussion at the country-level; iii) Influencing program design and implementation at the project-level.

Impact Indicator 1: Cumulative $ value of development spending directly influenced by GIL

A detailed deep dive into AGIL’s research uptake was completed at the end of 2024. The deep dive found that AGIL evidence has directly influenced the design of project sub-components spending $12.8 billion across 224 projects in 53 countries since its inception in 2013, with every dollar invested in AGIL influencing $184 in development spending (this doesn’t capture scale up outside World Bank operations). In 2023 ($1.5 billion) and 2024 ($1.4 billion), AGIL influenced the design of $2.9 billion[2] in direct sub-component value across 55 projects in 29 countries. Major projects, like the Chad Digital Transformation Project, Ethiopia’s Financial Sector Strengthening Project, and the Additional Financing to Nigeria’s Community Action for Resilience and Economic Stimulus (CARES) Program for Result, have all integrated evidence-backed programming based on evidence shared by AGIL.
[2] During the reporting period, FCDO funding constituted 19.7% of AGIL’s total funding and has reduced over the lifetime of the programme. This should be taken into consideration when discussing the attribution of the impact of FCDO funding through the Jobs and Income for Women Programme.

While too early to ascertain the influence of FCDO funded activities outside of AGIL which has been funded by FCDO since 2013, the annual review includes the following for illustrative purposes. EAPGIL has influenced almost $7 billion of development spending, of which £10 million was in the last year. As of June 30, 2025, SARGIL has shaped $671 million of development spending. This amounts to an impact of approximately $94 for every $1 invested in SARGIL. In FY25 alone, SARGIL influenced the design and/or implementation of three World Bank operations, totalling $277 million in development spending. During the reporting period LSMS reported influencing $1.2 billion of development spend.

Impact Indicator 2: Number of policies, strategies, planning documents, regulations or laws influenced by GIL

The programme partners influence how policymakers frame and approach challenges; contribute to World Bank reports and strategy; advise Ministries of Finance and key line Ministries on ways to achieve gender equality; and help improve the design of Government and World Bank programmes and policies. Through these efforts the programme helps policymakers sift through the evidence to identify the highest-priority constraints and how to cost-effectively address them.
During the reporting period, AGIL informed six new national policies and strategies in Cameroon, Côte d’Ivoire, Ethiopia, Lesotho, Mozambique, and Nigeria. In Cameroon and Côte d’Ivoire, AGIL supported the design of a Development Policy Financing (DPF) operation, a type of World Bank financing instrument that disburses based on the implementation of government reforms. At AGIL’s suggestion, the DPF in Cameroon included reforms to increase girls’ access to education while the DPF in Côte d’Ivoire unlocked tranches of financing based on the adoption of two ministerial directives facilitating the reintegration of female student teachers and female students when dropping out due to pregnancy or gender-based violence. In Ethiopia, AGIL's Gender Innovation Policy Initiative and Innovations in Financing Women Entrepreneurs initiative deepened its partnership with the National Bank of Ethiopia to advance gender inclusion in the financial sector, launching the country’s first “Women’s Financial Inclusion Scorecard. In Lesotho, AGIL collaborated with the Millenium Challenge Corporation on the design of two digital financial services to boost women’s access to capital, ultimately contributing to the implementation of the government’s National Financial Inclusion Strategy. Meanwhile, in Nigeria, the Nigeria Gender Innovation Lab (NiGIL) collaborated with the Kaduna State Government to domesticate the federal Women’s Economic Empowerment Policy, which reflects AGIL’s design inputs, at the state level by mapping relevant strategies from the federal policy to address state-level policy priorities.

POLICY IMPACT SPOTLIGHT: The Ethiopia GIL partnered with the National Bank of Ethiopia (NBE) to launch Ethiopia’s first Women’s Financial Inclusion Scorecard in March 2025. As an innovative tool to help financial institutions assess how well they serve women as clients, employees, and leaders, the scorecard evaluates institutions across three core areas—workforce inclusion, access to financial products, and tailored innovation—and scores them between 1 and 5, unlocking the possibility of benchmarking to encourage continuous progress across the sector. Results from the initial implementation of the scorecard with 30 financial institutions were presented at Ethiopia’s Finance Forum on May 16, 2025, and offered insights into promising developments for the sector, as well as key areas for growth.

Moving forward, the NBE is working to integrate the scorecard into its supervisory frameworks to reinforce accountability and track sector progress. The tool will also inform future policy development under Ethiopia’s next National Financial Inclusion Strategy. The Ethiopia GIL has been invited to engage on the further roll out of this work.
As with above, while too early to ascertain the influence of FCDO funded activities outside of AGIL, the annual review includes the following for illustrative purposes. This year, EAPGIL’s work influenced the World Bank supported Cambodia Basic Education Improvement Project is introducing new activities to increase household demand for childcare services. In the Philippines, land titling processes were adjusted based on recommendations from EAPGIL’s work which indicated the importance of including the names of both spouses on land title documents.

SARGIL influenced two policy changes in Pakistan and Bhutan during the reporting period, bringing the total number of policies, strategies, planning documents, regulations or laws influenced by SARGIL to five. SARGIL’s research has also informed the Khyber Pakhtunkhwa Rural Accessibility Project’s targeting strategy to encourage girls to attend school by offering subsidised public transport. SARGIL’s research informed the optimal level of the transport subsidy, and the M&E design, including safeguarding. SARGIL is working closely with the provincial government to explore opportunities for scaling up the intervention based on early evaluation findings. SARGIL has also influenced the gender strategy embedded in Pakistan’s new 10-year country partnership framework (CPF). Key contributions included organising a high-level workshop to share the latest research on gender innovative approaches, and co-authoring a companion document outlining how the CPF aims to reduce gender disparities across key outcome areas. A highlight of this collaboration was the establishment of the new Pakistan Data and Evidence Lab (DEL). SARGIL leads one of the DEL’s core pillars focused on generating rigorous impact evaluation evidence, with an emphasis on innovations to promote gender equality at scale. During the reporting period, LSMS indicated they had influenced 4 policies, strategies, planning documents, regulations or laws. These were on sustainable power and climate resilient roads in Nigeria, on human capital projections in Burkina Faso and governance modernisation in Ethiopia. The WBL’s data and insights have informed the World Bank Group’s latest Gender Strategy and its global implementation. Specifically, contributing to “enhancing strategic country engagement” and “mobilising collective action through data through data, knowledge, and advocacy with partners”. In addition, legal reforms informed by WBL are listed in the World Bank Corporate Scorecard Results Narrative on Gender.

Outcome achievements

The intended outcome of the Jobs and Income for Women programme is “increased knowledge on how to close gender gaps in the areas of agriculture; private sector development; property rights; youth employment and labour; social norms; and use and control of productive assets”.

Outcome 1: tracks the Cumulative number of academic papers and policy reports citing gender lab studies. In the last year, the programme reached over 3,300 citations according to Google Scholar.[3] Key examples of high-profile publications citing Jobs and Income for Women evidence include the "Gender Equality and Economic Transformation: Lessons From Africa” report by the African Center for Economic Transformation. The 2024 World Development report also cited the joint work with the IFC and Village Capital (including the paper on "Asking Better Questions: The Effect of Changing Investment Organizations’ Evaluation Practices on Gender Disparities in Funding Innovation"). Several other World Bank publications highlighted findings from AGIL, such as the “Leveling the Playing Field: Addressing Structural Inequalities to Accelerate Poverty Reduction in Africa” by the Poverty and Equity Global Practice and Africa Chief Economist Office.
[3] All AGIL economists are registered on RePec and Google Scholar. The AGIL team has also created Google Alerts and monitors citations

The programme’s evidence featured prominently in internal communications as well as external articles. The launch of the report Pathways to Prosperity for Adolescent Girls in Africa, in November 2024, was accompanied by a World Bank Africa Chief Economist’s podcast episode of Afronomics. This received global media coverage from over 20 media outlets in French and English, including regional and national media outlets in Australia, Liberia, Kenya, Morocco, Rwanda, and South Africa. The publication page itself has gathered over 18,000 unique visitors (86.5% of whom are based in developing countries) since the report launch, and over 7,000 downloads of the report and/or the executive summary. Other GIL reports and papers were also highlighted in the news media and via podcasts and knowledge sharing platforms. The papers produced by the LSMS were cited in 1,602 papers in FY25.[4] WBL was cited in 23 papers or reports drawing on its data to assess gender disparities in areas such as legal rights, workplace protections, and economic agency during the reporting period.
[4] The LSMS compiled citations using Google Scholar.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme should continue. The Jobs and Income for Women programme contributes directly to delivering the UK strategic commitment to growth and economic development as is demonstrated by the forthcoming Economic Development Strategy and the forthcoming UK International Gender Equality Framework. These key documents both highlight the need for investment in research to inform effective policy and programming on these issues. The UK Government has highlighted empowering women and girls as a priority area for UK international development efforts.

The programme has a strong track record of conducting robust impact evaluation to test new and ongoing interventions, producing high-quality evidence and influencing World Bank operations and increasingly country government policies. FCDO’s support has demonstrated strong value for money and materially improved the lives of women and girls, through AGIL’s evidence improving the effectiveness of over $12.8b of World Bank operations to date. For example, AGIL’s calculations, to assess the financial return of AGIL investment estimated in 2025 that each dollar spent on research results in $184 of development programming being made more effective by the evidence. SARGIL estimates an impact of approximately $94 for every $1 invested in SARGIL.

## C. DETAILED OUTPUT SCORING

Output Title	Rigorous impact evaluations and analytical work that generates evidence on gender-related constraints and how to close gender gaps and advance women's economic empowerment.
Output number:		1.A and B	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1A.1: Number of rigorous IEs with an approved concept note (GILs only)	AGIL: 3 / EAPGIL: 2 / SARGIL: 2	Exceeded / AGIL: 7 / EAPGIL: 2 / SARGIL: 2
1A.2: Number of IEs (ongoing and new) with completed follow up surveys (GILs only)	AGIL: 4 / EAPGIL: 0 / SARGIL: 1	Exceeded / AGIL: 6 / EAPGIL: 0 / SARGIL: 2
1A.3: Peer reviewed journal publications	AGIL: 4 / EAPGIL: 0 / SARGIL: 1 / WBL: 0	Exceeded / AGIL: 9 / EAPGIL: 0 / SARGIL: 2 / WBL: 1
1A.4: Data sets made openly and freely available to external researchers	AGIL: 8 / EAPGIL: 1 / LSMS: 0 / SARGIL: 0 / WBL: 0	Exceeded / AGIL: 13 / EAPGIL: 1 / LSMS: 0 / SARGIL: 0 / WBL: 1
1b.1 Number of methodological studies designed and implemented.	LSMS: 0	Exceeded / LSMS: 2
1b.2 Number of datasets produced from methodological studies or national surveys that have integrated improved methods.	LSMS: 0	Exceeded / LSMS: 3
1b.3 Number of peer reviewed journal publications	LSMS: 0	Exceeded / LSMS: 16
1b.4 Number of survey modules and tool packages developed and disseminated	LSMS: 0	Exceeded / LSMS: 7
1b.5 Number of new or updated guidebooks	LSMS: 0	Exceeded / LSMS: 3

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on rigorous impact evaluations and analytical work. The World Bank teams have continued to generate high quality evidence on gender-related constraints and how to close gender gaps and advance women's economic empowerment. This year is the first since the programme extended to include EAPGIL, LSMS, SARGIL and WBL. We have scored this output an A+ with an expectation that targets for future years will be revised upwards and build on the strong delivery demonstrated this year. There were no targets set under Output 1b for the five indicators linked to LSMS delivery and therefore these have not been formally scored as part of this Annual Review, but have been included to capture the efforts of the programme team during the reporting period.

Output 1A.1 - In the reporting period, eleven new concept notes have been approved after a rigorous peer review process. These included:

- Inclusion and Financial Planning in Benin
- Rising Together: Assessing the Impact of Scalable Interventions to Overcome Barriers to Child Development and Women's Economic Empowerment in Côte d’Ivoire
- Impacts of large collateral-free loans for successful female group loan clients in Ethiopia
- Implementer-Led Evaluation and Learning Strengthening Productive Safety Net Program’s Institutions and Resilience in Ethiopia
- Increasing Women's Access and Use of an Agriculture Extension Hotline in Ethiopia
- Can low-cost health insurance boost individual economic outcomes and savings group sustainability in Nigeria
- Tweaking Savings Group Rules to Boost Economic Outcomes in Nigeria
- Bus-tling to Success: Experimental Evidence on Subsidized Transportation for Girls in Remote Contexts in Pakistan
- Impact Evaluation of the BISP-CRISP Savings Scheme in Pakistan
- Community based childcare and women’s economic empowerment in Indonesia
- Green public works program in Fiji (now cancelled)

Output 1A.2 – includes all impact evaluations with completed follow up surveys. In the reporting period, 8 new IEs completed follow up surveys. These range in topics, from agricultural finance in Nigeria Personal Initiative Skills, Firm Performance and Household Dynamics in Rural India and female entrepreneurship in Mozambique. The analysis from many of these surveys result in working papers and presentations, highlighted under Output 3.

Output 1A.3 – milestones against this output on peer reviewed journal publications were over-achieved this year, with 12 new peer reviewed journal publications in the reporting period. Of particular interest:

1. “Better Loans or Better Borrowers? Lifting Credit Constraints for Women-Owned Firms in Ethiopia” by Salman Alibhai, Niklas Buehren, and Sreelakshmi Papineni, Journal of Alternative Finance, April 2025.
2. “Impact of Inputs, Information, and Financial Services on the Adoption of a Biofortified Crop by Women Farmers in Uganda” by Niklas Buehren, Shyamal Chowdhury, Sreelakshmi Papineni, and Munshi Sulaiman, American Journal of Agricultural Economics, April 2025.
3. “Women’s Economic Participation, Time Use, and Access to Childcare in Urban Bangladesh” by Emcet O. Taş and Tanima Ahmed, Forum for Social Economics, November, 2024.

Output 1A.4 records the number of datasets made openly and freely available to external researchers in the World Bank open access repository, with 15 additional datasets published in the last 12 months surpassing the milestone in this previous reporting period. These data sets include those produced from impact evaluations and from other non-impact evaluation activities.

Output 1B.1 measures the number of methodological studies designed and implemented. This year LSMS had a target this year of zero but achieved two. These studies were1) a phone survey experiment in Malawi, using survey-to-survey imputation for more frequent and lower-cost poverty estimates and exploring the impact of recording interviews and 2) the Ethiopia integrated health facility survey which integrates the World Bank’s ongoing High Frequency Phone Survey of households with a phone survey of health facilities. The integration of these two surveys aims to generate additional insights into access, utilisation, and quality of service delivery and related factors.

Output 1B.2 measures the number of data sets produced from methodological studies or national surveys that have integrated improved methods. This year LSMS had a target this year of zero but achieved three in the reporting period. These were: 1) The LSMS-HFPS Harmonised Dataset; 2) the LSMS-ISA-Harmonised Dataset and 3) GHS-Panel Wave 5.

Output 1B.3 measures work towards peer reviewed journal publications. During the reporting period LSMS delivered 13 against a target of zero, of particular interest:

- Poverty Imputation in Contexts Without Consumption Data: A Revisit with Further Refinements
- Inequalities in Job and Income Loss in Countries with High Prevalence of Informal Employment in Sub-Saharan Africa during the COVID-19 Crisis
- Breadwinners and caregivers: Examining the global relationship between gender norms and economic behaviour

Output 1B.4 measures the number of survey modules and tool packages developed and disseminated, and this year LSMS delivered 7 against a target of zero. These were:

  - LSMS 2.0 Face-to-Face Survey Questionnaire
  - Survey Solutions CAPI Application - LSMS 2.0 Face-to-Face Survey Questionnaire
  - LSMS 2.0 Phone Survey Questionnaire
  - Survey Solutions CAPI Application - LSMS 2.0 Phone Survey Questionnaire
  - LSMS 2.0 Data Quality Assurance Package
  - LSMS 2.0 Manuals and Training Materials
  - LSMS 2.0 Survey report package (includes report template with tables, basic information document template, note for data formatting for dissemination)

Output 1B.5 considers the number of new or updated guidebooks, this year LSMS delivered 3. These include:
- Technical Note on GPS Coordinate Collection in 50x2030 Surveys
- Integrating AIM-ECD CR Child Development Items into Multi-Topic Household Surveys: Design and Implementation Guidelines
- Weighting, Chapter 8 of the UN Handbook of Surveys on Individuals and Households: Foundations and Emerging Approaches (Draft)

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme was extended in September 2024 and now includes EAPGIL, LSMS, SARGIL and WBL. The indicators under this output have therefore been revised to reflect this extension and expansion of focus.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations linked to this output under the previous annual review.

Recommendations for the next reporting period:

Revise the logframe targets for future years to reflect the impressive work achieved by all partners in the current reporting period while being mindful of potential changes to budgets.

Output Title	Synthesis papers that integrate the evidence
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Synthesis reports	AGIL: 1 / EAPGIL: 0 / LSMS: 0 / SARGIL: 1 / WBL: 0	Exceeded / AGIL: 1 / EAPGIL: 1 / LSMS: 4 / SARGIL: 1 / WBL: 0

Briefly describe the output’s activities and provide supporting narrative for the score.

The output focuses on the synthesis reports produced during the reporting period. AGIL and SARGIL delivered against their targets, while EAPGIL also delivered an additional synthesis report. For this reason the output exceeds expectations and scores an A+.

In November 2024 AGIL published “Pathways to Prosperity for Adolescent Girls in Africa”, in collaboration with the World Bank People Vertical, the Center for Global Development (CGD) and the Population Council. The report presents a comprehensive review of evidence-based interventions, an innovative framework for understanding and measuring girls’ empowerment, and a data-driven typology of African countries to inform policy and investment decisions. With six actionable pillars—from building girls’ human capital and economic success to addressing evidence gaps and targeting the most vulnerable, the report underscores the transformative role adolescent girls can play in shaping Africa’s economic future. Since its release, the report was downloaded over 7,000 times and was mentioned by over 20 global media outlets.

In December 2024, SARGIL launched Women's Economic Empowerment in Pakistan: An Evidence Guided Toolkit to coincide with World Human Rights day. The report highlights the extent of the gender gaps using the most recent data and evidence and provides an evidence-based toolkit for policy makers to support women’s economic empowerment through three pillars 1) wage employment and entrepreneurship; 2) productive assets, and 3) safety and mobility, agency, and the influence of social norms within the household and on women’s lives.

During the reporting period, EAPGIL launched a synthesis report called “What Have We Learned from EAPGIL Research”. The report reviews key findings on themes and how these lessons can be applied moving forward. The report highlights the importance of Removing Barriers to Productivity for Female Entrepreneurs and Farmers, Social Protection and Women’s Empowerment, Childcare and Women’s Work, Building and Protecting Women’s Human Capital, and Measuring Women’s Agency.

Lastly, during the reporting period LSMS published 4 synthesis reports, these were:

- The dynamics of financial inclusion in Ethiopia: Diversifying delivery channels, expanding digital technology, and enhancing financial knowledge for greater financial inclusion
- Urban Informal Business Enterprises in Ethiopia: Stylized Facts, Gender and Taxation
- Understanding Early Childhood Development in Nigeria
- Protecting Human Capital During Episodes of Forced Displacement: Ukrainian children in Italy.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme was extended in September 2024 and now includes EAPGIL, LSMS, SARGIL and WBL. The indicators under this output have therefore been revised to reflect this extension and expansion of focus

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review recommended that once the regional report on Adolescent Girls Economic Empowerment has been completed, that FCDO and AGIL work together to engage FCDO country offices on the findings and implications for policy and programming. Progress against this indicator has been delayed and should be retained for the forthcoming reporting period.

In addition, other recommendations for the reporting period includes:

- Now that the programme represents research from multiple regions and partners it would be useful to have an integrated research uptake strategy, and one which explicitly targets external stakeholders alongside those within the World Bank structure.
- As the programme partners are leading centres for research into Women’s Economic Empowerment FCDO is keen to ensure it pulls together global evidence on key topics to influence policy. Therefore, going forward there should be an increased focus on synthesis products and dissemination.

Output Title	Direct engagement with policymakers to inform and improve program design and with national and international institutions to promote the adoption of good data collection practices.
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Presentations of results to decision-makers with a development constituency	AGIL: 65 / EAPGIL: 4 / LSMS: 0 / SARGIL: 10 / WBL: 0	Exceeded / AGIL: 153 / EAPGIL: 13 / LSMS: 23 / SARGIL: 33 / WBL: 7
3.2 Number of policymakers with whom how to close the gender gap is discussed.	AGIL: 1466 / EAPGIL: 115 / LSMS: 0 / SARGIL: 250 / WBL: 0	Exceeded / AGIL: 7722 / EAPGIL: 1217 / LSMS: 414 / SARGIL: 664 / WBL: 35
3.3 (a) Engagements/contacts with policymakers (for GILs and WBL), and (b) data users/producers (for LSMS).	a) Engagements with policymakers / AGIL: 120 / EAPGIL: 8 / SARGIL: 13 / WBL: 1 / b) Data users/producers / LSMS: 0	Exceeded / a) Engagements with policymakers / AGIL: 226 / EAPGIL: 28 / SARGIL: 51 / WBL: 10 / b) Data users/producers / LSMS: 1130
3.4 Number of working papers and policy briefs	AGIL: 15 / EAPGIL: 3 / LSMS: 0 / SARGIL: 3 / WBL: 0	Exceeded / AGIL: 26 / EAPGIL: 5 / LSMS: 20 / SARGIL: 4 / WBL: 2
3.5 (for LSMS only): Number of countries per year in which NSO staff or local statisticians received technical support or training for the adoption/integration of improved methods.	LSMS: 5	Exceeded / LSMS: 30
3.6 Number of Help Desk assignments	All GILs: 4	5

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on policy engagement and research uptake. It aims to capture not just the ability of the partners to influence through formal presentations (including how many attendees there are) but also less formal bilateral meetings and other engagements. Broadly speaking the programme’s research uptake strategy focuses on i) bringing ideas together and getting them into the global discussion; ii) changing the discussion at the country-level; and iii) influencing programme design and implementation at the project-level. This output has been scored an A+ having exceeded all targets during the reporting period. This overachievement was due to participation in larger scale conferences and for more engagements than originally predicted. As the programme extension was approved in September, 2024, the logframe targets were set out of the usual cycle and underestimated the potential of the programme partners ability to deliver under a curtailed first year. This will form part of a review and refresh of the loframe for the next reporting period.

Output 3.1 counts the number of presentations given to development constituents e.g. World Bank, developing county governments, FCDO. This year’s target was for 70 presentations and this was exceeded by nearly three times as many presentations. Output 3.2 is a headcount indicator and measures the number of individuals at the presentations given under Output 3.1. The overarching target during the reporting period was over 1800 policymakers, this was significantly exceeded by over five times the target for the reporting period. Highlights include:

- In November 2024, AGIL presented at a joint gender engagement workshop with the World Bank Poverty Team, in support of the drafting process of the Ivorian National Development Plan 2025-2030. The presentation was delivered to 15 policymakers and focused on evidence-based avenues for improving productivity and growth in Côte d'Ivoire.
- In May 2025 AGIL co-hosted a two-day conference on Gender Policy and Research Gathering: Evidence, Innovation, and Action to Close Gender Gaps with the Social Development Practice under the DRC Country Management Unit (CMU) Gender Platform. AGIL presented evidence and operational insights from across the region. The event, organized and facilitated by AGIL, brought together government officials, civil society, universities, the private sector, and development partners from Angola, Burundi, DRC, and São Tomé and Príncipe.
- In September, 2024, EAPGIL and the World Bank’s Social Development Global Practice held a launch event for the “Supply of and Demand for Accessible and Affordable Childcare Services in Cambodia” report. This was attended by representatives from government and civil society. The launch included a presentation of the report and a round table discussion with ministers of the Government of Cambodia on how the findings related to the ongoing formulation of the sub-decree on childcare being prepared by the Ministry of Education, Youth, and Sport.
- In December 2024 SARGIL launched its publication, “Women’s Economic Empowerment in Pakistan: An Evidence Guided Toolkit for More Inclusive Policies”, in an in-person event in Islamabad, featuring the World Bank’s Pakistan Country Director alongside key stakeholders, including the Senior Joint Director for Agricultural Credit and Financial Inclusion of the State Bank of Pakistan and the Federal Ombudsperson for Protection Against Harassment of Women at the Workplace (Government of Pakistan). The event was attended by more than 80 participants – including representatives of the Pakistan national and provincial government, civil society, academia, and the media – and explored main highlights of this report and actionable guidance to prioritize women in policymaking and implementation, putting gender gaps at the front of the agenda. Key insights of the report were later featured by the Federal Ombudsperson Secretariat for Protection against Harassment and the President for Gender Equality at the Gates Foundation through their social media accounts.
- LSMS hosted an academic Conference in December 2024 called The Pulse of Progress: Harnessing High-Frequency Survey Data for Development Research in the Polycrisis Era. This conference held in Washington, DC was a forum to facilitate the exchange of ideas and solutions to development challenges related to the dynamics of resilience, tackling food insecurity in an era of crises, and advancing timely interventions and policies. It promoted the use of LSMS-HFPS data, which has generated knowledge that was previously unavailable in low- and middle-income countries, for operational and policy impact. The conference brought together researchers, experts and policymakers, and featured emerging, cutting-edge policy research papers that provided insights on wellbeing, jobs, gender, conflict and displacement, food security, extreme weather, shocks and their socioeconomic impacts using high-frequency survey data.
- In November 2024, WBL brought its data and analysis to the highest level of global policy debate at the G20 Social Summit in Brazil. The team presented evidence on how legislative reform in Brazil has reduced gender gaps by improving women entrepreneurs’ access to contracts, credit, and skills. Together with WBL’s engagement in the W20—the G20’s official platform for promoting gender equity—this work helped shape the G20 Rio de Janeiro Leaders’ Declaration. The declaration committed G20 members to adopt comprehensive policies to dismantle legal barriers and ensure women’s full and equal participation in the economy.

Output 3.3 measures less formal engagements and contacts with policymakers (for GILs and WBL) than the presentations counted under output 3.1. This had a target for 142 during the reporting period and was exceeded with 315 engagements and also measures data users and producers (for LSMS) which had a target of zero and exceeded this by 1130. These were with country governments, Development Finance Institutions and country project leads.

Output 3.4 focuses on the number of working papers and policy briefs, there was a target of 21 set for the reporting period, and 57 were delivered. This means more than 229 working papers and policy briefs have been published to date. This figure includes more than 109 working papers on gender issues, which inform policy briefs and results-sharing presentations. All World Bank working papers are reviewed by relevant country teams and a manager. AGIL has also published more than 120 policy briefs to date. The briefs identify gender gaps, assess gender differentials, and evaluate the gender impact of a number of policies and projects in African countries, and they also can inform global priorities. For example, AGIL evidence formed the core set of program and policy recommendations for a Global GIL Federation series of briefs prepared jointly with the Global Gender Group and partner GILs in other regions. These briefs also served as a key set of inputs for the formulation of the World Bank Group’s new gender strategy.

Output 3.5 measures the number of countries per year in which national statistics office staff or local statisticians received technical support or training for the adoption/integration of improved methods. This was exceeded six-fold compared to the target set for the reporting period. Details of which countries are in the table below:

Output 3.5: Countries where LSMS provided training for NSO staff or local statisticians
Algeria	Ethiopia	Nigeria
Benin	Gabon	Saudi Arabia
Burkina Faso	Guinea	Saint Lucia
Burundi	Guinea Bissau	Senegal
Cambodia	India	Solomon Islands
Cameroon	Equatorial Guinea	Somalia
Cape-Verde	Kenya	Tanzania
Central African Republic	Mali	Timor Leste
Congo Republic	Mauritania	Togo
Cote d’Ivoire	Niger	Zimbabwe

Output 3.6 concentrates on helpdesk requests from FCDO teams, and the target for this reporting period was exceeded by one. The requests this year were:

- A brief titled “Enhancing Women’s Economic Outcomes: Focus on Evidence-Based Options to Enhance Women’s Economic Participation and Earnings”. The brief synthesised global evidence from impact evaluations and rigorous research to identify effective interventions that promote women’s economic empowerment. Building on this work, the team developed a repository of systematic reviews and cost-effectiveness studies related to women’s empowerment outcomes in August 2024. This body of work culminated in the preparation of an internal FCDO evidence note on women’s economic empowerment in March 2025, which was peer reviewed by AGIL.
- In collaboration with the MENA Gender Innovation Lab, the team supported the FCDO Yemen office in identifying evidence-based pathways to enhance women’s participation in the country’s economic recovery.
- A rapid response brief synthesising global evidence on approaches to support women’s leadership, particularly in corporate settings such as business, finance, and entrepreneurship—drawing on AGIL’s work in this area.
- The team provided strategic guidance to the FCDO’s Global Food Security, Agriculture and Land Department on designing and implementing a gender portfolio review of agrifood systems and related programs.
- Explored the impact of a gender-based violence prevention programming in Zimbabwe.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme was extended in September 2024 and now includes EAPGIL, LSMS, SARGIL and WBL. The indicators under this output have therefore been revised to reflect this extension and expansion of focus

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review recommended a concerted effort from FCDO and AGIL to raise awareness of the Helpdesk to generate demand. This includes the possibility of a) using cadre conferences and newsletters to raise awareness b) direct outreach to specific policy teams in the wake of a new government c) use helpdesk products as themes for seminars to demonstrate how the helpdesk can be useful. FCDO can also engage with RED’s regional research hubs on the direction of the Helpdesk. While some activities were undertaken this remains a relevant recommendation for the next reporting period.

The recommendation for the next reporting period is:

- Output 3.4 should differentiate the target figure by Working Papers and Policy briefs rather than having a joint figure.
- The programme should build on the success of this year’s Helpdesk advice and capitalise on the push within FCDO to mainstream gender and women’s economic empowerment. FCDO and the programme team should finalise a joint strategy to that effect included agreed helpdesk protocols.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

Key observations on Value for Money across the programme are summarised below according to the ‘4 E’s’ of Economy, Efficiency, Effectiveness and Equity.

Economy
The input costs remain in line with the processes agreed centrally between the World Bank and FCDO, particularly contracted-in services, project staffing and travel costs. The programme has continued to make use of engaging with international partners remotely and keeping travel to a minimum.

Efficiency
- Impact Evaluations (which account for 80% of the total budget), have remained largely in line with the previous year’s costs. The average cost per impact evaluation has fallen by $25,000 to $625,000. This figure remains lower than the average cost of an Impact Evaluation, based on World Bank activities in 2018/19 which was around US$700,000. The World Bank anticipate that this will decline in the new fiscal year if, as proposed, the programme includes funding to some quicker-turnaround impact evaluations that examine short-run impacts to inform key operational questions. For benchmarking purposes, SARGIL’s average cost per impact evaluation is $535,000, EAPGIL’s average is $560,000.
- The cost to output ratio has also remained strong and consistent. The average cost per working paper has been consistent over the last few years and has marginally increased by $3,000 to $38,000 due the programmes staff cost increases. For benchmarking purposes SARGIL’s average cost per working paper is $37,000 and the figure for EAPGIL is $33,000.

Effectiveness
Number of downloads from document reports and the open knowledge repositories for AGIL: / Profiting from Parity report: 44,273 downloads / Levelling the Field report: 28,710 downloads / The cost of the gender gap in agricultural productivity in Malawi, Tanzania, and Uganda report: 17,651 downloads / In Search of Equity report: 8,510 downloads / Pathways to Prosperity for Adolescent Girls in Africa report: 7,232 downloads / Breaking Barriers report: 6,972 downloads / Nigeria Gender Diagnostic report: 5,155 downloads / Ethiopia Gender Diagnostic report: 4,286 downloads

- The programme has a strong reputation as a major provider of cost-effective and innovative interventions to enhance women’s social and economic empowerment, especially, but not only, in Sub-Saharan Africa. AGIL’s expertise is in high demand, its papers accepted in high level conferences and are increasingly cited as are SARGIL, EAPGIL, LSMS and WBL.
- The quantity of academic papers and policy reports citing AGIL studies reaching 3,073 during the reporting period, SARGIL outputs were cited 157 times, EAPGIL work was cited 151 times, and WBL’s work 23 times. LSMS academic papers were cited in 1,602 studies. All surpassed their targets. This is indicative of the programme’s effectiveness in increasing knowledge on how to close gender gaps in the focus areas.
- The programme has maintained delivery of a comprehensive communication strategy, ensuring strong WB comms coverage and support from senior WB officials. The quality of these reports, launched by senior WB and IFC managers, with high-profile media coverage and clear guidance on interventions to utilise, guarantees the attention of senior policy makers, academics and practitioners, globally. This is demonstrated by the high level of attendance, social media uptake and number of downloads.
- The attribution of programme impacts should consider the share of FCDO funding which has fallen from 60% to 19.7% during the programme’s lifetime.

Equity
- The programme is explicitly pursuing equity outputs and outcomes and therefore performs especially well in VfM in equity terms, especially on Gender equity.
- The programme has a large number of staff and consultant colleagues from low and middle income countries (especially Sub-Saharan Africa) and the team is majority female, along with two-thirds of the senior leadership team and two-thirds of the broader leadership team.
- The programme makes a concerted effort to partner with more local researchers across all of its research work, including through its regional adolescent girls work and through country labs. The team has a deep network of relationships with partner researchers based in (and nationals of countries in) Sub-Saharan Africa as well as East Asia and Pacific, and South Asia.
- Africa GIL’s decentralised Country Labs models in Nigeria and Ethiopia, and a lighter version of this in Cote d’Ivoire, are particularly well-suited to supporting local research capacity and ensures the work accounts for context specific factors.

Assessment of whether the programme continues to represent value for money

Based on the above assessment and the in-depth influence exercise discussed in section B of this review, the programme continues to represent good value for money. However, the programme should seek to strengthen it’s measures of cost-effectiveness.

E: RISK

Overview of risk management

During the reporting period the risks to the programme were within the risk appetite of FCDO. The overall risk rating for this project remains minor. A summary of the key risks and mitigation strategies are as follows:

- Strategy and Context: The programme looks to manage the risks associated with political contexts, including conflict, policy shifts, and election cycles in differing countries, by diversifying its portfolio across 25 countries. The Task Team Leaders manage and monitor the progress of specific activities and if they find progress to be unsatisfactory or emerging risks become above tolerances they ensure course corrections are made.
- Programme Delivery: The programme team collaborates closely with WB country offices to detect possible risks and pro-actively seek solutions that do not hamper project implementation.
- People: There is a risk of delays in decision making when working across several teams within the World Bank. This is mitigated somewhat as there are experienced management teams are in place at both FCDO and the World Bank and the programme is managed within the standards agreed between the two partners centrally.
- Fiduciary: There are no concerns over financial management within the programme as they follow standard World Bank processes.
- Reputational: The main risk during the period was linked to reputation of the programme if the research was not picked up by policy makers. However, as this annual review demonstrates, this risk has not come to fruition.
- Safeguarding: The project looks closely to mitigate the risks associated with social exclusion and the rigorous World Bank’s standard safeguards policies within the Environmental and Social Framework have been applied fully to mitigate this risk. The World Bank acknowledges the risk of sexual exploitation, abuse, and harassment by staff and enumerators, particularly given the power imbalances that exist within research and academia. The World Bank team have an internal Code of Conduct and zero tolerance for any act of social and sexual exploitation. A mechanism to report and pursue allegation exists.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The project is run by the World Bank and operates against World Bank standard procedures for financial management and reporting. These processes have been agreed centrally between FCDO and the World Bank and are therefore deemed to be a good use of resources.

AGIL, EAPGIL, LSMS, SARGIL and WBL all receive funding from a dedicated trust fund administered by the Umbrella Facility for Gender Equality (UFGE). All financial management and auditing requirements and processes are managed through the UFGE as agreed in the Administrative Agreement. This system provides only high-level financial data to FCDO via the Donor portal and the UFGE’s annual financial report. This is supplemented by detailed financial and narrative information on the use of resources supplied by AGIL on demand and when the bi-annual payments are made. FCDO funds are soft-earmarked to specific items to facilitate monitoring progress and disbursements. It is worth noting that in the spirit of a harmonised donor reporting system, the logical framework of the programme reflects progress of the entire programme and not only to FCDO soft-earmarked activities.

The breakdown of total budget has reduced from last year’s figure of 22% to 19.7%.

Donor	Cumulative Amounts for 24/25 (in USD)
FCDO	31,750,589
World Bank	29,215,928
Canada	29,931,683
Gates	31,776,740
Germany	3,240,000
Other WB Trust Funds	35,143,200
Total	161,058,140
FCDO % of total	19.7%

FCDO’s percentage of funding to SARGIL was 36% and EAPGIL 18% and this remains in line with the business case.

The AGIL programme falls under the single audit process for the World Bank and the most recent audit was dated September 2024. The audit of the internal controls over financial reporting is noted as being effective.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

There is a strong working relationship between the FCDO team and all programme partners. In addition to the AGIL bi-annual steering committee meetings there are regular bilateral meetings between FCDO and AGIL. The steering committee meetings look to provide scrutiny on deliverables and guidance for the future direction of the programme. These meetings include donor funder and academics and provide feedback on new calls. There are regular bilateral meetings with EAPGIL, LSMS, SARGIL and WBL. In the next reporting period the programme should look to finalise streamlined meeting protocols.

In addition to the above, FCDO also regularly meets with the Umbrella Fund for Gender Equality and is active member of the UFGE Partnership Council Meetings.

Evidence and Learning

The programme’s aim is to share evidence and influence policy. The detailed output reporting and annexes of publications and engagements speaks to the volume of work delivered in this regard.

Date of last narrative financial report	August 2025	Date of last audited annual statement	September 2024