Programme Completion Review

Title: The Global Road Safety Facility
Final Programme Spend £ (full life): £8.9m	Review Date:	31/03/25
Programme Code: 203212	Start Date: 29/01/2013	End Date: 31/12/24

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025 - PCR
Programme Score	A	A	B	A	A+	A+	A+	A	A	A	B	A
Residual Risk Exposure Rating	Med	Med	Med	Med	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Minor

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/3719422.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0007585.xlsx

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved

Road traffic accidents cause about 1.2 million deaths and 50 million injuries around the world annually, with 93% occurring in developing countries. They are the leading cause of death globally of those aged 5-29 years and a major cause of disability. Road crashes rank as the eighth leading cause of death globally, causing huge burdens for economies, health systems and transport networks. The majority of these deaths and injuries are preventable through improved infrastructure design and behavioural changes.

The World Bank-housed Global Road Safety Facility (GRSF) aims to reduce the number of road deaths and serious accidents in low- and middle-income countries by providing funding, knowledge, and technical assistance to scale-up countries’ efforts to build their scientific, technological and delivery capacities for road safety. It operates as a hybrid research and grant-making programme supporting global, regional, and country-level research and advisory activities. It is a multi-donor fund hosted by the World Bank (WB), which the Foreign Commonwealth and Development Office (FCDO) and the Department for Health and Social Care (DHSC) have supported as the UK Government’s main contribution to road safety internationally. The ultimate aim of FCDO (and previously DFID) support to GRSF is to reduce road deaths and injuries in low and middle income countries, through an improved evidence base on road safety and greater adoption of best practices in road project design and preparation, and in road management.

The UK has been the largest bilateral donor to GRSF, with UK funding representing approximately 35% of GRSF’s total contributions ($84.93m USD) since 2006. UK support to GRSF began in 2013, through financial contribution from GRD – a DFID policy team. In November 2014 programme responsibility transferred to DFID’s Research and Evidence Division, with UK contributions more specifically targeting research challenges and the generation of evidence and data on road safety. Under this business case £8.9m has been disbursed, supplemented through separate programmes by an additional £4.5m from DFID Nepal (2014-2018) and a total of £7.5m disbursed from DHSC (with a further £3m committed). The level of support was reflected when the UK was asked to chair the GRSF board for two consecutive terms between 2015 and 2018.

FCDO (and previously the Department for International Development, or DFID) has contributed £8.9m to GRSF split between two multi-donor trust funds (MDTFs) in the following way:

	Start/End Date	FCDO Funding Disbursed	Co-funders
MDTF-2	2011-2018	£4.5m	DFAT (Australia), FIA Foundation
MDTF-3	2019-2024	£4.4m	DHSC (UK)

Other donors have contributed to GRSF during these periods, but rather than contributing to an MDTF have elected to contribute via single-donor trust funds. FCDO made its final tranche payments to GRSF in UK Financial Year 2020/1, supporting research activities up to June 2024. The FCDO and DHSC have continued to engage with GRSF to help maximise impact and uptake of GRSF activities, and have continued to conduct ‘light touch’ annual reviews of facility performance since 2021. Following the completion of MDTF-3, the World Bank is establishing an ‘Umbrella’ trust-fund, which will consolidate MDTFs and single-donor trust funds, thus streamlining management requirements. DHSC has committed £6m to this Umbrella trust-fund, half of which had been disbursed by January 2025.

GRSF’s impact was recognised by receiving the prestigious Prince Michael of Kent Award for ‘Road Safety Impact over the past decade’ in December 2024. It is estimated that more than 36,500 lives have or will be saved through road safety interventions informed and catalysed by FCDO-supported GRSF activities, over a period of 20 years after the implementation of measures recommended by the facility. A collection of 110 published articles and technical reports have been produced and have been cited 417 times to date, as well as contributions to Global Burden of Disease publications, which collectively have been cited an additional 16,201 times.
[note] Close to 3500 lives saved through work in MDTF2, and 33,151 through MDTF3. Calculated through the World Bank’s economic appraisal of project proposals. The appraisal process uses the World Bank’s internal Road Safety Screening and Appraisal Tool – RSSAT – to calculate the lives saved over a twenty year period following project implementation, compared to a do-nothing scenario.

UK Aid-funded GRSF research has leveraged or informed an additional $20.3bn USD MDB and partner government funding through World Bank activities, and recipient governments have invested $3.3bn as co-funding for these projects. The capacity of 88 Governments has been strengthened to undertake and implement research on road safety strategies through MDTF-3 activities, building on previous capacity building support under MDTF-2 which was provided to43 government teams. In total 39 training events and joint meetings of MDBs, on road safety, have been conducted.

GRSF has funded the delivery of quantitative, qualitative and applied research on road safety themes such as; road safety management, road infrastructure, speed management, vehicle safety, road user behaviour and post-crash response. Examples of GRSF supported research projects, and knowledge advances include:

- An analytical study using big data and machine learning to automate road safety predictions, addressing limited data availability. An integrated framework analyzes street-level imagery to predict risks for road segments using an open-source tool on GitHub that automatically identifies 106 road characteristics, based on the Mapillary Vistas dataset, reducing the need for manual annotation. Case studies in Bogotá, Colombia, and Padang, Indonesia, showed promising results, with the framework achieving 72.5% accuracy in Bogotá. Further data is needed to confirm its performance in Padang. The methodology has potential for replication in other cities and is detailed in a guidance note, "Detecting Urban Clues for Road Safety: Leveraging Big Data and Machine Learning".
- Upgrade of the Highway Development and Management Model 4 software application for road administrators. The HDM model will include a new road safety module to capture road crashes and their potential impacts in the economic analysis of road construction, rehabilitation, and maintenance works.
- A research study and analysis of the discrepancies and under-reporting in global reporting of road crash data from official statistics and modelled estimates.  Global models—such as the Global Burden of Disease (GBD), WHO Global Status Reports on Road Safety (GSRRS), and WHO Global Health Estimates (GHE)—often report higher traffic fatalities than official LMIC statistics. A GRSF study found that while national decision-makers acknowledge under-reporting, they often reject higher global estimates, mostly relying on GSRRS data. The study suggested minor modifications to national health surveys to enhance road safety data and recommended incorporating these into global models to align estimates.
- A research project which to analysed the cost of injuries through a study involving over 2,300 hospitalized road crash patients across six countries—Bangladesh, Cambodia, Ethiopia, Malawi, Ukraine, and Zambia—to highlight the significant but often overlooked disability burden caused by road crashes, which claim over a million lives annually. Historically, road safety research has focused on fatalities, neglecting the prevalence and long-term impacts of traffic-related injuries. The study aims to broaden the discussion to include disabilities, advocating for comprehensive interventions in both the transport and health sectors, such as improved safety regulations, emergency services, rehabilitative care, and social safety nets for crash survivors.

GRSF has played a significant role in influencing World Bank funding on road infrastructure, steadily increasing the share of total road infrastructure financing utilised specifically for road safety from an average of 1.3% between 2006 and 2011, to 8.5% during the years of implementation of MDTF-3. GRSF internal lobbying of the World Bank has contributed to greater consideration of road safety at project preparation stage, and has led to road safety impact assessments now being mandated in World Bank road infrastructure project preparation procedures – indirectly but tangibly impacting billions of dollars of road infrastructure finance each year. Other examples of GRSF knowledge and evidence influencing road infrastructure spending include:
- The $358m Bangladesh Road Safety project, which was approved in mid 2023, and is the World Bank’s first standalone multi-sectoral road safety project in south Asia. Building on GRSF evidence and tools, the project will reduce road fatalities through in strategic high-risk portions of the national highway network and build institutional capacity for managing road safety.
- In Tanzania the Ten Step Plan project, which was co-funded by GRSF in 2023, trained 569 participants (including nearly 100 women), boosting Tanzania’s International Road Assessment Programme (iRAP) certification rank significantly. Improved road designs identified through the project are expected to reduce road crashes by 65%. The projects outcomes are anticipated to benefit $1.3bn of transport projects across Tanzania.
- In Ghana GRSF has engaged with the national government to enhance road safety outcomes and capacity. Approximately 750 km of roads have been assessed for the Ghana Highway Authority (GHA) and Department of Feeder Roads, with inspections around 50 school zones. Recommendations focused on protecting vulnerable road users, managing speeds, and improving school zone safety, guiding $187 million in investments through the World Bank-financed Transport Sector Improvement Project.

In Ghana GRSF has engaged with the national government to enhance road safety outcomes and capacity. Approximately 750 km of roads have been assessed for the Ghana Highway Authority (GHA) and Department of Feeder Roads, with inspections around 50 school zones. Recommendations focused on protecting vulnerable road users, managing speeds, and improving school zone safety, guiding $187 million in investments through the World Bank-financed Transport Sector Improvement Project.
Two road safety observatories, in Africa and in the Asia-Pacific region, have been founded with critical support from GRSF, enabled by funding under this business case. The African Road Safety Observatory (ARSO) was founded in 2018, and shortly afterwards the Asia Pacific Road Safety Observatory (APRSO) was founded in 2020. FCDO pushed for the APRSO to be located in the Asia Development Bank (ADB) which has proved positive for both impact, sustainability and co-funding (ADB recently secured funding from Japan for USD500 000). These fora gather together regional partners to improve road safety data and evidence, and build capacity for monitoring and analysis in their respective geographies.

The majority of end of programme targets have been met, with only one exception – where it was hoped that three additional donors would commit funding support to GRSF, and as of January 2025 two additional donors have contributed to GRSF directly. Each scored logframe output has scored an A – met expectations, and therefore the programme for the final review period scores an A.
[note] Additional funding has been received by the Asia-Pacific Road Safety Observatory (APRSO, $500k from the Government of Japan), a GRSF supported initiative, but this has not been counted as achievement against the logframe indicators.

Major lessons learned, evidence generated and recommendations

Lessons learned:

Significant impact can be achieved through integrating research and advisory activities into MDB-financed project preparation and operations. The ultimate programme logic of this contribution to GRSF has been to influence the road infrastructure spend and investment of MDBs, partner governments and international organisations through improved knowledge and evidence. This has been successfully achieved through GRSF – a key lesson is to strategically target influencing mandatory project preparation requirements for organisations with a large volume of transport infrastructure investment, to maximise impact and achieve ongoing benefit. In particular, the MDB’s with the highest levels of road transport infrastructure investment should be engaged with in order to have the most catalytic impact, achieving the greatest value for money and impact.

Active engagement with in-country transport stakeholders is crucial for turning knowledge, data and evidence into impact. It is essential to have in-country presence and engagement to support often small road safety teams to best inform road infrastructure investment and policy decisions. Throughout GRSF the team has benefited from contact and support from World Bank in-country staff, enabling closer contact with national stakeholders. Similarly where FCDO-posts have had an interest (e.g. DFID-Nepal), rapid uptake and change has been possible through GRSF.

Regional Road Safety platforms, such as the road safety observatories, can encourage peer-to-peer exchanges and learning – but require sustained funding and support to continue long term activities. The RSO’s serve an important role in improving road safety monitoring, reporting and data accuracy, as well as facilitating regional dialogues on the same. The observatories however need long term funding commitment and a sustainable secretariat function to continue, and achieve long term impact.

Flexible but consistent monitoring frameworks are required to demonstrate continuity of theories of change for long running programmes. The FCDO results framework, adopted by GRSF for monitoring of MDTF3, was somewhat fragmented following multiple significant revisions, and did not adequately reflect the causal chain of progress from GRSF activities to intended outputs. Whilst it has remained possible to articulate GRSF’s achievements and impact, these have not necessarily been captured to the most useful extent through the logframe, making it difficult to capture the breadth of activities and impacts across the lifetime of the programme.

Pilot road safety projects, targeting high-risk road locations, are a cost-effective means of reducing road deaths and injuries whilst demonstrating the benefits of relatively small interventions. The Nepal Road Safety project (funded by DFID Nepal between 2014 and 2018) installed 7.3km of crash barriers along a stretch of high-risk mountainous roads. The solution started saving lives immediately, and measurably. Successful road safety initiatives can have a powerful demonstrator effect.

How this report was conducted

This report has been produced with evidence drawn from previous FCDO authored annual reviews and documentation, along with regular GRSF narrative reporting on achievement against annual targets, GRSF Annual Reports, and MDTF-2 and MDTF-3 final reports which highlight expected achievement against agreed outcomes and impacts, alongside reflections on lessons and recommendations. The draft report has been reviewed by the GRSF team for accuracy.

Actions following approval of this report

There are no outstanding actions for this programme following programme completion. FCDO transport advisers will continue to engage with the road safety agenda, including but not limited to support in official UK Government engagements on the agenda, and the provision of technical advice to DHSC counterparts for the remainder of their contributions to GRSF. FCDO will continue to participate in GRSF’s partnerships council, with the assent of GRSF and other members, and will continue to advocate for improved road safety knowledge and evidence for the reduction of road fatalities and injuries. Future FCDO transport research programming should include explicit elements of road safety support, and should aim to build on the evidence and activities of GRSF. Outstanding research challenges on road safety include; the need to better understandsocio-economic barriers and blockages to implementation of road safety measures, the utilisation of the power of ‘big data’ and technological innovations for road safety analysis and decision support, the resolution of the inconsistencies between estimates of road safety deaths and measured fatality rates, and continued research in road safety issues as vehicles and the built environment change. Further work is also needed to support the uptake and implementation of existing road safety knowledge and evidence. Such engagement should in particular look to support the institutionalisation of road safety assessments in project preparation undertaken by FCDO programmes and with MDB partners.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£1.5m	£8.9m
Timeframe	29/01/13 – 31/03/18	29/01/13 – 31/12/24
Impact	Reduction in road deaths and injuries in low and middle income countries Original Indicator: Lives saved (per year) on road sections of the 10,000km total covered under this programme Original Target: 1000 lives saved per year, by original programme end	Reduction in road deaths and injuries in low and middle income countries / Final Target: 29,468 lives saved on road sections in target countries (cumulative) over a period of 20 years after implementation of projects. / Final Achievement: Over 36,500 lives saved over a period of 20 years following implementation of projects influenced and informed by GRSF research, enabled through UKAID grants. Equates to an average of more than 1825 lives saved per year.
Outcome 1 - Evidence	Ambition: Improved evidence based road safety management in LIC and LMICs, and improved attention to MDB and donor transport projects	Improved evidence-based road safety in LIC and LMICS and improved attention to road safety within MDB and donor transport projects: / Final Target: 354 citations of GRSF publications in academic literature (cumulative) / Final Achievement: 417 Citations of GRSF produced evidence in academic literature, or 16,618 if including Global Burden of Disease Publications which GRSF staff contributed to.
Outcome 2 - Influencing	Ambition: £1.5 million of support from DFID will influence and inform road safety content within $750 million of MDB road sector programmes. (target ratio of £1:$500)	Final Indicator: $17.465 bn (USD) of MDB and $3.614 bn (USD) of Government funds for road improvement programmes which have been leveraged/improved/directly informed by UK Aid funded GRSF research and evidence / Final Achievement: $20.734 bn (USD) of MDB and $3.361 bn (USD) of Government funds for road improvement programmes which have been leveraged/improved/directly informed by UK Aid funded GRSF research and evidence / £8.9 million of DFID and FCDO funding has influenced, leveraged and informed road safety content for $24.095 billion (achieved ratio of £1:$2707.3)
[note] Including ‘close to 3,500 lives saved over next 20 years’ attributed to activities under MDTF-2 and 33,151 attributed to activities under MDTF-3

Overall assessment of programme outcomes, sustainability and VfM

GRSF has performed well, and has achieved intended impacts stated in the original business case as well as those stated in addendums. The final impact target was substantially exceeded. The reported achievement likely understates the impact of the programme due to conservative measurement – the figures reported are conservative estimates of avoided fatalities on road projects directly engaged with by GRSF in the course of activities under MDTF-2 and MDTF-3. The diffuse impact through GRSF’s contribution to the body of knowledge, and championing of road safety indirectly contributes to a significant additional number of avoided road fatalities, although these cannot be readily quantified.
Two outcome areas were highlighted in the initial business case, and both remain relevant at programme close, although thanks to budget uplift and high performance, targets were updated during the course of the programme to reflect greater ambition. The first outcome raises GRSF’s ambition to improve and add to the evidence base on road safety. The final target for this has been exceeded – significantly so, if including publications that GRSF staff have collaborated on such as the World Health Organization (WHO)’s Global Burden of Disease publications.

The second outcome targets influencing MDB and partner government spending on road infrastructure, using comparatively small volumes of research funding to GRSF to influence much greater sums of infrastructure finance and improve road safety outcomes, by ensuring that infrastructure project design adequately considers and responds to road safety issues. The initial business case, with a budget of £1.5m, intended to influence $750m (USD) of multilateral development bank finance; an intended ratio of £1 to $500. In actuality, with £8.9m of FCDO funding, $24,095m was influenced ($20,734m of MDB and $3,361m of Government funds), resulting in a final ratio of £1 to $2707.3, more than five times the initial ambition. The final target for influencing partner government spending was narrowly not met, but this does not necessarily reflect an underachievement, rather a slightly different distribution of impact than that which was initially envisaged, with influence more effectively applied within the World Bank and with multilateral partners rather than country governments. GRSF’s ability to influence partner government finance was slightly lower than expected, given that IDA dominated the World Bank’s spending on roads and urban mobility in recent years, and IDA projects receive relatively less government co-financing as compared to IBRD projects.
[note] International Development Association
[note] International Bank for Reconstruction and Development

GRSF’s work will continue to influence World Bank (and other partner) spend on road infrastructure given that, thanks to GRSF’s efforts, road safety considerations and impact assessments are now mandated in World Bank road infrastructure project preparation procedures– indirectly but tangibly impacting millions of dollars of road infrastructure finance each year. These impacts can expect to be sustained over time given the integration of road safety in standard processes, although continued efforts will be needed to ensure that best-practice, evidence and data on road safety remains contemporary and relevant to changing mobility contexts.

Given the impacts and outcomes achieved, with a relatively small sum of funding, FCDO contributions to GRSF under this programme should be considered as good value for money, and a cost-effective means of addressing road traffic fatalities and injuries at scale. Through the estimated avoided injuries and fatalities, UK funded activities will contribute to the mitigation of billions of dollars of losses from national economies in partner countries due to road traffic accidents in the next twenty years.
[note] For example, with an estimated 36,500 fatalities avoided, and an estimated statistical value per avoided fatality of approximately $200k, ~$7.3bn of losses to economies would be avoided as a result of UK support of GRSF through fewer road fatalities. This estimate does not include avoided costs of injuries which per Ryan-Coker et al (2021) indicate can, depending on the severity of the injury and duration of its impacts, range between $119 and $178,634 per injury.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The initial theory of change, presented in the 2012 business case, is shown in Figure 1. This theory of change was not updated in subsequent business case addendums, and has remained broadly valid throughout the programme. Following the transfer of management and funding responsibility from the Growth and Resilience Department (GRD) to the Growth Research Team (GRT), the focus on support to GRSF shifted towards improved knowledge, data, evidence and expertise in road safety – all in service of achieving the same outcomes and impacts as originally described.

Figure 1: Original Theory of Change

The business case for FCDO contribution to GRSF changed a number of times since initial approval in September 2012. A timeline of these changes is presented below. The original business case was for a two year programme of activities, and a contribution of £1.5m, this ultimately grew to an £8.9m contribution over 12 years. Figure 1 summarises the changes to the programme between 2012 and 2025.

Figure 2: Programme Summary Timeline

The multiple amendments to the original business case, coupled with the long duration of the programme and changing intervention context has meant that the results monitoring framework (also referred to as the Logframe) has changed multiple times in order to remain relevant and to best monitor and incentivise progress. The most significant changes occured at the initial business case addendum in 2015, and then again with the addendum in 2018. The last business case addendum was approved in August 2023, extending the programme’s end date to December 2024 – enabling the completion of MDTF3 activities by June 2024.

Reductions to budgets during the COVID-19 pandemic (total budget reduced by £0.9m, from £9.8m to £8.9m) meant that some activities were scaled back, and following the last tranche payment in 2021 this lead to a number of logframe output indicators to be discontinued to ensure relevance. The following section covers achievement against the final agreed logframe targets (last updated for annual review carried out in May 2024). Discontinued indicators for the final version of the logframe are included for discussion.

## C: Detailed Output Assessment

Output Number and Title	Output 1 – Increased quantity, quality and relevance of road safety evidence available to improve policy design and implementation
Output Score	A – Output met expectations
Impact weighting (%)	54%		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
1.1 a) Research grants programme - number of road safety research projects across key sub-sectors; (safe systems approach - 6 pillars, including Road safety management; Road Infrastructure; Speed management; Safe vehicles; Road user behaviour; Post-crash response following robust expert review) / 1.1 b). Number overall projects, % under each of the themes (cumulative)		a) 34 / b) no target set / NB – indicator discontinued after 2021	1.1 a) 42 - Target exceeded (last reported June 2021) / 1.1 b) Cumulative figures for all 42 grants as of 2022 Annual Review / Road Safety management – 14 (33%) / Road Infrastructure – 8 (19%) / Speed Management – 10 (24%) / Safe Vehicles – 1 (2%) / Road User Behaviour – 4 (10%) / Post-crash Response – 5 (12%)
1.2 Number of papers published in relevant peer-review journals (cumulative)		26 (cumulative)	30, with an additional 2 papers accepted for publication – Target exceeded
1.3 High quality project grants approved following robust external review / a) Number (cumulative) / b) percentage subjective to robust external review (cumulative)		a) 31 / b) 100% / NB – indicator discontinued after 2021	32 / 100% / Target met. / Achievement last reported June 2021
1.4 Number of other publications for more applied impact (cumulative)		57 (cumulative)	61 - Target exceeded
1.5 Number of transport projects in which road safety delivery is improved by UK Aid funded research (cumulative)		16 (cumulative) / NB – indicator discontinued after 2021	13 (cumulative) – target not achieved. / Achievement last reported June 2021
1.6 a) Number of projects influencing policies at a national level (cumulative) / b) Number of projects supported which potentially affect national policy (cumulative)		a) 28 (cumulative) / b) 25 (cumulative) / NB – indicator discontinued after 2021	40 / 26 / Targets exceeded. / Achievement last reported June 2021
1.7 Amount of additional research funding leveraged by research teams as a result of GRSF research grant funding (cumulative)		$4.5m (cumulative) / NB – indicator discontinued after 2021	$1.768m – target not met / Achievement last reported June 2021.
1.8 P10 - (Supporting the MDB Road Safety Work Programme) annual spend on projects through MDB safety programme (cumulative)		$1,145k (cumulative) / NB – indicator discontinued after 2021	$975k – target not met / Achievement last reported June 2021
1.9 P4: Road safety calculator / a) Number of literature reviews on existing interventions undertaken (cumulative) / b) Number of new interventions added (cumulative) / c) no. calculator case studies (cumulative)		a) 19 / b) 20 / c) 3	a) 19 / b) 20 / c)3 / Target met

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output monitors GRSF’s achievement in producing and disseminating high quality knowledge products on road safety. All active targets have been met or exceeded, resulting in the final output area score being an A – output met expectations. A number of indicators under this output area were discontinued after 2021, meaning that targets were not updated and progress was not monitored. These indicators are presented for completeness. Final targets for these indicators are the targets that were expected to be achieved in the final year of measurement (i.e. 2021). In the case of indicators 1.1, 1.5 and 1.8, targets were not met primarily due to budget reductions that would have otherwise facilitated further progress. Indicator 1.7, which monitored ambition to leverage additional research funding through co-funding or otherwise, was discontinued due to the direction of GRSF not involving a focus on influencing further research spend, rather providing grant funding for road safety research, and informing infrastructure spend and finance through changes to process and practice. The target for approximately 50-50 co-funding was difficult to achieve given scarce resources for road safety research available with partner countries and organisations, in retrospect the initial target was overly ambitious and did not adequately account for resource scarcity, for road safety projects, with partners. All current programme end targets have been met or exceeded.

Under activities supported through GRSF’s MTDF-2 (33 published articles) and MDTF-3 (70 reports, systemic reviews, technical reports, manuals and journal articles) GRSF has contributed significantly to the body of knowledge on road safety, including through peer-reviewed publications. A list of all publications for MDTF-3 is available in Annex A. Other publications, including those produced under MDTF-2, are available on the GRSF website.
[note] https://www.globalroadsafetyfacility.org/publications

All outputs are monitored through logframe narrative reports provided by GRSF, supplemented by evidence where relevant (e.g. through hyperlinked lists of publications and research outputs).

Lessons learned through this output, and recommendations for future

This output tracks GRSF’s contribution to the body of knowledge on road safety, through research outputs produced by directly commissioned research as well as research proposed by partner institutions and researchers. In future programming it would be helpful to measure through similar indicators the extent to which these knowledge products are demand-led or responsive, as well as efforts to ensure the knowledge is assimilated by the stakeholders that will be able to best influence change. GRSF has produced high quality research on a range of road safety issues, and the profile of the organisation to some extent has assured uptake of research outputs, but to more explicitly link knowledge products to intended outcomes intermediary indicators would be beneficial – such as the discontinued indicator 1.6. It would also be helpful to understand in logframes for future programmes who the research output authors are, to be able to track the contribution of female researchers and researchers from partner countries, and to incentivise the participation of those most effected by the research agenda.

Output Number and Title	Output 2 – Effective Expansion of GRSF Grants program during funding period
Output Score	N/A
Impact weighting (%)	0% - Output discontinued following 2021 review		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
2.1 Applications: / a) Internal (non-cumulative) / b) External (non-cumulative)		a) 18 / b) 8	a) 7 (total 72) / b) 16 (total 51)
2.2 a) Average grant size: % increase from 2017 baseline (cumulative) / b) number of outside organisations being supported directly or indirectly (cumulative)		a) 50% / b) 27	a) 59% / b) 22
2.3 Change in grants / a) % at or below $150,000 (cumulative) / b) Number over $300k (cumulative)		a) 20% decrease from 11/16 (68.75%) grants at or below $150k / b) increase by 2	a) 71.4% grants at or below $150k as of June 2021 / b) increased by 3 (cumulative)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 2 sought to monitor GRSF’s progress on issuing grant funding for road safety research projects. The output was discontinued following the 2021 annual review due to FCDO budget reductions impacting available funds for annual calls for proposals, and so these indicators do not contribute to this review’s scores – they have been taken into account in previous annual reviews. The ambition of this output area was to expand GRSF’s grant funding to internal (i.e. World Bank) and external research project proposals, through the availability of FCDO funding. The indicators monitor efforts to increase value for money and impact through fewer, larger, and more strategic grant-funded research projects.

Between 2018, when the indicator was first measured, and 2021 GRSF’s call for proposals received 72 internal applications and 51 external applications. The average grant size increased from the 2017 baseline ($82,500 USD) by 59%, and supported (directly or indirectly) 22 external organisations. As of June 2021 a greater proportion of grants were issued (by number, not by volume) to projects at or below $150k, but the number of projects over $300k had increased.

Taken as a whole, reasonable progress was made against this output, despite some targets not being achieved. The non-achievement of targets can primarily be attributed to the programme budget reduction of £0.9m, which for the final round of calls for proposals in 2020-2021 meant that smaller proposals were generally preferred by GRSF (following discussion and agreement with FCDO) to ensure continued thematic coverage. If budgets had been maintained it is likely that targets would have been met. Following 2021, given unavailability of funds, the annual calls were cancelled and therefore the output was discontinued. These targets were initially added to incentivise more efficient management of research calls by GRSF (including through larger individual research projects), and to incentivise the commissioning of more externally conducted research.

Lessons learned through this output, and recommendations for future programming

This output tracked GRSF’s progress in issuing research grants on road safety, and the ability to cultivate a portfolio of larger, more strategic research grants with greater participation of external research teams. A key lesson has been that there are potential trade-offs between issuing larger research grants and crowding in research teams – it has been noted (through the volume of of internal and external applicants for calls for proposals) that larger grant sizes may have exceeded the needs or capacities of external research teams. For future programming it may be beneficial to reflect a balance of large/strategic grants, with smaller, responsive grants that may be more accessible to external researchers. Similar to comments made under output 1, it may be useful for future programmes to track who are successfully being awarded grants – and the extent to which programmes are able to balance the benefit between supporting new grant recipients versus supporting the continuation of proven research teams.

Output Number and Title	Output 3 – Improved accuracy in country-level data on rates of road-deaths and injuries
Output Score	A – Output met expectations
Impact weighting (%)	24%		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
3.1 P9: No. country case studies analysing official and actual rates (cumulative)		4	4
3.2 Revised modelling and prediction guidance published		Recommendations for improved modelling and prediction guidance published	Recommendations published / Target Achieved
3.3 P11: Draft regulatory framework for Road Safety Observatory in Africa		Completed	Completed in 2020
3.4 Number of country members in Regional Road Safety Observatory (RSO)		a) target number for Africa RSO: 40 (NB target met in FY21, indicator discontinued) / b) Asia-Pacific RSO target: 25 country members	a) 40 (achieved in FY2021) / b) 27 / Target Achieved
3.5 P11: Observatory Launch (Africa RSO)		Complete	Completed in 2020
3.6 Cumulative number countries / states / cities conducting Country Road Safety Data Reviews (using DRIVER or other open-source software)		7	8 – Target Achieved
3.7 Disability and road safety report published		Report complete	Report complete – Target Achieved
3.8 Report on feasibility and opportunities of Big Data complete		Report complete	Report complete – Target Achieved

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 3 monitors GRSF’s progress towards supporting partner countries to collect and maintain accurate data on road deaths and injuries, through data analysis support, capacity building and the convening of new international platforms. The output area has met all end of programme targets scoring an A, and a number of indicators were discontinued due to early achievement.

Indicator 3.1 measured the number of cases analysed as part of a GRSF study on discrepancies between reported and actual road fatalities and injuries. Estimates of road traffic deaths and injuries from global statistical models substantially exceed the official statistics reported by most low- and middle income countries, resulting in an understatement of the scale of the problem, and a lower ability to leverage necessary resources to address the issue. The case studies provide an evidenced benchmark for the underestimation or underreporting of these figures by relevant authorities. Four case studies were planned, and four conducted under the discrepancy study by June 2021, following which the indicator was discontinued. The four case studies (Cambodia, Ethiopia, Tanzania and Brazil) were reflected in the publication of the report tracked in Indicator 3.2.

Indicators 3.3, 3.4 and 3.5 track GRSF’s contributions to the launching of two new international platforms for road safety data; the Africa Road Safety Observatory and the Asia-Pacific Road Safety Observatory. The Road Safety Observatories (RSOs), inspired by the European Road Safety Observatory, are regional networks of government and partner organisation representatives that share and exchange road safety data and monitoring experiences, to reduce traffic fatalities and injures in their respective regions, and aim to improve accuracy of data collection and reporting. The work by GRSF towards the establishment of the RSOs was recognised in 2020 when GRSF was awarded a Prince Michael Award for Road Safety, one of three awarded to GRSF that year.

The Africa RSO (ARSO) was founded in 2018 under the auspices of the African Union with support from GRSF, the SSATP, UNECA, FIA Foundation, the International Transport Forum and the African Development Bank. GRSF, under this business case, provided grant funding for the initiation and early stages of the ARSO, with the intention of transitioning to a sustainable funding model beyond GRSF grant funding.The ARSO has secured the membership of 40 countries across the continent and providing a major platform for regional collaboration on road safety data and monitoring practices. Activities under the ARSO have however slowed in recent years with the last general assembly being hosted online in March 2022 (having previously met in 2019 in Durban, South Africa), and with the ARSO dedicated website no longer being functional. The ARSO has ambitious plans to scale activities, that have unfortunately not been fully realised due to lack of sustainable resourcing – this does provide a potential opportunity for impact for future programming as the need and potential benefit for a regional road safety observatory in Africa remains. Providing that the operating model of ARSO better reflects the operating context, with a view to improving prospects of financial sustainability, then with a relatively modest financial contribution, in parallel with a multilateral effort to sustain activities long-term, the ARSO could be reinvigorated.
[note] The Sub-Saharan Africa Transport Policy Programme, a programme hosted by the World Bank.

The Asia-Pacific RSO (APRSO) was founded in 2020 with the Asian Development Bank (ADB) acting as the RSO’s secretariat, with support from the GRSF (encouraged and enabled through FCDO funding contributions), FIA Foundation, UNESCAP and the International Transport Forum. To date APRSO has 27 member countries and one observer country. The APRSO has been more successful in attracting funding beyond initial GRSF grants (notably from the Government of Japan’s Fund for Poverty Reduction, JFPR ($500,000)) and so has successfully maintained momentum, with a regular cadence of annual meetings, capacity building events and knowledge dissemination activities. The partnership with ADB can be credited for a large part of the continued success, and so any efforts to re-invigorate the African RSO may benefit from emulating relevant aspects of the arrangement – such as secretariat function delivery.

Indicator 3.6 tracks GRSF’s progress in encouraging road safety data reviews at the city/state/national level, including with the GRSF developed Data for Road Incident Visualisation Evaluation and Reporting (DRIVER) software. GRSF has lobbied World Bank teams and partner countries to include these reviews as part of road projects, and has ensured that eight such reviews have been completed to date, including in Chad, Cameroon, Malawi, Kenya and Sri-Lanka, Laos PDR, Haiti, Federated States of Micronesia and Mongolia – exceeding end of programme targets.
[note] DRIVER is available in Arabic, Bengali, Chinese, English, Lao, Portuguese, Spanish and Vietnamese, and the open source code is accessible on World Bank’s GitHub - https://github.com/WorldBank-Transport/DRIVER

Indicators 3.7 and 3.8 track GRSF’s progress in issuing key publications on disability in road safety and the implications of Big Data on road safety data and monitoring, respectively. Both reports have now been published, as intended by the end of the programme. The publication on disability in road safety was subject to significant delays given the need to collect primary data over 6+ months from healthcare facilities in partner countries – this was due to be conducted during the COVID-19 pandemic, and so health systems were understandably preoccupied. Regardless, data collection was able to resume and the report has been completed and published.

Lessons learned through this output, and recommendations for future programming

This output tracked GRSF’s contributions to more accurate road safety data and monitoring in partner countries. GRSF supported the formation of the Road Safety Observatorys, both of which quickly attracted attention and a large membership. Whilst the ARSO and APRSO have both established themselves as regional platforms, hosted by reputable regional organisations and supported by international partners, the Asia-Pacific RSO has more successfully sustained momentum in its activities enabled through further funding, whereas the Africa RSO has been less successful in this respect. A re-invigoration of the ARSO remains worthwhile, and would likely offer value for money when seeking to support improved road safety data and monitoring practices across Africa, but lessons from the APRSO should be taken into account to ensure long-term sustainability – particularly considering the responsibility and incentives for carrying out the secretariat functions, that serve as the foundation for such initiatives.

It is widely understood that official estimates of road traffic deaths, in many countries, substantially underestimate the scale of the problem. Improved data, monitoring and reporting processes are necessary for national stakeholders to reflect the true extent of the issue, and to adequately and proportionately provide and access resources for mitigation and response. GRSF has contributed to highlighting and quantifying this discrepancy across case studies (tracked in indicator 3.1), but it remains important for any future transport (research and implementation) to acknowledge and account for a likely underestimation of reported road traffic fatality figures in LICS and LMICS, and therefore potential underestimation in the quantification of secondary impacts (such as health impacts, and impacts on economic productivity).

Output Number and Title	Output 4 – Improved capacity of road safety researchers and decision makers to inform national road safety plans etc
Output Score	N/A
Impact weighting (%)	0% - Output discontinued in following 2021 review		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
4.1 Strengthen the capacity of the client governments to undertake research to develop and implement national road safety strategies and undertake research (number of countries) (cumulative)		42	105
4.2 Number of researchers, data managers and reseach users trained in workshops and or by GRSF supported teams of researchers (cumulative)		807	876 (38% of attendees at the training workshop in Jordan were female)
4.3 Proportion of people trained at workshops who come from or work in LIC countries / Number of participants a) bilateral b) MDB instituitions involved		a) 65% / b) 65%	a)100% / b) no data recorded
4.4 P17: Behavioural survey data published / a) no. countries / b) no. stakeholder organizations interviewed		a) 3 / b) 45	N/A

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score

This output area tracks GRSF’s efforts to build capacity in road safety researchers and decision makers, and their improved ability to inform and contribute to national road safety plans. Indicators 4.1 and 4.2 have been tracked for information only (i.e. with no set targets) since the 2022 annual review, while indicators 4.3 and 4.4 were discontinued given decreased relevance to GRSF’s activities.

Indicator 4.1 exceeded end of programme targets substantially, supporting the capacity development of stakeholders across 105 countries through UK funding to GRSF – more than double the agreed end of programme target. Similarly, indicator 4.2 tracks the number of researchers who have benefited from GRSF arranged workshops, and was also exceeded by programme end. In a four day training on Road Safety Management in 38% of attendees were female, systemic tracking of the gender of training/workshop participants was not conducted.

Indicator 4.3 tracks GRSF workshop attendance by LIC and LMIC participants – in 2021 this was discontinued, given that GRSF only conducts workshops in LIC and LMIC partner countries with the support of UK funding. Indicator 4.4 was discontinued due to GRSF not undertaking work (through GRSF managed research grants or otherwise) on behavioural studies.

Lessons learned through this output, and recommendations for future programming

Capacity development in partner countries and institutions is an important part of development programming, to ensure programming results in sustainable benefits and to ensure that partners have the agency and capacity to make best use of research outputs and improved knowledge, however in GRSF this did not explicitly link through the theory of change to tracked and intended outcomes. It is important to be able to demonstrate how these activities and achievements have or will explicitly contribute to programme objectives in order for these to remain relevant for the programme lifetime, through research uptake strategies, theories of change or otherwise.

GRSF was only requested to track the gender balance of workshop participation since 2022, it will be useful in future programming and monitoring efforts to track this balance for events as standard, and with an agreed and consistent approach across the programme. This should however be benchmarked against an agreed baseline, to ensure that workshop participation is made available to representative balances of attendees – not necessarily limited to gender balance. It may also be useful to disaggregate between scales of different events, and to track the perceived quality of events to better highlight achievement and level of engagement by participants.

Output Number and Title	Output 5 – GRSF global focal point for coordinating knowledge management, advice and research on road safety for LMICS
Output Score	A – Output met expectations
Impact weighting (%)	15%		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
5.1 GRSF functioning as a sustainable international organisation (IO) and scale up plans		N/A – Indicator Discontinued	GRSF sustainable functioning assured
5.2 Cumulative number of “green manuals” published or similar guidance manuals on bike safety, data & evidence to policy, communications for behavior and road design		7 (last issued Jun 2022)	12 manuals published
5.3 a) Cumulative number of key documents on road safety published / b) Cumulative number of hard copies taken and downloads		a) 72 / b) 27,998	a) 74 / b) 29,595 / Target achieved

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 5 monitors GRSF’s progress in establishing itself as a global focal point for road safety knowledge and expertise, and achievement in making this knowledge and expertise available to partners. Indicator 5.1 was discontinued early given GRSF’s sustainability was assured, through contributions of partners such as the UK’s DHSC, FIA Foundation, Australia’s DFAT etc. All extant targets have been achieved or exceeded at programme end and so output 5 scores an A.

Indicator 5.2 tracks the cumulative publication of “green manuals” – good practice manuals produced by the WHO, World Bank (contributions led by GRSF), FIA Foundation and the Global Road Safety Partnership (GRSP) which provide guidance on implementation of interventions to address specific risk factors in road safety. Some delays were experienced in the delivery of these manuals, some of which was outside of the control of GRSF given the collective authorship which, despite delayed publication, ensures a wider dissemination and profile. At programme end, the target for publication of these manuals was exceeded.

Indicator 5.3 measures the number of key road safety documents published by GRSF. This indicator overlaps somewhat with indicator 5.2 but includes other documents than the green manuals. The end of programme target has been slightly exceeded. As for the second part of the indicator, measuring cumulative number of downloads taken, this has exceeded the final cumulative target but has fallen short of the annual target of 4000 new downloads a year, however a more reasonable indicator might be to measure average downloads per publication, with targets benchmarked against a sample considered to be roughly equivalent in profile and level of interest. Regardless, GRSF has exceeded agreed end-of programme targets for this indicator.

Lessons learned through this output, and recommendations for future programming

This output area intends to track GRSF’s ability to serve as a centre of excellence for road safety research in LICs and LMICs, whereas agreed indicators do not necessarily reflect this. Indicators tracked here could be seen as more aligned with the research outputs tracked in output 1, whereas this output could have tracked more relevant indicators regarding GRSF’s profile and ability to influence and engage with partners in LICS, LMICS and international organisations.

GRSF has successfully positioned itself as a well reputed world leading road safety initiative, reflected for example in the five Prince Michael Road Safety Awards received by the programme since 2018 and in GRSF’s continued high profile at international road safety events, such as hosting a well attended ministerial panel at the 4th Global Ministerial Conference on Road Safety in Morocco (February 2025).
[note] Road Safety Awards: Award Winners

Output Number and Title	Output 6 – Effective road safety partnerships with MDB and Donors through training, joint meetings, and quality research on road safety issues
Output Score	A – Output met expectations
Impact weighting (%)	7%		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
6.1 Strengthen partnership and collaboration amongst Multilateral Development Banks (MDBs), International Organisationgs (Ios), and Donors. / Cumulative number of: / a) New GRSF Donors / b) New partnerships with IOs / c) Participation in global fora		a) 3 / b) 15 / c) 33	a) 2 – Target not met / b) 17 – Target exceeded / c) 43 – Target substantially exceeded
6.2 Improved capacity of MDBs to deliver on the road safety research and policy agenda. / Cumulative number of: / a) Training Events and joint meetings of MDBs / b) Funding support to MDBs to conduct research / c) Tools and guidance documents shared		a) 39 / b) $1,145k / c) 14	a) 43 / b)$1,150k / c) 19 / Targets exceeded

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output, similar to discontinued indicator 5.1, tracks the sustainability of GRSF through partnerships, and it’s ability to influence partners through provision of training, funding and tools. Five of the six end of programme targets were met or exceeded, with one (6.1a) moderately not met. As a result, on balance, the output scores an A.

The final logframe target of 3 new GRSF donors was not achieved, with 2 new donors (DHSC, whose contribution was facilitated and encouraged through FCDO support, and CITA, the International Motor Vehicle Inspection Committee attracted instead. Through GRSF’s efforts, Japan has also contributed financially to the Asia-Pacific Road Safety Observatory, albeit not to GRSF directly so not included within achievement for the indicator. In the summer of 2024, and in line with World Bank multi-donor trust fund rules, GRSF transititoned to an umbrella trust fund model, aggregating all single donor and multi-donor trust funds into one delivery framework. This has required a significant amount of administrative work, and will further improve value for money for GRSF, by aggregating programme management functions under one trust fund. With the launch of the new umbrella trust fund (which DHSC have committed £6m to), the close of MDTF-3 and the launch of the 2024-2027 GRSF Business Plan, and the continued profile of GRSF in international fora, efforts to crowd in more multilateral support continue with renewed priority and clearly articulated direction.

Indicator 6.2a primarily tracks GRSF’s convening of and participation in MDB working groups on road safety, which are scheduled quarterly. These meetings continue, and serve as a constructive means of coordinating and aligning multilateral engagement on road safety. The indicator, however, would more usefully separate out training efforts (which could be covered in another output) and MDB meetings, which have different goals. The end of programme target for funding support to MDBs to undertake research on road safety has been exceeded, as has the target for sharing tools and guidance documents with MDBs. Through these meetings, and through other multi-lateral engagements, GRSF continues to act as the leading global road safety organisation, particularly on research and thought-leadership.

Lessons learned through this output, and recommendations for future programming

A key lesson regarding the crowding in of donors is to be sensitive to the business planning cycles of initiatives such as GRSF, as well as to reflect the potential saturation of the ‘market’ for initiatives on a given topic – to consider the long term sustainability of a programme like GRSF it may be beneficial to consider the diversity of donors over a certain time horizon alongside GRSF’s ability to withstand potential funding shocks (e.g. COVID-19).

GRSF has, somewhat understandably, been significantly more successful in influencing spend and process within the World Bank – which has significant impact and will likely be sustained for many years with relatively little ongoing intervention, but VFM could be further maximised by strategically and intentionally targeting the largest financing instutitions in road transport. GRSF has had some success in this, including through engagements with other MDBs, and this success should be built on in future road safety initiatives, and emulated in other sectors.

Output Number and Title	Output 7 – GRSF working at pace to deliver road safety applied research and capacity building in mainly LICs
Output Score	N/A
Impact weighting (%)	0% - Output discontinued in following 2021 review		Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
7.1 % of UK Aid funds approved for LIC/IDA/blend eligible countries +DFID priority countries (including research relevant to these countries)		100%	100%

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output monitors the focus of GRSF on low income partner countries. The sole indicator was discontinued early, as GRSF have consistently applied this eligibility criteria to their activies, and indeed MDTF-3 eligibility criteria have mandated this contractually. The indicator was originally included to ensure that GRSF would not utilise UK funding in non UKAid priority countries such as middle or upper middle income countries.

Lessons learned through this output, and recommendations for future programming

This output did not monitor programme performance as such, rather it was used to monitor adherence to UK spending conventions and restrictions. The indicator was discontinued as this was satisfactorily assured by GRSF MDTF-3 eligibility criteria. Future programmes should ensure that this is sufficiently reflected and assured in any legal or administrative agreements at point of initiation, or through eligibility criteria that provide sufficient assurance.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The original business case anticipated value for money to be achieved through procurement for both Bank-executed and Recipient-executed contracts, and that GRSF would follow all World Bank procurement guidelines relating to the procurement of consultants and trust fund management, ensuring competitiveness and fiduciary care. This has been borne out throughout the programme.

The initial business case proposed a number of value for money metrics, which have been supplemented through the approval of costed and no-cost extensions.

The initially proposed economy metrics were: a cost of $75 USD per km of roads assessed, and facility implementation unit costs remain below 5% of total resources. The cost per km of road assessments is difficult now to assess, as GRSF funds a wide variety of projects, only some of which are road safety assessments explicitly – a running total of kilometres of road assessed and the funding required for these assessments would need to be kept to track this if considered necessary. Disaggregating spend to calculate funds used for road assessment projects retrospectively would be difficult, and would not necessarily provide accurate measures to compare with the initial economy metric.

As for facility implementation unit costs; Program Management and Administration costs for MDTF 2 totalled $1.583m of a total allocation of $21.252m (7.4%) and for MDTF 3 totalled $1.384m of a total allocation of $15.499m (8.9%). In later years, reflecting the management burden of managing a large number of simultaneous projects with strong secretariat and financial management performance, with a relatively small team, and with significant time inputs required from GRSF staff in administering grants processes, the amended and agreed target for facility implementation costs was 7-9%, which was consistently met. Despite exceeding initial targets, this should still be considered good VfM. The VfM of contributions to GRSF will likely increase through the implementation of the umbrella trust fund, which will reduce the management burden for the GRSF team by consolidating management and reporting processes for all donors into a single framework. Whilst FCDO contributions have not benefitted from this management arrangement (with the final disbursement from FCDO taking place in 2021, before umbrella trust fund establishment), DHSC contributions of £6m through this umbrella trust fund will likely benefit from lower management and administrative costs.

The World Bank assured that fees for Bank executed activities (applied to Bank staff salaries and benefits, or consultant fees) would not exceed a 17% cap and would more likely average less than 10% of overall fees. This too was borne out.

At time of original business case approval, the then DFID secretary of state approved on the basis that £0.5m of the initial £1.5m would be contingent on GRSF onboarding a new donor in 2013, thereby reducing DFID’s share of the funding burden – this was achieved, although due to later funding increases from DFID and DHSC (due to the judgement of contributions to GRSF representing good value for money) have increased this share of UK contribution from 25% at the point of the initial business case to 36% as of June 2024. DFID/FCDO share of the burden as of June 2024 was approximately 20%, and DHSC’s was approximately 16%.

Perhaps most saliently, the cost-effectiveness of the programme can be best highlighted through the influence of the programme’s activities on spend and investment by MDBs (including the World Bank) and government partners – the initial outcome set a target of influencing $500 of road infrastructure spend per £1 of investment into GRSF, as of programme end the achieved figure is more than five times this ratio, at approximately $2700 of investment influenced per £1 of investment into GRSF. This ratio will likely continue to increase following programme end given the embedding of GRSF knowledge and research into WB processes.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

The risk rating during the past year has been minor. As the programme has neared its close delivery has continued to be strong.

Strategy & Context - risk rating is moderate. This is because the implementation of road safety improvements is dependent on political will and available financing. Funding within the sector is relatively small in comparison to the scale of the challenge. Targetting road safety interventions towards receptive governments and decision makers remains important.

Financial and Fiduciary – risk rating is minor. Financial and procurement management of GRSF is strong and adheres to World Bank processes.

Policy & Programme Delivery – risk rating is minor. GRSF is a well-established programme with strong governance and research commissioning processes in place.

Safeguarding – risk rating is minor. The World Bank’s overall central policies and procedures meet the FCDO’s safeguarding standards. In April 2018, the WB, alongside nine other international financial institutions (IFIs) reaffirmed its commitment to prevent Sexual Exploitation, Abuse and Harassment (SEAH) in its own organisation and in its operations and strengthen its procedures through setting out their commitment to ten principles. These were reiterated by the WB and other IFIs in October 2018 at the Safeguarding Summit, where the IFIs also set out the work they were doing to promote, implement and reinforce efforts relating to the principles.

Reputational – risk rating is minor. Research activities and topics pose little or no reputational risk.

People – risk rating is minor. Experienced management teams are in place at both FCDO and GRSF, communication remains proactive and institutional memory considered sustainable.

The main risks over the course of the programme have been:

Demand and uptake of road safety knowledge: improved knowledge, data and evidence does not contribute to improved road safety outcomes – this has been mitigated through selection of projects and country partners on the basis of proven level of interest and commitment in the road safety agenda. Demonstration of benefits of road safety improvements, and international awareness raising of the scale of the problem, remains important to ensure buy-in of prospective partners.

Share of burden and overreliance on individual donors: dependence on relatively small group of donors exposes GRSF to risk of financial shocks – whilst GRSF’s current ambitious business plan (2024-2027) is not currently fully funded, GRSF has commitments from a diverse range of donor organisations. FCDO and the UK Government should continue to engage and advocate on behalf of the road safety agenda, including the work of GRSF, to ensure sustained support.

GRSF has delivered within our risk appetite throughout the programme, and the residual risk exposure is low.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

GRSF secretariat programme and financial management performance is strong. GRSF has received $84.93m since 2006 from all donors, of which £20.9m is from the UK - £8.9m from FCDO under this business case, £4.5m from DFID Nepal for country-level work done from 2014-2018, and £10.5m from DHSC. UK funding represents approximately 31% of GRSF funding since the start of the programme.

GRSF uses FCDO and DHSC funds primarily for a research grant programme through both Bank-Executed and Recipient-Executed contracts. They follow the WB Guidelines for Operational Procurement to ensure competitiveness and fiduciary care in all activities supported under the Trust Fund and achieve best VfM. WB have robust systems to detect fraud and corruption and there have been no reports of fraud or corruption to date on this programme.

The WB provides FCDO/DHSC with an audit report comprising a management statement and financial statement within six months of the end of the banks fiscal year (June). FCDO/DHSC received the facility annual report by November 2024.

The VfM assessment of the GRSF remains similar to last year’s annual review with the facility continuing to deliver expected results whilst keeping management costs low. In FY24, GRSF disbursed $7.6M, with regional and global programme activities accounting for over 92.8 percent of disbursements and programme management and administration accounting for the remaining 7.2%.

FCDO and DHSC continue to encourage GRSF to report more on specific results and impact of individual research projects. As part of GRSF 2.0, the WB has prepared a new results framework to better measure its results and impacts, responding to expectations and requirements of all contributing donors.

The assumptions made in the appraisal case of the initial business case (i.e. that GRSF would be a strong option for influencing MDB finance, compared to alternatives) have been borne out well by the programme’s achieved outcomes.

Programme-level approach to monitoring and evaluation [1/2 page]

GRSF issues annual reports that cover all GRSF activities, progress, risks and finances. More targeted logframe narratives, issued annually by GRSF, report against progress made through FCDO funded activities specifically. FCDO participates in quarterly GRSF partnership councils alongside other GRSF donors and road safety experts, having chaired the council for two consecutive terms between 2015 and 2018. GRSF also issues final reports for each multi-donor trust fund subscriped to by FCDO (MDTF2 and MDTF3).

Collectively, and alongside regular communication between programme leads, GRSF has consistently and proactively provided useful reporting, allowing the monitoring of progress and risks. However, and due to length of the programme and the number of business case amendments, the results monitoring framework by FCDO has become somewhat detached from the theory of change and especially in later years has not effectively tracked contribution to intended outcomes and impacts. In design of future Theories of Change and logframes, and in the implementation of business case addendums, care should be taken to ensure explicit linkages between activities, outputs, outcomes and impacts – and to maintain these linkages through changes to the programme context.

FCDO, DHSC and the UK Department for Transport continue to engage to ensure alignment on the international road safety agenda, and our collective engagement with GRSF.

Date of last narrative financial report	29/01/2025	Date of last audited annual statement	24/09/2024

Annex A – MDTF-3 Publications as of January 6th 2025

No.	Title	Document Type	Country or Countries	Theme	Publication Date
1	Road Crash Trauma, Climate Change, Pollution, and the Total Costs of Speed: / Six graphs that tell the story.	Research Report	Global	Infrastructure	2020
2	Guide for Road Safety Opportunities and Challenges: Low- and Middle-Income Countries Country Profiles.	Manual	Global	Infrastructure	2020
3	Use of the Safe System Assessment Framework as a Safety Key Performance Indicator.	Journal Article	Global	Infrastructure	2020
4	Features of Low-Income and Middle Income Countries making Road Safety more Challenging.	Journal Article	Global	Infrastructure	2020-08
5	Integration of Road Safety Considerations in Transit-Oriented Development projects: Good Practice Note.	Technical Report	Global	Infrastructure	2020-09
6	Prevalence of alcohol use among road traffic crash victims presenting to a Malawian Central Hospital: a cross sectional study.	Journal Article	Malawi	Health	2020-10
7	Road Safety Management Capacity Assessment for the Solomon Islands.	Country Report	Solomon Island	Infrastructure	2020-11
8	Road Safety Management Capacity Review for the Independent State of Samoa.	Country Report	Independent State of Samoa	Infrastructure	2020-11
9	Cyclist safety: an information resource for decision-makers and practitioners.	Manual	Global	Infrastructure	2020-11
10	Adult pedestrian and cyclist injuries in / Lilongwe, Malawi: a cross sectional study.	Journal Article	Malawi	Health	2020-12
11	Economic impact of 30km/h – Benefits and Costs of Speeds in an urban environment.	Journal Article	Global	Infrastructure	2021
12	Geographical mapping of road traffic injuries in Lilongwe, Malawi.	Journal Article	Malawi	Health	2021-02
13	Road Safety Data Assessment in Vietnam for the Establishment of a National Road Safety Observatory. Report prepared under the Advisory and Analytics Towards Efficient and Sustainable Transport for Vietnam	Country Report	Vietnam	Infrastructure	2021-04
14	Guide for Road Safety Interventions: Evidence of What Works and What Does Not Work.	Manual	Global	Infrastructure	2021-04
15	Road Safety Management Capacity Assessment for Vanuatu.	Country Report	Vanuatu	Infrastructure	2021-06
16	Post-crash emergency response toolkit	Toolkit	Global	Health	2021-7
17	Road Safety Data Review in Cambodia: Summary Note	Country Report	Cambodia	Infrastructure	2021-7
18	Africa Status Report on Road Safety 2020	Report	Africa	Infrastructure	2021-9
19	Policy Brief: Trauma Incidence and / Emergency Medical Services in Malawi	Policy Brieft	Malawi	Health	2021-10
20	Economic impact of 30km/h - Benefits and Costs of Speeds in an urban environment	Journal Article	Global	Infrastructure	08/11/2021
21	Availability of population-level data sources for tracking the incidence of deaths and injuries from road traffic crashes in low-income and middle income countrie s	Journal Article	Global	Health	15/11/2021
22	Investigating the fatal pedestrian crash occurrence in urban setup in a developing country using multiple-risk source model	Journal Article	India	Infrastructure	2021-12
23	Detecting Urban Clues for Road Safety – Leveraging Big Data and Machine Learning	Technical Report	Global	Infrastructure	2021-12
24	Guidelines for Conducting Road Safety Data Reviews	Manual	Global	Infrastructure	2021-12
25	Road Safety Strategies for African Cities: A Guide to Development	Manual	Africa	Infrastructure	2021-12
26	Applying a Safe System approach across the globe	Journal Article	Global	Infrastructure	08/12/2021
27	Road Safety Data in Africa	Technical Report	Regional - Africa	Health	12/01/2022
28	Technical Report: Trauma Incidence and Emergency Medical Services in Malawi report	Technical Report	Malawi	Health	19/01/2022
29	Comparing estimates of road traffic deaths and non-fatal road traffic injuries in Cambodia	Journal Article	Cambodia	Health	2022-2
30	Saving Lives Through Private Investment in Road Safety : Knowledge Report - 2022	Technical Report	Global	Infrastructure	22/02/2022
31	Addis Ababa Sidewalk Design and Maintenance Guidelines	Technical Report	Ethiopia	Infrastructure	28/02/2022
32	Addis Ababa Sidewalk Safety and Improvement Study : Project Report	Report	Ethiopia	Infrastructure	2022-3
33	Epidemiology of adult trauma injuries in Malawi: results from a multisite trauma registry	Journal Article	Malawi	Health	2022-4
34	Motorcycle Safety in Africa	Technical Report	Africa	Infrastructure	2022-4
35	Socioeconomic impacts of road traffic injuries in Central Asia	Research Report	Central Asia	Economic Growth	2022-4
36	Estimates of road traffic deaths in Tanzania	Journal Article	Tanzania	Infrastructure	2022-4
37	A study of road safety lead agency in Africa	Discussion Paper	Africa	Infrastructure	2022-5
38	The Asia–Pacific Road Safety / Observatory’s Indicators for Member Countries	Technical Report	Asia	Infrastructure	2022-6
39	Guide to integrating Safety into Road Design	Manual	Global	Infrastructure	2022-6
40	The Safe System Approach in Action	Research Report	Global	Infrastructure	2022-6
41	Powered two-and three-wheeler safety: a road safety manual for decision-makers and practitioners, 2nd ed	Manual	Global	Infrastructure	2022-10
42	Profile of low and middle-income countries with increases versus decreases in road crash fatality population rates and necessity of motorcycle safety	Journal Article	Global	Infrastructure	2022-10
43	Addressing discrepancies in estimates of / road traffic deaths and injuries in Ethiopia	Journal Article	Global	Infrastructure	2022-12
44	Mozambique : Preserving Human Capital through Improving Road Safety	Technical Report	Mozambique	Infrastructure	2022-12
45	Estimating the Burden of Disability From / Road Traffic Injuries in 5 Low- and / Middle-Income Countries: Protocol for a / Prospective Observational Study	Journal Article	Global	Health	01/02/2023
46	Helmets: a road safety manual for decision-makers and practitioners, 2nd edition	Manual	Global	Infrastructure	27/03/2023
47	Estimation of the completeness of road traffic mortality data in Zambia using a three source capture recapture method	Journal Article	Zambia	Infrastructure	31/03/2023
48	Multilateral Development Banks Road / Safety Financing in Low and MiddleIncome Countries: 2018–2022 (2023-5)	Systematic Review	Global	Infrastructure	2023-05
49	Pedestrian safety: a road safety manual for decision-makers and practitioners, 2nd ed	Manual	Global	Infrastructure	02/05/2023
50	Review of Tanzania Road Geometric Design Manual	Technical Report	Tanzania	Infrastructure	2023-06
51	Beyond the Numbers: Estimating the / Disability Burden of Road Traffic Injuries	Research Report	Global	Health	15/06/2023
52	Improving Road Traffic Injury Statistics in Low- and Middle-income Countries : / Addressing Discrepancies Between / Official Statistics and Global Statistical Models	Research Report	Global	Infrastructure	29/06/2023
53	Road Infrastructure Safety National Training & Accreditation Scheme	Technical Report	Tanzania	Infrastructure	2023-07
54	A Road Infrastructure Safety Strategy for Tanzania	Technical Report	Tanzania	Infrastructure	2023-08
55	The State of Emergency Medical Services (EMS) in Uganda	Technical Report	Uganda	Health	2023-9
56	Assessing discrepancies in estimates of road traffic deaths in Brazil	Journal Article	Brazil	Infrastructure	2023-10
57	Speed management: a road safety manual for decision-makers and practitioners (WHO) - Second edition	Manual	Global	Infrastructure	23/11/2023
58	Effectiveness of Speed Management / Measures on Rural Roads: Bangladesh / Insights	Journal Article	Bangladesh	Infrastructure	2024-01
59	A case-control study of the impact of automated speed enforcement on motorist speeds and speeding violations in Rwanda	Journal Article	Rwanda	Infrastructure	2024-01
60	Research on the Impacts of Automated / Speed Enforcement in Rwanda to / Develop Recommendations for African Countries: Self-Published Compiled Reports	Technical Report	Rwanda	Infrastructure	12/01/2024
61	Guide for Safe Speeds: Managing Traffic / Speeds to Save Lives and Improve / Livability	Manual	Global	Infrastructure	2024-03
62	Philippines’ Leadership on Road Safety / Renewal While Motivating the EAP Region	Technical Report	Philippines	Infrastructure	26/03/2024
63	Speed Management Research: A / Summary Comparison of Literature / Between High-Income and Low and / Middle-Income Countries	Research Report	Global	Infrastructure	2024-04
64	Assessing the effect of automated speed enforcement and comprehensive measures on road safety in Rwanda	Journal Article	Rwanda	Infrastructure	08/05/2024
65	The contribution of excessive or inappropriate speeds to road traffic crashes and fatalities: A review of literature	Journal Article	Global	Infrastructure	23/07/2024
66	Disability and Road Traffic Accidents: Assessing the Costs and Consequences of Rehabilitation and Living with a Disability Following a Road Traffic Injury	Technical Report	Global	Health	01/08/2024
67	Road Safety Assessment of Schools Zones	Technical Report	India	Infrastructure	04/08/2024
68	The Impact of Speed Limit Change on / Emissions: A Systematic Review of Literature	Journal Article	Global	Infrastructure	05/09/2024
69	Psychometric Properties of the WHODAS 2.0 in Patients with Orthopaedic Injuries from Road Traffic Crashes in Bangladesh	Journal Article	Bangladesh	Health	18/11/2024
70	Evaluación de seguridad vial en 22.000 kilómetros de la red nacional de Colombia	Technical Report	Colombia	Infrastructure	08/11/2024