Annual Review 2024

Title: British International Investment (BII) Programme of Support in Africa, South Asia, Indo-Pacific & Caribbean (2015-2027)
Programme Value £ (full life): £7,285,933,340		Review date: August 2025
Programme Code: 203444	AMP start date: 21/07/2015	AMP end date: 30/09/2027

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A+	A+	A+	A+	A+	A+	A+	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-1-203444 (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-1-203444 (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW
Description of programme
This programme increases the financial capital (equity) to British International Investment (BII), the UK’s development finance institution (DFI). The increase in equity will support onward investment into companies, projects and investment funds. The purpose is to deliver increased development impact (DI) in Africa, South Asia, the Indo-Pacific, and the Caribbean through commercial investment, blended finance, and market-shaping strategies. BII will also support economic reconstruction in Ukraine. BII’s approach to the end of 2026 is set out in its 2022-2026 Technical Strategy.
In 2024, BII made investments in private companies and projects in the form of equity, debt and guarantees, either directly or via intermediaries, with the mission to help solve the biggest global development challenges. BII has a dual mandate to (1) achieve development impact whilst (2) generating a sustainable financial return. Long-term patient capital from BII, backed by high environmental, social, and business integrity standards, helps businesses to grow, and builds a track record of successful investments that demonstrates to other private sector investors the financial viability of investing responsibly in developing countries. BII reinvests the proceeds from its investments in improving the lives of millions of people in the markets it invests in.
This is the third Annual Review since BII adopted its 2022-26 strategy. This strategy defines BII’s three strategic objectives as contributing to development which is:
1. Productive – raising the productivity of an economy so that it can support a decent standard of living for all.
2. Sustainable – helping to transform the economy to reduce emissions, protect the environment and adapt to climate change.
Inclusive – sharing the benefits of higher productivity, and greater sustainability, with poor and marginalised sections of society.
FCDO secured approval for a cost and time extension for this programme through a business case addendum. As part of this process, we have updated the log frame to better reflect the new strategic priorities set out in BII’s 2022-2026 strategy.
This Annual Review covers BII’s performance throughout the 2024 calendar year. Further information on BII’s financial and impact performance can be found in BII’s own Annual Review and its Annual Report and Accounts 2024 which contain detailed reporting on BII’s activities, new investments and development impact such as its Task Force on Climate-related Financial Disclosures.
Summary supporting narrative for the overall score in this review
Highlights in 2024:
In 2024, BII made total new commitments of £1.75 billion supported by £1,160 million of new capital from FCDO. BII’s commitment pace was higher than last year’s figure of £1.31 billion, representing a 33% increase from 2023 levels.
[note] This included £60m of capital to support BII’s expansion into Ukraine. It is also worth noting that this figure represents the total capital provided to BII in 2024, but this represents equity injections across two separate financial years - FY23/24 and 24/25.
BII’s seven-year weighted average annual portfolio return at the end of 2024 was 5.1%, exceeding its target of 2% over the same period.
In 2024, BII mobilised approximately $1.6 billion of private-sector capital into developing economies in addition to its own investment, Using the multilateral development bank (MDB) methodology, this meant mobilising around $70 from the private sector for every $100 of BII’s overall commitments. In 2024, BII also launched a new Mobilisation Facility to to boost the flow of private investment into emerging economies, marking an increased focus from BII on private capital mobilisation.
BII continues to champion gender-smart investing and in its 2022-26 strategy set a target for 25% of all new investments across the strategy period to qualify under the 2X challenge, a joint initiative to boost financing for women. In 2024, 29% of BII’s investments (£499 million) qualified under the 2X Challenge.
In 2024, 41% (£708 million) of BII’s new commitments were climate finance - its largest annual climate commitments (by volume) to date, with its portfolio of investments avoiding 1.5 million tonnes of CO₂ equivalent emissions. BII backed major clean energy projects like South Africa’s Kenhardt Solar Project and have also built climate resilience where it is most needed for example by expanding climate risk insurance access through a partnership with InsuResilience. Climate finance assets now make up 26.5% of BII’s entire portfolio.
BII continued to play a leadership role amongst DFIs. For example, after launching the Adaptation and Resilience Investors Collaborative (ARIC) in 2020, as chair in 2024, BII supported the development of a common financing framework aimed at identifying and qualifying resilience investments, both at the level of investment vehicles and individual projects. BII has also continued to lead on the Africa Resilience Investment Accelerator (ARIA), a cross-DFI platform established in 2021 to scale investment in African fragile states (with an initial focus on 5 countries). In 2024, BII completed its first ARIA-supported investment - a new $25 million risk-sharing facility with Ecobank in Sierra Leone, which will provide much-needed capital for ambitious local businesses which typically face challenges accessing finance.
In 2024, BII committed £880 million to the poorer and most fragile countries across the regions it invests in, demonstrating BII’s commitment to playing a leading role in frontier markets that are often outside the investment horizon and geographic focus of commercial investors.
Under its Catalyst portfolio – which can take a more flexible approach to risk in return for enhanced development impact – BII backed pioneer businesses to shape nascent markets and build more sustainable and inclusive economies. BII supported 19 ventures and 4 Funds over the year through Catalyst, which included investment support into AgDevCo (an investment company and long-term partner of UK Government dedicated to developing African agriculture through investments in agribusinesses), and Etana (an energy trading company).
Leslie Maasdorp joined BII as the new Chief Executive, his background, spanning development finance, banking and government, and his early experience of the transition to democratic government in South Africa, position him exceptionally well to lead BII. He will lead BII into their next strategy period, supported by the Board and the BII team.
Major lessons and recommendations for the year ahead
BII delivered strongly in 2024, meeting all its core targets whilst substantially increasing its investment commitment pace, supporting the development of two new pilot concessional finance facilities, expanding its operations to begin investing in Ukraine, and evolving its approach to private capital mobilisation more broadly. BII’s investment commitments increased by 33% in 2024 compared to 2023, and its aggregate impact score increased to 7.0 (compared to 6.8 in 2023), demonstrating BII continued to prioritise and deliver impact across its portfolio. BII is a founding signatory to the Operating Principles for Impact Management, the impact investment industry standard for impact management. BII’s alignment with the Operating Principles for Impact Management was independently verified by BlueMark, which named BII a Practice Leader in BlueMark’s Making the Mark report for a third year in a row, and assessed BII’s approach in 2024 to be ‘advanced’ against every principle. As a consequence of this strong performance, BII has delivered against the vast majority of its output and outcome targets.
2025 will be an opportunity to further refine BII’s delivery approach and take these lessons into designing BII’s next 5-year Strategy to begin in April 2026. As such, key recommendations for this review include:
Learn lessons from BII’s evolving approach to private capital mobilisation to inform BII’s next five-year strategy.

Learn lessons from BII’s two new concessional finance facilities – ARIF and the Mobilisation Facility – to support discussions on BII’s next five-year strategy.

Explore opportunities to scale BII’s mobilisation of private capital for climate investments.

Explore with BII opportunities to evolve its approach to additionality, including consideration of market level additionality, and the role of the Catalyst portfolio within this.

Continue to monitor BII’s expansion into Ukraine.

Learn lessons from BII’s improved approach to transparency and work with BII as it considers its future approach.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The BII programme log frame was updated to align more closely with the objectives of BII’s 2022-26 Strategic Framework, the revised BII Investment Policy and the new BII Reporting Framework. We are confident that the theory of change remains relevant from the original business case as BII’s aims and remit under its new strategy and geographic approach remains unchanged.
A high-level summary of the theory of change for BII is summarised below:
(Inputs) In relevant countries of operation, where the market for private sector investment is underdeveloped, BII will deploy commercial investment and scale new innovative approaches with higher risk capital;
- (Outputs) which will provide both much-needed capital and expertise to businesses (capacities, skills, practices & standards) as well as strengthen sector specific markets for businesses and investors;
- (Outcomes) which in turn will spur growth in the quantity and quality of portfolio companies, building BII’s track record of successful investments, thereby demonstrating the viability of investing in such markets and businesses to other investors (improving the supply of finance), as well as helping build more productive markets (improving the demand for finance);
- (Impact) all of which will contribute - through increased jobs, tax receipts and better access to goods and services - to sustainable private sector and economic development to contribute to a range of the Global Goals, including poverty reduction.
As outlined in subsequent sections of this review, BII is maintaining its performance as set out against the theory of change.
There have been no changes to impact indicators since the last Annual Review. The following outcome indicators were updated in 2023 to reflect changes in reporting since the approval of the original business case, but no additional changes have been made this year:
Outcome indicator 1: Includes direct and indirect jobs supported by the portfolio.
- Outcome indicator 2: Includes finance mobilised per $100 committed in the year.
- Outcome indicator 3: Includes taxes paid.
- Outcome indicator 4: Includes split of electricity generated by renewables.
- Outcome indicator 5: Updated from “gross loan portfolio of BII financial sector investments” to cover loans and advances made, and number of clients reached by BII backed financial institutions.
- Outcome indicator 6: New indicator covering number of farmers reached by BII investments.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme remains on track to contribute to the expected outcomes and impact documented in the log frame, and as summarised in the table below.

Outcome level results
	KPI	2024 performance	2023 performance	2022 comparison
Outcome Indicator 1	Total jobs supported by BII investee companies including direct (disaggregated by gender); and induced/indirect - per £m invested in the portfolio	Direct: / 1,024,290 (24% women) / (82,410 new hires by BII investee companies in 2024) / Indirect: / Supply chains: 2.58m / Electricity: 0.86m / Wages: 3.1m / Bank lending: 5.3m	Direct: / 1,082, 370 (26% women) / (84,620 new hires by BII investee companies in 2023) / Indirect (restated): / Supply chains: 2.5m / Electricity: 0.9m / Wages: 3.2m / Bank lending: 5.3m	Direct: / 958,200 (28% women) / (54,090 new hires by BII investee companies in 2023). / Indirect: / Supply chains: 1.2m / Electricity: 0.9m / Wages: 0.9m / Bank lending: 8.2m
Outcome Indicator 2	Private finance mobilised by BII (absolute figure and per $100 committed in the year)	$1.55bn / $70 from the private sector for every $100 of its own commitments / (MDB methodology)	$938m / $58 from the private sector for every $100 of its own commitments. / (MDB methodology)	$1.43bn / $90 from the private sector for every $100 of its own commitments. / (MDB methodology)
Outcome indicator 3	Tax contributions by BII investees	$2.5bn	$2.42bn	$1.79bn
Outcome indicator 4	Electricity generated in the year (GWh) from BII backed power projects (with renewable split)	47,272 GWh generated / (56% renewable energy)	48,007 GWh generated (restated) / (52% renewable energy)	49,873 GWh generated / (49% renewable energy)
Outcome indicator 5	Loans and advances made, and number of clients reached by BII backed financial institutions	$102.8bn / [150m clients reached]	$105.8bn / [135m clients reached]	$86.1bn / [121m clients reached]
Outcome Indicator 6	Number of farmers reached by BII investments	10,271,680	13,165,320	9,994,850
[note] BII has used an updated methodology for calculating the ‘Indirect jobs’ and ‘electricity generated’ KPIs as part of its 2024 annual review. To allow comparison over time, BII has also provided restated 2023 figures for these KPIs using this updated methodology, which we have included in the above table. There is thus a discrepancy between the ‘2023 performance’ figures included in this annual review compared to the figures provided in the FCDO’s 2023 annual review of BII.

In 2024, BII made £1.75 billion of new commitments (2023: £1.31 billion) with the total value of BII’s portfolio remaining approximately flat at £7.3bn as of 31 December 2024 due to substantial investment receipts). BII delivered a profit after tax of £213.3 million in 2024 (2023: £44.0 million loss).
Outcome 1: Jobs - BII’s portfolio businesses employed over 1 million full-time equivalent workers in 2024, which included the creation of over 82,000 new jobs, approximately matching BII’s 2023 figures. In 2024, 24% of the workforce were women, slightly down on the proportion seen in 2023 (26%). BII also supports jobs beyond its portfolio, with its investments indirectly supporting many more businesses and livelihoods. Looking at indirect job metrics, the number of jobs BII supported through supply chain purchasing by investee business and by local spending of wages were marginally down, while jobs supported by economic activity enabled through BII’s portfolio supplying electricity and jobs supported by credit provided by BII-backed financial institutions marginally increased. The small variation in direct and indirect job creation reflects the evolution in BII’s portfolio of investees from year to year. Overall, the above demonstrates that BII’s portfolio continues to directly and indirectly support job creation through a range of channels, helping to support broader economic development in these markets.
Outcome 2: Private capital mobilised - In 2024, BII mobilised approximately $1.55 billion of private-sector capital. This meant that BII mobilised around $70 from the private sector for every $100 of its own commitments (MDB methodology). This compares to BII mobilising $58 mobilised per $100 in 2023.This follows a concerted effort by BII to strengthen its approach to private capital mobilisation in 2024, including by being more explicit in its origination activities to identify deals viable for unlocking private sector co-financing. We expect this approach will see BII deliver greater volumes of private capital mobilisation in future years as it’s embedded in the organisation (see Output 2 for more info).
[note] In BII’s 2024 Annual Review, the methodology used to calculate private capital mobilised (PCM) has been updated to use BII’s gross commitments rather than net commitments as the denominator in the calculation. To enable comparison over time, BII has also restated its 2023 PCM figure in the 2024 annual review. Hence, there is a difference between the PCM figure BII reported for 2023 between its 2024 annual review and 2023 annual review.
Outcome 3: Tax - BII’s investees paid $2.5 billion in taxes, the third consecutive year of growth (2023: $2.42 billion). This supports partner countries to raise the tax revenues needed to support broader spending, including on social welfare and public infrastructure.
Outcome 4: Electricity - BII investments generated more than 47 Terawatt hours (TWh) of energy (2023: 48 TWh), which is equivalent to 16% of the total electricity generated in the UK in 2024. Although there was a small decrease in overall electricity generated in 2024 compared to 2023, the amount of renewable energy generated within this increased (26.5 TWh compared with 24.9 TWh), noting that there has been a deliberate decrease in production in non-renewable assets.
Outcome 5: Loans and advances - In 2024, BII’s gross loan portfolio of its financial sector investments stood at $102.8bn (2023: $105.8bn), while customers reached materially increased from 135 million to 150 million in 2024. Therefore, while BII’s gross loan portfolio marginally shrunk due to changes in its portfolio, the remaining portfolio reached more people in developing economies, supporting broader access to capital. This reflects BII’s strategic focus in supporting both capital market development but also access to financial services.
Outcome 6: Farmers: - BII’s food and agriculture portfolio reached an estimated 10.3 million farmers in 2024 including suppliers of crops, livestock and timber, and customers for inputs such as feedstock and seeds, which marks a 21% decrease from 2023 levels (13 million). This is due to a combination of factors including exits in BII’s portfolio and a reduction in reported numbers from some BII investees.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As articulated above and in more detail below, BII is performing well against the majority of its output and outcome targets, providing strong justification for the continuation of the programme. BII’s investment activities continue to have impact at scale across a wide range of outcomes, including direct jobs created, tax revenues generated by investee businesses, electricity generated, access to finance, and supporting the agriculture sector. BII has substantially increased its investment commitments in 2024 whilst also raising its private capital mobilised, thereby providing impact at greater scale. BII continues to perform strongly against its sustainability and inclusion indicators (see below), exceeding its goals to have 30% of commitments qualify as climate finance and 25% of commitments qualify for the 2X Challenge to boost financing for women.
BII also represents good value for money for the FCDO. Capital invested through BII generates returns over time, which are then reinvested into new projects and businesses, multiplying the effect of every pound in generating development impact. BII’s portfolio return in 2024 was 4.3% in sterling, and 3.3% in dollar terms. BII also continued to exceed its target for its long-term portfolio returns, achieving a seven-year weighted average annual portfolio return of 5.1% against a hurdle rate of 2%, ensuring it can cover its own costs.
Several studies reinforce this picture of BII’s long-term impact – including, the final synthesis from the multi-year independent evaluation of BII’s Financial Services portfolio, which illustrates BII success in adapting its financial services strategy to deliver enhanced development impact, including through a shift towards more targeted lending and a greater focus on underserved segments and poorer markets. Another example is a rigorous analysis of the impact of BII’s investment in Virunga Energies, a hydropower plant adjacent to Virunga National Park in the Democratic Republic of Congo which shows a material increase in asset wealth for villages receiving electricity for the first time (from the 79th to the 86th percentile) despite conflict and instability. Finally, a study of women-owned and led businesses demonstrates their importance in supporting a range of gender-smart business practices, in line with BII’s commitment to the 2X Challenge.

## C. DETAILED OUTPUT SCORING
Output Title	Investment is made into high impact enterprises and markets in Africa, South Asia, Southeast Asia, and the Caribbean.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Aggregate Annual Impact Score (weighted by size and date of Relevant Investment)	Impact Score between 5.0 – 8.0.	Achieved – BII’s Impact Score for 2024 was 7.0.
% of NAV invested under BII’s enhanced impact Catalyst portfolio	Ensure progress in increasing BII’s enhanced impact Catalyst investments to at least 10-15% of BII’s portfolio by NAV by 2026.	Achieved – 13.5% of NAV in 2024.
Average impact score of Catalyst portfolio	Catalyst portfolio has higher impact score than core portfolio.	Achieved – new Catalyst commitments delivered an average impact score of 9.3 for 2024.

Briefly describe the output’s activities and provide supporting narrative for the score.
BII measures the development impact of its portfolio through an Aggregate Impact Score. BII’s Aggregate Impact Score for a given financial year is the sum of the most recent Impact Scores given to each relevant individual investment committed by BII over the period, weighted by size and date. BII assigns each relevant investment an individual Impact Score between -1 and 10 at the time such investment is committed or renewed using a framework agreed with FCDO. The framework scores each relevant investment depending on how much they contribute to each of BII’s three strategic objectives:
Productive score: measures the extent to which the investment addresses the biggest developmental needs and constraints to economic growth.
Sustainable score: measures the extent to which the investment contributes to a greener planet.
Inclusive score: measures the extent to which the investment reaches poor and marginalised people.
The Impact Score is thus designed to recognise and incentivise investments that are most likely to contribute to BII’s three strategic objectives. Each investment is assigned a score between 0 and 4 for each of the three dimensions, with the possibility of a -1 Sustainable score (where investments support large emitters). The total Impact Score for any Investment is capped at 10.
BII’s Aggregate Impact Score of 7.0 for 2024, compared to a target range of 5.0 – 8.0. BII also delivered a strong impact Score across each of its three strategic objectives, demonstrating that BII has constructed a balanced portfolio which delivers productive, sustainable and inclusive development. Moreover, BII delivered a strong impact score across each of its three sector vertical groups – Financial Services; Infrastructure and Climate; and Industry, Technology and Services – showing that impact was broad based across sectors rather than driven by any one sector. BII achieved this stronger impact score whilst substantially ramping up investment volumes in 2024 to £1.75bn (up 33% from 2023), demonstrating that the Impact Score is an effective tool for incentivising BII to originate impactful transactions.
The Catalyst Portfolio takes a more flexible approach to risk relative to the Growth portfolio – such as a greater focus on nascent markets where there are fewer viable commercial opportunities - in exchange for pioneering development impact. The Catalyst portfolio has a loss tolerance of up to 30% enabling BII to invest for innovation and impact in challenging markets. As distinct to BII’s core Growth portfolio, Catalyst transactions must qualify under an ‘enhanced development impact’ framework – a framework that was updated in 2020 and refined again in 2023. During 2024, BII made £311.2 million of gross new Catalyst investments (2023: £264.4 million), which accounted for 13.5% of BII’s portfolio at year end, up from 12% of BII’s portfolio in 2023. BII is therefore on track to meet its target to have 10-15% of its total portfolio in Catalyst by 2026. Furthermore, the Catalyst Portfolio continues to support highly productive, sustainable and inclusive investments evidenced by its high development impact score, which was 9.3 in 2024 (higher than BII’s aggregate score of 7.0)
Examples of impactful investments made through the Catalyst Portfolio in 2024 include:
- InfraCredit: BII's $20 million counter-guarantee facilitates the mobilisation of local capital to boost the development of distributed renewable energy solutions in Nigeria, including solar mini-grids, solar home systems, and solar lanterns.
- African Rivers Fund IV: BII's $15m commitment to XSML's African Rivers Fund IV provides long-term financing to SMEs in fragile markets of Central and East Africa.
- Etana: BII committed a $50 million default guarantee, alongside a matching contribution from GuarantCo, to support Etana, an energy trading company, in unlocking up to 500MW of new renewable energy capacity in South Africa.
In 2024, BII continued to expand its footprint in South-East Asia as part of its 2022 – 2026 strategy. Notably BII made its first direct equity (Xurya in Indonesia) and direct debt (BECIS SEA in Thailand) investments, both supporting the commercial and industrial (C&I) renewable energy space, focusing on distributed solar solutions. BII has also expanded into Ukraine through separate funding from the FCDO, with its first Ukraine transaction using this capital now completed.
BII has substantially updated its approach to transparency in line with its detailed plan set out in its Transparency Roadmap. We will work with BII to learn lessons from its work to improve transparency, and consider what its future approach should be on this agenda.
BII continues to deepen its partnerships with other DFIs and MDBs, including through initiatives such as the 2X Gender challenge focused on gender investing and the Africa Resilience Investment Accelerator focused on scaling investing in African fragile states. We will work with BII to learn lessons from these efforts and explore opportunities to further strengthen coordination and coherence with relevant instruments, institutions and posts to further deepen impact.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to this output over the past year, and none are planned following this year’s review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s recommendations:
Continued delivery of an investment programme aligned to the £7.5-10bn ambition - subject to the confirmation of the final funding profile over the next SR period – as well as delivery against impact performance (key aggregate impact score) as per the 2022-2026 Investment Policy.
1. Evaluate the merits of creating a new FCDO funded Low Income Country Facility within BII.
2. Work with BII to consider options for scaling DFI investment in the poorest and most fragile countries through the G7 and ARIA.
3. Evaluate the merits of creating a new FCDO funded private capital mobilisation facility within BII.
4. Work closely with BII as they begin to undertake ex-post scoring of investments made at the start of the 2022-26 strategy.
Progress:
Good progress has been made against these recommendations.
With regards to recommendation 1, BII substantially increased their investment commitment pace in 2024 to £1.75 billion - a 33% year-on-year increase in commitments – whilst delivering an aggregate impact score of 7.0, rising from 6.8 in 2023.
With regards to recommendation 2, FCDO and BII worked closely to evaluate and develop a new FCDO funded LICs Facility with BII focused on Africa (the Africa Resilience Investment Facility – ARIF), with this Facility receiving Ministerial approval in late 2024. BII is now operationalising ARIF to begin investing in 2025. This facility aims to unlock more finance for high potential businesses in those African countries which currently have the furthest to travel to attract commercial investment. The ARIF mandate will have the ability to invest across all African Low-Income Countries (LICs).
With regards to recommendation 3, in 2024, BII committed £880 million to poorer and more fragile countries within BII’s eligible regions. BII has continued to drive progress through the Africa Resilience Investment Accelerator (ARIA), deepening coordination with development partners to better identify and support private sector investment opportunities in fragile and conflict-affected regions in Africa (focused on five countries to begin with). In 2024, BII made its first investment under ARIA – following several years of support - in a new facility with Ecobank in Sierra Leone, which will provide much-needed capital for ambitious local businesses.
With regards to recommendation 4, in 2024, the FCDO worked closely with BII to develop and launch a new Mobilisation Facility within BII (announced by the Prime Minister at UNGA). The Facility provides BII with concessional capital to boost private investment (through the provision of risk mitigation) into climate and SDG aligned assets in emerging economies. The Facility will substantially enhance BII’s ability to mobilise private capital at scale, in particular from institutional investors who commonly allocate very little capital to BII’s markets. The process involved considerable collaboration with partners in the City of London, which led to a Call for Proposals being launched in early 2025, which will be captured in the next Annual Review.
With regards to recommendation 5, in 2024 BII started rescoring investments to reflect their actual impact performance (referred to as “ex-post scoring”), enabling comparison with their ex-ante anticipated impact. This led to 63 deals being rescored in 2024. Changes were typically small and evened out across the 63 transactions. Ex-post scoring ensures that BII has a better sense of how its transactions are delivering impact and can inform lessons learned for ex-ante impact scoring going forward.
In terms of lessons learned, one area to further explore with BII is whether there are opportunities to evolve BII’s approach to additionality, including opportunities to further drive impact at the level of the market rather than the firm. This would explore opportunities (and trade-offs) for further targeting transactions which have wider positive externalities on the market, delivering broader impact than at the specific firm level.
Recommendations for 2025:
Learn lessons from BII’s evolving approach to private capital mobilisation to inform BII’s next five-year strategy.

Explore with BII opportunities to evolve its approach to additionality, including consideration of market level additionality, and the role of the Catalyst portfolio within this.

Continue to monitor BII’s expansion into Ukraine.

Learn lessons from BII’s improved approach to transparency and work with BII as it considers its future approach.

Explore opportunities to further deepen partnership and coordination with relevant instruments, institutions and posts, enhancing impact through a more joined up approach.

Output Title	Investments are made which demonstrate commercial viability and support development of markets and sectors in BII’s target geography.
Output number:		2	Output Score:	A++
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Weighted Cumulative Investment Return on BII’s Total Portfolio – as defined in BII’s Investment Policy 2022-2026	2%	Achieved - 5.1%

Briefly describe the output’s activities and provide supporting narrative for the score.
BII achieved against this indicator, returning a 5.1% seven-year weighted average annual portfolio return, well above the 2% hurdle rate.
- In 2024, BII’s total portfolio return was £317.3 million (2023: £71.5 million). This represents a portfolio gain of 4.3% in GBP (1.1% gain in 2023) on portfolio investment assets.
- In US dollar terms, BII’s portfolio generated a gain of 3.3% in 2024 (2023 5.2% gain) due to a positive performance across markets.
- BII’s results are significantly impacted by changes in the sterling to US dollar exchange rate. This was the case in 2024, where sterling depreciated during the year, causing a differential in sterling and US-dollar results.
In 2024, BII published a report reflecting on 10 years of learning from Catalyst, which included detail of the variance in its performance. Greater impact is the central goal of Catalyst, which often requires BII to take on more risk, which BII will not always be fully compensated for. One might expect the Catalyst portfolio’s performance to be significantly lower than the rest of BII, with the higher probability of failed investments weighing on the portfolio’s overall returns. However, early indications, outlined in BII’s 10 years of learning from Catalyst, are that commercial performance is tracking well against expectations. This has demonstrated that it is possible to preserve capital – and secure a modest return – while applying a high-risk appetite to invest for transformational impact.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to this output over the past year, and none are planned following this year’s review
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s recommendations:
Continue to deliver against financial performance measure as per the 2022-26 Investment Policy.
Progress:
BII continues to demonstrate the commercial viability of investing in its eligible geographies, delivering a strong portfolio return in both GBP and USD. BII continues to deliver this strong financial return whilst having a substantial portion of its portfolio in higher risk activities – both in terms of the proportion of its portfolio invested in equity (approx. 70%) and in Africa (approx. 60%). In 2024, BII delivered a higher proportion of new debt commitments as part of a broader shift away from a generalist funds strategy, which we will want to monitor the impacts of working closely with BII.
Recommendations for 2025:
Continue to monitor the product mix of BII’s portfolio to ensure BII is meeting its strategic goals as set in the Investment Policy.

Output Title	Investments are made which support BII’s crosscutting objectives of climate finance and gender.
Output number:		3	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Climate finance as % of total commitments, and $ value of annual climate finance commitments.	30% total commitments by value to be climate finance.	Achieved – 41% of total commitments in 2024. / BII made £708 million in climate finance commitments in 2024.
% of commitments/ pipeline that qualify under the 2X challenge framework.	25% of commitment/ pipeline qualifies under the 2X Challenge framework.	Achieved – 29% of total commitments in 2024 .

Briefly describe the output’s activities and provide supporting narrative for the score.
BII continues to be a leader in gender-smart investing, pursuing its ambition to support women’s economic empowerment. BII’s 2022-26 strategy has set a target for 25% of all new commitments to qualify under the 2X Challenge, a joint initiative with other DFIs to boost financing for women. In 2024, 29% of BII’s new investments (£499 million) were 2X qualified and across 2022 to 2024, an average of 34% of BII’s commitments were gender finance qualified. In 2024, this included backing:
- BRAC Bank through a $50 million commitment to the leading SME bank in Bangladesh, which will provide vital funding to support the growth of up to 3,500 micro-small- and medium enterprises (MSMEs) and women-led businesses in Bangladesh.
- Through its technical assistance facility, BII Plus, BII also backed Veritas, an Indian non-financial banking company, to support women entrepreneurs. BII’s support enabled Veritas’ to launch Dhana Shakti, a collateral-free loan product with lower fees, designed to address barriers led by women-led MSMEs. To date, Dhana Shakti has reached over 1,600 customers and women borrower numbers grew by 60 per cent between 2023 and 2024.
Furthermore, in 2024, 41% (£708 million) of BII’s new commitments were climate finance, demonstrating BII’s increasing leadership in this space. Climate finance qualifying assets now make up 26.5% of BII’s total portfolio, compared to 15.4% in 2020.
Over the year, BII has made new investments across the full spectrum of renewable energy. This includes large scale energy generation (such as an investment in Suez Wind Energy to construct a 1.1 GW windfarm in Egypt). But also investment into underserved sectors that are key bottlenecks for energy transmission such as transmission and distribution and battery storage. At COP29 BII announced it will set up a new platform, Energrid, alongside investment from Norfund and IndiGrid to develop greenfield transmission and standalone battery energy storage system projects in India. BII has used innovative funding approaches to unlock clean energy markets, such as the guarantee provided to Etana Energy (in partnership with Private Infrastructure Development Group - PIDG) to help add around 500 MW of competitively priced renewable energy to South Africa’s grid.
Beyond energy infrastructure, BII investments have supported the green transformation of economies by scaling up innovations such as electric vehicles, clean cooking, energy efficiency, the circular economy, and new technology to help farmers adapt to climate change. BII has also continued to lead efforts to scale up private finance into adaptation, supported by BII’s Climate Innovation Facility (CIF) which deploys concessional capital into nascent climate technologies and business models, including for A&R. See further detail on CIF under Output 5.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to this output over the past year, and none are planned following this year’s review
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s recommendation:
Continue to champion gender-smart investing for DFIs. BII should lead other DFIs in updating the 2X Criteria and ensuring the next 2X investment target launched at the G7 is sufficiently ambitious.
Progress:
BII continues to champion gender smart investing, as noted above. BII also continue to show leadership more broadly by engaging in the broader process to update the 2X criteria and launch a new 2X investment target. At the G7 Leaders’ Summit in 2024, Development and Multilateral Finance Institutions committed to invest at least US$20 Billion over three years (from 2024-2027) to advance measurable changes and financing directed to women’s empowerment, with BII included in this commitment. They also called upon other public and private actors to join the 2X Challenge.
In 2024, BII published a new report, ‘Closing the gap: Lessons from six years of investing in women.’ The report charts BII’s journey in gender finance since the launch of its Gender Finance Strategy in 2018, offering key insights, real-world case studies, and provides an analysis of the challenges and opportunities shaping gender-focused investments.
Gender bonds are increasingly becoming an important financing tool to support women’s economic empowerment. In 2024, BII published a gender bonds toolkit in partnership with FSD Africa, FSD Network and UN Women to provide guidance on how to design and issue gender bonds with a focus on advancing gender equality in Africa. BII also held launch events and trainings based on its guidance in Nairobi, Lusaka and Lagos.
In 2024, BII also delivered trainings on gender-based violence and harassment to over 550 participants across 11 countries including partnering with four Development Finance Institutions - Proparco, DFC, DEG and Norfund. This delivered a new advanced training programme to equip companies with practical tools and strategies to tackle these issues, funded by BII Plus.
In terms of lessons learned, following discussion with BII, we recognise there is an opportunity for BII to further evolve its approach to mobilising private capital at scale to support the energy transition in middle-income developing economies. Further, we will seek to explore whether there are opportunities for BII to increase investment in A&R, building off lessons learned from BII’s existing efforts.
Recommendations for 2024:
Explore opportunities to scale BII’s mobilisation of private capital for climate investments.

Explore opportunities to support increased BII investment in A&R, and the future role of ARIC in pushing progress amongst DFIs.
Output Title	BII delivers against the 2022-2026 strategic framework, including annual corporate objectives outside of core impact and financial performance measures (covered elsewhere in the log frame).
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
FCDO assessment of performance against Annual Corporate Objectives set by the BII board not covered elsewhere (as chosen by FCDO on annual basis).	Satisfactory progress against below Annual Corporate Objectives set by the BII Board not covered elsewhere (as chosen by FCDO on annual basis): / Commitment pace / Receipts / Risk Appetite / People and Cultural Health	BII measures performance against its annual corporate objectives using a traffic-light system. We replicate this here. / a) Total gross new commitments of over £1.7bn - green / b) BII receipts totalled £1.4bn - an increase of over 47% from 2023 - green / c) risk appetite managed within appetite set by the Board – green / d) People and Cultural Health - Successful launch of Performance, Evaluation and Development Programme and interim global female and black leadership targets exceeded - amber

Briefly describe the output’s activities and provide supporting narrative for the score.
For 2024, the BII Board set ten annual corporate objectives for the organisation to pursue as it continues to implement its 2022-2026 strategy. These cover core operations and activities of the business and are grouped around three themes: ‘Investment Performance’, ‘Operations and Culture’ and ‘Stakeholder Relations’. 2024 was a strong year for BII, with eight of ten Corporate Objectives fully met or exceeded including impact targets on climate, inclusion and gender covered elsewhere in this annual review. BII delivered a number of ‘firsts’ and broke several records (e.g. number of deals, receipts, number of IC decisions etc). In this year’s annual review, we are focusing on assessing BII’s performance against four of the ten corporate objectives, with these objectives not covered elsewhere in this annual review (i.e. through KPIs).
Commitment Pace
BII committed a gross amount of £1.7bn ($2.2bn) across 94 deals (the highest number in a single year in their history) with a record number of 278 Investment Committee decisions. BII’s volume of commitments in 2024 represents a 33 per cent increase from 2023, and combined with 2023 gross commitments exceeded its $3.5bn two-year rolling target.

Receipts
Total receipts for 2024 were £1.4bn exceeding internal targets for 2024 and representing a 47% increase from 2023, primarily due to loan investment interest and principal receipts. This is the highest amount in a single year for BII and reflects the successful exit from investments such KELIX bio, one of the largest deals in the pharmaceutical sector in Africa over the last twenty years.
Risk Appetite
While risk levels in BII markets and portfolio remained high in 2024, BII continued to successfully manage its risk within the appetite set by its Board, and in line with its Risk Appetite Framework which it introduced in 2021 with most categories on its risk dashboard rated Green. More information on this can be found in its annual accounts. Although a small number of individual risks on the dashboard were outside BII’s appetite – BII has a timebound action plan in place to manage these, and overall BII was within its risk appetite.
People and Cultural Health
Performance against the People and Cultural Health corporate objective 2024 improved as a result of the successful launch of BII’s Performance Evaluation and Development Programme, and BII also exceeded its global female leadership and black leadership targets.
- PEDP launched successfully, which saw BII introduce performance ratings for the first time and roll-out training for line managers and for all employees.
- 39.1% female leadership against interim milestone of 37.5% by the end of 2024 (milestone exceeded, leading to revision of our 2026 targets).
- 14.3% black leadership against interim milestone of 11.5% by the end of 2024 (milestone exceeded, leading to revision of our 2026 targets).

BII’s Culture Dashboard shows that BII’s cultural health for 2024 remained amber overall, but trending green. The culture dashboard draws on a range of data sources to assess BII’s cultural health across a range of lenses. A range of key engagement indicators remain green, with further commitment to maintain this trajectory required. When combined with the findings of BII's 2024 employee engagement survey, some indicators, such as leadership and speak-up culture, have been identified as  focus areas for follow-on action.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output over the past year, and none are planned following this year’s review. BII’s Corporate Objectives themselves are updated by BII each year to reflect ongoing priorities. From 2023 to 2024, BII amended the objectives in a way that prioritised continuity, focus and efficiency. This entailed:
- Reducing the number of Corporate Objectives from 12 to 10.
- Increasing the consistency between objectives (e.g. BII now have a consistent approach to measuring Climate, Gender and Highly Inclusive targets, as well as between investment pace and receipts).
- Reflected progress made in 2023 (e.g. around mobilisation, and progressing work in SE Asia).
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s recommendations:
Continue to monitor BII’s progress against its annual corporate objectives.
Progress:
We have effectively monitored BII’s progress against its annual corporate objectives in 2024, utilising our formal governance arrangements – in particular the Quarterly Shareholder Meeting - to ensure we’re tracking progress and understanding the underlying drivers of performance against the individual objectives.
Recommendations for 2025:
None.

Output Title	BII successfully uses blended finance to support high impact, innovative investments, catalyse new markets, and mobilise private capital.
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Growth and sustainability of CIF pipeline: # deals screened and # reached financial close	Growing number of deals screened and reaching financial close	Achieved. 7 deals closed during 2024 and a further 15 deals had reached first stage approval as at end 2024. / This compares to 4 deals having closed in 2023.
Adaptation and Resilience: number of deals in pipeline and portfolio	Growing number of A&R qualified deals screened and/or reaching financial close	Achieved. 4 A&R qualified deals reached financial close during 2024 compared to 2 in 2023. / Across 2021 to 2024, 7 deals reaching financial close under this facility have qualified for A&R. The pipeline of deals having passed first stage approval as of end 2024 also include 3 A&R qualified investments.
Development Impact of CIF investments is expected to be higher than the average for BII FT portfolio)	DI Score for CIF Investments is higher than for FT portfolio	Achieved. The 7 CIF deals committed in 2024 have an indicative average PSI score of 9.3. / All deals screened for Enhanced Development Impact.

Briefly describe the output’s activities and provide supporting narrative for the score.
The CIF deploys concessional finance (fiscal C-DEL) to support the scale-up of frontier technologies and business models in BII target geographies that are typically considered too risky for private investors. The CIF supports higher-risk, often smaller deals in climate innovations that developing countries critically need – including for adaptation and resilience. It invests in the most innovative opportunities by using concessional capital to address the higher risks and costs faced by first movers for nascent climate investments.
2024 was a good year for CIF, with a significant increase in the portfolio and pipeline and a strong demonstration of CIF’s additionality in highly impactful sectors and business models. Commitment pace has increased from four deals in 2023 to seven deals in 2024 and commitment value has grown by over 100% year-on-year to £24.3m. The CIF continues to be a high impact facility, with the average Impact Score of the CIF portfolio (closed deals) from 2021-2024 at 9.0 (out of a maximum of 10), comfortably above the figures for the Growth and Catalyst portfolio. 74% of 2024 commitments are in Africa, followed by 19% in India. 37% of African commitments are in West Africa, indicating a diversification of exposure of the CIF portfolio to additional African markets.
The CIF’s focus on adaptation and resilience has continued to strengthen, with 29% of the total portfolio (incl. exited deals) by value now qualifying as A&R. This equates to seven deals in the portfolio (incl. exited deals) are A&R, with four of these deals committed in 2024. There is correlation between A&R deals in the portfolio and reach to low-income populations indicating that some of these transactions are delivering a dual mandate of inclusion as well as climate impact. A key challenge in originating and executing more scalable A&R opportunities has been a lack of investable assets in the market. However, the CIF is well-positioned to be able to demonstrate a private sector case for A&R through its use of catalytic capital that allows it to take higher risk and invest through smaller ticket sizes.
Significant investments this year include:
- Green and inclusive growth: BII’s investment into Loadshare is helping to transform India’s logistics sector, creating jobs whilst cutting emissions. Loadshare is creating a nationwide network connecting small and medium logistics firms with local suppliers and rural customers enabling these smaller companies to have better market access, which in turn boosts their growth and creates jobs. With the loan from Kinetic, Loadshare will support smaller electric vehicle fleet owners and Loadshare's last mile logistics riders to access electric vehicles and overcome financing barriers.
- Strengthening adaptation and resilience: BII’s investment into the Blue Orchard InsuResilience Fund II is expanding access to climate risk insurance and helping millions of vulnerable people. Similarly, BII’s investment into SunCulture is strengthening the resilience of farmers in east Africa by expanding access to affordable solar-powered irrigation technology.
- Decarbonising Transport: BII’s investment into BasiGo to scale local assembly of electric buses in Kenya is helping to transition Kenya’s public transport from diesel-powered vehicles to modern electric buses. Each BasiGo electric bus deployed in Nairobi in place of a diesel bus avoids over 50 tonnes of CO2 emissions per year.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The next Annual Review should expand this output to include indicators covering the two new blended finance facilities - Mobilisation Facility and the African Resilience Investment Facility (ARIF) - which form part of BII’s Kinetic portfolio. See below for further detail.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendations:
      1. MEL (Monitoring, Evaluation and Learning): As an innovation-focussed programme, learning from innovations tested through CIF (both successes and failures), and disseminating this to build the knowledge base of the wider blended finance community, is a key part of the MEL approach. This focus on learning should be captured as a logframe indicator from next year.
Progress on recommendations:
There has been significant progress on the CIF MEL project, including appointing a third-party project team to develop a monitoring and learning framework for CIF. This has included developing a theory of change, key monitoring indicators, a consolidated monitoring dashboard and the development of a learning agenda for CIF. The first CIF learning case study was identified in 2024 and focuses on the use of flexible debt in the electric vehicle sector (published in 2025). Further case studies and evaluations will be developed in 2025. It was decided not to add MEL to the log frame as we are currently evaluating the best approach to capture MEL across the whole Kinetic portfolio now that ARIF and the Mobilisation Facility are operational.
Lessons Learned:
The CIF is unlocking investments in high risk, high impact transactions that BII would not otherwise pursue and is showing high additionality to both BII’s product offering and the market. 2024 saw many “firsts” for BII including the approval of CIF’s first standalone deals with ARC Ride and Grow Indigo. Project Development Loans (PDLs) were also introduced in 2024, with the first deal committed (a project development loan to support feasibility studies on a coastal development project in Nouakchott, Mauritania). PDLs enable BII to finance development costs for high-risk high impact, early-stage infrastructure projects. This contributes to unlocking a pipeline of bankable green infrastructure projects that would otherwise have struggled to obtain funding.
This year has also seen enhanced coordination between BII Plus and CIF in ways that have helped unlock investments for the CIF portfolio. For example, BII Plus has provided pre-investment advisory support to transactions in the CIF pipeline to strengthen financial models and explore new innovative financing structures. BII Plus has also supported existing CIF portfolio companies to enhance climate impact and improve operational efficiencies.
Going forward, BII will be managing two additional concessional finance facilities – in addition to the CIF - as part of the Kinetic portfolio. In particular, the Mobilisation Facility provides BII concessional finance to de-risk commercial investment at scale into climate and SDG-aligned assets in developing economies. The Africa Resilience Investment Facility (ARIF) provides BII with concessional finance to enable them to further scale investment in African low-income countries, particularly in the real-economy, thereby supporting BII to further extend its impact in some of the riskiest markets. While the impact objectives of each facility are distinct, there is also opportunity to share learnings and best practices across facilities – for example in approaches to minimising concessionality and/or in development of TA interventions for early-stage companies across CIF and ARIF.
Recommendations for 2025:
1. Update output 5 in the log frame to cover the whole Kinetic portfolio, therefore capturing indicators related to ARIF and the Mobilisation Facility.
2. Learn lessons from BII’s two new concessional finance facilities – ARIF and the Mobilisation Facility – to support discussions on BII’s next five-year strategy.
3. Continue to support the strengthening of the A&R investment pipeline, as well as capturing and disseminating BII’s learning through Monitoring, Evaluation and Learning (MEL) activities under the Climate Innovation Facility (CIF).

Output Title	High impact support provided to BII’s portfolio companies, new high impact investments unlocked, and specific contributions made to building the broader field of impact investing.
Output number:		6	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# of projects approved and under management aimed at enabling and extending the development impact of investees.	Growing number of projects approved / 2023: 53	Moderately did not meet expectation. 53 projects approved in 2024
# of deals enabled through BII Plus TA (by BII and non-BII deals).	Start rolling out pre-investment TA projects across BII Plus programmes	Achieved. 8 pre-investment TA projects rolled out in 2024.
# of market shaping or country programmes approved and under management that seek to resource and scale new approaches to responsible and equitable private sector development.	Extend BII Plus’ country programmes	Achieved. 2 country programmes extended until 2026
[note] BII Plus has now introduced a new Fluxx-based grant management system which allows for better integration and tracking of projects. Overall figures for projects approved in 2024 have gone up since its introduction and BII will report restated figures for 2024 in next year’s annual review.

Briefly describe the output’s activities and provide supporting narrative for the score.
BII Plus is BII’s Technical Assistance (TA) Facility, focussed on 1) enabling BII to deepen the impact of its investments at a business level, 2) unlocking new and high-impact investment opportunities for BII and other, like-minded investors, and 3) supporting field building activities in order to better catalyse economic growth.
A total of 53 projects were approved in 2024, of which 41 projects supported investees in BII’s portfolio, eight were pre-investment technical assistance projects, and four were field-building projects that addressed critical ecosystem barriers. BII Plus delivered on the output indicators above, increasing the number of projects approved, pre-investment TA programmes rolled out (which is central to building a pipeline of investable activities), and extended its deep offer through two country programmes. This ensured a relatively balanced portfolio of BII Plus activity across different types of intervention.
In 2024, BII Plus approved £12.55 million of funding across three new thematic programmes— the ESG Technical Assistance Programme, the Gender & Diversity Advisory Programme, and the Climate & Environmental Advisory Programme and two country programmes – the Africa Resilience Investment Accelerator (ARIA) and the Ghana Investment Support Programme - were extended through to the end of 2026.
Across the whole portfolio of BII Plus’ TA interventions, the latest BII Plus semi-annual review report outlines a robust set of output activities focused on delivering technical assistance (TA) across financial inclusion, climate resilience, and gender equity. Key outputs include support to 190 investees, training for over 15,000 individuals, and the enablement of $275 million in deals. The programme also supported 32 innovations and achieved 65 market-shaping outcomes. Progress is strong in areas like TA delivery and innovation support, with most KPIs on track or achieved. However, targets related to unlocking climate finance and reaching underserved customers are currently off track for instance in its FSG Plus programme, indicating areas for strategic focus and improvement in the coming quarters within specific programmes.’
 More broadly under its Country Programmes, BII Plus continued to unlock investment in frontier markets and foster DFI collaboration. ARIA supported BII’s $25 million investment in Ecobank Sierra Leone through transaction origination and due diligence. The Ghana Investment Support Programme contributed to strengthening Ghana’s investment ecosystem, including through supporting the Ghana Venture Capital and Private Equity Association (GVCA)’s investment readiness programme, which has reached 35 SMEs with backing from Deloitte, KPMG, PwC, and EY. Invest for Impact Nepal (IIN) placed strong emphasis on ESG technical assistance for financial institutions and PE/VC funds through its partnership with One to Watch (OTW). OTW primarily engaged with IIN to support ESG integration, fundraising strategy, pitch deck development, and taxation guidance.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to this output over the past year, and none are planned following this year’s review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Last year’s recommendations:
1. BII Plus to provide FCDO with Semi Annual Reviews (SAR) that details activities, highlights and Facility level results achieved, so FCDO deepens its understanding of BII Plus activities.
2. BII Plus provides FCDO with regular sight of its activities and results achieved through ongoing coordination.
Both of these recommendations have been implemented, with BII Plus providing semi-annual reviews to BII, and the regular meetings between FCDO and BII providing FCDO with better sight of BII Plus activities and results (including an FCDO representative attending the BII Plus Committee meetings).
Lessons learned
BII Plus has adopted a programmatic approach to deepen BII portfolio’s impact around ESG, climate and inclusion themes. This approach has been helpful to drive a more coherent and coordinated set of projects focused on specific impact priorities - for instance, through projects which have successfully supported access to essential services for last mile communities, helped with physical climate risk measurement for at-risk small agribusiness, or through supporting innovations to improve water circularity. While this is effective to pursue thematic priorities, there are key challenges around scalability and operational efficiency which will be crucial to address in order to unlock further impact moving forward.
Since the introduction of pre-investment TA into BII Plus’ remit, there has been an intentional and steady growth of projects. Pre-investment support has primarily focused on targeted projects rather than exploratory initiatives. These efforts have been aimed at helping companies structure their deals and enhance execution capabilities through deal teams. For example, for Etana Energy, a new energy trading company incorporated in South Africa, BII Plus provided support for an independent market aggregator study. This study synthesised lessons learnt from global case studies to contextualise South Africa’s evolving power sector and played a key role in unlocking investment opportunity for BII.
Recommendations for 2025:
            1. BII and FCDO to identify opportunities for alignment with other HMG funded technical assistance programmes such as on project preparation and upstream advisory facilities.

            1. Monitor progress on achieving targets set within BII Plus' programmes'

## D: VALUE FOR MONEY (VfM)
Key cost drivers and performance
BII operates in a cost-efficient manner relative to the size of its investment portfolio and relative to other DFIs. Its operating costs are covered by returns from investments and not by additional FCDO funding – representing good value for money. Operating costs for 2024 increased in nominal terms to £151.6 million (2023: £146.2 million), but remained well within the agreement for BII to keep operating costs within 1.7% of its portfolio plus unfunded commitments, at 1.5%. This increase in operating costs was driven by employee numbers rising to 657 at year-end (2023: 606).
VfM performance compared to the original VfM proposition in the business case
BII tracks returns in US dollars meaning results can be significantly impacted by changes in the sterling to US dollar exchange rate. In dollar terms, the portfolio generated a gain of 3.3% in 2024, as a result of some positive macroeconomic performance across BII markets, although this remained below the 2023 return of 5.2%. In GBP terms, BII’s portfolio generated a £317m return (4.3%), up from £71.5m (1.1%) in 2023.
As BII is a long-term investor, it is important to look across multiple years for trends, understanding that in any isolated year, market conditions, such as currency fluctuations may cause significant variation in annual results. In line with BII’s 2022-26 strategy BII is seeking returns of 2% or higher across the portfolio, measured on a weighted average basis over a rolling seven-year basis. BII is ahead of this benchmark, with the seven-year weighted average annual portfolio return standing at 5.1% at the end of 2024. BII have predicted its portfolio return will fall over time due to its challenging mandate working in some of the most fragile and poorest countries in the world. It remains the case that adopting a more targeted developmental strategy in 2012 – involving a narrower geographic mandate and a higher risk appetite – has led to lower returns and increased volatility.
BII is making good progress towards its 2022-26 strategic objectives. In 2024, BII met its 2022-26 strategic target to ensure 25% of new investments qualified for 2X (demonstrating delivery against equity VfM), with 29% fitting the criteria (2023: 25%). BII is also on track to meet its COP26 commitment to invest £3 billion in emerging economies to help combat the climate crisis, committing £708 million in 2024 (2023: £448.6 million), increasing the climate finance assets in their portfolio to £1,970 million (2023: £1,715 million).
The Catalyst portfolio continues to represent good value for money by seeking out investments that unlock additional development impact. BII’s 2022-2026 strategy aims to expand the Catalyst portfolio as a proportion of BII’s total portfolio to 10-15% by 2026. The Catalyst portfolio represented 13.5% of BII’s total portfolio at the end of 2024 (2023: 12%). With developing countries continuing to be impacted by the Ukraine conflict, and wider global shocks and conflicts, Catalyst’s higher risk appetite remains a critical offering, reflecting BII’s appetite for development impact in hard-to-reach geographies and pioneering markets.
Assessment of whether the programme continues to represent value for money
Based on the above VfM analysis, progress in delivering outputs and outcomes, and alignments with the theory of change, we assess that BII continues to represent good value for money. FCDO strongly supports the continuation of BII’s activities in accordance with its five-year strategic priorities, and we are already seeing the strong development impact of BII’s provision of targeted investment to partner companies, responding flexibly within its mandate. BII’s operating model – deploying capital to deliver development impact and grow its resources over time – does not require perpetual taxpayer funding and represents good VfM, with capital FCDO invests being regularly recycled and reinvested into new deals by BII, thereby multiplying the effect of every taxpayer pound to generate further impact.

E: RISK
Risk Appetite
Table 2: Risk appetite and areas of pressure
Risk category	Risk Appetite	Residual Risk	Areas of pressure
Strategy and Context	Receptive	Receptive	BII programme risk appetite is in line with FCDO risk appetite.
Policy and Programme Delivery	Receptive	Receptive	BII programme risk appetite is in line with FCDO risk appetite.
People	Cautious	Cautious	BII programme risk appetite is in line with FCDO risk appetite.
Public Service Delivery & Operations	Cautious	Cautious	BII programme risk appetite is in line with FCDO risk appetite.
Safeguarding	Cautious	Cautious	BII programme risk appetite in line with FCDO risk appetite.
Financial & Fiduciary	Cautious	Cautious	BII programme risk appetite in line with FCDO risk appetite.
Reputational	Cautious	Receptive	BII activities carry distinctive reputational risks (e.g., BII supports businesses that could fail, or if successful, might make large profits - both outcomes could lead to public scrutiny), but we work closely with BII to proactively mitigate these reputational risks (e.g., the No Surprises policy).

We have a risk appetite specific to the BII programme which confirms we accept a higher level of residual risk in the Reputational category as part of expected programme delivery. Alongside this, we will continue to ensure sufficient sources of assurance over these risks are determined by the BII shareholder team. We have been able to comfortably deliver within the risk appetite in the other categories.
Table 3: Summary of major or severe residual risks
Risk	Gross risk	Mitigation	Residual risk
Macroeconomic and other external conditions limit the pipeline of investable deals, affecting BII's ability to deliver $10-12bn of investment targeted over 5-year strategy period.	Severe	Recent and planned growth in BII is designed to support an increased investment pace. Commitment pace and cashflows are monitored and reported to ExCo on a regular basis to allow for early identification of areas where business plans by product may need adjustment. BII has also strengthened its investment teams - organised along sector lines. BII is recruiting regional and country-based investment officers to build the networks required to identify relevant opportunities and oversee portfolios.	Major
Risk that under-performance or breaches in compliance with the Policy on Responsible Investing result in significant Environmental and Social (E&S) harm in or by BII investee companies.	Major	BII has a Policy on Responsible Investing, agreed with FCDO, which reflects international standards and practices and which has been strengthened to include modern slavery, sexual harassment and animal welfare. BII has a dedicated responsible investing team who risk assess each investment and provide ongoing monitoring based on the results of this risk assessment. BII's processes are designed to mitigate, not eliminate the risk of significant E&S issues occurring. The residual risk is managed by investee companies and fund managers as well as BII's investment and E&S teams.	Major

Risk management
BII is structured as an operationally independent public company in order to: (i) ensure that the BII Board is accountable for delivering objectives agreed with FCDO; and (ii) demonstrate to the markets that BII’s investment decisions are commercially driven and are independent of political involvement. This arm’s length arrangement is set out clearly in BII’s governance documents (The Act, Articles, MOU, Chair’s letter, and Investment Policy).
FCDO holds quarterly shareholder meetings (QSMs) with the Chair, CEO and other members of BII’s top management team to exercise ongoing oversight. BII formally reports to FCDO on risk management via the quarterly shareholder meetings (QSM). FCDO also holds Quarterly ESG meetings which provides the specific opportunity to monitor and hold BII to account for implementation of their ESG requirements and discuss the top business integrity and ESG risks across the portfolio. Additionally, the FCDO’s risk register for BII is updated on an ongoing basis. FCDO also obtain assurances from the Board and meets with the chairs of Board level Committees (including RiskCo) at least once a year to review high level risks and how they are being managed.
Key developments in 2024
The annual meeting of FCDO with BII Audit and Compliance Committee Chair took place in December 2024. BII updated FCDO on the BII Audit Committee framework and structure and gave a summary of work over the past 12 months and plans for the next year. BII also updated FCDO on BII internal and external audit including progress in implementing recommendations from the 2023 Deloitte Audit in which good progress has been made. FCDO reviewed BII Audit and Compliance Committee oversight, and gained assurances over BII’s internal control environment, valuation methodology and compliance systems.
In 2024, BII’s risk team developed a framework to identify, assess and manage model risk and enhanced risk-related processes including its stress testing methodology and Country Risk framework. BII also continued work to refine climate risk assessment methodologies and embed climate risk management across its Risk Appetite Framework.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
BII has the appropriate commercial expertise and track record of investing in businesses in developing countries. There is a positive, professional relationship between the FCDO team in the Development Finance, Infrastructure, and Partnerships Department (DFIP) that manages the Shareholder relationship and the Board and management of BII, with all parties clear on the terms and aims of the relationship and their mutual responsibilities. Frequent informal meetings take place between formal Quarterly Shareholder Meetings to ensure an open two-way exchange of information. We receive regular reporting (including on liquidity ratios, operating cost ratios, and disbursement and receipt volumes) as part of the formal governance arrangements.
In 2024, FCDO invested an additional £1,160 million of capital in BII through four new Promissory Notes (including a £60m Promissory Note for BII to expand into Ukraine in September). BII encashed three Promissory Notes in 2024 (two of which related to Promissory Notes that were lodged prior to 2024) to meet its funding commitments (see summary table below). Due to the highly illiquid nature of BII’s assets, BII’s liquidity policy currently is to maintain two ratios: (i) to hold less than 10% of Cash to Net Asset Value (NAV) – this ensures BII is not holding an unnecessary amount of cash; and, (ii) hold more than 100% Collateral Coverage Ratio (CCR) - a new metric introduced in 2023 that more accurately measures the ratio of the collateral BII has available to how much collateral it needs to meet projected cash flows (current undrawn contractual investment commitments and forecasted future commitments). The Collateral BII has available consists of cash, undrawn promissory notes, and their borrowing facility. FCDO regularly monitors BII’s cashflow requirements, in line with their liquidity policy, for existing commitments and new deals in the pipeline to ensure that amounts are only drawn down as and when required in response to demand.
Table 4: Summary PN’s lodged and cash drawdowns
Date	Promissory Notes / £m	Cash Drawn Down / £m
January 2024		30
February 2024	280
March 2024		130
April 2024		129.5
September 2024	480
December 2024	400	60
Total	1,160	349.5

Asset monitoring and control
BII’s financial returns and Impact scores are both audited by independent external experts (Deloitte and PWC respectively). For the purpose of recording the value of our investment in BII in FCDO’s Annual Report and Accounts (ARA) as of 31 March, FCDO uses the net asset valuation of BII as per BII’s ARA as of 31 December adjusted for material changes in the first quarter to 31 March.
FCDO is focused on working with BII to ensure that BII achieves value for money for the taxpayer. BII’s finance function oversees cost control according to annually set budgets for operational expenses and asset purchases. Annual budgets are approved by the Board and the finance function coordinates with all departments to establish the forward cost plan and identify efficiency savings.
G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
This programme is monitored in line with corporate governance arrangements between FCDO and BII, with the FCDO receiving regular reporting on BII’s performance including through quarterly and annual shareholder meetings. Key performance indicators (“KPIs”) cover the development impact and financial performance of BII’s portfolio. Together they allow FCDO to track BII’s financial and operational health, the structure of BII’s portfolio and the development impact of investment activities. These KPIs are aligned with FCDO-wide reporting metrics including those for International Climate Finance and FCDO Growth and Investment Partnerships.
Other sources of information include internal and independent evaluations and reports by organisations, such as the Independent Commission on Aid Impact and the National Audit Office. The FCDO undertakes annual reviews of BII to assess performance in compliance with FCDO requirements, which supports the development of specific recommendations to take forward with BII over the following year.
Evidence & Learning
An enhanced and systematic focus on evaluations and learning was launched in late 2017, to provide accountability to the taxpayer and deepen FCDO and BII’s knowledge of the best ways to support long-term positive change through development finance. This has produced publications evaluating the entirety of BII’s infrastructure, financial services and ITS (Industries, Technology, and Services) portfolios. Further evaluations are being developed to better inform FCDO and BII of the latter’s development impact under its new strategy and garner further lessons from its portfolio, and an updated approach to evaluation and learnings will be considered as part of the next BII strategy period. The strands of this work cover:
FCDO commissioned sector studies - these large multi-year sector studies cover BII’s three sector groups: Financial Services, Infrastructure; and ITS (Industries, Technology and Services). They focus on BII’s development impact above and beyond the impacts being tracked for individual investments. Reviews of all three of these portfolios have been completed and are now publicly available
[note] https://www.bii.co.uk/en/our-impact/how-we-learn/

  1. FCDO-commissioned in-depth studies – these thematic and investment studies provide insights into the actual or likely development impact of BII’s investments, generating useful learnings about innovative business models and strategies. In 2024, the ‘FCDO/BII Financial Services (FI) Evaluation: Final Synthesis’ was published, which presents the combined findings and lessons from an initial portfolio-wide review of BII’s financial services sector investments and five subsequent in-depth studies, highlighting how BII’s financial services strategy has respond to the initial portfolio review through more targeted lending and a greater focus on underserved markets.

  1. Insight studies – These studies and evidence reviews enable BII to enhance its understanding of how impact is created at strategic, thematic, or investment level beyond the FCDO commissioned sector and in-depth studies detailed above.
  2. FCDO commissioned 10-year longitudinal evaluation on mobilisation of private sector capital. The study aims to help BII and FCDO learn about the most effective means of mobilising private finance in different contexts, enabling them to improve strategic choices and maximise their influence and mobilisation activities via a series of think pieces, data analysis, learning reviews and evaluative case studies.
  3. Impact Research Challenge Fund – FCDO and BII have partner with the Centre for Economic Policy Research (CEPR) to run a financing window in the Private Enterprise Development in Low-Income Countries (PEDL) programme, which was consolidated into the Growth Research Platform (GRP) in 2024, to support new research that fills critical evidence gaps related to the work of BII and the impacts of private sector investment in developing countries
Date of last narrative financial report	17 April 2025	Date of last audited annual statement	17 April 2025