Title: Risk Pools Programme (RPP)
Programme Value £ (full life): Up to £100 million		Review date: March 2025
Programme Code: 203469	AMP start date: 13/03/2014	AMP end date: 31/03/2044

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	B	B	A	B
Risk Rating	Severe	Severe	Severe	Severe	Severe	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/4643483.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/90000093.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

In March 2014, the UK Department for International Development (DFID), now the Foreign, Commonwealth and Development Office (FCDO), approved support of up to £100m over 20 years to launch an African risk insurance pool – African Risk Capacity (ARC). Risk pools are fundamental in building the capacity of governments in low- and middle-income countries to respond to increasingly common and severe climate events, where only 5% of financial losses from disasters are absorbed by insurance, to utilise risk transfer mechanisms but also help lower premium costs via risk pooling and risk diversification.
[note] Cummins, D.J. & Mauhl, O. (2009). Catastrophe Risk Financing in Developing Countries.
The £100m Risk Pools Programme (RPP) business case includes £10m of grant funding, which was fully disbursed to ARC Agency by 2019/20, and £90m in development capital, the first £30m of which was invested in ARC Ltd in 2014 as a 20-year interest free returnable grant, which was matched by Germany’s KfW.
ARC includes ‘ARC Agency’, established as a specialised agency of the African Union (AU) and ‘ARC Ltd’, an affiliate mutual insurance company. ARC Agency provides technical assistance to countries to help strengthen their disaster risk management systems. ARC Ltd, through its regional risk insurance pool, provides access to rapid and predictable finance following a disaster to protect lives and livelihoods in African member states. ARC provides sovereign policies to ARC member states and ‘replica’ policies to humanitarian actors; WFP, START and UNHCR. ARC also offers ‘non-sovereign business’, which includes underwriting of World Bank programmes such as the Shock Responsive Social Protection in Malawi.
Although FCDOs development capital is invested in ARC Ltd, the success of the intervention depends in part on ARC Agency’s work to enable African countries to manage and respond to disaster risks effectively. ARC Agency activities that directly affect the ability of ARC Ltd to grow its business and deliver its services (e.g. country engagement) are also considered by this review.
In April 2021 a business case addendum expanded the geographic coverage of the Risk Pool Programme beyond Africa, enabling FCDO to make an investment in the Caribbean risk insurance pool – Caribbean Catastrophe Risk Insurance Facility (CCRIF). In September 2023, a $25m development capital investment was made in the Caribbean Water Utilities Collective (CWUIC) via CCRIF. CWUIC offers risk reduction planning and resilience-building investments to strengthen water and sanitation services in the Caribbean, as well as insurance through the Caribbean regional insurance scheme. The first insurance policies were sold in June 2024, to Dominica, Grenada and Belize. A payout to Grenada was made in July 2024 in response to Hurricane Beryl.
Summary supporting narrative for the overall score in this review
This Annual Review, covering ARC and CWUIC as a combined Regional Risk Pools programme (RPP), is scored ‘B’, meaning that overall outputs moderately did not meet expectation.
Below average rainfall driven by the El Nino cycle resulted in large ARC payouts (over $62m) in southern and eastern Africa. Whilst these payouts demonstrate the important role risk pools and pre-arranged finance can play, they have significantly reduced ARC’s capital base.
The in-year impacts have exacerbated pre-existing challenges to ARC’s capital base and the amount of cover ARC is able to offer member states. Delays with the development of new products have left some countries unable to access the cover they require. Similarly, growth in membership has been slow. Although new products might not directly lead to capital growth, delays reduce ARC’s ability to diversify their risk exposure.
ARC have been unable to gather payout monitoring data at the level FCDO feels is required to maximise learning, including on payout impact on vulnerable communities. Whilst this is in part due to data limitation across Africa, strong Monitoring Evaluation and Learning (MEL) is critical for innovative interventions such as ARC and needs to be prioritised. MEL is also a key tool for ARC to expand its membership as, without it, it will be difficult to demonstrate that countries should divert funds from fiscally constrained budgets.
After several years of preparatory activities led by the Inter-American Development Bank (IDB) and the Caribbean risk pool CCRIF SPC, the UK invested $25m to capitalise CWUIC on 8 September 2023. Three policies were sold in June 2024, with up to 10 policies expected to be offered in 2025. The CWIUC Management Committee has been established and met three times in 2024 with full C-suite attendance, and the CWUIC working group has provided strong support to CWUIC as it begins operations. The Output has been scored as A (met expectations) overall with an impact weighting of 40%.
An investment of £5.3m into the Pacific Catastrophe Risk Insurance Company (PCRIC) was made in March 2025, just within the scope of this review period. Its performance will be covered by subsequent reviews.

Major lessons and recommendations for the year ahead

Effective MEL is key to demonstrating the value of ARC and effectiveness of ex ante responses to disaster risk.

The increasing frequency and intensity of climate disasters is part of the rationale for ARC, but the changing risk profile makes modelling harder and therefore poses a significant challenge. Capital erosion will remain a persistent risk because of this, and a risk management strategy that reflects this will become increasingly important.

Based on our interviews and the information reviewed, we make the following key recommendations. Other recommendations can be found under each output assessment section.

Key Recommendations	Target Date
ARC should prioritise and allocate resources for Monitoring, Learning and Evaluation and should use this as a tool for improving the programme and leveraging growth in membership and donor finance.	January 2026 in advance of pool 13
FCDO should include PCRIC in next year’s Annual Review and Logframe to fully reflect the expansion of the RRP Programme.	September 2025
ARC should review and update its risk and reinsurance strategy to reflect the growing uncertainties associated with climate change. This will help safeguard against future financial losses and enhance its attractiveness as a viable investment opportunity. The review should be conducted with technical support from the UK Government Actuary’s Department (GAD).	June 2025 following the publication of the 2025-29 strategy

CWUIC
Business Development / CWUIC needs to continue to grow its client base, with more policy sales and new products (hurricane, runoff, drought). CWUIC and CCRIF should prioritise business development, using the early payout for Grenada for Hurricane Beryl to demonstrate the value proposition.	Updated Business Plan agreed by May 2025. / Up to 9 policy sales for 2025/6 policy year.
Fund-raising / It is important that additional fund-raising (including climate finance) continues for CWUIC. CWUIC, IDB and CDB to agree with members how to approach the Green Climate Fund (GCF).	GCF Information Note to be agreed between CWUIC, member countries, IDB, CDB and GCF by March 2026.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change (ToC), including any changes to outcome and impact indicators from the original business case.

The business case’s theory of change highlighted three key elements in supporting development insurance as outlined below. The theory of change and assumptions remain valid.
Early responses to drought to protect livelihoods is the first underpinning theory i.e. households are supported before they have to reduce food or sell their productive assets. ARC is index linked and provides payments earlier than a humanitarian response could and before ongoing development support could be scaled up. However, these payments need to be in support of a sound plan, the funds need to flow to the right instruments and benefit the right people.

Changing incentives for risk management. This is at the heart of the value of this programme i.e that by valuing their extreme weather risks for insurance, African governments become aware of the costs they face with each drought and are motivated to reduce these risks as far as they can and transfer the residual risk to a reasonably priced insurance policy.

Membership to ARC conditional on strong contingency plans. ARC requires countries to identify the right risks to transfer and to have strong contingency plans in place before they can join ARC. Through the pre-participation period, they will be supported to build the skills in risk assessment and in contingency planning – and through an effective monitoring process, they should gain further skills from the process and identify for themselves the evidence for the most cost-effective early responses in the event of drought.

The programme’s outcome and impact indicators have been revised to reflect the recent expansion of scope to include the Caribbean Regional Risk Pool; and removal or revision of indicators bringing the FCDO log frame in line with ARC Group’s log frame. This should facilitate easier monitoring and evaluation of performance going forward.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Despite challenges identified in this review, particularly in relation to ARC, the programme continues to make progress (increasing financial resilience to disasters). Experience to date has shown that pre-positioned finance, disbursed according to pre-agreed triggers and pre-approved contingency plans supports countries to better identify and manage their climate risk and deliver a timely response to disasters.

Impact – Countries are better able to manage climate risk as result of transferring climate risk to the regional risk pools.
Outcome – Increased risk pool coverage to expand climate risk insurance and increase financial resilience to disasters.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

In 2024 ARC made $84.8m of payouts and a total of 16.1m people were covered by insurance policies taken by member states and Replica partners. Out of the 53 policies, 29 (55%) were taken by the governments, 24 (45%) were taken by Replica partners (WFP, Start Network and UNHCR). Seventeen countries (Cote d’Ivoire, Mauritania, Burkina Faso, Mali, The Gambia, Togo, Somalia, Malawi, Madagascar, Zambia, Zimbabwe, Somalia, Comoros, Mozambique, Lesotho, Benin, Ghana) participated in risk pool 11 through sovereign and/or Replica policies. Total coverage was US$160m. Lesotho, Benin and Ghana participated in ARC risk pools for the first time.

During this review period, ARC has also seen its membership remain at 39 countries and total number of countries with ratified treaties has risen to 15, with the inclusion of Djibouti, Zambia and Zimbabwe.

2024 was CWUIC‘s first year of active insurance and saw early payouts in response to Hurricane Beryl. The water utility companies of three countries (Grenada, Dominica and Belize) were insured through CWUIC, with $2.2m paid out to Grenada’s water utility company NAWASA for response and recovery after Hurricane Beryl.
The headlines above demonstrate that RPP investments are providing broad coverage and enabling significant payouts in relation to climate risks in Africa and (through CWUIC) the Caribbean.

## C. DETAILED OUTPUT SCORING

Output Title	African Risk Capacity (ARC) - Increased capacity of ARC member states to identify climate risk and transfer climate risk to the risk pool. Improved capacity of ARC member states to implement payouts in a timely manner according to pre-approved contingency plans.
Output number:		1	Output Score:	C
Impact weighting (%):		20%	Weighting revised since last AR?	No.

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of ARC Member States that have a valid Certificate of Good Standing (CoGS).	22 Member States	Partially met. 20 out of 22 member states received a Certificate of Good Standing. All eligible countries currently are in good standing except for countries under sanctions.
1.2 Number of country strategy papers finalised and incorporating gender dimensions.	18 Country Strategy Papers	Not met. 6 out of a targeted 18 country strategy papers were finalised.
1.3 Ave no. of days between ARC payout trigger and start of the implementation of the response.	120 days	Not Met. There is delay in the response in Mozambique, Zambia, Zimbabwe and Malawi, which has taken implementation beyond the set standard.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output considers how ARC’s activities contribute to its member states’ ability to identify, manage and respond to climate risks. The first output indicator relates to ARC Agency’s activities in developing the capability and capacity of members states enabling them to meet the necessary requirements to be eligible to purchase ARC insurance policies. The second output indicator relates to ARC Agency’s process for identifying and engaging with countries to deepen their understanding of the various climate risks faced. These activities have a direct impact on ARC Ltd.’s ability to sell insurance products.

The third output is about equipping member states to respond more quickly to climate disasters than would be expected from international humanitarian actors. This means that ARC Ltd must be able to make a payout as soon as insurance is triggered, but also that governments have the systems in place to receive a payout and action its implementation plan. This relies on ARC Agency working effectively with the government to ensure that the final implementation plan that has been developed is feasible in the first instance.

During this review period twenty countries had a Certificate of Good Standard having met the requirements to purchase ARC insurance policies: Burkina Faso, Benin, Kenya, Madagascar, Malawi, Mali, Mauritania, Mozambique, Niger, Senegal, Chad, The Gambia, Ghana, Cote D’Ivoire, Zambia, Togo, Sudan, Somalia, Zimbabwe and Comoros. While this is below the 22 member states target, there are extenuating factors within some member states that prevent ARC from going to some countries to conduct an assessment of good standing.

A Country Engagement Committee was formed to support ARC’s growth ambitions and met four times in 2024. Country Strategy Papers outline ARC’s ambition for engaging with member countries, encompassing development goals, priorities, strategic objectives, and action plans. At the end of 2024, 6 Country Strategy Papers out of an annual target of 18 were developed for Madagascar, Senegal, Mali, Mauritania, Burkina Faso and The Gambia, while five are awaiting final approval, meaning that this target has not been met. More positively however, ARC’s 2024 Annual Report, reported that all 20 approved operation plans in 2024 were gender sensitive. The plans included gender sensitive targeting and monitoring (plan to report on sex disaggregated data where available) and gender equitable activities. This reflects growing awareness of gender issues and increased commitment to mainstream gender within the ARC disaster risk management process.

Indicator 1.3 which measures the timeliness of the payout by ARC Ltd and the start of implementation could not be measured, but ARC have confirmed that the payout period has gone beyond the set standard of 120 days. The reason this could not be measured was due to delays in some responses (Mozambique, Zambia, Zimbabwe and Malawi). As ARC report on actuals, this indicator will only be available once all implementations have kicked off and at the time of undertaking this review, some implementations were yet to begin.
Oxford Policy Management Evaluation (published October 2024)

OPM conducted an independent evaluation that was published in October 2024. The evaluation highlighted progress on coordination and response planning but also highlighted gaps (also reflected in this Annual Review) in relation to timely delivery of assistance and monitoring and evaluation.

The link to the full report can be found here: https://www.opml.co.uk/sites/default/files/2025-02/arc-ia1-evaluation-report.pdf

Given the above evidence, this output has scored a C. We believe there is room for improvement, particularly with respect to MEL. It is imperative that this activity is prioritised.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key Recommendations	Progress
Post payout evaluations are critical to protecting ARC against fiduciary and reputational risks; learning lessons to feed into the iterative contingency plan drafting process; and for gathering evidence of impact to share with donors providing funding. Therefore, imperative that ARC embed a sustainable post payout evaluation process and ensure that it is implemented.	Partially Met. For the period in question, the OPM evaluation reports that the payout assessments in Mauritania, Malawi, Togo and Zambia were made available. While this is progress, these evaluations should be carried out following each payout to ensure effective targeting and lesson learning. ARC cite budget constraints as the reason these are not carried out routinely.
ARC should use lessons from the current post payout evaluation pilots to engage donors in discussion and agree on what a “good enough” process, which is more cost effective and feasible in hard to access countries, could look like for post payout evaluations.	Not Met. Due to lack of progress with post payout evaluations, there has been no discussion with donors on what a “good enough” process would be.
ARC should work with the Government of Madagascar to expedite the implementation of the 2022 Tropical Cyclone Batsirai Payout and the payment of the 2023 Tropical Cyclone Freddy Payout. The payout should have been used to support vulnerable communities to respond to the disasters in a timely manner.	Met. The payout has now been implemented.

Reviewing last year’s recommendations and based on observations during this annual year process, Post Payout evaluations continue to be as crucial as they were in the previous year, therefore we make the following recommendation:

Recommendations for 2025
ARC should continue to prioritise post payout checks, (financial reconciliations, process audits) for all payouts and ensure sufficient budget allocation for this vital evaluation function. Learning should be shared in a timely manner to inform future iterations of contingency plans. This recommendation reflects a need to continue to deliver against the recommendation included in last year’s annual review

Output Title	African Risk Capacity (ARC) - ARC Group is well governed and managed and is delivering effectively and efficiently on its mandate.
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No.

Indicator(s)	Milestone(s) for this review	Progress
2.1 Auditors sign off unqualified audit for ARC Ltd.	Yes	Met. The most recent annual audit from year end 2023 is unqualified. The annual audit for 2024 is not yet complete because of timing of this AR.
2.2 Percentage of ARC Group Board Actions completed within agreed time frame.	85%	Not met. The information obtained by the FCDO showed that this was considerably below the intended benchmark.
2.3 Percentage of matters arising on ARC Ltd Board dashboard resolved within agreed time frame.	85%	Met. 90%

Briefly describe the output’s activities and provide supporting narrative for the score.

ARC Group is governed by the Conference of Parties (COP) comprised of ARC member states under the ARC Treaty. The ARC Group Board is responsible to the ARC COP. ARC Group Board is comprised of representatives nominated by the African Union Commission, by member states, and by partners (including FCDO represented at Director level). ARC Ltd Board is separate to the ARC Group Board. ARC Ltd Board directors are appointed by a nominations committee comprised of representatives of Class A and Class C members. Class A members are countries with an active policy. Class C members are development partners. The Chair of ARC Ltd Board sits on ARC Group Board. Finally, ARC Group and ARC Ltd Boards both have committees that oversee various workstreams including peer review mechanism, product development, and most recently country engagement.

ARC Group Board (as well as the committees of the Board) is responsible for setting strategic direction for ARC Group. The ARC Group held 3 regular sessions and one extraordinary session in 2024. Key recommendations from the OPM formative evaluation were considered and prioritised for action in light of budget constraints and have fed into the development of the new ARC Group strategy 2025-2029, which is awaiting approval by the CoP. The OPM recommendations include improvement of the drought response and Replica expansion. The ARC Group Board also adopted several key recommendations fed in from donor partners and have reflected them in the new Group Strategy. This includes review of ARC’s value proposition and a study of ARC Group Financial Sustainability.

While the Boards and committees are proactively identifying measures to improve their functioning, Board actions are not consistently being completed on time. Therefore, though ARC met two out of the three output indicators, the completion of ARC Group Board actions (indictor 2.2) fell significantly short of the target. For this reason, we have scored the output with an overall B which indicates the output was moderately not met.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key Recommendations	Progress
ARC should continue to use the recommendations from the OPM formative evaluation and their corresponding action plan to drive improvements and reform across ARC Group.	Ongoing. Selected OPM recommendations will be incorporated into ARC Group’s 2025-30 strategy.
In consultation with ARC Group, FCDO to revise the log frame to align with ARC’s own log frame. This will predominantly cover ARC Ltd indicators but will include ARC Agency indicators which affect the UK’s investment and the ultimate objective of maximising coverage for vulnerable populations.	Ongoing. FCDO agreed a revised log frame with ARC Ltd which has been signed off by the FCDO Director. However, ARC Group will develop a revised log frame for the next 5-year strategy from 2025-2029. FCDO alongside other partners should engage with this process to ensure the log frame reflects key areas for ARC.
ARC Group Board should use the next three-year board term to improve the Board working as informed by the Board Evaluation with a particular focus on timely implementation of actions.	Ongoing. The FCDO team should continue to press for progress in accordance with the Board Evaluation.
FCDO alongside other partners should engage with the next five-year strategy from 2025-29 and the development of the accompanying log frame.	Ongoing. The development of the strategy has been slightly delayed; however, it is likely to be approved by the CoP in April 2025.

Below is a summary of recommendations for 2025.

Key Recommendations
FCDO, in collaboration with the ARC Group Board, should continue to focus on strengthening timely implementation of agreed Board actions. Given how integral the new Group Director General (GDG) will be to strengthening ARC Group governance, the FCDO should engage early with the incoming GDG to offer support and progress this recommendation.

Output Title	African Risk Capacity (ARC) - Strengthened financial stability of ARC Ltd and growth of ARC capital base to ensure long term sustainability of ARC Ltd risk pool to provide climate risk insurance. Increased credibility of ARC products and elimination of basis risk events.
Output number:		3	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No. Log frame revised with new outputs since last AR.

Indicator(s)	Milestone(s) for this review	Progress
3.1 ARC Ltd financial indicators: Net profit / loss	2m USD	Not Met. 34.5m USD loss
3.2 Total premium income / 1) sovereign / 2) replica / 3) IIB (previously NSB)	1) 38m USD / 2) 3m USD / 3) 10m USD	Not Met. 1) 19.2m USD / 2) 13.8m USD / 3) 5.7m USD
3.3 Percentage of clients that continue to purchase ARC insurance	83%	Not Met. 78%

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on ARC Ltd and its performance in growing its business, increasing its income, and ensuring it remains a sustainable and viable company. While ARC Ltd leads on selling and underwriting insurance, growth in sovereign and replica clients—and sustainability in terms of returning clients—relies on ARC Agency activities. Inclusive Insurance Business (IIB) (previously referred to as Non-Sovereign Business) is the sole responsibility of ARC Ltd.
In 2024, ARC Ltd recorded a net loss of US$34.5 million, a significant financial outcome that reflects the scale of climate-related shocks and their impact on the organisation’s underwriting portfolio. This loss was primarily driven by exceptionally high claim payouts, which substantially exceeded revenues and placed pressure on ARC Ltd.’s balance sheet.
Total gross premium income for the year was US$43 million, covering Drought, Tropical Cyclone (TC), and Outbreaks and Epidemics (O&E) products, with 44% attributed to sovereign policies. This represents a 25% decrease from the US$58.2 million earned in 2023, largely due to a sharp decline in sovereign insurance uptake in Pool 11A. Additionally, ARC Ltd was forced to limit the size of policies offered due to the financial impact of losses from Pool 10, as it can only underwrite policies from its own balance sheet.
However, premium income from Replica policies ($13.8m) continues to be encouraging and was significantly higher than the $3m target, driven by a total of 19 Replica policies: 7 policies facilitated from The Start Network to cover both drought and tropical cyclones, 9 policies facilitated by WFP to cover drought and tropical cyclone and 3 policies from the UNHCR to cover drought in refugee and host communities, increased from 1 policy in the previous pool following a successful pilot in Malawi.
Total premium income from Inclusive Insurance Business amounted to $5.7m, with the West African Development Bank (BOAD) contributing the majority of this income. One Acre Fund, L’Oreal, DRIVE and WFP also contributed to NSB income. Like Sovereign business, which is underwritten from ARC Ltd.’s own balance sheet, IIBB has seen a decrease in premium income as ARC have been forced to limit the size of the policies offered due to the impact of the substantial losses incurred in Pool 10.
Claim payouts for the year totalled US$84.8 million, with the Pool 10B season particularly affected by below-average rainfall driven by the ongoing El Niño cycle of the ENSO phenomenon. This resulted in large drought payouts in Zimbabwe, Zambia, Mozambique, and Malawi, amounting to US$62.3 million. ARC Ltd also holds reserves for policies with ongoing seasons, which decreased by US$1.6 million, bringing total gross claims incurred to US$83.2 million.
The reinsurance programme provided significant protection, with US$30.9 million recovered from reinsurers across both sovereign and inclusive insurance business.
These losses significantly impacted ARC Ltd.’s capital position, reducing Available Capital and Surplus to US$27.3 million as of Q4 2024. Despite this, ARC Ltd continues to exceed both regulatory and internal capital requirements, with Enhanced Capital Requirement (ECR) ratios, the minimum number of capital a company needs to hold to cover potential losses and ensure solvency, of 269% and 179%, respectively. These ratios remain comparable to Q4 2023, due to a lower capital requirement resulting from reduced coverage in Pool 11 and a more conservative reinsurance strategy.
While volatility is expected in the insurance industry—particularly as the frequency and severity of climate-related disasters increase—the scale and concentration of losses in 2024 were exceptional. The impact of El Niño has been particularly severe, highlighting the need for a more conservative period of balance sheet strengthening. Going forward, ARC Ltd will need to reduce the size of policies it offers and adopt more cautious underwriting and reinsurance strategies to ensure long-term sustainability and resilience.
For indicator 3.3, Niger, Senegal and Chad did not renew their policies in 2024, however, Lesotho, Benin and Ghana took out new policies, meaning that number of participants in pool 11 remains unchanged from pool 10.

Based on this performance we have scored this output a B.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key Recommendations	Progress
FCDO should consider whether additional capital should be extended to ARC Ltd, given the financial challenges facing the ARC ecosystem. Further funding should be tied to a medium-term plan to achieve financial stability	Ongoing
Risk pool growth should be a priority, this includes the launch of new products, strategies to engage new partners, and engagement with new and existing countries. The proposed Country Engagement Committee should inform this engagement.	Ongoing.
FCDO should consider an extension to the loan term and additional capital, subject to review by GAD, to allow FCDO to support the expansion of the ARC risk pool and to provide greater climate risk insurance coverage.	Ongoing. FCDO should carefully examine the 2025-2029 strategy to determine whether extending loan terms and additional capital are the most effective course of action.

Key Recommendations
ARC should continue to develop its investment management and reinsurance strategy in light of increasing climate uncertainty to protect against further losses that may be caused by future adverse weather events, and ARC should seek the support of GAD in doing so.
ARC should continue to prioritise the Inclusive Insurance Business as a growth area, providing the opportunity to recoup capital.

Output Title	Caribbean Water Utilities Insurance Collective (CWUIC) is well governed and managed and is delivering effectively and efficiently on its mandate.
Output number:		4	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No.

Indicator(s)	Milestone(s) for this review	Progress
CWUIC SP Management Committee (MC) is fully operational and providing effective oversight of CWUIC	6 members in place, including one nominated by FCDO / IDB and one representative from an insured utility, meeting at least three times a year	Partially met: The MC is in place and meeting at least three times a year (most recently, Feb 2025). It includes CCRIF Board and Management IDB/FCDO and CDB representatives, but not yet any representative from an insured utility.
CWUIC staffed, with staff delivering against CWUIC business plan objectives	4 staff (team leader and specialists for components 1, 2 and 3) in place and performing well against their agreed objectives	Met: All planned staff are in place. CCRIF is providing direct support to CWUIC on its insurance business, so the funds for the Component 2 lead have been reallocated to cover an additional year of the team leader’s salary.
CWUIC performing well against its Business Plan projections for insurance policy sales	7 policy sales, discussions underway with 3 and expanded to 3 more utilities	Not met: Three policies are currently active, with 9 offers to be made for the 2025 policy year.
Excellent asset (capital) management in line with CWUIC’s Investment Guidelines and projections in the Business Plan. CCRIF is reporting to FCDO on the financial performance of CWUIC as agreed in the CCA	Investment return of at least 3%	Met: Yields of 2.9 to 4% across the portfolio.

Briefly describe the output’s activities and provide supporting narrative for the score.

This has been CWUIC’s first year of active insurance. It sold its first policies (to the water utilities of Belize, Dominica and Grenada) in June 2024. When Hurricane Beryl subsequently became the earliest and fastest intensifying hurricane in the Caribbean, Grenada’s water utility NAWASA received a full payout to enable it to undertake emergency repairs in affected areas. This provided an important test for the insurance product, as well as demonstrating the value of insurance for critical services.

The CWUIC team is now focusing on finalising the modelling and customising policy offers for the 2025 season. Insurance offers will be made to 9 water utilities for protection against either hurricane (tropical cyclone and rainfall) or runoff (flood), as appropriate. The three policy sales in 2024 were all to utilities in ODA (Official Development Assistance or aid)-eligible countries, all of which received premium subsidies (85% of the total premium price in the first year, reducing to 50% in year 2, 35% in year 3, before phasing out in year 4). Belize (an IDB member) received its subsidy via a UK grant to IDB, and subsidies for Dominica and Grenada from a share of the investment income earnt by CWUIC during the first year. Premium subsidies will be offered on similar terms to new joiners from ODA-eligible countries this year.

As well as the insurance, CWUIC provides support for response planning to help get services back up and running again quickly after disasters and resilience-building to strengthen the water utility’s infrastructure (pipes, water treatment plants etc). Fundraising is also continuing for this other work. Funding has been received from IDB and The Coca Cola Foundation and other fundraising efforts continue.

Haiti is extremely climate vulnerable and poor, and support to their water and sanitation services is a priority for CWUIC. Data there is weak and, given present insecurity, it is currently not possible to survey. A bespoke solution will therefore be provided for Haiti, with a top up (ie 100% subsidy) added to the sovereign CCRIF hurricane policy for Haiti with any payouts being used for emergency water supply through verified partners.

CWUIC has recruited the staff it needs to start work on all three components – an excellent team leader (previous CEO of a Caribbean water utility company) and the response and resilience leads are already in place. Support to the insurance business will come directly from CCRIF.

CWUIC has been formally established as a segregated portfolio of CCRIF SPC, and all agreed reporting is being provided on schedule. Investment income has been between 2.9 and 4%. The CWIUC Management Committee has been established and met regularly throughout 2024 and 2025, providing strong support to CWUIC. Now active insurance policies are place, it needs also to recruit a representative from an insured utility. The CWUIC Working Group is also active, meeting regularly and offering effective support to CWUIC.

Priorities for the coming year are business planning, new policy sales and product development (including drought cover). Fundraising needs to continue for the response and resilience activities, as well as for additional premium subsidies if required, to ensure the full set of resilience and response support will be available to members. CDB has agreed and is considering additional support for CWUIC, and the grant from The Coca Cola Foundation will support resilience work in 5 countries. Insured members, Governments, CCRIF, CWUIC, IDB and CDB need also to agree their approach to the Green Climate Fund, particularly for resilience investments.

This Output has been scored as A (met expectations) as CWUIC is making good progress overall. Activities have been slightly slower to start up than expected, but 9 policy sales for the coming hurricane season and new product development will help establish CWUIC as a well-diversified risk pool. The full payout to Grenada’s NAWASA within 2 weeks of Hurricane Beryl has provided an important demonstration effect for the region on the importance of building resilience and insured critical public services.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe indicators/milestones will be updated after this review, based on the updated Business Plan (currently being finalised).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learn and recommendations from 2024	Responsible lead/ Deadline	Progress
Awareness-raising / CWUIC is an ambitious new initiative combining risk reduction (resilience investments and response) and risk transfer (insurance).	CWUIC team and CCRIF SPC. / By May 2024 enabling prospective policy holders to understand the policy offer.	CWUIC and CCRIF has made good progress socialising the new insurance product to potential clients this year, with 9 policy offers to be made in the coming months / The payout to Grenada’s NAWASA has provided proof of concept.
Modelling / CWUIC’s success will depend on the accuracy of its modelling. TC and rain updates and the new runoff modelling must be completed in good time to allow the Centre for Disaster Protection and utilities to review well before the start of the new policy year.	CCRIF SPC (responsible for the ERN/RED contract). / By April 2024, so that prospective policy holders understand the policy offer.	Good progress with both the hurricane and runoff modelling customisation (complete for 9 utilities and others underway).
Fund-raising / It is important that additional fund-raising (including climate finance) continues and that the support offered is available to all Caribbean countries (not just IDB members). CDB modelling grant for the Eastern Caribbean to be agreed and received by CWUIC and formal programme approval process to start with the Green Climate Fund (GCF).	CDB and CCRIF (modelling grant) and IDB, CDB and GCF on resilience investments project design. / CDB grant to be received by May 2024 and GCF Information Note to be agreed between IDB, CDB and GCF by October 2024.	CDB grant has been received and additional support under consideration. Clear agreement needed between all stakeholders on whether/how to approach the GCF for support for resilience.
Oversight and staffing / The Management Committee should start to meet quarterly. / Now that the first 3 staff are on board, recruitment should start for the insurance specialist to enable CWUIC to get up to full operating strength.	CCRIF SPC (Management Committee). / Management Committee meeting by end of March 2024. / IDB and CWUIC (recruitment). / Component 2 specialist recruitment by October 2024.	Management Committee in place, meeting regularly – but needs now to recruit an insured water utility representative.
Key Recommendations for 2025		Responsible lead/ Deadline
Business Development / CWUIC needs to continue to grow its client base, with more policy sales and new products (hurricane, runoff, drought). CWUIC and CCRIF should prioritise business development, using the early payout for Grenada for Hurricane Beryl to demonstrate the value proposition.		Updated Business Plan agreed by May 2025. / Up to 9 policy sales for 2025/6 policy year.
Fund-raising / It is important that additional fund-raising (including climate finance) continues for CWUIC for response and resilience work as well as premium subsidies . CWUIC, IDB and CDB to agree with members how to approach the Green Climate Fund (GCF).		GCF Information Note to be agreed between CWUIC, member countries, IDB, CDB and GCF by March 2026.

## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost driver for the risk pools is payouts. Staff, consultants, contracted service providers and reinsurance are also important cost drivers.

Based on the unaudited ARC Ltd Q4 Dashboard, ARC Ltd administrative expenses totalled $8m for the year, $600K over their $7.4m budget. This overspend fell in 3 areas 1) Management and administration costs 2) Misc and One-Off Costs, and 3) Board costs. FCDO have been engaging with ARC Ltd to better understand these overspends and ARC Ltd have been taking necessary measures to reduce expenses.

Reinsurance and brokerage are major costs for the risk pools, and a key driver of their success. Both ARC and CCRIF have a Risk and Reinsurance policy which sets out their approach to purchasing reinsurance. Their placing broker runs a competitive process, aiming to obtain cover from a panel of reinsurers. The broker is selected by a competitive open tender. The actual costs of the reinsurance will be benchmarked (in the Final Offer Terms), tracked and reviewed to ensure best prices and value for money.

However, reinsurance pricing has cycles in line with international markets when prices harden (rise), and risk finance capacity is reduced (so coverage is harder to purchase). We remain in a ‘hard market’ so prices are fairly high, compounded by recent payouts and tangible impacts of climate change (making losses more likely).

Other cost drivers for the pools are risk management services including the development of models, and staff and administration (cell rental fee) fees. Robust and accurate models are crucial to the effectiveness of parametric insurance and hence the success of this project. Good models can also support better understanding of risks and hence have benefits outside of the parametric insurance itself. The share of CCRIF’s admin fees that CWUIC will pay through cell rental fees (initially $80K plus modelling sub-licences) are considerably cheaper (and have needed no additional procurement except for staff recruitment) than if CWUIC had been set up as a stand-alone entity and not able to benefit from the services already in place at CCRIF.

VfM performance compared to the original VfM proposition in the business case

Core Value for Money (VfM) performance is based on economy, efficiency, effectiveness, and equity. In 2022, OPM undertook and published an assessment of the VfM performance of ARC – the full report is available at this link. Following this VfM assessment from OPM, the ARC Due Diligence Assessment was refreshed in late 2023 with further inputs from GAD, who looked at the same categories. A similar review for CWUIC will be conducted by the Centre for Disaster Protection (CDP) in 2025.

Consolidated key findings from the ARC studies, as well as comments on CWUIC’s VfM, are outlined below:

Economy
ARC Group were judged to have performed adequately in the following criteria, as assessed by the OPM study;
1. Capital, reinsurance, and running costs are kept as low as possible, and
2. ARC offers relevant, well priced products.
Since the OPM review, ARC Ltd has decided to make further use of reinsurance by attaching a reinsurance sub-layer to cover losses between the 100% and 120% risk layers. This means that if payouts are triggered within this range, they will be covered by reinsurance. This arrangement provides additional protection for ARC’s capital base. Based on this structure—and assuming ARC Ltd.’s premium costs remain relatively stable—GAD believes that if the sub-layer is triggered in full more than once every five years, it represents good value for money. In such a scenario, ARC Ltd would receive more in reinsurance payouts than it has paid in reinsurance premiums, thereby making the arrangement financially advantageous.

The CWUIC investment capitalised a segregated portfolio offering parametric insurance to water and sanitation companies in the Caribbean. The added value of buying insurance as a group (a risk pool) is based upon the fact that that the same event will not hit all members at the same time – premiums are used as the first source of funds to pay claims, then the capital base (ie the FCDO investment) and finally the reinsurance. This arrangement makes the insurance considerably cheaper (up to half the price) than buying individual commercial contracts. This premise has been tested through CCRIF’s operations since 2007 and holds true – its assets and business are stable and growing with over 10% more risk cover last year ($1.2bn) than the year before.

Efficiency
ARC Group were judged to have performed well in the following criteria;
1. Reliability and timeliness of ARC payouts, and
2. ARC provides high-quality technical assistance and capacity building support to countries to improve drought preparedness.
At present, one of the key strengths of ARC’s insurance-based model is its ability to provide countries with consistent, year-on-year coverage and payouts. This continuity is central to ARC’s value proposition and its reputation as a reliable partner. The model functions as a revolving fund: capital is used to pay claims and is then replenished through reinsurance recoveries and premium income from the next pool. This cycle has allowed ARC to sustain its operations and deliver impact over multiple years.
However, ARC’s sustainability is now under increasing strain. The growing frequency and severity of climate-related disasters are leading to larger and more frequent payouts (exacerbated in 2025 by El Nino related drought), which are eroding ARC Ltd’s capital base. This is already limiting ARC’s ability to underwrite large insurance pools and is forcing a reduction in policy coverage. If this erosion continues, ARC’s revolving fund model will be compromised, and its ability to provide reliable, long-term support to Member States will be at risk.
The scale of recent payouts, relative to the capital invested, reflects the intended multiplier effect of the model—where a single investment supports multiple years of coverage. But this effect depends on maintaining adequate capital reserves. Without sufficient capital, the efficiency and long-term viability of the model are threatened. ARC must now carefully manage its capital, reinsurance strategy.
CWUIC insurance payouts enable early action – a quick response helps to pre-empt damage and get services from the utility company back up and running again quickly. The value for the utilities is that they will pay a small amount each year, but throughout their cover, have access to a large amount of money for urgent repairs if they need it. Policies and total risk covered will vary by country/utility, but the multiple will be about 1:10, so $x premium buying $10x of total risk cover. There are other incentives to join CWUIC including protecting new water sector investment funded through IDB lending programmes, to access anticipated risk reduction/investment grant funds from the Green Climate Fund ($50m application in progress) and also grant funded contingency planning, resilience and service continuity support (pledge already received of $500K from Coca-Cola to fund work in 5 countries).

Effectiveness
      1. ARC Group were judged to have performed adequately on the following criteria;ARC funded drought responses reduce negative household level coping strategies, and
      2. ARC successfully facilitates increased sovereignty and sustainability in country level risk planning.
ARC Group were judged to have performed poorly in the following criteria;
ARC support to enhanced contingency planning and capacity building contributes to timely and appropriate drought response.
ARC does not directly deliver payouts to beneficiaries but relies on third-party or member state bodies. Generally, payout dispersion is the function of the payout recipient, i.e. the country or humanitarian actor with the policy. Engagement with payout recipients is undertaken by the government responsible for implementing the payout. ARC should work closely with member states to ensure capacity and capability to disperse payments is in place. ARC has already contributed to country-owned risk management strategies in some member countries (Senegal, Madagascar).

CWUIC made one payout (to Grenada’s NAWASA) in 2024, which arrived within 14 days of Hurricane Beryl to help restore water services to affected areas.

Equity
ARC Agency are responsible for undertaking post-payout monitoring and evaluation to allow for lessons to be learnt, and to give assurance that funds were used as intended. Throughout 2024, evaluation reports of the payout assessments in Mauritania, Malawi, Togo and Zambia were made available on ARC’s website. While this is progress, we are still far from this being embedded as common practice. These evaluations should be carried out as a priority following each payout to ensure effective targeting and lesson learning. ARC site budget constraints as the reason these are not carried out routinely however it is imperative that budgets are reprioritised to ensure this vital work does not slip.

The social impact of CWUIC is achieved through improving the resilience and service recovery times of water utilities after disasters. Out of 30 Caribbean jurisdictions (countries/Overseas Territories), all are susceptible to disasters, with 21 susceptible to at least 5 of the 8 types of disasters. Floods due to heavy rains or hurricanes in the Caribbean have caused significant damage to the infrastructure and the livelihoods of people. Climate research projections are that extreme weather will increase in intensity, enhancing the potential for substantial damage, particular for small island and coastal states such as in the Caribbean.

Water and sanitation utilities are at the forefront of these shocks. Damage can prevent the water utility from providing services while also causing the utility to incur losses due to a reduction in its revenues. It typically takes a utility at least two months to restore operations following a category 1 hurricane. Additionally, service disruptions have huge consequences for sectors that are reliant upon regular services such as hospitals, hurricane shelters and schools. Women, girls and vulnerable people (the elderly, ill or disabled for example) always suffer worst when clean water supply and sanitation is disrupted. It is therefore critical for public health reasons that water utilities restore services to their customers as quickly as possible after a natural disaster strikes. This will reduce illness and disease outbreaks including dehydration, diarrhoea and cholera, and also avoid the need to pay for expensive potable water importation and distribution (as well as the huge plastic waste from water bottles).

Assessment of whether the programme continues to represent value for money

Despite challenges, ARC and CWUIC continue to represent value for money. Through the risk pool model, they provide consistent support to those most vulnerable to climate-related disasters. In 2024/25, ARC covered over 16 million people, and the huge scale of payouts ($84.8m) has validated its mechanism, attracting new countries, partners, and donors. CWUIC demonstrated its value by paying out to Grenada’s NAWASA within 14 days of Hurricane Beryl. Both (ARC and CWUIC) offer technical assistance and planning support to strengthen resilience, and enable early action, reducing humanitarian and economic impacts. CWUIC adds further value through grant-funded contingency planning and links to climate finance initiatives.
On this basis, ARC and CWUIC are cost-effective, reliable, and impactful tools for disaster risk financing. Their ability to deliver payouts, support national systems, and adapt to rising climate risks makes them important components of the resilience and response landscape. Nonetheless, there is room to improve VfM further. Recommendations follow below:

Economy
FCDO should consider further discussion with ARC Ltd to understand their reinsurance strategy and consider whether an extension to the loan term could allow ARC more time to recoup eroded capital.

Equity
FCDO should use their role as a member on the Peer Review Mechanism sub-committee, responsible for reviewing and approving contingency plans, to drive renewed engagement on the post-payout monitoring issue.

ARC Agency should prioritise funding for post-payout evaluations going forward to help ensure that timeliness and targeting of payouts is improved and thus they are able to improve its VfM performance. Timely process evaluations and financial reconciliations will be important to ensure lessons are learnt from payouts and to give donors assurance funds were used as intended, reaching the intended beneficiaries.

E: RISK

Overview of risk management

The overall risk rating for the programme is Severe. The principal risks, and mitigating actions, as outlined in the recent refresh of the ARC DDA, are as follows.

There has been an erosion of FCDO’s returnable capital. At the end of 2023 Q4, the GAD valuation of UK capital has declined to £15.5m. Since then, ARC have seen further capital erosion, largely as a result of the payouts triggered by the El Nino drought in Southern Africa. Consequently, they had to reduce coverage by an average of 40% for Pool 11, at the same time as having to increase premiums by 20% to account for increased climate risk. This led to reduced climate coverage across the continent. Continued capital erosion represents a risk to the sustainability of the ARC approach (and the ability to continue to provide wide sovereign insurance cover). This risk falls under the financial management and stability pillar and has a net risk rating of major.

Further growth of the revenues and insurance portfolio through non sovereign business and ARC Replica will continue to deliver scale and diversification, and the Country Engagement Committee will address the slow uptake by Sovereign Governments. Going forward, ARC should embed the practice of sharing a business plan with donors ahead of time. ARC should continue to diversify their product offer as they have done in recent years.

For CWUIC the main risks are around the erosion of capital due to repeated heavy payouts and/or ex gratia payouts, which would also push up reinsurance prices; and increased global reinsurance prices more generally, which could result in higher premiums for Caribbean water utilities companies and might require CWUIC to adjust their reinsurance strategy. To mitigate these risks, there is a robust reinsurance strategy in place through CCRIF with Gallaghers. The capital erosion risk can be mitigated by buying more reinsurance but that will increase costs to clients.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

In relation to ARC, FCDO works with one commercial partner: Oxford Policy Management (OPM), as well as the Government Actuary’s Department (GAD). On CWUIC, FCDO works with GAD and CDP, as well as supporting start-up costs for CWUIC via two grants (technical assistance and premiums) via IDB. The IDB grants were provided via our Global Risk Financing (GRiF) Programme and their performance is covered in the GRiF Annual Review.

In October 2015, FCDO (then, DFID) contracted OPM) to design and deliver an Independent Evaluation of ARC, with a total estimated cost of £2,293,549. The purpose of this evaluation is to identify and feed lessons learnt into the management of the programme, test if risk pooling and transfer is a cost-effective way to incentivise contingency planning and ensure rapid responses to extreme weather events and provide accountability to UK taxpayers. The contract was amended in December 2023. These amendments relate to:
- A revised end date (July 2026) with no change to the financial limit.
- Updates to key personnel.
- Budget Breakdown for Impact Assessment 1.
- Updates to fee rates of some personnel.
The OPM contract is an output-based contract. On completion of each output, FCDO pays 40% of the output value once the draft has been assessed as being of high-quality. It goes through the Evaluation Quality Assurance and Learning Service (EQuALS), and the consolidated feedback gives an output score using explicit KPI criteria. The remaining 60% is paid upon confirmation of a final report that takes feedback into consideration, and again is quality assured by EQuALS. These outputs have been of excellent quality and high value to the FCDO to date.

The most recent output of the OPM contract was delivered in October 2024 – Impact Assessment Phase 1 Report, with a total cost of £518,068. The Impact Assessment (IA1) aimed to assess the value of contingency planning and early responses in minimising the impact of (and accelerating recovery from) extreme weather. IA1 assesses the contribution made by ARC’s work, through its assistance to member countries, to reducing the impact of climate disasters on vulnerable households. Following finalisation, OPM are now concentrating on dissemination, including presenting to the ARC Group Board and Conference of Parties later in the year. EQuALS reviewed this report, giving an overall rating of Excellent, confirming that the report is comprehensive and of a high standard.

We have letters of engagement with GAD for technical actuarial work on ARC and CWUIC. GAD offers actuarial services at considerably lower rates than the open market and the agreement is continuous until terminated. GAD’s fees are based on the staff time spent on work undertaken for the provision of advice plus travel and subsistence expenses incurred for any official business travel deleting as old now under the contract.

GAD review ARC Ltd and CWUIC’s quarterly reports provide an annual loan evaluation and provided hoc support and advice, on the provision of an agreed terms of reference and budget. GAD inputs are timely and insightful, allowing FCDO greater oversight and technical understanding of risk pool activities. They help FCDO challenge and shape the pools’ risk profiling, dynamic financial analysis, capitalisation, underwriting and accounting/valuation policies for example

G: MONITORING, EVIDENCE AND LEARNING

In addition to the FCDO Annual Review Process, two external contractors have been procured to provide external evaluation.

Oxford Policy Management has been procured to evaluate the impact of the ARC programme in its entirety – the activities, operations and management of ARC Agency and ARC Ltd, as well as the use of the insurance pay-outs in country, and the wider context. In 2023, OPM completed a formative evaluation assessing the organisational structure, management and operation of ARC Agency and ARC Ltd. Findings and recommendations were presented to the Board and have been incorporated into ARC’s strategic plans. The first impact assessment was completed in 2024.

FCDO’s grant to support the establishment of CWUIC includes a budget for a formative evaluation in Year 3.

GAD also reviews ARC Ltd.’s and CWUIC’s financial statements and narrative reports. These reviews enable FCDO to assess the value of its financial assets. The findings have been used to complete the financial and value for money assessment of this Annual Review.

Date of last narrative financial report	ARC Agency: Annual Donor Report received in February 2024. / ARC Ltd: Q4 Dashboard received in February 2025.CWUIC included in CCRIF’s Annual Report (November 2024). Q2 reporting received in early February 2025.	Date of last audited annual statement	ARC Ltd: 2023 Audited Financial Statement received in April 2024. CWUIC Audited statements in published Annual Report (November 2024). Q2 financial statement received in early February 2025.