## Annual Review

Title: Risk Pools Programme (RPP)
Programme Value £ (full life): Up to £100 million		Review date: March 2026
Programme Code: 203469	AMP start date: 13/03/2014	AMP end date: 31/03/2044

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025	2026
Overall Output Score	A	A	B	B	A	B	B
Overall programme risk rating	Severe	Severe	Severe	Severe	Severe	Severe	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/4643483.odt
DevTracker Link to results framework:	New link to be added

A. SUMMARY AND OVERVIEW
Description of programme

Risk pools enable governments in low- and middle-income countries to prepare for and respond to increasingly common and severe climate events by providing affordable insurance.
The original £100m business case included £10m of grant funding and £90m in development capital, the first £30m of which was invested in Africa Risk capacity (ARC) Ltd in 2014 as a 20-year interest free returnable grant, matched by a contribution from Germany’s KfW. The ARC Group includes ‘ARC Agency’, established as a specialised agency of the African Union (AU) and ‘ARC Ltd’, an affiliate mutual insurance company. ARC Agency provides technical assistance to countries to help strengthen their disaster risk management systems. ARC Ltd, through its regional risk insurance pool, provides access to rapid and predictable finance following a disaster to protect lives and livelihoods in African member states. ARC provides sovereign policies to ARC member states and ‘replica’ policies to humanitarian actors; WFP, START and UNHCR. ARC also offers ‘non-sovereign business’, which includes underwriting of World Bank programmes such as the Shock Responsive Social Protection in Malawi.
Although FCDOs development capital is invested in ARC Ltd, the success of the intervention depends in part on ARC Agency’s work to enable African countries to manage and respond to disaster risks effectively. ARC Agency activities that directly affect the ability of ARC Ltd to grow its business and deliver its services (e.g. country engagement) are considered by this review.
In April 2021 a business case addendum expanded the geographic coverage of the renamed Risk Pools Programme (RPP) beyond Africa, enabling FCDO to make an investment in the Caribbean risk insurance pool – Caribbean Catastrophe Risk Insurance Facility (CCRIF). In September 2023, a $25m development capital investment was made in the Caribbean Water Utilities Collective (CWUIC), a segregated insurance product within CCRIF. CWUIC offers risk reduction planning and resilience-building investments to strengthen water and sanitation services in the Caribbean, as well as insurance through the Caribbean regional insurance scheme. The first insurance policies were sold in June 2024 to Dominica, Grenada and Belize. A maximum payout of $2.2m was made to Grenada’s water utility NAWASA in July 2024 in response to Hurricane Beryl, demonstrating the value of the mechanism. In June 2025, seven policies were sold to the utilities in six Caribbean country and one UK Overseas Territory and CWUIC is on track to continuing growing.
In January 2025, a further business case addendum was approved to change £5.3m of the remaining £40.5m headroom for CDEL investments from non-fiscal (financial transactions) to fiscal (investment grant). This enabled an investment grant to be made to the Pacific risk pool (the Pacific Catastrophe Risk Insurance Company, PCRIC) in March 2025.
Summary supporting narrative for the overall score in this review

The programme has been scored a B, driven by underperformance in the ARC component. The most notable issue related to review of ARC Agency is the continued absence of robust data on payout implementation timelines - a critical measure of the effectiveness of ARCs sovereign insurance. For ARC Ltd, financial performance improved significantly as a result of fewer payouts (with a return to profit and increased capital base). However, the departure of the CEO and key members of the senior executive team during the reporting period has brought new challenges. CWUIC met all its indicators and demonstrated strong governance, and PCRIC, reviewed for the first time, performed well against business case expectations.
Major lessons centre on the need for clearer, more realistic indicators for ARC; improved country engagement strategy; improved payout timeliness tracking; and a step‑change in post‑payout evaluation. Major lessons centre on the need for renewed indicators for ARC; improved country engagement strategy; improved payout timeliness tracking; and a step‑change in post‑payout evaluation.
Major lessons from the previous year
Robust oversight, transparent decision-making, and well-defined roles for Boards and management teams help maintain trust and ensure risk pools deliver on their mandates, even in complex evolving environments. The importance of the need for Boards to be equipped with the right skills and independence is clear.
Robust technical systems, effective data management, and proactive client engagement are key drivers of programme performance. The successes of CWUIC and PCRIC highlight how investment in strong data systems, innovative product development, and regular communication with clients can lead to expanded coverage, rapid payouts, and greater resilience. These components have shown that when risk pools are responsive to client needs and able to adapt their offerings, they are better positioned to deliver timely and relevant disaster risk finance.
Finally, FCDO has observed that the ability to generate reliable monitoring and evaluation data is fundamental to learning and continuous improvement. Persistent data gaps—such as those seen in ARCs post-payout evaluations but also present for PCRIC—have limited the programme’s ability to demonstrate impact and inform adaptive management. In contrast, components with stronger evidence systems have been able to showcase results, support accountability, and drive ongoing improvements. This underscores the lesson that high-quality data collection, routine evaluation, and transparent reporting are critical foundations for effective delivery and long-term value for money.
Major Recommendations for the year ahead
ARC Ltd Recommendations:
1. Develop and implement an ARC Performance Improvement Plan (PIP): Work collaboratively with ARC to deliver a structured 12‑month PIP with clear, time‑bound actions and milestones. This should prioritise governance reforms, strengthening financial sustainability, and improving monitoring and evaluation—particularly post‑payout performance—while providing a clear framework for restoring delivery confidence.
2. Strengthen ARC governance, oversight, and management effectiveness: ARC Ltd should continue to enhance governance structures, internal controls, and Board oversight, ensuring transparent decision‑making and clear accountability. This should align with wider reforms and actions arising from the PIP.
3. Refine ARC financial, investment, and reinsurance strategy: ARC should further develop its investment management and reinsurance approach, drawing on technical support (including GAD), to improve financial resilience and ensure milestones are realistic, aligned with its business plan, and responsive to increasing climate volatility.
ARC Agency Recommendations
1. Prioritise post‑payout evaluation and monitoring improvements: ARC should establish a consistent, well‑resourced approach to post‑payout evaluations, ensuring timely, high‑quality data on implementation and impact. Strengthened monitoring systems should focus on tracking payout timeliness and translating lessons into improved contingency planning and delivery.
2. Strengthen member state engagement and delivery capacity: ARC should improve country engagement and capacity building to support more effective contingency planning and faster implementation of payouts. This includes accelerating completion of Country Strategy Papers (with gender and inclusion integration) and supporting countries to meet Certificates of Good Standing requirements.
Risk Pool Cross Cutting Recommendations:
1. Refresh FCDO’s strategic engagement across the risk pools: FCDO should review its overall approach to engagement with regional risk pools to ensure support is targeted, coherent, and aligned with priorities in a constrained ODA context, with clear differentiation between cross‑programme priorities and component‑specific engagement.
2. Strengthen and clarify fundraising and financial sustainability approaches: Risk pools should develop clearer, targeted strategies to mobilise additional funding (including donors, climate finance, and partners), with a stronger articulation of funding needs and objectives to support long‑term sustainability and scaling.
3. Expand and strengthen non‑sovereign insurance and partnerships: Continue to develop non‑sovereign insurance products and partnerships (including with utilities, NGOs, and the private sector) to diversify risk pools’ portfolios, broaden impact, and strengthen financial sustainability.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The business case’s theory of change highlighted three key elements in supporting development insurance as outlined below. The theory of change and assumptions remain valid.
Early responses to drought to protect livelihoods is the first underpinning theory i.e. households are supported before they have to reduce food or sell their productive assets. Risk Pools provides payments earlier than a humanitarian response could and before ongoing development support could be scaled up. However, these payments need to be in support of a sound plan, the funds need to flow to the right instruments and benefit the right people.

Changing incentives for risk management. This is at the heart of the value of this programme i.e that by valuing their extreme weather risks for insurance, African governments become aware of the costs they face with each drought and are motivated to reduce these risks as far as they can and transfer the residual risk to a reasonably priced insurance policy. This assumption should be tested in the context of slow risk pool growth in Africa.

Countries need to understand their own specific risk profile, to identify the right risks to transfer and build strong contingency plans. Countries covered by risk pools are supported to build the skills in risk assessment and contingency planning – and through an effective monitoring process, they should gain further skills from the process.

The programme’s outcome and impact indicators have been revised to reflect the recent expansion of scope to include PCRIC.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact: Countries are better able to manage climate risk as a result of transferring climate risk to regional risk pools.

Outcome: Increased risk pool coverage to expand climate risk insurance and strengthen financial resilience to disasters.

The programme is making mixed progress toward its intended outcome and impact, with performance varying across components.

Overall, the programme continues to demonstrate the value of pre‑arranged parametric insurance in enabling timely and predictable responses to climate shocks. Risk pools are supporting access to rapid finance and contributing to improved resilience; however, progress toward expanded coverage and strengthened financial resilience remains uneven.

ARC Group continues to deliver core elements of the outcome, providing parametric insurance and enabling government‑led responses to droughts and cyclones. The renewal and expansion of insurance pools and continued payouts demonstrate ongoing relevance. Financially, ARC Ltd has strengthened its capital position, improved reinsurance arrangements, and reduced costs. However, progress is constrained by underperformance, including multiple off‑track indicators, weak monitoring data—particularly on payout timeliness—and challenges in sustaining and expanding coverage.

In contrast, CWUIC and PCRIC are performing strongly and broadly on track. CWUIC has expanded its client base, remained financially stable, and demonstrated value through rapid payouts and recovery support. PCRIC has increased access to parametric insurance, expanded membership and products, and strengthened disaster risk financing systems. These components illustrate the benefits of strong governance, clear delivery models, and robust monitoring.

Actions in the year ahead will focus on addressing these constraints, particularly within ARC, while sustaining progress elsewhere. A key priority is implementation of an ARC Performance Improvement Plan (PIP), targeting governance reform, improved monitoring and evaluation (especially post‑payout evaluation), and more realistic indicators. FCDO will also support stronger member‑state engagement and ARC will be expected to act on HR audit findings and rebuild donor confidence.

For CWUIC and PCRIC, the focus will be on sustaining growth while strengthening systems and evidence. CWUIC will expand its client base and secure additional funding, while PCRIC will embed its logframe, strengthen post‑event evaluation, and continue scaling membership and products.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme remains a central part of the UK’s disaster risk finance offer, with particularly positive performance in the Caribbean and Pacific components. CWUIC and PCRIC have demonstrated effective governance, growing policy uptake, and clear demand for pre‑arranged climate finance, showing how regional risk pools can deliver rapid, predictable support to countries facing increasingly severe climate shocks.

The ARC component continues to face challenges, but ARC Ltd has returned to profit and stabilised its capital position and is making progress with an ongoing governance refresh. It has also continued to make critical payouts, reducing negative impacts and enabling faster recovery from crisis. These developments, support continued engagement but with a structured and time‑bound approach to strengthening performance. Maintaining UK support will help sustain vital access to affordable climate risk finance for vulnerable countries, reinforce the UK’s leadership in this field, and ensure the programme continues to deliver meaningful, timely assistance where it is most needed.

## C. DETAILED OUTPUT SCORING

Output Title	African Risk Capacity (ARC) - Increased capacity of ARC member states to identify climate risk and transfer climate risk to the risk pool. Improved capacity of ARC member states to implement payouts in a timely manner according to pre-approved contingency plans.
Output number:		1	Output Score:	C
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of ARC Member States that have a valid Certificate of Good Standing (CoGS).	22 Member States	Not Met: 20 Member states
Number of country strategy papers finalised and incorporating gender dimensions.	19 Country Strategy Papers	Not Met: 8 Country Strategy Papers
Average number of days between ARC payout trigger and start of the implementation of the response.	120 days	Not Met: ARC Agency are unable to provide a definitive figure, but some payouts have faced significant delays

Briefly describe the output’s activities and provide supporting narrative for the score.

This output evaluates the effectiveness of ARC’s activities in enhancing member states’ ability to identify, manage, and respond to climate risks. Over the past 12 months, ARC Ltd has maintained active engagement with member states across Africa, focusing on supporting countries through the ratification process, expanding policy uptake, and strengthening technical capacity for disaster risk management. However, while ARC has overseen efforts to grow membership- with several countries completing ratification and others progressing towards accession- performance against this outcome continued to fall below the milestones. This suggests that ARC’s tailored engagement, and capacity building needs continued refinement to ensure impact.

Indicator 1:
Achieving a valid CoGS is a prerequisite for purchasing ARC insurance policies. 20 member states met this requirement, compared to the target of 22. This result is consistent with the previous year, where the number also fell short by two. ARC should continue to work closely with countries not meeting the requirements to identify and address specific barriers, potentially through targeted capacity-building or technical assistance.

Indicator 2:
Only 8 out of the targeted 19 Country Strategy Papers were finalised, with an additional five awaiting final approval. The limited number of completed strategy papers indicates that further efforts are needed to accelerate the process, particularly in relation to gender mainstreaming. However, while the pace of progress remains slow, positive steps have been made including the ongoing process to identify scope for improvement through an active process of member engagement, including a questionnaire of all committee members by the Country Engagement Committee (CEC) team. Improved CEC oversight should lead to improved country engagement outcomes.

Indicator 3:
The third indicator assesses the average number of days between an ARC payout trigger and the commencement of response implementation, with a standard set at 120 days. ARC reported that the payout period has exceeded this benchmark but were unable to provide a robust measurement of the average number of days. The target was exceeded due to delays in response implementation in several countries, including Mozambique, Zambia, Zimbabwe, and Malawi. These delays highlight the importance of robust government systems and effective collaboration between ARC Agency and member states to ensure that payouts are received and actioned promptly. Timely implementation is a critical comparative advantage of DRF over traditional humanitarian approaches. Addressing bottlenecks in the payout and implementation process should be a priority.

Score Justification
The output has been scored as a C, reflecting in particular concerns about the lack of progress in establishing robust data on the payout period (indicator 3), which is a critical dimension of effective disaster risk finance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output has not been updated in the last year. The indicators in this output relate primarily to ARC Agency, which is not funded or directly influenced by FCDO. As the indicators are relevant for the overall success of ARC, (despite being outside FCDOs direct control) the programme team will consider alternative approaches, as part of the proposed performance improvement plan (PIP).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
ARC should continue to prioritise post payout checks, (financial reconciliations, process audits) for all payouts and ensure sufficient budget allocation for this vital evaluation function. Learning should be shared in a timely manner to inform future iterations of contingency plans. This recommendation reflects a need to continue to deliver against the recommendation included in last year’s annual review	ARC confirmed that only two post-payout evaluations were completed in 2025- in Mozambique and Zimbabwe- indicating limited progress.

Recommendations for 2026	Targets
Refresh the Output Indicators: / Given repeated challenges in measurement and attribution, the programme team should review the indicators. New indicators should focus on components where ARC Agency and ARC Ltd have direct influence over decision making and should track in-year as well as cumulative progress. Programme team should work with ARC Agency and Ltd to consider whether and how these indicators could be refreshed to strengthen monitoring of critical dimensions.	FCDO to engage with ARC to agree new indicators by end of Q3 2026/27. These indicators will be utilised after the end of the PIP.
Increase the Frequency of Post-Payout Evaluations / Post‑payout evaluations remain limited despite repeated recommendations. ARC should allocate sufficient budget and staff time to ensure evaluations are completed for every payout, including basic financial reconciliation and process audits. Findings should be shared promptly with member states and donors to inform improvements in contingency planning and readiness.	ARC Agency to conduct post-payout evaluations for at least 40% of all payouts in 2026
Introduce a More Structured Approach to Identifying and Payout timeliness issues: / ARC should develop a systematic process to identify barriers to timely payout delivery, drawing on lessons from recent payout events. This should include country‑specific bottleneck analyses, clearer roles and responsibilities during implementation, and a routine mechanism for documenting and sharing lessons internally and with FCDO. Strengthening this process will help ensure payouts translate into timely and effective action on the ground.	ARC to develop and present a new, evidence-based approach to ensuring timeliness of payouts to FCDO and donors by end of Q3 2026/27

Output Title	African Risk Capacity (ARC) - ARC Group is well governed and managed and is delivering effectively and efficiently on its mandate.
Output number:		2	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Auditors sign off unqualified audit for ARC Ltd.	Yes	Yes (2024)
Percentage of ARC Group Board Actions completed within agreed time frame.	85%	92%
Percentage of matters arising on ARC Ltd Board dashboard resolved within agreed time frame.	85%	91%

ARC Group is governed by the Conference of Parties (COP) under the ARC Treaty, with oversight provided by the ARC Group Board, which includes representatives from the African Union Commission, member states, and partners (including FCDO at Director level). The ARC Ltd Board operates separately, with directors appointed by a nominations committee representing both Class A (countries with active policies) and Class C (development partners) members. The Chair of ARC Ltd Board also sits on the ARC Group Board, ensuring alignment and oversight across both entities. Both Boards have established committees overseeing peer review, product development, and country engagement.
The ARC Group Board and its committees are responsible for setting the strategic direction for the Group. In 2025, both ARC Ltd and ARC Group Boards have surpassed their intended milestones, reflecting a substantial improvement from 2024, particularly on the completion of Board actions. This improvement is indicative of enhanced operational efficiency and resourcing of key committees, especially within ARC Agency.
#### Indicator 1: Auditors sign off unqualified audit for ARC Ltd.
As in previous years, the timing of this annual review means that the audit for 2025 is not yet available; therefore, the 2024 unqualified audit is used as a proxy. This continues to demonstrate effective financial management, despite the challenging context of increased climate shocks.
#### Indicator 2: Percentage of ARC Group Board Actions completed within agreed time frame
There has been a significant improvement in this area, with completion rates rising from 36% in 2024 to 92% in 2025. This reflects the positive impact of recommendations made in the previous review to focus on the implementation of Group Board actions. The appointment of a new Group Director General has likely contributed to this progress, with a renewed emphasis on operational efficiency and effectiveness within ARC Agency.
#### Indicator 3: Percentage of matters arising on ARC Ltd Board dashboard resolved within agreed time frame
ARC Ltd continues to perform strongly against this objective, with a slight year-on-year increase from 90% to 91% of dashboard actions completed on time. This reflects positively on the performance of the Board Chair, ARC’s interim CEO, and other Board members in executing agreed actions.
### Score Justification
ARC Group has demonstrated improved governance and management, with strong progress against key indicators. The unqualified financial audit provides assurance of sound financial management. Overall, ARC’s operational and governance performance (reflected by progress against the above indicators) justifies the output score of A.
### Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to the impact weighting for this output since the last review. However, the appointment of a new Group Director General represents a significant development in ARC’s governance landscape. The logframe indicators will be reviewed in the coming year to ensure they remain relevant and reflect progress in governance and operational effectiveness.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
FCDO, in collaboration with the ARC Group Board, should continue to focus on strengthening timely implementation of agreed Board actions. Given how integral the new Group Director General (GDG) will be to strengthening ARC Group governance, the FCDO should engage early with the incoming GDG to offer support and progress this recommendation.	Substantive progress with a very significant improvement in indicator 2.1. FCDO has engagement closely with the new ARC GDG who has demonstrated a strong commitment to improve ARC Group Board and Agency’s operational efficiency and achieved meaningful progress

Recommendation	Progress
Review and update logframe indicators to reflect progress and ensure they continue to be stretching, alongside accurately assessing progress and achievement in ARC governance and operational efficiency. In particular, ensure they are well targeted for the proposed ARC PIP.	Updated indicators agreed by end of Q1 2026.

Output Title	African Risk Capacity (ARC) - Strengthened financial stability of ARC Ltd and growth of ARC capital base to ensure long term sustainability of ARC Ltd risk pool to provide climate risk insurance. Increased credibility of ARC products and elimination of basis risk events.
Output number:		3	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
ARC Ltd financial indicators: Net profit / loss	$18.1	$10m
Total premium income / 1)sovereign / 2)replica / 3)NSB	1) $49m / 2) $4m / 3) $12m	1)$25.8 / 2)$8.5 / 3)$11
Percentage of clients that continue to purchase ARC insurance	99%	85%

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses ARC Ltd’s financial stability, its ability to grow and diversify its premium base, and the extent to which its underwriting and capital position support the long‑term sustainability of the risk pool. ARC Ltd has seen a significant improvement in financial performance across this review period, with a return to net profitability- partially driven by a favourable volume of payouts in pool 12. ARC has also demonstrated a commitment to cost-cutting and improvements in operational efficiency. However, the financial performance of ARC Ltd continues to be below agreed milestones, indicating the need for further improvement.

Indicator 1:
ARC Ltd reported a net profit of US$10 million for 2025 against a milestone of US$18.1 million. This represents a significant improvement from the substantial loss recorded in 2024 and reflects reduced claims, strengthened underwriting discipline, more conservative risk selection, and reduced operational expenditure. Despite falling short of the milestone, the return to profitability marks potential to rebuild financial sustainability. The programme team will consider whether this milestone has been appropriately calibrated to the commercial environment ARC Ltd is operating and may make revision of this target for future AR cycles.

Indicator 2:
ARC Ltd generated US$45.3 million in total premium income: US$25.8m in Sovereign, US$8.5m in Replica, a mechanism that allows humanitarian organisations to purchase insurance coverage, enabling rapid, coordinated responses to disasters alongside national efforts and US$11m in IIB (Inclusive Insurance Business) IIB parametric insurance products to non-sovereign entities such as agribusinesses, and microfinance institutions. Sovereign premiums remained below target due to reduced coverage in some markets, and a slower‑than‑expected recovery in policy uptake. Replica premiums exceeded the milestone, reflecting strong engagement with Start Network, WFP and UNHCR, demonstrating continued appetite among humanitarian actors for parametric solutions. IIB premiums were slightly below target but continue to provide an important source of diversification for ARC business, which reduces reliance of sovereign coverage and expands the scope for impact from ARC Ltd’s capital base.

Indicator 3:
Client retention improved to 85%, up from 78% the previous year, but still below the milestone of 99%. This underlines the need for clearer analysis of client drop‑off, proactive engagement around renewal periods, and strengthened internal systems for tracking client decision‑making. However, retention is likely to have been adversely impacted by the realities of sovereign budgeting issues within Africa and exogenous shocks affecting country purchasing decisions, which may mean that the milestone for this indicator needs revision in line with the evolving macroeconomic environment in Africa.

Score Justification
This output is scored B, reflecting meaningful progress in restoring ARC’s financial strength while recognising continued gaps against milestones. ARC has re‑established profitability, strengthened its capital position, and implemented more disciplined underwriting and reinsurance strategies. However, milestone shortfalls indicate that ARC has more to do to secure a sustainable and diversified premium base.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The indicators within this output have not been changed within the last year. Over the next annual review period, the programme team will update the milestones to reflect changes ARC Ltd’s business plan, alongside a more challenging global environment in which ARC Ltd is operating. This will ensure that future annual reviews provide a reasonable assessment of ARC Ltd’s progress against expectations. This update will be made as part of the proposed PIP process.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations	Progress
ARC should continue to develop its investment management and reinsurance strategy in light of increasing climate uncertainty to protect against further losses that may be caused by future adverse weather events, and ARC should seek the support of GAD in doing so.	ARC Ltd has made substantial improvements to their re-insurance strategy this FY, and by the end of Q3 confirmed they had been able to access re-insurance for 80% their coverage in pool 12b. However, ARC Ltd could more actively seek support from the (UK) Government Actuaries Department (GAD) in the design of their reinsurance strategy.
ARC should continue to prioritise the non-sovereign as a growth area, providing the opportunity to recoup capital.	ARC Ltd continues to emphasise the importance of the non-sovereign, with a focus on expanding This includes in-year expansion into West Africa and Southern Africa.

Recommendations 2026	Target
Strengthen Client Retention and Engagement Strategies: While client retention improved to 85% in 2025, it remains below the 99% milestone. ARC Ltd should refresh their strategy engagement with existing clients.	ARC should present an updated client engagement strategy by the end of Q2 26/27 with measurable milestones for actions to improve engagement.
Expand and Diversify the Premium Base: Although replica premium income exceeded targets, sovereign and NSB premium income fell short. ARC Ltd should focus on diversifying its premium base by exploring new markets and strengthening partnerships with non-sovereign clients.	ARC Ltd should develop a clear, actionable strategy for diversifying its premium base by end of Q3 26/27.

Output Title	Caribbean Water Utilities Insurance Collective (CWUIC) is well governed and managed and is delivering effectively and efficiently on its mandate.
Output number:		4	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Yes, down from 40%

Indicator(s)	Milestone(s) for this review	Progress
CWUIC SP Management Committee is fully operational and providing effective oversight of CWUIC.	6 members in place, including one nominated by FCDO / IDB and one representative from an insured utility, meeting at least three times a year	Met: the CWUIC Management Committee is in place (including a representative of an insured utility, BWS) and meeting at least three times a year.
CWUIC staffed and performing well against CWUIC business plan.	4 staff (team leader and specialists for components 1, 2 and 3) in place and performing well against their agreed objectives.	Met: CWUIC is staffed as planned (team leader, expert leads for components 1 and 3, with CCRIF Chief Risk Officer leading component 2) and performing well against the business plan.
CWUIC performing well against its Business Plan projections for insurance policy sales.	7 policy sales, discussions underway with 3 and expanded to 3 more utilities.	Met: seven policies in place (6 countries and 1 overseas territory), with 7 renewals and policy offers to go out to others in time for June 2026 season.
Excellent asset (capital) management in line with CWUIC’s Investment Guidelines and projections in the Business Plan. CCRIF is reporting to FCDO on the financial performance of CWUIC as agreed in the CCA.	Investment return of at least 2% (to be updated annually in agreement with CCRIF). Reporting (3 quarterly and 1 annual financial statement and narrative reporting) continues to be received according to agreed timeline.	Met: investment income of over 2% ($515k) earnt, and regular reporting, including unqualified annual audit received.

Briefly describe the output’s activities and provide supporting narrative for the score.

CWUIC has performed well over the past year. The pool grew to 6 insured countries and 1 Overseas Territory (Montserrat), enabling good geographical diversification with discussions and risk modelling underway for additional new clients for June 2026 onwards. The most severe hurricane to hit the region over the past year was Hurricane Melissa, passing over Jamaica in October 2025. Jamaica’s water utilities NWC had not bought insurance, but CWUIC provided ‘mutual assistance’ support anyway as a show of solidarity to help restore water supply after the hurricane. This helped to keep CWUIC’s profile high, test systems in a real emergency and demonstrate the value of the approach (risk reduction/investment, service continuity and contingency planning and insurance to fund rapid repairs and recovery when needed).
CWUIC’s investment income was about the target of 2%,
Indicator 1:
The CWUIC SP (Segregated Portfolio) Management Committee (MC) is fully operational, with six members in place—including FCDO/Inter-American Development Bank (IDB) nominees and a representative from an insured utility—meeting at least three times a year. This has ensured effective oversight and guidance, supporting strong governance and decision-making. FCDO has recently been informed of the intention of two of the original MC members to stand down after two years and be replaced. FCDO will work with CDB and IDB to ensure good quality replacements, ensuring that they are in post and briefed ahead of the next MC meeting.
Indicator 2:
Financial and programme management within CWUIC is going well – all staff are in place, and there is regular financial reporting and informal updates on progress through the working group meetings and annual reports.
Indicator 3:
CWUIC has met its business plan projections for insurance policy sales, with seven policies in place (covering six countries and one overseas territory), and policy offers prepared for additional utilities for the upcoming season. While uptake of premium subsidies through the IDB grant has been slower than anticipated, these markets remain a priority for the next insurance cycle. An additional three policy sales including subsidies had been anticipated this year but were delayed by the calling of national elections in those countries (Jamaica, Guyana and Suriname). These countries, as well as cover for Haiti as a top up for the sovereign policy, will be a priority for coming insurance season.
Indicator 4:
CWUIC has demonstrated strong asset management, earning investment income of over 2% and maintaining regular, timely financial and narrative reporting. This has enabled the cost of premium subsidies to be made for utilities in ODA-eligible countries that were not members of IDB (and so unable to receive premium financing through the UK’s grant to IDB), as well as a contribution to recoup capital after payouts in year 1. The pool has also secured additional grant support from CDB and IDB, though further fundraising is needed to sustain risk reduction and contingency planning activities as the UK-funded grant through IDB is expected to be exhausted within 18 months.
Score Justification
CWUIC has performed well over the past year, expanding its client base, maintaining robust governance, and delivering effective financial management. The pool’s response to Hurricane Melissa, including mutual assistance to Jamaica’s water utilities, demonstrated the value of its approach and helped raise its profile. While some challenges remain in scaling up policy sales and securing long-term funding, CWUIC’s strong operational and financial performance justifies the output score of A. Continued focus on business development, fundraising, and technical support for new clients will be important to sustain momentum and impact in the year ahead.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting for the output was increased from 20 to 30% to reflect the proportion of the total programme that the CWUIC investment within the total RPP portfolio (£20m of £65m invested or spent). The number of policies sold will be updated according to CWUIC’s updates business plan projections.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Recommendations from previous AR	Target	Progress
Business Development / CWUIC needs to continue to grow its client base, with more policy sales and new products (hurricane, runoff, drought). CWUIC and CCRIF should prioritise business development, using the early payout for Grenada for Hurricane Beryl to demonstrate the value proposition.	Updated Business Plan by May 2025. / Seven policies sold for 2025/6 policy year.	Largely Met: Updated Business (policy sales) and financial projections agreed. / Seven policies were sold for the 2025/6 policy year. Three more sales had been expected (Jamaica, Guyana and Surname) but progress for all was affected by the calling of national elections in those countries.
Fund-raising / It is important that additional fund-raising (including climate finance) continues for CWUIC for response and resilience work as well as premium subsidies. CWUIC, IDB and CDB to agree with members how to approach the Green Climate Fund (GCF).	GCF Information Note to be agreed between CWUIC, member countries, IDB, CDB and GCF by March 2026.	Partially met: Fundraising remains an important priority for CWUIC and there were two further grants from CDB and IDB during the year. A fundraising/ donor outreach strategy was agreed, but there has not yet been a formal approach to GCF.

Recommendations for the coming year	Target/deadline	Responsible lead
Fundraising: / The donor/funding landscape is hardening with geopolitical changes, but outreach and fundraising remain important for CWUIC to be able to achieve the full range of its scope across all three components and provide additional premium subsidies if needed.	At least one additional donor / grant secured for CWUIC by Dec 2026.
Diversification: / CWUIC should continue to focus on new client engagement (sales) and also new product development to ensure it is a well-diversified risk pool.	At least 3 additional policy sales for the 2026 Hurricane season. / One additional insurance product (drought?) ready to pilot by June 2027.	CWUIC and donors to make the case for water sector resilience and publicise availability for premium subsidies in ODA-eligible countries.
Governance: / IDB, CDB and FCDO to work together to identify two new Management Committee appointees to replace those stepping down.	Two qualified MC representatives selected, briefed and in post by the next MC meeting (end of June 2026)	IDB, CDB and FCDO
Logframe refresh: / CWUIC has now been up and running for over two full years so the logframe indicators should be updated to reflect progress in a maturing organisation, rather than a start-up. New indicator also to be added to track uptake and impact of premium subsidies.	Refreshed logframe indicators to be agreed with CWUIC by Sept 2026.	FCDO and CWUIC/CCRIF.

Output Title	PCRIC is well governed and managed and is delivering effectively and efficiently on its mandate.
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	New output

Indicator(s)	Baseline	Progress
PCRIC performing well against its Business Plan projections for insurance policy sales.	8 PICs with active PCRIC Parametric Insurance coverage / 5 New policies. Solutions developed for non-sovereign coverage	N/A
Innovative PCRIC products developed tailored to the needs of clients.	5 products offered that cover different climate-linked disasters / No Formalised Product Development Framework	N/A
PCRIC staffed and performing well against business plan.	50% of roles with defined KPIs / 4 independent governance reviews passed / No adoption of a governance framework supported by all stakeholders	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

This year marks the first time that the Pacific Catastrophe Risk Insurance Company (PCRIC) has been included in the Annual Review. As PCRIC’s logframe indicators and milestones were only finalised at the end of the previous calendar year (end 2025), it is not analytically valid to assess progress against them for this cycle. The only recommendation from last year’s annual review was to integrate PCRIC into the RPP logframe which has been completed. This review draws on additional non‑logframe evidence to reflect performance during the period and to assess progress against the expectations set out in the business case addendum that accompanied the £5.3 million FCDO capital grant. These insights support the output score and help establish a baseline for future logframe‑based assessments.
PCRIC continues to provide rapid-payout disaster insurance to small island developing states, with the £5.3 million UK capital grant supporting expansion to more Pacific Island Countries, diversification of hazards covered, and a stronger capital base. The main objective for this period was to agree the logframe indicators, which has been achieved; formal assessment against these indicators will begin in the next annual review.
Indicative progress shows that PCRIC has expanded from five to eight sovereign policyholders, increased the number of hazards covered, and broadened its product offering, including non-sovereign coverage. These developments align with business case expectations and demonstrate a positive trajectory in participation, product innovation, and regional resilience.
While not formally assessed against milestones this year, PCRIC’s achievements provide confidence that it is delivering as intended and using FCDO capital effectively. This output is scored an A, reflecting strong progress and a solid foundation for future monitoring and value for money.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

As this is PCRIC’s first inclusion in the annual review, the main change is the introduction of new logframe indicators, now integrated into the RRP logframe and agreed with PCRIC and its donors. Since specific targets were not yet set at the time of this review, reporting has been aligned with the business case objectives. From the next review onwards, both indicators and targets will be used, enabling more robust monitoring and better alignment between FCDO and PCRIC reporting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s AR recommended integrating PCRIC into the RRP logframe. This has been completed.

Recommendations 2026	Targets
FCDO should work with PCRIC to embed the newly agreed logframe into routine monitoring and ensure clarity on reporting expectations. As PCRIC will be formally assessed against its logframe for the first time in the next review cycle, this includes agreeing a reporting timetable, clarifying evidence requirements.	FCDO and PCRIC should agree a clear reporting timetable by end of Q1 26-27. FCDO should review and finalise the methodology for all components, including KPI 15, by end of Q1 26/27.
PCRIC should seek to continue to diversify their donor base to reflect a challenging ODA environment. FCDO should actively support PCRIC to refine their offer.	PCRIC should produce an update structured donor engagement plan by end of Q3 26/27 to aimed at expanding and diversifying their funding base

## D: VALUE FOR MONEY

Key cost drivers and performance
Across the programme, the main cost drivers are payouts, reinsurance, and operational costs, though their relative importance varies by component.

For ARC Ltd, payouts and reinsurance remain the dominant drivers. Financial performance improved in 2025, with a return to profitability driven by lower payouts, improved pricing, and reduced operational costs. Reinsurance continues to be a major structural cost to protect the capital base in a volatile climate context. Despite these improvements, constrained funding and reduced sovereign uptake have affected delivery in some areas, including member‑state support and payout implementation.

For CWUIC, costs are more stable and predictable. Reinsurance is the primary ongoing cost, while operational costs remain low due to CCRIF hosting, which provides shared actuarial, modelling, and administrative services. Targeted premium subsidies are partly offset by investment income. This model enables CWUIC to maintain low overheads while expanding its portfolio and delivering rapid payouts.

For PCRIC, cost increases reflect planned scale‑up following UK capital investment. Key drivers include onboarding new members, expanding hazard coverage, and developing new products. These investments have supported growth in membership and coverage without significant increases in administrative overheads, indicating efficient use of capital.

Overall, differences in cost structures reflect varying maturity and delivery models. ARC faces more variable costs linked to payouts and coverage fluctuations, while CWUIC and PCRIC benefit from more predictable cost bases and stable platforms. Despite this, all three pools demonstrate the value of pre‑arranged finance—providing lower‑cost protection than commercial alternatives and enabling faster, more predictable responses to climate shocks.

VfM performance compared to the original VfM proposition in the business case

For all the risk pools, the single largest contributor to vfm continues to be the effect of risk pooling (buying insurance as a group, on the basis that the same disaster will not happen to all members at the same time). This significantly reduces the cost of insurance in comparison to buying individual commercial contracts.
The RPP continues to deliver strong value for money, leveraging the risk pooling model to provide rapid, cost-effective disaster risk finance for vulnerable countries in Africa, the Caribbean, and the Pacific. The programme’s three main components—ARC, CWUIC, and PCRIC—all demonstrate the benefits of pre-arranged finance, economies of scale, and technical innovation.
The CWUIC investment capitalised a segregated portfolio offering parametric insurance to water and sanitation companies in the Caribbean, operating through CCRIF. This has allowed them to buy into larger service provider contractors flexibly rather than set up their own standalone systems and contracts, providing savings from being part of an economy of scale.
Economy
Across the programme, all three risk pools demonstrate sound economy, showing that pooled, pre‑arranged finance remains a cost‑effective alternative to stand‑alone insurance. This reflects both the benefits of risk diversification and disciplined financial management.

- ARC: Strengthened economic fundamentals through improved pricing discipline, reduced operating costs, and more stable portfolio management. Pool 12A delivered US$84.4m coverage for US$16.8m in premiums, including minimum‑guaranteed payouts, demonstrating continued cost‑efficient delivery. Ongoing renewal planning for Pool 12B and expansion of inclusive insurance products further support affordability and diversification.
- CWUIC: Maintains strong economy through its CCRIF hosting model, which significantly reduces overheads by using shared actuarial, modelling, and administrative systems. This enables competitively priced products for utilities. Investment income (>2%) helps offset premium subsidies, improving financial sustainability.
- PCRIC: The UK capital injection has supported cost‑effective scale‑up, reducing reliance on external reinsurance and enabling expanded coverage (US$39m → US$52m) and membership (5 → 8 countries). This increased diversification strengthens the capital base and improves long‑term affordability.
Overall, the programme remains aligned with the business case, with pooled structures, efficient reinsurance arrangements, and strong financial discipline underpinning cost‑effective delivery.

Efficiency

Efficiency across the programme is generally strong, reflecting the benefits of parametric insurance and pre‑arranged finance, though performance varies between components.

- ARC: Efficient in design, with rules‑based triggers enabling rapid disbursement once payouts are activated. Operational performance improved in 2025, including cost reductions (~30%) and strengthened capital position. However, efficiency is constrained by delays in payout implementation at country level, driven by administrative and financial‑flow bottlenecks outside ARC’s direct control.
- CWUIC: Demonstrates a highly efficient delivery model, with payouts meeting CCRIF’s 14‑day target and enabling rapid restoration of essential services. The combination of low overheads and high coverage relative to premiums reflects strong operational efficiency and value for money.
- PCRIC: Delivered efficient scale‑up, expanding membership and hazard coverage without significant increases in administrative costs. Planned technical assistance and product development activities were delivered on schedule, indicating predictable and efficient use of resources.
Overall, while internal efficiency is strong across all pools, ensuring that this translates into timely on‑the‑ground delivery—particularly for ARC—remains a key challenge.

Effectiveness

 The programme continues to deliver meaningful impact, supporting timely disaster response and strengthening resilience, though effectiveness varies across components.
- ARC: Demonstrates clear impact through rapid parametric payouts supporting government and humanitarian responses (e.g. >US$5.4m to Mozambique in 2025). These resources have enabled timely interventions, including food distribution and response activities. However, effectiveness is limited by delays in implementation and uneven progress in contingency planning and Country Strategy Papers, reducing the consistency of impact.
- CWUIC: Has delivered tangible results through rapid payouts that support restoration of water services following disasters, reducing disruption and recovery time in vulnerable contexts.
- PCRIC: Expanded access to risk finance by increasing membership (5 → 8 countries) and widening hazard coverage (2 → 5 products), improving alignment between country risk profiles and available protection and strengthening preparedness.
Overall, the programme is delivering clear results, but strengthening implementation systems—particularly under ARC—is critical to ensuring that rapid payouts consistently translate into timely and effective support.
Equity

The programme contributes to equitable access to disaster risk finance across highly vulnerable regions, though evidence gaps constrain assessment.
- ARC: Limited progress on post‑payout evaluations restricts understanding of how effectively funds reach intended beneficiaries, including vulnerable groups. Strengthening routine evaluation, including disaggregated data collection, is essential to assess and improve equity outcomes.
- CWUIC: Demonstrates strong equity impact through rapid restoration of water and sanitation services, which are critical for health and disproportionately affect vulnerable groups, including women and girls. Its focus on ODA‑eligible utilities and provision of premium subsidies further supports access for those most in need.
- PCRIC: Expands access to pre‑arranged finance for highly climate‑vulnerable small island states, improving resilience in some of the most at‑risk contexts. However, as the pool grows, stronger post‑event reporting and beneficiary‑level data will be important to evidence equitable outcomes.
Overall, the programme is well targeted toward vulnerable populations but strengthening post‑event evaluation—particularly within ARC—will be key to demonstrating and enhancing equitable impact.
Assessment of whether the programme continues to represent value for money

The Risk Pools Programme (RPP) continues to represent strong value for money, demonstrated across the four value‑for‑money criteria: economy, efficiency, effectiveness and equity. The programme leverages risk pooling to reduce insurance costs and provide rapid, pre‑arranged disaster finance for vulnerable countries in Africa, the Caribbean and the Pacific.
Further improvements in payout timeliness, monitoring, evaluation and capacity building will enhance effectiveness and ensure benefits reach those most in need.

E: RISK

Overview of risk management

The overall risk rating for the programme is Severe.
The ARC Group faced several strategic and operational risks during the review period, though these were actively managed across the year. A key risk arose from the transition in senior management at ARC Ltd; however. The Board acted promptly by appointing a credible and experienced interim CEO to ensure business continuity. As a result, ARC Ltd maintained delivery of its core functions with no reduction in the overall volume of coverage and an improvement in financial performance across 2025.
ARC’s finances improved by Q3 2025, with Class C capital recovering to US$17.5 million, but earlier El Niño-related drought payouts and other losses still created pressure. ARC responded by tightening underwriting, adjusting premium levels, and diversifying into Inclusive Insurance and other non-sovereign products.
Across the other two components, risk levels were comparatively lower. CWUIC benefited from CCRIF’s mature governance, systems, and financial controls, which reduces operational and delivery risk. While the Caribbean remains highly exposed to climate shocks, CWUIC’s hosting arrangement, lean delivery model, and established procedures for payouts help ensure resilience. The key risk for CWUIC relates to the scale and frequency of regional disasters, which may test the pool’s capacity over time.
PCRIC also maintained a stable risk profile during the year. Its expansion from five to eight sovereign members and its broadened hazard coverage introduced additional operational considerations, but the organisation implemented these changes effectively. The main risks for PCRIC relate to ensuring timely payout implementation as the pool grows and embedding robust reporting systems for its newly established logframe. No significant governance, financial, or delivery risks were identified in 2025, and PCRIC continues to operate from a strong institutional base.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

On CWUIC, FCDO works with GAD and CDP (for advice), CCRIF (institutional host for CWUIC) and IDB (two UK-funded grants (technical assistance and premiums) help establish CWUIC.
We have letters of engagement with GAD for technical actuarial work on ARC and CWUIC. GAD offers actuarial services at lower rates than the open market and is provided on an “as needed” basis. GAD review ARC Ltd’s quarterly reports, provide an annual loan evaluation for ARC and CWUIC, and provided hoc support and advice, on the provision of an agreed terms of reference and budget. GAD inputs are timely and insightful, allowing FCDO greater oversight and technical understanding of risk pool activities. They help FCDO challenge and shape the pools’ risk profiling, dynamic financial analysis, capitalisation, underwriting and accounting/valuation policies for example.
In relation to ARC, FCDO has worked with one commercial partner: OPM. FCDO has concluded its independent evaluation contract with OPM for ARC Ltd after the first phase generated substantial findings and recommendations, providing a strong evidence base to inform improvements in ARC’s delivery and impact. FCDO has decided to pause further funding to allow ARC time to absorb and act on these learnings, while reaffirming its commitment to ARC’s role in advancing climate resilience in Africa and encouraging continued internal evidence generation. At the time of termination, the total contract value for OPM’s evaluation was £1,911,290 (excl. tax).

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
FCDO’s grant to IDB to support the establishment of CWUIC includes a budget for a formative evaluation in Year 3, and this is now underway.
GAD also reviews ARC Ltd.’s and CWUIC’s financial statements and narrative reports. These reviews enable FCDO to assess the value of its financial assets. The findings have been used to complete the financial and value for money assessment of this Annual Review.
Evidence
The FCDO has decided to conclude the contract for Oxford Policy Management’s evaluation of ARC Ltd. This decision is the result of a thoughtful assessment of current budget realities, procurement guidance, and the evolving needs of ARC and its stakeholders. Although an extension of the contract was not possible due to ODA budget constraints and governance considerations, the work delivered by OPM to date has established a strong platform for future learning and improvement.
The contract, fully funded by FCDO, will not continue into review period 26/27. While this will mean a reduction in the volume of external evaluation evidence available, FCDO remains committed to supporting robust monitoring and learning at ARC. ARC Agency has committed to supporting ARC’s internal evidence generation, including post-payout evaluation. These evaluations assess the impact of ARC payouts on vulnerable communities, including women and girls, at the request of donors. This collaborative approach will help ensure that ARC continues to generate and use high-quality evidence to strengthen its impact and demonstrates ongoing support from FCDO and its partners for ARC’s learning and improvement agenda. This includes the continued use of OPM’s valuable insights to inform future activities.
Learning
Throughout the review period, FCDO has played an active role in the Peer Review Mechanism (PRM), which reviews the operational and implementation plans for payouts in all ARC member states. The programme team has worked closely with FCDO posts to assess the appropriateness, targeting, and likely impact of these plans, with a particular focus on identifying gaps and opportunities for improvement in ARC’s delivery model. Posts have provided substantive, evidence-based contributions, which the programme team has taken to the PRM and used to refine implementation plans. These lessons have been shared widely across the ARC ecosystem, generating improved know-how and supporting more effective contingency planning.
In addition, the programme team has drawn on insights from external evaluations and quarterly dashboard reviews, as well as engagement with other risk pools such as CWUIC and PCRIC, to inform best practice and drive continuous improvement. Lessons from CWUIC’s rapid payout to Grenada and PCRIC’s expansion in the Pacific have highlighted the importance of timely, well-targeted payouts and robust post-event evaluation for maximising impact and equity.
Looking ahead, the programme team will renew its focus on learning generated from post-payout evaluations, which ARC has committed to increasing. This will be crucial as ARC seeks to attract new sources of finance and continuously improve its impact for vulnerable populations. The team will also work closely with ARC Ltd’s management and board to identify and apply lessons learned in governance, with the aim of streamlining processes and maximising value for money across the RPP. Strengthening routine post-payout evaluations, embedding systematic learning, and sharing findings across all components will be essential to ensure the programme remains responsive, effective, and equitable.

Date of last narrative financial report	ARC Q3 2025 Dashboard (received 23 December 2025) / CCRIF 2025 Annual Report (covering policy year 1 June 2024- 31 May 2025) available at www.ccrif.org	Date of last audited annual statement	ARC 1 January – 30 September 2025 (received 17 February 2026) / CWUIC 1 June 2024- 31 May 2025 audited financial statements received November 2025 (and available at www.ccrif.org).