Programme Completion Review

Title: Productive Social Safety Net Programme
Final Programme Spend (full life): £112,322,798	Review Date:	Initial review: November 2021 / Updated: September 2023
Programme Code: 203473	Start Date: 10/08/2015	End Date: 01/12/2023

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2023
Programme Score	A	A+	A+	B	B	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/41426899.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/90000307.xlsx

A. Summary and Overview

Description of the programme and what it has achieved.

The Productive Social Safety Net (PSSN) programme is the largest UK investment in social protection in Tanzania to date. Launched in 2012 by the Government of the United Republic of Tanzania (GoURT) and the World Bank, the UK joined in 2015 after a decision to more than double the programme’s scope to reach 1.1 million households (HH) from the poorest 15% of the population. UK support co-financed this expansion and our strategic and technical input improved PSSN’s value for money, climate sensitivity and institutional arrangements.

Implemented by the Tanzania Social Action Fund (TASAF), PSSN activities included a Conditional Cash Transfer (CCT) to supplement the incomes of extremely poor HH. The PSSN’s targeting approach combined a geographical poverty index, a community-based targeting tool, and a proxy means test (PMT) to confirm eligible beneficiaries. CCTs consisted of a fixed amount and a variable amount with conditions to incentivise the use of health and education services. Additional amounts were given to HH employed in labour-intensive green Public Works (PW) during the lean farming season to smooth their consumption and build their resilience to climate shocks. A community savings and livelihoods enhancement activity complemented the CCTs by encouraging HH savings and eventual graduation from CCTs.

The initial programme approved budget in 2015 was £110,115,000. In 2020 a business case addendum was submitted and approved for an additional £20m over two years (2020-2022), to respond to the deterioration of incomes and livelihoods caused by Covid-19. The final approved UK budget was £130,115,000 (40% from International Climate Finance). Total UK expenditure against the approved budget was 86% at £112,322,798.

As announced in November 2020, the UK moved to a target of spending 0.5% (instead of 0.7%) of GNI as Official Development Assistance (ODA). Following a portfolio review, FCDO no longer had the budget to make all disbursements in the planned timeframe. The initial project completion review for the programme was completed in November 2021.

In 2022/2023 FY, the United Republic of Tanzania committed to helping its citizens recover from the global pandemic and cushion the effects of rising food, fuel and fertiliser price increases. Support mechanisms offered by government included support through PSSN. In recognition of this strong commitment, and in alignment with UK priorities to protect the poorest during times of instability, the British High Commission committed to disbursing £3m emergency humanitarian funding towards PSSN Phase II activities between April 2023 – September 2023. Other donors included the World Bank, Sweden, Norway, the United States of America, Bill and Melinda Gates Foundation, the International Fund for Agriculture Development, OPEC and the Global Fund.

UK funding supported the TASAF implemented PSSN programme for over seven years, spanning two phases. UK funding was paused during financial year 2021/22 and only recommenced for six months of PSSN II from March 2023 to September 2023.
[note] Phase I of the programme ran from 2015 to 2020 Phase II of the programme runs from April 2023 to September of 2025.

According to the programme midline assessment, after three years of implementation PSSN HHs had enhanced, diversified consumption and improved livelihoods. They were more resilient to shocks and less likely to experience income or asset losses as a result. They were more engaged in trade, owned more assets and were incentivised to keep their children in school and attend health visits. The assessment also found that PSSN contributed to a 10% reduction in basic needs poverty compared with the control group. According to the baseline assessment for PSSN II conducted in early 2023, 71% of PSSN II beneficiary households fall within the bottom two consumption quintiles, compared with the 61% achieved under PSSN I.

Main achievements of the PSSN I programme.

- 10% fewer people living below the basic needs poverty line, by programme close.
- Reaching a peak of 1.1 million HH (5.4 million beneficiaries – 52% women) with CCTs
- 96% of children in beneficiary HH attending health facilities regularly
- 95% of children in beneficiary HH enrolled in primary school with > 80% attendance.
- 7,775 green public works projects delivered in 2,578 villages across the country.
- 253,117 PSSN HH in 44 districts engaged in public works during lean farming seasons.
- 23,618 village savings groups formed and an estimated total of $34 million saved.
- Effective three-step targeting mechanism reaching 100% of HH among the poorest 20%
- Unified Registry of Beneficiaries (URB) developed for faster registration and payment.
- Pilot of e-payments service across 16 Project Area Authorities (PAAs) and improved mechanism for use in PSSN Phase II
  [note] PSSN Programme uses the term PAA, but this is synonymous to Local Government Authorities/ Districts
- By project closure, 88% surveyed recipients reported being fully satisfied with the programme.

Main achievements of Additional 6 months support to PSSN II programme
- Recertification of 267,275 beneficiaries in 51 Project Area Authorities (PAAs) and identification of 78,895 beneficiary households to exit the programme due to their improved income and living conditions.
- 1,356,607 households in 186 PAAs reached with CCTs over two payment windows. Compliance to education conditions is at 98.7% and for health it is 98.9%
- 581,553 HH reached with one round of Public Works payments.
- The National Social Protection Policy has been updated with comments from stakeholders and the Policy Advisory Board and has been submitted to the Cabinet Secretariat for approval.

Summary supporting narrative for the overall score in this review.

The PSSN programme scored an A in this project completion review (PCR). Of the programme’s three outputs, one weighing 40% scored a B, while the other two outputs weighing 40% and 20% scored As.

Output 1: The number of extremely poor and vulnerable HH receiving cash transfers surpassed the target, but the transfers were not always regular and predictable. The target to reach 920,143 HH was surpassed in 2016 when PSSN reached 1.1 million HH. In the last year of the PSSN I programme, 995,500 HH were reached with cash transfers. HH receiving wage payments from public works surpassed the logframe target at 253,117. Severe budget constraints in the latter half of the programme led to a 13 months pause in cash transfers and failure to conduct public works until additional financing was secured. During the six months of additional financing under the PSSN II programme, two rounds of transfers were made to 1,356,607 HH and one round of PW payments were made to 581,553 HH, as double payments, in response to previously delayed payments which occurred during the recertification process. Recertification was rolled out in phase II to assess the eligibility of longstanding beneficiaries (receiving CCTs since 2015) to continue receiving payments as a way for the programme to address a financing gap identified at the start of the programme. The first round of recertification was concluded in 51PAA in which 78,895 beneficiary households out of 267,275 (30%) have been recommended for exit.

Output 2: climate sensitive public works, community assets and livelihoods support improved productivity and resilience. The wage payments received by PSSN beneficiaries taking part in public works compensated for seasonal shortfalls in income and protected against economic and climate shocks. Increased income from community assets allowed HH to increase their productivity and livelihoods opportunities, with the proportion of them owning or raising livestock increasing from 36% to 50%. There was a shift among some HH, from casual labour to self-employment through livelihoods training and savings programmes and the acquisition of higher value agricultural products (e.g., seeds, livestock, etc.). In FY 2023, an additional 19,960 savings groups were reached, surpassing the target set by the programme. Overall, the PSSN programme (PSSN I and PSSN II) reached 152 PAAs with basic livelihood services and established a total of 49,991 savings groups with 671,994 members.

Output 3: Institutions providing systematic social protection in Tanzania were strengthened. PSSN I and II have successfully established the institutions, staffing, routines and governance structures needed to implement an effective national social protection programme. PSSN strengthened TASAF’s capacity in procurement, financial management, environmental safeguards, research, ICT and monitoring. A Unified Registry of Beneficiaries (URB) was established, improvements have been made to the management information systems (MIS), education and communication campaigns and a Grievance Reporting Mechanism (GRM) continue to be operational with emphasis on raising awareness among beneficiaries of how to report complaints.

Adaptions during the Covid-19 Pandemic: In line with global best practice, FCDO Tanzania identified social protection as a key mechanism to protect vulnerable populations from the socio-economic impacts of Covid-19. FCDO commissioned a report to model newly vulnerable groups and develop a targeting plan for an emergency cash transfer. A costed extension for £20 million was approved by ministers to reach an additional 300,000 HH made newly poor by the pandemic. Up until early 2021, GoURT’s Covid-19 strategy was one of non-intervention and, steered by TASAF and other donors, they decided to retain PSSN’s focus on chronically poor, rural, populations. A pause on UK financial aid to government following Tanzania’s national elections in November 2020, UK ODA reductions, and subsequent budget reductions in early 2021 limited the ability to disburse the additional funds agreed under the Business Case amendment. In 2023, in light of the worsening economic situation caused by Covid-19 and Russia’s invasion of Ukraine, resulting in high food, fuel and fertiliser prices, UK support was extended, and a small amount of approved humanitarian funding disbursed to support GoURT efforts to cushion the impacts of these price shocks on the most vulnerable.

Major lessons learned, evidence generated and recommendations.

Social protection is a cost-effective intervention with multiple impacts on poverty reduction. Evidence from the RCTs conducted during the midline impact assessment found a poverty reduction of 10% among beneficiary HH. Cash transfers improved children’s educational enrolment, ownership of productive assets and household consumption and dietary diversity. The PSSN climate assessment highlighted the potential for climate resilience to be improved through generations as children attend school, are employed, or become self-employed, and reduce their reliance on land for livelihoods. The PSSN public works component was essential in stabilising household consumption during the lean seasons. Sustained FCDO support for social protection in Tanzania could improve the population’s resilience to shocks and multiply the impacts of the UK’s human capital and climate investments.

Supply side assessment and inter-ministerial coordination must be incorporated from the start. The PSSN programme included a variable part transfer to HH based on compliance with verifiable conditions (school attendance of children under 18 and maternal and child health visits). While these conditions incentivised the use of government provided services, less focus was paid to the availability or quality of these services. As a result, while PSSN was found to improve health seeking behaviours, there was no accompanying decrease in the prevalence of the most common illnesses affecting children or increase in their educational attainment. Better sectoral coordination between Ministries (PORLAG, MOEST, Ministry of Health and TASAF under the State House) was needed to meet the increased demand with improved availability, access and quality of basic services.
[note] President’s Office Regional and Local Governments (PORALG), Ministry of Education Science and Technology (MOEST),

Longer term investment is needed to support HH to fully exit chronic poverty. While there is strong evidence to suggest PSSN protected HH from shocks and diversified their livelihoods opportunities, there is only limited evidence that it provided the foundations from which to graduate out of extreme poverty. A preliminary assessment during the validation exercise for PSSN II in 2021 indicated only 1600 HH out of 1.1 million (1.5%) graduated from PSSN citing the accumulation of adequate benefits to continue their livelihoods without the programme. Following recertification, we have anecdotal evidence that the graduation rate is closer to 5% although this needs to be confirmed through the annual reports. Follow up evaluations of PSSN II should seek to assess outcomes over a longer timeframe to test for intergenerational benefits in human development outcomes, such as reductions in child stunting and malnutrition and increased educational attainment.

Donor coordination is essential to manage the multiple demands on implementing partners. Several donors supported the PSSN programme alongside the World Bank. Core PSSN contributors included the World Bank, UK, SIDA, NIDA, USAID, IFAD, Norway, Ireland; while others earmarked their contributions for specific components (OPEC, Global Fund). A donor governance mechanism was developed, chaired by the World Bank with a rotating donor co-chair seat. Donors joined six technical working groups led by TASAF, leading to more coordinated resource management, joint monitoring, and policy dialogues. Nevertheless, conflicting demands from donors coupled with gaps in grant management capacities within TASAF remained a challenge until 2019, prompting even closer alignment among the donor group through consolidated progress reports, joint field missions and audits, etc.

Include clear progress indicators on timeliness of cash transfers and the impact of pauses. The PSSN programme experienced budget constraints from the beginning of 2019 until closure, leading to a 13-month pause in regular cash transfers and failure to pay wages for public works in a timely manner. Improved monitoring and management of programme expenditure, higher weighting placed on consistency of payments and evaluation of the impact of payment pauses on beneficiaries should be considered in the design of future social protection programmes. PSSN II should carefully consider the impact of budget constraints, political imperatives and wider contextual changes on the consistency and timeliness of cash transfers and adjust plans early to mitigate impact of pauses to beneficiaries.

Design realistic, phased exit strategies to transition CCTs responsibly to government. The original business case envisaged GoURT would increase financial commitments to reach 100% of the costs of PSSN by 2024. Although PSSN started with strong political will, this waned from 2016 due to limited fiscal space and competing priorities. As such GoURT cash contributions (excepting the IDA concessional loan) did not exceed 1% of the total costs. Experience from neighbouring countries such as Kenya reveal longer timeframes (over 17 years in Kenya’s case) and moderate cost sharing agreements are needed to see incremental government financing of social protection. A phased transition plan should have been developed at design stage, and a capacity programme and financing strategy implemented and adjusted as needed. Future programs should undergo robust and regular financial and political economy analysis to test whether our policy ambitions remain viable, trigger adjustments to the Theory of Change, and inform programme adaptations and influencing strategies.
[note] It was estimated that $90,9 million in-kind contributions from GoURT were realised over the life of the programme.

How this report was conducted

This PCR was compiled from two phases. The first phase was completed in 2021 from a desk review of TASAF progress reports covering the PSSN implementation period, Joint Review Missions undertaken by the World Bank and other donors, and various studies and evaluations commissioned through the course of the programme including beneficiary surveys and random control trials. An independent reviewer from the UK previously unconnected to PSSN provided an objective analysis of the programme’s performance against logframe outputs (Section C). In addition, interviews were conducted with TASAF officials involved in the delivery of PSSN, donor partners and FCDO staff involved in managing the programme. As the programme had already ended, we were not able to organise a specific field visit to observe payments under PSSNI but have previously observed payment windows during 2017 – 2019 (see Section E). A case study of a PSSN beneficiary is attached at Annex 1.
The second phase was completed in September 2023 from a desk review of TASAF progress reports covering the PSSN implementation period, Joint Review Missions undertaken by the World Bank and other donors. The second phase is light touch and updates the original content to reflect additional £3m that was disbursed by the UK in March 2023.
Actions following approval of this report.

Satisfactory audit assurances have been provided by the Comptroller Auditor General (CAG) report of the PSSN programme received in March 2020 and follow up actions all completed by March 2021. Further review of the CAG report of the PSSN programme in 2023 will be considered and any outstanding actions followed up prior to closure. There remain a few outstanding closure actions that will be completed after approval of this PCR:

- Final budget reconciliation and closure of all component budget lines
- Upload final PSSN logframe final results onto Development Tracker
- Check all documents on Development Tracker are accurately loaded and remove incorrect items.
- Hold a lesson learning session with BHC Tanzania and social protection policy teams in UK/ region.
- Send archiving checklist to Development Director and archive the programme by March 2024

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£110,115,000	£109,322,798 expenditure / (99% of original, 85% of revised amount)
Timeframe	5 years (August 2015 – July 2020)	years (August 2015 – January 2022) / (April 2023 – September 2023)

Overall assessment of programme outcomes, sustainability and VfM

PSSN sought to improve the life chances and reduce the vulnerabilities of poor and vulnerable Tanzanians by establishing a sustainable safety net and improving coping strategies in times of economic hardship. PSSN was intended as a foundational cash transfer scheme upon which a national social protection system could be established. As a consequence of lack of prioritisation and political support, this latter long-term goal has not yet been achieved, but recent discussions in parliament on the social security and pensions bill may provide a possible point at which to re-engage government on this important policy. In 2023, the draft National Social Protection policy has been updated with comments from stakeholders and the Policy Advisory Board and has been submitted to the Cabinet Secretariat for approval. The additional £3 million funding to the programme does not have a bearing on the overall programme at impact level, as that funding was for a 6-month period, supporting two rounds of CCTs and one round of public works payments.

Progress against impact and outcome indicators
Original Indicator	Revised Indicator	Target at July 2020	Progress
Impact 1: Improved household income and consumption	Proportion of HH with consumption below the adjusted poverty line	70%	64% - Partially Achieved / While the indicator intended to measure the efficiency of targeting it may indicate beneficiaries became less poor over the course of the programme.
Impact 2: Improved anthropometric measures	Proportion of beneficiaries’ HH with an increased food consumption	30%	43.7% - Achieved.
Outcome 1: Government takes two concrete steps to establish evidence-based climate sensitive social protection system	Unchanged	Climate change recognised by national structures as an integral part of social protection systems. / NSPF vision and policies promote climate resilience.	Climate assessments mainstreamed in public works. / National thematic working group within TASAF on Environmental Safeguards / Draft NSPP includes climate resilience, but policy is not yet approved by the Cabinet. / Partially achieved
Outcome 2: Reduction in HH selling productive assets to cope with climate and/or other shocks.	Reduction in HH using negative coping strategies to cope with climate and/or other shocks	15% reduction in negative coping strategies.	HH reduction of negative coping strategies by 16.1% / Achieved
[note] All indicators were updated in 2018.

Programme performance against impact and outcome indicators

% of Benefit Incidence to Lowest Quartile
Impact 1: This indicator sought to measure the effectiveness of the PSSN targeting mechanism. Targeting aimed to reach the 15% poorest HH (10% extreme poor, 5% transient poor). A three-stage targeting mechanism was used combining geographical prioritisation, community knowledge to identify the poorest HH in each geography, and a proxy means test (PMT) to verify household eligibility. At midline, 100% of PSSN HH were assessed in the poorest 20%, while 64% came under the nationally adjusted food poverty line, against targets of 85% and 70% respectively. According to the baseline evaluation, PSSN outperformed other CCT programmes with one of the highest shares of beneficiaries in the lowest consumption quintile of any CCT as shown by the adjacent graph.
[note] Rosas, Nina & zaldivar, samantha & Pinzon-Caicedo, Mariana. (2016). Evaluating Tanzania's productive social safety net: targeting performance, beneficiary profile, and other baseline findings.

Impact 2: The end target to enable 30% of beneficiary HH to increase their food consumption was surpassed at the time of the midline impact assessment with 44% of HH increasing their food consumption. The assessment also noted that PSSN HH ate more diverse diets when looking at the number of food groups consumed within the past seven days of being surveyed. While PSSN improved both dietary diversity and increased utilisation of health services, impacts on child health outcomes have not yet been observed and may take longer to materialise.

Outcome 1: At the national level, there has been some progress in achieving climate sensitive social protection systems, most importantly within the public works component. With support from UK technical assistance a draft national social protection policy was developed covering climate sensitive social protection, although this draft has not been formally approved by Cabinet due to a lack of prioritisation.

At PAA level, 60% of public works included climate resilient activities such as afforestation, soil and water conservation activities, and protective structures to prevent sea water expansion to farms. This resulted in the use of climate risk assessments to inform multi-year plans in more than 70% of the 44 local government areas that participated in the pilot projects.

At individual level, cash transfers had a positive impact on climate sensitive behaviours within HH, particularly their fuel usage. The impact assessment found HH in the treatment group were 3.9% more likely to use solar fuel for lighting purposes when compared to the control group.

Outcome 2: cash transfers reduced household’s use of negative coping strategies (selling of productive assets, withdrawing children from school, etc.) by 16% in response to shocks. The likelihood of income or asset loss was also reduced by 4.3%.

VFM analysis

An in-depth VfM assessment carried out in June 2019 found the programme provided good VfM at economy, efficiency, and effectiveness levels, in line with international experience. In relation to economy, all procurement activities were implemented under prepared and approved procurement plans. TASAF was awarded a Certificate of Recognition for compliance with the national Public Procurement Act (PPA).

The PSSN programme was delivered and facilitated through existing GoURT structures at central and local levels which reduced overhead costs. Further efficiency gains were attained with the pilot of an e-payment system using the existing GoURT e-payment gateway. The admin costs for PSSN’s conditional transfers (generally more expensive than non-conditional) came within globally accepted ranges at 13%.

The PSSN programme has been effective at reducing poverty amongst beneficiaries and increasing food consumption, surpassing both targets set. Furthermore, effectiveness in achieving the desired social and economic impacts can be measured using the Total Cost to Transfer Ratio (TCTR). At the first year of set up, the TCTR ratio was 5 as expected due to front-loading of set-up costs. This fell to 3.6 in the second year and 1.3 in the third yielding an average of 1.8. The final ratio was 1.15.

Equity Central to PSSN’s aim of reaching 15% of the poorest HH was to target the extreme poor, many of them women, elderly, those living with a disability or with caring responsibilities. Disaggregation is only available at head of household level, as follows: 12.7% were over 60 years, 85% were women, 2.5% had a disability and 18% of HH has a child less than 5 years. The PSSN gender assessment found public works projects achieved double the participation of women in temporary employment than predicted, while saving groups increased women’s incomes and enabled them to acquire more assets.

Summarise the programme’s theory of change and results framework, including any changes

The Theory of Change, while largely robust, should have been revised during the course of the programme to reflect three core assumptions not holding. This would have enabled greater programme adaptation.

The envisioned outcome of a ‘sustainable safety net laying the foundation for a national social protection system’ relied on strong political appetite for social protection schemes, and financial commitments to fund these from domestic budgets. While the national social protection policy and strategy was drafted, political will to see this enacted waned ahead of the 2020 election. The national budget contributions to the PSSN were never fully disbursed due to competing demands on domestic finances and changes in the political context. Thus, although the institutional architecture for a social safety net was established, a clear policy embedding this within broader social welfare systems (e.g., pensions, national insurance) is outstanding.

The output of ‘regular, predictable cash transfers to extremely poor and poor HH’ relied on predictable financing from the World Bank, GoURT and donor partners to cover CCTs for 1 million HH alongside the development of public works and livelihood enhancement activities. Sustaining these ambitious outputs was contingent on GoURT’s ability to raise and maintain additional financing to meet the shortfall in the budget. As a result of repeated low disbursement of GoURT committed budget, coupled with delays in accessing additional World Bank financing, the programme experienced pauses in payments. There was a 13-months pause in regular cash transfer under PSSN I that began in 2019. No pause in payments during PSSN II (September 2020 – date) but delays in payments have occurred intermediately including during the six months of additional support from the UK.

Assisted by ICF financing, investments in green public works were aimed at an additional outcome to ‘reduce vulnerability to climate shocks’ by smoothing consumption during adverse climate events and preventing harmful coping mechanisms. As a result of budget constraints, public works never went beyond the pilot stage, limiting the number of HH supported to smooth their consumption during the lean season. Where PW were effective, they created community assets and enabled communities to mitigate against the impacts of climate change. Additional support is needed to ensure community assets are maintained after the programme ends, which should have been factored in as an original assumption in the TOC.

Changes to Logframe Output Indicators undertaken during the lifetime of programme implementation.

#	Output Indicator	Revised / Additional	Reason for Change
1.1	Number of HH enrolled in the programme and receiving conditional cash transfers	Numbers of: / HH enrolled in the programme and receiving conditional cash transfers and; / HH receiving regular wage payments from public works. / All disaggregated by sex of head of household	Merged 1.1 and 1.2 together into one indicator
1.2	Number of HH receiving regular wage payments from public works (disaggregated by sex of worker)	Proportion of HH receiving timely and predictable PW benefits	Updated to match TASAF / World Bank programme result framework
1.3	Percentage of payments made within 5 days of due date	Learning from PSSN I is reflected in the design of PSSN II to ensure the programme payment system is cost effective and reaching the right beneficiaries	Updated to match TASAF / World Bank programme result framework.
2.1	Number of climate proofed community assets created	Proportion of projects identified by the climate risk assessment that include measures for reducing climate risk or improving climate resilience	Clarification of indicator for improved measurement
2.2	Number of beneficiaries directly and indirectly supported to cope with effect of climate change (directly – recipients of cash transfers, indirectly – communities with climate sensitive assets created)	Number of public works project created at the community level.	Clarification of indicator for improved measurement
3.1	National Social Protection Framework developed	PSSN aligned with National Social Protection Policy developments	Clarification of indicator
3.3	Unified Registry of Beneficiaries established in all programme districts	Effective communications and accountability systems to PSSN beneficiaries are in place and operational	As indicator 3.3 was achieved in 2018, we replaced the indicator with one that monitors TASAF’s communications and accountability approach

## C. DETAILED OUTPUT SCORING
Output 1	Regular, predictable cash transfers to extremely poor and vulnerable HH
Output Score	B
Impact weighting (%)	40%	Impact weighting revised since last AR?	N

Output Indicator	Final Logframe Target	Final Result Achieved
a) Numbers of HH enrolled in the programme and receiving conditional cash transfers / b) HH receiving regular wage payments from public works / This indicator is disaggregated by sex of head of household.	920,412 / 250,000	Partially Achieved / 995,500 existing HH reached in February 2020 with double payment. / 1,356,607 existing HH received two rounds of cash transfers in March and April 2023 / 321,975 HH on registry but did not complete work or receive payments in the reporting year due to agreed pause in component. / 581,553 HH received one round public works payment in 2023. / Disaggregation: / 56% of HH recipients are female / 44% of HH recipients are male / 38% are children 6-18 years / 6% are children 0-5 years / 40% are of productive age / 16% are over 60 years / NB these figures will not sum 100%
1.2 Proportion of HH receiving timely and predictable PW benefits	80%	Not Achieved / Due to budget constraints during transition from PSSN I to PSSN II, no public works payments were made during the reporting period. / Public works payments were made in June – July 2023 but these were delayed payments that should have been made in the January – February window
1.3 Learning from PSSN I is reflected in the design of PSSN II to ensure the programme payment system is cost effective and reaches the right beneficiaries		Achieved / Payment mechanism within PSSN II reflects key findings of e-payment pilot to ensure payments are timely, regular, and cost-efficient. PSSN II approach incorporates re-certification strategy.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative score.

Between 2015 and 2020, UK support enabled the PSSN programme to provide 31 consecutive bimonthly payments to targeted HH at a maximum amount of 38,000 Tanzanian Shillings (Tsh), or £12 between 2015 – 2020.
[note] Conversion correct at 08/10/2021.

Payments were received predominantly by female household members consisting of a fixed and variable transfer based on compliance with educational and health conditionalities. HH located too far away from schools and health facilities were waived from compliance requirements and received both the basic and variable tranche if they were eligible. Public works were targeted at eligible HH with at least one work-able adult between the ages of 18 and 65, not pregnant beyond four months, or having a disability.

Under PSSN an ambitious, comprehensive, and well-targeted social safety net system was set up from the onset. After one year of implementation 1.1m HH (5.4 million beneficiaries) were receiving CCTs over half of whom were women. PSSN used a three-stage targeting system consisting of a geographical mechanism to identify the poorest districts, wards, and communities; a community-based targeting approach to prepare a preliminary list of extremely poor and vulnerable HH. Finally, a proxy means test (PMT) was applied to HH to verify their eligibility.

Finalised in 2019, the independent mid-line assessment used Random Control Trials (RCT) to assess the change in poverty levels after three years of implementation. It found that 68% of HH in the control group lived below the national basic needs poverty line, but only 61.1% of PSSN HH did - a 6.9% change. When adjusted for the total population rather than the number of HH, this results in a 10% reduction in poverty reduction relative to the control group. PW wage payments were intended to boost family consumption and build resilience to livelihood shocks, while linking beneficiaries to skills training, agricultural and other livelihoods interventions to help them to graduate from PSSN. However, with the budget constraints resulting in both PW and LE activities remaining in pilot stages, this loop was not fully implemented, and the full graduation strategy was not realised in the lifetime of the programme.
[note] https://documents1.worldbank.org/curated/en/150071582090321211/pdf/Evaluating-Tanzania-s-Productive-Social-Safety-Net-Findings-from-the-Midline-Survey.pdf

Budget constraints linked to low disbursement of planned GoURT allocations and delays in agreeing additional World Bank financing led to some activities being delayed, and indicators remained unmet at closure. A decision was made to slow the implementation of the public works component and output indicator 1.2 was not achieved as a result. Despite these measures, PSSN I funds were exhausted by early 2019 and there was a gap in payments from March 2019 until February 2020. FCDO (then DFID) and SIDA agreed to frontload resources to support a double payment in February 2020 for 995,500 HH. The decrease against the original 1.1m HH is due to beneficiary deaths, reallocation to areas where PSSN is not operational, or absence on payment day.

During the pandemic, CCTs followed guidelines rapidly developed by TASAF and UNICEF to mitigate risks and ensure safe transfers such as physical distancing, provision of handwashing stations and temperature checks at payment days, etc. The World Bank estimated that Covid-19 risked pushing some 500,000 people below the poverty line, particularly those in urban settings relying on self-employment and informal/micro enterprises. Rapid studies by the World Food Programme estimated that up to 2.1 million people may require food assistance as a result of the socioeconomic impacts of COVID-19 in Tanzania.
[note] World Bank (2020) 14th Tanzania Economic Update: Addressing the Impact of Covid-19
[note] Tanzania Food Security Overview Context of COVID-19

No formal evaluation was conducted of the impact of the payment pause, but global evidence suggests interrupted CCTs erode recipients’ ability to plan and invest. Given this time period coincided with brief Covid-19 economic lockdown measures, there is likely to have been a dual impact on beneficiaries. A UNICEF research paper monitoring the impact of Covid-19 on adolescents living in PSSN HH found that one in three reported the use of negative coping strategies. Unfortunately, the mid-line evaluation had concluded prior to the pandemic and there was low appetite among TASAF to conduct specific Covid-19 related studies given GoURT’s position at the time.
[note] UNICEF Tanzania, University at Buffalo, TASAF, EDI Global, 2021. Real-time Monitoring of COVID-19 Impacts Among Adolescents and Young People, Their Families, and Communities in Southern Highlands Region of Tanzania.

During the second phase of UK support from 2023, which recommenced after a pause from November 2020 to March 2023, two further bimonthly payments occurred in March – April and May-June 2023 reaching 1,356,607 households. In addition, the successful scale up of the public works component (PW) during the time UK funding was inactive, meant 581,553 households received an additional £11 for 15 days of work per month, for a maximum of 60 days during the lean season.
[note] HH with at least one work-able adult between the ages of 18 and 65, not pregnant beyond four months, or having a disability.

Assess the VfM of this output based on performance over the past year and the programme lifetime

The following qualitative assessment against the 4Es (Economy, Efficiency, Effectiveness, Equity) finds that the programme offered good VfM against the original proposition.
Effectiveness: The programme was found to target well compared with similar cash transfer programmes. For example, 100% of beneficiaries were assessed to be in the bottom 20% for national food consumption. PSSN contributed to the expected impact of improved life chances and reduced vulnerability for poor and vulnerable people in Tanzania, with the World Bank’s 2019 Tanzania Mainland Poverty Assessment reporting that that PSSN had been effective in enabling HH to move above the poverty line: “Without PSSN [..], poverty would have been about 2% higher, which translates to an additional 1 million poor people, and extreme poverty would also rise from 8% to 9.2%, equivalent to 700,000 more people.”
[note] https://openknowledge.worldbank.org/handle/10986/33031

Equity: Over half of all beneficiaries of the programme (56%) are female, while households with disabilities accounted for (13%). Moreover 84% of single headed households in receipt of cash transfers were women. There is some evidence the programme had positive impacts on women’s roles in household decision-making, for example in decisions about reinvesting their own earnings, their children’s health and education and household purchases. Aside from ensuring people with disabilities received assistance and putting in place special provisions to ensure they could access cash transfers, there is a noticeable lack of wider attempts to analyse the impact of CCTs on people with disabilities.

Economy: The CCTs utilised a decentralised low-cost model using Community Management Committees (CMCs) to facilitate cash payments to beneficiaries. Administration costs as a percentage of total programme costs ended at 13%. The final total cost: transfer ratio was 1.15 and is equivalent or lower than many other East Africa based CCTs.
[note] Marito Garcia and Charity M. T. Moore (2012), ‘The Rise of Cash Transfer Programs in Sub-Saharan Africa’
Efficiency: An electronic payment system was piloted in 16 PPAs in 2019-20, improving the efficiency of cash transfer payments. During the first payment window of PSSN II, approximately 50% of beneficiaries of 16 pilot Project Area Authorities (PAAs) were paid electronically.

Lessons learned through this output, and recommendations for future programming.

- Payment pauses can have serious impacts and can jeopardise the programme’s aims. Insisting on realistic budgets and phased financing strategies is needed to avoid disruption to cash transfers.
- To achieve transformational programme impacts, social protection programmes like PSSN require extensive supply side contributions achieved through close inter-ministerial coordination. Current gaps in basic service accessibility and quality must be considered when designing conditional cash schemes, and donors should look to support complementary basic service activities alongside.
- FCDO did not revise the logframe sufficiently to reflect the agreed pause in public works resulting in some of the indicators scoring a B in the penultimate Annual Review in 2020 and this PCR.
- The full realisation of graduation from CCTs takes longer than the life of a five-year programme.
- Other FCDO social safety net programmes could learn from the hybrid approach to targeting.

Output 2	Community assets created which reduce vulnerability to climate change and increase resilience to shocks
Output Score	A
Impact weighting (%)	40%	Impact weighting revised since last AR?	N

Output Indicator	Final Logframe Target	Final Result Achieved
2.1 Proportion of projects identified by the climate risk assessment that include measures for reducing climate risk or improving climate resilience.	60%	Achieved / 60%
2.2 Number of public works projects created at the community level.	3700	Achieved / A cumulative total of 7775 public works projects were created at community level by 2019.
2.3 Proportion of communities with climate risk assessments incorporated into multi-year plans.	70%	Achieved / 70% over lifetime of programme.
2.4 Livelihoods strategy developed and begins implementation.	Livelihood strategy implemented as per work plan	Achieved / Training of trainers on basic economic skills was conducted for 180 facilitators in 6 PAAs. / Further activity was delayed due to budget constraints and Covid-19.

Briefly describe the output’s activities and achievements and provide supporting narrative score.
Given the relationship between extreme poverty and climate vulnerability, PSSN sought to build communities’ climate resilience. 7,775 subprojects in 2,578 villages worth TZS 119 billion were identified and implemented by community members. Examples of projects implemented included afforestation and tree planting, rural access roads, agriculture and irrigation, environmental conservation and soil and water conservation. A 2019 TASAF commissioned impact assessment of the public works found subprojects had positive impacts on natural resource conservation and mitigation of climate change effects. The same report found 97.2% of HH reported increased consumption-based benefits. PW involved identification and implementation of projects with potential for improved productivity and climate resilience at community levels. To meet the minimum standards for projects, PW needed close involvement of regional and district officials including, project-specific technical support. This was not always well coordinated or accessible.

In the context of severe budget constraints and limitations on public gatherings during the Covid-19 pandemic, GoURT decided to delay further roll out of the public works component until 2021. The logframe contains cumulative output indicator targets which were already achieved by 2019 and subsequently not increased due to the decision to pause the component. During the final year of review there were no new community assets created or public works projects undertaken.

In the first phase of support to the PSSN programme, 2015 – 2020, planned livelihoods enhancement activities were rolled out with 375 village livelihood enhancement committees formed, 23,618 savings groups established and 319,940 individual savers with cumulative savings of over Tsh 7.9 trillion ($34 million). Training of trainers on basic economic skills was conducted for 180 facilitators in 6 PAAs, with the aim of trainers to cascade this to cash transfer recipients. A total of 42,324 beneficiaries in the same 6 PAAs were trained on basic skills, including development of business plans to help them prepare for applications for productive grants as part of a planned graduation scheme. Initial assessment noted the need for further work to integrate them within existing supportive infrastructures, especially linking them with existing livelihood enhancement programmes led by GoURT under the 10% Empowerment Loans Fund and by civil society organisations.

Under PSSN II period of support, 14,022PW subprojects that had begun in 2022 were completed. Payments made for PW beneficiaries in the June – July payment window, covering work completed between September to November 2022. From April 2023, the programme started screening for subprojects to be implemented in 123 PAAs in the 2023/24 FY. There have been delays in the selection, preparation and completion of subprojects, attributed to challenges within local procurement and lack of inputs from PAA experts to support local service providers. These concerns have been raised and will be taken up by relevant PAA authorities and be reported against in the next mission report.

The livelihood enhancement activities, had not expanded past the pilot phase at the end of PSSN I. During the 2022 – 2023 phase of support, the target for the 2023 – 2024 FY is to reach 50,000 HH with productive livelihood grants. To date, 43,877 beneficiaries have received the first livelihood productive grant instalment and 20,255 received their second. Initial assessments following field visits indicate early signs of increased investment in income generating activities from recipients of the productive grants.

Assess the VfM of this output based on performance over the past year and the programme lifetime

Effectiveness: although too ambitious for the budget available, PW realised 90% of its desired impacts on consumption smoothing and the creation of productive assets. The mid-line assessment did not find a significant difference in the benefits experienced by groups undertaking CCTs alone vs CCTs and PW. Due to the pause in implementation of the PW programme, a more meaningful comparison should be carried out in PSSN II to compare the complementarity of implementing CCTs alongside public works.

Efficiency: While no formal metric of efficiency was established, an assessment by Alpha and Omega Consulting Group in 2019, found no evidence of major adverse effects on core socioeconomic activities from participation in the public works programme. Only 16.8% of HH surveyed reported a temporary shortfall in agricultural output from their participation, offset by individual wage and community benefits.

Economy: According to the final TASAF report which used a narrow definition of administration costs, the implementation cost of PW was 13% against an ambitious target of 12%. Many Local Government Authorities (LGAs) found the administrative burden of planning and implementing PW heavy and reported that their time supervising works was not adequately remunerated. Further research on the full range of design, administrative and maintenance cost inputs is needed prior to embarking on similar PW projects.

Equity: Women’s participation in PW exceeded the target of 40%, with women making up approximately 70% of those engaged in public works. The implementation of gender sensitive guidance, (provision of light work for pregnant or breastfeeding women) varied across project locations and should be more consistently applied in PSSN II. Additional positive practices beyond those required in the PW manual, such as putting in place childcare arrangements, were implemented in some localities but not all.

Lessons learned through this output, and recommendations for future programming.
- TASAF and partners to build on learning from the climate assessment (section E) in PSSN II
- Future PW should cost the full range of design, administrative and maintenance inputs needed prior to embarking and ensure adequate technical support is available at the right levels.
Output 3	Social protection institutions established and functional
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	N

Output Indicator	Final Logframe Target	Final Result Achieved
3.1 PSSN aligned with National Social Protection Policy developments	PSSN II design and National Social Protection policy are aligned and mutually supportive.	Achieved
3.2 Impact evaluation conducted, and findings used to inform policy.	End line Impact Evaluation final report	Not Achieved / The Midline Impact Evaluation Report was produced one year behind schedule and disseminated but the End line Evaluation was merged with the baseline for the PSSN II programme.
3.3. Effective communications and accountability systems to PSSN beneficiaries are in place and operational	Effective roll-out and implementation of new communications and grievance mechanisms in PSSN II.	Achieved / 90% of grievances were resolved in a timely manner.

Briefly describe the output’s activities and achievements and provide supporting narrative score.

At programme close, PSSN II project activities were in full alignment with a draft National Social Protection Policy.

In 2017/18 FCDO, via UNICEF, provided technical assistance to the GoURT to develop a national Social Protection Policy led by the Ministry of Labour under the coordination of the Prime Minister’s Office. While political will for social protection was high during the design of PSSN, appetite, especially for national cash transfers, waned over the course of the programme. Cabinet approval for the policy was delayed due to the 2020 election.

In 2023, the draft National Social Protection policy has again been updated with comments from stakeholders and the Policy Advisory Board and has been submitted to the Cabinet Secretariat for approval. This is a promising step towards fully codifying social protection, including the PSSN mechanism, into state policy and law.

TASAF’s National Steering Committee was established in early 2012 but having lapsed, was reconstituted in 2019 and is chaired by the Permanent Secretary of State House, to date. This demonstrates increasing buy-in and ownership from GoURT.

Baseline and mid-line evaluation data was analysed and effectively disseminated to government through a number of briefings and in person meetings. As a direct result of budget constraints, a decision was taken to merge the end-line survey data collection of PSSN Phase 1 with the baseline data collection of PSSN phase II. The baseline report for PSSN Phase II was finalised in June 2023.

A new output indicator was added in 2018 to track the effectiveness of a Grievance Redress Mechanism (GRM) system. As of 2020 the GRM has been effective in all PAAs. A total of 92 grievances were received through the call centre between January and March 2020, and all received feedback. 83% of grievances related to delays in PSSN payments, 11% focused on PSSN’s targeting process, 30% on the expansion of PSSN II to other villages, and the remaining 6% were related to challenges with e-payments. At the end of the programme, 90% of grievances were resolved in a timely manner based on the final implementation report.

Between January to June 2023, 4,422 grievances were filed, of which 71% have been resolved and closed. Most grievances reported are related to payments. Further awareness raising will be conducted on availability of tool to address non-payment related grievances.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Economy: TASAF is embedded within existing government structures, which saves costs compared to establishing parallel structures.

Efficiency: Over the course of this programme, modifications were made to improve system efficiency which will bear greater dividends in PSSN II. For example, the proportion of registered HH with updated school and health information necessary to assess compliance was 90% against a target of 80%. Through additional controls and guidance developed by TASAF, PSSN built institutional structures and capacity for effective programme management at national, regional, PPA, ward, and community levels. These measures include having a functioning computerised Management Information System (MIS) and Unified Beneficiary Register (URB) capturing the full profile of over 1 million HH.
Lessons learned through this output, and recommendations for future programming.

- The long-term sustainability of PSSN relies on it being formalised through a government-led social protection policy and accompanying implementation strategy. Linked to this, TASAF would benefit from being more embedded within line ministry structures with a policy instrument that underpins its operations as well as having direct oversight from State House.
- A comprehensive end-line review would aid evaluation especially on the impact of the CCT pauses on beneficiaries’ chances of graduating from PSSN CCTs and the added benefit of a combined CCT and PW payment to the same HH.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

At the time of writing the Business Case the PSSN programme was classified as ‘Medium’ risk but was revised to ‘Major’ from the start of implementation and remained so throughout all annual reviews. FCDO kept an updated risk register as part of the delivery plan. During implementation the key risks that impacted the programme and their mitigating actions are outlined below.

Policy & Programme Delivery: Risks centred on low GoURT disbursements against commitments leading to an inability to embed PSSN into the broader social protection framework. Although mitigating actions were put in place through joint donor efforts, domestic funding to the programme did not meet the intended levels by programme closure. Budget constraints experienced from 2018 onwards impacted on the affordability of the ambitious workplan. While FCDO flagged this during our annual reviews and stakeholder meetings and tried to mitigate the worst impacts on beneficiaries by frontloading funds for emergency transfers, we could not prevent the pause in CCTs that occurred from mid-2019 to early 2020. The GoURT has continued to pledge financing into the PSSN II programme, and in 2023 has committed to financing 1% of the 2023/4 annual budget, increasing to 3% of the annual budget by 2024/5. The development of a medium-term financing framework for PSSN II have been written into the disbursement-linked targets for a World Bank Development Policy Operations (DPO) grant.

FCDO monitored potential negative impacts of the PSSN programme on women’s burden of unpaid work. To mitigate this FCDO ensured that PW guidance manuals supported women’s participation in wage labour. Field visits and monitoring reports found good consideration of reduced hours and labour types.

Strategy and Context. While social protection institutions were established and strengthened within the programme’s lifetime, a lack of clear policy framework and legislation for social safety nets was a materialised risk for the long-term sustainability of cash transfers in Tanzania. While FCDO, via UNICEF, provided technical assistance to support GoURT to develop a National Social Protection Policy (NSPP), there has been limited traction in getting this approved by Cabinet exacerbated by the 2020 elections and by Covid-19 depleting GoURT’s budget. In 2023, following two successful years of PSSN II and the increasing importance GoURT is placing on social protection as budgetary tool, the NSPP is now awaiting Ministerial approval before being resubmitted to Cabinet. Political preference for prioritising public works over cash transfers was effectively mitigated via collaboration between development partners and GoURT to retain focus on CCTs.

Financial and Fiduciary: FCDO monitored the risks of misuse and misappropriation of funds and the high reputational risks associated with it. To mitigate the risks, FCDO transferred resources directly to the Bank of Tanzania (BoT) which paid directly to the programme to avoid delays and risks of leakage. An e-payment system was piloted, and a grievance reporting mechanism put in place to help monitor whether resources were going to intended recipients. KPMG was contracted to provide fiduciary risk assessments (FRAs) and high-level scrutiny of annual audits. In 2018, SIDA contracted PWC to provide similar services for the donors, with these reports being shared and action points discussed during the Fund Management TWGs.

Many aspects of PSSN were administered through Local Government Authorities (LGAs) where the financial procedures and capacities were not always as robust as at the national level. This presented additional risks that misuse of funds would occur, hampering PSSN’s ability to effectively deliver outcomes and achieve VFM. To mitigate this, TASAF developed manuals and a set of controls, which included close monitoring of processes to identify public works, quarterly LGA audits and a taskforce consisting of donors and TASAF management to provide oversight and follow-up on audit findings. No significant discrepancies were found between LGAs receipts and beneficiaries’ payments as measured through the Comptroller Auditor General (CAG) reports, discussed in more detail in the next section.

Safeguarding: The programme monitored and mitigated social and environmental risks, especially those associated with public works. Through a programme of technical support funded by donors, TASAF conducted robust climate resilience assessments to inform the roll out of public works projects. The second type of safeguarding risk was sexual exploitation, abuse, and harassment particularly at the local level where transfers were disbursed. No reports of this nature were raised during the lifetime of this programme and even within the six months timeframe of the additional financing provided by the UK, the majority of the grievances related to payments. The targeting process for beneficiaries used a three-stage approach, thereby reducing (but not entirely eliminating) the power held by any individual to abuse or exploit others. The GRM and anonymous reporting facilities provided a safe reporting mechanism. A gender working group was established to monitor and provide technical support throughout programme implementation.

Update on Partnership Principles

The Partnership Principles Assessment for Tanzania was most recently updated in August 2023. It found that the Government of Tanzania continues to demonstrate a long-term commitment to poverty reduction, sound management of public finances and most economic and social rights, but that Government’s commitment to civil and political rights and domestic accountability has deteriorated. Overall, we conclude that there remains sufficient commitment across the Partnership Principles because the positives on service delivery, corruption and financial management are likely to deliver results, but we will continue to monitor the situation closely.

Annual Statement of Progress (Financial Aid programmes only

Current level of fiduciary risk and direction of travel since last ASP	Moderate (stable)
Specific assessment of corruption risk and direction of travel since last ASP	N/A

Risks primarily related to theft of cash during the CCT process (either while being transported between local government authority LGAs to communities or during payment day). Mitigation included adding additional security to vehicles transporting cash, introducing e-payment and the use of independently verifiable cash voucher numbers to reconcile amounts disbursed with LGA expenditure reported.

An identified fiduciary risk that materialised was poor record keeping by the LGAs resulting in missing vouchers and unaccounted spends which had to be repaid in full. This was dealt with through audit follow up and clear recovery of funds processed by TASAF from LGAs. By programme closure all unverifiable expenditure by LGAs was refunded to the programme.

Finally, there was a risk that TASAF staff subvert procurement processes for their own profit through bribes or collusion. Procurement was done in accordance with the Government Procurement Manual and followed the World Bank Procurement guidance. Procurements are competitive, are spot-checked and undergo a post-procurement review. Spend above the agreed threshold is approved by the donors. At the end of the programme the World Bank rated TASAF procurement controls and procedures as ‘Satisfactory’ and TASAF was awarded a Certificate of Recognition for compliance with the national Public Procurement Act (PPA) regulations.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Implementing Partner Performance
PSSN was an effective, high performing programme, scoring A / A+ in annual reviews up to 2019. At the point activity was constrained by lack of funds in late 2018, most output and outcome objectives had been met. Were it not for these constraints, indicators would have been revised upwards from 2019 onwards.

PSSN was implemented by the TASAF Management Unit (TMU), set up by the World Bank under State House with 20 years of experience implementing community development initiatives. The TMU led the programme in accordance with the PSSN operational manual and other guidelines, (e.g., Public Works and Livelihoods Manuals). They developed a set of effective community arrangements working closely with PAAs and Community Management Committees (CMCs) for successful implementation of CCTs and PW, from whom they received timely quarterly consolidated implementation and financial reports.

Governance
TASAF is answerable to GoURT’s National Steering Committee, who provide overall supervision and monitoring of PSSN activities. TASAF staff are embedded within existing government structures. A donor governance mechanism was developed, chaired by the World Bank and a rotating donor co-chair seat that the UK held several times. Donors joined six technical working groups led by TASAF which led to more coordinated resource management, effective joint monitoring, and policy dialogues.

Financial Management

TASAF submitted quarterly harmonised financial and semesterly reports of good quality. Early in the programme, there were some forecasting challenges, especially in tracking real-time PAA expenditure and managing exchange rate fluctuations. With support from the World Bank, improvements were made to TASAF’s expenditure tracking system and reporting format. A fund management working group of donors and technical assistance was set up to monitor progress against audit recommendations. The quality of financial reporting improved and was considered satisfactory in the final implementation report of the World Bank.

The combination of World Bank IDA, donor partner and domestic government contributions was insufficient to cover PSSN’s ambitious work plan. In FCDO Annual Reviews, and during the bimonthly meetings and review missions, we raised the risk that PSSN would exhaust its funds prior to the planned end date. A programme adjustment and budget realignment were conducted, scaling down the public works and livelihoods components to pilots, leaving more funds available for the CCTs. A follow-on programme and supplementary IDA loan was designed to take over from PSSN. Unfortunately, delays to the approval of PSSN II exacerbated the funding issue causing CCTs to be halted in March 2019. FCDO twice brought forward spend allocated for later financial years to smooth the funding gap; in November 2018 for the 2019 Jan-Feb and Mar-April payments and in January 2020 for an emergency double payment in February 2020. Consistent bimonthly payments resumed in June 2020, including to 30,000 new HH under PSSN II.

Audits
Regular audits were carried out over the lifetime of the programme by the Office of the Comptroller Auditor General (CAG) in Tanzania. These were all unqualified, and the management letters provided detailed findings and actions for TASAF. Common findings were:
- Grounded vehicles in PAAs, with no clear budgets or agreements for their maintenance
- Unsupported fuel consumptions (e.g., receipts and logbooks missing)
- Discrepancies in beneficiaries’ payment in PAAs including the timely refund of uncollected amounts.
- Other PAA expenditures (e.g., for PW sub-projects) not fully reconciled and requiring repayment.
- Unmatched names of eligible HH in specific PAAs

The CAG carried out an audit covering the TMU and 186 PAAs covering the period of 1st July 2021 to 30th June 2022. The report and management letter were shared with TMU for the necessary actions and the remedial action plan was prepared and shared with DPs in which 68 percent of issues were implemented, 32 percent of issues were under implementation and there was no issue which was not implemented.

Our in depth VFM analysis conducted in 2019 focused on the relationship between the costs of delivering the social transfer programme and the value delivered to beneficiaries.

Economy: Administrative costs are comparable with other cash and in-kind transfer schemes at 13% versus total costs. PSSN compares favourably with other Sub-Saharan transfer programmes, the majority of which failed to achieve admin costs below 15% (e.g., Ghana, Kenya, Zambia Rural, Ethiopia, Malawi). This is significant considering PSSN’s large conditional element. We compared the changing cost of delivering CCTs over the course of the programme using the Total Cost to Transfer Ratios (TCTR). The more TCTR approaches 1 the more cost-effective the programme is provided outcomes are being met. When PSSN was first established the TCTR stood at 5. This was as expected due to front-loading of set-up costs. This fell to 3.6 in the second year and 1.3 in the third. The final ratio was 1.15 in the final year.
[note] pg. 185: Marito Garcia and Charity M. T. Moore (2012), ‘The Rise of Cash Transfer Programs in Sub-Saharan Africa’ https://documents1.worldbank.org/curated/en/435291468006027351/pdf/672080PUB0EPI0020Box367844B09953137.pdf

Efficiency: Payments and verification of conditions continue to be conducted via existing GoURT structures which reduces the overhead costs. Moreover, the programme has rolled out an e-payment system as a pilot using the existing GoURT payment gateway (see output 1). Electronic payments systems reduce administrative and recipient costs, and improve reliability and the security of the transfer, which will further mitigate key financial and fiduciary risks and result in reduced admin costs.

There is increasing discussion amongst donor partners, the World Bank and TASAF on the private costs to recipients for collecting benefits, following up on grievances and fulfilling cash transfer conditions (e.g., distance to health centres and schools) which will be tracked closely under PSSN II.

Effectiveness: PSSN reduced the prevalence of poverty by 6.9% among beneficiary HH from baseline to midline (end line was not conducted due to budget constraints) which resulted in a 10% overall population poverty reduction relative to the control group. Evidence from the impact assessment shows the proportion of HH owning or raising livestock increased from baseline to midline from 36% to 50. HH receiving CCTs were effectively incentivised to attend and use basic services.

Equity: Although equity was not covered as a key VfM metric in the business case, equity is central to this programme’s aim of reaching the poorest 15% of the population. In the last year, the programme reached 995,500 enrolled HH and 5,281,591 beneficiaries across the country. Disaggregation is only available at head of household level, as follows: 12.7% were over 60 years, 85% were women, 2.5% had a disability and 18% of HH had a child less than 5 years. This programme therefore succeeded in targeting the extreme poor, women, and elderly as well as those with caring responsibilities.

After a review of geographic coverage of the poorest regions in 18/19 using the Household Budget Survey (HBS) indicated that poverty was concentrated in the Lake Zone and Western regions where PSSN I coverage was low. A decision was taken at the time of PSSN II design to increase the beneficiary caseload by an additional 30% covering the poorest regions underserved by PSSN I.

Programme-level approach to monitoring and evaluation

M&E costs are 1% of the total expenditure of the programme. TASAF monitored the progress of the PSSN programme against a detailed central results framework and the FCDO log frame was aligned with this results framework. TASAF’s provided consolidated quarterly progress reports, which were comprehensive and timely. Bimonthly working groups comprising TASAF TMU staff and donor partners provided a chance to identify issues and follow up on progress. These meetings were complemented by a bimonthly donor partner group, chaired by the World Bank and a rotating co-chair, and a separate fund management group to review audit actions and conduct capacity and fiduciary risk assessments.

FCDO participated in all PSSN I bi-annual Joint Review Inspection and Support (JRIS) missions, in coordination with TASAF, the World Bank and other development partners, including supporting UN agencies (WFP and UNICEF) and Non-Governmental Organisations (NGOs). FCDO participated in field visits in Mwanza, Arusha, Singida, Unguja and Mafia where we interviewed beneficiaries and visited a payment day in Dar es Salaam. A PCR-related visit to a payment day was not possible. Two further PSSN related field visits were conducted in 2023 to Dodoma with senior leadership at FCDO to review e-payments and the administration of conditionality-linked payments.

In addition to programme monitoring, FCDO deployed its technical assistance funds to conduct studies and assessments to strengthen the PSSN programme, making it more climate and gender sensitive and resulting in a significant reduction in the World Bank administered costs to deliver the CCT element before joining the programme in 2015. This has not only improved the results achieved over the course of the programme but has provided useful lessons for future social protection programmes.

A summary of the key learning from these reports is provided below.

Report	Finding				Recommendation
Baseline Assessment (2016)	PSSN had strong targeting performance, reaching a higher share of beneficiaries in the bottom quintiles of consumption compared to other similar CCT programs worldwide. / It is not cost-effective to perform population wide PMTs for targeting purposes.				Combined approaches, such as use of community or geographical targeting as a primary tool, followed by a PMT to validate only the shortlisted beneficiaries is advised.
Mid-line Assessment (2019)	PSSN improved school enrolment: in treated HH the proportion of children ages 5 to 19 in school was 5.6% higher than the control. / Additionally, while improved literacy is a long-term outcome, primary school age children in treated HH saw a 13.9% increase in self-reported literacy rates relative to control group. / A much smaller impact is observed for students of secondary school in terms of both enrolment and literacy, suggesting more focus is needed to ensure children transition and remain in education. / PSSN performance would benefit from revising the benefit scheme and co-responsibilities to further address the key barriers to supply and incentivise long term human capital benefits.				PSSN II should consider: / adopting targeted compliance monitoring focussed on key transition points, such as primary completion, transition to secondary, and secondary enrolment. / recalibrating the transfer amounts tied to secondary school to account for opportunity and other costs (e.g., transport costs, fees). / explore the possibility of bonuses for primary completion. / eliminate monitoring of primary attendance which is already high and has low-cost benefit.
Climate Assessment, 2018	PSSN HH are indirectly vulnerable to climate change due to their reliance on communities for employment and charity, which reduces in times of stress. The value of PSSN’s unconditional cash transfers in providing a safety net for the elderly, disabled, chronically ill, orphans or widows, is high, particularly during lean periods. / Improved climate resilience may be achieved within a generation, if CCTs make it more likely that PSSN children complete school and enter employment or self-employment in sustainable sectors. This approach needs to factor not only climate resilience but also work towards a demographic transition in which the dependency ratio reduces.				PSSN should ensure that the vision of climate resilient development includes education and skills training translating into progressive and diversified employment or self-employment. Useful interventions include helping young rural people – particularly women – successfully transition to employment and town life by providing life-skills coaching and family planning advice.
Gender assessment / 2018	The impact of PSSN on intra-household gender relations is complex, and the results are mixed. For some, CCTs provided women the opportunity to take part in decision-making regarding household expenditure. Some reported that tensions and conflicts within the household reduced after the programme started. / For others, relying on women to collect cash transfers and comply with conditions have negative implications for gender equality, reinforcing gender stereotypes and adding to women’s already heavy workloads, which could limit their time available for more productive, wage-earning activities.				Public works and savings groups, if designed with a gender perspective, play a key role in providing more diverse income generating opportunities for women. / More thorough research is needed on the role of cash transfers on intra-household relationships, especially in cases of gender-based violence as there is no clear findings from this gender assessment.
Public Works Impact Assessment / 2017	Public Works (PW) projects stabilized consumption during the lean season. 97.2% of participants said that PW helped to smooth consumption. 85.7% and 85.2% said they increased their household ‘s expenditure on children clothing and on education respectively. 90% indicated that PW increased expenditure on health care services. / Public Works projects can be expensive and challenging to coordinate to the required high standards. Despite the existence of screening of sub-projects using the environmental and social management framework (ESMF), the results of the assessment show that the quality of screening is only about 48%. Only 62% of the subprojects were assessed at high quality.				Public Works need to involve relevant regional and district officials and have clear governance arrangements. / Manuals, such as those developed under PSSN are useful in determining which projects can be selected based on their potential for enhanced productivity and/ or climate resilience. / Checks and balances must be in place to prevent works that risk causing harm to the environment or communities.
Resilience to Shocks Assessment / 2020	While the PSSN Proxy Means Test (PMT) was not designed to be shock responsive, chronic poverty correlates sufficiently with vulnerability to shocks that the PSSN PMT is the most cost-effective tool for addressing shocks rapid onset shocks in Tanzania compared with alternative targeting options, e.g., categorical targeting.				A horizontal expansion of the current programme focussed on urban areas would help to mitigate the impact of the 2020 economic crisis caused by the global Covid-19 pandemic.
The Impact Evaluation of Productive Social Safety Net in Tanzania Phase II: Baseline Report – June 2023	The baseline survey confirms that most PSSN households are living below the national poverty line, and nearly all households surveyed face food insecurity with almost all surveyed having worried about food, skipping a meal, eating less, and running out of food in the past 12 months. / The demographic data including sources of income, health and education levels is available for PSSN II beneficiaries. An assessment of the effectiveness of the targeting methods is provided.				To address the heavy burden faced by women in complying to programme requirements. / Increasing scope for diversification of incomes for poor households outside of farm activities

Date of last narrative financial report		January 2023	Date of last audited annual statement	March 2023

ANNEX 1 – Beneficiary Case Studies

Mariamu, CCT and Public Works Beneficiary, Kinyikani, Pemba
Mariamu has been the sole care giver for her 6 children since her husband deserted her.  4 children are now grown up and have left home, Abdalla (17) and Rashid (12) live with their mother in a home with two rooms – 1 sleeping area with twin beds and 1 cooking area.  She has been a PSSN beneficiary since the programme started 2 years ago.

Before receiving the cash transfer the family struggled, regularly going one or two days without food and not able to meet their health needs or purchase basic school materials.  Following the introduction of the cash transfer Mariamu has been able to regularly purchase food and cover the costs of education for her eldest son.  She buys beans to supplement the rice and cassava she grows on her farm.  Mariamu is now become a member of a savings group that has 10 chickens and a communal farm on which she sometimes works.  She has also invested in her own business, buying oranges to make special vinegar that is very popular in the village.

Mariamu particularly welcomes the public works programme, as this has provided work for her during the time when there is no activity on the farm.  During the lean season in 2014/15 she worked constructing a feeder road in the village, which has been of benefit to the entire community ensuring they stay connected during the rainy season.

Abdalla is in Standard 5 (primary school) as his father took a very long time to enrol the children in school.  He enjoys school and wants to work hard to become an askari (security guard) when he is older.

Despite the benefits they have seen from the programme the family still faces challenges.  They eat one meal during the day, meaning that Abdalla spends the morning in school with no food.  Mariamu’s younger son has only completed one year of education, having left school following repeated beatings from his teacher.  He hopes to return next year, and Mariamu believes the money from the transfer will make this a possibility.

Grace, 32 CCT beneficiary, Amani, Nyamagana
 Grace became a widow when she was just 27 and has struggled in the past 5 years to provide for her four sons; aged 6,9,13 and 16. She has insisted that all of them attend school as she understands the importance of education.

Before the conditional cash transfer, Grace felt alone as there was ‘no-one to help’ after the death of her husband. She worked in petty businesses and engaged with casual labour but found it difficult to support her family.

She has been receiving the conditional cash transfer for the past year, and since then has been able to buy food to ensure that her family is fed. Crucially, she can now provide 3 meals a day for them. She has also put the money towards buying school uniforms and school materials for her sons.

Her bi-monthly payment of 52,000 Tanzanian Shillings has enabled her to build a toilet and she has now invested in a small business of buying and selling tomatoes and oranges. With the extra money she receives from her business she has bought three ducks, with the knowledge that ducks are more resistance to diseases.  The cash transfer has impacted her and her family’s life significantly, she now feels that she has social recognition in the community and is immensely happy to be receiving the conditional cash transfer.