## Annual Review – GAGE 2025

Title: Adolescence Research Programme / Gender and Adolescence: Global Evidence (GAGE)
Programme value £ (full life): £30,896,804 / GAGE (ODI) – £27,352,239		Review date: / April 2026
Programme code: 203529-401	AMP start date: April 11th 2014	AMP end date: November 30th 2026

Summary of programme performance
Year	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025	2026
Overall output score	A	A	A+	A+	A+	A+	A+	A+	A++	A+	A	A+
Risk rating	Med	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod	Mod

DevTracker link to Business Case:	Business Case
DevTracker link to results framework:	Logframe

A. SUMMARY AND OVERVIEW
Description of programme
The Gender and Adolescence: Global Evidence (GAGE) programme explores ‘what works’ to transform the lives of poor and marginalised adolescent girls in low- and middle-income countries (LMICs). [1] The GAGE consortium is led by ODI and includes 33 organisations (11 NGOs and 22 research partners) with expertise in research, policy and programming in the fields of adolescence, gender and social inclusion. The programme was initially set to run for nine years from 2015 to 2024 but received Deputy Director approval in 2022 for a no-cost extension until November 2026 due to in-year budget reductions and the Covid-19 pandemic, which had led to delays in the in-person midline data collection. A further short no cost extension is being progressed to allow programme closure by March 2027.
[1] GAGE is part of the Adolescence Research Programme (ARP) announced by the then DFID Secretary of State at the 2014 Girl Summit. The ARP also included the Adolescent Wellbeing Programme (AWP) led by UNICEF’s Office of Research, Innocenti, but this component ended in 2018.
GAGE is a mixed-methods longitudinal research and evaluation study. It follows the lives of 20,000 adolescents from two cohorts (aged initially 10–12 years, now 17-19 years and 15–17 years at baseline, now 21-25 years) in six LMICs in Africa (Ethiopia and Rwanda[2]), Asia (Bangladesh and Nepal) and the Middle East (Jordan and Lebanon and now again in the occupied Palestinian Territories). GAGE remains the largest longitudinal study on adolescents in LMICs and generates evidence on ‘what works’ to enable adolescent girls and boys to emerge from poverty and fast-track social change for young people, their families and communities, through:
[2] Following discussions with FCDO, there has been no new data collection in Rwanda since 2020.
- Output 1: Rigorous, policy-relevant research on how to enhance adolescents’ capabilities, and the development of new methodological tools and approaches, including those that foreground girls’ experiences and perspectives. This includes: (1) evidence synthesis to map existing knowledge, identify gaps, and contextualise GAGE’s primary research findings; (2) mixed-methods longitudinal research that follows approximately 20,000 adolescents in Bangladesh, Ethiopia, Jordan, Lebanon, and Nepal with nested impact evaluations; and (3) participatory research with especially disadvantaged adolescents, including adolescents with disabilities and married girls. GAGE’s cohort includes more than 4,500 refugee and internally displaced adolescents, including Congolese (in Rwanda), Palestinian, Rohingya and Syrian refugees, and internally displaced adolescents in Ethiopia.
- Output 2: Effective research uptake. Knowledge and evidence are effectively communicated by GAGE and accessed by national and international decision-makers to improve policy and practice related to adolescents.
- Output 3: Capacity strengthening. Researchers from the Global South (including youth researchers) have greater capacity to employ new research tools and methodologies and to strategically engage policy-makers in the use of evidence.
The GAGE study’s longitudinal design is making significant contributions to FCDO priorities: understanding interconnected issues at a critical life juncture; supporting evidence-informed policy and programme investments in adolescent girls’ education, voice and agency, freedom from violence, psychosocial well-being, and sexual and reproductive health knowledge and services; addressing complex humanitarian needs; understanding constraints to girls’ education; supporting developing countries to build back better after the pandemic; and support to adapt to the impacts of climate change.
This breadth and depth enables GAGE to assess the longer-term impact of policies and programmes on adolescents’ lives (including how to make programmes more inclusive) and broader progress towards the Sustainable Development Goals (SDGs). GAGE’s analysis helps governments, donors, UN agencies and NGOs to allocate scarce resources more effectively.
Summary supporting narrative for the overall score in this review

During the reporting period, GAGE’s primary focus has been the delivery and completion of endline data collection, marking a critical milestone as the programme enters its final phase. Alongside this, GAGE has begun dissemination of emerging endline findings to key national stakeholders, ensuring that evidence is informing policy and programming decisions in real time. Despite rapidly evolving and often volatile research contexts, GAGE has continued to perform strongly against the revised logframe, with all output targets for Year 9 met or exceeded.

Throughout the year, GAGE has maintained a consistent and long‑term investment in relationships with government, NGO, UN agency and donor stakeholders across focal countries. The programme has continued to demonstrate flexibility and responsiveness, balancing the demands of high‑quality longitudinal research with the need for timely evidence and policy engagement in fast‑changing contexts. GAGE has sustained a strong commitment to frequent country engagement, capacity strengthening, mentoring of early‑career and youth researchers, and inclusive co‑authoring and presentation opportunities at national, regional and international fora.

In Year 9, GAGE’s finalised endline data collection across all core country contexts for the main adolescent cohorts. At the same time, the programme continued to respond rapidly to emerging priorities and crises. This included engagement with Gen Z adolescents involved in protest movements in Nepal, research with returnee adolescents in Syria, and data collection with adolescents in post‑conflict northern Afar and Tigray in Ethiopia to understand recovery trajectories (with finalisation scheduled for early 2026).

Key emerging endline findings (headline insights)

Emerging findings from GAGE’s endline analysis highlight important shifts in adolescent risks and opportunities over time, with direct implications for policy and programming:
- declines in caregiver and teacher violence as young people age, alongside rising exposure to peer violence and intimate partner violence;
- greater awareness among young men than young women of how and where to report violence, but persistently low justice‑seeking behaviour across genders, driven by stigma and low confidence in system effectiveness;
- high levels of psychosocial distress, particularly among young women married as children and adolescents with disabilities;
- improving awareness of modern contraceptive methods, but continued low uptake and widespread misinformation linking contraception to infertility; and
- rapidly increasing mobile phone and internet connectivity, creating new opportunities for information access while also heightening risks of online exploitation and reinforcing digital divides linked to gender, poverty and disability.

GAGE has continued to leverage FCDO funding through additional partnerships and co‑financing, securing a further £51,914 in external research funding in Year 9, alongside significant in‑kind contributions from consortium members and strategic partners, further amplifying the impact and reach of the programme.

In the past year, GAGE has continued to influence how diverse international and national actors use evidence to improve policies and interventions to reach disadvantaged adolescent girls in LMICs. Highlights during Year 9 include the following:
- GAGE’s ongoing technical assistance to UNICEF’s Makani programme in Lebanon has supported programme recommencement for disadvantaged Lebanese, Palestinian and Syrian adolescents. GAGE evidence from Jordan underpinned funding for the programme and GAGE’s selection as the evaluation partner.
- In Jordan, GAGE endline findings on education, transitions to work and access to technical and vocational education are being used by the Ministry of Education and senior national advisers to inform implementation of the Education Strategic Plan.
- In Ethiopia, GAGE evidence contributed to a national public hearing on Female Genital Mutilation (FGM) as a human rights violation, leading to public commitments by authorities and the drafting of a new regional law criminalising FGM in Afar, alongside follow‑up engagement with parliamentarians on endline findings.
- GAGE evidence has continued to shape global debates on adolescent wellbeing, including through UN high‑level technical roles on child marriage and substantive contributions to the Lancet Commission on Adolescent Health and Wellbeing, drawing on GAGE data.

During Year 9, FCDO country posts played an active role in supporting the dissemination and use of GAGE endline findings. In Ethiopia, FCDO participated in multiple dissemination events and stakeholder engagements, including endline workshops and follow up policy discussions, with FCDO staff joining missions and supporting communications and outreach. In Jordan, FCDO post colleagues participated in and supported validation workshops on GAGE endline findings, including senior level engagement and discussions on implications for education, health and protection programming.

Overall, Year 9 demonstrates strong delivery, adaptability, sustained influence and excellent value for money, positioning GAGE well to maximise the impact and legacy of its final endline findings.

Major lessons and recommendations for the year ahead
Recommendations:
Given the scale of GAGE’s datasets and methodological assets, GAGE should develop a time‑bound legacy and stewardship plan covering data archiving, access to tools and instruments, maintenance of key online resources, and clear signposting for future users of GAGE evidence and datasets.
In the final phase, GAGE should place increased emphasis on cross-country and cross-capability synthesis products that distil key patterns, divergences and transferable lessons from the longitudinal evidence. This should include development of synthesis reports to highlight the global learning around the six capabilities.
GAGE should document and disseminate learning on conducting longitudinal mixed methods research in fragile, conflict affected and rapidly changing contexts, including adaptations to fieldwork, safeguarding, respondent tracking and ethical practice.
As GAGE enters its final phase, GAGE and FCDO should jointly develop an internal knowledge sharing strategy to consolidate and disseminate key methodological, operational and policy learning across FCDO policy teams as well as at country level.
GAGE and FCDO should consider how best to consolidate and disseminate lessons learned from GAGE’s participatory research approaches, including insights on adolescent engagement and ethical practice, to inform future research, policy and programming. GAGE should also consider producing a short, practical note capturing best practice from its experience in engaging and supporting Southern researchers, to inform learning across FCDO programmes and support more inclusive research partnerships.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s Theory of Change, including any changes to outcome and impact indicators from the original Business Case.
As GAGE completes Year 9 of programme delivery, the original Theory of Change largely remains valid. The external context has, however, shifted significantly since programme inception, and this has required the programme to refine how key assumptions operate in practice, particularly in fragile and crisis‑affected environments.
GAGE’s conceptual framework and Theory of Change take a holistic approach to understanding what supports girls’ and boys’ development and empowerment during adolescence and as they transition into early adulthood. The programme focuses on the ways gender norms shape everyday experiences, risks and opportunities, and it examines change across three inter‑connected dimensions:
Adolescent capabilities: investigating young people’s individual and collective well-being in terms of six broad domains: education and learning, bodily integrity (including freedom from sexual and gender-based violence, and child marriage), physical and reproductive health and nutrition, psychosocial well-being, voice and agency, and economic empowerment.
Change strategies: assessing programme impacts for adolescents by simultaneously intervening at individual, family, community, service and systems levels.
Contexts: investigating the ways in which adolescents’ local, national and international environments shape their lives and development trajectories, and the efficacy of programming and policy.
The Theory of Change (please also see figure 1 below) remains supported by emerging GAGE evidence about adolescents’ outcomes across six capability areas, and in-depth understanding of the political, economic and socio-cultural contexts of its focal countries. However, longer-term impacts of the Covid-19 pandemic, conflicts in Ethiopia, Gaza and Lebanon, the political transition in Bangladesh, the spillover effects within the MENA region of the Gaza-Israel war and the regime transition in Syria and most recently in Gaza, as well as the intensifying effects of climate change have meant that it has been necessary to nuance some of GAGE’s original assumptions, in line with these emerging changes and threats.
Updated assumptions include: (i) how influencing works in practice when political will and fiscal space are constrained; (ii) pressures on evidence use, including misinformation and information disruption in crisis settings; and (iii) the implications of rapidly changing digital information environments (including the growing use of generative AI tools) for how evidence is communicated and interpreted. In response, GAGE has prioritised sustained engagement with research champions within government, civil society and UN agencies, alongside targeted capacity strengthening for evidence use (including with officials and journalists), to support the accessibility and responsible interpretation of research findings.

Figure 1: GAGE’s Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
GAGE is on track to contribute to expected outcomes and impact. Endline data collection and analysis were major priorities in Year 9, alongside continued use of emerging findings to inform policy dialogue and programme design in several focal contexts.

Planned focus for Year 10 is to: (1) complete remaining endline data collection; (2) finalise analysis and publish longitudinal findings (including through planned journal special issues); (3) undertake targeted stakeholder engagement on endline findings through national and regional dissemination; (4) support the FCDO endline evaluation; and (5) complete quantitative data archiving and consolidate learning and legacy products.

Outcomes	Milestones	Milestones for this annual review	Progress
Outcome 1 focused on: 1. Enhanced demand for information about "what works" by policy makers and practitioners; or 2. Enhanced demand for methods, tools and technical guidance to support and advance research, monitoring and evaluation of complex programmes for adolescent girls	Milestone 9 (2025):	3	Milestone exceeded: / 6 stories of change
	Cumulative:	27: year 9	30
Outcome 2 focused on: 1. Enhanced access to and engagement with information about "what works" by policy makers and practitioners, including feedback on the usefulness and relevance of GAGE evidence; or 2. Enhanced access to and engagement with methods, tools and technical guidance to support and advance research, monitoring and evaluation of complex programmes for adolescent girls	Milestone 9 (2025):	3	Milestone exceeded: / 4 stories of change
	Cumulative:	27: year 9	28
Outcome 3 focused on enhanced policy impact and collaboration including: 1. Verifiable contributions from GAGE evidence have influenced numerous international, national, regional, and/or subnational policies, programmes, and services. 2. Close collaboration with implementing partners, focal ministries, and UN agencies ensures informed policies, services, and programming tailored to reach and support adolescents, with specific recommendations for effective interventions.	Milestone 7 (2023):	1	Milestone exceeded: / 3 stories of change
	Cumulative:	23: year 9	25
Outcome 4 focused on instances of increased public or private funding for adolescent girls, leveraged or influenced by GAGE	Milestone 7 (2023):	1	Milestone exceeded: / 3 stories of change
	Cumulative:	29: year 9	31

Outcome 1 & 2: Increased demand for and use of GAGE evidence by policy‑makers.

GAGE evidence is increasingly being requested and used by governments, UN agencies and global policy processes, reflecting its maturity as a longitudinal evidence base. Notable examples include:
- GAGE evidence on adolescent experiences in Gaza directly informed humanitarian coordination, including UN‑led psychosocial and mental health clusters, and guided adolescent‑specific service provision by the Ministry of Health and NGO partners. In addition, GAGE co‑published a Lancet correspondence with the Global Disability Fund highlighting the need to prioritise adolescents with disabilities in humanitarian responses, including in Gaza.
- At global level, GAGE was approached by the UN Girls’ Education Initiative (UNGEI) to contribute to a research and advocacy knowledge product on gender norms change in and through education. GAGE provided a dedicated contribution advocating for a more varied evidence agenda, including the use of longitudinal mixed‑methods research. This formed part of a broader advocacy compendium launched on the sidelines of UNGA 2025.
- GAGE leadership roles ensured GAGE evidence directly informed global normative and policy agendas. The GAGE Director was invited to serve as a technical expert on child marriage in low‑ and middle‑income countries to two high‑level UN committees (convened by UNICEF/Innocenti and UNFPA/CEFMU), and the GAGE hub quantitative lead was invited to co‑chair the Lancet Commission on Adolescent Health and Wellbeing.
- GAGE was requested by the Ethiopian Ministry of Women and Social Affairs, the Amhara Regional Bureau of Women and Social Affairs and ActionAid to provide technical guidance on the use of community readiness tools to address child marriage and FGM. Guidance on implementation in conflict‑affected areas of Amhara was subsequently adopted by government counterparts.
- GAGE provided research inputs in Nepal to inform the redesign of the Girls’ Insurance Programme and the National Roadmap on Early Marriage, working through FCDO and UNICEF. GAGE is also engaging with the Policy Research Institute, Nepal’s government think tank, to support evidence‑based strategies on return migration.

On Outcome 3, GAGE evidence has contributed to tangible policy and programme change through close collaboration with implementing partners, focal ministries and UN agencies:

In Ethiopia, GAGE evidence informed the Ethiopian Human Rights Commission’s national public hearing on FGM, contributing to the announcement of a new Afar regional law criminalising FGM. GAGE evidence is now being used to inform a subsequent public hearing in the Somali region.
- GAGE midline evidence on child marriage, FGM and teenage pregnancy was presented to 65 Ethiopian parliamentarians at a national stakeholder event organised by UNESCO, UNAIDS and UNICEF. This led to a request for a follow up briefing on endline findings for two parliamentary committees. A tailored briefing, attended by over 60 parliamentarians, concluded with commitments to integrate GAGE findings into sectoral and regional monitoring checklists.
- GAGE findings shaped the design of the Girl Rising pilot in the Rohingya camps, a partnership with UNICEF Bangladesh and Girl Rising. The robustness of the evidence base supported continuation of the pilot despite significant cuts to the broader response, and GAGE has completed both rounds of data collection with recommendations for potential scale‑up.
- At federal level in Ethiopia, GAGE endline findings are informing development of the second‑generation Road Map to End Child Marriage and FGM/C, drawing explicitly on longitudinal evidence to shape future implementation.

On Outcome 4, focusing on increased public or private funding for adolescent girls, influenced or leveraged by GAGE in year 9:
- GAGE was awarded $8,000 (£5,890) from AGIP to develop youth‑friendly versions of recent research findings and to support an advocacy workshop.
- GAGE was awarded £21,000 from Girls Not Brides to undertake new research on child marriage in Nepal, led by the NISER team. The research will inform the National Inquiry on Child Marriage by the Nepal Commission for Human Rights, with engagement expected to recommence in April 2026. GAGE is also providing co‑funding.
- GAGE was awarded approximately £25,000 from Fondation Botnar to support followup to the second Lancet Commission on Adolescent Health and Wellbeing, including documentation of GAGE research to policy uptake processes in Ethiopia.
- GAGE secured £39,000 for new implementation research in Gaza. Although the funding was not ultimately awarded due to security constraints, this reflects demand for GAGE’s evidence and partnerships in high‑risk contexts.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
GAGE has demonstrated consistently strong performance since inception, continuing to deliver against outputs and outcomes in Year 9. The programme has met or exceeded its revised logframe targets for 2025, including following significant upward revisions to targets in 2023 and 2024, reflecting both delivery strength and appropriate ambition‑setting being scored A+.
This performance has been achieved in an increasingly challenging external environment. During Year 9, GAGE completed or advanced endline data collection across Bangladesh, Ethiopia, Jordan, Lebanon, Nepal and Palestine, despite conflict, political instability and access constraints. This demonstrates the programme’s operational resilience and its capacity to deliver complex longitudinal research in fragile and crisis‑affected contexts.
Evidence from Year 9 indicates that GAGE findings are informing policy and investment decisions at national, regional and global levels, including in humanitarian settings. The quality and credibility of the research remain high, with outputs published in leading peer‑reviewed journals and strong citation performance, reinforcing GAGE’s position as a trusted evidence source for policy‑makers, practitioners and donors.
From a value‑for‑money perspective, the programme has reached the phase where earlier investment in longitudinal research yields its greatest returns, through endline analysis, dissemination, learning and data consolidation. The focus in this final phase is therefore on consolidating and maximising the value of earlier investment rather than expanding scope.
In this context, continuation is justified to ensure that the full value of FCDO’s investment in GAGE is realised and sustained within the wider portfolio and enabling consolidation and dissemination of learning from the programme.
## C: DETAILED OUTPUT SCORING

Output title	GAGE generates a robust and high-quality evidence base for policy-makers and practitioners on what works to enhance adolescent girls’ capabilities, and develops the methodological tools and approaches that are most effective in gaining a better understanding of ‘what works’.
Output number:	1	Output score:	A+
Impact weighting (%):	60%	Weighting revised since last annual review (AR)	No

Indicator(s)	Milestones (cumulative)	Milestones for this AR	Progress
1.1 Number and description of peer-reviewed journal articles produced by GAGE (open access and non-open access) accepted or published on ‘what works’ to enhance adolescent girls’ capabilities	Milestone 9 (2025):	10	Milestone exceeded: 11
	Cumulative:	123	124 / 11 journal articles
1.2 Number and description of knowledge products produced and published by GAGE (policy briefs, reports, working papers (WPs), case studies, blogs and opinion pieces) with policy- and programming-relevant messaging on ‘what works’ to enhance adolescent girls’ capabilities	Milestone 9 (2025):	18 / 10 policy briefs / digests / 6 reports / WPs / 2 blogs	Milestone exceeded: 28 / 8 policy briefs /digests / 11 reports/ WPs / 5 blogs / 4 newsletters/ correspond-ence
	Cumulative:	333 / 128 policy briefs / digests / 95 reports / WPs / 33 evidence / synthesis papers / 77 blog entries / opinion pieces	343 / 126 policy briefs / digests / 101 reports / WPs / 33 evidence / synthesis papers / 80 blog entries / opinion pieces / 3 newsletters
1.3 Number of qualitative and quantitative datasets produced via the longitudinal mixed-methods impact evaluation and panel study	Milestone 9 (2025):	14[3]	Milestone exceeded 16
	Cumulative:	226[4]	228 / Datasets have been produced by GAGE
1.4 Number of quantitative datasets archived publicly as part of the longitudinal mixed-methods impact evaluation and panel study	Milestone 9 (2025):	5	Milestone met: / 5
	Cumulative:	47	47 datasets produced by GAGE are publicly archived on the UK Data Service
1.5 Number of citations of peer-reviewed journal articles produced by GAGE	Milestone 9 (2025):	250	Milestone substantially exceeded: / 348
	Cumulative:	969	1067 / Citations achieved of peer-review journal articles produced by GAGE
1.6 Number of public and peer-reviewed guidance products, tools and resources on new or improved methods and methodologies produced and published by GAGE	Milestone 9 (2025):	4	Milestone exceeded: / 6
	Cumulative:	43	45 / Public guidance products produced
[3] To reflect the change in exchange of deliverables between 1.1 and 1.3, the milestone target for data sets produced have been updated from 14 to 15.
[4] To reflect the change in exchange of deliverables between 1.1 and 1.3, the cumulative target for data sets produced have been updated from 226 to 227.

Brief description of activities and supporting narrative for the score

GAGE has met or exceeded all Output 1 milestones for evidence generation this year. The programme continues to demonstrate both high productivity and high quality across peer‑reviewed publications, policy‑relevant knowledge products, publicly archived datasets, and citation performance, reinforcing GAGE’s position as a leading global evidence programme on adolescence.

Output 1.1 – Journal articles:
In 2025, GAGE published 11 peer‑reviewed journal articles and one book chapter. Book chapters are no longer counted as a deliverable under Output 1.1 in Year 9, although they were assessed differently in earlier years.

GAGE articles were published in a range of highly respected international journals, including World Development, BMC Conflict and Health, Child Abuse and Neglect, and the Journal of Ethnic and Migration Studies. This reflects GAGE’s continued success in reaching diverse disciplinary audiences and broadening its academic exposure and readership.
Selected Journal Articles

Child marriage and its consequences for adolescent mental health in conflict-affected contexts: evidence from Bangladesh, Ethiopia and Jordan
This study examines the largely overlooked mental health and psychosocial consequences of child marriage in conflict‑affected settings, using mixed‑methods data from over 8,500 young people across Bangladesh, Jordan, and Ethiopia. It finds that girls who married before age 18 experience significantly higher emotional distress and depression, lower resilience, and weaker access to social support than never‑married peers. These harms are reinforced by restrictive gender norms, limited mobility, and exclusion from education, highlighting the need for targeted safe spaces and engagement with household gatekeepers to support married girls.

Formal and informal integration in contexts of displacement: Exploring implications for youth civic identities
This article explores how displaced young refugees understand and enact civic identity in contexts where they are excluded from full legal and political rights. Drawing on research with refugee youth in Jordan and Lebanon, it shows that while legal recognition matters, civic belonging is more powerfully shaped by geopolitical histories, economic precarity, place, and gender. These findings nuance understandings of young refugees’ civic identities as shaped by both interpersonal and institutional marginalisation.

Adolescence, Interrupted: A narrative review of the impact of Covid-19 on adolescent wellbeing
This narrative review synthesises global evidence on how the Covid‑19 pandemic affected adolescent wellbeing beyond education and health outcomes. Using a multidimensional wellbeing framework, it shows that service disruptions, economic stress, violence, and social isolation significantly harmed adolescents’ mental health and resilience, particularly in low‑ and middle‑income countries. The review highlights that existing inequalities were exacerbated, with refugee adolescents, married girls, and adolescents with disabilities among the most adversely affected, underscoring the need for targeted support to strengthen resilience in post‑pandemic recovery.

In line with FCDO guidance, GAGE continues to prioritise open‑access peer‑reviewed publishing, ensuring wide accessibility of research findings to policymakers, practitioners, and researchers globally

Output 1.2 – Knowledge products:
During Year 9, GAGE produced 28 knowledge products, comprising 8 policy briefs, 11 reports, 3 newsletters, 1 correspondence in The Lancet, and 5 blogs. These products primarily synthesised findings from endline research and translated evidence into context‑specific, policy‑relevant messages. Key highlights from the year 9 include: (1) the Jordan endline capability themed reports on bodily integrity, health and nutrition, education and learning, economic empowerment, SRHR and psychosocial wellbeing;

and Ethiopia endline capability-themed reports on young people’s development and wellbeing in Dire Dawa City Administration, East Hararge, Oromia Region, and Afar , (2) policy briefs from focal countries including on WASH, girls’ health and gender-based violence in Palestine and on education in Nepal, (3) blogs from youth researchers on their empowerment journeys in GAGE, and (4) a report on the funding landscape for investments in adolescent girls.

Output 1.3 – Qualitative and quantitative datasets:
In Year 9, GAGE produced 16 qualitative and quantitative datasets involving adolescents, caregivers, and key informants across multiple contexts. Together, these datasets reflect GAGE’s continued commitment to methodologically rigorous, mixed‑methods evidence generation across fragile and diverse contexts, significantly expanding the programme’s cumulative data assets.

Output 1.4 – Quantitative datasets archived publicly:
To date, GAGE has publicly archived 47 quantitative datasets with the UK Data Service, including five datasets submitted in Year 9. Three of these are already publicly available, with additional Ethiopia datasets currently under review by the UK Data Service.
Bangladesh and Ethiopia remain GAGE’s most frequently downloaded datasets. Over 85% of downloads are by students and staff in higher and further education. Downloads were the highest in 2025, with 97 downloads in the reporting year, and 229 undergraduate, master’s, and PhD students have used GAGE data to date.

Output 1.5 – Citations of peer‑reviewed journal articles:
In Year 9, GAGE achieved 348 citations (excluding self‑citations) - the highest annual citation count to date. This strong performance results from the programme’s multi‑country, mixed‑methods research design, publication across a wide range of disciplinary and area studies journals, the breadth of GAGE’s six‑capability analytical framework, and the cumulative effect of a growing body of open‑access publications over time.

GAGE research on adolescent health attracted particular attention in 2025. Three of the four most frequently cited articles focus on puberty and menstruation knowledge, mental health, and access to health services. Overall, 30.7% of cumulative citations relate to COVID‑19 impacts, 17.24% to age‑ and gender‑based violence, and 12.94% to sexual and reproductive health.

GAGE articles were cited in high‑impact journals across multiple disciplines, including The Lancet Planetary Health, Trauma, Violence and Abuse, World Development, and The Annual Review of Political Science. In Year 9, nine GAGE articles were cited more than 10 times, together accounting for 33.05% of annual citations. The five most cited GAGE journal articles in year 9 were:

1. Coast, E., Lattof, S. R. and Strong, J. (2019) ‘Puberty and menstruation knowledge among young adolescents in low- and middle-income countries: a scoping review’, International Journal of Public Health. 64(2), pp. 293–304– 23 citations in 2025.
2. Banati, P., Jones, N. and Youssef, S. (2020) ‘Intersecting Vulnerabilities: The Impacts of COVID-19 on the Psycho-emotional Lives of Young People in Low-and Middle-Income Countries.’  European Journal of Development Research. 32:1613–1638– 14 citations in 2025.
3. Baird, S., Bhutta, Z. A., Hamad, B. A., Hicks, J. H., Jones, N. and Muz, J. (2019) ‘Do restrictive gender attitudes and norms influence physical and mental health during very young Adolescence? Evidence from Bangladesh and Ethiopia’, SSM - Population Health, 9, p. 100480 – 13 citations in 2025.
4. Jones, N., Sanchez Tapia, I., Baird, S., Guglielmi, S., Oakley, E., Yadete, W.A., Sultan, M. and Pincock, K. (2021) ‘Intersecting barriers to adolescents’ educational access during COVID-19: Exploring the role of gender, disability and poverty’ International Journal of Educational Development 85: 102428.– 12 citations in 2025.
5. Jones, N., Pincock, K., Baird, S., Yadete, W. and Hamory Hicks, J. (2020) 'Intersecting inequalities, gender and adolescent health in Ethiopia.' International Journal for Equity in Health, 19: 97, (available here) – 10 citations in 2025.

Output 1.6 – Public and peer‑reviewed guidance products:
Given the programme’s focus on endline data collection in Year 9, the focus on guidance products has been on tools for endline data collection. GAGE published 5 survey toolkits in Y9:

No.	Country	Survey instrument/ Toolkit
1	Bangladesh	GAGE Bangladesh Impact Evaluation Rapid Virtual Survey (2021): Core respondent questionnaire
2	Lebanon	Longitudinal participatory research: lessons from engaging with youth in the context of crisis and conflict in Lebanon
3	Bangladesh	Bangladesh Chittagong and Sylhet Impact Evaluation Follow up (2025)
4	Bangladesh	Cox’s Bazar Panel Survey Round 3 (2025): Core Respondent Module and Adult Female Module
5	Jordan	Jordan endline survey 2024/2025 (round 3): Core Respondent Module and Adult Female Module

Describe any changes to this output during the past year, and any planned changes as a result of this review

There were no significant changes to the scope or overall objectives of Output 1 during Year 9. Indicators for Output 1 were revised upwards to reflect sustained strong performance, particularly in relation to citations. No further substantive changes to the output design are planned as a result of this review.

Recommendations from the previous AR:
FCDO and GAGE to increase the ‘citations’ targets (output 1.5) to reflect the average achieved during the past two years.
GAGE and FCDO agreed an updated target for citations which was included in the Operational Plan for Year 9 and the logframe and has been used in this Annual Report.
GAGE to revise the programme-specific Safeguarding Policy by June 2025 with named roles and responsibilities, reporting quarterly on any emerging safeguarding issues and referrals.
GAGE developed an updated safeguarding policy in year 9, integrating the recommendations from the FCDO from the year 9 Annual Report and has shared with the teams still actively involved in data collection. The research teams have been providing regular updates to the hub team on referrals being made, in-line with the updated policy on safeguarding and referrals. The research teams did not report research-specific safeguarding incidents during year 9.
Lessons learnt this year and recommendations for the year ahead.
Lessons learnt:
1. Adaptive and safe research delivery is essential in conflict‑affected contexts: Experience across Bangladesh, Ethiopia (Amhara), Gaza, Lebanon, Nepal and Syria shows that sustained longitudinal research in fragile settings requires flexible, context‑responsive approaches underpinned by strong communication systems. GAGE adapted research designs and modalities in response to changing conditions (e.g. phone‑based data collection, temporary pauses and re‑sequencing), enabling completion of endline data collection while prioritising staff and participant safety.
2. Proactive respondent tracking is critical in crisis and displacement settings: Early and sustained investment in respondent tracking, including pre‑tracking and regular updating of contact information, helped maintain longitudinal samples, reduce attrition and generate cost savings. Research with Syrian returnees further highlighted the importance of retaining contact details across host and origin countries and sequencing data collection in line with mobility patterns.
3. Endline and longitudinal analysis require adequate time and resourcing: Endline analysis has been more resource‑intensive than earlier rounds due to the complexity of synthesising findings across cohorts and over time. Adequate planning and analytical capacity are essential to maximise the value of longitudinal data, particularly as thematic cohorts on issues such as conflict and climate change are added.
Recommendations:
1. Given the scale of GAGE’s datasets and methodological assets, GAGE should develop a time‑bound legacy and stewardship plan covering data archiving, access to tools and instruments, maintenance of key online resources, and clear signposting for future users of GAGE evidence and datasets.
2. In the final phase, GAGE should place increased emphasis on cross‑country and cross‑capability synthesis products that distil key patterns, divergences and transferable lessons from the longitudinal evidence. This should include development of synthesis reports to highlight the global learning around the six capabilities.
3. GAGE should document and disseminate learning on conducting longitudinal mixed‑methods research in fragile, conflict‑affected and rapidly changing contexts, including adaptations to fieldwork, safeguarding, respondent tracking and ethical practice.

Output title	Research uptake: Knowledge and evidence on what works to transform girls’ lives is effectively communicated by GAGE and accessed by decision-makers to improve policy and practice
Output number:	2	Output score:	A+
Impact weighting (%):	30%	Weighting revised since last AR	No revisions

Indicator(s)	Milestones (cumulative)	Milestone(s) for this review	Progress
2.1 Number of events organised by GAGE to communicate evidence, methodological tools and approaches to policy-makers and practitioners	Milestone 9 (2025):	10	Milestone exceeded: 12
	Cumulative:	104	106 / Events organised or co-organised by GAGE
2.2 Number of public and quality-assured audio-visual and multimedia products co-produced by adolescent girls and boys	Milestone 9 (2025):	4	Milestone exceeded: 5
	Cumulative:	71	72 / Products including adolescent boys and/or girls
2.3 Number and description of instances where GAGE is invited to present evidence or analysis to policy-makers and practitioners	Milestone 9 (2025):	22	Milestone substantially exceeded: 74
	Cumulative:	413	442
2.4 Number and description of instances where GAGE evidence is cited in media and news reports	Milestone 9 (2025):	10[5]	Milestone achieved: 10
	Cumulative:	131	131 / Instances where GAGE has been cited in media outlets
2.5 Number of high-level visible partnerships consolidated to engage practitioners and policy-makers evidenced by memorandums of understanding (MoUs)	Milestone 9 (2025):	N/A	Milestone exceeded: 2
	Cumulative:	22	24 / High-level partnerships through MoUs and/or letters of partnership
[5] This is the updated target for media citations from the year 9 operational plan.

GAGE has achieved, exceeded or substantially exceeded the Year 9 milestone targets for Output 2, reflecting sustained demand for GAGE evidence and its effective use by policy‑makers and practitioners across global and national platforms. In the reporting period, GAGE organised 12 events and delivered 74 invited presentations at seminars, workshops, conferences and webinars, demonstrating strong uptake by diverse decision‑making audiences. GAGE evidence has been cited on 10 occasions across a range of media outlets, supporting broader public engagement with programme findings.

Output 2.1 – GAGE organised events

GAGE hosted or co‑hosted 12 events. These included:
- A webinar ‘Investing in Adolescent Girls: Mapping the Donor Landscape (2022 Update)’ co‑organised with the Adolescent Girls Investment Plan (AGIP);
- ‘Bold Policies – Programmes and Partnerships to End Violence against Girls’, co‑sponsored by the Ministry of Women and Social Affairs (MoWSA), Ethiopia, UNFPA, UN Women and the Global Disability Fund at the CSW69 Forum in New York;
- A stakeholder workshop in Amman to launch the GAGE midline report on ‘Age‑ and gender‑based violence faced by adolescents in Jordan’ in partnership with the National Council for Family Affairs (NCFA); and
- A side event ‘Resourcing Adolescent Girls’ Rights: Building a Toolkit for Just Futures’ organised in collaboration with Plan International, Malala Fund, UNGEI, ICRW, AGIP, IPPF and the Government of Chile as part of the 4th UN Financing for Development Conference (FFD4).

Together, these events provided direct entry points for GAGE evidence into donor financing discussions, national policy debates on violence against girls, and UN‑led global agendas on adolescent rights.

Output 2.2 – Multimedia products co‑produced by adolescents
GAGE developed four multimedia products co‑produced with adolescents and youth researchers, ensuring that young people’s voices and lived experiences directly shaped the messages presented to policy and practitioner audiences. Highlights include:
- ‘Sectarian shadows and civic light: narratives from Baalbek’ – (available here)
- An exhibition of photos taken by participatory research participants from Lebanon was displayed at a conference in Geneva, accompanying the launch of the second Lancet Commission on Adolescent Health and Wellbeing organised by WHO. During the event a sequence of videos were played, presenting the young Lebanese participants sharing their experiences with GAGE participatory research.
- A photo gallery of young researchers’ photographs was featured at the “Adolescent Transitions in Crisis – Insights on Voice and Agency from GAGE Research in Lebanon (2019–2025)” event in Beirut.
- Understanding Intimate Partner Violence (IPV) Over Time: The Power of Longitudinal Research. The latest episode of The Sexual Violence Research Podcast from the SVRI (available here).

Output 2.3 – Invitations to present evidence and analysis

GAGE delivered 74 invited presentations for global, national and local policy‑makers and practitioners, responding to high and sustained demand for GAGE findings and expertise. Invitations spanned academic, policy and practitioner audiences across Africa, the Middle East, Asia and global forums, with highlights during Year 9 including presentations on:

- ‘Exploring Ethiopian adolescents’ economic aspirations and opportunities: findings from the GAGE longitudinal study’ at the 15th Anniversary of the Child, Youth and Women Research and Practice Forum – Protection & Empowerment of Children and Women event in Ethiopia;
- The importance of mixed‑methods social research for policy and social change at the University of Chittagong Research Fair;
- GAGE midline findings on age‑ and gender‑based violence faced by young people at the Inter‑Agency UNHCR‑UNFPA GBV Working Group meeting in Amman, Jordan;
- Adolescent girls’ bodily integrity risks in MENA, presented at the UNFPA Social Practice Lab in the Arab region;
- ‘They say “you don’t know how to live in Syria”: Political identity, belonging and hope among young Syrian refugees in Jordan and Lebanon after the fall of Assad’ at the American Political Science Association Conference in Canada;
- A panel on ‘Inequality, poly‑crises and young people in the Global South’ at the DSA Conference at the University of Bath; and
- Participation in a discussion panel on ‘The Role of Youth in Research and Policy: Turning Evidence into Action’ in Lebanon.

Output 2.4 – Media and news reports citing GAGE’s work

GAGE knowledge and evidence was effectively communicated through media engagement, particularly in Jordan and Ethiopia. Highlights include:
On the International Day of Zero Tolerance for FGM, GAGE presented ‘Female Genital Mutilation: Evidence from GAGE’ at two events, one of which was recorded and broadcast by Arts TV, a private television network in Ethiopia;
- GAGE, in partnership with NCFA, published a study on violence against adolescents in Jordan, which was covered by four media outlets including Jordan News Agency (English) and Ammon News (Arabic);
- The Reporter, an established newspaper in Ethiopia, published coverage following GAGE’s presentation on ‘The impact of armed conflict and child marriage on the lives of girls and women in Ethiopia’ at the She Leads workshop organised by the Network of Ethiopian Women’s Associations; and
- GAGE researcher Fitsum Workneh was interviewed by EBS TV in Ethiopia on GAGE’s work on gender‑based violence.

Media uptake remains context‑specific and can be uneven across focal countries, particularly in Bangladesh and Nepal. In these contexts, GAGE has complemented traditional media engagement with virtual and digital outreach, including through the GAGE website, which recorded 613 new users from Bangladesh during the reporting period. While digital channels help sustain visibility and engagement, national media uptake continues to vary by context.

Describe any changes to this output during the past year, and any planned changes because of this review.
There has been no overall change to the scope of the output.

Progress on recommendations from the previous AR (if completed), lessons learnt this year and recommendations for the year ahead.
Recommendations from the previous AR:
GAGE should consolidate the learnings from the decade-long GAGE programme, legacy planning for the programme and also track the learnings from rolling out closely sequenced endline data collection.
The approach on the consolidation of learnings is being planned into the internal preparations for the endline evaluation, and a knowledge product reflecting on the longitudinal participatory research in Lebanon has already been published.
A series of products is now being developed, including on: what we know about young people’s capabilities and inequalities across countries; what we have learned regarding what works to support adolescents and young adults’ individual and collective capabilities in terms of services and programming, and other forms of support (e.g. from peers/ parents/ role models); and what we have learned about how a longitudinal mixed methods research programme can shape knowledge, attitudes, policies, programmes and funding.
Lessons learnt:
1. Strategic convening and sustained engagement strengthen policy influence: Strategic engagement and convening of government, donor and multilateral actors has been central to strengthening the uptake of GAGE evidence in policy discussions and partnership building. Supporting government stakeholders to engage with evidence at high‑profile events, combined with timely synthesis and rapid responses to emerging policy opportunities, has helped integrate research into decision‑making processes. Experience from Nepal and Ethiopia highlights the value of sustained, localised engagement with national and sub‑national government actors where policy reform processes are ongoing.
2. Visual and narrative‑based approaches can enhance accessibility when used alongside policy‑focused engagement: Visual and narrative‑driven communication approaches, including photo exhibitions grounded in community voices, have been effective in translating complex research findings into accessible and engaging messages for diverse audiences. These approaches have supported advocacy and public understanding of girls’ lived experiences, particularly in international and policy‑facing spaces. Their impact is strongest when used as a complement to, rather than a substitute for, targeted policy engagement and conventional evidence products.
3. Coalition‑based engagement offers strong value for money and supports legacy building: Engagement in coalitions and networks, including AGIP, the National Alliance to End Child Marriage and FGM in Ethiopia, and the MENA Adolescent Health and Medicine Coalition, has provided cost‑effective pathways to amplify GAGE evidence to wider and more varied audiences. These partnerships have enabled shared advocacy, reduced duplication of effort, and are expected to play an important role in sustaining influence beyond the life of the programme.
4. Tailored, relationship‑based media engagement can strengthen evidence uptake over time: Experience from Ethiopia indicates that sustained, relationship‑based engagement with media actors can increase understanding of and demand for research evidence. Inviting journalists to GAGE events, providing tailored briefings for different media outlets, and responding to media interests with timely, relevant analysis helped build familiarity with GAGE’s work and strengthened journalists’ capacity to engage with evidence, particularly on conflict‑related impacts affecting adolescents. Over time, this approach contributed to more proactive media interest in GAGE findings.
Recommendations:
As GAGE enters its final phase, GAGE and FCDO should jointly develop an internal knowledge‑sharing strategy to consolidate and disseminate key methodological, operational and policy learning across FCDO policy teams as well as at country level.

Output title	Capacity strengthening: Researchers have greater capacity to strategically engage policy-makers in the use of evidence or new research tools and methodologies
Output number:		3	Output score:	A+
Impact weighting (%):		10%	Weighting revised since last AR	No revisions

Indicator(s)	Milestones (cumulative)	Milestone(s) for this review	Progress
3.1 Percentage of GAGE research reports, policy papers and journal articles authored or co-authored by Southern principal investigators (PIs) or co-PIs	Milestone 9 (2025):	71%	Milestone exceeded: 92% (for year 9)
	Cumulative:	71%	71%
3.2 Number of capacity-building sessions, including GAGE Learning Exchange, held to support GAGE researchers to generate and position research for policy and programming uptake	Milestone 9 (2025):	4	Milestone exceeded: 21
	Cumulative:	140	147 / Capacity-building sessions held

Briefly describe the output’s activities and provide supporting narrative for the score

GAGE has exceeded the indicator targets for Output 3 on capacity strengthening, demonstrating sustained progress in building the capacity of Southern, early‑career and participatory researchers to generate and position research for policy and programming uptake.

Output 3.1 – Southern leadership and inclusive authorship

The proportion of GAGE research outputs authored or co‑authored by Southern principal investigators or co‑PIs reached 92% in Year 9, substantially exceeding the milestone target. Of the 39 research reports, policy and evidence papers, journal articles and toolkits produced during the year, 36 were co‑authored by Southern researchers, and 13% (5) were led by Southern authors. Female researchers were strongly represented across outputs, co‑authoring 75% of policy briefs, 75% of reports, and 58% of journal articles and book chapters. All knowledge products produced in Year 9 included at least one female researcher.

GAGE also continued to strengthen the involvement of early‑career researchers. In Year 9, 72% of publications were co‑authored by early‑career researchers, and 26% were led by early‑career researchers, reflecting deliberate investment in developing the next generation of researchers with the skills and confidence to engage policy‑makers using evidence. Together, these patterns demonstrate sustained progress towards more equitable research partnerships and contribute to the longer‑term resilience and credibility of the global evidence base on gender and adolescence.

Progress was driven by deliberate efforts to embed Southern and early‑career researchers across the full research‑to‑policy cycle. GAGE provided structured mentoring and editorial support to enable Southern researchers to lead and co‑author policy briefs, reports and journal articles, alongside opportunities to present findings directly to policy audiences at national, regional and international events. Capacity strengthening for policy‑relevant writing and communication was integrated with data collection, analysis and dissemination processes.

Output 3.2 – Capacity‑strengthening for policy‑relevant research

In Year 9, GAGE delivered 21 capacity‑strengthening and knowledge‑sharing sessions, substantially exceeding the milestone target. These sessions engaged research teams across Jordan, Ethiopia, Nepal, Bangladesh and Lebanon and focused on practical skills for data collection, analysis, safeguarding, dissemination and policy engagement.

Capacity‑strengthening activities were embedded throughout the research cycle, including debriefings during data collection, training for enumerators and participatory researchers, and support for researchers to present findings in policy and academic forums. In several contexts, adolescents and youth researchers played active roles in dissemination events and panels, reinforcing participatory approaches and strengthening young people’s confidence to engage with policy audiences.

Regular cross‑country dialogue and collaborative learning spaces further supported peer exchange and reflection, enabling teams to adapt methods and engagement strategies across diverse and challenging contexts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There has been no overall change to the scope of the output.

Progress on recommendations from the previous AR (if completed), lessons learnt this year and recommendations for the year ahead.
Recommendations from the previous AR: no specific recommendation for output 3.
Lessons learnt this year and recommendations for the year ahead.
Lessons learnt:
Targeted capacity strengthening supports high‑quality, context‑responsive research: Experience across country teams demonstrates the importance of targeted capacity strengthening that responds to identified skills gaps and evolving research needs. Structured training, for instance support to strengthen the Nepal team’s enhanced quantitative analysis skills and adoption of Statistical Package for the Social Sciences (SPSS), enabled teams to adapt tools and methods to local contexts. This approach helped ensure that research processes remained rigorous, relevant and responsive to changing conditions, particularly in complex and fast‑moving environments.
Investing in early‑career and adolescent researchers strengthens capacity and programme impact: Providing structured opportunities for early‑career and adolescent researchers to engage in research dissemination and policy‑facing roles strengthened both individual capacity and the quality of programme engagement. Roles such as event moderation, panel participation and structured briefings supported skills development, built confidence, and improved the effectiveness of dissemination activities. These investments contribute to a stronger and more sustainable research ecosystem while enhancing the credibility and impact of programme outputs.
Recommendations:
GAGE and FCDO should consider how best to consolidate and disseminate lessons learned from GAGE’s participatory research approaches, including insights on adolescent engagement and ethical practice, to inform future research, policy and programming. GAGE should also consider producing a short, practical note capturing best practice from its experience in engaging and supporting Southern researchers, to inform learning across FCDO programmes and support more inclusive research partnerships.

D: VALUE FOR MONEY

The programme has met or exceeded all 2025 logframe milestones, even with significantly increased targets across many indicators for Year 9. The key costs drivers outlined in the Business Case remain valid, and expenditure continues to be aligned with the programme’s core objectives of longitudinal evidence generation, research uptake and capacity strengthening.

GAGE continues to provide a reasonable split of budget across the consortium; in year 9, approximately 59.5% of the overall budget was allocated to Northern institutions and consultants and programme event and travel costs for all consortium members, and 40.5% was allocated to Southern institutions and consultants[6]. In comparison, two of EGIR’s leading programmes within inclusion, Violence Against Women and Girls (VAWG) and Data and Evidence to Tackle Extreme Poverty (DEEP) allocated 30% and 33% of their budgets for Southern institutions in 24/25.
[6] A higher margin was agreed for the remaining years of the programme between ODI Global Senior Leadership Team and FCDO, resulting in a shift in the split of resourcing over time.

The programme continues to follow FCDO’s 5Es VfM framework, assessing Economy, Efficiency and Effectiveness, underpinned by considerations of Equity and Cost-effectiveness. VfM is reviewed annually by the GAGE Project Management Office and GAGE Director, with quarterly tracking and reporting shared with FCDO. Updates in the table below in bold report on new indicators agreed in Year 8. Key updates for Year 9 include the following:

Category	Performance / best practice
Efficiency = maximising research outputs in relation to budget inputs	To date, 367 datasets have been downloaded from the UK Data Service; 97 downloads were recorded in Year 9. Cost sharing and delivery efficiencies: approximately £89,000 saved on endline tracking budgets due to strengthened endline planning and reduced need for follow-up tracking; savings reprogrammed across Years 9–10 to support priority activities (including co-funding and additional quantitative analysis capacity). / Managing attrition: endline attrition mitigation and intensive tracking budgets managed centrally to maximise resources for endline completion and allocate funds across partners as required, contributing to the tracking savings noted above.
Economy = minimising input costs	Significant additional funding leveraged: approximately £52,304 in Year 9 for new GAGE-led research and knowledge mobilisation (including child marriage research in Nepal; youth-friendly AGIP products and workshops; and documentation of research-to-policy pathways in Ethiopia). / Partners contributed an estimated £99,500 in Year 9 in in-kind time (cumulative estimate of at least £845,000 across the programme lifetime), supporting data collection management, safeguarding follow-up, publications, presentations and stakeholder engagement. / Delivery on time: activities delivered on time and within budget in Year 9, with one agreed exchange of deliverables in Quarter 2; 100% of Year 9 logframe targets achieved despite successive upward target revisions.
Effectiveness = translating research outputs into real-life impact	Research influence: the cumulative number of citations for the top 10 publications was 128 in Year 9. The cumulative number of citations for the top 10 cited articles to date is 525. / Policy and programme influence: To date, GAGE evidence has leveraged 25 instances of influencing policies for adolescents. Year 9 highlights include: (1) contribution to the Ethiopian Human Rights Commission public hearing on FGM in Afar and subsequent regional commitments; (2) informing design of the Girl Rising pilot in the Rohingya camps; and (3) a request from the State Minister of MOWSA to brief on endline findings to inform the second generation Road Map to End Child Marriage and FGM/C. / Stakeholder engagement: 12 events organised/co-hosted and 74 invited presentations in Year 9, reaching an estimated 4,100 decision-makers and stakeholders.
Equity = ensuring that research is inclusive and benefits the target group	Adolescent voice and participation: adolescents involved in Ethiopia and Lebanon research spoke at endline events, describing benefits for aspirations and educational opportunities. Southern and early-career authorship: 92% of Year 9 publications were authored/co-authored by focal-country partners; 13% led by southern authors. 72% of publications were co-authored by early-career researchers; 26% led by early-career researchers. Female researchers co-authored 75% of policy briefs, 75% of reports and 58% of journal articles.

Assessment of whether the programme continues to represent value for money.
Based on performance over the past year, the programme continues to represent value for money. GAGE remains on track to deliver the outputs set out in the Business Case, while demonstrating increased efficiency in endline delivery and sustained effectiveness in influencing policy and investment decisions. As the programme enters its final phase, VfM is increasingly driven by the efficient completion of longitudinal endlines, the translation of evidence into policy reform, and the consolidation of a durable evidence and capacity‑strengthening legacy.

E: RISK

Overview of risk management
The current programme risk rating remains as moderate.
Risk matrix
Strategy & Context	Public Service & Delivery Operations	Policy & Prog. Delivery	Financial & Fiduciary	Safe-guarding	Reputational	People	Overall
Moderate	Minor	Moderate	Moderate	Minor	Moderate	Minor	Moderate

The main risks the programme has faced in this reporting period include the following:
Strategy and context (political): The residual strategy and context risk rating remains moderate and unchanged compared to the previous reporting period, despite significant shifts in the operating environment across several GAGE focal countries.
The security situation in Amhara (Ethiopia), Gaza, Jordan, Lebanon and Nepal continues to be of concern. In Gaza, the team continues to undertake data collection during especially challenging circumstances. In Nepal data collection was paused temporarily during the political upheaval and the team is now undertaking data collection with Gen Z adolescents on the impact of the crisis. The situation in Amhara, Ethiopia impacted on the design of endline data collection and additional phone surveys were undertaken and additional safety measures put in place. In Jordan and Lebanon, GAGE has been liaising closely with the cohort, to track the impact of the significant political changes in Syria with adolescents who are refugees from Syria in the GAGE cohort.
While these developments represent an increase in inherent contextual risk, the residual risk has been contained through strengthened mitigation measures, allowing research activities to continue while prioritising the safety of participants and staff. Mitigation measures implemented and reinforced during the reporting period include adaptive research designs (including phone‑based and remote data collection), temporary pauses and resequencing of fieldwork where required, enhanced security and safeguarding protocols, and close, ongoing monitoring of political and security developments in collaboration with country partners. These measures will continue into Year 10.
Policy and programme delivery: Endline data collection has been progressing well in year 9, the main endline data collection activities have been completed for Ethiopia, Jordan and Lebanon, data collection in Nepal is being completed in year 10, Q1, and in Bangladesh in Q2. Data collection taking place in early year 10 includes in northern Afar and Tigray in Ethiopia, in Nepal with Gen Z adolescents.
Programme closure in the upcoming reporting period may limit GAGE’s ability to finalise data analysis, publish endline outputs, complete archiving, and disseminate key findings. This could reduce the impact and value‑for‑money of the programme by leaving evidence, learning, and datasets inaccessible or under‑utilised by policymakers and partners. A planned no‑cost extension provides dedicated time to complete analysis, produce endline reports and peer‑reviewed publications, finalise knowledge products, and complete archiving in line with open‑data requirements. Clear closure milestones and a time‑bound workplan are in place to ensure timely delivery.
Financial and fiduciary: The contract variation between the FCDO and ODI has now been signed, and variation letters have been issued to the GAGE partners.
In this reporting period, as noted above, GAGE’s activities were delayed by factors beyond the programme’s control. To mitigate this ODI and FCDO are working together to implement a four‑month no‑cost extension, moving the end date from 30 November 2026 to 31 March 2027. This extension will enable GAGE to complete all planned dissemination activities, within the full budget by programme end.
People: The team in Gaza has continued with quantitative (via phone) and qualitative (in-person) data collection with adolescents on the impacts of the conflict. The data collection has been successfully completed, under extremely challenging circumstances. Bassam Abu Hamad and Nicola Jones are in regular contact; we have applied to the Council for Academics at Risk on behalf of Bassam, Unfortunately, the application process has been very slow and is still ongoing. The precarious political situations in Nepal and Bangladesh are also being closely monitored by the GAGE team. In Lebanon, due to the heightened risks, there have been significant delays with the data collection for the UNICEF Makani programme; however this is now recommencing in year 10, Q1.
GAGE follows ODI safeguarding policy, which was last updated in 2022. The GAGE research teams receive training on safeguarding. For high-risk safeguarding cases, GAGE recommend referral to support services – i.e. cases where respondents disclose neglect, violence or abuse of various types that they have experienced outside of the research process – and for which they could benefit from referral to support services. GAGE regularly makes referrals for cases which GAGE receives information on during the research process. The GAGE research teams receive detailed training on the process for referrals. The research teams have internal trackers to monitor referral cases.
The GAGE risk register is regularly updated, tracking risk by workstream. This is discussed with the management team and shared with FCDO each quarter.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
Programme Management
FCDO and GAGE meet on a quarterly and basis to discuss any programme, finance and risk updates and also have an annual meeting to present their annual report to FCDO as part of the Annual Review process. The FCDO terms and conditions and the Payment by Results approach are cascaded down to GAGE partners. A key strength of the programme is the breadth and depth of the 33 consortium partners. They include world-class institutions, academic organisations, leading NGOs, and private sector and communications partners with expertise on gender studies and adolescence. Moreover, partners span the Global North and South, bringing local knowledge and skills, and maintaining equitable partnerships across the programme. The core consortium includes delivery partners (country research partners and methodological leads) and a wider group with more ad hoc involvement.
The GAGE programme office and management team have regular and robust governance and operations processes through which the programme is managed. The GAGE Director and programme office meet on a weekly basis to support programmatic progress, manage operational activities including contracting, finance and risk management and resolve any issues. The GAGE Director also has regular bilateral meetings with members of the GAGE management team. The programme office also hosts regular meetings with country teams during data collection, data processing or analysis periods to monitor progress, problem solve and facilitate collaborative working. The management team also convenes on a quarterly basis to review and interrogate programme progress and discuss the strategic direction of the programme. The GAGE Advisory Group are consulted on an annual basis to reflect on annual progress and strategic direction and provide insightful recommendations. There is also some bilateral engagement with different IAG members as required by the programme.

Financial management
The overall budget and payments are managed by ODI Global. The total value of the contract is £27,352,239 following an increase of £1,479,489 in last year’s reporting period, primarily to cover increased margin costs required by ODI Global management, and to support an 11-month extension in 2026 to allow sufficient time for final analyses. ODI requested a no cost extension for up until March 2027 in order to ensure the completion of planned activities that have been delayed due to external factors beyond the programme’s control. Programme expenditure to date (November 2015 to December 2025) is £25,882.821.

Annual GAGE year expenditure details for the overall programme to date are as follows:
2015/Y0	2016/Y0	2017/Y1	2018/Y2	2019/Y3	2020/Y4	2021/Y5	2022/Y6	2023/Y7	2024/Y8	2025/Y9	TOTAL
£388,091	£2,849,539	£2,850,452	£2,519,384	£2,717,566	£2,721,680	£1,704,148	£1,894,980	£1,976,002	£2,920,565	£3,340,414	25,882,821

GAGE maintains an asset list that is shared with FCDO at least annually (last updated January 2026). ODI has been assessed as being 100% compliant with the Supply Partner Code of Conduct.
Quarterly expenditure for the review period
Narrative and finance reports have been received on time each quarter, with a total spend of £3,340,414.76 for the year 9 period (fully in line with workplans and agreed milestone payments). GAGE is audited as part of the ODI overall annual audit process. The table below provides details:

(£)	Jan–Mar 2025	Apr–Jun 2025	Jul–Sep 2025	Oct–Dec 2025	Total
Forecast workplan (£)	£884,343,26	£872,395.90	£769,996.42	£813,679.18	£3,340,414.76
Actual spend (£)	£ 884,343.26	£ 872,395.90	£769,996.42	£813,679.18	£3,340,414.76

G: MONITORING, EVIDENCE AND LEARNING
Summarise performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
1. Monitoring and evaluation.
GAGE is delivered through a performance-based milestone contract whereby quarterly milestones are agreed in advance, and milestones reviewed and refined on an annual basis, through the GAGE Operational Plan. GAGE has performed well throughout the review period, with high quality quarterly reports have been submitted on time with in-depth reviews conducted during quarterly meetings with FCDO.
GAGE have regular calls and email check ins with the teams across the programme and these usually take place weekly during data collection periods. They receive quarterly updates across the programme which feed into the quarterly reporting to the FCDO. They report regularly to the GAGE management team and convene the management team regularly during the year. In addition, the hub team make regular country visits to support with the training/ capacity building sessions and also to monitor roll out of the data collection in communities, alongside country PIs.
An independent endline evaluation has been launched to assess GAGE’s overall performance, value for money and contribution to policy and practice over the life of the programme. The evaluation will focus on the use and influence of longitudinal evidence, research uptake and partnerships. Findings will inform final learning, legacy products and future evidence and research investments.
2. Evidence
During Year 9, GAGE has generated important new evidence through the commencement of endline data analysis, providing robust insights into adolescents’ experiences over time across diverse low‑ and middle‑income country contexts.
GAGE continues to demonstrate both high quality and breadth of evidence, publishing across a wide range of sectors and disciplines. Outputs during the year include journal articles, reports, policy briefs, blogs, slide decks, newsletters, infographics, posters, and digital and social media content. Audience reach has continued to grow, with the GAGE website attracting approximately 28,000 users, and social media followers increasing by 38.9% on Facebook and LinkedIn and 13.5% on Instagram, supporting wider uptake and visibility of programme evidence.
Emerging lessons on intervention components that promote adolescent development and wellbeing by capability type have been included in Annex A.
3. Learning

Over the past year, GAGE has used a range of structured learning processes to capture, synthesise and share lessons and emerging evidence from midline and endline data collection. This has enabled learning to be shared efficiently beyond individual outputs, supporting coherence and cross‑country learning as the programme enters its final phase.

Key lessons emerging from Year 9 include:
1. The critical importance of maintaining up‑to‑date respondent tracking in contexts affected by conflict and crisis. This has been particularly salient for qualitative research with Syrian refugee respondents who are returning to Syria, where mobility and insecurity pose heightened risks to continuity.
2. The need for enhanced communication protocols and additional safety measures to protect respondents and research teams and ensure continuity of data collection in insecure environments. This has been especially relevant in contexts such as Amhara, Ethiopia, where security conditions have fluctuated rapidly.
3. The continued value of prioritising national partner leadership and authorship, even at the endline stage of a long‑running programme. In Year 9, 92% of publications were authored or co‑authored by national partners, reinforcing ownership, contextual relevance and longer‑term research capacity.

These lessons reinforce the importance of adaptive fieldwork strategies, robust safeguarding and security planning, and sustained investment in equitable research partnerships through to programme closure.

Date of last narrative financial report	September to December 2025 (sent to FCDO on December 23rd) / GAGE Q3 Report - 23rd Dec.docx	Date of last audited annual statement	ODI Global - CS Accounts 2025.pdf

Annex A: Lessons on intervention components that promote adolescent development and wellbeing by capability type

Education
Education enrolment
School systems that allow very late enrolment (Ethiopia) and accelerated learning to promote education catch-up – e.g. post-covid Ethiopia, post-conflict Tigray
Adolescent focused programming that raises awareness about the importance of education and how young people can advocate for their own access and work together with siblings to improve family access, Act with Her (AwH) Ethiopia
Governments willing to work with donors to quickly scale the number of classrooms and seat spaces to accommodate students fleeing conflict, MoE Jordan
Education attendance
Provision of e-learning options – through TV, radio, internet (MoE)– and through provision of devices for poorest plus cash for connectivity – can support continued learning during crises and conflict (Covid–adapted Makani in Jordan, Gaza war by various NGOs)
Adolescent focused programming that helps address MHM barriers to attendance, e.g. tackles stigma and provides period products, AwH Ethiopia
Means-tested cash transfers labeled for education—UNICEF’s Hajati Jordan
Home education to allow young females not permitted to attend school to continue learning, MoE Jordan
Providing the poorest students with free school supplies and uniforms, SOS Ethiopia and Hajati Jordan
Night school (primary and secondary) and weekend education (post-secondary) for students who are combining work and education, urban Ethiopia
Encouraging girls’ education aspirations through exposure to inspirational stories and role models – Girl Rising, Bangladesh
Inclusive education
Stipends for young people with disabilities to attend school, Amhara regional state, Ethiopia
Special needs education to equip young people with communication/literacy skills (e.g. Braille or sign language)– then follow up and scaffolding as young people are moved into inclusive education - Amhara, Ethiopia
Learning outcomes
Remedial education sessions run by tutors who use engaging pedagogies and positive discipline approaches enhances learning outcomes – Makani Jordan
Schools that provide students (especially girls) with free room and board in the semesters that they sit gateway exams, BoE Oromia, Ethiopia
Long-term mentors to support school retention and coping with exam pressures – Room to Read, Nepal
Encouraging adolescent resilience and positive attitudes to support their educational journeys – Growth Mindset, Bangladesh

Health, nutrition and SRH
Physical health
Provision of bed nets and mobilizing communities to fight mosquitoes—and malaria. Oromia Bureau of Health, Ethiopia
Awareness raising about the importance of timely follow up for ear and eye infections to prevent longer-term disabilities. This is an example of what is not working well – e.g. Ethiopia.
Food and water security
Improving farmers’ access to fertilizer—to increase yields and reduce hunger. Ethiopia
Installing improved and centrally located water sources where communities rely on surface water, Ethiopia
Provision of electronic food vouchers for refugees – UNHCR/WFP Jordan, UNRWA Jordan
School feeding, especially in communities where food insecurity is common, Ministry of Education, Ethiopia
Exercise
Sports for development –esp. for girls and for young people in camps, Makani Jordan
Sports programming for young people with disabilities, Dire Dawa Ethiopia and Makani Jordan
Puberty education and SRH
Structured curriculum on gender norm change – for puberty, menstrual hygiene management (MHM) – AwH Ethiopia
Health care workers that work with newly married couples to discuss contraceptive options. Amhara regional state, Ethiopia
Synchronised gender norms and SRH programming for girls, boys and parents – Makani, AwH in Ethiopia, Foundations in West Africa
Strengthened self-confidence, awareness of rights – has spillover effects on SRH decision-making – Makani Jordan
School-based sexuality education teaches puberty, reproductive biology and contraception/ disease prevention, provided teachers are adequately trained. Ministries of Education, Bangladesh, Ethiopia
Community awareness raising by community healthcare workers about the importance of delaying parenthood and spacing pregnancies—until economically capable, and providing information to newly married couples about contraceptive options. Amhara Bureau of Health, Ethiopia
Provision of free sanitary products, soap and water for the most vulnerable girls and women – UNOCHA and UNHCR for IDPs in Ethiopia, UNRWA and various NGOs for IDPs in Gaza
Provision of adolescent-friendly spaces at health clinics, accompanied by training of personnel in adolescent-friendly communication approaches – Safe Spaces in Rohingya camps in Bangladesh, Bureaux of Health with Foundations support in Mali, Niger, Sierra Leone
Working with mentors from the same cohort/ background as target audience on SRH education – e.g. persons with disabilities, women engaged in commercial sex work (e.g. DKT-Ethiopia and Ethiopia Center for Disability and Development [ECDD])

Bodily integrity
Child marriage
Structured curriculum (in-school or extra-curricular) for adolescents and parents on risks of child marriage (vs community conversations that promote didactic soundbites) – AwH Ethiopia, Makani Jordan
Community surveillance committees (e.g. health extension workers, teachers, community leaders) can help to prevent CM – Ethiopia (highlighted through re-emergence of child marriage during Covid-19 and conflict)
Legal enforcement of age of marriage laws - Jordan (esp. for Syrian refugee community) and Ethiopia (but not where Shariah courts dominate)
Making families pay for child deliveries if the mother is a survivor of child marriage with the aim of discouraging child marriages and adolescent pregnancy – Jordan
FGM
Structured curriculum for adolescents and parents on risks of FGM for their daughters (vs community conversations that promote didactic soundbites) – AwH Ethiopia, Gender Clubs run by Bureaux of Education Ethiopia
Religious leaders preaching against FGM, esp. the most invasive forms (Types 2 and 3) – Ethiopia, with support/ training from UNICEF and from Save the Children Ethiopia
Age-based violence
Awareness about rights + where to report – Jordan Family Protection Unit, One Stop Centres in Ethiopia
Teaching children and adolescents how to communicate and solve problems with words rather than through physical force, Makani Jordan and AWH Ethiopia
Parenting classes to teach positive discipline strategies, Makani Jordan
School-based violence
Raising awareness of children and parents that they can report cases of teacher violence including through anonymous feedback boxes in schools – Jordan, UNRWA Jordan
Training teachers on non-violent/ positive discipline pédagogies – Makani Lebanon and Jordan
Gender-based violence
Awareness about rights + where to report – Save the Children Ethiopia programme for pastoralist communities, Makani Jordan, Jordan Family Protection Unit, One Stop Centres in Ethiopia
Providing comprehensive SRH, psycho-emotional, shelter and legal aid services for survivors of gender-based violence - One Stop Centres in Ethiopia
Teaching girls (and boys) how to prevent and respond to SGBV, AWH Ethiopia and Makani Jordan

Psycho-social wellbeing and voice and agency
Mental health disorders
Structured curriculum on feelings and how to deal with them, Makani Jordan
Psychological first aid for trauma-affected adolescents – Amhara and Tigray Bureau of Women and Children’s Affairs post-conflict
Peer networks
Programming that targets different communities to promote social cohesion, peer networks, and friends who are supportive and keep confidences– Jordan and Lebanon Makani, AWH Ethiopia
Participatory research programming to foster peer networks and build skills – GAGE Lebanon and Jordan
Trusted adults
Providing young people with access to caring adults in the form of adolescent programme facilitators or supportive female teachers, Makani Jordan and Lebanon, AWH Ethiopia, gender clubs Ethiopia, Foundations
Working with trusted adult mentors that are based in the community - Makani Jordan, R2R, Girl Rising
Teachers, life skills mentors, health extension workers – with whom adolescents have regular contact – can serve as powerful role models, esp. for girls – all countries
Agency in family
Parenting programming that includes a self-care element – leads to better adolescent -parent communication – Makani Jordan
Synchronised adolescent and parent programming that promotes communication and negotiation skills- AwH Ethiopia

Agency in school and community
Providing young people with opportunities to contribute to community solutions, Social Innovation Labs (Jordan), Ethiopia Qeeroo (youth development movement in early phase)
School parliaments that provide young people with opportunities to develop and exercise leadership skills, urban Ethiopia and UNRWA Jordan
Clubs/ PTAs that encourage student engagement and leadership, Ethiopia
Structured curriculum on confidence and goal setting and voice, Makani Jordan, AWH Ethiopia

Economic empowerment

Expand access to social protection that sufficient to allow young people to invest in education, rather than work, Jordan Hajati and Ethiopia’s PSNP and Education Stipends for Students with Disabilities
Financial education that encourages saving and links young people with formal and informal opportunities to do so, AWH Ethiopia, Makani Jordan
Improved access to credit paired with small-business skills training and financial education and sustained support, Save the Children Somali Region, Ethiopia
Training opportunities tailored to local economies (e.g. mobile repair shops; female plumbers in sex-segregated societies – e.g. UNICEF Jordan,
Donor funded ‘volunteer’ opportunities for work for refugees – e.g. Jordan, Bangladesh – UNHCR and various INGOs