Programme Completion Review

Title: Centre of Excellence for Development Impact and Learning (CEDIL)
Final Programme Spend £ (full life): TBC	Review Date:	May 2023
Programme Code: 203569	Start Date: September 2013	End Date: April 2023

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019	2020
Programme Score	C	B	A	B	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Year	2021	2022	2023
Programme Score	A	A	A+
Residual Risk Exposure Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/47588801.odt
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-1-203569 Documents (fcdo.gov.uk)

A. Summary and Overview

Description of the programme and what it has achieved
The Centre of Excellence for Development Impact and Learning (CEDIL) programme was established to: innovate in the field of impact evaluation and evidence synthesis; design, commission and implement impact evaluations and evidence synthesises; and promote the uptake and use of evidence from impact evaluations. Managed by a consortium led by Oxford Policy Management (OPM) and the London School of Hygiene and Tropical Medicine (LSHTM), CEDIL’s objectives were to:

- Develop and test innovative methods for evaluation and evidence synthesis.
- Fill gaps in knowledge by developing a rigorous evidence synthesis, impact evaluation and data sciences research programme (known as the Programme of Work [PoW]).
- Promote the use of this evidence and innovations in international development.

In pursuit of these objectives, CEDIL’s Research Directorate (RD) and Intellectual Leadership Team (ILT) undertook extensive scoping and academic analysis to identify the most important and promising areas for new work to strengthen methods of evidence synthesis and evaluation. This was consolidated into a specification for research in three thematic areas: (i) evaluating complex interventions; (ii) enhancing evidence transferability; and (iii) increasing evidence use. To deliver this, CEDIL was commissioned with three main components, a Research Directorate, Programme Directorate and Programmes of Work.

The programme was implemented by the CEDIL Directorate. The CEDIL Directorate consists of:
- Programme Directorate (PD), led by OPM.
- Research Directorate (RD) including the Campbell Collaboration, EPPI Centre, London School of Hygiene and Tropical Medicine (LSHTM) and the International Initiative for Impact Evaluation (3ie). The RD drew upon the expertise of an eighteen-member Intellectual Leadership Team, which included academics from the consortium members and several independent researchers.
  [note] The Centre for the Evaluation of Development Policies in the Institute of Fiscal Studies were part of the consortium until 2021.
  [note] The ILT include experts from eight other universities or institutions. There are Newcastle University, La Trobe University, Bangor University, Bath University, University of California San Diego, Oxford University, International Food Policy Research Institute (IFPRI) and Columbia University.

The procurement process involved a two-stage approach with separate Terms of Reference and procurement for the RD and the PD. The RD and ILT had overall responsibility for the strategic and technical direction, and the PD were responsible for delivery. RD was commissioned in 2017. Due to procurement and contracting delays, the PD did not commence work until April 2018, causing some challenges; the lessons from this experience are captured below.

In recent years, the operating context for CEDIL was affected by major shocks including: the onset of the Covid pandemic; the reduction in the UK’s Official Development Assistance (ODA) budget; the creation of the Foreign Commonwealth & Development Office (FCDO), which merged the Foreign and Commonwealth Office (FCO) with the Department for International Development (DFID); staff changes; the FCDO’s transition to a new financial management system; and, introduction of new DFID contractual Terms & Conditions which moved from an output-based milestone contract to more of an open book accounting model which required more detailed reporting. These factors created significant implementation challenges and had a material impact on the scope of the programme, with 40% of the research projects cut as part of ODA reductions. While CEDIL continued to deliver against logframe targets, as evidenced by previous Annual Reviews, the challenging context led to tensions between the FCDO and CEDIL Directorate, slowed decision making and generated a heavy administrative burden on both sides.

Despite these challenges, the programme delivered an ambitious portfolio and met or exceeded all of its final output targets within timeframe and budget. This included:

- 50 working papers including evaluations, synthesis and lessons learned papers
- 33 papers for academic journals
- 27 user-oriented summary products including briefing notes, portals/maps and methodological guidance
- 68 dissemination and training events held with FCDO or other users
- 42 blog and vlog posts published on the CEDIL website
- 2,006 CEDIL Twitter account followers
- 6,218 attendees at CEDIL Directorate events, including post-event online viewing.

Major lessons learned, evidence generated and recommendations

This review has captured a range of lessons for future programming of this nature – both in terms of programme design and management, as well as overarching methodological lessons relating to the CEDIL funded studies.
Methodological lessons

Evaluating complex methods
The CEDIL programme received relatively few proposals aiming at evaluating complex interventions using new methods and limited interest from academics to evaluate FCDO interventions of higher complexity. Researchers tend to approach the evaluation of complex interventions by singling out small components of the overall project that can be evaluated with existing methods such as RCT or qualitative approaches. One possible explanation for this is the current incentives. Studies addressing complex interventions and studies not employing RCT or other accepted method are less likely to succeed and less likely to be published. It is unlikely that researchers will start evaluating complex interventions using new methods unless they are actively encouraged to do so and this should be proactively designed into future programming of this nature.

It must also be recognised that the evaluations funded by CEDIL, although not always using innovative combinations of existing methods, did answer many policy-relevant question. This suggests that the challenges posed by complexity can often be overcome through careful use of existing methods which can deliver evaluations that make significant contributions to research and policy.

Machine learning methods
The use of machine learning methods in impact evaluation had not been identified as distinct Programme of Work but became a cross-cutting theme, as many of the research proposals included the use of machine learning methods. Some high-level lessons:
- Machine learning algorithms are designed to make good predictions, not to explain mechanisms. Although there are potential applications of machine learning methods in policy prediction and targeting, machine learning is not a substitute for causal inference and will be mostly used to support statistical analysis within existing methods such as RCTs.
- There are promising statistical approaches to the estimation of impacts for groups and individuals. CEDIL supported three studies using causal forest to assess the impact of interventions for specific subgroups.
- It is likely thsocial at, in future, machine learning methods will support the collection of inexpensive data in an innovative way. A CEDIL review of big data methods covers many of the existing opportunities in this area.
- Funding for conducting research using machine learning methods seems to be available, and researchers’ interest is high because the opportunities for publishing are many. There is limited added value for an organisation like CEDIL to promote the use of these methods unless it focuses on some niche, e.g., the study of heterogeneity through causal forests or similar.
- There are ethical issues involved in the use of machine learning methods, and one potential role for an organisation such as CEDIL could be to direct, or influence, machine learning research in areas that are useful for policy and known not to cause any harm.

Enhancing transferability through middle range theory
Middle range theory groups together observed empirical regularities, such as a common causal mechanism. Identification of such causal mechanisms, and the context in which they operate, can aid transferability of study findings. Examples of studies that applied this theory include:

- Teaching at the right level, which conducted a review to establish key moderators for effectiveness. Implementation fidelity – specifically assuring that a child was assigned to the right level – was found to be an important moderator, and this finding was subsequently confirmed in an RCT conducted in Botswana.
- A study of social accountability (SAcc) in health identified three approaches or pathways to scaling up. These are: resonance (build on expertise and existing experience within government), resistance (leveraging conflict by mobilizing civil society to advocate for change) and best practice (a technocratic approach based on evidence of what’s working elsewhere). One pathway sees change happen chiefly as a response to new information, another sees change happen chiefly through conflict, and another through deliberation, compromise, and collective action. Under the CEDIL project, the authors developed and tested these theories based on existing literature and found that context influences which pathways to scale are more likely to be effective at a particular point in time. They argue that there are four important aspects of context that should be considered when selecting the preferred pathway: organisational identity; connectors who have the legitimacy to convene actors from different places in the system; decision makers’ incentives; and, the broader enabling environment.

However, it was not always possible to apply this theory. For example:
- A review of Structural FP interventions used a conceptual framework which suggests that interventions need to be adapted to the life stage of the target group. However, they found that the included studies rarely specified the life stage so the theory could not be tested.
- A project to transfer an education evidence portal from the UK to West Africa planned to use income per capita as a moderator for assessing likely effectiveness in different settings, but found the evidence base too small to allow such an analysis.

Programme design and management lessons

The commissioning process
The CEDIL portfolio tended to focus on quantitative methods as the means to address difficult problems, with qualitative research under-represented in the portfolio. While it had been intended to prescribe which approaches would be used, it was instead decided to invite studies under the broader Programme of Work. This meant there was less opportunity to ensure that methods identified at inception got funded, so some approaches were not covered – e.g. structural equation modelling as an approach to middle range theory, or approaches to assess portfolio or country level effects.

CEDIL projects can be conceived as ‘settlers’ rather than ‘scouts’ in terms of innovation; that is, the funded studies used methods which had already emerged but are still being investigated (e.g. machine learning), rather than innovate in entirely new areas. Funding of ‘scouts’ would likely need a more targeted approach in terms of eligibility and specification and higher risk appetite.

Participation from research organisations from the global south and specifically Southern leadership was less frequent in the final portfolio of projects than had been hoped. Some additional strategies may have helped – e.g. grants for proposal preparation, use of different language and presentation/branding. Future programming of this nature should consider combining the development of methods with the commissioning of Southern-led evaluation and research to share, apply, test and further develop these insights, responding to evaluation challenges and evidence needs prioritised by southern policy makers.

One of the chief innovations in the commissioning process was the matchmaking route. This process identified suitable DFID programmes – prospective and retrospective – to be matched with proposals submitted under a call for proposals. This was effective in fostering new partnerships, and could be developed further as a mechanism to promote research co-production.

Research uptake and communication
A significant success of CEDIL is the high level of engagement of PoW teams with activities to support research uptake, dissemination and stakeholder engagement. This is in part due to the focus on research uptake in the design of CEDIL. Developing a research uptake and communication workstream (as opposed to just a communication workstream) was important for ensuring there was adequate staff time and resources dedicated to this area, which in turn informed a strategic approach to promoting stakeholder engagement and evidence use. The guidelines on stakeholder engagement and evidence use, the requirement of a robust plan from all project teams, clear reporting requirements and support from an embedded Research Uptake lead have been crucial for delivering a strong performance in this area.

Future programming in this space should include research uptake and communication along with a dedicated budget as part of programme design, and flow this down to subcontracted research projects. The grant timelines of research projects should also include some time for uptake activities post the completion of the study. The consumption and use of evidence takes time; allowing time for it will both signal to project teams that this is an important area, and also allow commissioners to generate clearer evidence of uptake. Research programmes that are working on developing methodological innovations should have a capacity development strategy for ensuring that the learning is shared with and used by a diverse set of stakeholders – leaning heavily on in-person, peer learning workshops where possible.

Contracting and sequencing of work
The original intention was for the PD to begin work six months after the RD. However, due to procurement and contracting delays, the PD did not commence work until April 2018, fifteen months after the RD. This delayed the development of the Programmes of Work and created challenges towards the end of the programme, when the RD went through a lengthy contract extension, which delayed work on certain outputs. Efforts to transfer RD and ILT contracts to OPM, creating a single line of reporting, were abandoned after it became clear that the complexities were too great. The introduction of new DFID Terms & Conditions required significant staff time to implement, detracting from substantive programme management and delivery.

While there was a clear rationale for a staggered start between RD and PD, future programmes should be keenly aware of the risks and put measures in place to ensure contracts align and to support efficient procurement. The introduction of new Terms & Conditions (or any similar substantive organisational change) could have been accompanied by a clearer specification of requirements to reduce the need for time consuming iterations and frustration on both sides.

Fast Track studies were added as a funding window for two reasons: (1) to build on ideas in the inception papers to make them more accessible, and (2) to generate CEDIL products earlier than some of the longer-term studies in order to enhance visibility. These were a useful addition which could have been built into the original design.

Risk appetite
Research programmes which aim to generate innovation in theory and practice entails a substantial degree of risk and uncertainty about outcomes and impacts at the outset. Promising areas of research may not produce the results that were anticipated, and transformative breakthroughs can occur from unexpected areas. Furthermore, many of the impacts of such programming will only be fully realised long into the future, after the period of funding has elapsed. Future programming of this nature should allow for some flexibility to respond to these risks and explicitly consider how to reflect this into the overarching approach to programme management on both sides.

Management and monitoring
Quality standards for PD deliverables were clearly defined and linked to the programme’s KPIs to ensure a shared understanding of expectations and to manage risks around delivery. These were stringently applied. This became a source of significant frustration for PD who argued for more flexibility to adjust these standards to better reflect reasonable delays or other unavoidable delivery issues. A reflection for the future is to consider how best to manage situations where there appears to be a discrepancy between achieving project logframe targets and the quality standards used for managing contracts. Concerns should be raised early to build a shared understanding of the issues, such that both parties are comfortable with proposed adjustments to KPIs or other standards to support programme delivery.
How this report was conducted
The review was conducted by the CEDIL Senior Responsible Owner (SRO) and Programme Manager (PM) during April and May 2023. It is based on:
- A review of documentation including minutes of relevant meetings, CEDIL work plans, CEDIL Annual Reports, programme logframe and KPIs.
- Interviews with the CEDIL Directorate, members of the ILT, grantees under the Programme of Work and the previous FCDO programme SRO.
- Group discussions with the CEDIL Advisory Board and Steering Committee.

The Deputy Director for the Economics and Evaluation Directorate has reviewed and approved this review.

Actions following approval of this report

Final invoices for the RD are expected by end of June 2023, due to late staff changes on the programme. The invoices outstanding are for the periods Jan – Mar 23 and Apr 23. Any unspent funds will be returned to FCDO and redistributed as appropriate. PD will be returning a balance of £1,276.44 due to an overcharge on NPAC. All outstanding audited annual statements and financial reports will be received in June.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£20 million	Final spend to be added on receipt of all outstanding invoices
Timeframe	5 years	5 years
Outcomes	CEDIL’s original outcome statement was “increased access, awareness and uptake of high quality evidence from impact evaluations in key policy and programme areas” with the intended impact of a “strengthened evidence base and understanding of what works in international development built around more and better impact evaluations”	Impact: ‘Stories of Change' which document and evidence accounts of evidence use arising from CEDIL's work or the use of methods and approaches promoted by CEDIL: Exceeded target / Outcome 1: Increased access, awareness and uptake of high-quality evidence from impact evaluations and syntheses in key policy and programme areas: Exceeded targets / Outcome 2: Increased capacity in the development and evaluation communities to commission and conduct evaluation in previously hard to evaluate areas: All but one target exceeded

Overall assessment of programme outcomes, sustainability and VfM

Overall the programme has scored an A+. All 15 of the cumulative programme end logframe indicators have been achieved within the timeframe and budget for CEDIL as agreed after the ODA cuts and subsequent reduction in the portfolio of PoW research projects. Several targets have been substantially exceeded demonstrating the effectiveness of CEDIL’s management and communications efforts.

CEDIL’s value for money in terms of effectiveness rests on improving the development policies and programmes, addressing knowledge gaps, and contributing to better use of evidence and evaluation findings to feed into more effective new interventions. So long as this evidence is used in decision making, the value for money on spend is likely to be high since the budgets spent by developing country governments, FCDO and other donors are far greater than CEDIL’s budget. As discussed below, CEDIL has exceeded its impact target and generated concrete examples of how CEDIL outputs have made a difference. Outputs have very high download statistics, and CEDIL dissemination events have been well attended. Feedback from the stakeholder survey also indicates that outputs are perceived as useful and that they are being used.

In terms of sustainability, all CEDIL-funded outputs are publicly accessible on the CEDIL website, the FCDO internal library and Policy Commons in order to retain accessibility following the closure of the programme website. This is a free database of high-quality grey literature, indexed in Google Scholar and other institutional libraries. In addition: a CEDIL landing page on the OPM website will provide information about the programme and signpost to Policy Commons; social media accounts will be used to disseminate links; a dedicated YouTube channel has been created with all audio/visual outputs; and, PoW teams have all been encouraged to share their outputs in social media and through their own channels. Sustainability, access and dissemination will also continue separate from CEDIL Directorate activities and after the official close of CEDIL. PoW teams have been submitting project papers to academic journals and will continue to do so after the close of CEDIL.

A sustainability strategy had been developed for the CEDIL programme to develop a second phase using core funding from FCDO. Due to budget constraints and limited ODA funding, implementation of the strategy was suspended in the 2021 and abandoned in 2022. However, individual projects were able to attract additional funding
on the strength of their CEDIL-funded work e.g. a disability evidence portal received funding from Wellspring Philanthropy for scale up; findings have been used to inform the design of a pilot project on performance-based financing in Cameroon, funded by the World Bank.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators

CEDIL has had success reaching the envisaged audience including researchers, evaluation practitioners, evaluation commissioners and users of evidence, and users are finding CEDIL’s products useful. Together with the output assessments in the next section, there is evidence that products have been well managed, high quality and that CEDIL has implemented a good approach to reach its audience with these products. The programmes’ theory of change has remained valid and relevant and the programme has had impact on the development community.

Theory of change
A summary of the programme’s theory of change is as follows. The CEDIL Directorate, using a consultative process, assessed current theory and practice in international development impact evaluation, identified strategic gaps and designed a ‘Programme of Work’ to address them. Projects within the PoW conduct research and evaluation activities. These generate outputs that provide recommendations to improve development interventions and policies, as well as guidance to enable others to deploy the innovations in methods that have been developed.

Stakeholder engagement at both a programme (CEDIL) and individual project level occurs through three channels to generate outcomes:

- Implementers and designers of interventions which are being evaluated by CEDIL, or those involved in similar interventions where CEDIL recommendations are relevant, receive actionable, well-evidenced recommendations to improve interventions from evaluation reports, policy briefs and evidence syntheses.
- The wider community of evaluation practitioners and academics receives methodological tools (e.g. guidance) and training to strengthen their capacity to conduct other evaluations in the gap areas addressed by CEDIL;
- Organisations which commission impact evaluations of development interventions and users of evidence will be provided with evidence on lessons learned and guidance on how to commission evaluations in areas where gaps in methods previously existed.

These will lead to the outcome of “increased access, awareness and uptake of high-quality evidence from impact evaluations in key policy and programme areas” and the impact of a “strengthened evidence base and understanding of what works in international development built around more and better impact evaluations”. One of the assumptions underlying CEDIL’s theory of change is that many of the thematic evidence gaps exist because current methods are poorly suited to evaluating programmes within them.

This high-level theory of change has not changed since the business case and remains valid and relevant. Since the programme began, CEDIL and FCDO have significantly developed the theory of change to tease out the pathways to impact, the assumptions and risks. CEDIL and FCDO worked to define the breadth of CEDIL’s reach and depth of impact that is reasonable within the programme’s resources and timescales, including adjusting this to the level of resources available to the programme. As a result, the impact and outcome indicators have been refined, and milestones have been added or adjusted.

Results framework
CEDIL’s intended impact is to contribute to a strengthened evidence base and increased understanding and application of what works in international development built around more and better impact evaluations and evidence syntheses. Evidence of CEDIL’s contribution to impact will be a long-term process beyond the life of the programme. Most of the robust evidence and methodological innovations emerge near the end of research projects, and it will take further time for this to influence development policy, programming and decision-making more generally. Nevertheless, impact has been evidenced through ‘stories of change’, defined as an instance of evidence use arising from CEDIL's work in which CEDIL-supported evidence, methods, or new approaches had informed decision-making.

Impact Indicator	Final target (cumulative)	Achieved
‘Stories of Change' which document and evidence accounts of evidence use arising from CEDIL's work or the use of methods and approaches promoted by CEDIL	5	9

The target for this indicator has been exceeded. Over the final six months of the programme, there were three additional instances of evidence use that meet CEDIL’s definition of a ‘story of change’, building on those described in previous Annual Reviews:

- ‘Seeds for recovery: the long-term impacts of a complex agricultural intervention on welfare, behaviour and stability in Syria’, has reported that lessons learned from the project have been shared with the Food and Agriculture Organisation’s (FAO) Syria team and have been incorporated in the design of the new Building Local Resilience Programme (BLRS), funded by FCDO.
- The fast track study on engaging stakeholders with evidence and uncertainty is being used to inform new guidance for the World Health Organisation on ‘How to promote evidence-informed decision making in the context of complexity and uncertainty of evidence’.
- A key finding of the first ever study to develop a Women Empowerment in Migration Index (WEMI) showed that lack of engagement with formal migrant advocacy groups, restricted mobility and lack of asset ownership are the largest contributors to women’s disempowerment. Based on these findings, the NGO, Bangladesh Nari Sramik Kendra has committed to promoting the freedom of association of migrant women in destination countries as a key focus area change in its action plan.

A summary of all stories of change are included in Annex C.

The outcome indicators below include a basket of measures covering potential users’ views on CEDIL’s evidence and methods; the proportion of attendees at CEDIL events who report they are likely to use methods or approaches from CEDIL in future evaluation activities; and downloads of CEDIL working papers or methods outputs. While one of the indicators is slightly below the final target, the remaining five indicators are above, some substantially so.
[note] It should be noted that while all the indicators have measurement challenges, together they provide reassurance of CEDIL’s approach.

Outcome 1: Increased access, awareness and uptake of high-quality evidence from impact evaluations and syntheses in key policy and programme areas
Outcome Indicators	Final target (cumulative)	Achieved
1.1 Percentage of relevant stakeholders who report in the stakeholder survey that CEDIL evidence outputs are useful or very useful	80%	83%
1.2 Number of downloads of working papers from CEDIL website, excluding those in the methods' series	1,050	2,782
1.3 Percentage of all stakeholders in CEDIL stakeholder survey4 who are non-academic users and who say that CEDIL evidence outputs are useful or very useful	70%	81%
[note] The stakeholder survey was sent to the CEDIL mailing list subscribers, project team members, ILT, Advisory Board, FCDO, disseminated on social media platforms and reposted via other relevant mailing lists. This means that it captures stakeholders who have come into contact with CEDIL through a number of different routes, such as engagement with CEDIL projects, attendance at seminars, social media etc.
[note] Working papers covered under the methods series are covered in outcome 2.

Outcome 2: Increased capacity in the development and evaluation communities to commission and conduct evaluation in previously hard to evaluate areas
Outcome Indicators	Final target (cumulative)	Achieved
2.1 Percentage of attendees at relevant CEDIL events who report that they are likely to consider using methods / approaches learned from CEDIL in future evaluation activities	80%	86%
2.2 Percentage of online survey respondents who report they are likely to consider methods learned from CEDIL when conducting or commissioning future evaluations	75%	74%
2.3 Number of downloads of CEDIL methods outputs (methods working papers, guidance notes and tools)	781	6,700

Revisions to logframe over the programme
The CEDIL logframe underwent two rounds of revisions during the course of the programme’s implementation. The first revisions and updates took place in the 2019-2020 programme year, with the second revisions taking place during 2020-2021.

Logframe revisions 2019-2020
The revisions that took place in 2019-2020 followed the completion of the first full year of CEDIL’s implementation phase and following the commencement of the PoW commission process. The changes were in response to a better understanding of the implementation of CEDIL and how it should be monitored. A number of indicators were clarified, revised or dropped. Changes included:

- Dropping 3 indicators that were judged not to be relevant (one on blogs republished and one on the participation of users directly in the research; and one referring only to evaluation commissioning, captured elsewhere).
- Revision to 10 indicators to improve clarity, measurability or relevance to CEDIL’s theory of change.
- The data sources for each indicator were revised, where necessary
- Milestones/targets were updated based on the total number of projects that have been contracted, the distribution of their contract end dates and an expected average number of outputs of a given type per project.

Logframe revisions 2020-2021
The logframe was further revised in 2020-2021 to take into account the reduction of PoW projects as a result of DFID ODA cuts. Changes were made to some indicators and targets and milestones were re-set once the effects of the budget cuts on both the portfolio of projects and the directorate workplans had been fully agreed. This meant it was only finalised at the end of the programme year.

- At the impact level, ‘Improved bodies of evaluation evidence in areas identified by CEDIL as evidence and synthesis gaps and addressed through the programmes of work’ was dropped as an indicator, since individual outputs which respond to this objective were counted at the output level. Instead, attention was focussed on reporting on the use of evidence and methods through ‘stories of change’.
- At the outcome level, the indicator ‘Percentage of evaluation findings and recommendations accepted by organisations conducting or financing the interventions evaluated’ was dropped. This was difficult to benchmark and monitor, and of limited practical relevance since CEDIL only funded a small number of evaluations that would provide recommendations at the end of the programme.

Indicators that counted downloads of CEDIL outputs were also revised to fully separate evidence outputs from those that are primarily methods focussed. Target numbers for indicators were also revised to reflect the reduced portfolio of research projects and the revised content and timing of the workplans of both the programme and research directorates. In addition, milestones for download numbers were revised to reflect current average download counts.

2021-2022
During 2021-2022 there were no further changes made to the logframe however it was agreed with FCDO that the results associated with three outcome indicators should be considered the endline as of September 2022:

- 1.1 Percentage of stakeholders who report in surveys that CEDIL evidence outputs are useful or very useful
- 1.3 Percentage of all stakeholders in CEDIL stakeholder survey / feedback who are non-academic users and who say that CEDIL evidence outputs are useful or very useful, and
- 2.2 Percentage of online survey respondents who report they are likely to consider methods learned from CEDIL when conducting or commissioning future evaluations are considered to be the endline.

These indicators relied on undertaking another stakeholder survey just 4/5 months after the previous survey. It was agreed that it would be very unlikely that we would achieve a good enough response rate to provide meaningful results and undertaking another survey therefore would not represent value for money.

## C: Detailed Output Assessment

Output Number 1	Relevant, high-quality evaluations and methodological papers / outputs produced
Output Score	A+
Impact weighting (%)	50	Impact weighting revised since last AR?	No

Output Indicator	Starting Target (from 2019/20 logframe)	Final Logframe Target	Final Result Achieved
1.1 Number of high-quality evaluation, synthesis and methods development projects commissioned	32	19	19
1.2 Number of working papers published on CEDIL website, including evaluations, synthesis and lessons learned papers	58	43	50
1.3 Number of papers for academic journals drafted by PoW and RD	20	26	33
[note] Note that final logframe targets were adjusted in 2021 to reflect programme cuts following the reduction in the UK’s ODA budget.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

All targets have been met or exceeded. Indicator 1.1 reports the total number of CEDIL funded projects that are either complete or ongoing. This number was achieved in the 2020-21 reporting period as no new projects were initiated after this point. This was an agreed reduction from the original planned 32 projects.

Indicator 1.2 reports the number of working papers published on the CEDIL website, produced either by the research directorate or the PoW. It includes methodological, evaluation, synthesis and lessons learned papers which are produced in any phase of the programme. During the final six months of the project, sixteen papers were finalised, exceeding the final logframe target, itself reduced to reflect the cuts made during the reduction in the ODA budget. The papers that are complete and are either published or in the final stages prior to publication include six from the Research Directorate, one from fast-track studies, three from small and six from large projects. These are listed in Annex A and can be accessed on Policy Commons.

Indicator 1.3 reports the number of papers that have been drafted for peer-reviewed academic journals by the directorate and the PoW. In the last six months of the programme, eight papers were drafted bringing the cumulative total to 33.These are listed in Annex B.

Lessons learned through this output, and recommendations for future programming
The programme has generated a wealth of academic papers, user-oriented outputs, and communications activities. At the start of implementation, the output measures were refined until they were agreed in the final iteration of the logframe in 2019-20. The indicators were revised again after the FCDO budget cuts in 2021 so that they were aligned to the reduced number of PoW projects and expected outputs, with the revised version of the logframe agreed in 2021. Lessons from this experience cut across programme outputs so are captured in Section A.

Delivery was underpinned by careful planning and selection at each stage of the programme, including the selection of ILT members who wrote the inception papers and careful management of the PoW competitive commissioning process. Outputs were disseminated widely within the FCDO and across the development sector more broadly; FCDO will continue to draw on these papers and promote them via internal communication channels.

Output Number 2	User-oriented outputs produced by Directorate or Programmes of Work which provide clear policy recommendations and enable broader take-up of methodological innovations
Output Score	A++
Impact weighting (%)	30	Impact weighting revised since last AR?	No

Output Indicator	Starting Target (from 2019/20 logframe)	Final Logframe Target	Final Result Achieved
2.1 Number of user-oriented summary products produced and published on CEDIL website, including briefing notes, portals/maps and methodological guidance	46	18	27
2.2 Number of Directorate dissemination and training events held with FCDO or other users; for 2021/22 and beyond: & attended by at least 20 people	65	47	68
[note] Note that final logframe targets were adjusted in 2021 to reflect programme cuts following the reduction in the UK’s ODA budget.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output measures the progress of the programme in translating its research to user-oriented products and ensuring that the knowledge generated can be effectively used by FCDO and other stakeholders. It includes two indicators, both exceeded, demonstrating that CEDIL outputs are being disseminated both via the website and through interactive workshops and events.

Indicator 2.1 reports the excellent progress made in producing user-oriented summary products and publishing these outputs on the CEDIL website. These include methods briefs, evidence briefs, toolkits, maps and methodological guidance. These are designed to be more accessible than the full academic working papers and therefore appeal to a wider audience, as well as being a means to direct readers to the full reports. Over the last six months, 12 outputs were published on the CEDIL website thereby exceeding the target by nine. This includes:

- Access to Justice Evidence and Gap Map
- Malawi Country Evaluation Map
- Methods brief: Innovations in measurement and the evaluation of human behaviour
- Evidence briefs:
  - Gender equality and social inclusion in WASH interventions
  - Involving men and boys in family planning
  - Beyond Kafala: Employer roles in growing vulnerabilities of women migrant domestic workers
  - Development and validation of a Women's Empowerment in Migration Index (WEMI)
  - Economic development interventions in humanitarian settings
  - Making and justifying evidence claims in international development
  - Language of instruction in schools in LMICs: A systematic review
  - Financial services in refugee hosting areas
  - Structural interventions to enable adolescent contraceptive use

CEDIL outputs continue to be downloaded regularly. Overall, the most downloaded paper from the CEDIL programme has been CEDIL Methods Working Paper 6: Evaluating complex interventions in international development, which has been downloaded an impressive 957 times since it was published in December 2021. CEDIL Methods Working Paper 9: Evaluation and Measurement has also seen particular interest,
attracting 594 downloads since it was published in August 2022.

Indicator 2.2 details the number of directorate-level dissemination and training events held with FCDO or other users. In the final six months, 11 events were held thus bringing the cumulative total to 68, far exceeding the target of 47. This includes:

- 6 webinars: ‘Gender equality and social inclusion mainstreaming in WASH interventions: experiences from implementation, research and policy’; ‘The effectiveness of digital financial services in humanitarian interventions: results of an adaptive randomized trial in Ethiopia’; and ‘SEEDS for recovery; The impact of agricultural interventions in Syria’;Can we reduce vulnerabilities of short-term low-skilled women migrants in the South-to-West Asia corridor? Results from the Gender-Sensitive Risks and Options Assessment for Decision Making (ROAD) to Support WiF-2’; ‘Evaluation and Measurement’; and ‘How Biased are observational methods in practice? Accumulating Evidence using randomised controlled trials with imperfect compliance’.
- 4 FCDO workshops: ‘What is the contribution of machine learning to the evaluation of development interventions?’’; ‘What Works for you’; ‘Middle range theory’; and ‘Assessing the strength of evidence claims’
- 1 CEDIL Conference: ‘Innovations in Impact Evaluation: What Have We Learned?’

Lessons learned through this output, and recommendations for future programming
Having project teams host CEDIL-supported outputs on their own websites promotes accessibility and sustainability in the long-term, and ensures that the outputs can be updated by the grantees, if they receive additional funding. It is also cost effective as hosting these outputs on the CEDIL website was not practical as it would have required significant website development work. However, despite ensuring that these outputs included the CEDIL and UK Aid logos on their site and acknowledged CEDIL funding these were not captured under indicator 2.1 as they were not posted or hosted on the CEDIL website. Consideration should be given to defining indicators in the future such that it takes into account other hosting platforms and develop mechanisms to track this over implementation.

Events targeted specifically at FCDO were helpful for raising awareness of CEDIL and highlighting the relevance of the programme outputs to FCDO activities.

CEDIL webinars and conferences have significantly contributed to building CEDIL’s brand in the public domain. By convening conversations on a range of topics, the programme was visible, engaged with diverse audiences and steadily built the mailing list. The high attendee numbers in the final conference is testimony to the credibility built over the years and the high level of interest in CEDIL’s work.

Output Number 3	A range of communication products and activities to disseminate its objectives, activities and outputs effectively to generate broad interest in CEDIL among the research, evaluation and user community
Output Score	A+
Impact weighting (%)	20	Impact weighting revised since last AR?	No

Output Indicator	Starting Target (from 2019/20 logframe)	Final Logframe Target	Final Result Achieved
3.1 Number of blog and vlog posts published on the CEDIL website	53	29	42
3.2 Total number of CEDIL Twitter account followers	1,980	1,980	2,006
3.3 Total number of 'attendees' at CEDIL Directorate events, including post-event online viewing, numbers and diversity of stakeholders represented by these	3,900	3,000	6,218
[note] Note that final logframe targets were adjusted in 2021 to reflect programme cuts following the reduction in the UK’s ODA budget.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output indicator 3.1 reports on the number of blog and vlog posts published on the CEDIL website. In the last six months, 10 blog posts were posted on the CEDIL website, bringing the total to 42, far exceeding the endline target of 29. These discussed a broad range of CEDIL-funded projects for example the findings of experiments to increase financial access in areas of Ethiopia with large refugee populations or insights from a participatory action research study with women migrant domestic workers in Lebanon.

Output 3.2 reports the total number of CEDIL Twitter account followers. Strong interest in the CEDIL conference and in the final CEDIL outputs led to a surge in followers in the final quarter. The handle added 317 followers over the last six months to reach a total of 2,006 at the end of March 2023, exceeding the endline target by 26. More importantly than follower numbers, there has been good engagement with those followers, with tweets being viewed, shared, liked and commented on, generating the kind of dialogue that will contribute to ongoing learning and discussion beyond the lifetime of CEDIL.

Output 3.3 records the total number of 'attendees' at CEDIL directorate events, including post-event online viewing, their numbers and diversity. The target of 3,000 was more than doubled, largely driven by high levels of interest in the CEDIL conference in February 2023 which saw high registration and attendance numbers and strong interest in watching the recordings after the event; videos of each day were uploaded to the CEDIL YouTube channel and each has seen triple figure views. Conference attendees who completed post-event feedback represented a broad range of job roles and a good geographical spread, covering 38 countries. Webinar attendees for events this year also represented a diverse set of audiences based on collected job function data.

Lessons learned through this output, and recommendations for future programming
Blogs and vlogs have been an important communication output for raising CEDIL’s profile and establishing the programme’s link to the research projects. They have aided the plain language communication of research and have contributed to building conversations on issues that need to be amplified. Over the last two years, blog numbers significantly increased as research projects came to fruition. Cross-posting PoW project blogs on the CEDIL website also helped support the dissemination efforts of project teams.

Social media platforms, particularly Twitter, have helped to build CEDIL’s brand and the dissemination of work. Many of the target audiences are on Twitter and LinkedIn and focussed efforts on these platforms have paid off. In the operations pack shared with grantees, they were encouraged to tag CEDIL on social media platforms. Many grantees followed the guidance, which notified the secretariat and triggered support for teams in their outreach activities.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

Value for Money (VfM) has been assessed throughout the life of the progamme using FCDO Research and Evidence Division’s ‘quality and value at each step’ approach, which is most suitable for investments which do not and cannot have entirely pre-determined outputs (in terms of research and evaluation findings), outcomes and impacts.

Key features of this approach include:
- Working through strong partnerships
- Always requiring good quality
- Procurement - controlling quality and costs via open, competitive processes
- Programme Management – tight oversight of programme delivery.

The tracking of VfM also utilises FCDO’s VfM framework: Economy, Efficiency, Effectiveness and Equity.

The open call for proposals and the review process of the PoW was crucial to ensuring its VfM potential. The FCDO’s review for relevance strengthened the PoW’s potential VfM, as it included consideration of whether each research project’s evidence output would fill existing, high priority evidence gaps. The cuts made as a result of the reduction in the UK ODA budget prioritised the highest potential projects based on criteria judging value and relevance. However, the reshaping of the programme meant some projects were closed before they were able to reach fruition, which had costs and reduced overall potential value.

The research projects have advanced and utilised cutting edge methods in both impact evaluation and evidence synthesis. They were managed for quality and to maximise learning across the portfolio. Quality for the PoW was also incentivised by the professional expectations and settings of most participants, such as for university academics.

Crucial to CEDIL’s effectiveness and cost effectiveness is that the research and learning is well disseminated to potential users. Previous sections of this review describe the range and reach of dissemination activities. The publications have been well received by the target audience and provide outputs that can highlight the value of the programme’s research within FCDO and more broadly. The dissemination and training events have far exceeded their targets. The excellent performance in this area increased the value from CEDIL as more people gained access to CEDIL’s outputs. CEDIL’s performance on the outcome indicators show that products and dissemination events are valued by users.

On economy and efficiency for CEDIL Directorate’s management costs:

The fees and overheads for CEDIL Directorate staff were fixed during the procurement, although some were restructured during the recent PD contract amendment which reduced costs or increased value. Both RD and PD were procured via an open and competitive process.

CEDIL Directorate actively managed the costs of their expenses. Some specific examples where they made good decisions to minimise costs without decreasing quality were:
- The restructuring of the research uptake staffing provided better value for the inputs by ensuring work is done at the appropriate skill level.
- The two CEDIL-organised conferences (2022, 2023) were held online, enabling a larger and more diverse audience and significantly saving on costs (comparing to other academic conferences on FCDO projects the savings could have been as great as £80-100k).
On equity, gender and social inclusion: The original guidelines for the PoW included recommendations on conducting impact evaluation that is sensitive to disability. Several of the research projects had an explicit focus on equity, gender and social inclusion e.g.: “Gender and social outcomes of water, sanitation and hygiene interventions: Synthesis of research evidence”, and “Synthesising evidence on generating demand for contraception among adolescents”. Several of the programmes focused on improving the availability of evidence for disadvantaged groups, such as the impact evaluations funded through CEDIL for refugees and for female migrants. Many CEDIL research projects explored who the interventions work for and in what context. These methodological innovations are important for producing better evidence for gender and social inclusion. At a management level, the composition of the Advisory Board went some way towards addressing the inclusion of voices from the global south, which was light in the CEDIL Directorate and the ILT.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating for CEDIL was moderate. This was within the risk appetite for the programme. CEDIL had 16 open risks that were categorised into six areas:

- Public Service Delivery & Operations
- Policy & Programme Delivery
- Safeguarding
- Financial & Fiduciary
- Reputational
- Strategy & Context
CEDIL’s risks were monitored and updated regularly throughout the life of the programme by both FCDO and CEDIL. All risks had appropriate mitigation strategies in place to ensure these risks were minimised.

At programme closure, the residual risk ratings were:

Residual risk rating	Number of risks
Major	1
Moderate	9
Minor	6

In the final year of the programme, the number of residual risks rated as major reduced to one and this was related to the effectiveness and timeliness of the CEDIL programme in light of upheavals caused by the reshaping of the programme following the onset of COVID-19 the reduction in the UK ODA budget.

There were nine risks rated as moderate. On the FCDO side, they were around adequate staffing being available to effectively deliver the programme, and organisational and UK political changes affecting decision making and the potential to gain value from CEDIL products and learning. From the partner perspective the risks were quite varied, ranging from misuse of funds due to the work taking place in high fraud environments and safeguarding, ensuring quality of CEDIL’s outputs, through to CEDIL not being able to deliver if performance levels reduce or staff turnover, particularly if staff choose to find other opportunities before the programme ended. Research projects finishing on time remained a significant risk, not least due to context risks such as the current Ebola outbreak in Uganda. Mitigation strategies proved effective to manage these risks.

In the final year of the programme, four risks which were rated as moderate in the last Annual Review were reduced to minor, bringing the total number of minor risks to six. This was due to PD performance improvements; improvements in financial processes for each component, and proven delivery showing that risks had been successfully mitigated.

Through the lifetime of the programme, 9 risks were closed. Of these, six were moderate risks and three were minor risks. For the moderate risks, on the FCDO side, they were around tendering, procurement, and contracting issues. All the risks had appropriate mitigation strategies in place to ensure these risks were minimised.

COVID-19 risks and impact
The risks caused by COVID-19 related to delays in research projects, or delays in the interventions being studied/evaluated, was recognised early. The COVID-19 pandemic emerged just as projects were starting to undertake their research work which caused delays in many aspects of project implementation. These included reduced staff working hours on the research projects (e.g. to cover childcare responsibilities), staff sickness, delays in recruitment, delays to planned fieldwork activities, travel bans, and, in some cases, delays to the interventions being studied. Virtually all projects that were undertaking primary data collection had to postpone their fieldwork or switch to remote data collection methods.
The pandemic generated also additional work for the CEDIL Directorate. The PD had to spend a great deal of time understanding the expected impacts of COVID-19 on projects and mitigation measures being implemented.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Delivery and performance of partners
Overall, both parts of the CEDIL Directorate - RD and PD - performed well. Early in the programme, the timeliness of responses on aspects of programme management and delivery led to some improvements being required. This included more emphasis being placed on ensuring that resources were allocated to high priority tasks, changing the balance of the team, increasing the amount of administrative support to then free up capacity for more strategic programme management and more hands-on management by senior OPM officials. A regular meeting was added between a senior member of OPM’s staff and the FCDO SRO. This was helpful in enabling progress to be made on CEDIL’s day to day management and removing some of the frustrations and difficulties that had formed in the relationship. Together, these steps were effective at supporting good performance.

Relationships between PD and RD were positive and productive, though there were occasional issues of confusion on roles and responsibilities. However, the team were able to work together to resolve these challenges.

Financial
At the start of the programme, the quality of financial management and forecasting was raised as an issue with both PD and RD. For PD, the issue was around a lack of timeliness on forecasting. For RD, difficulties in getting invoices from downstream partners combined with staffing issues had resulted in delays to submitting invoices. PD improved their forecasting of PoW expenditure over the programme and started to produce forecasts regularly that were better informed by information from PoW subgrantees.

Over the life of the programme, all aspects of finance improved, with invoicing and forecasting being more timely leading to a more accurate financial picture. Reporting on expenditure was provided quarterly, along with narrative reports.

Assets
RD confirmed no changes to their asset register. The laptops are in their possession and functioning. The condition is fair. On closure, these laptops will remain with RD following guidance in the PrOF.

PD confirmed no changes to their asset register. This contains minor electronics and stationery. PD keep oversight of the assets for the PoW research projects. On closure assets for the PoW will be transferred to the existing delivery partners. The required asset transfer forms have been received in line with the Programme Operating Framework guidance.

For any assets that are transferred externally, the following requirements will be met:

- The recipient has adequate resources to maintain and operate the asset, including purchase of any consumables
- The recipient will not sell the asset, or use them for a non-aid related purpose for a minimum of 1 year from the date of transfer
- The recipient has adequate controls in place to ensure that the asset is used as intended
- The recipient will meet any local requirements regarding duties and taxes or any other formalities, on transfer
- Once no longer in use, the recipient will dispose of the asset in line with the EU Waste Electrical and Electronic Equipment (WEEE) Regulations and all personal data will be removed

Commercial
FCDO agreed contract amendments with both RD and PD to reflect the reshaped programme, as well as to incorporate new cost and transparency requirements. The contract amendments’ revised deliverables were central to the governance and management relationships between FCDO and RD / PD.

Both RD and PD submitted annual declarations for 2020, 2021, 2022 in line with suppliers’ commitments for open book accounting. The declarations show that their profit levels are within the targets agreed.

LSHTM and OPM were both compliant with the Supply Partner Code at their last assessments. LSHTM was assessed in June 2019 and OPM was assessed in October 2018.

Monitoring
FCDO’s Senior Responsible Owner (SRO), Programme Manager and other staff had regular meetings with CEDIL staff over the life of the programme, and throughout the final year of operation. Many matters of substance and administration have been discussed, both in regular CEDIL Directorate meetings and through e-mail conversations. CEDIL produced quarterly reports that allowed for detailed monitoring on progress, finances and risks. FCDO staff attended CEDIL’s conferences, seminars and workshops and regularly reviewed research and communication outputs.

Date of last narrative financial report	Oct 2022	Date of last audited annual statement	PD: Apr 2020 - Mar 2021 / RD: Aug 2020 - Jul 2021

Annex A: Working papers published on CEDIL website, including evaluations, synthesis and lessons learned papers, October 2022 – March 2023 (Output 1.2)

Research Directorate:
• Verma, A., Higginson, A., Saran, A., Adona, J., Bless Taremwa, R., Kachero, B., Beveridge, E., Zhen, L., White, H.: Evidence and gap map – studies of the effectiveness of justice sector intervention in low and middle – income countries. CEDIL Syntheses Working Paper 8
• Kapoor-Malhotra, S., Vigneri, M., Dela Cruz, N., Hou, L., White, H.: Systematic Review: Effectiveness of economic development interventions in humanitarian settings in low- and middle-income countries: a mixed-methods systematic review. CEDIL Syntheses Working Paper 9
• Bangpan, M., Draper, A., Minchenko, D., Stansfield, C., Dickson, K., Tripney, J., Oliver, S.: Making and justifying evidence claims: evidence synthesis of impact evaluations and systematic reviews in international development. CEDIL Syntheses Working Paper 10
• White, H.: The use of middle-level theory in CEDIL-funded research studies. CEDIL Lessons Learned Paper 1
• Oliver, S., Minchenko, D., Banpgan, M., Dickson, K., Stansfield, C., Tripney, J.: Evidence claims for informing decisions for socio-economic development. CEDIL Lessons Learned Paper 2
• Lewin, A., Diaz-Ordaz, K., Bonell, C., Hargreaves, J., Masset, E.: Machine learning for impact evaluation in CEDIL-funded studies: an ex ante lesson learning paper. CEDIL Lessons Learned Paper 3
Fast-track studies:
• Crincoli, T., Beveridge, E. and White, H.: Development impact evaluations in Malawi: A country evaluation map. CEDIL Syntheses Working Paper 6
Small projects:
• Macura, B., Dickin, S., Sharma Waddington, H., Liera, C., Soto, A., Orlando, A., Foggit, E., Pross, C., McArthur, .J, Fadhila, A., Del Duca, L., Njoroge, G.: Gender and social outcomes of WASH interventions: synthesis of research evidence, CEDIL Syntheses Working Paper 7
• Aventin, Á., Robinson, M., Hanratty, J., Keenan, C., Hamilton, J., McAteer, E. R., Tomlinson, M., Clarke, M., Okonofua, F., Bonell, C., & Lohan, M.: Involving men and boys in family planning: A systematic review of the effective components and characteristics of complex interventions in low- and middle-income countries. CEDIL Research Project Paper 3
• Bernard, D., Bryan, G., Chabé-Ferret, S., de Quidt, J., Fliegner, J., Roland R.: How Biased are Observational Methods in Practice? Accumulating Evidence Using Randomised Controlled Trials with Imperfect Compliance.
Large projects:
• Handa, S., Liu, Z., Tembo, G., Adamba, C. and Mvula, P.: ‘An empirically driven theory of poverty reduction’, CEDIL Research Project Paper 4
• Juden, M., Mapuwei, T., Tietz, T., Sarguta, R., Medina, L., Prost, A., Humphreys, M., Jacobs, A., Allen, E., Mwambi, H. and Davey, C.: ‘Process Outcome Integration with Theory (POInT): academic report’, CEDIL Research Project Paper 5
• de Brauw, A., Gilligan, D., Leavens, L., Moges, F., Roy, S., and Tefera M.: Impact Evaluation of the SHARPE Programme in Ethiopia: Academic Report, CEDIL Research Project Paper 6
• Baliki, G., Weiffen, D., Al Daccache, M., Kayaoglu, A., Sujud, L., Jaafar, H., Ghattas, H., and T. Brück: Impact evaluation of complex agricultural interventions in Syria: An Overview
• Ringler, C., Abdulrahim, S., Adra, Alvi, M. F., Choudhury, Z. A, ElDidi, H., Kilby, P., Nassif, G., Ratna, N., Sufian, F., van Biljon, C. and Wu., J.: Gender-Sensitive Risks and Options Assessment for Decision Making (ROAD) to Support WiF2 Final Academic Report and Evaluation. CEDIL Research Project Paper 8
• Bernard, D., Bryan, G., Chabé-Ferret, S., de Quidt, J., Fliegner, J., Rathelot, R.: How Biased are Observational Methods in Practice? Accumulating Evidence Using Randomised Controlled Trials with Imperfect Compliance. CEDIL Research Project Paper 9

Annex B: Papers drafted for academic journals, (Output 1.3)
Making predictions of programme success more reliable: https://cedilprogramme.org/publications/making-predictions-of-programme-success-more-reliable/

Using big data for evaluating development outcomes: a systematic map:
https://cedilprogramme.org/publications/cedil-methods-working-paper-2/

The science in the middle: middle level theory in international development evaluation: https://cedilprogramme.org/publications/methods-working-paper-3

Engaging stakeholders with evidence and uncertainty: developing a toolkit: https://cedilprogramme.org/publications/cedil-methods-working-paper-4/

The strategic use of evidence and gap maps to build evidence architecture: https://cedilprogramme.org/publications/cedil-methods-working-paper-5/

Evaluating complex interventions in international development: https://cedilprogramme.org/publications/cedil-methods-working-paper-6/

Timely evaluation in international development: https://cedilprogramme.org/publications/timely-evaluation-in-international-development/

The unfinished evidence revolution: riding the five waves: https://cedilprogramme.org/publications/the-unfinished-evidence-revolution/

Evaluation and Measurement: https://cedilprogramme.org/publications/evaluation-and-measurement/

Development evaluations in Uganda 2000-2018: A country evaluation map: https://cedilprogramme.org/publications/cedil-syntheses-working-papers/cedil-syntheses-working-paper-1.1

Development impact evaluations in Pakistan: A country evaluation map: https://cedilprogramme.org/publications/cedil-syntheses-working-paper-2

Evidence and gap map-studies of the effectiveness of transport sector intervention in low and middle-income countries: https://cedilprogramme.org/publications/evidence-and-gap-map-transport-sector-intervention

The role of implementation in generalisability: A synthesis of evidence on targeted educational instruction and a new randomised trial: https://cedilprogramme.org/publications/synthesis-of-evidence-on-targeted-educational-instruction-and-new-randomised-trial/

Structural interventions aiming to enable adolescent use of contraception in low- and middle-income countries: https://cedilprogramme.org/publications/structural-interventions-aiming-to-enable-adolescent-use-of-contraception-lmics

Development project evaluations in Malawi: A country evaluation map: https://cedilprogramme.org/publications/development-evaluations-malawi-map/

Gender and social outcomes of WASH interventions: synthesis of research evidence: https://cedilprogramme.org/publications/gender-and-social-outcomes-of-wash-interventions

Access to justice evidence and gap map - studies of the effectiveness of justice sector intervention in low and middle–income countries: https://cedilprogramme.org/publications/access_to_justice_gap_map

Systematic review: The effectiveness of economic development interventions in humanitarian settings in low- and middle-income countries: A mixed-methods systematic review : https://cedilprogramme.org/publications/effectiveness-humanitarian-interventions

Making and justifying evidence claims: evidence synthesis of impact evaluations and systematic reviews in international development: https://cedilprogramme.org/publications/making-and-justifying-evidence-claims-evidence-synthesis

How do we shape and navigate pathways to social accountability scale? Introducing a middle-level Theory of Change: https://cedilprogramme.org/publications/cedil-research-project-paper-1/

Using meta-analysis to explore the transferability of education mid-range theories to Cameroon, Chad, Nigeria and Niger: Final academic report – Evidence synthesis: https://cedilprogramme.org/publications/using-meta-analysis-to-explore-the-transferability-of-education-mid-range-theories

Involving men and boys in family planning: A systematic review of the effective components and characteristics of complex interventions in low‐and middle‐income countries: https://cedilprogramme.org/publications/involving-men-and-boys-in-family-planning

An empirically driven theory of poverty reduction: https://cedilprogramme.org/publications/empirically-driven-theory-poverty-reduction/

Process Outcome Integration with Theory (POInT): academic report: https://cedilprogramme.org/publications/process-outcome-integration-with-theory-point-academic-report/

Impact Evaluation of the SHARPE Programme in Ethiopia: Academic Report: https://cedilprogramme.org/publications/impact-evaluation-sharpe-programme-ethiopia

Seeds for recovery: The long-term impacts of a complex agricultural intervention on welfare, behaviour and stability in Syria (SEEDS) : https://cedilprogramme.org/publications/seeds-for-recovery

Gender-Sensitive Risks and Options Assessment for Decision Making (ROAD) to Support WiF2: https://cedilprogramme.org/publications/gender-sensitive-risks-migration/

CEDIL Final Report: How Biased are Observational Methods in Practice? Accumulating Evidence Using Randomised Controlled Trials with Imperfect Compliance : https://cedilprogramme.org/publications/how-biased-are-observational-methods-in-practice

Empowering Women: Teaching Leadership Skills to Youth in Uganda: https://cedilprogramme.org/publications/teaching-leadership-skills-to-youth-uganda

Making Entrepreneurs: The Return to Training Youth in Hard versus Soft Business Skills: https://cedilprogramme.org/publications/making-entrepreneurs

The use of middle-level theory in CEDIL-funded research studies: https://cedilprogramme.org/publications/middle-level-theory-cedil-research

Evidence claims for informing decisions relating to socio-economic development: https://cedilprogramme.org/publications/evidence-claims-socio-economic-development

Machine learning for impact evaluation in CEDIL-funded studies: an ex ante lesson learning paper: https://cedilprogramme.org/publications/machine-learning-for-impact-evaluation

Annex C: Summary mpact stories
2020-2021
Country evidence and gap maps
The Office of the Prime Minister (OPM) in Uganda has been using the Development evaluations in Uganda evaluation map in various ways:
- OPM has used the map to develop an Evaluation Agenda for the health sector.
- The evidence and gap map has also been used to identify recent relevant studies across the different Sustainable Development Goals to inform Uganda’s Voluntary National Review of the implementation of the goals. The report on this review was presented by the Minister for General Duties at the UN High Level Political Forum in October 2020.
- The studies in the map have been one source for a scoping study of research on women’s groups in Uganda.
Evaluating complex interventions
CEDIL funded the first-of-its-kind Disability Evidence Portal, which contains evidence briefs that offer clear, actionable recommendations as well as a rating of the synthesised evidence. An evidence portal is a CEDIL-promoted approach that directly relates to the programme of work on evidence use. This approach is now being scaled up – the project team received additional funding from Wellspring Philanthropy for scaling up the site and expanding from eight briefs to a hundred.
The team believes that the additional funding came through because CEDIL enabled the set-up of a ‘proof of concept’ site that was considered viable investment. CEDIL’s disability evidence map was also the basis for four (then) DFID-funded rapid reviews which were registered as full systematic reviews. These reviews will generate quality evidence and feed into the rapidly expanding Disability Evidence Portal.
2021-2022
Using Meta-Analysis to explore the transferability of education: mid-Range theories to Cameroon, Chad, Nigeria and Niger (2 stories)
Findings from the study have been used to inform the design of a pilot project on performance-based financing in Cameroon. Funded by the World Bank and implemented by Health Development and Consultancy Services, Community Action for Global Development, and Effective Basic Services (eBASE), the pilot project provided teachers in 24 schools with incentives to improve teaching and learning. The performance pay intervention was designed based on gaps identified in the meta-analysis to improve access and retention of poor children, strengthen education quality governance, safety and security.
The eBASE team’s engagement with government officials in Cameroon for the CEDIL project also helped build trust with policymakers. They went on to sign a convention of support with the ministries of basic education and secondary education. The team believes that work on the project has stimulated government investments in performance-based financing and raised their interest in improving parental engagement through community schools. The World Bank were interested in financing supply side education interventions through the School Reforms Project of Cameroon. Performance based financing is an approach that theoretically increases incentives to teachers who work with low salaries and poor work conditions. As the meta-analysis showed that evidence in the area is ‘very limited’ the best bet was to implement a pilot project for better defining the intervention and assessing its acceptability and feasibility. A report based on the pilot project was submitted to the World Bank and the Government of Cameroon, showing promising results.
eBASE have also used the findings of the meta-analysis also to inform the design of another pilot evaluation of menstrual hygiene management (MHM) in Cameroon. This is being funded through a separate Education Endowment Fund project. The meta-analysis (and the toolkit) shows that MHM interventions are low cost but have unclear impact based on insufficient evidence. Although MHM is an approach that is funded by many donors in Cameroon and rolled out by civil society organisations, the intervention is not well defined. The pilot evaluation being carried out by eBASE is based on a review of existing MHM projects in Central Africa and in Cameroon where they have been implemented in mixed settings of conflict (North West and Far North Regions) and extremely poor settings with indigenous populations (East Regions).

The role of implementation in generalisability: A synthesis of evidence on targeted educational instruction and a new randomised trial
Evidence from the study has been used to inform the programme design and scale up of teaching at the right level (TaRL) in Botswana and has informed discussions on programme implementation in Namibia and South Africa. As Youth Impact is supporting the implementation of TaRL in multiple contexts, the evidence has been very relevant to programme related decisions. For example, the CEDIL-supported study showed the importance of strong monitoring data to track implementation fidelity. To this end, the TaRL scale up in Botswana has employed daily accountability surveys to assess student progress and learning. These surveys include student performance on 'problem of the day' questions that enable close scrutiny of targeted content delivery and how well students respond to it.
The CEDIL-funded study also highlighted how small differences in delivery and implementation can have potentially large effects on the effectiveness of TaRL programming. The Botswana scale up employed rapid iterative testing with each implementation period to test tweaks to the regular TaRL formula. An example of a rapid test was to learn whether differences between how learning groups are created in TaRL classrooms affects learning outcomes. In the same way that the study showed that the delivery person matters (i.e., youth volunteers vs. teachers), the TaRL Botswana scale up and other innovation hub initiatives have begun to look at how delivery happens to learn whether similar small changes can have a big effect on program impact.
The CEDIL-supported study has also been influential in terms of providing credible evidence for backing programme design decisions. The TaRL scale-up in Botswana used government employed youth volunteers to deliver the program in primary schools across the country. Although this model has been in use for several years, the authors report that the CEDIL-supported study provided strong evidence about the continued benefits of the youth volunteer model to the Ministry of Basic Education and TaRL Botswana implementers like Youth Impact.
Youth Impact has provided technical support to a new TaRL start-up in Namibia, advising on the relative differences between delivery models. This includes discussions on teachers versus youth volunteer delivery. Youth Impact also engaged in discussions with partners in South Africa, notably the Department of Basic Education, to bring TaRL to the country. Conversations in the early stages centred around delivery models, including the use of youth volunteers for program delivery. The authors believe that the close affiliation with several dissemination networks, such as the PAL Network and TaRL Africa, including the latter's Innovation Hub in Botswana, implies that the study will continue to be relevant, as governments and implementers bring TaRL to new country contexts, especially within the context of Sub-Saharan Africa.
Involving men and boys in family planning: A systematic review of the effective components and characteristics of complex interventions in low- and middle-income countries
The CEDIL-funded study, along with previous work carried out by the research team, has influenced the World Health Organisation (WHO) to commission several members of the project team to lead the WHO/MenEngage global network on engaging men in sexual and reproductive health and rights (SRHR) and to undertake global research on a priority setting exercise on masculinities and SRHR. According to the project team, the CEDIL project also helped build on the policy and researcher network developed through previous systematic review work done for the WHO. Stakeholder engagement carried out through the CEDIL project, particularly with an international advisory group, has helped in expanding the network to include independent consultants and representatives of NGO.
2022-2023
‘Seeds for recovery: the long-term impacts of a complex agricultural intervention on welfare, behaviour and stability in Syria’
The project team has reported that lessons learned from the project have been shared with the Food and Agriculture Organisation’s (FAO) Syria team and have been incorporated in their current programming through the new Building Local Resilience Programme (BLRS), funded by FCDO. This five-year, GBP 35.25 million programme, which began in April 22, will reach at least 65,000 Syrians per year. It aims to make them less dependent on emergency aid, and more economically and socially resilient to prevailing shocks and stresses. It will target the most vulnerable, particularly women, young people, and those with disabilities.
One of the team’s recommendations to FAO was to cluster interventions to achieve stronger impact, particularly for achieving stronger resilience of households. The BLRS programme will aim to provide the same beneficiaries with multiple agricultural interventions to avoid spreading support too thinly. The team also recommended that FAO foster local markets to ensure the sustainability of the impacts. In line with this, the BLRS focuses more on building local markets and resilience in Syria.

Engaging stakeholders with evidence and uncertainty
The fast-track study (FT.2) and toolkit on engaging stakeholders with evidence and uncertainty is being used to inform new guidance for the World Health Organisation (WHO) on ‘How to promote evidence-informed decision making in the context of complexity and uncertainty of evidence’. According to the lead author of this fast track study, the lead of WHO’s unit for Evidence to Policy and Impact considered the CEDIL-supported toolkit to be an excellent starting point for developing new guidance for the WHO. The author is currently working on a first draft of this guidance for WHO.
The Evidence to Policy and Impact Unit is located in the Research for Health Department/Science Division at the World Health Organization. It aims to strengthen the regular use of context-specific research evidence for improving accountability and accelerating impact in countries. The WHO typically shares guidance with its member states for supporting the use of evidence in policy formulation and implementation. We can therefore expect the guidance being developed by Sandy to be disseminated widely across WHO’s members states. The CEDIL-supported fast track study can potentially have global influence on the stakeholder engagement approaches used by governments and organisations in WHO’s networks.
Gender-Sensitive Risks and Options Assessment for Decision Making (ROAD) to Support WiF2
A key finding of the first ever study to develop a Women Empowerment in Migration Index (WEMI) has informed the action plan of the NGO, Bangladesh Nari Sramik Kendra (BNSK). The NGO focusses on promoting social and economic justice for women workers, including migrants. The CEDIL-supported study showed that group membership, restricted mobility and lack of asset ownership are the largest contributors to women’s disempowerment. Women with higher empowerment scores were more likely to have established contact with other migrants in the destination country, indicated by a positive statistically significant coefficient. Based on these findings, BNSK has committed to promoting the freedom of association of migrant women in destination countries as a key focus area change in its action plan, adopted on International Women’s Day (8th March) in 2023. The NGO has committed to pursue this area of change, amongst other changes, and report on the progress made on International Women’s Day in 2024.
[note] Bangla translation of Bangladesh Centre for Women Workers.
BNSK has worked with over 18,000 potential and returnee Bangladeshi women migrant workers since 2010. The NGO has been supporting women migrant workers working in Jordan, Saudi Arabia, Bahrain, Oman, Qatar, UAE, Kuwait, and India. To promote the freedom of association for women, the NGO plans to (i) raise awareness and develop the capacity of women migrants to improve access to information and services and offer them opportunities to network and organize themselves; (ii) support the production of data and research evidence, drawing on the experiences of women migrant workers, to feed policy advocacy efforts in Bangladesh and in destination countries for promoting gender equality in migration; and (iii) support skill development for building livelihoods and strengthening economic leadership in all spheres (family, community, state, country and destination country).
The key factor that influenced evidence use in this instance is the continued engagement of the research team with a diverse set of stakeholders including NGOs, policymakers, civil society organisations, the UN, and funders. The study leads acknowledged that CEDIL’s advice to look beyond academic audiences was helpful for developing a strategy to engage with a diverse set of stakeholders.