## Annual Review Template

Title: Investing in Human Capital through Partnerships Beyond Aid (PBA)
Programme Value £ (full life): 25 million		Review date: 22 January 2021
Programme Code: [AMP ID#] 203640	AMP start date: 22 January 2020	AMP end date: 30 December 2024

Summary of Programme Performance
Year	2020	2021
Overall Output Score	A	B
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-203640/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-203640/documents

A. SUMMARY AND OVERVIEW

Description of programme

The goal of the ‘Investing in Human Capital through Partnerships Beyond Aid’ Programme (PBA) is self-reliance by Government of Ghana (GoG) in managing and financing the social sectors to deliver quality services to all Ghanaians. Ultimately this will contribute to the achievement of the GoG’s ambition of a Ghana Beyond Aid, reducing the need for UK and other donors' support.

The expected PBA outcomes of greater accountability and more efficient, higher quality and equitable delivery of services by the Ministries of Health (MoH), Education (MoE) and Ministry of Gender, Children and Social Protection (MoGCSP), will ensure that human capital, the foundation for Ghana’s economic transformation, poverty reduction, and prosperity, is strengthened. Better management of available resources will reduce the cost of quality social sector services and encourage greater national resource mobilisation. Programme objectives will be delivered through three main components as follows:

- Expert technical assistance (TA) to GoG Ministries to build capacity, support regular analyses and reviews to inform innovative solutions to address fiduciary and other systemic weaknesses across the three sectors.
- Building partnerships between GoG and Her Majesty’s Government (HMG) and other UK institutions for mutually beneficial learning and exchange of expertise. FCDO Ghana will also support improved coordination of UK social sector aid to GoG across HMG departments and multilateral organisations.
- Grants and TA support to Civil Society Organisations (CSOs) to hold the GoG to account and advocate for increased and strategic government spend on the social sectors through effective monitoring of social sector budgets and services.

During the 2021 Annual Review (AR) period, programme components were implemented by the following partners:

- Christian Health Association of Ghana (CHAG) continued to implement the ‘Covid-19 response and institutional capacity building’ project for the continuous provision of basic health services at the district level (The CRIB Project – June 2020 – June 2022), focusing on delivery of high quality Covid-19 response services and continuing delivery of essential health services in 40 underserved districts.
- STAR Ghana Foundation (SGF) was contracted for a year from 1 October 2021 to 30th September 2022 to promote accountability and responsiveness of government to citizens around Covid-19 responses and mitigation strategies through five civil society organisations
- The Centre for Democratic Development’s (CDD) was contracted for a second year (December 2021 – March 2022) to assess the outcome of the Ministry of Education’s medium-term interventions (2018-2021) that addressed challenges in the Education sector, including regional disparities in quality and access to education that result in low completion rates, unreasonably high number of out-of-school children, and access to water and sanitation in schools. The scope of the CSO projects is aligned with the priorities of the PBA programme for the period under review.
- West Africa Centre for Cell Biology and Infectious Pathogens (WACCBIP), as part of the Covid-19 pivot that continued during the 2021 AR period, was contracted for 18 months period, November 2021 to 2023 to address a specific gap in the surveillance component of the Ghana’s Covid-19 response by expanding Covid-19 sero-prevalence and genome sequencing activities nationally, particularly to border towns and building capacity within institutions for health security surveillance.

Summary supporting narrative for the overall score in this review

Overall, the PBA programme moderately did not meet expectation during this second AR period despite notable achievements in three of the four outputs assessed during this AR period. The programme output focusing on sector financing and public financial management capacity (output two) was not scored for the second year.

During the first year of the programme, PBA had two external changes in context that required an adaptation of the programme - the onset of the Covid-19 pandemic which led to a necessary focus on support tackling Covid-19 and the Ghana Presidential Elections impacted the type of accountability work that could be delivered. The ongoing challenge of the pandemic has meant that the programme continued to focus support on Covid-19 during the 2021 AR period, due to second, third and fourth waves of infections in country. In addition, the 2021 AR period saw the continued reduction of the PBA budget allocation for fiscal year 2021 to 50% of forecast. The reduced programme budget resulted in the difficult decision to halt work on procurement of the primary technical assistance supplier for the programme with a detrimental impact on set milestones for several of the programme outputs.

The flexible and adaptive design of PBA nonetheless led to significant achievements, particularly in response to Covid-19, and important progress was made on the social accountability programme component. The objectives of PBA were not to support direct service delivery, but the pandemic necessitated this pivot. However, this support - through CHAG - for Covid-19, was also designed to address a primary objective of PBA - health system strengthening. There are examples of the CHAG component establishing at the local level quality Covid-19 response services interventions including high quality diagnostic center’s and intensive care units in underserved areas and improving co-ordination of information and service delivery for both essential health care and Covid-19. Under this component, the district health service leaders met the Director General of Ghana Health Service (GHS) for the first time, providing a forum to raise issues and generate open discussions with senior leaders in the health sector. Therefore, via the Covid-19 component, the programme has been able to contribute to improved health service delivery, system strengthening through improved co-ordination mechanisms and community engagement that have been critical in tackling the health burden in the 40 districts of operation and beyond.

The health workforce partnership with the UK Department for Health and Social Care (DHSC) has been developed closely between the Department and FCDO Ghana. This has required the relationships and networks the Health Adviser, Programme Management staff and Team Leader have with GoG to facilitate the development of the partnership. This will contribute to PBA’s focus on addressing a priority area for GoG, building capacity in the workforce and through the migration of Ghanaian Heath workers to the UK, ensuring a mutually beneficial partnership. The PBA team supported the design of the DHSC Health workforce systems strengthening programme for upskilling health Ghana’s health workforce. The DHSC programme is on track to achieve the target of training over 6,000 health workers on reproductive health and Covid-19 case management; supporting improved management of the health workforce through training of health workforce managers and providing data to inform equitable distribution of the health workforce; and the provision of scholarships for the training of persons from refugee and host communities for training as healthcare workers. The UK/Ghana partnership therefore is a potential example of the types of partnerships the UK will seek to establish across other sectors. Whilst not currently built into programme plans, we are conducting exploratory discussions in the education sector including learning lessons from the partnership the health sector. At present there are exploratory discussions for how to build peer to peer learning in the education sector although a similar partnership is not presently planned.

The social accountability interventions have been successful in supporting Government of Ghana (GoG) to safely re-open schools and holding GoG to account on its response to Covid-19. The approach to engaging with parliament, whilst a useful way to consider holding GoG to account, was a challenge to try and initiate given the outcome of the Presidential Elections with the ruling party returned with a narrow margin, increasing the adversarial nature of discourse and pressure on members of parliament to vote along party lines. The other challenge has been the short timeframe for identifying and supporting CSOs to establish various interventions because of delays in agreeing the programme resource allocation and ensuing difficulty in agreeing a one-year programme of work with SGF on a limited budget and a late decision to contract CDD for further work on the education sector. These issues have constrained partners to deliver this year however overall, the social accountability programme component met expectations.

Major lessons and recommendations for the year ahead

The delays in establishing partnerships with CSOs has proved challenging for identifying activities and hinders the ability to develop sustainable interventions.

Engaging community and traditional leaders as part of Ministry of Health led committees on health co-ordination and for the Covid-19 response specifically has been critical in improving outcomes in districts. It would be important to maintain these committees which span both medical, political and opinion leaders to ensure the sustainability of the co-ordinating mechanisms the CHAG component has helped establish.

Recommendations for the PBA 2021 Annual Review Period

Re-set – An assessment is required of how fit for purpose PBA remains linked to the wider portfolio, including consideration of FCDO’s refreshed vision and objectives, the changing country context and how this should influence future interventions. An early decision is required by senior management and should be undertaken as part of the country business planning process. Final PBA refreshed programme offer to be concluded and submitted by PBA’s SRO to FCDO’s Development Director for approval and implementation by July 2022, after which the logfame will be updated in line with agreed activities.

Preliminary analysis by the PBA team in line with FCDO’s strategic vision suggests a continuation of existing PBA objectives of improving quality, efficiency, and access across the social sectors with a sharper focus on interventions that deliver improved outcomes for women and girls. Focus areas include effective sexual reproductive health rights education and services delivered for adolescent girls through Ghana’s National Health Insurance Scheme (NHIS), Ghana’s School Health programme, Ghana Education Service, linked to work of civil society (e.g. STAR Ghana, Camfed) and UN agencies (UNICEF, UNESCO, UNFPA), ensuring integration with other social protection systems to reach the most vulnerable girls and women. A sub theme would be building greater resilience across the sectors to mitigate, adapt and withstand shocks, building on the lessons learned through the Covid-19 pandemic.

Education - As the bilateral Education Beyond Aid (EBA) programme comes to an end in September 2022, the PBA team should agree what can be supported in the sector through PBA, cognisant of FCDO’s wider education portfolio, GoG priorities and requests for TA, FCDO priorities and identifying areas which can also maximise cross-sectoral co-ordination. PBA team to work with FCDO Ghana senior management for a final decision on education focus within PBA, extension of EBA and/or design of any future bilateral education programmes as soon as budget allocations are known to allow for effective transition of interventions from EBA to PBA as needed.

PFM - PBA is set up to support the management and financing of the social sectors which includes a focus on public financial management. FCDO Ghana has a standalone public financial management (PFM) programme, and the PBA team is in discussion with the country economist on how to align work on PFM. This could be drawing on advice and inputs from the economist and/or seeking centrally managed support through a potential new central resource on PFM. The final decision is dependent on final PBA budget allocation and the outcome of the PBA reset activity by July 2022.

1. Co-ordination across sectors – PBA was in part established to support co-ordination across social sectors, at present the programme is not delivering this due to the current context. The FCDO team should explicitly look at how this can be part of PBA for the coming year with plan of action developed by PBA team for implementation by July 2022 in line with the scale of ambition agreed for PBA
2. Future Technical Assistance - FCDO to review the need for procurement of TA support for the social sectors as was originally planned prior to Covid-19 and budget cuts once the final budget allocation for the PBA is known.

Covid-19 Support - PBA had to reorient support to address the Covid-19 Pandemic. However, it is likely GoG will continue to require support on Covid-19 as the pandemic continues into a third year. A reassessment of FCDO Ghana’s continuing bilateral support for Ghana’s Covid-19 response is however required in the face of competing PBA priorities, continuing reduced PBA funding envelope, and the transition of Covid-19 towards endemicity. Therefore, there should be consideration of a six months costed extension of the CRIB project until December 2022 for a responsible exit to ensure attainment of Ghana’s Covid-19 vaccination target, a key step towards Covid-19 recovery, and to consolidate gains made in maintaining high quality health service delivery in underserved communities. The PBA team to intensify engagement with MoH, Health Development Partners and multilaterals on including CRIB project activities under current and planned programmes head of closure of the CRIB project.

Social Accountability in the Social Sectors - With a three-year Spending Review agreed for FY 2022, FCDO should aim to sign Social Accountability Accountable Grant with CSOs with a three-year timeframe to enable them to plan their interventions over a longer time. This will help improve delivery and effectiveness.

Star Ghana Foundation - the value for money proposition for implementing this PBA programme component through the SGF requires further scrutiny, particularly considering the scope of HMG’s engagement with SGF that extends far beyond PBA’s remit. FCDO Ghana Development Director, informed by advice from the PBA team, should by June 2022 decide on the preferred delivery route for the social accountability component of PBA.

Health workforce Partnership – Preliminary steps taken during the AR period have been productive in drawing together lessons learned from FCDO engagement with DHSC on the health workforce and broader DHSC partnerships from across FCDO country platforms. PBA team to continue to draw best practice from other teams within the British High Commission, and FCDO’s global directorates to build strategic partnerships between UK government departments and Ghana in the social sectors.

Assets - FCDO to conduct asset verification on programme funded assets with CDD-Ghana, CHAG, WACCBIP and SGF by March 2022.

Audit - FCDO to conduct an expenditure verification exercise on SGF by March 2022 and commission overall programme audit by July 2022 to coincide with CHAG’s closeout audit.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme theory of change as outlined in the Business case is that provision of timely high quality technical assistance, analysis, and partnership with UK institutions, coupled with greater GoG accountability for spend in the social sectors will lead to sufficiently robust, efficient, and equitable social sector institutions. Institutions are then equipped to deliver quality and equitable social sector services that meet the needs of all Ghanaians. Better management of GoG and other existing external resources will lead to improved outcomes, will reduce costs and in time, lead to greater GoG self-reliance in delivering quality education, health, and social protection services. Key principles to drive effectiveness are strong GoG ownership, accountability, and coordination across sectors.

The impact of Covid-19 continues to constrain the ability of GoG to fund social sectors sufficiently and meet service needs of Ghanaians. Therefore, supporting GoG to address funding gaps will be critical. Covid-19 has also changed the funding context in country since PBA was established. There was an influx of support through the World Bank for health as well as an increasing number of foundations and other donors that have emerged and are providing support across the social sectors. Whilst Ghana accessing these sources of funds is not contributing per se to reaching self-sufficiency, it will still be important through PBA to support GoG to leverage available funds from diverse sources and manage these funds appropriately, ensuring adequate accountability.

The issue of resourcing links to resilience and GoG’s priorities to build back better during and following the pandemic. The theory of change does not explicitly mention resilience, but it is in part implied through the focus on self-sufficiency of funding, and systems strengthening.

Therefore overall, the theory of change still holds. The resourcing of the social sectors, alongside ensuring improved accountability remains critical, especially within the evolving context of the pandemic. Given the changes in context since PBA’s inception it would be important for FCDO Ghana to review the underlying assumptions and consider how to build resilience into the outcome and impact targets once the programme reset is agreed.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

There is limited data available within this AR period to assess progress against impact and outcome milestones, a situation compounded by the impact of Covid-19 on routine surveys and analyses.

The programme is off track in achieving the programme impact of self-reliance by Government in managing and financing the social sectors to deliver quality services to all. Government expenditure in the social sectors as a percentage of GDP is unavailable for the FY2021 however a review of allocations to the social sectors as a percentage of GDP shows that allocations are consistently below expectations although increasing for health (Table 1)

Table 1: PBA Impact assessment
Impact: self-reliance by Government in managing and financing the social sectors to deliver quality services to all.
Impact Indicator	2021 Target	Achievement 2021
% of Government's expenditure on (i) Health (ii) Education and (iii) Social Protection as % of GDP	Health (1.6 %, 2018); Education (6 %); Social Protection (0.6 %)	Information on expenditure unavailable. Allocations to GDP %: health 2.1%, Education: 3.5%, Social Protection: 0.2% STAR Ghana budget review 2021

Progress was made on the PBA programme outcome of greater accountability and more efficient, higher quality and equitable delivery of services by the Ministries and Agencies of Health, Education and Gender. Overall, Government allocation to the social sectors increased in the 2022 budget when compared with 2021, with a 14% increase in allocation in Education, 25% in Health and 34.3% for Ministry of Gender, Children and Social Welfare. As a percentage of total government allocation, health and social protection allocations however remained generally flat, with 8.4% allocated against 8.1% in 2021 in health, 0.8% against 0.7% in Social but declined for education with 12.9% allocated against 13.7% for education. Government expenditure in health has been demonstrated however to be consistently above allocations however late release of funds and irregular disbursements contribute to inefficiencies in delivery, limited additional impact and overall poor value for money. An assessment of the levels of poverty and inequality in Ghana is expected in mid-2022.

The CRIB project contributed to GoG health gains in the 40 implementation districts by surpassing the AR targets for outpatients utilization rate at district and sub district levels with 54.1% utilisation rate against a target of 50% at sub district level and 45.9% utilisation rate against a target of 44% at district level.

PBA has therefore contributed to a small degree to mitigating the scale of the negative impact to the programme’s expected health outcomes anticipated as a consequence of Covid-19. The work delivered through PBA during this AR period has contributed to supporting programme objectives including systems strengthening, keeping a focus on quality of services, and enabling some measure of self-sufficiency in GoG funding in the current context of Covid-19. However, as PBA starts a third year, the programme needs to re-orient to capitalise on the opportunities for improved co-ordination and inter-sectoral learning that PBA was designed to deliver. At present the programme is off track in achieving this element.

Whilst PBA has worked across all sectors, the focus has been more weighted to health and accountability with some success, but less support provided to education and social protection. Due to budget constraints and the need to focus on Covid-19 support, there has not been a more strategic approach to working across all the sectors for the first two years of the programme. Furthermore, given existing programmes in the education and social sectors and some flexing within these to ramp up support during Covid-19, it had not been necessary to use PBA to support interventions in these sectors.

Constraints in bilateral funding over the next three-year period and the natural closure of some programmes provide an opportunity to consider support across all social sectors and bringing the programme back on track. There is a risk that with the closure of the bilateral education beyond aid programme and streamlining of FCDO Ghana’s social protection Leave No one Behind Programme, hard-won gains may be lost and there will be nothing to replace these unless PBA pivots back to its primary remit. The ongoing country business planning process will also provide a useful point for re-positioning PBA within the wider portfolio of bilateral support. A plan for the final three years of PBA will need to be developed in line with the changing context and shifting GoG priorities which may necessitate a t re-calibration in the framing of interventions within each output area. GoG has focused on building back better and supporting resilience because of the pandemic and as stated above this will need to be weaved into PBA’s future interventions.

This assessment should also be done with a focus on key cross cutting themes that PBA seeks to support and how these will shape future interventions across all sectors. This will be important to ensure PBA’s adaptable and flexible design does not lead to ad hoc or small-scale interventions that are not able to build out to coherent contributions to the overall programme impact. The key themes are:
- Leadership and Governance
- Efficiency in service delivery
- Quality, Data and Accountability

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The overarching purpose of the programme is to enable Ghana to self-finance social sectors and deliver equitable and quality services to citizens. This is still relevant and should continue for Ghana to attain middle income status and a Ghana beyond Aid. Covid-19 continues however to impact the ability of GoG to fund and deliver effectively in the social sectors. Given the successive waves of Covid-19 in country and emergence of new variants, GoG will continue to need support in addressing the pandemic and its likely transition towards endemicity. Therefore, whilst the primary purpose of PBA was not to deliver health services for Covid-19 it may require a continued focus on strengthening systems to adapt to each new phase of the Covid-19 outbreak in Ghana.

The social accountability work has enabled support across social sectors and education albeit at a smaller scale than had been envisaged. However, the success of these activities and the ability of the Covid-19 work to contribute more broadly to system strengthening highlights how despite a challenging change in context, PBA has been able to continue to contribute to the overarching objectives. The challenge will be to effectively shift the programme back to its primary purpose but within a changed and evolving context. Whilst doing this, it is important to ensure the flexible nature of the programme that has enabled adaptation over the last two years, does not lead to small scale interventions across the sectors that collectively, do not enable impactful results for equitable and quality service delivery.

## C. DETAILED OUTPUT SCORING
Output Title	Improved governance capacity, systems, and mechanisms within social sector ministries to organise and deliver high quality services for all.
Output number:		1	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, revised downwards from 15%

Indicator(s)	Milestone(s) for this review	Progress
1.1: Extent of effective governance structures for the social sectors to deliver quality services	Institutional assessment of systems and capacities undertaken, and recommendations shared with stakeholders	Met Expectation / Health: a) MoH-led Health May Summit assessed capacities/systems against health outcomes. Recommendations were captured in Aide Memoire signed with DPs and informed Sector Operational plan. / b) WB health allocative efficiency assessment shared with stakeholders to inform work on strengthening financial management in the health sector. / Education: MoE held its annual National Education Week in October, where regional education directors and the national inspectorate presented to stakeholders on education system, infrastructure, district delivery and capacity challenges, against school access and learning outcomes. Recommendations were captured in an Aide Memoire signed with DPs. MoE is conducting capacity assessment of agencies responsible for edtech and complementary education and plans to strengthen district delivery processes with support from the Reform Secretariat. / Social Protection: a) Ministry of Gender, Children, Social Protection held their annual summit – Innovations for service delivery – on 10th November. The Summit focused on showcasing key innovations e.g., the impact of the Integrated Social Service and Case Management (SWIMS) system. / b) The integrated Social Sectors annual review highlighted various interventions to strengthen provisions of services to the vulnerable through the government social protection programmes e.g. increasing access and outreach of community health services to the Government’s Livelihood Empowerment Against Poverty (LEAP) programme households specifically the development of additional collaboration protocols between Ghana’s National health Insurance Scheme and LEAP to simplify enrolment and renewal onto the health insurance system and on strengthening data interoperability between LEAP and Ghana Health Service (GHS).
1.2: Level of readiness, responsiveness, and effectiveness of TA	TA providers procured and inception phase commenced	Procurement process for the main TA suppliers halted. TA finalised for Fiduciary Risk Assessments for the social sectors
Indicator(s) Milestone(s) for this review Progress	Indicator(s) Milestone(s) for this review Progress	Indicator(s) Milestone(s) for this review Progress
1.3: Level of digitisation of government business data reporting, interoperability, and delivery of new/improved systems	Not measured during this AR period due to the absence of contracted TA to take forward work in this area
1.4 Level of intersectoral coordination, monitoring and accountability mechanisms strengthening GoG systems social sector services	Not measured during this AR period due to the absence of an objective review

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this output moderately underachieved against set milestones. FCDO Ghana social sectors advisers leveraged the pivotal role FCDO holds in each of the sectors as part of Development Partners networks and sector working groups to contribute to sound sector assessments and recommendations for improving systems., despite the disruptions to operations caused by the second, third and fourth Covid-19 waves experienced in Ghana during the AR period. Changing business operating environment and reduced budget settlement for FCDO Ghana and consequently PBA led to a reduced scope of work for the planned technical assistance supplier’s procurement during the AR period.

1.2: Procurement of technical assistance suppliers: The three separate procurements envisaged in the business case were consolidated to two to reduce complexity and expedite the procurement process during the previous AR period. During this AR period, continuing reduced bilateral funding settlement for FY 2021 in the context of Covid-19 led to the termination of the process for procuring the main technical assistance supplier providing TA to the ministries and managing grants and capacity building to CSOs. The terms of reference for the second TA supplier for fiduciary risk assessments and a programme monitoring and evaluation and learning was reduced to address only fiduciary risk assessments (FRAs) for the health and education sectors. After a competitive tender process, the Crown Agents led consortium was identified to execute the FRAs.

The implementation of the FRAs for the education and health sectors would in the short term, provide the necessary assurance required to continue implementation of financial aid and other funding instruments through FCDO Ghana’s Leave No One Behind and Education Beyond Aid programmes. It will also inform development of PBA’s refreshed programme offer to the social sectors during the next AR period.

Output Title	Strengthened sector financing (e.g., allocation, accessing alternative sources of financing) and PFM capacity (e.g. improved budgeting, management) within social sector ministries to implement effective financing and efficiency reforms.
Output number:		2	Output Score:	Not Scored during the AR period
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1: Extent to which spending MDAs are able to plan and commit goods and services expenditures in accordance with original/revised budgets.	5% increase in goods and service expenditure against allocated budget	Information on incremental increase from 2019 to 2020 unavailable during the AR period. Allocations for goods and services in the social sectors for GoG 2022 fiscal year are as follows: / Health: 22% of the budget allocated for goods and services. / Education: 25% of the budget allocated for goods and services / Social Protection: 96% of the budget allocated for goods and services (optimised)
2.2: Number of expenditure reviews conducted	Not Measured this AR period	Expenditure Reviews for Health and Education commenced.
2.3: % increase in Ghana’s score on Open Budget Survey (OBS) and level of implementation of recommendations.	5% increase in Ghana’s score on OBS	OBS not conducted within the AR period.

Output two, for the second year running, was not scored during this AR period due to absence of PBA contracted TA to take forward programme engagement in this area. PBA advisers in health, education, and social protection however engaged with their respective sector ministries in monitoring financial allocations and expenditure, and working with development partners in their sectors, undertook advocacy initiatives to improve financing to the social sectors. A broad summary of progress against indicators during the AR period is outlined below.

Government allocation for goods and services is optimised for Social Protection with a 96% allocation. For social protection, increased allocation for 2022 is driven primarily by an increased allocation to Government’s school feeding programme. The LEAP allocation for 2022 remained at 2021 levels, curtailing the programme’s ability to flex to cater for the increasing number of poor households as a result of the pandemic and making the 2022 MTEF target of 350,000 households reached unattainable without additional funding.

The continuing lack of priority given to the goods and services budget within the health budget, particularly at the critical primary healthcare level where the greatest value for money can be achieved, is concerning. In 2020, health expenditure on goods and services in the sector were mostly restricted to clinical services, leaving Government funding of primary healthcare services under resourced and largely dependent on declining donor funds.
Lessons learned
The imbalances within the social sectors budget allocations are likely to deepen existing equity issues in all the sector and limit improvements in outcomes in the medium term. As such, exploiting opportunities for greater integration across sectors in a resource constrained landscape will yield benefit even as the push for granular data on social sectors expenditures continues.

The imminent roll out of family planning within the NHIS benefit package is one such opportunity to expand the reach of social protection to the poor and most vulnerable households (that are primarily female led) leading to improved health outcomes for mothers and newborn, preventing unwanted pregnancies and ultimately alleviating poverty. By working to address teenage pregnancy by increasing access to family planning methods, PBA focus on the NHIS benefits package will work to reduce school dropout rates due to pregnancy. Programmatically this would entail supporting the efficient and national roll out of Family planning services as part of the refreshed NHIS benefits package, with a specific focus on increased enrolment and use of NHIS for family planning services by the poor and vulnerable including LEAP beneficiaries and persons with disabilities and increasing reach to adolescent girls. The PBA programme will leverage FCDO centrally managed programmes address child marriage and sexual violence to tackle the root cause of teenage pregnancy. The social accountability section will focus on advocacy for policy reform to extend family planning services to, adolescent girls in and out of school in addition to monitoring investments towards national expansion of FP services.

Output Title	Improved MoF policies and processes in place to drive better PFM, procurement, human resourcing, VfM /efficiencies, and equity in the social sectors and across government.
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of HMG Partnerships established to support peer to peer learning and driving efficient policies and systems for quality services delivery in the (i)health, (ii)education and (iii) social sectors.	Appraisal conducted to assess HMG capacity to support new partnerships in place and potential areas for new partnerships identified	A / Targeted appraisals were undertaken by sectors to assess interest in UK/Ghana partnerships, followed by work in determining the scope of possible partnerships as appropriate. / Partnership with DHSC for Health Workforce systems strengthening and migration / DHSC £3.5million ODA funding for Health Workforce capacity building and HR management for commenced for FY 2021 results / DHSC NHS Recruitment MoU negotiation in progress. / Steady progress on including Ghana focused interventions in FCDO centrally managed programmes: / FCDO multi-country Strengthening Evidence for Development Initiative (SEDI) pivoted to complete Covid-19 Epidemiological modelling support to Ghana’s MoH. Ghana is focus country for scoping for new FCDO CMP on Epi-modelling. / The central UK Medical Emergency Programme approved the secondment of a public health Specialist to WHO to support Ghana’s Covid-19 and Yellow Fever outbreak vaccination campaigns. / Preliminary scoping discussions with UK’s Department of Education on a teacher workforce partnership revealed limited appetite by UK’s Department of Education to engage in a formal partnership with Ghana at present, but prospects remain for limited support through involving Ghana in a new international teacher recognition scheme.
3.2 Level of MDAs compliance with new/improved systems (PFM, HR, procurement) across social sectors for budgeting/ accounting	No Milestones set for FY2021	TA workplan removed due to reduced budget allocation to PBA
3.3 Existence of a transparent procurement system in education, health and social protection MDAs as an integral part of the PFM system, supported by a regulatory framework that provides value for money and effective controls	No Milestones set for FY2021	TA workplan removed due to reduced budget allocation to PBA

The output overall met expectation. The cancellation of the plans for procurement of TA supplier and development of an agreed workplan has resulted in no movement on establishing new milestones and baseline for indicators 3.2 and 3.3.

The PBA team engaged with UK’s Department of Education to explore partnership opportunities at the behest of Ghana’s Ministry of Education. UK’s DfE is unable to commit to a partnership with Ghana’s MoE at present but made a presentation to the head of the National Teaching Council during the AR period to explain the new requirements and process for international recruitment of Teachers to the UK.

NHS Health workforce, Systems Strengthening Partnerships

UK/Ghana Health Workforce Partnership: FCDO Ghana brokered the inclusion of Ghana in Department of Health and Social Care’s £5million Future International Workforce ODA programme with an award of £3.6million to WHO Ghana, Christian Health Association of Ghana and a consortium led by Tropical Health Education Trust for implementation in Ghana for the fiscal year 2021/22. The Building the Future International Workforce – Ghana project will deliver four outputs in the 2021/2022 fiscal year through the three implementing partners as follows:
i) Training more health workers and up-skilling specialist care nurses (WHO). ii) Training for refugees and host communities with a view to preparing them for skilled health roles (CHAG). Up to twenty refugees who hold the sufficient entry level qualifications will be given three-year scholarships to train and qualify as nurses.
iii) Improved national frameworks and guidance on workforce management, medical practices and training (WHO and THET). Iv) Partnerships between local health systems and NHS institutions that will form the basis for building strength and resilience in the Ghanaian healthcare workforce. THET and Liverpool School of Tropical Medicine

Plans for education migration partnerships led by Health Education England (HEE) did not progress due to funding challenges and limited support for prioritisation of this component by DHSC, the lead HMG department for the NHS Workforce.

FDCO Ghana is a member of the DHSC ODA programme oversight team, monitoring project progress against targets. Assessment of progress at the December 2021 oversight meeting with implementing partners was largely positive with all partners largely on track to meet set targets. Implementing partners were able to shift and in some cases substitute activities between quarters to address the challenge of implementing within the health sector as the pressure on the heath sector increased in November/December due to the onset of the fourth Covid-19 wave in Ghana.

UK Partnerships for Health Systems (UKPHS) Programme: The centrally managed programme ‘Strong Health Partnerships for Stronger Health Systems’ (launched in late 2019) suffered FCDO cuts, resulting in early closure of programme activities in Ghana. The NHS UKPHS implementing consortium, leveraging past engagement in Ghana, were also contracted by DHSC to implement a FY2021 health workforce programme.

FCDO Ghana leveraged the UKPHS programme before closure to carry out scoping with MoH agencies and Health Development Partners for priority areas of joint working to inform a UK/Ghana Health Workforce Partnership framework (as per the recommendation of the 2020 AR) that would be mutually beneficial for both countries and contribute to attainment of Ghana’s health strategic objectives. A draft Partnership framework document was developed to inform FCDO systems strengthening interventions going forward and provides insights into GoG and Health development partners interests for FCDO, in the design of bilateral interventions for strengthening the health workforce and for DHSC as they negotiate a health worker migration partnership with the Government of Ghana.
.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Value for money was achieved during the AR period as follows

For Economy, all engagement were brokered by FCDO Ghana Human Development Pillar team (PBA team), with support from the contracted TA adviser and cross sectoral governance and economic advisers. Furthermore, the PBA was able to leverage the DHSC ODA funding to contribute to GoG’s implementation of health priorities during the AR period.

 For Efficiency, FCDO Ghana leveraged the existing UKPHS and SEDI programmes, the DHSC ODA programme and HD Pillar programme team for attainment of targets on this PBA output and Ghana’s health workforce priorities.

In terms of Effectiveness, Output activities met expectation in strengthening partnership between UK and Ghana, despite the limited success in the education sector. DHSC’s ODA grants is performing well with indications that most targets will be met by programme end in March 2022. The slow pace of implementation of the Epi-modelling support meant that the project output, although useful in assessing impact of Ghana’s Covid-19 response in 2020, was unable to provide clear input into Ghana’s decision-making process for responding to the evolving Covid-19 epidemiological landscape and the emergence of several variants of international concern.

Lessons Learned and Recommendations for the Future

The FCDO PBA team continued to use FCDO Ghana senior management and CMPs and OGD during the AR period to progress work on Partnerships and address bottlenecks to progress.

- UK/Ghana Education Partnership: Within the education sector, despite the current lack of appetite for an international recruitment partnership by the UK, there is sufficient mutual interest and potential for the PBA team to build on the engagement between DfE and MoE over the next few years
- PBA team to continue to engage with UK Department for Education and Ghana’s Ministry of Education with a view to developing a longer-term partnership between UK and Ghana from Sept 2022 / Sept 2023 when all new teachers coming out of colleges of education will have degrees, 1 year induction and be licensed by the National Teaching Council. At this time, DfE will have introduced a new online international teacher recruitment system. MoE/GES will need to work out their policy around advertising this opportunity to teachers in Ghana, managing applications, linking them with UK schools, incentivising them to return.

UK/Ghana Health Workforce Partnership: Engagement with DHSC on the health workforce partnership revealed overlapping areas of interest. During the AR period, a clear delineation of roles and responsibilities between DHSC and FCDO Ghana was agreed with regards the proposed recruitment of Ghanaian Health workers to the NHS. DHSC, as the lead Government department with responsibility for the NHS will take a lead in progressing NHS migration agreements with Ghana. FCDO Ghana will continue to support DHSC in designing ODA programmes that meet Ghana and UK’s shared interest in Ghana in addition to adhering to UK’s commitment to WHO’s code of conduct for ethical recruitment of international healthcare workers as overall responsibility for HMG’s engagement with Ghana lies within the remit of the UK High Commissioner.
As the PBA programme progresses on the path of HMG partnerships with Ghana, there’s a need for a better understanding of the strategic remit of OGDs and alignment with FCDO development agenda and strategic objectives to meaningfully progress UK/Ghana strategic partnerships in the social sectors. Close engagement with FCDO global departments and other pillars within FCDO Ghana is required in addition to Senior Country leadership to address interventions that have a bearing on global policy issues to progress work at pace in establishing UK/Government partnerships.

Output Title		Increased capacity of Civil Society Organisations (CSOs) to effectively hold Government to account for equitable and effective delivery of quality social sector services.
Output number:			4	Output Score:		A
Impact weighting (%):			25%	Weighting revised since last AR?		Yes, upwards from 20%
Indicator(s)	Milestone(s) for this review				Progress
Indicator 4.1; Level of readiness of CSOs and relevance of interventions to TA and HMG partnerships	Priorities of CSOs established, project designed and commenced.				Met - STAR Ghana Foundation (SGF) in consultation with FCDO approved proposals from five CSOs to promote accountability and responsiveness of government to citizens around Covid-19 responses and mitigation strategies. The second phase of the Centre for Democratic Development’s (CDD) project is assessing the outcome of the medium-term interventions (2018-2021) implemented at the basic level aimed at addressing challenges with school management, high repetition rates, out-of-school children, low completion rates, system accountability challenges, teacher deployment and pupil-to-teacher ratio, shortage of classrooms, regional disparities in quality and access, water and sanitation, among others. The scopes of these projects are aligned with the priorities of the PBA programme for the period under review.
Indicator 4:2; / Number and percentage of quality strategic partnerships with the social sector MDAs	At least 3 strategic partnerships established with MDAs and 25 % are aware of systemic challenges and commits to address them.				Met- CDD, in collaboration with Africa Education Watch (AEW) and SEND-Ghana held strategic engagements with Joint Parliamentary Committee on Women and Labour, Employment and Social Welfare Committees and the Education Committee between April and May 2021 to increase their knowledge on systemic challenges in the education and social protection sectors. / SGF has established partnership with Parliament to support the leadership of Parliament and three parliamentary select-committees (Health, Education and Gender and Social protection) to improve oversight over the provision of public goods and services within the education, health and social protection sectors. SGF’s grant partners are also collaborating with relevant ministries including Ministry of Gender, Children and Social Protection (MGC&SP), Ministry of Education (MoE) and Ministry of Health (MoH). These ministries have participated in convenings and other key stakeholder engagements in support to addressing key salient issues such as girls’ re-entry to school and access to quality health services.
Indicator 4:3; / Number of policies, practices and systems that have been changed as a result of the CSOs interventions.	1 (National) & 1 (Local) - influencing strategy gaining traction)				1(National)- Met. Africa Education Watch (AEW) (SGF’s grantee) produced a Policy paper on Ghana Education Service’s (GES) ‘Back-to-school’ guidelines and held policy engagements with stakeholders including the GES, MoE and Parliament. The Ministries are currently working with the National Planning Development Commission (NDPC) to improve implementation of the Re-entry Policy for Student Mothers and Pregnant School Girls. They have committed to examine proposals raised by AEW, on financial support for student mothers and pregnant girls to re-enter school. / Based on evidence produced by the Christian Health Association of Ghana (CHAG) under this programme, the MoH and the National Commodities Committee have revised the procedure and guidelines for government’s requisition, distribution and monitoring of COVID-19 usable products and commodities. / 1 (Local). Under the Baobab Initiative for Social Accountability (BISA) on Government’s response to COVID-19 led by the Ghana Developing Communities Association (GDCA), associations of 210 small-scale enterprises (SMEs) in northern Ghana have been mobilized to demand accountability around government’s Corona Virus Alleviation Programme (CAP). The initiative has received response from the Ghana Employment Agency (GEA). The GEA has responded to the association’s demand by providing the requested information. The interest of these associations provides a strong basis for citizen-led compelling advocacy on the findings of the assessment.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 4.1: STAR-Ghana Foundation in collaboration with FCDO approved proposals from five CSOs to implement projects to improve accountability and responsiveness of government to citizens around COVID-19 mitigation measures, particularly in the health and education sectors. The outcomes of these proposals are as summarised in Table 1 below.

Table 1: CSO Grant Partners and their outcomes of their projects
Name of CSO	Project Outcome
SEND-Ghana	Strengthened civil society and government dialogues for inclusive access to public goods and services- health, and social protection sectors around Covid-19 response and recovery plans by 31st March 2022.
Centre for Social Policy Studies (CSPS)	A synthesised report consolidating CSOs report on COVID-19 (under the Phase 1 of the STAR-Ghana programme). This report will describe, categorise, and analyse new initiatives and existing programmes that were deployed in response to COVID-19 by government, in the areas of education, health and social protection. The report would complement existing evidence available to CSOs for improved advocacy.
Africa Education Watch	Increased re-entry and enrolment of teenage mothers and out of schoolgirls into basic and secondary schools.
Christian Health Association of Ghana (CHAG)	Strengthened health care delivery through the effective monitoring of COVID-19 commodities allocation, distribution, and receipt at the level of use and advocacy.
Ghana Developing Communities Association (GDCA)	Increased support to citizens to assess government accountability in its response to COVID-19 for Micro Small Medium Enterprises (MSMEs)in Northern Ghana.

Within the period under review, the five CSOs set up their projects and laid the foundations for effective attainment of project outcomes. For instance, the Africa Education Watch (AEW) produced a Policy paper on Ghana Education Service’s (GES) ‘Back-to-school’ guidelines for advocacy engagement with Parliament and relevant ministries. The paper has been shared at both national and regional stakeholder dialogues to elicit government responsiveness. Key recommendations include:

- Ensuring consistency in the delivery of sexual reproductive information (synergy between information given by Ghana Health Service (GHS) and GES.
- Providing economic support for girls. This may include expanding the scope of the current safety net programmes such as the Livelihood Empowerment Against Poverty (LEAP) cash transfer, School Feeding programmes, etc. to include adolescent pregnant girls and teen mothers.
The second phase of CDD’s project was agreed in December 2021, building on the successful conclusion of the first phase of the PBA CDD project that concluded in June 2021. This project will use the underspend within the PBA programme to assess the Education Strategic Plan 2018-2021 commitments towards improving education outcomes and medium-term interventions at the basic level. Evidence gathering has commenced and a preliminary briefing of findings has been shared with duty bearers to promote uptake of empirical evidence in the education sector.

Indicator 4.2: CDD-Ghana held sessions with the Joint Parliamentary Committee on Women and Labour, Employment and Social Welfare Committees and the Education Committee between April and May 2021. The two sessions were organized in partnership with SEND-Ghana and Africa Education Watch to promote the relevance and sustainability of government policies and programmes through engagement on evidence and issues compiled by CDD across the key sectors health, education, social protection. CDD also shared a report of their analysis of the manifestos of political parties (especially on Government flagship programmes) with the aim of improving government policy actors’ access to empirical data to improve decision making; and encourage the active participation, inclusion and involvement of citizens in government policy formulation and implementation. These engagements enhanced the legislative and oversight role of Parliament over the social sectors.

STAR Ghana Foundation (SGF) has established partnership with the leadership of parliament and three parliamentary-select committees (Health, Education and Social Protection) to support build their capacity to improve parliament’s oversight over the provision of health, education and social protection goods and services. The Speaker of Parliament was also supported to hold a Forum in Kumasi to improve the interface between Parliament and citizens for transparent and accountable governance around the provision of public goods and services. The meeting which had the Otumfuo Osei-Tutu, the Asantehene as guest of honour also explored among others the role and challenges faced by Parliament in executing its mandate. https://www.myjoyonline.com/i-did-not-get-the-real-picture-of-the-weakness-of-our-parliament-until-i-became-speaker-alban-bagbin/. The Speaker of Parliament committed to engage the executive to revamp the constitutional amendments review processes to address fundamental issues reinforcing weak governance and accountability of public goods and services. The Speaker would mobilise support from its partners to introduce dialogue series on the constitutional review process.

STAR Ghana Foundation has also obtained commitments from the Ghana Education Service, three Regional Coordinating Councils (RCCs) and five metropolitan, municipal and district assemblies (MMDAs) to collaborate with the five CSO partners for the achievement of project objectives. Similarly, STAR’s grant partners are also collaborating with relevant ministries such as the MoE, MoH and MGC&SP. including Ministry of Gender, Children and Social Protection, Ministry of Education and Ministry of Health. These ministries have participated in convenings and other key stakeholder engagements in support to addressing key salient issues.

At the national level, the partner CSOs strengthened their relationships with the ministries responsible for education, health and social protection. They participated in dialogues with the partner CSOs and committed to address issues raised. For instance, the MoE and GES participated in the review of the re-entry policies and jointly proposed strategies for strengthening its implementation. The Girl-Child Education Unit of the Ghana Education Service (GES) was among the expert panel that reviewed the AEW’s report on student mothers and pregnant girls’ re-entry. The Ministry of Health was engaged on the health component of the synthesised report on Covid-19 and Social Policy Interventions prepared by SEND-Ghana. These collaborations and engagements are aimed at promoting the use of evidence by these Ministries, Departments and Agencies (MDAs) in policy making and implementation.

Indicator 4.3- The CSOs advocacy activities have contributed to the following policy changes;

- The Ministry of Health and the National Commodities Committee have revised the procedure and guidelines for government’s requisition, distribution and monitoring of COVID-19 usable products and commodities. The review was informed by evidence gathered by CHAG.
- The Ministries of Education and Gender, Children and Social Protection are currently working with the National Planning Development Commission (NDPC) to improve implementation of the Re-entry Policy for Student Mothers and Pregnant School Girls. They have also committed to examine proposals raised by AEW, on financial support for student mothers and pregnant girls to re-enter school.
- The Ghana Employment Agency (GEA) has responded to the associations of SMEs in Northern Ghana’s demand by providing the requested information. The interest of these associations provides a strong basis for citizen-led compelling advocacy on the findings of the assessment of the Corona Virus Alleviation Programme (CAP). This is to enhance transparency and accountability in the implementation of the COVID-19 social protection schemes for SMEs.
- The Baobab Initiative for Social Accountability (BISA) project has been launched to serve as an interface forum between the SME associations and duty bearers, providing a foundation for long-term engagements.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Economy: The procurement policies of both CDD and SGF provide guidance on how to procure the highest quality of desired goods and services at the best possible value. Payment for goods and services were at negotiated rates.

Efficiency: CDD included analysis on the extractive sector, examining allocations from oil revenues to the social sectors at no cost to PBA. This was achieved through partnership with the Natural Resource Governance Institute (NRGI). CDD’s collaboration with the National Development Planning Commission (NDPC) provided the platform for broadening the discourse on funding of social sectors across government departments, increasing the likelihood of evidence uptake at a national level and usage to inform national policies and planning, again at no extra cost.

Effectiveness: CDD’s engagement with the National Development Planning Commission (NDPC) on the issue table was in time for the commencement of the preparation of the 2022-2027 Medium Term Development Plan and hence promoted the use of evidence by the NDPC. Again, CDD’s partnership with Parliament enhanced evidenced debate on the floor of parliament. About 92 % of STAR-Ghana's grant partners were assessed to be meeting their respective milestones and actively engaging duty bearers on selected salient issues such as girls’ re-entry and management of the grants to small and medium enterprises under the Corona Virus Alleviation Programme.

The AR assessed the social accountability delivery routes, i.e., through (i) CDD and (ii) STAR-Ghana Foundation and noted low value for money for PBA by delivering through STAR compared to CDD. While STAR-Ghana brings advantages such as its convening power (e.g., to bring high level government officials to the table to dialogue on relevant issues) and the ability to facilitate linkages between national and local level CSOs, it lacks the capacity to follow through to the end of the advocacy process.

FCDO’s engagement with STAR-Ghana goes beyond PBA and therefore may require a different approach to future partnership with the organisation. For instance, a significant proportion of the funding to STAR-Ghana during the 2021/2022 FY was spent on institutional/operating costs as opposed to delivering to set PBA objectives. In contrast, funding to CDD primarily focused on delivering PBA objectives. CDD like STAR, has the credibility to convene high level dialogues. However, achieving sustained impact of CDD’s intervention in the health and social protection sectors would require CDD to invest in strengthening partnership with health and social protection CSOs (similar to its partnership during this AR review period with Africa Education Watch in the education sector). Based on this assessment, a consortium of CSOs with expertise in the relevant sectors (health, education and social protection) would deliver more value for money for PBA. This is also dependent on CSOs being motivated and agreeable to consortium type arrangements for action.

Equity: All five CSOs funded by STAR-Ghana have mainstreamed gender into their projects. This include ensuring that government policies reach the most vulnerable in society such as women and Persons with Disabilities (PWDs). For instance, AEW project seeks to promote the education rights of vulnerable students in COVID-19 and post-pandemic era. Specifically, the project’s overall outcome is to see an increased re-entry and enrolment of teenage mothers and out of schoolgirls into basic and secondary schools. About 60 % (337 out of 561) of beneficiaries reached by STAR-Ghana's grant partners were women.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to the targets and indicators.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lesson Learned
- The partnerships with parliament, ministries, departments and agencies (MDAs) enhanced learning and most importantly contributed to aggregating the voice and influence of civil society and eventual uptake of evidence shared. CDD reported that the political parties were very cooperative due the collaborating approach taken by the project team.
- Data is a powerful tool for mobilising the media around important national issues and sustaining interest. CDD found that partnership with the media helped to improve the quality of information shared by the partner media organisations. Access to timely and well packaged historical and trend data is critical in strengthening the oversight role of the media and civil society.
- Well-tailored information has the potential to stimulate responsiveness from duty bearers. CDD found the targeted engagements with the Parliamentary-select committees were more effective.
Recommendations

- With a three-year Spending Review agreed, FCDO should aim to sign at least three-year Accountable Grant with the CSOs to enable them to plan their interventions over a longer time. This will help improve delivery and effectiveness.
- FCDO should as soon as financial allocations are received make a decision on the preferred delivery route for the social accountability component of PBA along the lines assessed in Output 4’s value for money assessment.

Output Title	Sustained service delivery of essential quality services and communication activities including for Covid-19.
Output number:		5	Output Score:	A+
Impact weighting (%):		50%	Weighting revised since last AR?	Yes (from 45%)

Indicator(s)	Milestone(s) for this review	Progress
5.1 Percentage of population that know about Covid-19 prevention protocols in 40 CHAG districts	70% of survey participants from communities in the 40 CRIB districts know basic Covid-19 prevention protocols (hand hygiene, social distancing and mask wearing.	Achieved. / Survey revealed 78.5% of community respondents were knowledgeable on Covid-19 prevention and mitigation protocols
5.2 Number of facilities with functional Quality Improvement teams	40	Exceeded Expectation: 99 facilities have Quality Improvement Teams operating
5.3 Number of health personnel (private, CHAG and GHS) trained in Covid-19 management in 40 districts with CHAG district hospitals	2107 (disaggregated by health facility type (CHAG, MoH, Private)	Exceeded Expectation: / 3,404 health workers trained (F: 61.5%, M:38.5%) / Type of Health facility / GHS: 1,248 / CHAG: 2,046 / Private:110

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, programme progress on Output 5 exceeded expectations when measured against set milestone during the AR period. Additional notable achievements include the establishment of three critical care units in three regions to address the lack of Covid-19 critical care facilities in strategic locations with limited MoH capacity in this regard, establishment of six Covid-19 diagnostic labs, 37 Covid-19 isolation centres refitted to standard, and intensified support to Ghana’s Covid-19 vaccination campaign in rural communities. The increased high profile of CHAG’s Covid-19 activities has elevated the standing of the participating health facilities in the 40 districts with MoH with CHAG an active participant of the Covid-19 technical coordinating committee. Strong collaboration between CHAG, regional and district health authorities and community leaders were pivotal in expanding quality Covid-19 services and ensuring uptake of essential services during the AR period.

To address gaps in the national Covid-19 surveillance strategy, FCDO signed an 18 months £999,000 cooperative agreement with the West African Centre for Cell Biology and Infectious Pathogens (WACCBIP) in October 2021 to expand Covid-19 sero-prevalence and genome sequencing activities nationally, particularly to border towns. The WACCBIP project activities will inform Ghana’s response to the evolving Covid-19 pandemic in addition to building the capacity of government and CHAG laboratories and personnel to carry out high quality surveillance activities for Covid-19 and future disease outbreaks.

CRIB project activities during the AR Period

Community knowledge of Covid-19 Prevention Measures: During the AR period, CHAG undertook an additional small survey on vaccine hesitance in the 40 implementing districts to gain insights into reasons for slow Covid-19 vaccines uptake. Two hundred and forty-eight (248) residents were sampled from the 40 districts for the survey. From the survey, awareness of Covid-19 vaccination was high at 89.5%. Forty-nine-point six percent (49.6%) of the respondents indicated however that they were unwilling to take the Covid-19 vaccination. Gender, educational status, co-morbidities were factors that influenced Covid-19 vaccination acceptance (P<0.05). Females were more likely to take the Covid-19 vaccine compared to males. Although the sample size was small, the results tallied with surveys carried out by Ghana Health Services and other development partners at the start of the fourth Covid-19 wave. Subsequent to the survey, vaccine hesitancy is increasing in pockets of Ghana, most notably in the Eastern and Volta regions, driven by low-risk perception from severe Covid-19, vaccine misinformation warning of grave religious and infertility consequences for persons taking vaccines. The CRIB project has intensified Covid-19 communications campaign in five regions, working with GHS and communities to tackle vaccine hesitancy.

Functional Quality Improvement Teams: The successful establishment of 99 QI teams will be instrumental in ensuring high infection prevention and control standards are maintained in health facilities, PPEs are available and used appropriately, and clear pathways to accessing health services safely are established. This is especially important considering high Covid-19 health worker infections, that over the AR period, periodically shut down elective surgery and outpatient’s department in health facilities nationally, including some CHAG health facilities and a major teaching hospital in Accra. An organizational performance assessment tool score average of 3.5 against a target of 3 out of five was achieved by the health facilities, indicating overall a satisfactory level of health care delivery by the facilities.

Training of Health workers: 3,404 health workers were successfully trained, primarily on Covid-19 response interventions, including Covid-19 laboratory diagnosis, case management and behaviour change communications.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

CHAG is adhering to FCDO’s VfM guidelines in implementing activities under output 5.3. The costs of all activities in the output are in line with the market norms. In terms of Economy: Venues for trainings were selected based on the best value for venue costs, including quality of refreshments and other provisions for training participants.
Efficiency: Experienced Trainers from various departments of the GHS were used to conduct the Training of Trainers. A small number of GHS Trainers were also used as lead trainers for the downstream trainings, providing a quality assurance function for the downstream training initiative.
Effectiveness: CHAG was able to leverage to leverage the CRIB project diagnostic activities to expand Covid-19 diagnostic services to two additional remote districts with Ministry of Health funds during the AR period.

Participants for both the Training of Trainers and the downstream trainings were sequestered from their normal workstations to ensure that participants were fully focused on training activities. For each training session, the host district was one of the beneficiary districts, facilitating effective practice simulation exercises.

Gender and Equity considerations continue to be strong implementation of the CRIB project in terms of health workers trained. All 40 districts selected for the CRIB project are underserved with limited access to public sector clinics, most are rural and in poor and hard to reach communities. The expansion of diagnostic services in 7 CRIB districts has improved access to timely Covid-19 diagnosis in regions, ensuring that these contribute to effective decision making and management of Covid-19 in districts. Training was provided to the Association of Persons with Disabilities on Covid-19 safety measures including the benefits of vaccination to strengthen Covid-19 prevention communications in in three regions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The evolving Covid-19 pandemic and multiple waves experienced during the AR period has further strained health services but continue to provide opportunities for innovation in addressing the pandemic. Covid-19 response interventions, in particular, Covid-19 vaccination, hampered by global supply chain issues during this AR period, has lagged behind expectation with approximately 11% of the Ghanaian population fully vaccinated (February 2022) and at 22% of the 20million person’s national target. Vaccine coverage is lowest in underserved regions, outside of Accra, hampered by persistent vaccine misinformation on side effects of Covid-19 vaccination. Continued intensive community level communications campaign, led by community leaders and health stakeholders is required to effectively address vaccine hesitancy and sustain the high Covid-19 vaccination rates observed in December and early February to meet the target the national target of 20million persons vaccinated by July 2022.

Lessons learned this year and recommendations for the year ahead
Leadership with communities - close working with the right community leaders such as chiefs and pastors and traditional authorities has been critical in supporting both improved co-ordination of information at a local level and service delivery.

Importance of co-ordination mechanism - the platforms established for coordination have been critical and it will be important to consider ways to maintain and build on this for the sustainability of service delivery.

Recommendations

FCDO to agree with CHAG several quality indicators for Covid-19 and essential services in facilities with functioning QI teams to monitor the anticipated downward trend in Covid-19 indicators in participating facilities from April 2022.

PBA team to propose for Development Director’s approval, a costed extension of the CRIB project to 31st December 2022 (from current end date of June 2022) to enable a responsible exit by concluding plans for inclusion of CRIB project activities into ongoing national Covid-19 programmes as appropriate. The newly formed Ghana GAVI/UN Covid-19 vaccine delivery partnership with its one plan, one budget and joint coordination structure approach is one such opportunity to consolidate Covid-19 response interventions nationally and ensure funding to high performing interventions to meet national and global Covid-19 vaccination targets.

D: RISK

Overview of risk management

The overall programme risk continues to be assessed as major (previous annual review also noted a major risk rating). The key risks evolve around the covid 19 pandemic, budget reprioritisation and compliance with FCDO financing rules. The major risk is mainly the result of the covid 19 disease and its effects on economic, social and health factors in Ghana and the UK (and the world broadly). With the third and fourth waves of the covid 19 disease, economies including Ghana continue to focus on interventions that would mitigate the overall effects of the disease particularly on the health of populations and on economies. Concerns remain about the seeming growth of Ghana’s economy albeit at a reduced rate with introduction of taxes and levies that continue to put a strain on incomes/livelihoods. Increasing commitments to debt servicing and a lower-than-expected increase in spend on the social sectors by government (despite increasing need), remains a cause for worry.

The Covid 19 pandemic for the second year running, is included as one of the key risks identified for the PBA programme. This is in the addition to those identified in the business case around reduction in spend on the social sectors and the ineffectiveness of technical assistance. However, during the year under review where the programme anticipated procuring TA support in line with PBA’s mandate to promote systems strengthening and efficiency, cuts to the ODA budget meant a halt in the procurement process. This was however mitigated by securing a temporary Health TA to continue to support PBA health interventions including Covid-19 spend through multilateral organisations and more broadly HMG’s health interventions in Ghana. This is expected to help lay the foundation for future TA provided by a mainstream supplier should the decision be made to proceed with TA procurement.

The programme funding to the SGF started this financial year following the ODA cuts and closure of the main STAR Ghana II programme. Despite significant delays due to the budget prioritisation exercise and agreeing with STAR Ghana a suitable proposal for delivery, the SGF worked quickly and quite proactively with FCDO to pick up the pace with delivery once the accountable grant agreement was signed. Given that the SGF is fairly new as an organisation, FCDO will be carrying out an expenditure verification exercise as a fiduciary risk management measure to ensure that the SGF has the requisite robust systems to continue to manage our funds. This was a recommendation from their due diligence assessment that is being taken forward under the PBA programme. The contracting of credible CSOs such as CHAG, CDD (for a second phase post-manifesto project) and a Health TA to support the national Covid-19 response continued under this period and contributed to addressing fiduciary risks through Covid-19 programming. To date, all implementing partners have complied with FCDO financing rules and are monitored through biweekly or monthly update meetings, quarterly reporting, and field visits where possible and rules allow.

A due diligence assessment (DDA) refresh was completed for CHAG in line with FCDO guidelines and no adverse findings were identified. The DDA refresh gave the Department of Health and Social Care (DHSC) the assurance to enter into another project agreement with CHAG as it proved to have the required systems and structures to manage (additional) funding. CHAG and other CSO partners (CDD and SGF) implemented actions highlighted in the DDAs undertaken. FCDO continues to monitor the respective projects for any emerging risks.

A new DDA was also conducted on the West African Centre for Cell Biology of Infectious Pathogens (WACCBIP) ahead of signing the accountable grant for genome sequencing work. Although the DDA found WACCBIP’s systems adequately robust to manage FCDO funds, recommendations from the DDA will be closely monitored to ensure that our funds are safeguarded. Risks identified included: delays in project implementation due to slow procurement of supplies and equipment for the project due to ongoing challenges with global supply chains and concerns around the heavily bureaucratic University of Ghana administrative system that WACCBIP would need to interface with. With regards safeguarding, WACCBIP had sound safeguarding policies however uncertainty on the robustness of implementation of the policies resulted in FCDO recommendations to strengthen enforcement to FCDO standards.

Although PBA’s focus is on systems strengthening and improving efficiency, the programme has seen some level of direct service delivery with the pivot to supporting interventions around covid 19. This increases the risks of fraud (particularly with procurements) and safeguarding primarily via our funding through CHAG which involves direct health provision. With partners updating their policies around SEAH (sexual exploitation, abuse and harassment), FCDO continues to monitor awareness and compliance with their own policies around the subject. The PBA teams regular engagement with partners (fortnightly for CHAG and monthly for WACCBIP and SFG) and project reports serve as the primary means of monitoring risks. The PBA team supplement these monitoring activities with periodic field visits.

FCDO has commissioned a full fiduciary risk assessment of Ghana’s health and education sectors to provide insight into the areas of risk that FCDO should focus on. This assignment should be completed by March 2022.

Overall, the programme continues to operate within FCDO Ghana’s risk appetite with continued close monitoring and updates to the risk profile on AMP.

Recommendation
FCDO to closely keep track of partner DDAs and monitor recommendations particularly around fiduciary risks and safeguarding throughout the coming year.

FCDO to review the need for TA support as envisaged in the business case, considering the risks to achievement of programme objectives to determine its relevance or otherwise as the programme progresses and plans next steps.

Update on Partnership Principles
The PBA programme, although aligned to GoG priorities in the social sectors, does not provide direct funds through Government systems. The partnership principles of poverty reduction and the sustainable development goals, management of public finances, tackling concerns about human rights abuses and corruption, and improving domestic accountability are regularly assessed by FCDO, and the last update was done in January 2021.

Covid-19 has increased the risk of reversal of some of the gains made towards poverty reduction and the SDGs. The health sector and education sector however has shown remarkable resilience in the face of Covid 19. Health outcomes have not plummeted and, in general, use of services is back up at pre-Covid 19 levels, a notable exception being decreased uptake of family planning services and a rise in teenage pregnancy. In education, 98% of school aged children returned to school according to the Ministry of Education and enrolment numbers have increased, spurred by an intensive back to school campaign. Remote education options have increased with TV learning channels continuing and more schools are accessing online digital platforms and resources. Despite the increase in pregnancy, there is evidence that the school re-entry policy for young mothers is helping to reduce the link between pregnancy and dropping out of school.

In a context of extreme fiscal constraint, poverty reduction expenditure (especially for health and Social Protection) continues to be at risk of stagnating or falling, driving poor people even deeper into poverty whilst creating new categories of poor and vulnerable struggling to meet their basic needs. Stronger and sustained GoG commitment to increasing the share of resources allocated and expended on the social sectors and the leave no one behind agenda is required to place progress on the SDGs on a firm footing and progress the Ghana Beyond Aid ambition.

It is assessed that the Government of Ghana is broadly committed to the UK’s four Partnership Principles. The overall risk is assessed as moderate. For the PBA programme, the risk is low since it does not involve financial assistance.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme Delivery and Commercial Performance
 The continued impact of the Covid-19 pandemic and the ODA budget cuts meant significant delays, budget reductions and continuation of the agreed first year reprioritisation of planned programme activities under the PBA programme. The late confirmation of budgetary allocations following the ODA cuts led to delays with fund disbursements and the start of some workstreams such as the SGF and WACCBIP projects. The FCDO programme management team, working with implementing partners, was however able to respond appropriately to the identified gaps to deliver activities aligned to programme outputs and outcomes through the following agreements and contracts.

CHAG
CHAG continued to deliver support to the Covid-19 public health response and essential health services in the 40 districts under the CRIB project. Furthermore, CHAG received additional funds from PBA through STAR Ghana to monitor uptake of family planning services. They are also being funded directly by the DHSC through a separate accountable grant agreement to train refugees for skilled health roles. Quarterly reporting and meetings were consistent, and effective delivery against set targets was observed during field visits. Close monitoring of CHAG’s interventions and finances by the PBA team should continue in order to avoid duplication of activities and ensure continued performance against the targets set by the various projects.

CDD-Ghana
Due to delays with the start of the first CDD project during the previous AR period as a result of the then emerging Covid-19 pandemic, a no-cost extension was approved from the December 2020 end date to March 2021 and subsequently to June 2021 to ensure responsible project closeout. Following the successful delivery of the first project, FCDO signed an accountable grant with CDD-Ghana to monitor the delivery of a post manifesto project around the Education sector plan from 2018 – 2030. This second phase covers a four-month period of delivery from December 2021 to March 2022.

STAR Ghana Foundation
PBA’s support to the SGF started through an accountable grant agreement which covers the period 1st October 2021 to 30th September 2022 to implement projects aimed at improving accountability and responsiveness of government to citizens around Covid-19 mitigation measures, particularly in the health and education sectors. Quarterly update meetings have been held as planned and reports (narrative/financial) received on time. The PBA programme is also serving as a conduit for a one-year CSSF funding to SGF through the existing AG for a small project aimed at promoting peace and stability in northern Ghana. This is a collaborative effort between the HD team (we manage the funding arrangement) and the Upstream Threats team (manages the technical reviews). Going forward, there is a need to clearly separate the different objectives of FCDO Ghana’s projects with SGF to ensure effective programme management accountability, value for money and impact.

WACCBIP
An extensive DDA was conducted for WACCBIP ahead of signing our accountable grant agreement for WACCBIP to undertake comprehensive national surveillance for Covid-19/genome sequencing and build laboratory capacity for sustainable disease control in Ghana. The DDA was completed in September 2021 and the AG signed in October 2021 for the 18 months project ending March 2023. An inception meeting was held and as at the time of this review the first quarter milestones achieved, aided by proactive planning by WACCBIP ahead of AG signing.

Interim TA arrangement
Contracting of the technical assistance suppliers has been halted as outlined in the Output 2 review. To ensure continuity, interim arrangements have been put in place through two contracts:

- In the absence of FCDO’s/PBA’s planned national level technical assistance supplier, a short-term technical expert in Ghana’s health sector (full-time) was contracted to support the UK government's programmes in the health and social sectors and ensure that these are appropriately responding to, and incorporating lessons learned from Covid-19 into building resilience more concretely into GoG systems; and implementing high quality impactful UK interventions in the health sector. The contract is for a year from October 2021 to September 2022.
- A team of consultants has also been contracted to carry out an extensive fiduciary risk assessment (FRA) of the health and education sectors in Ghana. The FRAs will help FCDO to assess and monitor partner government commitment to improving Public Financial Management (PFM) (including fiscal transparency), strengthening domestic financial accountability, and the fight against corruption.
DHSC
FCDO Health Adviser and Team Leader continue to support the DHSC on the UK Health Partnerships/NHS MoU activities. It was originally envisaged that DHSC would channel funds to FCDO Ghana for ODA-funded activities. However, the DHSC have retained the funds and signed direct agreements with various delivery partners (WHO, CHAG and THET) to deliver various outcomes. FCDO Ghana continues to play a pivotal brokerage role with the MoH in the negotiation of the NHS migration MoU. This has minimised the direct programme management inputs and freed more time for the team to engage in strategic programme oversight activities

The Ghana UK Health Workforce Partnership Framework was drafted during the period under review in consultation with key stakeholders within Ghana’s health sector. The framework document seeks to guide HMG investments (bilateral and through other Government departments) in Ghana’s health workforce for the next ten years. However, the initial proposal to ratify this framework agreement has been set aside to allow DSHC greater autonomy to negotiate a workforce migration partnership with Ghana’s Ministry of health that is in keeping with the objectives of DHSC’s international recruitment policies.

FCDO maintained good working relationships with implementing partners, other Development Partners (DPs), government and other stakeholders during the AR reporting period; contributing to progress made to date. Senior level participation of key stakeholders at the launch of CHAG’s Covid-19 testing programme and commissioning of two of the three FCDO funded High Dependency Units (HDUs) by the UK’s High Commissioner to Ghana and Development Director, illustrates FCDO’s collaborative working with Implementing Partners.

Programme Financial Performance

The BC approved budget is £25million, out of which £22.2 million was programmed in the BC. The programme received an overall allocation of £3million for the financial year 2021/22 following ODA cuts and reprioritisation of country budgets. This was therefore split across the components to cater for critical areas of need. A breakdown of the budget allocation for the period under review is detailed below in Table 1.

Table 1: Revised FY 21/22 PBA Detailed Budget against Expenditure
PBA Programme Component	Budget for FY21/22 £	Spend to date for FY21/22 £	Remaining balance for FY21/22 £	Comment
103: Technical Support	0	0	0	Funds were initially held for the proposed demographic dividend index project scheduled to run from January – March 2022 but project was unable to commence within the set period due to delays in finalising plans with government counterparts.
105: M&E/Health TA Expert	33,297.35	33,297.35	0	Contract signed in October 2021 and payment made on quarterly basis, first payment for October – December 2021. January to March payment also on track.
106: FRA/ASP/Impact Reviews	43,346	-	43,346	Allocated for health FRA and funds to be fully expended by March 2022.
107: AG to CHAG	1,671,178.44	1,526,694.44	144,484	Includes a variance of £377k identified within the programme following profiling has been reallocated to CHAG for vaccine work. Minimal underspend is expected by March 2022.
109: AG to SGF	403,076.59	268,530	134,546.59	Remaining amount to be expended by March 2022 with likelihood of little underspend given the current pace of implementation.
110: AG to WACCBIP	500,000	92,530	407,470	First disbursement of £92k made. Remaining amount to be expended by March 2022.
111: UKPHS/THET	35,000	35,000		Payment made centrally to UKPHS for THET-led health partnership framework
112: AG with CDD for phase 2 – post manifesto project	78,303	68,678.50	9,624.50	First tranche of £68k disbursed in December 2021 and balance expected to be fully expended by end of March 2022.
Total FY 2021/22	2,829,201.38	2,089,476.88	739,724.50	Minimal overall underspend anticipated

The main cost drivers of the programme during the AR period remain (partner) project staff costs including short-term consultancy fees/expenses, training and workshop expenses for health workers and mass media activities. The VfM strategy/metric which should have been developed by the main TA supplier is yet to be done given the suspension of procurement (of the TA). Nonetheless, VfM is monitored against the standard 4 Es (effectiveness, efficiency, economy and equity) through quarterly progress reporting and budget reviews by partners.

Overall, the quality of programme financial management has been good with particular attention to fiduciary risks associated mainly with the accountable grant agreements but could be strengthened to improve forecast accuracy and expenditure reporting. Implementing partners have submitted narrative and financial reports on time at an acceptable quality. Forecasts have been mostly accurate with variations due mainly to cost savings from exchange rate fluctuations and late start of some projects with regards to SGF and WACCBIP. A programme delivery plan that serves as one of the monitoring and delivery tools has been developed and is routinely updated. A delivery chain for the programme has been developed for the active components of the PBA programme on the AMP system. This will be updated as and when suppliers are contracted, and partnerships are formalised.

The assets procured by implementing partners (mostly laptop computers and health equipment) are listed in respective partner asset registers maintained by both FCDO and related partners. Asset Registers have been updated by CHAG, SGF and CDD-Ghana. Asset checks conducted by the FCDO team in the early part of the review period on the two projects – CHAG and CDD have reported no adverse findings. The main recommendation was for CDD-Ghana to brand the project laptops with the UKaid logo. All assets were in good condition for both projects. No significant issue has been identified through review of quarterly financial and narrative reports. The expenditure verification (EV) conducted on CDD-Ghana’s project revealed no major findings as CDD-Ghana had sufficient appropriate evidence to support transactions reviewed.

Recommendations

- FCDO to conduct asset verification on programme funded assets with CDD-Ghana, CHAG, WACCBIP and SGF by June 2022.
- FCDO to carry out expenditure verification (EV) on SGF by March 2022; and commission overall programme audit to coincide with CHAG’s closeout audit.
Monitoring activities throughout the review period

During the AR period, regular meetings were held with CHAG; weekly meetings with the Health TA and quarterly update meetings with SGF provided opportunities for monitoring of project progress and timely resolution to issues as they arose. FCDO Advisers and Health TA participated in meetings and events and supported implementing partners, providing useful inputs and contributions. These included the launch of CHAG’s Covid-19 testing programme and commissioning of two FCDO-funded High Dependency Units (HDUs) in Akwatia (Eastern region) and Berekum (Bono region); Joint Parliamentary Committee on Women and Labour; Employment and Social Welfare Committees and the Education Committee; and SGF project inception meeting.

Field visits by FCDO included visits to selected CHAG project sites such as St. Dominic Hospital in Akwatia on two occasions, the Holy Family Hospital in Berekum, St. Mary’s Hospital, Hwidiem, Fetentaa Refugee camp where CHAG’s work with refugees and DHSC was seen. The field visit equally enabled the FCDO team to see other UK-funded interventions including work on HIV/AIDS, TB, infant vaccination, and malaria. Through all the visits, it was evident that CHAG was delivering in the communities and particularly supporting the national Covid-19 response efforts in addition to providing essential health services in these remote areas. Community level engagement was clear from the interactions with various traditional rulers.

A team of three staff from the GHS Public Health Unit also visited each of the participating (CRIB) District hospitals to monitor their data reporting. CHAG’s monitoring team also visited all the participating facilities to provide onsite facilitation support where necessary and address teething challenges on the ground.

During the period under review, SGF conducted a compliance and monitoring visit to its Grant Partners identified as having medium to high-risk ratings. This offered the Foundation the opportunity to provide capacity-building support to such Partners and to re-assess the extent of compliance to due diligence recommendations.

Progress against recommendations from the 2020 AR period

2020 Recommendations	Progress (date) six months after review
OUTPUT 1
COVID-19 demonstrates more clearly than ever the links between the social sectors and the need for the Ministries to work together. For example, vaccine roll out will require co-ordination between all PBA Ministries with Ministry of Finance leading the financing, MoH leading the delivery, Ministry of Gender holding the central database on the poorest, and schools a likely venue for mass vaccinations. PBA should continue to focus on building the links between the Ministries to ensure more lesson learning and effective working across the sectors.	PBA Advisers supported establishment of Covid-19 Health and Education DPs working group to support GHS and GES on safe reopening of schools and measures to ensure prompt detection and effective management of Covid-19 outbreaks in schools. This group was eventually subsumed into a government led task force that led to safe school reopening and coordinated efforts to quickly and effectively tackle school Covid-19 outbreaks. Vaccination of school age children 15 years and over has been approved as policy and implementation commenced. Work in progress to support greater links between MGCSW and GHS to coordinate Covid-19 vaccination and risk communication campaign to reach poor and marginalised communities.
There is the need for CHAG to strengthen coordination with national COVID-19 response structures including the EOC and NTCC, ensuring that FCDO support to districts through the CRIB project is visible at national level, in line with the practice for other DP interventions.	Greater visibility of CRIB project achieved with MoH through periodic reporting of CRIB project activities at National Covid-19 Technical Coordination meeting, greater use of mass media to showcase achievements. Strong MoH/GHS and community leaders attendance at events.
Risk of Ministries, in particular Ministry of health, becoming overwhelmed by requirements from donors. By March 21, FCDO PBA team to consider offering MoH with additional support to ensure coherence and complementarity between donor offers.	Greater technical engagement of FCDO Ghana advisers in supporting MoH to achieve compliance with donor requirements. COVAX has developed a Country Counterpart Platform to help with Ghana and other countries to streamline and better organise compliance issues for COVAX vaccines supply.
OUTPUT 2 (N/A)
OUTPUT 3
PBA has not directly funded anything under this output. But the FCDO PBA team has carefully brought in niche TA and partnerships from existing CMPs to build capacity in the social sector Ministries - a quicker and more effective approach on issues that are common across countries as allows lessons learning. The FCDO PBA team should continue to use CMPs in this way, using PBA TA and partnerships to supplement these as needed.	PBA team continues to leverage CMPs to achieve objectives. For example, Ghana included in FCDO Epi-modelling CMP scoping activities.
FCDO to promote participation of relevant Health DP stakeholders in the HMG Health Partnerships design process to ensure FCDO Partnerships are complementarity and build on existing DPs technical support and experience	Stakeholder engagement was central to exploring UK/Ghana health workforce partnership intervention areas.
OUTPUT 4
It is therefore recommended that the PBA accountability CSO implementers produce and widely disseminate Sectoral Issues Tables or a similar document periodically, ideally every two years, for political parties, Parliament, Ministries, the general public, media and development partners. The PBA accountability CSO component should also carry out periodic Political Party Manifesto Tracking for ruling parties, to ensure that they are held accountable for their stewardship. Political party manifesto trackers should be translated into local languages and community radio stations used to reach rural, poor and hard to reach communities.	Between January and March 2021, CDD produced three policy briefs on issues in the education, health and social protection sectors. These policy briefs were shared with the respective Parliamentary committees namely; Health, Education and Gender and Children/ Employment, Social Welfare and State Enterprises. Dialogues with the Parliamentary committees were followed with media engagements in both English and Twi languages. The second phase of the project is currently tracking implementation of the Education Sector Strategic Plan.
PBA accountability CSO implementing organisations such as STAR to proactively reach out to media houses and other institutions for partnerships on projects promoting responsive and responsible manifestos for inclusive development. Such collaboration will begin to address the challenges media houses have in obtaining information and data, particularly on the state of the economy. Increased and mutually beneficial collaboration and partnerships between media houses, CSOs and academic institutions will build the trust needed for safe data transfer for policy influencing.	CDD-Ghana established partnership with Citi FM and the Multimedia Group particularly with Joy FM and Joy News TV. As part of the partnership, a national campaign and advocacy including engagement with experts and opinion leaders on sectoral issues, challenges and constraints were championed to demand political parties’ response and actions.
FCDO PBA team to rethink the milestones and targets from this output before the next AR given they are not clearly matching up.	A review of the milestones was undertaken by the FCDO PBA Team starting in September once budget allocations were concluded and an agreement reached on priority PBA components. The team agreed to continue to prioritise Outputs 4 and 5 – increasing the outputs weightings to 25% and 55% respectively and reducing the weighting of Output 1 to 10%. Weightings for Outputs 2 and 3 remained the same as during the 2020 AR period. prior to the start of this AR.
FCDO PBA team to explore feasibility of providing support (budget permitting) to CSOs (possibly CDD-Ghana or STAR) to maintain momentum in keeping the new GoG accountable for responsible prioritisation of its manifesto and other commitments in the interim period before contracting the TA supplier or STAR as proposed is finalised.	Accountable grants agreed with CDD-Ghana and STAR Ghana during the AR period.
OUTPUT 5
FCDO PBA to continue to monitor implementation of CHAG’s safeguarding policy through project meetings and field visits.	Safeguarding risks have been identified and are monitored through the CRIB project risk register, DDA recommendation updates during the fortnightly CRIB project meetings, and during field visits.
OTHERS
FCDO to conduct asset verification on programme funded assets with CDD-Ghana and CHAG by February 2021.	Completed – asset checks conducted by the FCDO team on the two projects managed by CHAG and CDD-Ghana reported no adverse findings. The main recommendation was for CDD-Ghana to brand the project laptops with the UKaid logo which has been followed up with. All assets were in good condition for both projects.
FCDO to commission audits of CDD-Ghana and CHAG in the next AR period to coincide with a full year of programming for each of the implementing partners.	Yet to be done as new projects are onboard. EV done for CDD but plan is to conduct EV for the entire programme then do a full programme audit after.
Major lessons and recommendations for the year
What PBA delivers:
PBA continues to fit squarely into FCDO’s human development objectives around global health security, girl’s education and the bottom billion, as well as accountability and human rights. It is also key to HMG’s efforts to support Ghana’s move towards self-financing and so to exit. PBA should therefore be prioritised as part of future business planning processes.	PBA is a priority in the current business planning process.
The FCDO PBA team to consider bringing in the domestic revenue mobilisation as part of its work with Ministry of Finance on efficiency and effectiveness. FCDO Team to make a recommendation by March 2021. If domestic revenue is not increased and GoG spend on the social sectors reduces at a time of increasing need, then PBA’s ToC will be undermined. Supporting GoG to raise revenues and to spend those effectively and efficiently on the social sectors is vital to Ghana’s human development and self-sufficiency.	A separate five-year Ghana Revenue Programme was approved and commenced during the AR period to drive reform and accountability. / PBA will continue to support advocacy for increased domestic funding of social sectors, stronger public financial management and greater efficiency in delivery of social sectors services.
How PBA delivers:
Setting up HMG partnerships with GoG may get harder given HMG’s domestic Covid -19 focus. However, the NHS partnerships should continue to be prioritised given the benefits to both governments while others that were envisaged (e.g., with the Department of Education, Quality commission) may need to be delayed.	DHSC established Ghana Partnership during AR period as follows: / £3.5m ODA programme WHO, Tropical Health Education Trust and CHAG in strengthening the Health Workforce. NHS/DHSC involved in UK-Ghana Health Workforce Partnership with work on health worker migration far advanced.
A flexible and adaptive approach to programme implementation continues to be highly relevant for PBA in light of continuing delays in procurement. FCDO programme team to assess programming options, assessing risks, benefits and costs associated implementation and put forward a submission with a recommendation for programme delivery to the Development Director for review and approval by March 2021. A key element will be coherence between the elements across the sectors.	The reduced funding envelope during the AR period (50% of forecasted need) and the unfolding of two separate waves of Covid-19 resulted in the PBA continuing with the first year focus of supporting Ghana’s Covid-19 response, continuation of essential health services and exploring partnership opportunities.
STAR’s pivot in 2020/21/22 to Covid -19 and social sectors means it is now a better fit with PBA than it was during programme design when the option to integrate it into PBA was rejected. STAR should now be brought under PBA to ensure coherence and complementarity with the technical assistance to Ministries. Once contracted, STAR will need to work closely with the supplier ensuring “demand side” issues are integrated into the supply side work plans.	Completed- STAR Ghana Foundation now under PBA through AG agreement starting October 2020 to September 2022
PBA should continue to work through sector and donor groups in the social sectors to maximise coherence and co-ordination. Where sectors (e.g., Health) are struggling to manage donor requirements, FCDO PBA team to consider by March 2021 whether to provide additional support as means to ensure UK ODA (via PBA but also multilaterals) is effectively used. FCDO PBA advisers will also need to continue to work closely with supported multilateral partners and global initiatives to ensure coherence across HMG’s ODA spend.	Ongoing (Sector and DP close working). FCDO is co-lead of the Health Development Partners Group (August 2021 – July 2023) and Gender Working Group FCDO participates in the Social Protection Sector Working Group as well as Development Partner meetings. The UK is co-Chair with the Ministry of Gender, Children, Social Protection on the Gender Equality Sector Working Group (GEST). Limited additional FCDO funding support provided to coordination activities due to competing FCDO funding priorities. Focus on improved coordination of Covid-19 support through multilaterals
FCDO Ghana, working with the Mental Health and Disabilities TA supplier in FCDO Ghana’s Leave No One Behind Programme, to advocate for inclusive Covid-19 vaccine readiness and deployment mechanisms with broad representation of people with disabilities and women in key planning committees, including the communications group for an effective Covid-19 vaccine campaign.	PBA CRIB project supporting Federation of Persons with Disabilities with Covid-19 risk communication activities with plans to extend work to Mental Health Self-Help groups under FCDO’s Leave no One Behind programme. FCDO Ghana supporting WB Covid-19 programme to advocate for greater inclusion of disabilities group in Ghana’s Covid-19 response planning groups.

2021 Annual Review Process

The PBA programme AR was led by the FCDO Cities and Infrastructure Adviser with support from the Health and Governance Advisers and Programme Officer/Manager. The team drafted the review report following desk review of key documents including PBA Business Case; logical framework, workplans, budgets, risk register, and quarterly/monthly progress and financial reports from CHAG, SGF, CDD-Ghana and the Health TA. The review was also shaped with inputs from meetings held with selected partners such as CHAG, DHSC, MoH and GHS. The review report was quality assured by the Programme’s Senior Responsible Owner (also Human Development Team Leader) and approved by the Development Director. The final Annual Review report will be uploaded on FCDO system (AMP) and published on Development Tracker.

Date of last narrative financial report	November 2021	Date of last audited annual statement/EV report	November 2021 - EV report for CDD-Ghana