## Annual Review Template

Title: Anti-Corruption Evidence (ACE)
Programme Value £ (full life): £32m		Review date: Feb-Apr 25
Programme Code: 203752	AMP start date: / April 2015	AMP end date: / September 2027

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2023	2024	2025
Overall Output Score	A	A	A	A	A	A+	A+	A+	A+
Risk Rating								Major	Major

DevTracker Link to Business Case:	All published documents (including annual reviews, business case, logical framework)
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

Anti-Corruption Evidence (ACE) aims to deliver new practical research about what works to tackle corruption, illicit financial flows and serious organised crime. It provides independent, rigorous research with a long-term funding commitment that allows teams to produce a large body of evidence over time as a global public good. ACE directly informs strategy, policy, operations and programming in FCDO, the UK government and beyond with impact around the world.

The ACE programme has three components, each of which specialise in certain thematic areas:
- SOAS ACE researches anti-corruption in infrastructure, power, health, education, climate change investments, digital government service delivery and political corruption and is led by Professor Mushtaq Khan, School of Oriental and African Studies (SOAS) University of London.
- Governance & Integrity ACE (GI ACE) researches illicit finance, enablers, corruption in emergency measures, trade and state capture and is led by Professor Paul Heywood, University of Sussex/University of Nottingham
- Serious Organised Crime ACE (SOC ACE) researches organised crime, illicit finance, kleptocracy and transnational threats and is led by Professor Heather Marquette, University of Birmingham.

ACE takes as its starting point the following framing principles:

- Being problem-led, not starting with preconceived ideas about the ‘right solutions’.
- Taking politics seriously, developing politically viable reforms and approaches in ways that are context-sensitive and avoid negative unintended consequences.
- Focusing on real world priorities in sectors in which corruption, organised crime and illicit finance are part of, but rarely all of, the problem.
- Thinking differently about prevention through better understanding the ways in which corruption and organised crime provide solutions to the everyday problems people face that often have deep social, structural, economic and political roots.
- Developing innovative approaches to testing and measuring the effects of anti-corruption, counter-organised crime and illicit finance interventions.
- Planning ‘nose to tail’ engagement with policy makers and practitioners – from research design, implementation, delivery, communications and engagement.

The programme is funded by ODA and non-ODA (NODA) from Research and Evidence Directorate. It supports research on corruption and illicit finance and serious organised crime and to date has worked with over 200 researchers focusing on over 30 countries.

ACE’s overall programme outcome is that robust new knowledge and evidence on anti-corruption leads to the development of and investment in more effective policies and programmes, including by FCDO and partners.

Summary supporting narrative for the overall score in this review

ACE has achieved progress in a range of areas this year. Key achievements include:

1. SOAS ACE:
  1. There has been an explosion of interest in SOAS ACE corruption research following the July uprising in Bangladesh and subsequent change of government, with requests for advice from Ministers in the new interim government, donors, foreign ministries and NGOs. Mushtaq Khan was invited to join the National Commission to Reform the Anti-Corruption Commission (ACC) in Bangladesh. The Reform Commission published a February 2025 report with recommendations inspired by SOAS ACE research (for example a recommendation to include horizontal checks by independent actors within the ACC to ensure that it is not itself subject to corruption). and this report was accepted by the interim government to become an official document of the Government of Bangladesh.

  1. Mushtaq Khan was invited to join the National Committee on Re-Evaluating Power Sector Contracts in Bangladesh and he and the National Committee are now using a SOAS ACE methodology to analyse previous contracts, identifying suspicious contracts for further investigation by comparing prices of otherwise identical plants.

  1. SOAS ACE’s work in the health sector in Bangladesh made significant progress. Already before the change of government in mid-2024, the health sector partnership initiative, led by the Swedish Embassy/ Swedish International Development Agency and including FCDO, used two SOAS-ACE papers to define two specific areas for an anti-corruption drive. Since the change of government, change has accelerated with the Director General of the Drugs Regulatory Agency of Bangladesh (DGDA) interested in the SOAS ACE methodology for testing and certification as a way of reducing corruption and limiting drug overpricing. USAID’s withdrawal from Bangladesh presents problems for this work which may focus now on regulatory changes.

GI ACE:
John Heathershaw and his team at Exeter University published Indulging Kleptocracy (Oxford University Press), a path-breaking account of how transnational kleptocracy operates within the zones of legal ambiguity created by the globalization of financial and legal services. The book received a Best Book of 2024 Award from Foreign Affairs, and the authors have engaged in numerous briefing sessions with officials from across HMG.

Dan Haberly’s research on the regulation of illicit financial flows has generated new insights into transnational movements of funds, notably highlighting a shift to a ‘Dubai-Kong axis’ as the central hub in many different types of sanctioned and criminal networks, the continued role of the UK and its Overseas Territories, and a rising importance of the US and China in specific areas. The work has prompted several briefings across HMG, and has also been featured in the FT’s ‘The Banker’. Haberly, together with Tax Justice Network, is in discussions with the International Centre of Expertise on Illicit Finance about building a dashboard to facilitate risk-based analysis of illicit finance links.

SOC ACE:
Following SOC ACE-supported research by Eliza Lockhart which made the case for financial rewards for whistleblowers, the Government in March announced the introduction of a cash reward scheme for whistleblowers who expose tax avoidance and fraud. James Murray, Exchequer Secretary of the Treasury, announced on Tuesday, 11 March that the scheme will look to target serious non-compliance in large corporates, wealthy individuals, offshore and avoidance schemes, taking inspiration from the successful US and Canadian ‘whistleblower’ models, and complementing the existing HMRC rewards scheme. The timing of this announcement, combined with the high levels of engagement in Eliza’s research, and media coverage, indicates that Eliza Lockhart’s research has contributed to this move.

Matthew Redhead’s SOC ACE-funded research on the challenge of state threats, published in January this year, is showing early indications of influencing thinking and policy on how the UK considers and approaches the issue. FCDO’s DG Defence & Intelligence opened the paper’s launch at RUSI. Redhead was then invited to deliver a cross-Government presentation of the findings.

The SOC ACE-funded Medellín demonstration project continues to inform both on-the-ground efforts to tackle organised crime in Medellín, Colombia, and wider public debates on the issue. Three interventions are currently under way to test, scale and evaluate different approaches to tackling extortion in Medellín. The positive impact of the research on the city and region has been recognised by the Medellín Mayor’s Office through award of the Medellín Impact Award 2024 to SOC ACE researcher Santiago Tobón and team. In addition, Benjamin Lessing was invited to write an article for The Economist which speaks of the specific ‘carrot and stick’ methods identified in the research which helped to incentivise and coerce gang members to change their courses of action.

Major lessons and recommendations for the year ahead

ACE Principal Investigators and FCDO have developed significant learning through the course of the year. Key lessons are summarised below. Where appropriate, lessons are linked to recommendations.
L1 [SOAS ACE]. The nature of SOAS ACE research is inherently ‘operationalisable,’ yet the programme lacks funding pathways to initiate small-scale experimental implementations that would translate research findings into practice. Many FCDO posts’ allocations of ODA are declining significantly, and in many cases they may not have funds available for anti-corruption related programming. Even in posts where funding is available, this is often tied up in larger, long-term programmes which are not able to provide the small amounts of funding which would allow SOAS ACE research to translate into policy and programme implementation.
L2 [SOAS ACE]. The rapid transition following the fall of the Awami League government in Bangladesh was foreseen by SOAS ACE political settlements analysis which had pointed out the ‘vulnerable authoritarian’ nature of the regime and that it could suddenly collapse. The value of SOAS ACE research and analysis was that the programme was then able to adapt rapidly following the political transition, using its knowledge on how informal networks and corruption operate in Bangladesh to assist the interim government in critical areas. For example, its work on power sector corruption in Bangladesh had identified entry points for reform during the tenure of the previous government. This was very useful after the transition, when the research switched to looking for evidence of corruption in the award of contracts. The SOAS-ACE research method of beginning with the sector and sequentially looking for entry points until a feasible one emerges generates information that is also useful when the background political settlement changes, because the knowledge gathered can help to identify more impactful entry points that may now be feasible.
L3 [GI ACE]. Corruption is evolving fast, in a global political environment which is also rapidly evolving. In the face of these changes – which pose significant risks both to global development efforts and to UK interests – research needs also to evolve quickly to meet the scale of the challenge. GI ACE has already responded to this through new workstreams on state capture, on changing patterns of illicit financial flows, and on the role of enablers in the global north.

L4 [GI ACE]. Agreeing proposals for non-ODA research under GI ACE has been challenging this year. FCDO and GI ACE have discussed and will continue to liaise to ensure a joint understanding of the scope of this research in future.

L5 [SOC ACE]. SOC ACE has noticed that some research outputs submitted during the reporting period have demonstrated a potential misunderstanding of the nature of SOC ACE research standards compared to research commissioned by FCDO policy or geographic teams. In these cases, extensive revisions were required to bring research papers up to standards of rigour required for CDEL research. The researchers have been academics with PhDs, so have had the capability to produce high quality work. However, their experience producing FCDO-commissioned policy research and consultancy had shaped expectations of what was required.

L6 [SOC ACE]: As reported through the year, several structural challenges in SOC ACE’s financial management were identified as part of the FY23/24 financial reconciliation process and internal management review. The reporting period has seen these challenges resolved, with two lessons emerging during the process. Firstly, it is key for both parties of the Accountable Grant to agree on the financial reconciliation at the end of each financial year, ensuring that both parties' financial records reflect the agreed figures. The second lesson has been that given the time intensiveness of resolving issues that lay across both parties' desks, resolution dependencies should be considered so that resolution is more efficient, less time intensive and less impactful on other areas.

L7 [Pan-ACE]. Agreeing pan-ACE approaches in the reporting year has been challenging. Whilst the pan-ACE brochure has been completed, the Illicit Finance synthesis has stalled with disagreement on some fundamentals including who it is for and what is meant by synthesis. Also, the health sector synthesis has not yet been agreed. There appears to be limited appetite among ACE partners for greater efforts to forge a common approach. This is understandable as their respective approaches are very different, and are also complementary.

Recommendations
R1 [All ACE partners]. Following the Impact and Outcome workshop in June, agree an approach for how to count and differentiate between outputs, outcomes and impact in the programme. Revise the logframe, updating targets for future years and making some targets more ambitious where previous thresholds have already been significantly exceeded [PIs and FCDO, by September 2025].
R2 [Pan ACE]. Complete pan-ACE synthesis product on Illicit Finance in a way that all ACE partners agree, as there remains significant policy demand for this product. If necessary, this may involve a joint meeting with all partners and FCDO. [PIs, by December 2025].
R3 [SOAS ACE and GI ACE] To enhance website and engagement and increase the number of newsletter opens, each partner should develop a plan for improving communication efforts. This may include, for example, ensuring timely posting of briefs and working papers, or circulating newsletters at the end of each quarter. [SOAS ACE and GI ACE PIs, by March 2026]

R4 [SOAS ACE]. In the new reporting year, aim to return publication of research papers to levels before the political transition in Bangladesh. This is to ensure that lessons are captured from the important work done under the programme including especially in Bangladesh itself [SOAS ACE PI, by March 2026].
R5 [SOAS ACE]. Following SOAS ACE’s own reflection, and given the difficulties accessing programme funds from FCDO posts, SOAS ACE to extend its development of options for solutions that do not involve donor programme funds (as is currently happening in some sectors in Bangladesh, for example). [SOAS ACE PI, by March 2026].

R6 [SOC ACE]. SOC ACE to implement its proposal to add clear guidance to proposal templates on the standards of rigour for CDEL-funded research and ensure researchers' understanding at the outset of research implementation and throughout. This guidance can also be shared with other ACE partners. [SOC ACE PI, by September 2025].

R7 [SOC ACE]. SOC ACE and FCDO to agree on previous years’ financial reconciliations, ensuring each parties’ financial systems and the Accountable Grant Agreement reflect the correct values [FCDO and SOC ACE, by June 2025].
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The ACE Business Case, SOAS ACE’s contract, and GI’s proposal for GI ACE, were based on a standard Theory of Change (ToC) for GCIH research programmes, which also underpins the ACE logical framework. Both SOAS ACE and GI ACE have further refined this and have produced their own ToCs (see two diagrams below), which link to their own activities and monitoring systems (including their own logical frameworks). SOC ACE does not have its own individual Theory of Change and assesses that focusing on the principles behind the (SOC) ACE approach across all of our work is in effect a theory of change that the research is helping to test, to challenge and to evidence. There is an option for SOC ACE to develop a distinct ToC or perhaps instead reflect on ToC lessons, in consultation with HMG stakeholders and researchers in 2023/4.

The basic ACE ToC is that:
- ACE (GI, SOAS, SOC) research frameworks and strategies identify priority research questions and themes that will contribute to the evidence base for policy makers and other interest groups, including FCDO and its partners.
- Programme leads design and oversee implementation of a portfolio of research projects (with fieldwork in specific settings and with appropriate methods and analysis) to deliver this new evidence (output 1).
- Throughout the research cycle, researchers and programme teams engage with policy makers to ensure that the research addresses real needs, and also to prepare audiences for uptake of the new research products.
- ACE produces a range of research outputs tailored to different audiences, and actively disseminates these, including through publication, online, and at events (output 2).
- Where required, ACE builds capacity as it works with research partners to deliver the research to expected quality and on time (output 2).
- ACE research is used by policy makers and other interest groups to improve the effectiveness of Anti-Corruption programmes and policy (outcome).

SOAS ACE and GI ACE Theory of Change

ACE has demonstrated three main paths from research to policy influence. The first is where academic research and academic engagement with policy teams is used by FCDO staff designing programmes (for example anti-corruption programming, power sector or health reforms, or the state threats portfolio). The second is where academic research leads to greater parliamentary, media and civil society and public understanding of a set of issues (for example the influence of kleptocracy or shell companies, and how to address these) and this feeds into UK legislative changes. The third is where academic research informs others to change (for example World Bank procurement or emerging work on digitisation). These pathways to change are not mutually exclusive and cannot necessarily be mapped out in advance, but learning across ACE about what has worked continues to be a useful endeavour.

The ACE business case sets out plans for ensuring gender equality, including gendered analysis in research delivery. Both SOAS ACE and GI ACE have strengthened their delivery of truly gendered analysis relevant to corruption and Anti-Corruption. This is also part of the SOC ACE planning. If feasible, ACE partners will aim to provide aggregate reporting on the genders of researchers being engaged. All SOAS ACE research projects are collaborations with partners and there is a PI from both SOAS and the partner – they are the intellectual leads for the projects - “a co-PI” in recognition of the collaborative partnership. In SOAS ACE research projects, out of a total of 17 co-PIs, 47% of co-PIs are women. GI ACE introduced an additional logframe indicator (Output 1.b.5) to track success in supporting increased representation of women in anti-corruption research, with a target that at least 40% of outputs aimed at practitioners, academic articles published, and project-related material on the website, should include and/or involve women.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

ACE’s impact is: “Measurably reduced prevalence of corruption with positive impacts on service delivery, poverty reduction, safety and security, economic development and the lives of poor people.”

ACE partners agreed a set of indicators to attempt to measure pathways to impact, understanding this as A) conceptual impact (changing ways of thinking etc); or B) instrumental impact (influencing policy and practice etc); or C) networks and connectivity impact (e.g., building and strengthening networks etc); or D) capacity building impact. There is no prior prescription about what type of impact would be achieved, but rather the purpose is to track this as the programme progresses.

Impact Indicator	Milestones March 2025	Progress
Examples of A) conceptual impact (changing ways of thinking etc); OR B) instrumental impact (influencing policy and practice etc); OR C) networks and connectivity impact (e.g., building and strengthening networks etc); OR D) capacity building impact (building researchers' capacity to strengthen research uptake etc).	12 / (cumulative)	17 cumulative / (6 annual) / SOAS ACE: 3 / GI ACE: 2 / SOC ACE: 1

18. The three ACE partners each track how their respective programmes contribute to impacts across the four impact areas. Although they expect to see outcomes lead to impact over time, across ACE partners are in the process of further work to define criteria to distinguish between what we might include as outcomes and impacts. Drawing on the outcome mapping M&E approach, the concepts of the programme’s sphere of control, sphere of influence and sphere of concern, they plan to map out how we differentiate between outputs, outcomes and impact.

19. SOAS ACE [conceptual/instrumental]
As a result of SOAS ACE research and reputation, in October 2024 Mushtaq Khan was invited to join the National Commission to Reform the Anti-Corruption Commission (ACC) in Bangladesh. One of the key conceptual innovations and insights of SOAS ACE is the importance of horizontal checks for ensuring that formal enforcement is not itself corrupted. In February 2025 the reform commission published a report including recommendations to set up independent actors – important individuals with the political and social capital to exercise horizontal checks within the ACC – to ensure the formal enforcement is exercised with reduced corruption. The Chief Adviser (interim Prime Minister) has accepted this publication and set of proposals as an official document. The next step is a conversation with political parties and stakeholders for it to be converted to legislation.

20. SOAS ACE [conceptual/instrumental]
As a result of SOAS-ACE research on corruption in power sector contract, in September 2024 Mushtaq Khan was invited to join the National Committee on Re-Evaluating Power Sector Contracts in Bangladesh. The National Committee is now reviewing all previous contracts using the methodology developed in earlier SOAS-ACE research to identify suspicious contracts for further investigation. At the request of the Power Advisor (the Power Minister) to raise additional funds for taking forward findings of corruption to legal arbitration processes and as a result of Mushtaq Khan’s presentations UNDP committed $1m to take the power sector anti-corruption investigation forward to international arbitration when the Committee is ready with its findings.

SOAS ACE [instrumental]
In December 2024, the health sector anti-corruption initiative in Bangladesh, led by a multi-partner coalition including Mushtaq Khan, met with the Director General of the Drugs Regulatory Agency of Bangladesh (DGDA) and to explain the testing and certification process identified in the SOAS-ACE paper as a tool to set up horizontal checks and limit drug overpricing. The Director General provided enthusiastic approval and instructed his team to take actions to take the certification process forward. Rollout of the regulatory changes will follow; the Swedish Embassy has appointed a part-term consultant to coordinate this work. There has been a partial setback in that USAID had been helping DGDA to improve their testing facilities and is no longer operating, but the Director General remains supportive.

GI ACE [instrumental]
Paul Heywood’s research, funded under GI ACE in previous years, was in January 2024 identified by the Minister of the Office Comptroller General (CGU) of Brazil, Vinicius Marques de Carvalho, as having had a significant influence on the development of the CGU’s Integrity and Anti-Corruption Plan 2025-2027, launched in December 2024. At the CGU-led Academic Connections event on 23 Jan 2025, the Minister said: “Recently the CGU [Comptroller General of the Union] launched the integrity and anti-corruption plan, a broad national initiative, significantly influenced by Professor Heywood’s research, [...] which brings together 260 strategic actions developed by 53 agencies of the federal executive branch, with the participation of 50 experts from universities and research institutes”. CGU staff explained that Paul Heywood’s GI ACE-funded research had contributed in two ways: “First, his work on public integrity has enriched the Office of the Comptroller General’s (CGU) perspective on the topic. Second, prior to drafting our plan, CGU conducted an extensive review of relevant international guidelines and benchmarking of other countries’ experiences. In this context, the insights shared by Professor Heywood—who kindly granted us an interview on April 23, 2023—on the design and monitoring of national plans proved especially valuable”.

GI ACE [instrumental]
Under British Academy-ACE, Jan Meyer-Sahling led a project which conducted large-scale surveys of public servants in developing countries across the globe in order to examine the impact of civil service management practices in key areas on reducing corruption in the civil service. The team behind the project have gone on to implement the surveys developed as a part of the project in additional contexts. For example, the findings of this research were presented to the Inter-American Development Bank, who went on to initiate a project, informed by the research, to develop a survey on competences and integrity of National Statistics Office employees across 14 Latin American countries, generating 13,000 responses. This work was completed in 2024. Building on the work under BA-ACE, Jan led a subsequent project under Global Integrity-ACE which sought to design and implement ethics training courses with civil servants in Nepal and Bangladesh. In Nepal, the research has led directly to the incorporation of ethical leadership training in the Inland Revenue Department’s induction and leadership curriculum, overseen by Meyer-Sahling.

SOC ACE [instrumental]
His Majesty’s Revenue and Customs in the UK (HMRC) has announced introduction of a cash reward scheme for whistleblowers who expose tax avoidance and fraud. James Murray, Exchequer Secretary of the Treasury, announced on Tuesday, 11 March, that the scheme will look to target serious non-compliance in large corporates, wealthy individuals, offshore and avoidance schemes, taking inspiration from the successful US and Canadian ‘whistleblower’ models, complementing the existing HMRC rewards scheme. The timing of this announcement, combined with the high levels of engagement with Eliza’s whistleblower research, including HMT’s participation in pre-announcement briefings (see Annex 1 for details), media coverage, and the fact that the Canadian experience is not generally referenced in economic crime whistleblowing literature, indicates that SOC ACE research has contributed to this move by HMRC.

ACE’s outcome is: “Robust new knowledge and evidence on Anti-Corruption leads to the development of and investment in more effective policies and programmes including by FCDO and partners.”

Outcome Indicator(s)[1]	Milestones March 2025	Progress
SOAS ACE a.1 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by FCDO. (Cumulative)	22	Moderately exceeded. / 24 cumulative / (3 annual)
SOAS ACE a.2 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by other development partners and stakeholders. (Cumulative)	38	Moderately exceeded. / 41 cumulative / (4 annual)
GI ACE b.1 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by FCDO.	19 cumulative / (3 annual)	Met. / 19 cumulative / (1 annual)
GI ACE b.2 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by other development partners and stakeholders.	12 cumulative / (2 annual)	Substantially exceeded. / 17 cumulative / (3 annual)
SOC ACE c.1 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by HMG	18 cumulative / (5 annual)	Moderately not met. 17 cumulative / (4 annual; 3 NODA funded, 1 NODA/ODA)
SOC ACE c.2 Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by other partners and stakeholders.	4 cumulative / (3 annual)	Met. 4 cumulative / (3 annual; including 1 NODA funded)
[1] Outcome indicators have no initial numeric marking, but for outputs, the initial numeric ‘1’ and ‘2’ refers to the first and second outcome. Throughout, SOAS ACE indicators are marked ‘a’, GI ACE indicators are marked ‘b’ and SOC ACE indicators are marked ‘c’.

In aggregate, ACE has met its outcome milestones for this year:

Outcome a.1 [SOAS ACE]
FCDO Nigeria has commissioned a political economy study (Macro Political Economy Analysis Scoping, Nigeria), separate to ACE, where Pallavi Roy is the Principal Investigator. Key recommendations from the PEA study, some of which have already been presented to the Senior Management Team, including the High Commissioner, senior governance advisers, and PMEL Team have included findings from SOAS-ACE research on electricity supply governance models for SMEs and on mitigation and transformation strategies for contexts like the Niger Delta. This is the first time that SOAS-ACE's PCI framework is being used in FCDO research and will contribute to further conceptual uptake in the FCDO’s PEA toolkit.
Pallavi Roy was invited to be a member of the political economy advisory group of the Decision Support Unit for the FCDO’s Land Facility (LF) which is the main component of its umbrella Global Land Governance Programme. The group will be expected to critically evaluate the LF strategy and approach for assessing and develop political support for reforms, including political engagement and influencing strategies, as well as provide technical support for implementation as necessary.
Pallavi Roy's participation in the PMEL-curated PEA advisory group at FCDO Nigeria provided a crucial platform for engaging with senior FCDO staff. By showcasing how SOAS-ACE applies the PCI approach across sectoral research in Nigeria, she was able to contribute directly to discussions on the use of PEA within FCDO. This engagement created a significant opportunity to influence FCDO Nigeria’s approach to PEA.
Outcome a.2 [SOAS ACE]
- Mushtaq Khan was invited to join the National Commission to Reform the Anti-Corruption Commission in Bangladesh, based on reputation achieved through SOAS-ACE research. The Reform Commission published its report in February 2025 (outcome level result). The report was then accepted by the interim government (impact level result listed above).
- Mushtaq Khan was invited to join the National Committee on Re-Evaluating Power Sector Contracts in Bangladesh, based on SOAS-ACE research on corruption in power sector contracts. (outcome level result). The National Committee is going through all previous contracts using the methodology developed in earlier SOAS-ACE research to identify suspicious contracts for further investigation (impact level result listed above).
- An influential briefing by Pallavi Roy to diplomats in Bangladesh led to further high-level engagements with the garments industry in the country, with the prospect for significant positive change.
- USAID Bangladesh began using the SOAS ACE horizontal checks approach in its work on asset recovery in October and November 2024 given that formal investigation agencies could not be relied on to provide accurate information for the international asset recovery process. However, support and analysis has been discontinued as a result of the closure of USAID. (As a result, this example is not counted as an outcome.)
Outcome b.1 [GI ACE]
Dan Haberly and the Tax Justice network (funded under GI ACE) is working with FCDO’s International Centre of Excellence on Illicit Financial Flows to build a new dashboard for illicit finance analysis, incorporating the data/datasets that the team put together as part of their GI ACE project. This represents a policy and programme design link.
Outcome b.2 [GI ACE]
- As a direct consequence of the Jan Meyer-Sahling projects on civil service reform, a new instrument – the Global Survey of Public Servants (GSPS) – was set up by the World Bank, Stanford University, the University of Nottingham and UCL. The GSPS (the latest version of which was launched in May 2024 at the WB) pools data from 30 countries.
- The team led by Meyer-Sahling has worked with OECD Support for Improvement in Governance and Management (OECD SIGMA – a joint initiative of the EU and OECD) to use public servant surveys as part of assessments of EU candidate states' public administrations’ readiness for EU accession.
- Further surveys that built on the initial civil service research led by Jan Meyer-Sahling were carried out in Central and Eastern Europe, in collaboration with the Regional School of Public Administration (ReSPA), and the team also carried out the third national public servant survey with the government of Chile.
- The GI ACE report, ‘Merchants of Integrity? Commodity trading and corruption research for a world in transition’ had a direct influence on the PROTECT project (Promoting Responsible Ownership & Transparency in Critical Minerals), a collective action programme designed to address corruption risks in the critical minerals supply chain – which was launched in 2024 as an initiative of the Anti- Corruption Governance Center within the Center for International Private Enterprise (CIPE). Staff at the CIPE confirmed that the GI ACE research had ‘played a key role in shaping the parameters of the PROTECT project’. However, the PROTECT project has had funding withdrawn by the new U.S. presidential administration. (As a result, this example is not counted as an outcome.)

Outcome c.1 [SOC ACE]
- Eliza Lockhart’s research paper, published Dec 2024, has contributed to a change in the UK Financial Conduct Authority’s (FCA) official position with regards to financial rewards for economic crime whistleblowers, now recognising that there are benefits in, and implications of, providing incentivisation to whistleblowers. The report, by Lindsey Rogerson for Compliance Corylated (12/12/24), explicitly references Eliza’s paper and compares the new position with the FCA’s previous position of 2014 that “there was no empirical evidence of incentives leading to an increase in the number or quality of disclosures received by the regulators.” SOC ACE will monitor the FCA position and actions concerning economic crime whistleblower reward schemes. The later decision by the Government to introduce a scheme for financial rewards for whistleblowers is reported as an impact level result above. [NODA funded]
- Matthew Redhead’s State Threats research is showing early indications of influencing thinking and policy on how the UK considers and approaches the issue. FCDO’s DG-Defence & Intelligence opened the paper’s launch at RUSI, which was picked up by iNews (14/01/25). Redhead was then invited to deliver a X-HMG briefing on the findings. [NODA funded]
- Heather Marquette was invited by IFAC to a Ministerial Engagement Session with FCDO Ministers on illicit finance and corruption. During the session and in a follow-up note, the Minsters were provided with information about SOC ACE research projects relevant to their priorities as well as ways in which SOC ACE’s research on improving integrated working across multiple agencies and thinking and working politically can support the government’s agendas. Ministers requested further information on three SOC ACE projects, and further follow-up engagement is being planned around these, as well as other key research from SOC ACE. [NODA/ODA funded]
- Erica Marat and Alexander Kupatadze’s SOC ACE paper, ‘Under the Radar: How Russia Outmanoeuvres Western Sanctions with Help from Its Neighbours’ has been included as recommended reading in a 17 Jan 2025 House of Commons research briefing on Sanctions against countries supporting Russia’s invasion of Ukraine. [NODA funded]

Outcome c.2. [SOC ACE]
- SOC ACE Research Paper 4 by David H. Ucko and Thomas A. Marks, has been included in NATO’s Hybrid Threats and Hybrid Warfare Reference Curriculum as required reading under Theme 2, Threat Vectors: Domain-related means and methods of exercising hybrid threats and hybrid warfare, Sub-Theme T2-B8, Organised Crime. This NATO course is deployed internationally with NATO personnel (practitioners) participating. The research paper demonstrates that applying an Irregular Warfare framework can assist NATO personnel in understanding, assessing and responding to organised crime in operational theatres, providing course participants with new knowledge and tools to factor in organised crime dynamics in their work. The paper therefore has a significant potential to inform SOC-sensitive NATO approaches to hybrid warfare. The curriculum was published in June 2024. [NODA]
- Findings on some of the deficiencies in the Total Peace Policy legal framework found by the SOC ACE-funded Total Peace research project in Colombia have been used as the foundational starting points for strengthening the legal framework for the negotiations with the armed group, Comuneros del Sur de Nariño, through advice provided by a SOC ACE researcher and other colleagues at Laboratorio de Justicia y Política Criminal (LJPC), via a process funded by The Carter Centre.
- Research findings of the Medellín Impact Lab’s demonstration project in Colombia, co-funded by SOC ACE, are directly informing the development, testing, scaling and evaluation of treatment interventions to tackle extortion in Medellin. Three interventions are in progress: 1) conditional repression to reduce extortion; 2) scaling of a multi-pronged approach to reduce gang recruitment; and 3) evaluation of city government unarmed approaches to tackling disorder and crime for improving state legitimacy across the city.

27. All impact and outcome indicators will be reviewed for numerical ambition and clarity considering the Global Integrity – Sussex transition and new phase of SOAS and SOC ACE plus the need for differentiation from output to outcome to impact.

Whether the programme should continue, based on its own merits and in the context of the wider portfolio

28. ACE is delivering highly relevant research which is having clear, real-world impact. It continues to address FCDO ministerial priorities such as the Foreign Secretary’s campaign on Illicit Finance. As such, there is a very strong case for it to continue.

Update on implementation of each of the recommendations from last year

29. All 2024 recommendations are listed here with the implementation recorded in italics.

R1. A rolling joint ACE seminar series should commence, to provide a forum for researchers engaged in ACE research to share ideas and experience and to connect with FCDO and other HMG colleagues working in this area (PIs plus SRO, by September 2024).

Completed. GI ACE, SOAS ACE and SOC ACE have developed a programme of events for 24/25, with each partner leading in turn on organising an event on a rolling basis. So far, 6 seminars have taken place and have proven to be very popular, with attendance averaging around 90-100 people.

R2. Identify appropriate opportunities to promote the ACE programme as a whole (such as major set-piece events like IACC, OECD GIobal Anti-Corruption & Integrity Forum) and ensure there is relevant promotional material (for instance, information sheets, pop-up banners, QR code links) to highlight the ACE programme overall (PIs, ongoing).

Completed. This year SOC ACE has worked with GI ACE and SOAS ACE to complete the production of the PAN-ACE brochure, which is now available in print and digital formats. Also, SOC ACE and GI ACE hosted a joint marketplace stall at the International Anti-Corruption Conference (IACC 2024), where both programmes displayed research outputs and information. GI ACE and SOAS ACE also joined the SOC ACE Researcher Conference in September.

R3. ACE partners should continue to consolidate their networks across FCDO as relevant, building from the contacts with IFAC, JACU and the HMG advisory group which also includes Heads of Profession and HMT. For each ACE this will look different, for example GI ACE may wish to facilitate meetings with researchers particularly as the latest round of research begins. SOAS ACE continues to build work in its focus countries while supporting the applications of its research elsewhere. SOC ACE can start to share leadership of FCDO contacts and connections with other member of the core SOC ACE management team. Building a range of communication and engagement tools may also support engagement and uptake (PIs by December 2024).

Completed. All ACE partners continued to engage strongly with FCDO and other Government Partners in 2024/25. SOAS ACE researchers have established strong relationships with FCDO Posts in Bangladesh and Nigeria, sharing ongoing research and implications for programming, but also engaging in other areas of FCDO interest, such as climate change in Bangladesh and economic reforms in Nigeria. GI ACE has had a variety of engagements with various FCDO staff throughout the year, including various meetings with researchers, a seminar on state capture for an FCDO audience, briefings on state capture to FCDO teams in Ecuador and the Western Balkans, and engagement with the International Centre of Expertise on Illicit Finance. SOC ACE’s significant engagement with FCDO is summarised under output 2.c.1 and the Annex. This year the programme has broadened its offer of communication materials for effective engagement with FCDO, including the SOC ACE Brochure, a suite of project summaries in print and digital, information notes and press-pitches. There is still more to do to share leadership of FCDO contacts and connections with the wider SOC ACE management team; this will be a priority in the next reporting year now that a new Senior Research Communications Officer has been successfully recruited.

R4. Hold a pan-ACE reflection and learning session to understand the types of change ACE is generating and to build a consensus on how to define and differentiate between Impact and Outcome Indicator measurement. Following the Impact and Outcome workshop, update results framework both with indicator definitions and simplifying output monitoring where this can be streamlined. SOAS ACE output 2 indicators should be reduced and ‘active learners’ should be redefined possibly as greater than 50% step completion. (PIs plus SRO/PM, by September 2024)

Not completed, in progress. SOC ACE and SOAS ACE have been working to organise the workshop, but diary challenges for the PIs have meant that it has been difficult to find a time that works for all. This is now scheduled for 1 June 2025. The workshop will be able to address topics which arose in this annual review, for example how to count an impact that spans across both conceptual and instrumental, or how to deal with case studies that are counted at outcome level one year and impact level the following year, etc.

R5. Given the direction of travel for Twitter/X, ACE partners and FCDO should consider alterative platforms/outlets and adapt output indicators where relevant (PIs plus SRO/PM, by September 2024).

Completed. All three ACE partners have established presences on alternative platforms, though some continue to use X additionally. SOAS ACE has prioritised LinkedIn where it has grown its follower base. GI ACE has decided to prioritise LinkedIn and Bluesky as key social media platforms; it has its own Bluesky account and is using the Centre for the Study of Corruption LinkedIn platform to take advantage of the established reach on that channel. SOC ACE has set up a page on Bluesky which was soft launched in December 2024; there are plans to increase activity on the platform once the new Senior Communications Officer joins the team.

R6. All ACE newsletters and websites should flag that colleagues or policy makers should get in touch to let ACE know if the research has been used and provide contact details to do so. Where possible, and notwithstanding the sensitivity of ongoing strategy, policy and decision-making processes, ACE should follow up with key posts and teams to understand how the research is being used, which can also help inform communications and engagement strategies (PIs, by September 2024).

Not completed, in progress. SOC ACE’s newsletter now includes a call for policymakers and practitioners using SOC ACE research to inform thinking and/or ways of working to get in touch via the impact-socace@contacts.bham.ac.uk inbox to share how they are using it. This will be added to the website in the new financial year as part of a wider planned website upgrade. For GI ACE and SOAS ACE, this recommendation has not been fully implemented, although both programmes do discuss how research is used in conversations with policy and country teams.

R7. To enable SOC ACE to maintain the momentum built and capitalise on gains made to date, if NODA is not able to have multi-year allocation, explore the potential of converting a portion of the indicative NODA allocations for subsequent years into ODA (SRO and SOC ACE by June 2024).

Completed. In the reporting period, SOC ACE made a proposal to convert a portion of the indicative NODA allocation for subsequent years into ODA – adding an additional £975k of ODA funding over the programme’s life. The proposal was approved and an amendment to the Accountable Grant was signed in August 2024.
R8. SOAS ACE should consider gathering feedback from its core FCDO country offices in the coming year to help identify research topics that align with the priorities outlined in the country plan and therefore where piloting might be most feasible. SOAS ACE may consider organising high-profile seminars/workshops bringing relevant stakeholders together to implement some of its recommendations, and where appropriate, FCDO Bangladesh is interested in being part of some of its government and private sector engagement.
Completed. SOAS ACE has been liaising closely with the Bangladesh and Nigeria FCDO Posts. Before, during and after the July Uprising, SOAS-ACE provided insights and analysis to FCDO Bangladesh. SOAS-ACE researchers with their expertise in identifying feasible policy were called upon by FCDO Nigeria to work on the reform agenda. SOAS ACE has been in regular touch with staff at the Nigerian High Commission in Abuja and this has included regular updates about SOAS-ACE research. The team now has established regular touch points in the office who also provide feedback on the direction of the research and share information about possible opportunities for the research to inform FCDO’s own work.
R9. GI ACE should look to aggregate key themes and insights in what the research is adding to corruption and IF debates, to find more and more creative communications. Leads may wish to liaise with the IFAC team in FCDO on opportunities for research engagement.
Completed. GI ACE has developed its approach to communications. GI ACE is using social media to communicate summaries of key insights from their research. Several GI ACE researchers have featured on Kickback, the global anti-corruption podcast. GI ACE are developing a monthly newsletter, with the first iteration published in March 2025. Regarding engagement with FCDO, GI ACE have agreed to draft summaries and update notes for key audiences, with the most appropriate formats to be determined on a case-by-case basis. There remains some more work to do to increase engagement with FCDO leads.

## C. DETAILED OUTPUT SCORING

Output 1	High quality, policy relevant new evidence and methodologically advanced research produced on 'what works to reduce corruption' and 'anti-corruption in the private sector'
		Output Score		A+
Impact weighting (%):	60%	Weighting revised since last AR?		No
Indicator(s)	Milestone March 2025		Progress
1.a.1 [SOAS ACE] / Number of working papers and policy briefs	128 (cumulative)		Moderately not met. / 123 cumulative (7 annual)
1.a.2 [SOAS ACE] / Number of peer reviewed journal articles produced/ submitted	26 (cumulative)		Met. 26 cumulative (1 annual)
1.b.1 [GI ACE] / Grants awarded and implemented for high-quality research to improve evidence of ‘what works’ to reduce corruption	29 cumulative / (2 new NODA)		Moderately exceeded. / 30 cumulative (3 new – 2 ODA, 1 NODA)
1.b.2 [GI ACE] / Number of policy briefs, reports, datasets, and working papers produced	120 cumulative / (20 annual)		Met. 125 cumulative (14 annual)
1.b.3 [GI-ACE] / Number of peer-reviewed articles submitted, in the review/ resubmission process, or published	65 cumulative / (7 annual)		Moderately exceeded. 84 cumulative / (7 annual)
1.b.4 [GI-ACE] / GI-ACE website is up to date with clear indication of why/ how research is relevant: specifically blogs & one-pagers or other project explainers, including podcasts, videos and interviews	299 cumulative / (40 annual)		Moderately exceeded. 450 cumulative / (38 annual)
1.b.5 [GI-ACE] / Total in 1.b.2 to 1.b.4 that were led by women	40%		Moderately exceeded. 52.5%
1.c.1 [SOC ACE] / Number of SOC ACE projects selected for funding: i) Total cumulative, ii) Multiyear comprehensive projects (disaggregated by PI and Research Team gender)	48 cumulative (5 new annual) / 9 cumulative (1 new annual)		Met. / 49 cumulative (6 new annual) / 9 cumulative (1 new annual)
1.c.2 [SOC ACE] / i) Number of policy research products (briefs, blogs, national press articles) and research papers (cumulative) / ii) % of research papers and evidence review papers peer-reviewed	121 cumulative (25 new annual) / 100%		Substantially exceeded. / 134 cumulative (37 new annual) / 100%

Despite some variation between partners, overall this output has been moderately exceeded. GI ACE and SOC ACE produced some major publications during the year – both academic and policy-oriented – which generated significant interest and influence. SOAS ACE’s publications were affected by the political developments in Bangladesh, which represented a great opportunity for progress on anti-corruption but also led to previous research being inappropriate for the new context.

Output 1.a.1 [SOAS ACE] The July Uprising in Bangladesh was a major opportunity for SOAS-ACE but also disrupted many planned programme activities. Much previously planned research had been designed for application to a context where only incremental change on corruption was possible. However, after the uprising and change of government, many more significant opportunities presented themselves. At the same time the wider development context changed dramatically. This meant that many existing projects had to be paused or reoriented. Some ongoing research was suspended, and resources were transferred to new research questions with potential for greater impact, thereby enhancing VfM. This has had an impact on publication dates for SOAS ACE papers. Several could not be completed within the reporting year. Several papers are planned to be issued early in the new reporting year. A full list of papers published is in the Annex.

1. Output 1.a.2 [SOAS ACE] For similar reasons to output 1.a.1, SOAS ACE’s peer reviewed publications were relatively limited this year. Nonetheless the programme met its cumulative target for journal publications by publishing one article in April 2024 – details below. In addition to this, a further paper on the Bangladesh garment industry has been resubmitted to the Journal of Development Studies.
  1. Islam MR, Angell B, Naher N, Islam BZ, Khan MH, McKee M, et al. (2024) ‘Who is absent and why? Factors affecting doctor absenteeism in Bangladesh.’ PLOS Glob Public Health 4(4): e0003040. https://doi.org/10.1371/journal.pgph.0003040.

Output 1.b.1 [GI ACE]. During the financial year GI ACE completed the contracting process for two ODA projects (led by Exeter University and RUSI) and commissioned one new NODA project (led by Tena Prelec). Also, a new theme of state capture was added to the current programme of research. Under this theme, Liz Dávid-Barrett will lead a project on ‘building resilience to state capture’. Following a competitive call, one further project is planned to be added to the theme, led by Caryn Peiffer at Bristol University.

Output 1.b.2 [GI ACE]. Fourteen policy briefs, reports, datasets, and working papers were produced during the reporting period, which met the cumulative milestone for this indicator. Full details are provided in the Annex, but highlights from this year include:
  - In June 2024, Paul Heywood and Mark Pyman published their open access book Sector-based Action against Corruption, which builds on a past GI ACE working paper. The book has attracted a good deal of attention, including over 18k downloads, and the authors have been invited to present to the World Bank and the Swedish International Development Agency.
  - In February 2025, John Heathershaw, Tena Prelec and Tom Mayne published Indulging Kleptocracy: British Service Providers, Postcommunist Elites, and the Enabling of Corruption. This work partly draws on several years of research completed under Global Integrity ACE, and was included under Foreign Affairs ‘Best Books of 2024’ list.
  - In June 2024, GI ACE published From Secrecy to Scrutiny: A new map of illicit global financial networks, a briefing paper highlighting Dan Haberly’s research into global illicit financial flows, including a large-scale shift from the UK to a ‘Dubai-Kong axis’ as the central hub in many different types of sanctioned and criminal networks. This publication garnered significant press coverage, and was featured in both the Financial Times’ The Banker and by the International Consortium of Investigative Journalists (ICIJ).

Output 1.b.3 [GI ACE]. Seven journal articles stemming from projects under previous phases of GI ACE were published. Highlights included:
  - “Addressing Bribery and Associated Norms in Healthcare: Results of a Behaviour Change Intervention in Tanzania” (Baez Camargo).
  - “Unethical leadership, moral compensation, and ethical followership: Evidence from a survey experiment with Chilean public servants” (Meyer Sahling)
  - “Elections and Corruption: Incentives to Steal or Incentives to Invest?” (Red Flags)

Output 1.b.4 [GI ACE]. Project explainers have been updated with new GI ACE branding and uploaded to the website. The website has also been updated with new project pages for the state capture project led by Deputy Director (Research) Liz Dávid-Barrett and the NODA project led by Tena Prelec. GI ACE researchers have appeared on the Kickback podcast to promote outputs as they come out (see here, and here). Recordings of GI ACE-led seminars and other live events are uploaded to the GI ACE YouTube. GI ACE has additionally been building out a schedule of monthly blogs. Anti-Corruption Data Collective (ACDC) have published a blog on the GI ACE website covering the Data against Kleptocracy conference they co-convened in November, and Dan Marks has written a blog about corruption risks in a changing voluntary carbon market landscape.

Output 1.b.5 [GI ACE]. GI ACE is performing well on the indicator measuring representation of women in research. Over 50% of GI ACE products were led by women. GI ACE are also working with the Interdisciplinary Corruption Research Network (ICRN) in delivering the GI ACE Fellowship scheme. This scheme is a skills- and network-building programme aimed at early career researchers from the Global South. GI ACE will support ICRN’s 2025 Forum, whose organising team this year consists mainly of female early career researchers.

Output 1.c.1 [SOC ACE]. Six new research projects have been signed this year, seeing a cumulative total of 49 projects selected for funding since SOC ACE’s outset. Two of the new projects are Evidence Review Papers (ODA), both led by Huma Haider. The first will explore the linkages between transitional justice, anti-corruption and counter-OC initiatives; the second seeks to examine the evidence on the relationship between organised crime, the environment and the welfare of Indigenous populations to inform policy thinking and responses. Two follow-on phases to previous research projects (1 NODA, 1 ODA) were agreed; these continue the work of Matthew Redhead on State Threats and Christopher Baber and Heather Marquette on interoperability and sensemaking. Finally two new research projects were agreed, one led by Kathryn Westmore (RUSI) (NODA), looking at the threat of Chinese Professional Money Laundering Organisations, and the other by Jonathan Goodhand and Patrick Meehan (SOAS CIVAD) (ODA), exploring how conflict-affected borderlands are connected to development processes and wealth accumulation in metropolitan centres, using the corridor between China and Myanmar as a case study. Jonathan and Patrick’s project is multi-year. Within these projects, of a total of eight Principal Investigators, four are female and four are male. A full list of projects signed this year can be found in Annex 1.

1. Output 1.c.2 [SOC ACE]. 37 policy research products and research papers have been produced this year, seeing a cumulative number of 134 products since programme outset. Highlights included:
  1. Matthew Redhead’s much anticipated paper ‘Old wine, new bottles? The challenge of state threats’;
  2. Eliza Lockhart’s ‘The Inside Track: The Role of Financial Rewards for Whistleblowers in the Fight Against Economic Crime’;
  3. David Lewis and Olivia Allison’s ‘Looting Mariupol: Russia’s use of illicit finance and economic crime in Ukraine’;
  4. A book by David Lewis informed by his SOC ACE-funded research on Russian IFFs, called Occupation: Russian Rule in South-Eastern Ukraine (Hurst Publishers);
  5. Two papers by the Total Peace research project team led by Felipe Botero, ‘Total Peace Policy: Between light and shadow’ and Juanita Duran, ‘Institutional architecture of Total Peace: A normative review studied in practice’.

1. Five academic journal articles were published this year. These were:
  1. Maria Nizzero’s SOC ACE research on sanctions and kleptocracy, ‘Illicit Finance as a National Security Threat: Balancing security and unintended consequences’ in The RUSI Journal, Vol.169, No.06, pp.64-76.
  2. A further article from the co-funded Medellin demonstration project led by Christopher Blattman et al., ‘Gang rule: Understanding and Countering Criminal Governance’, The Review of Economic Studies, 5 September.
  3. Two articles from Nic Cheeseman and Caryn Peiffer, ‘Opening the door to anti-system leaders? Anti-corruption campaigns and the global rise of populism’, in the European Journal of Political Research, and ‘Getting the message right: what are the impacts of counter-serious and organised crime awareness-raising strategies?’, in the journal Behavioural Public Policy.
  4. Sami Bensassi and Raz Arisyi’s article in the journal Economica, ‘Combatting trade-related fraud: Do the Financial Action Task Force Recommendations Bite?’.

The year has also seen six podcasts (2 ODA, 4 NODA), two videos (NODA), and five blogs/articles (4 ODA, 1 NODA). These included an article by Benjamin Lessing in the August edition of The Economist on using incentives rather than brute force to tackle cartels. Full details of all publications, policy briefs and working papers are provided in the Annex.
Changes to this output during the past year, and any planned changes

Milestones and targets need to be agreed with FCDO for the remainder of the programme. A review of the results framework will be conducted including reviewing the ambition and consistency of this output.

Output 2	Stakeholder engagement throughout the research and capacity building of research partners and stakeholders
			Output Score		A
Impact weighting	40%		Weighting revised since last AR?		No
Indicator(s)		Milestone March 2025		Progress
2.a.1 [SOAS ACE] / Number of sector specific corruption and governance diagnostics developed based on new evidence of corruption drivers and mechanisms		0 (1 diagnostic toolkit already completed in previous years)		N/A. ‘How to’ guide further updated
2.a.2 [SOAS ACE] / Active learners (a key indicator of those who engage with some parts of the course and acquire the skills that those weeks provide) from the total number of MOOC participants		175		Substantially exceeded. / 1468 active learners cumulative / (498 annual)
2.a.3 [SOAS ACE] / Number of workshops and public events held with key stakeholders where ACE research findings are disseminated. (Cumulative from 2021)		115 (cumulative)		Moderately exceeded. / 147 cumulative / (41 annual)
2.a.4 [SOAS ACE] / Extent to which a range of stakeholders are engaging with research produced by SOAS-ACE through the programme's website / learning platform.		15,000 active users per annum		Substantially not met. 9,400 active users
2.a.5 [SOAS ACE] / Evidence that ACE research is being disseminated in accordance with a flexible and adaptive media and social media strategy.		1800 followers on X		Met. / 1576 users on X, but mitigated by major media engagement in Bangladesh including 5 newspaper articles and 3 TV show appearances.
2.b.1 [GI-ACE] / Number of engagement events (speeches, engagements, panel appearances, participation in workshops, requests for input, etc.) & resultant feedback.		529 cumulative / (70 annual)		Moderately exceeded. / 582 cumulative / (75 annual)
2.b.2 [GI-ACE] / Assessment of website traffic (# visitors), newsletter engagement rates (% opens)		35% newsletter open rate / 1.5k unique visitor per month		Moderately not met. / 57.1% newsletter opens (one newsletter) / 1133 active users per month
2.c.1 [SOC ACE] / Number of HMG events & engagement activities – (seminars, participation in workshops, briefings, requests for input into strategies, programmes etc.)		108 / cumulative / (15 / annual)		Substantially exceeded. / 143 cumulative (41 annual)
2.c.2 [SOC ACE] / Number of external events and engagement activities (speeches, engagements, panel appearances, participation in workshops, request for input etc.)		62 / cumulative / (15 / Annual)		Substantially exceeded. / 79 cumulative (34 annual)
2.d [ACE Programme Level] / Number of joint initiatives by SOAS and GI that advance ACE’s agenda (workshops, joint publications, data sharing) (non-cumulative)		No new milestone. 3 products originally due to be achieved by March 2024 to be completed by March 2025		Substantially not met. One pan-ACE brochure has been produced but no other products completed.

Again, with some significant variations, overall this objective has been met. There was substantial overachievement against key engagement targets for all three partners. GI ACE and SOC ACE were involved in a large number of engagement events, and for SOAS ACE the year was dominated by dramatic interest in their research and analysis of corruption in Bangladesh following the uprising and political transition. Performance was generally weaker on websites, newsletters and social media. Also, two out of three planned pan-ACE products remain uncompleted with differences between partners about their aims and purpose.

Output 2.a.1 [SOAS ACE]. In the previous year, SOAS ACE had developed a “How To” guide which set out how to implement its approach to designing anti-corruption reforms (the Power-Capabilities-Interests approach which focuses on identifying policy reforms which are likely to work within a particular political economy context). Following the production of a ‘beta’ version of the guide in March 2024, this reporting year SOAS ACE held 3 consultation workshops to discuss and get feedback from over 35 key target stakeholders including FCDO, other donors, NGOs and consultancies working in the anti-corruption field. The guide was well received and SOAS ACE received valuable feedback. Significant areas of feedback included areas to improve framing and readability; more input on required skills/resources; and some forward-looking insights on areas in which the SOAS ACE approach could be useful beyond anti-corruption – such as to address policy implementation gaps. SOAS ACE revised the “How To” guide in response to this feedback and it was published on 28 March 2025.

Output 2.a.2 [SOAS ACE]. SOAS ACE launched the “Making anticorruption effective” online course at the start of January 2023. During the reporting year, 493 active learners participated in the course.[2] This is down from 970 active learners in the previous reporting period. This lower engagement with the course is likely to be due partly to the reduced promotion of the course following its initial launch; and partly also as those on SOAS ACE mailing lists who are interested in the course are likely to have participated already in previous years. In 2025-26, SOAS ACE aims to update the online course, and create a new area of the website to link it to the SOAS ACE “How to” guide, toolkit and promote them as a package of resources to help stakeholders engage with and make use of the SOAS ACE approach.
[2] Active Learners are defined as “those who have completed at least one step at any time in any course week, including those who go on to become Leavers. Completion varies by step type, with some requiring additional user interaction (e.g. “mark as complete”) while others are completed through submission (Assignment, Review) and question attempts (Quizzes & Tests). Also presented as a percentage of Learners”.

Output 2.a.3 [SOAS ACE]. SOAS ACE substantially exceeded the target of 115 cumulative workshops, meetings and events, with 41 this year, leading to a cumulative total of 147. In particular, the Bangladesh uprising and change in government led to a dramatic increase in interest in SOAS ACE research. PI Mushtaq Khan and the wider research team found themselves called on for advice and insight by a large range of parties including NGOs, donors, and student organisations. The huge extent of corruption involving the previous regime had come to light, and these organisations wanted to draw on SOAS ACE research in order to learn lessons and inform their actions in relation to governance and corruption in the country. SOAS ACE shared objective analysis and evidence with everyone who reached out at a time of great uncertainty. There were substantial engagements with organisations including Transparency International (global), Al-Jazeera, the Financial Times, the International Centre for Asset Recovery, the National Crime Agency (UK), Department of Justice (US), US Agency for International Development, Swedish International Development Agency, the Swiss Embassy Dhaka, the Stolen Asset Recovery programme, the UN Fact Finding Mission, the Bangladesh Bank, the Bangladesh Anti-Corruption Commission, and various government Advisors (Ministers).

In addition to this, SOAS ACE and Mushtaq Khan were invited on several occasions to work with key change agents in Bangladesh: the students. Student objectives included changing the political settlement by changing the distribution of power in the country and taking on the all-pervasive corruption that had destroyed the economy. In this context, SOAS-ACE research and the political settlement analysis became relevant and important for the student movement. Mushtaq Khan addressed students on five occasions as sole or keynote speaker. His first address to students in August 2024 went viral on various Facebook pages with views exceeding 500,000 in a few weeks.

Outside of the Bangladesh context, there were also a series of other presentations and events featuring SOAS ACE research. These included lectures at the International Anti-Corruption Academy (IACA) in Laxenberg, Austria; an invitation by the Institute of Strategic Studies (ISS) in South Africa to present virtually to senior South African bureaucrats working on compliance and regulation; briefings for Embassies in Nigeria and Bangladesh; keynote lectures at Indian universities; and presentations at academic conferences.

Output 2.a.4 [SOAS ACE]. SOAS ACE did not meet its target of 15,000 active users per year to the website and learning platform. This year there were 9,400 active users – this is likely because the team were unable to publish many research outputs throughout the course of the year due to the significant disruptions surrounding the Bangladesh Monsoon Revolution. As research outputs are now being published again, it is expected that website traffic should pick up. SOAS ACE is also in the process of making some improvements to the website which will improve usability and provide a new section which brings together methodological outputs such as the online course, how to guide and toolkit.

Output 2.a.5 [SOAS ACE]. During the reporting year, SOAS ACE made the decision to deprioritise the use of X (formerly Twitter) as key audiences have moved away from the platform. They are now prioritising LinkedIn as a channel which can reach target audiences. The current output indicator relates to X (Twitter) and has not been met this for this year with 1576 followers against a target of 1800. SOAS ACE has 858 followers on LinkedIn and will look to build this over the coming years.

In addition to this, SOAS ACE has this year significantly engaged with media in Bangladesh including various newspaper articles and TV appearances. As the situation in Bangladesh developed, PI Mushtaq Khan published five articles in newspapers including Bonikbarta, Shomokal and Prothom Alo (in Bengali/ Bangla) and the Daily Star (in English). Additionally, an interview with him was also published in both English and Bengali in Prothom Alo. He also featured in three television interviews/ talk shows including on Jamuna TV and Tritiyo Matra Channel. These articles and appearances are not counted against logframe data but were also an important route for SOAS ACE research to have influence in the rapidly developing context in Bangladesh.

1. Output 2.b.1 [GI ACE]. Amongst the 75 engagement events carried out this year, highlights included:
  1. GI ACE Programme Director Paul Heywood gave the keynote speech at the 2024 Australian Public Sector Anti-Corruption Conference (APSACC) on the subject of public integrity;
  2. Paul Heywood and Tom Shipley delivered a workshop for the Consortium for Elections and Political Process Strengthening (CEPPS) on designing a corruption typology for electoral processes in January 2025;
  3. GI ACE Deputy Director (Research) Liz Dávid-Barrett and Paul Heywood took part in a National Risk Assessment Academic Engagement one-day workshop, held at the Home Office in August 2024;
  4. Liz Dávid-Barrett spoke on a panel on detecting corruption risks in public procurement at a conference organised by Guatemala’s national anti-corruption commission;
  5. Various GI ACE partners delivered seminars, workshops and briefings for FCDO and wider Government colleagues, including Liz Dávid-Barrett and Dani Kaufmann, Dan Haberly and John Heathershaw;
  6. GI ACE attended the International Anti-Corruption Conference in Lithuania, with a dedicated information stall, and co-hosted a panel at the OECD Global Anti-Corruption and Integrity Forum.
  7. GI ACE partners ACDC, Exeter, OCCRP and the National Endowment for Democracy convened a Data against Kleptocracy conference in November, which brought together a range of investigators from academia, civil society and investigative journalism, and explored the opportunities and challenges in cross-border investigations into illicit financial flows and kleptocracy using leaked, commercial and public data sets.

Output 2.b.2 [GI ACE]. This indicator is moderately not met as, firstly, the website did not see increases in active users as anticipated, and secondly, only one newsletter was issued during the reporting year. The GI ACE website saw an average of 1,133 active users per month in the period 1 September 2024 to 31 March 2025 – which was a similar level to last year. The busiest month on the website was October, when the call for expressions of interest under the state capture theme was first running. One GI ACE newsletter was released during the year, at the end of March 2025; it achieved an open rate of 57.1%. The average engagement per GI ACE-related post on LinkedIn was 8.73%, significantly higher than the average engagement rate across the platform of 3.85%. In addition, GI ACE’s average engagement score for Bluesky was 4.55% (platform-wide average engagement scores for Bluesky are not yet available).

Output 2.c.1 [SOC ACE]. SOC ACE substantially exceeded its milestone target for engagements with HMG this year, seeing 41 engagements and events undertaken, resulting in a cumulative total of 143. Full detail is provided in the Annex, but key highlights include:
- In July, Eliza Lockhart was invited to deliver a joint briefing on her research to civil servants from the Department of Business & Trade, Home Office Joint Anti-Corruption Unit, and HM Treasury. Feedback from participants explicitly stated how the research will inform whistleblowing policy decisions.
- 18 and 19 September the SOC ACE Researcher Conference was held at the University of Birmingham. 11 sessions were held over the two days covering state threats, peace processes and stabilisation, illicit financial flows, innovations in data, measurements, and methods in researching Serious Organised Crime. Representatives from FCDO, National Crime Agency, and other ACE partners attended the conference.
- On 16 September, Benjamin Lessing provided a briefing to representatives of the National Crime Agency and FCDO on ‘How not to fight corruption’, drawing on findings from the Medellin demonstration project.

Output 2.c.2 [SOC ACE]. SOC ACE substantially exceeded its milestone target for engagements with HMG this year, seeing 41 engagements and events undertaken, resulting in a cumulative total of 143. Full detail is provided in the Annex, but key highlights include:
- SOC ACE Director Heather Marquette and Tom Keatinge participated in a RUSI-coordinated workshop titled, ‘Combatting Modern Kleptocracy: Assessing the Impact of Two Years of Sanctions on Russia’ at the International Anti-Corruption Conference (IACC2024) in Vilnius, Lithuania.
- David Lewis and Tena Prelec participated in a roundtable at the Central and Eastern European Schools Association - International Studies Association (CEEISA-ISA) Conference, titled ‘Illicit Finance, Transnational Corruption, and Informal Economies in Contemporary Conflict’.
- Heather Marquette and Caryn Peiffer held a two-day workshop titled, ‘Functionality of Corruption and Organised Crime’, which brought together a group of 20 multidisciplinary experts – academics, practitioners and policymakers. FCDO and Home Office colleagues also participated, including chairing sessions.
- The launch event for Matthew Redhead’s paper ‘Old wine, new bottles? The challenge of state threats’, was attended by over 100 people from across the UK and international policymaking, practitioner and academic circles, as well as MPs and journalists. The event resulted in press coverage by iNews and several requests for further engagements
- Alexander Kupatadze and Heather Marquette met with EUROPOL to introduce SOC ACE’s work and to share research findings from a forthcoming paper on Serious Organised Crime, smuggling, trade-based money laundering and other displacement effects from Western sanctions on Russia following its invasion of Ukraine.

Output 2.d. In the 2024 annual review, three Pan-ACE products (health, illicit finance and a pan-ACE explanation product) had not been completed and were due for completion in 2024/25. Of these three products, one has been completed: the pan-ACE brochure. The other two remain unfinished. Work was done on both the IFF and health synthesis products during the year, but they have not yet been agreed across ACE partners. There is significant demand for the IFF synthesis product within FCDO, but this has faced substantial differences of opinion between ACE partners about its aims and purpose, and it has not yet been possible to agree a way forward.

Changes to this output during the past year, and any planned changes

Milestones and targets need to be agreed with FCDO for the remainder of the programme. A review of the results framework will be conducted including reviewing the ambition and consistency of this output.
## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the Business Case

The key cost drivers from the Business Case remain valid and currently are the cost of research personnel, the research uptake activities, management costs and monitoring costs. The partners are achieving VfM by operating within the Economy, Efficiency, Effectiveness and Equity, to demonstrate how VfM has been achieved from input to outcome and impact.

Assessment of whether the programme continues to represent value for money

The programme continues to represent good Value for Money (VfM). Outputs are delivering against the logframe targets and maintaining processes which consider Value for Money when funding new or existing projects.

Economy
- GI ACE negotiated and oversaw a migration of the GI website to a new domain with new hosting options. GI ACE secured a five-year domain purchase and hosting plan with Pantheon for a total cost of £15,066, including a capped year-on-year fee increase. GI ACE reviewed alternative website hosting options during the procurement process, and awarded the contract based on both product quality and price, saving over £6,000.
- SOC ACE research teams work effectively with researchers in countries of focus to reduce travel and logistics costs where feasible. Modelled savings based on the field trips undertaken within projects funded by SOC ACE (the Total Peace research project, the Balochistan research project, and the “Under the Radar” research project) amount to £13,486.00. These savings were calculated by comparing the costs of engaging local researchers instead of international researchers travelling to the project areas.
- SOC ACE undertook procurements with both cost and quality evaluation criteria to ensure best value. By using a three-quote process which allows different options to be weighed up, £6000 has been saved on event venue hire as well as 2p per word on proof-reading services.
- SOC ACE brought a grant to an early close where the outputs planned were non commensurate with the approved budget. This reduced the value of the grant to a level proportionate with the final research output, saving £48,651.45.
- GI ACE successfully negotiated a reduction in overheads charged by the University of Birmingham to increase Professor Cheeseman’s time allocation the project from 10% to 13% at no extra cost, providing him more time to work on the project as co-lead conducting fieldwork, empirical analysis, and write up.

Efficiency
- SOAS ACE outsources specific expertise such as editorial and communications to avoid staff costs if input is not needed regularly. In the past year, SOAS has saved £45,668 by utilising its communications consultant rather than recruiting a full-time staff member.
- GI ACE meets grantees regularly to discuss project management and resolve any potential issues. GI ACE has developed and implemented a new quarterly meeting to surface common challenges, identify synergies and share learnings.
Recruitment of a full GI ACE team has allowed effective monitoring of downstream activity. GI ACE was able to identify and respond quickly to emerging concerns with a project’s research approach and reporting delays.
SOC ACE Director’s established networks and relationships within HMG enables SOC ACE to engage with key stakeholders across HMG at pace, reducing management time and opportunity cost. Whilst the cessation of the Director’s role as a Senior Research Fellow has had an impact on efficiency, it has been limited by the strong relationships nurtured beforehand, demonstrated through exceeding the target for engagements this year.

Effectiveness
- GI ACE is ensuring that ‘legacy’ projects from previous rounds of the DFID/FCDO ACE programme can continue to remain live in relevant policy forums and through further dissemination. GI has worked with FCDO and the authors of Indulging Kleptocracy to produce an update note for FCDO on key messages and recommendations from the book, and to facilitate a briefing by the authors to HMG.
- The GI ACE funded work conducted by Dan Haberly under the Offshore Financial Secrecy Reform project continues to gain attention, both from policy makers and the media. The Secrecy to Scrutiny briefing event led to invitations to brief FCDO and Home Office, with the former using Dan’s sanctioned entity network data to contribute to their analysis on sanctions on Iran. The briefing was also covered in the FT’s The Banker and by the International Consortium of Investigative Journalists (ICIJ).
- SOC ACE funded work by Eliza Lockhart on rewards for economic crime whistleblowers ensured that foundations for research uptake and conversion of outputs into outcomes is agreed early and that relationships with interested stakeholders was maintained effectively. To date, 22 media outlets have published reports on the research following its publication and launch event and Eliza continues to be invited to speak on panels and present at events. This is also being done through more formal means, such as RUSI’s establishment of a SOC SSR Task Force, and SOAS CIVAD’s Policy Lab that bring stakeholders together to strengthen the relevance and quality of research outputs to achieve high impact. For example, participants suggested that case studies on responses to paramilitarism would be useful in helping them to apply research findings in their day-to-day work. As a result, three case studies have now been prepared as part of the projects research outputs. The communications efforts around this research have likely contributed significantly to the decision by the Government to introduce of a cash reward scheme for whistleblowers.
- SOAS ACE identified climate infrastructure and corruption in renewable energy projects as potentially high impact areas for anti-corruption in Bangladesh. Research by SOAS demonstrated that by making climate infrastructure dual use, corruption can be significantly reduced in the construction of this infrastructure.
- SOAS effectively targets its findings to influence actors relevant to their research, for example, Mushtaq Khan and Pallavi Roy have been working with a range of government, civil society actors, development partners and the private sector in Bangladesh to incorporate insights and analysis into strategies for supporting reform following the collapse of the Awami League regime in Bangladesh. For example, Mushtaq Khan has advised the students movement on how changing the constitutional rules is insufficient with regard to improving governance and reducing corruption, and that this will require shifts to the organisational power structures of government.
- GI ACE has trialled incorporating a civil society ‘impact partner’ to help disseminate the research findings. This has led to a number of fruitful conversations, most notably from Open Contracting Partnership (OCP) and Government Transparency Institute and have expressed interest in collaborating with both as an impact delivery partner. There is scope here for OCP to support impact work across their global and local communities as well as integrate findings into their own programming work.
- The two Global Public Procurement datasets co-funded under the GI ACE Red Flags project and made available for scientific use continue to garner significant attention, having been downloaded a total of 1,012 times since being published in March 2024.

Equity
All SOAS ACE research projects are collaborations and there is a PI from both SOAS and the partner who is a “co-PI” and intellectual leads for the projects. Out of a total of 17 co-PIs, 47% of co-PIs are women.
- This year, GI ACE has surpassed the 40% target for research products to be led by women; in total, 52.45% of all outputs produced led or co-led by women. After the addition of the new theme of state capture, 40% of current ODA projects under GI ACE are now led by women.
- As part of GI ACE’s commitment to research capacity building, it has launched the GI ACE Fellowship scheme in partnership with the Interdisciplinary Corruption Research Network (ICRN). This scheme is a skills and network-building programme aimed at ‘early career researchers’ from the Global South. It will consist of a series of workshops aimed at building research skills, supported with mentorship from GI ACE’s network of researchers. GI ACE put out a call for applications to join the GI ACE Fellowship via the ICRN’s established process for applying to present at their annual Forum, under a newly established panel called ‘New ideas from the Global South’.
- Over the span of SOC ACE, of the 49 projects, 27 have been led by woman PIs and 23 led by men. Across these 49 projects, 32 of the research team members have been women and 46 were men (excluding PIs).

Cost Effectiveness
ACE partners have delivered value for money by maintaining processes which allow the partners to continue to fund high impact projects whilst ensuring that costs are sustainable.

E: RISK

Overview of risk management

The overall risk for ACE is major. This is broken down as follows:
Strategy and Context	Policy and Programme Delivery	Public Service Delivery & Operations	Safeguarding	Financial and Fiduciary	Reputational	People
Major/ Possible	Major/ Possible	Moderate/ Unlikely	Moderate/ Unlikely	Moderate/ Possible	Moderate/ Unlikely	Moderate/ / Unlikely

Policy and Programme Delivery.

Risk: Variability in Delivery Partner Performance and Decision-Making. The programme relies on the performance and judgment of multiple delivery partners, which creates an ongoing risk around the quality and timeliness of delivery, financial compliance, and overall value for money. These risks have been mitigated through proactive engagement which allowed issues to be understood and addressed by the leading ACE partners and swift, appropriate action being taken. For example, organising an in-person visit and providing close technical support regarding financial reporting in line with FCDO standards and developing an action plan which subsequently led to improved performance. This highlights both the risks and benefits of devolved delivery responsibility, and the importance of maintaining strong oversight and open dialogue to support partners and enable informed course correction where needed.

Risk: Fragmentation of Research Outputs Across Delivery Partners. The programme is delivered by three academic institutions conducting research on anti-corruption, each with distinct thematic focuses and methodologies. While this diversity is an intentional design feature and a core strength of the programme, there remains a risk that outputs are not sufficiently synthesised or positioned to influence the wider anti-corruption evidence and policy agenda. However, efforts have been made to address this risk. Notably, the development of a pan-programme brochure represents strong progress in communicating the programme's collective contribution and improving visibility of cross-institutional work. In addition, a pan-programme workshop is planned during the reporting year, which is expected to further encourage knowledge exchange and complementarity between partners. Continued monitoring will be important to ensure that opportunities for strategic collaboration are captured, while maintaining the academic integrity of each institution’s approach.

Financial and Fiduciary.

Budget Uncertainty and Delays in Funding Releases by FCDO. One key financial risk stemmed from delays in receiving clear budget allocations and uncertainty around the timing of FCDO’s funding releases. This created significant challenges for the programme in terms of cash flow management and financial planning. The uncertainty surrounding the budget made it difficult to forecast expenditure accurately, which in turn caused delays in the disbursement of funds to partners. These delays had a knock-on effect on the programme’s ability to maintain a smooth operational flow and could have jeopardised timely implementation of planned activities.

To mitigate this risk, the programme engaged with FCDO’s finance team to establish clearer communication and agree on timelines for funding releases. Although these efforts have resulted in some improvement, further work is needed to ensure more predictable financial flows in the future. Continued dialogue with FCDO and closer monitoring of funding releases will be necessary to reduce the impact of budget uncertainty.

Fraud and Financial Management. Fraudulent misappropriation of funds by lead and downstream partners is something that is closely monitored as part of the programme management, both by FCDO and programme partners. ACE partners submit detailed financial reports which are reviewed quarterly as well as on an ad hoc basis where necessary.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery Performance
The programme has made significant progress regarding delivery in the past year. Across the three strands of the programme, ACE have consistently met or exceeded their Outcome and Output milestones set out in the logframe. The evidence shown across the Outcome and Output sections in this review demonstrates ACE’s ability to produce research that directly or indirectly influences policymakers in FCDO, HMG and other key stakeholders beyond. Across the programme, ACE has delivered by exceeding Output milestones.
Progress Against Milestones:

As of 11/04/25, 21/26 (81%) of the agreed Outcome and Output milestones have been completed. Notable achievements include SOC ace publishing 37 policy research products (briefs, blogs, national press articles) and research papers, SOAS ACE having 498 active learners on its “Making anticorruption effective” online course, and GI ACE achieving 75 key engagements in the year.
Challenges and Solutions:
While the project has progressed largely as planned, there have been some challenges faced across the programme. There have been some difficulties with downstream partners and funded projects underperforming. This is not uncommon in programmes where there are a large number of partners and projects involved. Crucially, these issues have been recognised and managed effectively, either by taking appropriate steps to work with partners to understand the reasons for the issues and taking appropriate steps to engage and ensure that actions are taken to improve performance, or where necessary, by taking difficult decisions to withdraw funding that would ultimately be better spent elsewhere.
Quality of Deliverables:

The quality of outputs has been high, with positive feedback received from key stakeholders. Some examples of this include:
- Feedback from the Office of the Comptroller General (CGU) of Brazil, stating that Paul Heywood’s research was ‘especially valuable’ and had had a significant influence on the development of the CGU’s Integrity and Anti-Corruption Plan 2025-2027.
- Mushtaq Khan being invited to join the National Committee on Re-Evaluating Power Sector Contracts in Bangladesh based on a recognition of the SOAS-ACE research on corruption in power sector contracts in Bangladesh;
- Dan Haberly’s research on illicit finance funded by GI ACE prompting several briefings across HMG, as well as being featured in the Financial Time’s “The Banker”.

Alignment with FCDO Objectives:

ACE is well-aligned with FCDO objectives:
- Growth: ACE invests in networks of researchers which put UK universities at the forefront of research on what works to tackle corruption. Understanding flows of global illicit finance supports a positive growth agenda domestically and internationally.
- Security: Addressing illicit financial flows and serious organised crime contributes to the FCDO's priority of enhancing security and resilience. ACE's research on beneficial ownership and anti-money laundering provides insights into how illicit financial activities can be curtailed, thereby strengthening financial systems and governance.
- Development including climate: ACE focuses on ways to improve the effectiveness of health, education, infrastructure and climate investments. For example, ACE's research in Nigeria and Bangladesh focuses on improving public procurement processes and climate projects which can lead to better allocation of resources and enhanced public service delivery.
Financial Performance
The programme has maintained transparency and accountability in its financial management. SOAS, the University of Sussex and the University of Birmingham each submit their claims for funds quarterly in arrears based on actual spending against a forecast of their predicted spending pattern, showing ODA and NODA separately, to minimise any financial risk. Payments are based on actual expenditure against the approved grant budgets. The quarterly claims are confirmed against the forecast amounts shortly before the end of each quarter with a justification for any differences being provided in the narrative report supporting the invoice. Subsequent forecasts are adjusted to update the total annual forecast as necessary.
Financial Statements and Budget Tracking:

The programme’s financial status remains in line with the approved budget. Where necessary to accommodate changes in direction of the research funded across the programme, ACE partners have communicated this need to FCDO and provided full transparency, allowing FCDO to consider options and make decisions such as agreeing Accountable Grant Amendments or deciding that unfortunately it is not possible to make changes to the budget due to budget uncertainty.

Across the programme, there have been some minor difficulties created by forecast underspend and overspend. However, in a similar vein, these have been communicated to FCDO transparently.

ODA
2024/2025	Budget	Actual	Underspend	Variance
SOAS University of London	£969,668.13	£919,686.89	£49,981.24	5%
GI University of Sussex	£1,103,881.00	£980,452.00	£123,429.00	11%
University of Birmingham	£1,090,672.74	£900,870.77	£189,335.97	17%
Total	£3,164,221.87	£2,800,009.66	£364,746.21	11.5%

NODA
2024/2025	Budget	Actual	Underspend	Variance
SOAS University of London	£0	£0	N/A	N/A
GI University of Sussex	£200,000.00	£57,576.00	£142,424.00	71%
University of Birmingham	£650,000.00	£644,683.70	£5,316.30	1%
Total	£850,000.00	£702,259.70	£147,740.30	17%

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Regular engagement with delivery partners has been a key feature of the programme’s MEL approach. This includes both individual and collective meetings, providing space for focused discussion on progress, challenges, and emerging risks. During the reporting year, a new approach to partner engagement has introduced monthly check in meetings that have been useful and will allow for more effective communication between FCDO and ACE partners going forward. These meetings have provided space for discussion around strategic direction of research and the current state of play with ongoing projects, finances, and briefing of seniors in FCDO.

Evidence

ACE provides external, independent, rigorous research with a long-term funding commitment that allows it to produce a large body of evidence over time as a global public good. ACE directly informs FCDO and HMG strategy, policy, operations and programming, with impact around the world.

Learning

There is a strong focus in ACE on learning, and this is reflected in the Annual Review which includes partners’ and FCDO’s reflections. Extensive lessons from the implementation of the programme over the course of the past year are articulated at the front of the Annual Review, see Lessons.

The main learning from ACE is the anti-corruption research and evidence itself, which is shared in the journal articles, newsletters and websites, academic conferences and policy engagement. This is shaping the field in the ways articulated in this Annual Review.

Date of last narrative financial report	SOAS – 11/03/2025 (Q3) / UoB – 05/03/2025 (Q2) / UoS - 30/04/2025 (Q4)	Date of last audited annual statement	SOAS – 06/05/2025 / UoB - 26/03/24* / UoS – 28/02/2025

The figures in the table are indicative considering that FCDO has not received Q4 actual spend figures from all ACE partners.

* UoB is in the process of completing its 2025 audited annual statement at the time of the submission of this Annual Review

Annex 1

SOAS ACE Indicators and Results FY2024/5

SOAS ACE 1.a.1 Working papers and policy outputs
#	Title	Authors	Type	Pub date
1	Resource leakages in primary schools in Bangladesh: Do horizontal checks have an effect on the quality of governance?	Mushtaq Khan, Mehnaz Rabbani, Faruq Hossain, Rabeena Sultana Ananna	Working paper	31/03/2025
2	Improving energy access for SMEs in Abuja through horizontal checks and cooperative ownership: a scoping survey	Pallavi Roy, Najim Animashaun, Adebayo Olajide, Henry Adigun, Rahila Thomas	Working paper	31/03/2025
3	Peer-to-peer enforcement among businesses to assure electricity payment in Nigeria: a lab-in-the-field experiment	Mariona Tres Vilanova and Pallavi Roy	Working paper	31/03/2025
4	Political Corruption, Material Interests and Social Norms	Cathy Shutt	Blog post	28/02/2025
5	Political corruption and enforcement: How to amplify demand without increasing risks?	Cathy Shutt	Working paper	28/03/2025
6	Navigating the Political Economy of Corruption: Observing and understanding actors’ behaviours, to inform effective policy	Alan Hudson, Kathy Bain, Mushtaq Khan, Pallavi Roy and Duncan Edwards	Working paper/toolkit / (Our How To Guide)	28/03/2025
7	Process Mapping Report: Documenting the Health Intervention of the Anti-Corruption Partnership in Bangladesh	Md. Noorunnabi Talukder	Working paper	31/03/2025

SOAS 2.a.3 Number of workshops and public events held with key stakeholders where ACE research findings are disseminated.

#	Event	Date
1	Pallavi Roy invited by Institute of Strategic Studies (ISS) in South Africa to present virtually to senior South African bureaucrats working on compliance and regulation on the topic of “The Theory Behind Standard Anti-Corruption, and the Reality”.	22/05/2024
2	Pallavi Roy recorded an interview with the ISS which was broadcast at a separate event for civil society “Driving Justice – how to ensure effective anti-corruption in South Africa”	28/08/2024
3	Pallavi Roy delivered two lectures at the International Anti-Corruption Academy (IACA) in Laxenberg, Austria as part of their Summer School for Alumni. The topics were “Illicit Financial Flows: The challenges of measurement and its implications” and “Politics Development and Corruption”. Both of these significantly highlighted SOAS-ACE research.	06/05/2024
4	Mushtaq Khan and Pallavi Roy continued their lecturing engagements with IACA for the Masters’ course, where they presented SOAS-ACE case studies as well as introduced the PCI framework in detail.
5	As part of her work as PI for the political economy scoping project in Nigeria, Pallavi Roy presented to the Nigerian High Commissioner and the senior leadership team in Abuja, including recommendations informed by SOAS-ACE research	05/06/2024
6	Mushtaq Khan and Pallavi Roy were invited to be discussants at the annual conference of the Bangladesh Studies Network where they presented on ongoing SOAS-ACE research including the 'Bangladesh Big Bang’ research project on the unintended consequences of ‘shock’ implementation of good governance reform	01/07/2024
7	Pallavi Roy chaired a session on ‘Politics and Development’ at the annual conference of the European Consortium for Political Research in Dublin where she introduced the PCI framework as a critical addition to political economy frameworks	12 – 15/08/2024
8	Pallavi Roy was the keynote speaker at the inaugural international conference at India's Azim Premji University campus in Bhopal. Her address titled “The Interaction of Identities, Narratives, Institutions, and their Outcomes” drew on SOAS-ACE's ongoing research into the Monsoon Revolution in Bangladesh.	16/01/2025
9	Pallavi Roy was invited to deliver a lecture by Presidency University in Calcutta, India on the Monsoon Revolution in Bangladesh. Titled “State Capture by Narrative: A Case Study of the Monsoon Revolution in Bangladesh”, the lecture drew heavily from SOAS-ACE research.	05/03/2025
11	Pallavi Roy joined a podcast designed by ABT Global on systems thinking in international practice. She shared insights implementing political economy analysis to improve development programmes using successful cases studies from SOAS-ACE	24/02/2025
12-33	Work with anticorruption NGOs, government ministries and agencies, international donors, and legal firms in Bangladesh. In the post-uprising context in Bangladesh, the massive extent of corruption involving the previous regime came to light. A large number of international NGOs, legal firms, international partners, and media outlets became interested in assisting Bangladesh and understanding what happened to learn lessons. The SOAS-ACE research team was a key resource point for many of these conversations and assisted a large number of initiatives. The team shared objective analysis and evidence with everyone who reached out at a time of great uncertainty. There were substantial engagements with the following organisations which were each met at least once: Spotlight, Transparency International (global), Al-Jazeera, the Financial Times, Restitution, the Mintz Group, the Sentry, White Case, Boies Schiller, Keystone Law, Ankura, International Centre for Asset Recovery, the National Crime Agency (UK), Department of Justice (US), US Agency for International Development, Swedish International Development Agency, the Swiss Embassy Dhaka, the Stolen Asset Recovery programme, the UN Fact Finding Mission, the Bangladesh Bank, the Bangladesh Anti-Corruption Commission; as well as various government Advisors (Ministers)	06/2024 - 03/2025
34-38	University lectures/seminars in Bangladesh. Mushtaq Khan was very involved in working with and informing students and student leaders during the period of the uprising. Public lectures for students where Khan was the sole or the keynote speaker include the following: / Dhaka University 20th August 2024 (two weeks after the regime collapse). ‘The Political Settlement, Reform and the Constitution’. This talk went viral on various Facebook pages with views exceeding 500,000 in a few weeks. / ‘Unity, Reform and Elections’: National Dialogue of Students and Political Parties, Dhaka 27th – 28th December 2024. Khan was Keynote Speaker. / ‘Programme for a New Political Settlement’: Khan was keynote speaker at the founding conference of the student’s new political party the Jatiyo Nagorik Party (National Citizens Party), Dhaka 5th February 2025. / ‘July Revolution and Bangladesh 2.0: the Legacy of the Private University Front’. Khan was Keynote Speaker at this conference bringing private and public universities together. 20th February 2025. / ‘Policies for Addressing Violations of Rights in Academic Institutions’, National Press Club, Dhaka 17th December 2024.	08/2024 - 12/2025
39	SOAS University of London 10th October 2024. ‘The July 2024 Bangladesh Uprising: Causes and Prospects.’ Mushtaq Khan was one of three key speakers.	10/10/2024
40-41	Two Consultations to discuss and get feedback for the SOAS ACE 'how to" guide with key target stakeholders	14/05/2024 and 16/05/2024

SOAS 2.a.5 Evidence that ACE research is being disseminated in accordance with a flexible and adaptive media and social media strategy.
#	Event	Date
1	Political Reforms and the Reality Situation: Jamuna TV 24 Hours 18th August 2024. রাজনৈতিক সংস্কার ও বাস্তবতা | ২৪ ঘণ্টা | 24 Ghonta | 18 August 2024 | Jamuna TV	18/08/2024
2	The Immediate Tasks of the Emergency Government: Tritiyo Matra Channel I, 21st August 2024. জরুরী সরকারের জরুরী কাজ | সরাসরি টকশো | পর্ব-৭৬৯০	21/08/2024
3	Driving Change: Unlocking the Potential of the Bangladesh Financial Market, Dhaka Sheraton 12 December 2024.	12/12/2024

GI ACE Indicators and Results FY 2024/25

#### GI ACE Indicator 1.b.2:
#### Reports, Working Papers, Book Chapters, Books, Policy Briefs, Case Studies, Datasets

###### WORKING PAPERS (3)
Chmura	Alysandratos, T., Barr, A., Bryce, C., Chmura, T., David-Barrett, E., & Giamattei, M. (2024). The behavioural foundations of international anti-bribery laws: Results from an international lab-type experiment. ResearchGate. Available at: https://www.researchgate.net/publication/378822110_The_behavioural_foundations_of_international_anti-bribery_laws_Results_from_an_international_lab-type_experiment.
Haberly	Haberly, D., Gullo, V., Shipley, T., Boukal, T., Palansky, M., & Barrington, R. (2024). The Regulation of Illicit Financial Flows (RIFF) dataset: A new world map of 30-years of financial secrecy and anti-money laundering reforms. Centre for the Study of Corruption Working Paper no.20. https://giace.org/wp-content/uploads/2024/12/Haberly-RIFF-full-paper.pdf.
Haberly	Haberly, D., Gullo, V., Shipley, T., Boukal, T., Palansky, M., & Barrington, R. (2024). The Regulation of Illicit Financial Flows (RIFF) dataset: Methodological details. Centre for the Study of Corruption Working Paper no.21. https://giace.org/wp-content/uploads/2024/12/Haberly-RIFF-methodology.pdf.

###### BOOK CHAPTERS (3)

GI ACE	Dávid-Barrett, E. (2024). ‘Measuring Grand Corruption’. In R. Rotberg & F. O. Hampson (Eds.), Grand Corruption: Curbing Kleptocracy Globally. Routledge. Available at: https://www.routledge.com/Grand-Corruption-Curbing-Kleptocracy-Globally/Rotberg-Hampson/p/book/9781032719337 30 Aug. 2024
GI ACE	Dávid-Barrett, E., & D’Emidio, R. (2024). ‘Curbing Corruption in Aid’. In R. M. Desai, S. Devarajan, & J. L. Tobin (Eds.), Handbook of Aid and Development. Edward Elgar. https://ideas.repec.org/h/elg/eechap/20736_8.html
GI ACE	Dávid-Barrett, E. (2024). ‘State Capture’. In S. Coroado & L. de Sousa (Eds.), Encyclopedia of Corruption and Society. Edward Elgar. Available at: https://www.e-elgar.com/shop/gbp/elgar-encyclopedia-of-corruption-and-society-9781803925790.html 2 May 2024

###### POLICY BRIEFS (3)

David-Barrett (Phase Two)	Understanding state capture: roles and responsibilities of business (2025) World Economic Forum. 09 February.
Haberly	From Secrecy to Scrutiny: A New Map of Illicit Global Financial Networks (2024) GI ACE website. 04 August. Available at: https://ace.globalintegrity.org/resources/from-secrecy-to-scrutiny-a-new-map-of-illicit-global-financial-networks-and-regulation/
Prelec	18.03.25. Gatekeepers, Enablers or Technicians? The contested role of lawyers in kleptocracy and grand corruption. Policy report - Executive Summary.

REPORTS (1)

Prelec	18.03.25. Gatekeepers, Enablers or Technicians? The contested role of lawyers in kleptocracy and grand corruption. Policy report published with Spotlight on Corruption.

###### BOOKS (2)

Heathershaw	Heathershaw, J., Prelec, T., & Mayne, T. (2025). Indulging Kleptocracy. Oxford University Press. Available at: https://academic.oup.com/book/58173 4 Feb. 2025
GI ACE	Pyman, M., & Heywood, P. (2024). Sector-Based Action Against Corruption. Springer. Available at: https://link.springer.com/book/10.1007/978-3-031-59336-9 31 May 2024

DATASETS (2)

Haberly	Haberly, D., Gullo, V., Shipley, T., Boukal, T., Palansky, M., & Barrington, R. (2024). Regulation of Illicit Financial Flows (RIFF) dataset. GI ACE. Available at: http://ace.globalintegrity.org/docs/RIFF/RIFF-Data-Dec-6-2024.csv 11 Dec. 2024
Dávid-Barrett	Dávid-Barrett, E., et al. (2024). Global Contract-level Public Procurement Dataset. Mendeley Data. Available at: https://data.mendeley.com/datasets/fwzpywbhgw/3 8 Apr. 2024

#### GI ACE Indicator 1.b.3:
#### Peer-reviewed Articles

PUBLISHED ARTICLES (6)

Dhillon	Afridi, F., Bhattacharya, S., Dhillon, A., & Solan, E. (2024). Electoral Competition, Electoral Uncertainty and Corruption: Theory and Evidence from India. Journal of Economic Behavior & Organization. Available at: https://www.sciencedirect.com/science/article/abs/pii/S0167268124002385 28 Aug. 2024
Dávid-Barrett	Fazekas, M., Tóth, B. B., Abdou, A., & Al-Shaibani, A. (2024). Global Contract-level Public Procurement Dataset. Accompanying Paper. Online (Elsevier). Available at: https://www.sciencedirect.com/science/article/pii/S2352340924003810?via%3Dihub 15 Apr. 2024
Dávid-Barrett	Fazekas, M., Toth, B., Alshaibani, A., & Abdou, A. (2024). Elections and Corruption: Incentives to Steal or Incentives to Invest? Online (Springer Nature). Available at: https://link.springer.com/article/10.1007/s12116-023-09412-0#Ack1 3 Nov. 2024
Baez Camargo	Baez Camargo, C., Gadenne, V., Mkoji, V., Perera, D., Persian, R., Sambaiga, R., & Stark, T. (2025). Addressing Bribery and Associated Social Norms in Healthcare: Results of a Behaviour Change Intervention in Tanzania. European Journal of Social Psychology. Available at: https://doi.org/10.1002/ejsp.3140 9 Jan. 2025
Meyer-Sahling	Schuster, C., Fuenzalida, J., & Mikkelsen, K. S. (2024). Unethical leadership, moral compensation, and ethical followership: Evidence from a survey experiment with Chilean public servants. Public Administration Review. Available at: https://onlinelibrary.wiley.com/doi/10.1111/puar.13815 11 Apr. 2024
Meyer-Sahling	Woodhouse, E. F., Meyer-Sahling, J.-H., Mikkelsen, K. S., Schuster, C., Islam, K. M., & Rahman, T. (2024). Does political corruption reduce pro-social behaviour by bureaucrats? Lab experimental evidence from Bangladesh. Governance. Available at: https://onlinelibrary.wiley.com/doi/full/10.1111/gove.12900 4 Oct. 2024

SUBMITTED ARTICLES (1)

Chmura	The behavioral foundations of international anti-bribery laws: Results from an international lab-type experiment. Submitted 26.02.25

#### GI ACE Indicator 1.b.4:
#### Blogs, Videos, Podcasts, Press, Miscellaneous

BLOGS (3)

GI ACE	Shipley, T. (2024). Does donor support to civil society organizations help in the fight against corruption in Africa – and how can it be improved? Democracy in Africa. Available at: https://democracyinafrica.org/does-donor-support-to-civil-society-organizations-help-in-the-fight-against-corruption-in-africa-and-how-can-it-be-improved/ 14 Oct. 2024
Haenlein	Marks, D. (2025). What changes to the carbon market landscape mean for corruption risks. GI ACE blog. Available at: https://giace.org/what-changes-to-the-carbon-market-landscape-mean-for-corruption-risks/ 24 Feb. 2025
Szakonyi	Szakonyi, D., & Hornsby, M. (2024). Academics aren’t usually part of leaked data investigations. That’s starting to change. GI ACE blog / CSC blog. Available at: https://giace.org/academics-arent-usually-part-of-leaked-data-investigations-thats-starting-to-change/ 17 Dec. 2024

VIDEOS (12)

Meyer-Sahling	(2025) ACE Seminar series recording: Jan Meyer-Sahling on Ethical Leadership: Lessons from Ethics Training in the Global South. YouTube video, 30 January. Available at: https://www.youtube.com/watch?v=MIeo9MZwrB0
Meyer-Sahling	(2025) Recording of 'Let's Talk Data: A Clear-Eyed View at Latin America's National Statistical Offices (NSOs). World Bank video, 22 January. Available at: https://www.worldbank.org/en/events/2025/01/22/let-s-talk-data-a-cleared-eye-view-at-latin-america-s-national-statistical-offices-nsos
Haenlein	(2024) Interrogating Corruption Risk in Voluntary Carbon Markets. Video. Available at: https://www.rusi.org/explore-our-research/projects/interrogating-corruption-risk-voluntary-carbon-markets
Dávid-Barrett (Phase 2)	(2024) ACE Seminar Series recording: Liz Dávid-Barrett and Dani Kaufmann on State Capture. YouTube video, 3 October. Available at: https://www.youtube.com/watch?v=MpIpqiDjrLo
GI ACE	(2025) ACE Seminar series recording: Paul Heywood on SFRA approach. YouTube video, 13 February. Available at: https://www.youtube.com/watch?v=AZ96uYzDoeg
GI ACE / (PMH)	(2025) Corruption Measurement 101: Why measurement matters and how to go about it. YouTube video, 7 November. Available at: https://www.youtube.com/watch?v=cwrhYPSnHYk
GI ACE (LDB)	Recording of OECD panel session: Recording: OECD Public Integrity Indicators: From Evidence to Reform
GI ACE (LDB)	Recording of OECD panel session: Creating certainty in an uncertain world: the evolving role of gatekeepers (PACI). https://www.oecd-events.org/gacif/en/session/e84e8f8b-1fde-ef11-88f8-6045bd89b60c/knowledge-partner-session-creating-certainty-in-an-uncertain-world-the-evolving-role-of-gatekeepers-presented-by-world-economic-forum-s-partnering-against-corruption-initiative-paci-
GI ACE / (LDB, PMH)	(2025) CGU-hosted Academic Connections session on measuring corruption. YouTube video, 23 January. Available at: https://www.youtube.com/watch?v=SAtaXfi7viI
GI ACE / (LDB)	(2025) Corruption Measurement 101: Anti-corruption measurement - quo vadis? YouTube video, 14 November. Available at: https://www.youtube.com/watch?v=UJMYwjqFiB8
Stefanov	International Anti-Corruption Conference (2024). Panel: "Confronting Strategic Corruption and Illicit Finance: Democratic Resilience and Economic Security." Available at: https://youtu.be/kRP_rsL7kZA?si=kytRCsw5GDO7Jhzi 20 Jun. 2024
Stefanov	Recording of OECD GACIF session on ‘Cutting-edge research in anti-corruption'. https://www.oecd-events.org/gacif/en/session/32408c56-78f3-ef11-90cb-6045bda07d25/knowledge-partner-session-cutting-edge-research-programmes-on-tackling-corruption-today-presented-by-bridgegap-gi-ace-respond

PODCASTS (2)

Heathershaw	Heathershaw, J., Prelec, T. and Mayne, T., 2025. Indulging kleptocracy. Kickback podcast. [online] Available at: https://soundcloud.com/kickback-gap/ep-125-john-heathershaw-tena
Haberly	Haberly, D., 2025. Illicit global financial networks. Kickback podcast. [online] Available at: https://soundcloud.com/kickback-gap/126-dan-haberly-on-illicit-global-financial-networks

PRESS / NEWS (11)

Heathershaw	Foreign Affairs (2024) Indulging Kleptocracy: British Service Providers, Postcommunist Elites, and Enabling Corruption. Available at: https://www.foreignaffairs.com/reviews/indulging-kleptocracy-british-service-providers-postcommunist-elites-and-enabling
Heathershaw	The Conversation (2025) How banks, lawyers and lobbyists in the west help post-Communist kleptocrats stay rich. Available at: https://theconversation.com/how-banks-lawyers-and-lobbyists-in-the-west-help-post-communist-kleptocrats-stay-rich-248973
Heathershaw	The Irish Examiner (2025) How kleptocrats hide their ill-gotten gains in Ireland and Britain. https://www.irishexaminer.com/opinion/commentanalysis/arid-41590441.html
Heathershaw	ICAEW Insights (2025) “How to manage risks around kleptocracies”. https://www.icaew.com/insights/viewpoints-on-the-news/2025/mar-2025/how-to-manage-risks-around-kleptocracies
Haenlein	Haenlein, C. (2024) Post announcing launch of GI ACE project. LinkedIn, March. Available at: https://www.linkedin.com/posts/cathy-haenlein-41186a11_giabrace-corruption-climatetransition-activity-7166451175972683776-L-4S?utm_source=share&utm_medium=member_ios
Haberly	Rosca, M. (2024) US lags on financial transparency compared to other developed nations, researchers say. International Consortium of Investigative Journalists. Available at: https://www.icij.org/news/2024/08/us-lags-on-financial-transparency-compared-to-other-developed-nations-researchers-say/
Haberly	Hawser, A. (2024) US now favoured over Switzerland for corrupt banking, claims new research. The Banker (FT). Available at: https://www.thebanker.com/US-now-favoured-over-Switzerland-for-corrupt-banking-claims-new-research-1723197000
Haberly	Sussex News (2024) Researchers identify global hotspots for flows of 'dirty money', with Dubai and Hong Kong emerging as focal points. Available at: https://www.sussex.ac.uk/broadcast/read/65151#:~:text=Among%20their%20findings%20is%20a,actors%20in%20US%2Dsanctioned%20countries
Haberly	Sussex News (2024) Sussex experts launch first-of-its-kind dataset to reveal gaps in global financial regulations. Available at: https://www.sussex.ac.uk/news/article/66586-sussex-experts-launch-first-of-its-kind-dataset-to-reveal-gaps-in-global-financial-regulations
GI ACE	UoS News (2025) GI ACE marks one year at Sussex’s Centre for the Study of Corruption. Sussex news, 7 February. Available at: https://www.sussex.ac.uk/broadcast/read/67170
GI ACE	The Bookseller, 2025. Professor Liz David-Barrett wins The Ideas Prize for non-fiction. [online] Available at: https://www.thebookseller.com/news/professor-liz-david-barrett-wins-the-ideas-prize-for-non-fiction

MISCELLANEOUS (10)

GI ACE	GI ACE contribution to ACE brochure, [no date]. ACE brochure.
GI ACE	Landing page for EOI on state capture (2025) GI-ACE: State Capture Theme Call for Expressions of Interest. 03 October. Available at: https://giace.org/state-capture-theme-call-for-expressions-of-interest/
GI ACE	Project explainer - LDB state capture (2025) GI-ACE: LDB State Capture Project Explainer. Available at: https://giace.org/wp-content/uploads/2025/03/LizTom-State-Capture.pdf
Dávid-Barrett (Phase Two)	Project webpage – Building resilience to state capture - https://giace.org/projects/building-resilience-to-state-capture/
Dávid-Barrett (Phase Two)	LDB and TS, 2025. Submission to Think20 call for abstracts under the theme 'Financing for Sustainable Development'. Think20 South Africa. [online] Available at: http://t20southafrica.org/wp-content/uploads/2025/01/T20-South-Africa-Call-for-Abstracts.pdf
Haberly	CSC (2025). Rights of Access to the Register of Beneficial Ownership for BVI Business Companies and Limited Partnerships. Available at: https://www.sussex.ac.uk/webteam/gateway/file.php?name=rights-of-access-to-the-register-of-beneficial-onwership-for-bvi-companies-and-limited-partnerships--feb-2025.pdf&site=405
GI ACE	GI ACE brochure. 2025. https://giace.org/wp-content/uploads/2025/04/GI-ACE-Brochure_12pp.pdf
GI ACE	Project explainer – Gatekeepers, Enablers, Technicians? Available at: https://giace.org/wp-content/uploads/2025/03/Tena-One-Pager.pdf
GI ACE	Project webpage - Gatekeepers, Enablers or Technicians: The Contested Interpretation of Lawyers as Facilitators of Kleptocracy and Grand Corruption.

GI ACE Indicator 2.b.1
Engagements: Speeches, Panels, Workshops, Courses, Trainings, etc.

ALL ENGAGEMENT EVENTS: Speeches, Panels, Workshops, etc. (74)
GI ACE	International Centre of Expertise on Illicit Finance (ICE) Baseline Assessment Workshop. 5 June 2024
GI ACE	Home Office (2024) National Risk Assessment Academic Engagement Workshop. In-person meeting, 30 August 2024.
GI ACE	(2024) International Centre of Expertise on Illicit Finance - GI ACE introductory call. Remote meeting, 27 August 2024.
GI ACE	Anticorruption for Development (AC4D) Global Programme and Transparency Community of Practice (2024) Talk at World Bank on sector-based approaches to tackling corruption. In-person and online event, 17 September 2024.
GI ACE	PMH (2024) ‘Public Integrity: from rhetoric to reality’. In: Australian Public Sector Anti-Corruption Conference (APSACC), 29 July. National A‑C Commissioner Paul Brereton was present.
GI ACE	PMH (2024) GI ACE seminar on Sector Focus Remediation Action approach to tackling corruption, with A. Hayward as discussant. In-person and online event, 7 November 2024.
GI ACE / PMH, TS	(2024) Workshop for CEPPS on design on a corruption typology for electoral processes.16 January 2025
GI ACE	(2024) Meeting with UKACC representatives. In-person meeting, 27 September 2024.
GI ACE	(2025) Meeting with PMH on IF policy leadership and GI ACE follow-up. In-person meeting, January 2025.
GI ACE	Heywood, P. (2025) Academic Connections session on measuring corruption. Hosted by Minister of the Office of the Comptroller General of Brazil, 23 January 2025.
GI ACE	Panel. OECD Global Anti-Corruption & Integrity Forum Session 6: OECD Public Integrity Indicators: From Evidence to Reform.
GI ACE	Panel. OECD Knowledge Partner session - Creating Certainty in an Uncertain World: The Evolving Role of Gatekeepers
Dávid-Barrett	(2024) UNDP meeting with LDB to discuss Tackling Transnationally Enabled Corruption. In-person meeting, 11 April 2024.
Dávid-Barrett	CGU Brazil (2025) Academic Connections session on measuring corruption, hosted by Minister Vinicius Marques de Carvalho. In-person event, 23 January 2025.
Dávid-Barrett	Johnson, J., Hayman, G., Cehic, D., Kos, D., and Cardamone, T. (2024) Corruption Measurement: How to Hit a Moving Target. Panel discussion at the International Anti-Corruption Conference (IACC) 2024, 19 June. Available at: https://youtu.be/E75t5eX4MP8?si=EGvUTNGt1LqktylD
Dávid-Barrett	(2024) Panel: "Tools for detecting risks and investigating corruption in public procurement". Conference organised by Guatemala's National Anti-Corruption Commission, 11 December. Available at: https://cnc.gob.gt/cnc-inaugura-el-evento-regional-innovacion-coordinacion-y-participacion-ciudadana-hacia-un-sistema-nacional-anticorrupcion/
Dávid-Barrett (Phase Two)	(2024) "Confronting Strategic Corruption and Illicit Finance: Democratic Resilience and Economic Security". Panel discussion at the International Anti-Corruption Conference, 20 June. Available at: https://youtu.be/kRP_rsL7kZA?si=kytRCsw5GDO7Jhzi
Dávid-Barrett / (Phase-Two)	(2024) International Summit against Corruption. Hosted by UTE University Ecuador, 23 October. Available at: https://admisionesute.ec/seminario-intl-de-transparencia-y-anticorrupcion/ and https://x.com/LizDavidBarrett/status/1849233470775509047
Dávid-Barrett / (Phase-Two)	(2024) Ministerial meeting "listening event" regarding the Government's priorities around countering illicit finance, corruption, and kleptocracy. In-person meeting, 10 January 2025.
Dávid-Barrett / (Phase-Two)	David-Barrett, L. and Kaufmann, D. (2024) ACE Seminar Series: State Capture. Online seminar via Teams, 10 September.
Dávid-Barrett / (Phase-Two)	Shipley, T. (2024) 2024 Zambia Anti-Corruption Conference. Organised by TI Zambia, supported by the British High Commission and other donors, 25 November.
Dávid-Barrett / (Phase-Two)	(2024) State Capture and Human Rights: Strengthening Diplomacy for Prevention. Panel discussion organised by the Center for International Cooperation at New York University, 10 December. Available at: https://docs.google.com/document/d/1IRP_5LTYS1N6aVFnnLhgYJs-29wdP87iFJIzoL0PvE0/edit?tab=t.0
Dávid-Barrett / (Phase-Two)	David-Barrett, E. and Kaufmann, D. (2024) FCDO seminar on State Capture. In-person seminar, 2 October.
Dávid-Barrett / (Phase-Two)	Tom Shipley and Liz Dávid-Barrett presented a seminar on state capture with the IMF's governance and anti-corruption division in South Africa. The event was requested by Patrick Rafolisy, resident advisor in the IMF's governance and anti-corruption division, who had seen Liz's presentation to the IMF in 2024 and had viewed the GI ACE seminar on state capture delivered by Liz and Dani Kaufmann. Participants were senior officials in anti-corruption and judicial institutions in specific sub-Saharan African countries where state capture is of significant concern.
Dhillon	Dhillon, A. (2024) Keynote presentation - Activating Change: The Role of Information and Beliefs in Social Activism. International Meeting on Experimental and Behavioural Social Sciences (IMEBESS) 2024, 25 May. Available at: https://coms.events/imebess2024/data/sessions/en/session_39.html
Dhillon	Dhillon, A. (2025) Keynote presentation - Activating Change: The Role of Information and Beliefs in Activism. Annual Economics Conference, Ahmedabad University, 6 January. Available at: https://ahduni.edu.in/site/assets/files/24707/6th_annual_economics_conference_schedule.pdf
Haberly	Centre for the Study of Corruption (2024) From Secrecy to Scrutiny: A New Map of Illicit Global Financial Networks (launch event). In-person event, 13 June. Available at: https://www.tickettailor.com/events/thecentreforthestudyofcorruption/1256087
Haberly	(2024) Invited to brief FCDO. In-person briefing, 29 August.
Haberly	Haberly, D. (2024) Presentation of RIFF paper. International Institute of Public Finance Congress, Prague, 21 August. Available at: https://corptax.cuni.cz/uncategorized/miroslav-palansky-has-brought-the-iipf-congress-to-prague-corptax-researchers-presenting-their-latest-findings/
Haberly	(2024) Webinar: The Regulation of Illicit Financial Flows (RIFF) dataset: A new world map of 30 years of financial secrecy and anti-money laundering reforms. GI ACE webinar, 11 December. Available at: https://www.eventbrite.co.uk/e/the-riff-dataset-launch30-years-of-financial-secrecy-and-aml-reform-trends-tickets-1097123258199?aff=oddtdtcreator
Haberly	(2024) FCDO briefing - sanctions, FCPA data, RIFF. FCDO, 6 December.
Haberly	Haberly, D. (2024) From London to Dubai-Kong: Mapping Geographic Shifts in US Sanctioned Global Financial Networks, 1980-2023. Presentation at the Bahamas AML conference, 17 January. Available at: https://bahamasamlconference.centralbankbahamas.com/documents/2025-01-15-13-40-17-SixthAnnualBahamasResearchConferenceonFinancialCrime-FinalAgenda2025.pdf
Haberly	Government-Academia cooperation event hosted by the British Embassy at the Hague.
Haberly	September 2024. Home Office policy meeting to advise on UK beneficial ownership transparency strategy.
Haberly	October 2024. Participation in NECC-Home Office symposium on financial crime.
Heathershaw	(2024) Institute for Public Policy Reform event: 'Tackling Kleptocracy'. Institute for Public Policy Reform, 21 May. Available at: https://www.ippr.org/past-events/combating-transnational-kleptocracy
Heathershaw	D. (2024) Invitation to brief NCA. In-person briefing, 10 June.
Heathershaw	(2024) Invitation to brief Cabinet Office. In-person briefing, 10 June.
Heathershaw	(2024) Ministerial meeting "listening event" regarding the Government's priorities around countering illicit finance, corruption, and kleptocracy. In-person meeting, 1 October.
Heathershaw	(2025) Presentation on Indulging Kleptocracy given at Bayreuth University within the series 'Bayreuth Peace Talks'. Bayreuth Peace Talks, 22 January. Available at: https://www.peaceandconflict.uni-bayreuth.de/en/news/2025/pictures_heathershaw_talk/index.html
Heathershaw	(2025) Parliamentary launch of Indulging Kleptocracy, hosted by APPG on Anti-Corruption and Responsible Tax. Parliamentary event, 10 February.
Heathershaw	(2025) Kleptoscope: Indulging Kleptocracy. Frontline Club Kleptoscope series, 11 February. Available at: https://www.eventbrite.co.uk/e/kleptoscope-indulging-kleptocracy-tickets-1104622719289
Heathershaw	(2025) Indulging Kleptocracy event at Columbia University's Harriman Institute. Harriman Institute, Columbia University, 26 February. Available at: https://harriman.columbia.edu/event/indulging-kleptocracy-british-service-providers-postcommunist-elites-and-the-enabling-of-corruption/
Heathershaw	(2025) Indulging Kleptocracy event at George Washington University. George Washington University, 27 February. Available at: https://calendar.gwu.edu/event/indulging-kleptocracy-british-service-providers-postcommunist-elites-and-the-enabling-of-corruption
Heathershaw	(2025) Indulging Kleptocracy event at Davis Centre for Russian and Eurasian Studies (Harvard Uni.). Davis Center for Russian and Eurasian Studies, 25 February. Available at: https://daviscenter.fas.harvard.edu/events/indulging-kleptocracy-postcommunist-elites-and-corruption
Heathershaw	(2024) The Long Reach: How Authoritarian Governments Silence Critics Abroad. Index on Censorship/Exeter University, 2 May. Available at: https://www.indexoncensorship.org/events/the-long-reach-how-authoritarian-governments-silence-critics-abroad/
Heathershaw	Indulging Kleptocracy launch event at Northeastern University, hosted by the Equality Development and Globalization program. 03.03.2025.
Heathershaw	Indulging Kleptocracy launch event at Indiana University hosted by the Hamilton Lugar School of Global and International Studies. 07.03.25
Heathershaw	Presentation to Europol on the role of the legal sector and legal structures in enabling. 04.12.24
Heathershaw (Phase Two)	HMG meeting on recent innovations in sanctions towards Russian elites and enablers. 26.02.25
Heathershaw / (Phase Two)	Prelec, T. (2024) Tackling the 'enablers' of IFFs. Panel at UNDP's first Finance, Integrity and Governance (FIG) Policy Symposium on 'International Tax Cooperation and the Challenge of Illicit Financial Flows', 1 May. Available at: https://www.undp.org/publications/finance-integrity-and-governance-initiative-international-tax-cooperation-and-challenge-illicit-financial-flows
Heathershaw / (Phase Two)	(2025) Presentation of research to academic colleagues. Zoom, 4 February.
Heathershaw / (Phase Two)	(2024) Invitation to brief FCDO. In-person, 10 June.
Heathershaw / (Phase Two)	(2024) Invitation to brief Home Office. In-person, 10 June.
Heathershaw / (Phase Two)	(2024) Meeting at NCA. 12 July.
Heathershaw / (Phase Two)	(2024) Meeting with representatives from regulated industries to brief them on project. 1 June.
Heathershaw / (Phase Two)	(2024) Meeting with TI-UK researchers. 1 July.
Meyer-Sahling	Schuster, C. (2025) Let's talk data: A clear-eyed view at Latin America's national statistical offices (NSOs). World Bank, 22 January. Available at: https://www.worldbank.org/en/events/2025/01/22/let-s-talk-data-a-cleared-eye-view-at-latin-america-s-national-statistical-offices-nsos
Prelec	04.03.2025. International Studies Association Convention 2025. Chicago. Conference paper presenting initial research findings presented.
Prelec	26.02.2025. Meeting with UNODP, UNODC representatives
Prelec	18.03.2025. APPG event launching policy report produced with Spotlight on Corruption, distilling research findings for a policy audience.
Prelec	Tonin, P. (2024) NECC-HO conference on economic crime, hosted at RUSI. 17 October.
Stefanov	Meeting with FCDO Central European Network representative. 01.12.2024
Stefanov	2025. EU Commission meeting.
Stefanov	Meeting at Bulgarian Ministry for Justice. 2025
Stefanov	OECD Global Anti-Corruption and Integrity Forum. Cutting-edge research in anti-corruption panel. 27.03.2025
Stefanov	Centre for the Study of Democracy (CSD) (2024) The State of Capture in Bulgaria: The Elusive Quest for Anti-Corruption Results. 16 April. Available at: https://csd.eu/events/event/the-state-of-capture-in-bulgaria-the-elusive-quest-for-anti-corruption-results/
Stefanov	Petrova, V. (2024) Confidential briefing for British Embassy in Yerevan: Estimations of IFFs in Armenia (2010-2022). 3 April. Confidential report produced for exclusive use by the UK Embassy.
Stefanov	Stefanov, R. (2024) Panel: Building Resilience against Foreign Interference in Open Societies. OECD Global Forum on Building Trust and Reinforcing Democracy Agenda. 22 October. Available at: https://www.oecd-events.org/global-forum-on-democracy/en/onlinesession/feb94f10-64fd-ee11-aaf0-000d3a2b945f
Szakonyi	(2024) Data against Kleptocracy workshop. 12 November. Hosted by ACDC, OCCRP, and the National Endowment for Democracy (NED).
Villeneuve	International Research Society for Public Management Conference (2024) International Research Society for Public Management Conference. 01 April. Available at: https://www.irspm.org/conference-2024/conferences/programme-1
Villeneuve	UNODC-organised Addis Ababa international expert meeting on asset return and sustainable development (2024) UNODC-organised Addis Ababa international expert meeting on asset return and sustainable development. 11-13 December. Available at: https://www.unodc.org/corruption/en/uncac/expert-meetings/addis4-egm-2024.html#:~:text=International%20Expert%20Meeting%20on%20asset,Ababa%2C%2011%2D13%20December%202024
Villeneuve	UNODC background paper (2024) UNODC background paper on asset return and sustainable development. 11-13 December. Unpublished background paper.

SOC ACE Indicators and Results FY2024/25

Impact Indicator: Examples of a) conceptual impact (changing ways of thinking etc); OR b) instrumental impact (influencing policy and practice etc); OR c) networks and connectivity impact (e.g., building and strengthening networks etc); OR d) capacity building impact (building researchers' capacity to strengthen research uptake etc).

No.	Result	Evidence	Fund
1	HMRC announcement of a cash reward scheme for whistleblowers who expose tax avoidance and fraud, with James Murray, Exchequer Secretary to the Treasury, referencing the US and Canada’s reward schemes when announcing the plans. The Canadian experience is not generally referenced in whistleblowing literature, indicating that Eliza Lockhart’s economic crime whistleblower research has informed the decision.	https://www.lbc.co.uk/news/money/government-cash-whistleblowers-expose-tax-avoidance-fraud/ / https://www.gov.uk/government/news/boost-for-side-hustlers-as-300000-people-to-be-taken-out-of-tax-returns-government-announces#:~:text=The%20scheme%20will%20take%20inspiration,more%20money%20that%20it%20costs.	NODA

SOC ACE Outcome Indicator C.1.: Number of cases where ACE research directly or indirectly influences policy,
programme design or implementation by HMG. Target: 5. Achieved: 5.

No.	Result	Evidence	Fund
1	Heather Marquette was invited to a Ministerial Engagement Session with Minister Doughty and Minister Jarvis on illicit finance and corruption, with Ben Judah, Special Advisor to the Foreign Secretary, also in attendance. During the session and in a follow-up note, the Minsters were introduced to ACE and SOC ACE, as well as key messaging informed by SOC ACE research findings. As a result, Minister Doughty requested further information on three SOC ACE projects: 1) Lockhart’s whistleblowing project, 2) Kupatadze & Marat’s organised crime and trade displacement project, and 3) Lewis, Prelec & Allison’s Russia's use of IF in its foreign policy research. Minister Doughty also requested an in-person briefing with Eliza Lockhart, which is being planned.		NODA
2	Erica Marat and Alexander Kupatadze’s SOC ACE paper, ‘Under the Radar: How Russia Outmanoeuvres Western Sanctions with Help from Its Neighbours’ has been included as recommended reading in a 17 Jan 2025 House of Commons research briefing on Sanctions against countries supporting Russia’s invasion of Ukraine.	https://researchbriefings.files.parliament.uk/documents/CBP-10048/CBP-10048.pdf (Pg.10)	NODA
3	Alexander Kupatadze, Heather Marquette and John Collins were invited to speak at a SOC / Academia event hosted by British Embassy to The Hague, organised by SOCnet. Alexander spoke on global threat typology, with a focus on corruption and illicit finance, and Heather led a discussion on SOC ACE’s approach to policy engagement and impact. Heather and John also co-chaired a roundtable discussion on opportunities and challenges for academia to inform policy.		NODA/ODA
4	Matthew Redhead’s State Threats research is showing early indications of influencing thinking and policy on how the UK considers and approaches the issue. FCDO’s DG-Defence & Intelligence opened the paper’s launch at RUSI, which was picked up by iNews (14/01/25).	https://inews.co.uk/news/arson-sabotage-cyber-attacks-uk-threats-hostile-states-3481620?srsltid=AfmBOopM9FgiGqOfKjoChPFlDikzv7Zj6D7qHI11CU_78nK9WjV7ee12	NODA
5	Eliza Lockhart’s research paper, published Dec 2024, has contributed to a change in the UK Financial Conduct Authority’s (FCA) official position with regards to financial rewards for economic crime whistleblowers, now recognising that there are benefits in, and implications of, providing incentivisation to whistleblowers.	https://www.compliancecorylated.com/news/uk-fca-changes-official-stance-opposing-payments-to-whistleblowers/	NODA

SOC ACE Outcome Indicator C.2.: # of cases where ACE research directly or indirectly influences policy, programme design, or implementation by other non-HMG partners & stakeholders. Target: 3. Achieved: 3.

No.	Result	Evidence	ODA / NODA
1	SOC ACE Research Paper 4 by David H. Ucko and Thomas A. Marks, has been included in NATO’s Hybrid Threats and Hybrid Warfare Reference Curriculum as required reading under Theme 2, Threat Vectors: Domain-related means and methods of exercising hybrid threats and hybrid warfare, Sub-Theme T2-B8, Organised Crime. The curriculum was published in June 2024.	https://www.nato.int/nato_static_fl2014/assets/pdf/2024/7/pdf/241007-hybrid-threats-and-hybrid-warfare.pdf (Pg.35)	NODA
2	Findings on some of the deficiencies in the Total Peace Policy legal framework found by the SOC ACE-funded Total Peace research project have been used as the foundational starting points for strengthening the legal framework for the negotiations with the armed group Comuneros del Sur de Nariño, through advice provided by a SOC ACE researcher and other colleagues at Laboratorio de Justicia y Política Criminal (LJPC), via a process funded by The Carter Centre.		ODA
3	Research findings of the Medellín Impact Lab’s demonstration project co-funded by SOC ACE are directly informing the development, testing, scaling and evaluation of treatment interventions to tackle extortion in Medellin. Three interventions are in progress: 1) conditional repression to reduce extortion; 2) scaling of a multi-pronged approach to reduce gang recruitment; and 3) evaluation of city government unarmed approaches to tackling disorder and crime for improving state legitimacy across the city. In December, Santiago Tobón and team won the 2024 Medellín Investiga Award for Research with the Greatest Impact. The award is an initiative of the Medellín Mayor’s Office in recognition of research with a positive impact on the city and its metropolitan area.	https://premiosinvestigacionmedellin.org/premios-y-reconocimientos-medellin-investiga-2024/ / eafit.edu.co/noticias/agenciadenoticias/2024/santiagoymariaalejandra-premios-medellin-investiga-2024 / https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/677d38ac3409ac5b312e4ec4/1736259759090/SOCACE-BN33-MapCombatUrbanCrime-Dec24-Proof02.pdf	ODA

SOC ACE Output 1.c.1: # of projects selected for funding: i) Total cumulative, ii) Multiyear comprehensive projects (disaggregated by PI/Research Team gender) Target: i) 5, ii) 1. Achieved: i) 5, ii) 1.

No.	Result	Evidence	Fund
1	2024/RUSI/001/China PMLO: Exploring the Threat of Chinese Professional Money Laundering. / PI = 1 x Female, Research Team = 1 Female, 0 Male	https://www.socace-research.org.uk/projects/rusi-exploring-the-threat-of-chinese-professional-money-laundering	NODA
2	2024/HAIDER/001/Transitional: Addressing organised crime through a transitional justice framework / PI = 1 x Female, Research Team = 0 Female, 0 Male	https://www.socace-research.org.uk/projects/addressing-organised-crime-through-a-transitional-justice-framework	ODA
3	2024/UOB/001/Interoperability: Interoperability, multiagency sensemaking and the potential for AI - Phase Two / PI – 1 x Female 1 x Male, Research Team = 1 Male	https://www.socace-research.org.uk/projects/22-uob-interoperability-ai	ODA
4	2024/RUSI/003/Understanding State Threats – Phase Two / PI – 1 x Male, Research Team = 0 Female, 0 Male	https://www.socace-research.org.uk/projects/socace-rusi-understanding-state-threats	NODA
5	2024/HAIDER/002/Environment: The relationship between OC, the environment and Indigenous communities / PI = 1 x Female, Research Team = 0 Female, 0 Male	Launching in April 2025	ODA
6	Multi-Year Project / 2024/SOAS/001/Corridors: The centrality of the margins: Borderlands, illicit economies and uneven development / PI – 2 x Male, Research Team = 0 Female, 0 Male	https://www.socace-research.org.uk/projects/socace-soas-the-centrality-of-the-margins-borderlands-illicit-economies-and-uneven-development	ODA

SOC ACE Output 1.c.2: a) Number of policy research products (briefs, blogs, national press articles) and research papers (cumulative)*. b) % of research papers and evidence review papers peer reviewed. Target: a) 25 New, b) 100%. Achieved: a) 38, b) 100%.

No.	Type	Result	Evidence	Fund
1	Briefing Note	Reitano, T. and Mahadevan, P. (2024) Migrant Smuggling, SOC ACE Briefing Note 28	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/661d2160f5cb993a0897292f/1713185121618/SOCACE-BN28-Migrant-Smuggling.pdf	ODA
2	Briefing Note	Oliveira, A. P. (2024), ‘Human Rights and Organised Crime Agendas: Four Areas of Convergence for Policymaking’, SOC ACE Briefing Note 29	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/6617a48d6725f71bcb042e94/1712825486084/SOCACE-BN29-Human-Rights-and-Organised-Crime-Agendas-MAR24.pdf	ODA
3	Journal Article	Cheeseman, N, and Peiffer, C. (2024) ‘Opening the door to anti-system leaders? Anti-corruption campaigns and the global rise of populism’, European Journal of Political Research, published 24 April.	https://ejpr.onlinelibrary.wiley.com/doi/10.1111/1475-6765.12682?af=R	NODA
4	Journal Article	Cheeseman, N. and Peiffer, C. (2024) ‘Getting the message right: what are the impacts of counter-serious and organised crime awareness-raising strategies?’, Behavioural Public Policy, 30 April	https://www.cambridge.org/core/journals/behavioural-public-policy/article/getting-the-message-right-what-are-the-impacts-of-counterserious-and-organised-crime-awarenessraising-strategies/5611B28AE46910B60EBE88A2F94CEBE1	NODA
5	Workshop Report	Lockhart, E. (2024) ‘Conference Report: State Threats Workshop: Perspectives from Germany and the UK’, RUSI and SOC ACE, published 29 April	https://static.rusi.org/486_CR_German-state-threats-web-final.pdf	NODA
6	Evidence Review Paper	Haider, H. (2024) ‘Addressing organised crime and security sector reform and governance: Linkages, processes, outcomes, challenges’, SOC ACE Evidence Review Paper 05	https://www.socace-research.org.uk/publications/socace-erp05-addressing-organised-crime-and-security-sector-reform-and-governance-linkages-processes-outcomes-and-challenges	NODA
7	Briefing Note	Haider, H. (2024) ‘Addressing organised crime and security sector reform and governance: Linkages, processes, outcomes, challenges’, SOC ACE Briefing Note 30	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/66bb5a2f5c966444a24e3ce2/1731067227329/SOCACE-BN30-Addressing-SSR-and-governance-Haider-Jul24.pdf	NODA
8	Briefing Note	Haider, H. (2024) ‘Grupos del crimen organizado, agendas criminales, violencia y conflicto: Implicaciones en materia de participación, negociación y procesos de paz’ Spanish translation of the peace processes evidence review paper, SOC ACE Briefing Note 24	https://www.socace-research.org.uk/publications/grupos-del-crimen-organizado-agendas-criminales-violencia-yconflicto-bn24	ODA
9	Book Chapter	David-Barrett, L. and Tomic, S. (2024) ‘The legal design of domestic MLA procedures in Southeast Europe: A comparative analysis of Serbia, North Macedonia and Bosnia and Herzegovina’ in Goldbarsht. D, and de Koker. L, (Eds.) Financial Crime, Law and Governance: Navigating Challenges in Different Contexts, pp 257 – 286, Springer	https://link.springer.com/chapter/10.1007/978-3-031-59547-9_11	NODA
10	Journal Article	Blattman. C, Gustavo. D, Lessing. B, Tobón. S, (2024) ‘Gang rule: Understanding and Countering Criminal Governance’, The Review of Economic Studies, 5 September	https://academic.oup.com/restud/advance-article-abstract/doi/10.1093/restud/rdae079/7749621?redirectedFrom=fulltext	ODA
11	Media Article	Lessing. B, (2024, August 09). ‘Use incentives, not brute force, on the cartels, says political scientist’, The Economist	https://www.economist.com/by-invitation/2024/08/09/use-incentives-not-brute-force-on-the-cartels-says-a-political-scientist	ODA
12	Briefing Note	Prelec, T. (2024) 'Information Manipulation & Organised Crime: Examining the Nexus', SOC ACE Briefing Note 31	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/66d04408d4632462c4cceb38/1731067227329/SOCACE-BN31-Disinformation-Prelec-Aug24.pdf	NODA
13	Research Paper	Lockhart, E. (2024) The Inside Track: The Role of Financial Rewards for Whistleblowers in the Fight Against Economic Crime. SOC ACE Research Paper No. 31	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/6756cfd024f33859fb718888/1733742545613/SOC-ACE-RP31_Whistleblowing-Dec+24.pdf	NODA
14	Briefing Note	Lockhart, E. (2024) The Inside Track: The Role of Financial Rewards for Whistleblowers in the Fight Against Economic Crime. SOC ACE Briefing Note No. 32	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/6756d027e609b51014f36650/1733742632384/SOCACE-BN32-Whistleblowing_Dec+24.pdf	NODA
15	Briefing Note	Blattman, C., Lessing, B., Tobon, S. (2025) How to map and combat organised crime: Lessons from the Medellin Impact Lab. SOC ACE Briefing Note 33	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/677d38ac3409ac5b312e4ec4/1736259759090/SOCACE-BN33-MapCombatUrbanCrime-Dec24-Proof02.pdf	ODA
16	Briefing Note	Blattman, C., Lessing, B., Tobon, S. (2025) The political will to measure organised crime: Why we need it and how to build it. SOC ACE Briefing Note 34	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/677d4288978e4218b675eab0/1736262281460/SOCACE-BN34-PoliticalWillOrganizedCrimeMeasurement-Dec24-Proof02.pdf	ODA
17	Research Paper	Redhead, M. R. (2025) Old Wine, New Bottles? The Challenge of State Threats. SOC ACE Research Paper 32	https://static1.squarespace.com/static/63e4aef3ae07ad445eed03b5/t/67852e69ff4ff4079a9c3000/1736781420568/SOCACE-RP32-OldWineNewBottles_final.pdf	NODA
18	Blog	Blattman, C. et al (2023), Civilian alternatives to policing: Evidence from Medellín’s community problem-solving intervention Operación Convivencia, Innovations for Poverty Action	https://poverty-action.org/publication/civilian-alternatives-policing-evidence-medellins-community-problem-solving	ODA
19	Journal Article	Bensassi, S. & Arisyi, R. (2025) Combatting trade-related fraud: Do the Financial Action Task Force Recommendations Bite? Economica, 92(365), 322-347.	https://doi.org/10.1111/ecca.12561	ODA
20	Podcast	Meegan-Vickers, J. (Host) (2024, Oct 28) “Colombia & Total Peace: Part 1: The ELN – The Easy Win”. In Deep Dive: Exploring Organized Crime, GI-TOC.	https://globalinitiative.net/analysis/deep-dive-podcast/#podcast-31034-1	ODA
21	Podcast	Meegan-Vickers, J. (Host) (2024, Oct 28) “Colombia & Total Peace: Part 2: Buenaventura – “The Pact for Life”. In Deep Dive: Exploring Organized Crime, GI-TOC.	https://globalinitiative.net/analysis/deep-dive-podcast/#podcast-31034-1	ODA
22	Journal Article	Nizzero. M, (2024) Illicit Finance as a National Security Threat: Balancing security and unintended consequences. The RUSI Journal, Vol.169, No.06, pp.64-76.	https://www.tandfonline.com/doi/abs/10.1080/03071847.2024.2424788	NODA
23	Research Paper	Durán. J, (2025) Institutional architecture of Total Peace: A normative review studied in practice. SOC ACE Research Paper 33	https://www.socace-research.org.uk/publications/total-peace-institutional-architecture-rp33	ODA
24	Research Paper	Botero. F, et al (2025) Total Peace Policy: Between light and shadow, SOC ACE Research Paper 34	https://www.socace-research.org.uk/publications/total-peace-light-and-shadow-rp34	ODA
256	Briefing Note	Botero, F. et al (2025) Total Peace in Colombia: Lessons for Negotiating with Organized Crime Groups and Promoting Peacebuilding, SOC ACE Briefing Note 35	https://www.socace-research.org.uk/publications/total-peace-criminal-groups-bn35-ksfck	ODA
267	Briefing Note	Botero, F. et al (2025), Negotiating with Criminal Groups: Colombia´s Total Peace, SOC ACE Briefing Note 36.	https://www.socace-research.org.uk/publications/total-peace-lesson-bn36	ODA
278	Blog	Khoruk, M. (2025) Smoke and mirrors: Afghanistan’s illicit drug trade economy after the opium ban, GI-TOC Analysis Article, 17 February	https://globalinitiative.net/analysis/afghanistans-illicit-drug-economy-after-the-opium-ban/	ODA
289	Podcast	David-Barrett, L. (Host) (Ep. 118, 2024, Sep 26) “Caryn Peiffer and Nic Cheeseman on how to get anti-corruption messaging rights” in KickBack – The Global Anticorruption Podcast, Interdisciplinary Corruption Research Network	https://soundcloud.com/kickback-gap/118-how-to-get-anti-corruption-messaging-right	NODA
2930	Blog	Ginn, P. (2025) Trigger warning: Afghanistan’s unchecked arsenal under Taliban rule, GI-TOC Analysis Article, 06 February	https://globalinitiative.net/analysis/afghanistans-unchecked-arsenal-under-taliban-rule/	ODA
301	Research Paper	Blattman, C. et al (2023), Gang Rule: Understanding and Countering Criminal Governance, NBER Working Paper 28458, April	https://www.nber.org/papers/w28458	ODA
312	Video	RUSI Research Event Recording: ‘Tackling the Growing Threat from Hostile States’. 14 Jan 2025	https://rusi.org/research-event-recordings/recording-tackling-growing-threat-hostile-states	NODA
323	Podcast	Carvin, S., David, J., West, L., (Hosts), Redhead, M. (Guest) (25 February 2025), Implausible Deniability: The New Age of State Threats, in Secure Line Podcast. Canadian Association for Security & Intelligence Studies (CASIS)	https://www.youtube.com/watch?v=m8ABjMB9QuY	NODA
334	Podcast	Keatinge, T. and Redhead, M. (17 January 2025) Episode 10: State Threats - Same Old Same Old, or Something Different? Suspicious Transaction Report Podcast, RUSI	https://rusi.org/podcasts/suspicious-transaction-report/episode-10-state-threats-same-old-same-old-or-something-different	NODA
345	Video	RUSI Research Event Recording: ‘Whistleblowers’ Rewards in the Fight Against Economic Crime’, 10 Dec 2024	https://www.rusi.org/research-event-recordings/recording-whistleblowers-rewards-fight-against-economic-crime	NODA
356	Podcast	Keatinge, T. and Lockhart, E. (31 January 2025) Episode 11: Incentivising Whistleblowers to Expose Economic Crime? Suspicious Transaction Report Podcast, RUSI	https://rusi.org/podcasts/suspicious-transaction-report/episode-11-incentivising-whistleblowers-expose-economic-crime	NODA
367	Blog	Lockhart, E. (2024) Money Talks: Financially Rewarding Economic Crime Whistleblowers, RUSI Commentary	https://www.rusi.org/explore-our-research/publications/commentary/money-talks-financially-rewarding-economic-crime-whistleblowers	NODA
378	Book	Lewis, D. (2025) Occupation: Russian Rule in South-Eastern Ukraine, Hurst Publishers.	https://www.hurstpublishers.com/book/occupation/	NODA

SOC ACE Output 2.c.1: Number of HMG events & engagement activities (seminars, participation in workshops, briefings, requests for input into strategies, programmes, etc.) Target: 15. Achieved: 41.

No.	Type	Result	Fund
1	Event	APPG’s second Economic Crime Manifesto on Anti-Corruption & Responsible Tax and Fair Business Banking – 17 April – Heather Marquette	NODA/ ODA
2	Engmnt.	Department of Business & Trade’s labour market directorate, who were leading an internal review of whistleblowing laws – 16 May - Eliza Lockhart.	NODA
3	Engmnt.	FCDO/SSD to discuss SSR and SOC, plus Ukraine, stabilisation and transnational threats evidence needs and the stabilisation guide refresh - 11 & 19 April, 19 May, 05 & 15 June – Heather Marquette.	NODA/ ODA
4	Engmnt.	Early engagement with FCDO, NCA, and Home Office on the second phase of the RUSI SOC sanctions research project – 20 May 2025 – Cathy Haenlein.	ODA
5	Event	Stabilisation Leaders Forum – 25 June 2025 – Heather Marquette.	NODA/ ODA
6	Engmnt.	Serious Fraud Office’s senior policy team and investigator on whistleblower reward schemes – 19 June 2025 – Eliza Lockhart.	NODA
7	Engmnt.	JFU and FCDO/NSD on potential research collaboration on ‘what works’, to tackle SOC – 29 June 2025 – Heather Marquette	NODA/ ODA
8	Engmnt.	SOCnet Western Balkans on SOC, illicit finance and destabilisation challenges and potential future collaboration – 02 July – Heather Marquette	NODA
9	Engmnt.	FCDO Iraq Unit to discuss preliminary anti-corruption initiatives – 16 July – Heather Marquette	NODA/ ODA
10	Briefing	Financial Conduct Authority’s Legal Division and Whistleblowing Team – 17 July – Eliza Lockhart.	NODA
11	Advisory	Home Office consultation on its future SOC portfolio – 22 July – Heather Marquette.	NODA/ ODA
12	Briefing	Home Office JACU, Department for Business & Trade, His Majesty’s Treasury briefing on different models of whistleblowing schemes – 23 July - Eliza Lockhart.	NODA
13	Engmnt.	Ministry of Defence Human Security Team on human security dynamics of SOC and corruption – 07 August – Heather Marquette & Lyndsey Hand	NODA/ ODA
14	Advisory	HMG Reference Group for FCDO Illicit Finance Centre of Excellence (ICE) – 13 August – Heather Marquette	NODA/ ODA
15	Advisory	FCDO Reform Hub, Ukraine Early Recovery & Reconstruction Department discussion on anti-corruption and counter-SOC interventions – 15 August – Heather Marquette	NODA/ ODA
16	Engmnt.	FCDO Deputy Director NSD SOC Team on potential new SOC Sanctions and plans for ongoing regular engagement – 16 August – Heather Marquette	NODA/ ODA
17	Engmnt.	FCDO Director for Counter-Proliferation to discuss priorities, intersections between SOC and future proliferation threats, and counter-proliferation finance – 29 August – Heather Marquette	NODA/ ODA
18	Engmnt.	Home Office/HMT National Risk Assessment Academic Engagement workshop to provide feedback on the new framework for assessing risks on counter-proliferation finance – 30 August – Heather Marquette & Olivia Allison	NODA/ ODA
19	Briefing	FCDO and NCA briefing on ‘How not to fight corruption’ drawing on findings from the Medellin demonstration project - 16 September – Benjamin Lessing	ODA
20	Engmnt.	FCDO to discuss current IFF threats and garner reflections on preliminary findings of the IFF Pyramid research project – 16 & 17 September – Tuesday Reitano, Michael McLaggan & Kristina Amerhauser	ODA
21	Engmnt.	FCDO/SSD SSR Network on early findings of the SOC SSR research – 17 September - Liam O’Shea & Louis-Alexander Berg	ODA
22	Event	SOC ACE Researcher Conference, bringing together researchers and HMG representatives from IFAC, ICE, NECC, ISF, OCSM, and NCA to consider the portfolio of current research and findings to date and provide feedback on current research and advice on impact planning – 18 & 19 September.	ODA/ NODA
24	Briefing	Olivia Allison and Tena Prelec presented to FCDO state threats team on their SOC ACE-funded research on IFF in Russian foreign policy – 09 October.	NODA
25	Event	RUSI Economic Crime Academic Forum with Home Office and National Economic Crime Centre -17 October – Maria Nizzero & Heather Marquette	NODA/ ODA
26	Engmnt.	National Crime Agency, HUMINT Academic Hub briefing on whistleblowing research findings – 11 November – Eliza Lockhart	NODA
27	Engmnt.	Serious Fraud Office, Chief Capability Officer, Head of Policy, Deputy Head of Policy, Senior Policy Advisor briefing on findings of the whistleblower research – 21 November – Eliza Lockhart	NODA
28	Engmnt.	Serious Fraud Office, Director pre-launch event briefing – 04 December – Eliza Lockhart.	NODA
32	Event	Heather Marquette organised and chaired a panel on ‘Responding to evolving nature of transnational threats in a hostile world’ at the UK Integrated Security Fund Conference - 4 February, while Matthew Redhead presented his state threats research on a panel on ‘Allies, partners and adversaries: how do actors operate in their national security interests’.	NODA/ ODA
34	Advisory	Elijah Glantz, Sasha Jesperson and Heather Marquette participated in an Expert Challenge Session for a new West Africa SOC Joint Assessment (SOCJA), organised by SOCnet regional lead, NSD SOC team, and regional Conflict Advisor – 14 January.	ODA
35	Event	X-HMG seminar on the findings of the State Threats research paper organised by RED & FCDO/NSD State Threats Unit – Matthew Redhead, chaired by Heather Marquette – 03 March.	NODA
36	Advisory	Matthew Redhead, Tom Keatinge & Heather Marquette to a request of the NSD’s Deputy Director State Threats Unit to provide views on an emerging strategy for addressing state threats. Avenues for continued advisory are in discussion – 03 March.	NODA
38	Advisory	Heather Marquette provided advice to FCDO SSD on SOC and conflict trends to inform the team’s business planning – 14 March.	NODA/ODA
39	Event	Heather Marquette attended FCDO Reception Celebrating the Impact of R&D, Science and Technology Across Government – 17 March	NODA/ODA
40	Event	Olivia Allison and Lyndsey Hand attended SOCnet & BE-Riga conference on Awareness to Action: Solutions to combating illicit finance	NODA
41	Training	Heather Marquette delivered a training session on Countering State and Transnational Threats on the inaugural HMG Conflict and Stabilisation Course	ODA

SOC ACE Output 2.c.2: Number of external events & engagement activities (speeches, engagements, panel appearances, participation in workshops, requests for input, etc.) Target: 15. Achieved: 34.

No.	Type	Result	Fund
1	Event	International Studies Association 2024 Annual Convention in San Francisco – David Lewis presented aspects of his SOC ACE-funded research on Russian IFF – 03 to 06 April.	NODA
2	Event	IPPR event ‘The Anti-Corruption Capital of the World?’ – Maria Nizzero was on a panel drawing on aspects of her SOC ACE-funded kleptocracy research – 21 May.	NODA
3	Event	Tena Prelec presented at the first Finance, Integrity and Governance (FIG) Policy Symposium hosted by UNDP’s Global Policy Centre for Governance in Oslo – 14 & 15 May	NODA
4	Event	SOC ACE roundtable at BISA 2024 Conference on ‘Rethinking stabilisation and responding to transnational threats’ – Heather Marquette and David Lewis – 07 June.	NODA/ ODA
5	Event	IACC2024 with Heather Marquette and Tom Keatinge participating as panellists in a RUSI-coordinated workshop on combatting modern kleptocracy – 20 June.	NODA/ ODA
6	Event	Heather Marquette and Caryn Peiffer’s workshop titled, ‘Functionality of Corruption and Organised Crime’, as part of the second phase of their research project brought together a multidisciplinary group of policymakers, academics and practitioners (HMG and non-HMG) – 24 & 25 June.	NODA
7	Event	Round table at the Central and Eastern European Schools Association - International Studies Association (CEEISA-ISA) Conference, titled ‘Illicit Finance, Transnational Corruption, and Informal Economies in Contemporary Conflict’ – Tena Prelec, David Lewis, Olivia Allison – 18 to 21 June.	NODA
8	Event	Tena Prelec with David Lewis workshop on strategic corruption in Croatia drawing on their SOC ACE-funded Russian IFF research - 20 & 21 June.	NODA
9	Advisory	Heather Marquette delivered a session for Lithuanian anti-corruption police visiting the NCA on an exchange initiative – 26 September.	NODA/ ODA
10	Event	Felipe Botero and Juanita Durán participated in a panel on ‘Peace processes and organised crime: the case of Medellín, Colombia’ as part of the OC24 Conference on Global Organised Crime – 30 October	ODA
11	Event	Prem Mahadevan and Maria Khoruk participated in a panel on ‘Human trafficking and migrant smuggling in Central and South Asia: experience of local civil society actors’ as part of the OC24 Conference on Global Organised Crime – 31 October	ODA
12	Event	OCCRP, National Endowment for Democracy, and Anti-Corruption Data Collective workshop on ‘Data against kleptocracy’ attended by Heather Marquette along with researchers and investigative journalists to discuss collaboration on datasets to target kleptocratic flows – 11 November.	NODA/ ODA
13	Event	Launch event for Matthew Redhead’s paper ‘Old wine, new bottles? The challenge of state threats’, with opening remarks by FCDO DG Defence and Intelligence, Jonothan Allen and panel involving Matthew, Suzanne Raine and Professor Rory Cormac and attendance of over 100 persons – 15 January.	NODA
14	Event	Launch event for Eliza Lockhart’s paper on whistleblower reward schemes with panellists Nick Ephgrave QPM, Susan Hawley, Eliza Lockhart, and Judith Seddon, and over 50 in-person attendees – 10 December.	NODA
15	Webinar	Pan-ACE/SOC ACE webinar on strategic corruption led by Dr Tena Prelec, with panellists Dr Bertram Lang and Claudia Baez Camargo, critically exploring the concept and reflecting on the future direction of research on the subject. 110 persons attended – 20 February.	NODA
16	Engmnt.	Heather Marquette met with the World Bank’s lead on anti-corruption to share information on pipeline research and to explore potential collaboration – 20 June.	NODA/ ODA
17	Engmnt.	Heather Marquette met with the Director of the Global Anti-Corruption Consortium at OCCRP to discuss potential collaboration with the GACC and the potential for establishing a similar initiative on organised crime, something that was suggested by FCDO and HO colleagues as a potential collaboration to explore – 20 June.	NODA/ ODA
18	Engmnt.	Alexander Kupatadze and Heather Marquette met with EUROPOL to introduce SOC ACE’s work and to share research findings from Alexander’s forthcoming paper with Erica Marat on SOC, smuggling, trade-based money laundering and other displacement effects from Western sanctions on Russia following its invasion of Ukraine. Follow up on specific research is planned, as well as establishing links for future engagement – 06 March.	NODA/ ODA
19	Webinar	Heather Marquette joined Jessica Toale MP (Co-Chair, Labour Foreign Policy Group) and Tom Cargill (Director, Wilton Park & British Foreign Policy Group) as speakers on a BISA Security Policy & Practice Working Group panel on how better relationships can be built between academic, practitioner, and policy making communities working on security and foreign policy – 22 October.	NODA/ ODA
20	Engmnt.	Jonathan Goodhand and Patrick Meehan engaged with representatives from HMG, ODI, Brookings Institute, Humanitarian Dialogue, MSF, GI-TOC, and academia through their Policy Lab series under the second phase of their SOC ACE-funded paramilitaries project – multiple.	ODA
21	Engmnt.	Liam O’Shea and Louise-Alexander Berg’s RUSI Taskforce on Security Sector Reform involving representatives from FCDO, Home Office, MOD, State Department, USAID, INL, EU, NATO, USIP, the Dutch and German Foreign Ministries, UN Office of Rule of Law and Security Institutions, Transparency International, among others – 20 November & 27 March.	ODA
22	Event	Transparency International Ireland: Integrity at Work Week – Online Conference – Eliza Lockhart presented her research on a panel titled, ‘A look at the latest trends encouraging whistleblowing’ – 25 November.	NODA
23	Event	Olivia Allison presented to EU RELEX, the Working Party of Foreign Relations Counsellors, the body drafting sanctions in the EU, on trade sanctions and financial institutions, informed by Olivia’s research under the SOC ACE-funded Russian IFF project – 22 November.	NODA
24	Event	National Crime Agency HUMINT Academic Hub (HAH) Virtual Meeting, Eliza Lockhart was invited to present her research to a group of 30 participants – 28 November.	NODA
25	Event	Paddy Ginn of GITOC and part of the SOC ACE-funded research project on Balochistan participated on a panel at an Afghanistan side event of the Commission on Narcotic Drugs, with participants from the UN architecture – 12 March.	ODA
26	Event	Tena Prelec’s participation as a discussant/speaker on four panels at the ISA Convention, Chicago, drawing on her research under the SOC ACE funded Russian IFF project.	NODA
27	Engmnt.	Tena Prelec meetings with UNODC and UNDP on enablers of corruption, drawing on her research under the SOC ACE funded Russian IFF project.	NODA
28	Engmnt.	Tena Prelec engagements with National Endowment for Democracy on issues of kleptocracy. drawing on her research under the SOC ACE-funded Russian IFF project.	NODA
29	Event	Olivia Allison presented on sanctions evasion, middle corridor, and black sea at RUSI SIFMANet Learning Hour – 30 January.	NODA
30	Briefing	Olivia Allison presented to the Washington Institute for Near East Policy titled, ‘Illicit Trade and Sanctions: Lessons from The Last Three Years’ – 13 March.	NODA
31	Event	LJPC of the SOC ACE-funded Total Peace project convening the first meeting of Secretaries of Security & Government of cities where Total Peace is being negotiated, where Felipe Botero presented findings of the research, particularly regarding including key policy actors that have to date been excluded from the process – 21 February.	ODA
33	Event	Launch event of two new research papers by the research team of the Negotiating with criminal groups: Colombia’s Total Peace policy research project – March.	ODA
34	Event	2025 OECD Global Anti-Corruption & Integrity Forum. Eliza Lockhart has been invited to present her research as part of a side event organised by The National Whistleblower Centre in partnership with the Institute for Human Rights on how US transnational anticorruption laws use whistleblowers, journalists, and NGOs as a cornerstone in the detection of foreign corruption – 25 March.	NODA