Annual Review

Title: Mobile for Development Strategic Partnership (incorporating M4D Utilities since 2016)
Programme Value £ (full life): 38,897,334.00		Review Date: August 2019
Programme Code: 203804	Start Date: 4 January 2013	End Date: 31 March 2020

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019
Programme Score	A	A	A+	A++	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Upload pending
DevTracker Link to Log frame:	Upload pending

A. Summary and Overview

Description of programme

Since 2013, DFID and the GSMA Foundation have been working together under the Mobile for Development Utilities (M4D Utilities) programme (formerly Mobile–Enabled Community Services) to seize the opportunities of mobile technology for energy, water and sanitation.

Building on the success of the M4D Utilities programme, GSMA Foundation and DFID agreed to develop a wider strategic partnership - launched in February 2016 - with the aim of leveraging the power of mobile to improve the lives of 20 million people by 2020. DFID has committed £27.6m across 4 years (April 2016 to March 2020) to the strategic partnership. The GSMA’s yearly contribution was £2.9m (£1.8m direct contribution and £1.1m in-kind contribution) for a total contribution of £11.6m over 4 years.

Using private sector innovation and scale to realise the potential of mobile technology for development impact, the Strategic Partnership works in eight strategic areas under the Mobile for Development (M4D) portfolio:

1. Connected Society - Delivering digital inclusion: identifies innovation and new business models to (1) deliver coverage to remote areas that have traditionally been economically unviable and (2) accelerate mobile internet usage for the underserved.
2. Digital Identity - Enabling high impact digital identity services: supports mobile operators and partners in developing countries to (1) define and test new business models and (2) promote policy and regulatory environments that will unlock the opportunity for sustainable mobile-enabled digital identity.
  1. Digital Identity – CHOGM: help provide access to a digitally enabled identity for women and girls in the Commonwealth
3. Connected Women – Digital and financial inclusion for women: works with mobile network operators and key development partners to drive action to reduce the gender gaps in mobile internet and mobile money services.
4. Disaster Response - Ensuring mobile can be a lifeline in disaster: supports operators to play a role across the disaster lifecycle- from mitigation, to preparedness, response and recovery. This work has been scaled up and broadened under the scope of the separate Mobile for Humanitarian programme.
5. Ecosystem Accelerator - Acceleration of the digital ecosystem: aims to promote mobile operators as leaders of the innovation ecosystem and strengthen the opportunities for the implementation of collaborative partnerships between operators and start-ups (specifically in Africa and Asia). EA aims to enable the delivery of services and jobs for low income communities and contributes to the development of work on the science of scaling.
6. M4D Utilities – Acceleration of adoption of mobile-enabled energy, water and sanitation: supports the development of new technologies and business models leveraging mobile technology to deliver clean energy, water and sanitation to low-income communities
7. IPN Hub: catalytic funding to support industry utilities by offering a single point of integration between mobile money operators and service providers (in particular PAYG service providers). This integration delivers immediate services to customers and reduces transaction costs for both start-ups and MNOs.

In addition, and on a non-monetary basis (although initially co-funded by DFID), DFID participates in National Dialogues, funded by Swedish International Development Cooperation Agency (Sida). The National Dialogue convenes decision makers in the public sector and MNOs to demonstrate how mobile can be a positive force for societal change.

The Strategic Partnership makes contributions to all 17 of the Sustainable Development Goals, with key contributions in the areas of gender equality (SDG 5), reduced inequalities (SDG 10), clean water and sanitation (SDG 6) and affordable and clean energy (SDG7).

Figure 1 - Mapping of global goals to Mobile for Development projects funded under the DFID-GSMA Strategic Partnership. One project maps to multiple SDGs, so this visualisation includes double counting and per-row totals cannot be combined to reach the overall impact target.

Summary supporting narrative for the overall score in this review

In its third year, the Partnership has reached or exceeded all of its output and outcome targets, and most significantly, the end user impact target has already been exceeded with over 21.3 million beneficiaries impacted (considering double-counting, as explained in section C of this report, 17.6m of these being direct beneficiaries, and 71% being women). In addition, over £257m has now been leveraged in additional funding by the grantees invested in through the innovation funds.

The split per programme is the following (also represented in the figure below):
- Over 5.2 million beneficiaries (including over 2.7 million direct beneficiaries) impacted by M4D Utilities’ activities since inception in 2013 (with 47% being women), therefore benefiting from improved access to energy, water or sanitation services.
- Over 10.4 million beneficiaries (all women) directly impacted by Connected Women Commitment Partners that have become new mobile financial service or mobile internet users under the programme
- Over 1 million beneficiaries (including 635,538 direct beneficiaries) impacted by Disaster Response’s activities with mobile operators (49% of beneficiaries are women), are better able to manage disasters and shocks.
- 2.9 million beneficiaries (of which over 2 million are direct beneficiaries) impacted by Ecosystem Accelerator’s grantees (44% are women) are benefitting from digitally enabled services; from health, education and mobility to financial inclusion, jobs and improvements in access to markets.
- Over 1 million direct beneficiaries impacted by Digital Identity’s mobile birth registration service in Pakistan (with 72% being women), unlocking maternal and child services
- Over 777,000 beneficiaries (including 686,710 direct beneficiaries) impacted by Connected Society’s activities (with 47% being women) are now connected and digitally included.
- Over 750,000 beneficiaries of the IPN Hub, of which 46% are women, are able to access energy, agriculture and water services provided by start-ups connected to the IPN hub.

The Strategic Partnership theory of change is based on delivering impact through unlocking innovation (new technologies, services and business models), crowding-in private sector resource, scaling innovation, and advocating for enabling policy environments.

Progress from the third year of the Partnership has identified the following key lessons:

Effective private sector engagement model - GSMA M4D's model to engage the private sector (mobile operators and start-ups/ innovators) has demonstrated ability to unlock scale for social impact. This is evidenced by a third year of over-delivery for impact targets.

Virtuous circle of crowding-in - In Year 3 of the partnership, start-ups continued to enjoy high levels of follow-on funding, with £45m raised this year by grantees in Ecosystem Accelerator and M4D Utilities. There were increased numbers of partnerships between operators and start-ups (Ecosystem Accelerator), increased number of operators/service providers connected to the IPN Hub and increased number of actions taken by mobile operators to close the gender gap or increase mobile internet usage.

Cross-portfolio approach: Having the partnership cover a wide range of vertical services creates a rich environment for cross-pollination. Year 3 saw collaborations between mobile money and energy (IPN hub), Connected Women and Digital Identity – CHOGM (leading to a number of seminal insights on digital identity for women and girls) and Ecosystem Accelerator and mAgri (leveraging mAgri knowledge for start-ups such as Agrocentra).

The scale up of the IPN Hub is proven to be a success with operations expanded from Rwanda (original pilot market) to five new markets, connecting seven mobile money operators in the process and eleven service providers to date. However, it should be noted that the scale up and commercialisation of business model was slower than originally expected. This is due to a combination of factors such as MNOs having slow moving business processes and complex technical infrastructure.

The Digital Identity & CHOGM programmes have had challenges with getting digital identity services live in market. This is due to the nascent stage of the Digital Identity value proposition and Digital Identity being viewed more as an enabler of other services, serving as a foundation on which MNOs layer a broader service platform. Additionally, ongoing regulatory challenges or ambiguities leave operators hesitant to go to market. Despite these headwinds, the programme has been successful e.g. in Nigeria to convince the government to invite operators to express their interest to become licensed partners to support citizen enrolment into the new national digital ID programme.

After two years of challenges in Connected Society, the third year saw the programme focus and succeed in three areas: coverage maps, innovation fund for rural connectivity and Mobile Internet Skills Training Toolkit (MISTT). This re-focus has proven to be successful with the successful launch of the Innovation Fund and the strong appetite of MNOs in Ghana and Uganda to trial and deploy innovative solutions on their network. Additionally, MISTT and coverage maps have proven to be tools favoured by MNOs to facilitate coverage investment decisions in remote rural areas (maps) or increase usage in covered areas with a high return of investment (MISTT). For example, MTN Nigeria has used the country map to expand 3G coverage to 20 new sites, while the GSMA has partnered with all of Rwanda’s MNOs to support the national youth digital literacy programme with MISTT.

Innovation Fund: the number of rounds of innovation funding required for sufficient extraction of learnings varies depending on the topics of focus and the breadth and depth of the rounds themselves. Moving forwards, GSMA programmes will be nimbler and more market-driven on the topics that have innovation funding to better assess the optimum number of rounds to generate substantive learnings.

The DFID programme-funded post at GSMA has proven to be very effective at building bridges between the two organisations, optimising internal DFID coordination and profiling the Partnership work through different channels both internally and externally.

GSMA as a trusted partner on digital for development - GSMA M4D's reputation on digital impact has matured, resulting in knowledge products being frequently cited and team members often invited to speak at global fora.

There has been a strong ministerial engagement between GSMA and the UK government over the past 12 months. Examples include:

  - Engagement with Matthew Rycroft CBE - UK DFID Permanent Secretary

8th July 2019: the head of M4D attended DFID Leadership Conference 2019 Reception invited by Matthew Rycroft.

5th October 2018: GSMA London office technical workshop. Matthew Rycroft attended a 2hrs interactive workshop focused on core GSM technology and innovations in mobile for developing countries.

Friday 14th June 2019: the head of M4D was a panellist at DFID Digital and Frontier Technologies in International Development conference at Oxford University, with Matthew Rycroft opening keynote and panellist.
  - Engagement with Harriett Baldwin MP - UK Minister of State for Africa at the Foreign & Commonwealth Office and Minister of State for International Development (DFID)

Thursday 23 May 2019: Harriett Baldwin was invited at the GSMA London office visit and met with GSMA leadership to discuss the current GSMA-DFID Partnership, impact and SDG achievement to date, followed by a 60min workshop with the M4D team focused on humanitarian, gender, innovation funding and the future collaboration

Tuesday 16 July 2019: The Minister announced the extension to the Strategic Partnership during her visit to Nigeria, which was subsequently echoed on stage in Kigali at Mobile 360 to an audience of relevant industry stakeholders.

Recommendations for the year ahead:

Next phase of the Partnership: The Business Case for the next phase of the partnership was approved in July 2019. Over the coming year, the GSMA will operationalise the next phase, which includes landscaping and agreeing the scope of the CleanTech programme, ramping up the Assistive Technology programme (working closely with AT2030) and the launch the DFID demand-led cross-functional insights initiative. The GSMA will also prepare the pivot of their existing programmes towards the next phase of the Partnership as outlined in the new business case, including the centralisation of the Innovation Fund. – December 2019

Extend the current Accountable Grant to March 2022 with a no-cost extension to allow for the completion of i) the Connected Society innovation fund by March 2021 and ii) the third round of the Mobile for Humanitarian (M4H) innovation fund by March 2022. The rationale for the Connected Society extension is due to risks linked to customs clearance for imported goods and the M4H extension is detailed in the M4H 2019 Annual Review. As both programmes are under the same AG, we propose to extend it accordingly while simultaneously agreeing the MoU for the new Partnership – October 2019

IPN Hub: The GSMA and DFID will agree on the best option to ensure financial and commercial sustainability of the IPN Hub. Options appraisal to ensure growth and sustainability of the service is currently underway and will be presented in September 2019 and implemented in the following 6-12 months – October 2019

Do no harm: The global dialogue on the role of technology in society has changed over the past 3 years.  Breaches of consumer trust by large digital giants have raised the questions for consumers around the globe, and professionals working both in digital and in development are evaluating what approach they should take to strengthen the ‘do no harm’ practices incl. data protection and privacy.  GSMA has undertaken a preliminary look at the ethical considerations of digital development and in what ways GSMA programmes should embed consistent practices to ensure ‘do no harm’.  In year 4 of the partnership, GSMA will assess how to develop these recommendations further and incorporate them into the current portfolio and the next phase of the partnership – July 2020

- The GSMA will undertake the following activities under the new Partnership by July 2020;
  - Landscaping study on the future of Youth employment in SSA (in partnership with Mastercard Foundation)
  - Landscaping study on Data and AI for Development Impact (with DFAT, EPIC and Digital for Development) - pending agreement by DFAT
  - Landscaping study on Digital Health with the RED Health team
  - Increase number of coverage maps, to include a minimum of Sierra Leone and Malawi, based on demand from those country offices.

Analysis of the routes to scale (science of scaling) – building on the innovation fund portfolio (EA, M4D Utilities and M4H) and programmes like Connected Women. Such an analysis will collaborate with relevant partners (e.g. Wheeler Institute, London Business School) and will inform the next phase of the Partnership – July 2020.

GSMA will follow up on the implementation of the PwC due diligence recommendations (to be reviewed on quarterly basis);

PwC recommendations	Priority as set in the PwC report	Agreed actions
ToR not available for all advisory groups	M	A ToR will be drafted for each advisory group created as part of the next phase of the Strategic Partnership. Action for GSMA to propose which advisory group will make sense (note: it was agreed that, for Connected Women, only regular bilats with the DFID Gender Group could make sense)
No Internal Audit function which is responsible for conducting audits over the internal controls and processes in place. GSMA should continue to develop its internal governance function by developing a plan to undertake risk-based audits over its system of internal controls, which would also cover the Foundation’s activities and programmes.	H	There are currently various assurance procedures that operate to ensure the efficacy of the GSMA internal controls and processes. The GSMA voluntarily subjects itself to an annual external audit (conducted by KPMG) which includes the review of our systems and controls. The GSMA continues to assess (due to happen in October-19) its assurance arrangements, including the need for an Internal Audit, with its Audit and Risk Committee and the Risk and Compliance Committee in line with the guidance from UK Corporate Governance Code / Additionally, the GSMA Mobile for Development Foundation undergoes an A133 audit, specifically commenting on the internal controls within the Foundation including test of compliance with laws, regulations and grant agreements. / The GSMA also conducts various risk based internal reviews of its own processes and controls as and when required. Particularly, with respect to its downstream partners the GSMA is in the process of developing plans to undertake regular risk-based reviews / The results of the October assessment will be communicated to DFID and PwC
GSMA should consider consolidating a formal programme management methodology as a guidance for all programme teams to refer to, which defines the processes and documents required for programme delivery. This would ensure a consistent approach to the quality and delivery of the programmes.	L	An induction document for new joiners will be built
The Foundation/GSMA should consider enhancing its due diligence process over a sub-grantee’s internal controls for non-high/extreme-risk countries by performing reviews over the policies, processes and controls, in areas such as risk management, governance, financial compliance, anticorruption, safeguarding, fraud prevention and supply chain management.	L	This will be addressed by the downstream partners’ review process (currently ongoing) and reported as such
It is recommended that a formal consolidated version of the procurement policy should be created. This should cover the following requirements: • Legal requirements • Ethical considerations (e.g. Safeguarding, modern slavery, etc) • Confidentiality • Conflict of Interest • Accounting and Audit • Approvals and review process	M	Ongoing. GSMA will look at linking the different existing policies
The Foundation and DFID should agree a formal M&E approach that is tailored to measuring the indicators set out in the logframe and ensure that this is consistently applied across the programmes. The approach should define the objectives, processes and evidence required for each of the activities.	M	Already done
After the grant has been awarded, sub-grantees are contractually required to make books and records available for inspection and to permit the Foundation to audit financial and other records connected with the grant and project, however this is not necessarily something that the Foundation would carry out during the life of the grant. In order to give downstream partners further incentive to maintain proper financial processes and controls, the Foundation should include, within their contractual agreement, a request for downstream partners to submit their audited annual financial statements, where applicable, or other form of independent review. This will ensure that even if the Foundation do not perform annual inspection/audit of downstream partner’s records, they will be able to obtain external verification of the sub-grantee’s financial accounts. This will be increasingly important as programme activities move into higher risk countries	M	This will be addressed by the downstream partners’ review process (currently ongoing) and reported as such
Sub-grantees are required to provide supporting receipts for all expenses above £500 to the external Fund Manager for review. We were informed by the Finance and Compliance team that this applies to all programmes as per the requirements from DFID. The Foundation should consider requiring all expenses incurred by sub-grantees to be accompanied with a supporting receipt. If this is not practicable, then a formalised approach should be implemented which requires further evidence from sub-grantees which have a high volume of expenses under the threshold.	M	This will be addressed by the downstream partners’ review process (currently ongoing) and reported as such. / The GSMA Foundation will update the sub-grant agreement to strengthen the clause related to the requirements of backups for £500 or more, also adding that the sub-grantee will need to be able to share at any time the backup of all the expenditures.

## B: DETAILED OUTPUT SCORING

Output Title	Operators actively engaged with GSMA M4D and our partners to implement partnership activities that will improve mobile access and usage
Output number per LF		1	Output Score	A+
Impact weighting (%):		50%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress (please ensure data is disaggregated where possible)
1.1 – Number of documented commitments received from operators to take a concrete action to increase mobile access and usage (cumulative)	308	Exceeded – 321
1.2 – Number of cases with evidence of concrete actions (e.g. implementation of project) being taken by operators (cumulative)	109	Exceeded – 116
1.3 – Number of low/medium-income countries actively represented within M4D-driven activities (cumulative)	63	Exceeded – 70
1.4 – Intensity/quality of MNO engagement (qualitative)	Medium	On track

Briefly describe the Output and provide supporting narrative on the score

This Output demonstrates the engagement that the GSMA M4D programmes have had with mobile network operators, the actions taken by operators and the reach of the partnership across markets. Overall, all programmes (with the exception of Digital Identity, CHOGM and IPN Hub) in the partnership either achieved or exceeded June 2019 output 1.x targets, reflecting the high level of engagement that the GSMA workstreams have had with Mobile Operators and the actions taken by them. The disaggregation per programme is detailed below.

  1. - Number of documented commitments received from operators to take a concrete action to increase mobile access and usage
  2. - Number of cases with evidence of concrete actions (e.g. implementation of project) being taken by operators

Connected Society: The programme achieved 4 additional commitments, meaning a cumulative total of 26 (+2 versus target) and 6 cases with evidence of concrete action being taken by operators (+5 versus target). On coverage, the programme successfully collaborated with MTN Nigeria who used the country coverage map produced by GSMA to deploy 20 new rural sites, therefore extending 3G coverage in the country. The programme also signed letters of agreement (LoA) with MTN Uganda and Vodafone Ghana to collaborate on the new Innovation Fund for Rural Connectivity.

On usage, the programme signed an LoA with Vodacom Tanzania for the implementation of MISTT and is collaborating with Facebook to launch MISTT in partnership with mobile operators in a number of new markets. The first launch took place in June 2019 in Myanmar in partnership with Ooredoo Myanmar.
In addition, the programme has successfully supported operators to deploy the MISTT toolkit: MTN Uganda, Vodacom Tanzania, Orange Burkina Faso and Banglalink Bangladesh implemented/are implementing pilots using MISTT to deliver digital skills training, reaching over 160,000 people to date. Results from the first phase of the deployment in Bangladesh can be seen below.

Connected Women: The programme achieved 2 additional commitments, meaning a cumulative total of 54 (+2 versus target) and 8 cases with evidence of concrete action being taken by operators (+5 versus target). The Connected Women Commitment Initiative received an additional 2 commitments, bringing the cumulative total to 54 Commitments, by 38 operators, to take concrete action to reduce their mobile money and/or mobile internet gender gap (note: some operators have made more than 1 commitment, and 4 of these Commitments are no longer active as the MNO no longer exists, has been acquired or no longer recognises the Commitment).

In addition, there were an additional 8 cases with evidence concrete action(s) taken by Connected Women Commitment Partners this year. Examples of actions include affordability initiatives (device financing), safety initiatives, and mobile money platforms for female merchants.

Digital Identity: The programme achieved 5 additional commitments, meaning a cumulative total of 8 (+2 versus target) but only 1 case with evidence of concrete action being taken by operators (-1 versus target). Vodafone Ghana committed to develop and test an economic identity product focusing on the Olam Cocoa Farmers in Sefwi Wiawso in Ghana. The programme supported Vodafone to launch the minimal viable product, allowing iterative qualitative trials to test and refine the concept with a small audience, prior to a larger scale launch. This launch is currently on hold, due to the change of CEO at Vodafone Ghana.

In addition, Telenor Group signed a commitment letter with the Digital Identity programme to produce a sustainability map of the mobile-enabled birth and death registration platform in Myanmar, which is currently being piloted by Telenor Myanmar and Unicef. This will help inform Telenor’s decision to scale the platform once the pilot is finished.

After engaging with the programme to research the identity challenges faced by small-scale fisheries, Mobitel Sri Lanka committed to develop and pilot an economic identity platform for fisher folks, which is linked to a customer’s eKYC-verified SIM. Finally, In June 2019, both MTN Zambia and Zamtel Zambia committed to work with the programme to develop, test and implement a digital identity for Social Benefits platform in Zambia, in an industry-wide collaboration.

CHOGM: The programme engaged with different MNOs throughout the reporting period (e.g. Sierra Leone, Rwanda). The programme received interest from Telenor Easypaisa Pakistan to develop and pilot an economic identity platform targeting female garment workers in Karachi. However, due to acquisition of Easypaisa by another entity, subsequent changes in management and de-prioritisation of this project, this project is currently on hold.

Ecosystem Accelerator: The programme achieved 11 additional commitments, meaning a cumulative total of 27 (+7 versus target) with all of them converted in actions by operators (+6 versus target).

Over the last year the programme has successfully facilitated 11 additional partnerships between start-up grantees and mobile operators across the portfolio, supporting them on their respective routes to scale. Examples of new partnerships include Agrocenta’s (Ghana) partnerships with Orange and Vodafone to integrate mobile money within their services, Twiga Foods (Kenya) partnership with Safaricom to simplify the transactions process, and Kargo (Myanmar) receiving bulk data services as part of their new partnership with Telenor.

M4D Utilities: the programme achieved 4 additional commitments, meaning a cumulative total of 33 (+1 versus target) with all of them (+ 1 additional commitment from last year) converted in actions by operators (on target).

Examples of these partnerships include the provision of market insights to Telma Madagascar for them to define their strategy and the creation of their partnership with Greenlight Planet (PAYG Solar Home System). Another example is CityTaps (current grantee) who achieved a partnership to scale their GSMA project with Orange Burkina Faso in addition to their existing partnership with Orange Niger.

IPN Hub: The programme achieved 11 commitments (9 below target) with 7 cases with evidence of concrete action being taken by operators (8 below target). Despite operational challenges (see lessons learned) the IPN Hub project succeeded in expanded operations from Rwanda (original pilot market) to five new markets (Uganda, Kenya, Tanzania, Malawi and Nigeria) connecting seven mobile money operators in the process (MTN Uganda, mSente, Safaricom, Finserve, Airtel Tanzania, Airtel Malawi and Swifta) and eleven service providers to date. Furthermore, four other mobile money operators confirmed their commitment to connect to the IPN Hub (Airtel Zambia, Orange Senegal, Vodacom Mozambique and Wari in Senegal) which could potentially lead to an increase in the number of markets covered by the IPN Hub

Disaster Response: 9 new signatories (Telenor subsidiaries in Pakistan, Myanmar, Bangladesh and Scandinavia); DTAC Thailand; Digi Malaysia; AsiaCell) joined the Humanitarian Connectivity Charter, bringing the programme’s cumulative total to 162 commitments.

1.3 – Number of low/medium-income countries actively represented within M4D-driven activities (cumulative)

The cumulative total figure of 70 low/medium-income countries excludes double counting as many programmes work in the same country. The markets include those represented in programme activities.

1.4 – Intensity/quality of MNO’s engagement (qualitative)

Output 1.4 was introduced in the 2017-18 Annual Review as part of Altai’s midline evaluation. In 2018, Altai made an assessment of qualitative data from interviews they conducted with GSMA staff and MNOs and awarded a score of ‘medium’ against the indicator.

In order to measure this indicator in the absence of external evaluation, each programme team came together and reflected on their MNO engagements from the past reporting year. They graded each MNO engagement in keeping with the scale definitions, and then nominated one example each for strong, medium and weak type of engagement which were then discussed in depth. Responses were analysed to pull the following main findings and trends.

The M4D programmes registered a majority of strong or medium intensity engagements with MNOs, and a few weak ones. The teams undertook a reflection exercise to help identify a set of factors which can characterise the quality of MNO engagement:

Buy-in from the senior management: Nearly all strong MNO engagements across all programmes relied on support from senior MNO staff in global or regional headquarters. Top-level buy-in was found to be a necessary condition to ensure high quality engagement.

Face-to-face engagement: Teams reported that having face time with MNOs at critical junctures of a project or collaboration significantly improved the quality of engagement. The EA and M4DU teams met with the (prospective) MNO partners of Innovation Fund grantees early on during the due diligence visit which contributed to strong MNO engagements later. Programmes which had staff stationed in regional offices experienced more active engagement with MNOs.

Dependencies: Engagements with high number of dependencies (e.g. partners, stakeholders, regulations, approvals required etc) were observed to be generally weaker as MNOs had less control on driving the engagement forward. The sensitivity of the domain of product or service, as well as the regulatory environment in the MNO’s market played an important role in determining the type and extent of dependencies.

Alignment with MNO strategy or objectives: This was a critical factor in determining the initial uptake as well as the continuation of an engagement with MNOs. A few engagements were classified as weak because of a lack of alignment between the MNO’s own strategic objectives or needs and the programmes’.

Resourcing actions from MNOs: Strong engagements were characterised by MNOs taking action to transform ideas into action, for instance allocating staffing (e.g. dedicating technical and market engagement teams for a digital literacy toolkit deployment) or committing technical expertise for a digital identity project. In some cases, the engagement was formalised as a KPI for the MNO staff, which was impactful especially when targets were set at a Group level as they cascaded down to country level (as for the example from the Connected Women programme).

Other factors: Some other factors which were proportional to the quality of engagement were for specific engagement or programmes were: maturity of start-up supported by the Innovation Funds (with more mature start-ups generating more interest from operators), visibility potential offered by the GSMA through videos and other promotional material (with more visibility generating better engagement), internal MNO politics and externalities such as mergers and acquisitions, political crises or natural disasters.

Lessons identified this year, and recommendations for the year ahead linked to this output

IPN Hub: The scale up of the IPN Hub is proven to be a success with operations expanded from Rwanda (original pilot market) to five new markets, connecting seven mobile money operators in the process and eleven service providers to date. However, it should be noted that the scale up was slower than originally expected. This is due to a combination of factors such as MNOs having slow moving business processes and complex technical infrastructure.

Digital Identity & CHOGM: The programme struggled to gain traction to pilot digital identity services in market. This is due to the nascent stage of the Digital Identity value proposition and also Digital Identity being viewed more as an enabler of other services, serving as a foundation on which MNOs layer a broader service platform. Additionally, ongoing regulatory challenges or ambiguities leave operators hesitant to go to market. An innovation fund will be more effective in testing Digital Identity services and could accelerate interest from MNOs.

M4D Utilities: In a major shift for the MNO and energy sectors, over the last 12 months, the programme has received numerous requests and had a select number of bilateral engagements with MNOs (e.g. Orange Group, MTN, Telma Madagascar) interested in developing a pay as you go strategy for mobile-enabled utilities services (particularly energy). There is a growing appetite to take action, even without the direct availability of grant funding. This type of engagement requires time and effort to help MNOs build their business case and consider partnerships with service providers. Currently the programme has constraints which limit how much support can be provided; in future the programme should build a strategy to provide more leadership in this area and be able to provide the critical brokering role.

Connected Society: After the challenges that the programme faced in the first two years of the Partnership, the programme applied the recommendations set out in last year’s review and has now focused its activities on three areas: coverage maps; innovation fund for rural connectivity and MISTT. As evidenced by this year’s results, this re-focus has proven to be successful with the successful launch of the Innovation Fund and the strong appetite of MNOs in Ghana and Uganda to trial and deploy innovative solutions on their network and MISTT and coverage maps proving to be tools favoured by MNOs to facilitate coverage investment decisions in remote rural areas (maps) or increase usage in covered areas with a high return of investment (MISTT).

Ecosystem Accelerator & Connected Women: These programmes continue to be successful, proving that their respective model of operation (e.g. commitment campaign for Connected Women or setting up partnership between start-ups and MNOs) is fit for purpose.

Progress on recommendations from last year: Output indicators 1.1 and 1.2 were amended as suggested and Connected Society has focussed on its Coverage Maps, MISTT and the Innovation Fund in order to more fully engage MNOs on the issue of rural coverage, with strong successes.

Output Title	Technological innovations and business models selected and funded by the Innovation Fund
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress (please ensure data is disaggregated where possible)
2.1 Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)	2,804	Exceeded – 2,830 applications were received / (Geographical detail of EA fund below)
2.2 Number of grantees of the Innovation Fund (disaggregated by geography)	84	Achieved- 84 grantees / (Geographical detail of EA fund below)

Briefly describe the Output and provide supporting narrative on the score

During the last reporting year, the Connected Society Programme announced an open call for its first innovation fund targeted at solutions to tackle the coverage gap by increasing rural connectivity and selected three grantees. The Ecosystem Accelerator programme selected eleven grantees for its third round of innovation fund. Neither M4D Utilities or Disaster Response (now part of Mobile for Humanitarian Innovation Programme) ran new calls in this reporting period.

The inaugural round of the Connected Society Innovation Fund for Rural Connectivity launched in October 2018 and attracted 36 expressions of interest (+26 versus target) from consortiums of suppliers based in 15 countries. Of these, 19 applications were invited to submit a full proposal, five of which were shortlisted for recommendation to the Fund Panel. Two applications were selected outright by the panel, which convened in March 2019, and two more were shortlisted, pending requests for clarification. The fund will now be moving forward with three sub-grantees (and their consortium partners), one of whom will be partnering with MTN in Uganda and the other two who will partner with Vodafone in Ghana.

For Round 3 of the Ecosystem Accelerator innovation fund, of 27 short-listed applicants 11 start-ups from 10 countries were selected by an independent fund panel, 6 in Africa and 5 in Asia Pacific. As Round 2 and Round 3 are funded by DFID (60%) and DFAT (40%), 7 additional grantees are counted as part of the DFID logframe for the Ecosystem Accelerator programme. This increased the total portfolio of start-ups to 25. The full portfolio can be found here whereas the list of start-ups funded as part of the Round 3 is found in the figure below.

Lessons identified this year:

Overall, the Ecosystem Accelerator model, especially in regards to profile grantees at big events (such as Mobile World Congress 2019) as well as bootcamps has been proven very successful. This provides opportunities for the start-ups’ teams to meet and pitch to individuals that would help accelerate the socio-economic impact of their businesses. It also brings opportunities for start-ups to meet international donors, investors, mobile operators and tech hub representatives.

Through the first round of the Connected Society fund, it has become apparent that this fund is a particularly complex fund to manage due to a number of factors: (1) necessity to get the buy-in from MNOs to implement innovations on their own mobile network; (2) dependency between the GSMA-sub grantee contract and the MNO partner-sub grantee contract; (3) need to ensure asset transfer to the MNO partner at the end of the grant period; (4) tighter restrictions around match funding; (5) the need to secure customs wavers and tax levies on imported infrastructure.

Recommendations:

Use the Ecosystem Accelerator model throughout all relevant social-enterprise orientated innovation funds in the second phase of the Partnership (i.e. not Connected Society).
Owing to the slow development of technological innovations around coverage, it is recommended that the second round of the Connected Society fund focuses on innovative solutions to tackle the usage gap.

Progress on last year’s recommendations:

Output indicators 2.1 and 2.2 were amended to reflect the Connected Society programme launching an innovation fund. The risk identified in some EA and M4D Utilities grantees not completing their grants prior to March 2020 has been mitigated, with only the Connected Society innovation fund at risk of slippage (as referenced earlier) – hence the recommendation of a no-cost extension.
Output Title	Research, insights and learning generated and disseminated by the partnership and used by stakeholders
Output number per LF		3	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress (please ensure data is disaggregated where possible)
3.1 – Usage: number of publications' downloads from the GSMA M4D website and physical distribution (content relevant to the partnership) (cumulative)	32,901	Exceeded – 43,432
3.2 – Thought leadership: Number of publications which demonstrate new insight including reports, blog posts, case studies and videos (cumulative)	125	Exceeded – 139
3.3 – Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings (cumulative)	168	Exceeded – 193

Briefly describe the Output and provide supporting narrative on the score

Overall, the partnership exceeded all June 2019 milestones. This was due to the programmes’ success in generating new insights, along with strong support in encouraging research uptake via social media (and other channels). The GSMA events (Mobile World Congress, M360 events) also added significant impact in disseminating research as well as increasing profile of the programmes as well as DFID.

In addition, and independently of the logframe, GSMA tracks the number of high-level stakeholders who cite / endorse GSMA positions. From April 2018 to March 2019, 31 key stakeholders have cited / endorsed GSMA positions on Digital Identity, Connected Women, Connected Society, and M4D Utilities. Examples include W20, G20, OECD, World Bank, UNESCO, CITEL, CGAP, Asia Clean Energy Forum, UN Ecosoc, or World Water Week.

Output 3.1 – Usage: number of publications' downloads from the GSMA M4D website and physical distribution (content relevant to the partnership)

Reports and case studies by the six Partnership programmes have been downloaded, physically distributed or viewed online a cumulative total of 43,432 times, which exceeds the Year 3 target of 32,901.

Output 3.2 – Thought leadership: Number of publications which demonstrate new insight including reports, blog posts, case studies and videos (cumulative). Overall the programmes produced 36 publications with new insights over the reporting period, bringing the cumulative total to 139 and exceeding the target (125).

Connected Society: generated 4 publications, reaching a cumulative total of 14 and exceeding the target of 12. These include: the Rural Connectivity Innovation Case Study: Cellcard Cambodia and Solar Power; Rural Connectivity Innovation Case Study: Using light sites to drive rural coverage – Huawei RuralStar and MTN Ghana; Triggering Mobile Internet use in Cote d’Ivoire and Tanzania report; and, Mobile Internet Skills Training Toolkit: Banglalink Pilot Evaluation.

Connected Women: produced 4 publications with new insights, bringing its cumulative total to 20 and meeting the Year 3 target. The publications include: The Gender Analysis and Identification Toolkit, The Mobile Gender Gap Report 2019, Mobile Gender Gap Report 2019 Methodology, and the 2018 EQUALS Access Coalition Progress Report.
Digital Identity: published 6 new publications, reaching a cumulative total of 21, exceeding its target of 20. The reports include: Mobile DI solutions, financial inclusion and birth registration; Innovative Mobile solutions linking health and Identity; Access to Mobile Services and Proof of Identity 2019, Mobile-enabled economic identities for smallholder farmers in Ghana; Identity and Urban Poor; and Understanding Capture and Validate KYC processes: Global Experience, Challenges and Learnings.

CHOGM: introduced the first research pieces, specifically targeted to Commonwealth countries, including 4 Digital Identity market opportunities for Malawi, Zambia, Uganda and Sri Lanka; Policy insights on 10 countries exploring the Gender Gap in Identification; and an end-user on the Digital Identity opportunities for women from Nigeria, Bangladesh and Rwanda.

Ecosystem Accelerator: published 8 new publications, reaching a cumulative total of 16, exceeding its target of 10. introduced three new insights focused on “Start-ups and Mobile in Emerging Markets- Issue 3, Issue 4, and Issue 5 rebranded as the “Ecosystem Accelerator Compass”. Five new video case studies about Round 2 and Round 3 start-ups (Sehat Kahani, Joonak, eFishery, Ensibuuko and Coliba) have been produced as well.

M4D Utilities: generated 8 new publications, reaching a cumulative total of 48 and exceeding the initial target of 45. This includes the annual report Intelligent Utilities for All, the CityTaps case study video Delivering water to urban homes through smart metering and mobile payments; Mobile money transaction fees and utility bill payments in emerging markets; Mini-grids, macro impact?; Supporting waterless flush sanitation through mobile technology – Loowatt; Digital payments in water: Findings from two new research projects; World Toilet Day – to flush down the sanitation challenge, we need to think beyond toilets; From pay-as-you-go solar to pay-as-you-go smartphones and cookstoves.

No insights were planned for the IPN Hub in this reporting period. All Disaster Response insights are reported as part of the Mobile for Humanitarian programme.

Output 3.3 – Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings.
Together, all programmes organised, hosted and/or participated at (speaking or sitting on a panel) 66 convenings during the reporting period. This brought the Partnership’s cumulative total to 193, exceeding its Year 3 target of 168.
GSMA events, such as m360 Africa in Rwanda and Mobile World Congress 2019 in Barcelona served as key platforms to share insights and learning with industry and the development community. The programmes also disseminated their messaging and facilitated discussions with key stakeholders as various external events and international platforms, including the W20 Summits (Argentina, Japan), The United Nations General Assembly, the World Economic Forum, Women Deliver, World Summit Information Society, FIGI Symposium, Africa Utility Week, East Africa Com, West Africa Com, and many more.

Lessons identified this year, and recommendations for the year ahead linked to this output:

It is clear from the continuing rise in downloads and invitations from other practitioner forums that the Partnership’s programmes are increasingly recognised as thought leaders in their respective areas.

Dissemination strategy: Across the programmes, multiple channels are used, delivering tailored content and messaging to help promote the various insights and outputs. In terms of channels, we use social media (Twitter, Facebook and LinkedIn), email newsletters, blog posts, partner platforms and press releases. Through these, we provide various media types (videos, GIFs, imagery, infographics) and depending on the relevant objective, paid promotion per channel (using targeting criteria across demographic categories). Each programme will usually also base their marketing around specific events, both internal and external. These can include UN days (World Toilet Day, for example), GSMA MWC and Mobile 360 series events and partner/external conferences, such as Women Deliver and UNGA.

Recommendations: Although GSMA insights are well adopted overall, it is doubtful that industry stakeholders have the time to absorb all the insights produced in a year (36 for this reporting period). It is proposed that, in the next phase of the Partnership, GSMA produces less but consolidated insights and concentrates on the dissemination of them.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

By 2020, the Strategic Partnership aims to impact over 20 million people (directly and indirectly) with improved access and use of life-enhancing mobile-enabled services, contributing to the achievement of the Sustainable Development Goals. The programme aims at achieving these impact targets through outcomes in the following areas:
- Identify and support new business models and/or new technologies with the potential to improve people’s life (at least 67 by 2020)
- "Crowd-in" further replication of the innovations and follow on funding (at least £295m by 2020)
- Scale innovations to ensure long term commercial sustainability (at least 27 by 2020)
- Influence key stakeholders to implement changes in policy that will enable these services to flourish (at least 22 stakeholders by 2020)

M4D’s approach to achieve impact is three-fold:
1. “Think”- Research and Insights to unlock new models – M4D generates, identifies and disseminates insights and learning, through applied research, case studies and industry reports.
2. “Do” - Demonstrate and encourage crowding in – M4D works with operators and innovators to launch, test and improve early stage innovations with the potential for high social impact and commercial sustainability.
3. “Advocate” - Tell the story to help drive change – M4D convenes the private sector, philanthropic community and government to share best practice and advocate for more enabling policy environments.

Through this approach, M4D delivers increased access to and use of life-enhancing mobile-enabled services; accelerating socioeconomic improvements for the underserved, especially women, youth and rural populations. The theory of change that supports the partnership is illustrated below.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Summing all beneficiaries across programmes, the Strategic Partnership has impacted more than 21.2 million individuals, (6 million of these in the past year), exceeding the 20.5m target for this reporting period. This figure for impacted users represents beneficiaries in 39 countries across Africa, Asia Pacific and the Caribbean.

As the six programmes under the strategic partnership operate in similar geographies, the GSMA has undertaken work to remove the risk of double counting in the top ten beneficiary markets. Based on this assessment, a total of 838,591 users have been discounted – leading to the reported total of 21,262,376 users in this report and associated logframe.

Regarding the Partnership’s outcome indicators, they are either on track or exceeded:

Outcome indicator 1: Number of new services (technological innovations, services and business models) supported through the partnership. This indicator has been achieved with 62 innovations in total (against a target of 62), with 10 incremental this year alone. The services counted here come from the innovation fund as well as other programmes such as Digital Identity or Connected Society. The details per programme are:

Connected Society (2 additional this year): Banglalink (Bangladesh) embedded the MISTT toolkit into their own self-care application: using this application, customers can prove that they have completed the modules, the data for which is zero-rated, and can get free data as a reward. In addition, MTN Nigeria used the Coverage Maps to deploy new sites (see box below).

Ecosystem Accelerator (4 additional this year – see box below): Out of the 11 grants awarded by Ecosystem Accelerator in its third round, 7 projects were categorised as new value propositions (Pacific Ads Group, SkyEye, Greenovator, Eziti, Agrocenta, and Coliba) or launch of an existing value proposition in a new market (Eneza) and therefore are counted as part of outcome indicator 1. Due to the funding split between DFID (60%) and DFAT (40%), 4 additional projects are counted in the DFID logframe in this reporting year. The projects selected also contributed to two new learning agenda items for the programme, meaning supporting lesser developed ecosystems (e.g. Pacific Ads Group in Papa New Guinea, Coliba and Eneza in Cote d’Ivoire & Skyeye in Samoa) and business models for scale (Agrocenta in Ghana and Eneza).

Digital Identity (1 additional this year): Vodafone Ghana’s economic ID platform for farmers is building on Vodafone’s in-house identity capabilities and provides farmers with a single source of access for their profiles. The programme conducted research to identify key data to build a credit-scoring algorithm to inform the development and design of the economic identity platform.

IPN Hub (3 additional this year): the IPN Hub service has on-boarded service providers delivering three additional use cases beyond PAYG Solar: Clean Cooking (Inyenyeri in Rwanda); Agriculture (Farmerline in Kenya); Water (e.g. Upande, Lilongwe Water Board and Wonderkid).
The Ecosystem Accelerator has a diverse Round 3 portfolio with technologies ranging from ed-tech, agri-tech, citizen engagement, health tech and job matching. This includes Coliba in Cote d’Ivoire, which is deploying a large scale and mobile-supported value chain in 10 districts across Abidjan to collect, sort, store, recycle and resell plastic waste from households and businesses. For the first time two start-ups in the Pacific region, Papua New Guinea (Pacific Ads Group) and Samoa (Sky Eye), are represented in the portfolio.
Connected Society supported MTN Nigeria to tackle the rural coverage gap in an economically sustainable way: MTN Nigeria used the Coverage Maps developed by GSMA to identify areas appropriate for coverage, segmenting them by type of technology and type of investor. With its new coverage mapping tool, Connected Society is supporting operators to increase the efficiency of their infrastructure investments by helping them locate and target uncovered areas with sufficient economic potential to deploy profitable sites. The tool overlays very high resolution population distribution data with the coverage footprint of the mobile operators in the market. This allows operators to identify the areas which are not covered by any operator, as well as to estimate the exact location and amount of population living in those areas. Furthermore, using this data, the GSMA has developed an algorithm to generate a list of the most promising uncovered sites, along with the recommended site configuration (macro site, small site) that yields the highest ROI and maximizes revenues.
Murad is part of the beneficiaries of the MISTT deployment by Banglalink who are now making the most of the internet. He lives in Dhaka, works in a drugstore and he lives with his wife and their two children.
Murad says that he was an analogue person before, and now considers himself as a “digital person”.
“I had simply no idea about Internet before the training and I feel pretty confident and my usage has gone up greatly. If I don’t know about something, I can always google about it. I can also search on YouTube to learn any tutorial. I need almost 2-3 GB of data per week and very often, I have come running to the shop just after my internet was used up.”
“My family can talk to my younger brother living in Saudi Arabia. Earlier we had to talk via a voice call. Now we use WhatsApp, Messenger and IMO. We use the video call feature to see him directly. Previously, I used to recharge BDT 99 which won’t even last a week. I can now watch BPL matches through live streaming on YouTube. I watch songs and funny videos and my children can now watch cartoons.”
There was a time when many people used to tag him in different indecent Facebook posts but the retailer has trained him how to avoid being tagged in those posts.
Murad is also very proud to share that he has also taught his family members how to use WhatsApp and Facebook.

Outcome indicator 2: Number of changes in policy as result of programme activities or cases where GSMA is actively supporting the creation of a more enabling policy environment.

The GSMA exceeded this indicator, achieving 15 results (5 from the reporting period), vs. a target of 14.

Connected Society (1): The Comision Interamericana de Telecommunications (CITEL) used the Connected Society Enabling Rural Coverage report in its recommendations on rural infrastructure. These recommendations was subsequently approved at the 33rd PCC.I CITEL meeting held in Washington (August 2018). The approved text recommends that Member States facilitate the adoption of regulatory frameworks that support the deployment of infrastructure in rural and remote areas, identifying necessary changes to be made on regulatory policy and in models to achieve universal access. It also recommends Member States and Sector Members to contribute with the compilation of documents, experiences and best practices about supporting the deployment of infrastructure in rural areas to reduce the connectivity gap.

Connected Women (2): the programme successfully included its core messaging at two global fora: the W20 Argentina 2018 Communique to the G20 following the W20 Argentina summit, which identified four key areas for priority action, including digital inclusion for women, and called on the G20 to ensure women’s digital inclusion by: “Developing holistic and cross-sectoral policies that abolish the barriers to women's access and use of digital technologies and the internet, especially in rural and remote areas. Improve access, affordability, safety and security of digital services, broadband and connectivity plans, and the availability of relevant content and services, while taking into consideration women in all their diversity.” This messaging was adopted by the G20 which emphasized the need to address the digital gender divide in the G20 Leaders Declaration and the G20 Digital Economy Ministerial Declaration.
Connected Women was also included in the W20 Japan 2019 Communique, which emphasized the importance of mobile and is being further expanded on through an accompanying Action Plan.

Digital Identity (2): In Nigeria, the Digital Identity programme facilitated several discussions with key stakeholders (the government, National Identity Management Commission (NIMC), the World Bank, ICT regulator, and all four MNOs) on the role MNOs could play as trusted digital Identity partners to the government. As a result, the NIMC invited operators in April 2019 to formally express their interest to become licensed partners to support citizen enrolment into the new digital ID programme. This was a welcome policy change that paved the way for MNOs to play a much more ‘hands on’ role in enabling millions of currently unregistered Nigerians be digitally and financially included. The Digital Identity programme spearheaded a similar effort in Uganda that began in August 2018, which resulted in a commitment by the Government of Uganda (in March 2019) to pursue a mobile-enabled digital ID platform which, when implemented, will enable millions of mobile users in Uganda to access more than 100 e-government services.

Outcome indicator 3: Number of services (inc. technological innovations and business models) supported or influenced by the partnership and that are reaching early indication of scale.

The GSMA exceeded this indicator, achieving 19 results (9 from the reporting period) vs a target of 16.

One of Connected Women’s commitment partners, Vodafone Idea India – Sakhi, has reached millions of users, well above the programme’s 100,000 users threshold (see below box).

Six Ecosystems Accelerator-funded grantees have raised over $1 million in additional non-grant funding:
  - Round 1 grantees
    - Safemotos (undisclosed)
    - Twiga raised over £4 million

  - Round 2 grantees
    - eFishery raised over £2.9 million (see below box)
    - Farmcrowdy raised over £1.5 million
    - Kargo raised more than £800,000 in new funding
    - Lynk raised over £1.2 million

  - Round 3 grantee – Qlue raised more than £1.1 million

The IPN Hub reached scale in Rwanda with 715,310 beneficiaries, above the 400,000 threshold.

In year 1 of the Partnership, M4D Utilities already reported Wonderkid as having reached scale (809,768 beneficiaries). Since then, Wonderkid, with the support of the programme, has replicated its product in two additional countries (Malawi and Nigeria) and is serving over 22 water utilities across Africa (including Malawi and Nigeria) with a total population of those 22 utilities at over 25 million people. As discussed with DFID, we are not reporting these figures as part of the impact target of the Partnership but chose to count the replication of Wonderkid as an additional example of reaching scale (see below box).

eFishery | Indonesia | Founded in 2013| Crowding-in: £2.9m
eFishery offers an Internet of Things (IoT) and mobile-based smart feeding solution to improve efficiency and accountability in fish and shrimp farming
Following the funding that was secured from GSMA Ecosystem Accelerator in February 2018, eFishery was successful in attracting further substantial commercial investment backed by series of global investors such as Aqua-spark, Wavemaker Partners, 500 Startups, Maloekoe Ventures, Social Capital, Unreasonable Capital and Triputra Group

Vodafone Idea India launched the Sakhi pack in 2017 with support from Connected Women in evaluating the pilot. They went on to launch the Sakhi opt-in service nationally in October 2018, promoting it to women through mainstream media as well as targeting them in female environments (e.g. women’s college campuses). The Sakhi service is exclusively for women customers and delivers three key features: emergency alerts, emergency balance and private recharge. All features work on even the most basic handset. Within months of its launch, more than a million women subscribed to Sakhi. Research found Sakhi has had a positive social impact on women, increasing social, human and positive psychological capital.

In May 2015, Wonderkid received a grant from M4D Utilities to develop a suite of mobile tools for 4 water utilities in Kenya. The grant supported a complaint management and tracking system that allows customers to report maintenance and upkeep issues. It also offered a mobile app for meter readers that allows meters to be photographed, helping to address disputes and verify meter readers’ activities in real time. A self-meter reading and payment system allows users to send their own meter reading via SMS and receive a preliminary bill with instructions for paying via mobile money using Safaricom’s M-Pesa.
At the end of the grant Wonderkid reported they had reached 809,768 beneficiaries of which 50% were women.

As of December 2018, using the tools developed and improved during the project, Wonderkid have reported unprecedented scale and is serving over 22 water utilities across Africa (including Malawi and Nigeria) with a total population of those 22 utilities at over 25 million people (taken from WASREB regulatory Impact report for the Kenyan utilities and b) in-house utility data from the regional implementations in Nigeria and Malawi)

In addition to direct funding, M4D Utilities facilitated connections between Wonderkid and the Lilongwe Water Board (grantee) and have provided numerous speaking opportunities including at the UN High Level political forum.
Outcome indicator 4: Amount of additional £ funding mobilised for the technological innovations and business models trialled through the innovation fund.

This indicator has largely exceeded its targets by 14% (actuals of £257.5m instead of planned £226m): This includes additional funding from M4D Utilities phase 2 and phase 3 (£225.2m) as well as from Ecosystem Accelerator rounds 1, 2 and 3. In particular Twiga raised a staggering £20m, whilst eFishery raised £2.9m.

The total amount of funding raised by Ecosystem Accelerator grantees is now £37.7 million, equal to eight times the amount of funding received from Ecosystem Accelerator innovation fund, £4.7 million - £33.6 million is counted to DFID due to the funding split between DFID (100% R1 and 60% R2 and R3) and DFAT (40% R2 and R3). Additional streams of income have come in the form of debt, equity, grants and prize money, from a diverse pool of investors including Google, Tech Stars, Wamda Capital, UOB Venture Capital and Overseas Private Investment Corporation.

The total amount of funding raised by M4D Utilities grantees is now £225.2 million across DFID and USAID funded grants, £223.9 million is counted towards DFID due to the funding split between DFID (100% Phase 1, Phase 2, Phase 3 round 1 and 80% of Phase 3 Round 2) and USAID (20% of Phase 3 Round 2). This is equal to 24 times the amount of funding received from the M4D Utilities innovation fund, £9.4 million. This value exceeds the funding target of £157.4m. A recent highlight of this is in October 2018, CityTaps raised 1 million Euros (~£910k) to continue expansion plans for their prepaid meter, in order to provide for 2 million people by 2022.  €440,000 (~£400k) of this came from the Global Innovation Fund (see article and below).

In 2017, the GSMA Mobile for Development Utilities programme awarded CityTaps a grant to scale their prepaid water service platform to enable the urban poor to access affordable and safe running water at home. Their prepaid smart meter incorporates machine to machine (M2M) technology, which allows households to make micro-prepayments for their water at any time using mobile money. CityTaps is working in partnership with Orange Niger and the SEEN (Niger Water Utility Company) to trial 1,325 meters across Niamey, Niger. This grant will be concluding at the end of this year.
“Currently, there are more than one billion people who do not have access to running water in cities and the CityTaps vision is to allow these people to more easily access running water at home.“ “CityTaps has designed a water prepayment solution that relies on a prepaid smart water meter and billing software. Our solution aims to achieve the goal of Sustainable Development Goal Six by enabling subscribers to more efficiently manage their consumption and water budgets and avoid accumulating unpaid bills.” - Clémence Malmejean, CityTaps Project Manager.

Outcome indicator 5: Number of activities GSMA has contributed to, which is likely to result in transformational impact over time.

This is a new indicator, introduced following the midline review. We are still in discussion as to the best way of measuring success given the difficulty in defining ‘transformational impact.’ Whilst the scale of impact is clear by engaging nationally (to bring MNOs and government together) or engaging globally to bring sectors together, the models and roadmap to impact are less evident. Activity includes;

- The third National Dialogue in Uganda, culminating in the High Level Round Table taking place in March 2019. DFID Uganda’s Economic Advisor attended and presented to dignitaries including the 1st Deputy Prime Minister and the Permanent Secretary of the ICT Ministry, among others. Symbolic commitments were made to the incorporation of digital into the upcoming third National Development Plan (NDP III).
- Connected Women chairs the EQUALS Access Coalition which has conducted potentially transformational work in Rwanda over the last year. An Access Coalition Member, Digital Opportunity Trust (DOT), in collaboration with the Rwanda Ministry of Information, Technology and Communications (MITEC), is implementing the Digital Ambassadors Programme in Rwanda (see further details here). This programme aims to train and empower young individuals to become Digital Ambassadors who can share knowledge of digital skills in their communities to drive digital inclusion. The programme recently concluded its first implementation phase where 50 Digital Ambassadors impacted 17,647 citizens, 49% of which are female. In Phase two the programme will be scaled to a national level.

Outcome indicator 6: Perceived non-monetary value of GSMA M4D’s (i.e. SP's) grants to raise further funding and unlock partnership with MNOs (qualitative)

Introduced in the 2017-18 Annual Review as part of Altai’s midline evaluation, this indicator aims to measure the GSMA’s added value as a delivery partner in two key areas, based on the below scale (we are currently considering whether this indicator is truly the best way to be assessing the GSMA’s added value and if there are alternative methodologies we should be considering instead);

- Fundamental: GSMA's support was key to raise additional funding and/or ensure MNOs' participation
- Helpful: GSMA's support contributed to raise additional funds and/or facilitated dialogue with MNOs
- Residual value: GSMA's support did not help raise additional funds and did not facilitate contacts with MNOs

Of the ten grantees assessed, eight found the influence of the GSMA to be fundamental in at least one of the two areas outlined (raising additional funding or supporting partnerships with MNOs), and one found it fundamental to both. Combining scoring on both areas, the median score for 2019 remains ‘Fundamental’.

Explain major changes to the logframe in the past year:

As per recommendations from the previous annual review:
1. Some indicators have been revised following overachievement in last year’s Annual Review.
2. New targets have been included for the IPN hub and CHOGM activities
3. Following the external evaluators review of the theory of change and logframe during 2017-18, a number of changes have been made to the logframe after consultation with DFID in November 2018:

Original phrasing	New phrasing	Rationale
Output 1.3: # of low/medium-income countries actively represented in PLG or working groups	Output 1.3: # of low/medium-income countries actively represented within GSMA-driven activities	The indicator has been rephrased to signify the way in which it was being interpreted
Output 3.2: # of insights generated of which some are seminal reports that influence the industry	Output 3.2: # of publications which demonstrate new insight including reports, blog posts, case studies and videos	Amended to clarify what should be counted as an ‘insight’ under output 3 is industry facing (therefore unpublished insights should not be counted) and that this should include blog posts and videos where the insights are not published elsewhere. The different programmes variously interpreted what constituted a ‘seminal’ report, and the recommendation was to drop this sub-indicator.
Outcome 1: # of new services (technological innovations and business models) supported through the partnership	Outcome 1: # of new services (technological and business model innovations) emerged as result of programme activities	Amended in line with the theory of change to capture the fact that the outcome level should not be the direct result of the activities of the Strategic Partnership but the consequences of those activities.
Outcome 5: # of activities GSMA has contributed to, which is likely to result in transformational impact over time	Outcome 5: # of activities undertaken by MNOs or public sector stakeholders with potential for transformational digital impact as a result of GSMA activities.	This new outcome has been rephrased to reflect similar language to the other outcomes – in line with the rest of the review, this change is intended to emphasise that what is counted here is the consequence of GSMA action rather than the direct product.

Describe any planned changes to the logframe as a result of this review

Disaster Response Innovation Fund Round 1 grants are scheduled to close by January 2020. It is suggested that any future beneficiary figures should be captured under the separate M4H logframe and tracked for 24 months after each Round 1 grant has ended.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

There has been no change from the original value for money (VfM) proposition in the Business Case. The four main cost drivers are highlighted in the table below.

Categories	% of total budget (FY18/19)	Cost Drivers
Innovation Fund	44%	Number of sub-grants awarded
Personnel	30%	Market value of specialist skills / Fluctuation of GBP value
Research and Insights	9%	Suppliers’ costs
Travel	5%	Travel destinations

The table below outlines how the GSMA-DFID Strategic Partnership is managing the key costs using the DFID 4 E’s framework.

		VfM Measures	Performance in this area
Economy –whether the project has bought inputs of the appropriate quality at the right price?		Procurement: The GSMA is governed by the GSMA Procurement Policy covering all purchasing process, whether as purchasers, negotiators or authorisers; and in all business interactions with suppliers on behalf of the GSMA. / Human resources: The GSMA has strict policies in terms of recruitment, remuneration (based on set market benchmarks) and performance appraisal. In addition, staff are generally recruited in the market / close to the market of programme focus. / Travel: Booked in advance and at the cost of economy fare only. The hotel and subsistence rates meet GSMA’s strict travel policy guidelines to ensure best value for money per trip.	The GSMA Procurement process resulted in notable achievements in cost savings across numerous programmes, including: / Connected Women programme achieved 33% reduction in costs and negotiated a saving of £31,784 following a rigorous process to select a supplier to conduct a study on the impact of MTN Ghana’s MoMo Pay market project, and the influence of the different characteristics of merchants, on female Mobile Money adoption and use. / In a similar vein, the Connected Society programme negotiated £84,550 in savings (32% reduction) for a 2G-3G baseline country research. / In the process to secure a supplier to conduct end-user research in Rwanda, Bangladesh and Nigeria, the CHOGM programme generated £11,193 in savings following negotiation with the supplier
Efficiency- how well the project is converting inputs into outputs? (‘Spending well’)		Input maximisation: cross-collaboration between programmes of the partnerships to mutualise inputs (staff, suppliers, travels, processes) and maximise output impact (joint research and joint advocacy) / DFID Profiling: GSMA M4D activities have been able to leverage GSMA flagship events such as Mobile World Congress and the Mobile 360 events and high level platforms (UNGA, WEF) to profile the Partnership outputs / Monitoring and evaluation: constant improvement of services based on user feedback, business intelligence and monitoring and evaluation feedback. / Strengthened due diligence to mitigate risks that sub-grantees of the Innovation Fund could misuse funds	Across M4D the programmes with an Innovation Fund (Ecosystem Accelerator, M4D Utilities, Disaster Response, Connected Society and Mobile for Humanitarian Innovation) use the same Fund Manager (Coffey). The GSMA negotiated reduced rates with Coffey. / GSMA has developed a risk assessment framework to analyse country wise risk and align the sub-grant pre award due diligence and monitoring processes with the risk / The GSMA has strengthened the M&E component across the M4D programmes, by recruiting additional specialist M&E resources and introducing common M&E frameworks and systems. / The programme keeps costs down by purchasing marketing material from suppliers who offer GSMA corporate discounts and using a combination of paid and organic marketing and promotional techniques.
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’) / Cost-effectiveness - What is the project’s ultimate impact on poverty reduction, relative to the inputs that we invest in it?		Achievement and overachievements of all targets as set in the agreed logframe / Crowding in of new donors, demonstrating the effectiveness and attractiveness of the Partnership to other donors	Indicators overachieved: The Partnership has achieved or overachieved all its targets for the third year. In particular, the strong crowding-in figures (additional funding raised by sub-grantees) has been impressive and is a testimony that our Innovation Fund model results in scaling for our grantees. / Since the last reporting period, USAID have increased their commitment to the partnership (~£96k to Connected Society for coverage maps) and DFAT have extended their commitment to another M4D programme outside of the strategic partnership (~£90k to Agritech). They joined Sida (~£2.2m over 4 years for National Dialogue, Connected Women and Sustainability initiative) , DFAT (~£3.17m over 3 years in the Ecosystem Accelerator and added ~£290k for the CHOGM Digital Identity work as well as ~£100k to fund insights and convening for Papua New Guinea digital transformation) and USAID (~£413k over 3 years for M4D Utilities).
	Equity - ensuring that research is inclusive and benefitting the target group	All the programmes in the Partnership monitor the number of women impacted. In addition, the Connected Women programme has a specific focus on reducing the gender gap on Mobile Internet and Mobile Money. / Following the study on how mobile can act as transformative technology for people with disability in emerging markets, the GSMA has formally set up the Assistive Tech programme to drive greater digital inclusion for persons with disabilities through research and insights, innovation funding, partnerships development, advocacy, knowledge sharing and advisory to mobile operators.	The Connected Women programme plays a key role to reduce the gender gap in mobile internet and mobile money services in low- and middle-income countries and unlock significant commercial and socio-economic opportunities. / The Digital Identity programme is playing a key role in advocating and raising awareness of the opportunity for mobile technology to enable accessible and inclusive digital identity for the most vulnerable segments of society. / In June 2019, the GSMA has adopted the UN Women’s Empowerment Principles as part of its commitment to promoting gender equality and the empowerment of women in the workplace, marketplace and community.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The original (as set in the business case) estimated impact was up to 14 million people as a result of DFID’s £37.5 million investment, equivalent to a cost of roughly £2.67 per impacted user by 2020.

As of this annual review (year 3), the programme has already reached 21.2m users on the back of a revised £38.9m investment (including CHOGM additional investment), meaning that the cost of each impacted user has already gone down to £1.8 by June 2019.
The projected impacted users by 2020 is now 26.25m on the back of a this £38.9m investment, with a projected cost per impacted user of £1.48

In addition, value for money is especially strong when the amount of private capital raised by sub-grantees is considered: The additional funding raised by M4D Utilities and Ecosystem Accelerator’s grantees as well match funding the grantees contributed during their grant period has increased significantly to £257.5m, 21% growth since last year and exceeds the target for this year (£226m), and represents a 24:1 ratio for every pound of DFID money spent on these innovation funds.

Finally, other donors are crowding in in the Partnership. Since the start of the Partnership, DFAT has contributed AUD 6.4m, USAID has contributed over $600k and Sida has contributed SEK26m.

During the period from 1 April 2018 to 31 March 2019, GSMA has contributed ~£1.6m (above the original £1.1m set in the original business case) and £1.63m cash (similar to the £1.65m envisaged in the original business case).

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall the risk of the DFID GSMA Foundation strategic partnership programme is judged to be Moderate risk. The programme takes an innovative approach, across a broad range of areas and is large in size to have the desired transformation and impact. The key risks at this stage are shown in the table below and the mitigation actions have been reviewed as per this annual review.

The key risks at this stage are shown in the table below and the mitigation actions have been reviewed as per this annual review. ‘↑’ indicates an increased probability or risk, ’↓’ indicates a decreasing probability or risk, and ‘-’ indicates that the level has not changed since programme inception.

Risk Management Table for the Mobile for Development (M4D) GSMA Foundation strategic partnership programme:

Risks and Description	Probability (H, M, L)	Impact / (H, M, L)	Mitigating Actions
Research, Innovation and Uptake Risks
New mobile technology and business solutions do not directly benefit the poor and underserved communities	L-	M-	The Partnership only fund Operators’ initiatives that have both socio-economic and commercial impacts. In addition, all applications to the Innovation Fund must have a clear charitable purpose
Mobile Network Operators are not interested in the products and business models developed and as such scale up does not occur.	L-	H-	The Partnership programmes ensure that models for delivering services are not focussed on mobile providers’ corporate social responsibility programme, but instead, are well integrated with lines of business. / The programmes also develop stronger business rationale for local operators to invest time and money in M4D services. This is needed when the level of investment needed to deliver a project without immediate return on investment is important. This approach has been successful overall, with some persistent challenges for the Digital Identity programme. / Finally, the programmes work with grantees from the Innovation Funds to help them partner with Mobile Operators and therefore support them in the route to scale
There is a wave of market consolidation for Mobile Network Operators in Africa and Asia, which may affect delivery of commitments and implementations	M-	M-	The Partnership programmes adopt a pipeline approach on commitments and implementations, by diversifying partners to minimise risk of impact of change of priority by operators
Achievement of some programme goals can be dependent on regulatory environments that could delay projects	M-	M-	The Partnership programmes regularly engage with regulators to build the case of the socio-economic benefits of M4D projects and influence them. The national dialogue activities supported (not funded) by DFID is also an opportunity to build bridges between government stakeholders and private sector
The applications received and supported, and business models developed do not generate sufficient market demand to meet output and outcome indicator targets	L-	H-	The programmes using the Innovation Fund undertake targeted outreach including sending personalized emails to a large number of contacts, working strategically with a number of regional tech hubs or accelerators to promote the Fund. / In order to support crowding-in of the programme innovations, the programme profiles them to operators and also at big events (e.g. M360s….) / Taking the example of the new Connected Society Innovation Fund, GSMA investigated the appetite of the local Mobile Network Operators ahead of choosing the countries where the Fund focused its efforts.
Market uptake of the recommendations and ideas demonstrated by the disseminated research and innovation support is less than anticipated	L-	M-	The Partnership programmes leverage GSMA convening platforms (e.g. Mobile World Congress; M360 Africa) as well as high level platforms (e.g. World Bank; WEF; UN General Assembly) to disseminate and profile the messages of the partnership.
Governance and Programme Management Risks
Implementing partner (GSMA Foundation) is too engaged in managing their existing core businesses to devote sufficient time and effort to develop new innovations.	L-	L-	The Partnership programmes have a clear governance structure that has evolved to reflect the evolution of the programmes. The majority of programme has a governance body (mainly an advisory committee) convening mobile operators and donors. Also, DFID is fully involved in the yearly business planning of each programme and signs off the programme brief for each programme
Choice of sub-grantees is not made transparently	L-	M-	Sub-grantees are selected through a fully transparent process and the selection is done by an independent Fund Panel (with one member of DFID, one member of GSMA and 3 independent experts)
Risk profile of the Partnership is increasing given DFID commitment to fragile countries, leading to reputational risks for DFID	L-	H-	GSMA has developed a risk assessment framework to analyse country wise risk and align the sub-grant pre award due diligence and monitoring processes with the risk
The implementing partner does not follow the DFID guidelines on safeguarding	L-	H-	As evidenced by the recent due diligence undertaken by PwC in 2019, the GSMA has implemented safeguarding procedures as part of their core processes and policies
The current head of GSMA Mobile for Development will leave GSMA by the end of 2019	H	M	GSMA has started recruitment of a new head and DFID met with GSMA Leadership to give feedback on the replacement. Continuity solutions will be in place (acting head…) so that the delivery of Partnership activities are not affected

Risk Management Strategies applicable to the Partnership Programmes

At organisational level, a Group Risk Matrix is maintained. It documents the strategic risks for GSMA along with an assessment of the impacts, risk ratings based on the likelihood and impact assessments and the mitigation in place to address the risks. Risk management is part of the remit of the GSMA Controls, Compliance and Ethics Committee.

- At Partnership programme level, risk and issue management procedures are applied to the management and delivery of GSMA programmes, under the responsibility of each Head of Programme and Programme Manager. These include the following key elements:
  - High ranking risks and issues have mitigation plans, are tracked on at least a monthly basis, owners assigned, and updates are recorded within the new GSMA programme management software, PPMA. Top priority risks and issues are reported monthly to the GSMA Leadership Team.
  - Any changes to programme scope due to issues or risks will be handled according to the GSMA’s change control procedure.

At Grant Portfolio level, risk matrices (RAID logs) are held to record risks and issues which are relevant to the overall portfolio. Each risk or issue is assigned a unique ID (based on proximity, impact and probability) and mitigation plans assigned per risk. Key risks are reported monthly to senior management through a pipeline review. For each grant, risks and issues are regularly logged through the monthly reporting mechanisms owned by the programme teams. Medium to high impact and/or high proximity risks or issues may be escalated to the Fund Manager (Coffey International Ltd.) and Programme Manager who provide support in developing and implementing mitigation strategies and who record it at the portfolio and/or programme level. A dedicated Conflict of Interest log (COI) is maintained to track and record interactions between the programme team and applicants to the Innovation Funds as well as the Fund panel making the portfolio selections.

New risk assessment framework: GSMA has developed a risk assessment framework to analyse country wise risk and align sub-grant pre-award due diligence and monitoring processes with the risk. Countries are classified into 4 categories (sanctioned countries; extreme risk countries; high risk countries; others). This categorisation is based on an aggregate view of the country level risk assessments by verifiable and reputable (reliable and credible) agencies such as World Bank, iSOS (Control Risks), Transparency International and the Economist Intelligence Unit (EIU). Over 120 indicators were considered, denoting current and/or forecasted expectations across various factors including corruption, political stability, physical safety and security, macroeconomic factors and prevalence of terrorism. The indicators help assess the likelihood of key risks as below:

  - Terrorism financing
  - Safety and security
  - Legal/regulatory non-compliance
  - Operational disruption

In order to mitigate these risks in the riskiest countries, strengthened due diligence processes have been put in place for countries in the extreme risk and high-risk categories. These new due diligence processes are systematically applied before the applicant is presented to the Fund Panel.

DFID Safeguarding guidelines: As evidenced by the recent due diligence undertaken by PwC in 2019, the GSMA has implemented safeguarding procedures as part of their core processes and policies.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery against planned timeframe
Compared to the original business case, original logframe and original budget, the partnership has been overall on track.
- All output indicators (operator engagement, innovation fund and insights generation / dissemination) have been on track or overachieved
- All outcome indicators are on track or overachieved.
- The impact target is ahead reflecting the success of the engagement with stakeholders (mobile operators, grantees etc…)

As underlined in section E (risks), the main risk factors that could affect programme delivery against the planned timeframe are appetite of the operators to implement Partnership’s initiatives, uncertain environments (especially regulatory ones) and delays with sub-grantees projects. As underlined in section E, mitigations are in place for these risks.

Performance of partnership(s)
Much like 2018, this year the GSMA has continued to prove themselves as an industry leader with a unique offering to development; close links to mobile network operators and other private sector stakeholder, the ability to be a convener between private sector and development partners, and exceptional technical expertise across a broad range of thematic areas. DFID has, once again, found the partnership to be honest, open and based on mutually agreed impact aims. GSMA have responded in a timely fashion to all requests, engaged proactively with PwC during the updated Due Diligence process (already putting into action the proposed responses to the key findings) and have actively engaged with other parts of DFID (especially EPIC), HMG (especially DIT), and our senior management and Ministerial teams.

Their performance is seen as on-par with 2018, hence the recommendation of an A+ in this Annual Review. One of the key recommendations last year was to have discussions on a broadened strategic partnership. We are pleased that the GSMA’s consistency in delivering, bold ambitions and unique positioning within the development community has been recognised through the approval of our extended partnership for another 3 ½ years. The business case for this extension can be found on Vault here.

Asset monitoring and control
Annex with full list submitted with review (Annex H)

Date of last narrative financial report(s)	July 2019
Date of last audited annual statement (s)	June 2019

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

Each programme tracks their contribution to the logframe indicators, and evidence to support, throughout the reporting period (a monitoring plan is provided in Annex H).

Each of the innovation funds focuses on project monitoring to ensure sub-grantees are on track and understand some element of the socio-economic outcomes of the subgrant:
- The M4D Utilities innovation fund continues to monitor projects using a lean, adaptive methodology depending on the scope and scale of the projects and drawing on a menu of business, mobile and social KPIs built up over six years of operations.
- The Ecosystem Accelerator innovation fund tracks KPIs per project including number of beneficiaries, ‘crowded in’ investment and income unlocked for the local economy.
- Connected Society will monitor changes in activity on different mobile channels at the pilot towers, subject to data availability.
- The Disaster Response innovation fund grantees developed bespoke logframes alongside the market engagement and M&E teams, tracking bespoke indicators for each project.

In each case, the beneficiary indicator rolls up to contribute to the logframe; output and outcome indicators reflect the diversity of different projects and goals throughout the Strategic Partnership portfolio.

Connected Women: Additional monitoring has been piloted on their Women and Mobile capacity building courses during this reporting period with a pre / post test approach that was piloted at a recent course in Benin. The pre-test suggested that participants came to the course with a good understanding of the mobile gender gap – over 85% gave responses to the questions which aligned with GSMA messaging before the course had been completed. Only 35% of respondents accurately answered the knowledge question correctly in the pre-test, compared to 76% of respondents in the post-test – this is a significant difference suggesting that the course successfully communicated on key messaging. Almost all participants (92%) said they planned to take action based on what they had learned in the course.

Evidence

Many M&E activities (specifically tailored to each programme) are on-going, with most of the evidence expected during the next reporting year. A flavour of the activities in progress can be found below;

Ecosystem accelerator: One evaluation completed this year was on Sehat Kahani, a telemedicine provider connecting female doctors to women in rural Pakistan, with six more such exercises planned:

A clinic mapping exercise in four areas in Sindh province found that, in one rural area, the Sehat Kahani clinic is the only source of qualified doctors. In both clinics in the Hyderabad area, Sehat Kahani was the only place to see a female medical professional.

A qualitative study found that women prefer to see female doctors for certain conditions, but that there remain cultural barriers for women to visiting the doctors outside of very serious illness, and that in many cases the family remain the gatekeepers to treatment. The Sehat Kahani team aims to continue to work on these barriers through their public health drives.

In 2018, 48% of Sehat Kahani appointments occurred in rural areas. 83% of appointments were with women, and 16% of appointments were with pregnant women or were antenatal appointments. Local Sehat Kahani mobilizers were the most common source of referrals for appointments (37%, rising to 43% in urban areas), suggesting that the mobilizer model is effective in encouraging people to visit the doctor.
Connected Society: the main goal of the M&E work is to evaluate the impact of the MISTT (usage) and coverage innovation fund. An evaluation of the uptake and commercial impact of Banglalink’s MISTT deployment was published in May 2019. Moving forwards, we are seeking a partner to help understand the impact of MISTT beyond the commercial indicators, i.e. whether the training generates benefits for users beyond those who are trained

Connected Women: the main goal of the M&E work is to evaluate the impact on women of services launched by our commitment partners. Two evaluation projects were conducted this year with one more planned over the next year. A case study of MoMo Pay (MTN Ghana’s flagship mobile money merchant payments platform) is below.

Ama’s motto is simple: ‘the customer is king’. She offers outstanding customer service by providing different payments options to her clientele, including mobile money from different providers so that customers don’t have any excuses for not being able to pay. She promotes the MoMo Pay brand for its ease of use and even teaches customers how to use it.
“Someone may want to buy something from me and will tell me he does not have cash on hand. I inform them that they can pay through Merchant Pay if they have money on their wallets. Often the customer ends up buying more than initially planned. If the customer doesn’t know how to go about making such payments even though they have money on their e-wallets, I educate them on how to do so.”
Ama was an early adopter of both mobile money and MoMo Pay. MoMo Pay distinguishes itself from the rest of the MTN mobile money platform with its comparatively low fees. Peer-to-peer transfers have historically charged a 1% fee, but with MoMo Pay there is only a charge of 0.2%. Ama loves MoMo Pay because of its ease of use and lower charges compared to regular mobile money transfers. She has connected her MoMo Pay wallet to her bank account to enable her to save and also uses it to pay her suppliers without leaving her shop, increasing the overall time she is available to attend her customers. For her, the future of payment is mobile money.
M4D Utilities: One evaluation completed this year was on Drinkwell, a provider of safe drinking water to low income households in Bangladesh, via mobile enabled water ATMs:

- All respondents using Drinkwell water live on $2.50 USD a day or less: 9.3% of the respondents were living on $1.25 or less a day.
- 97% of Drinkwell users reported a reduction in instances of water-related disease since using Drinkwell.
- Users have not replaced other water sources completely as they use those sources for cooking/ washing/ bathing etc.
- However, for drinking water, other water sources have been almost displaced by Drinkwell. 98% of the Drinkwell users use only Drinkwell water as their drinking water source.

Digital identity and the Disaster Response programmes either have evaluations underway or planned for completion over the next year.

Learning

In April 2019, we took the opportunity to reflect on the M&E foundations for the Strategic Partnership. An exercise was conducted, first with the heads of programme then with all programme staff across the Strategic Partnership, to review and comment on the theory of change, its assumptions and any gaps in the logic. Some interesting outputs from this exercise – which will be implemented over the next reporting year for the Strategic Partnership - included:

- Doing no harm requires a triple bottom line approach – we need to ensure we look at both environmental and social impacts of our work (including digital inclusion topics), in such a way that we consider negative as well as positive consequences.
- Clear business case is required for digital players to engage in M4D services – we need to revisit the way we look at return on investment for these stakeholders and come up with compelling, and ideally comparable, measures.
- How could we better measure the demand and appetite for our Insights work? – in order to enable inclusion goals and other best practices are being enshrined, we need to know that our work is being well received – we currently lack a mechanism to understand that in some of our stakeholder groups.

Progress on recommendations from previous reviews:

FY2019 Annual Review Recommendation	Update
Continue to drive digital inclusion for sub-Saharan Africa - The risk of digital exclusion for the underserved is rising; with1.09 billion people uncovered by mobile broadband. The Connected Society programme has pivoted to more directly address this coverage gap and the GSMA should continue to be proactive with ways to support/catalyse the industry in this area.	Completed. This has been achieved as part of the refocus of the programme. Main results can be seen in this review, especially use of coverage maps and rural coverage Innovation Fund
Increase understanding of digital solutions for disability - GSMA is already increasing its understanding of how digital solutions can contribute to socioeconomic impact for people with disabilities, including establishing a ‘baseline’ for the potential impact of mobile technology. In Year 3 of the partnership the GSMA should use its new understanding to incorporate a 'disability lens' across the partnership where appropriate.	Completed. This has been achieved through the GDI –GSMA grant (signed in November 2018) as well as the plans laid out in the next phase of the Partnership
Refine operator engagement approach - In light of the insights from the midline M&E undertaken this year, and the continued commercial pressures facing the telecoms industry, GSMA M4D will make its operator engagement model more ‘sophisticated’; This will reflect that a proportionate and adequate level of engagement is needed to achieve impact on a project by project basis.	Completed through different programme-specific approaches: / Connected Society: innovative approach of involving operators through the Innovation Fund and focussing on demonstration MISTT projects with key operator groups / Ecosystem Accelerator: innovative approach of building partnerships start-up / operators / M4D Utilities: innovative approach of building partnerships start-up / operators or operators and utilities / Connected Women: funnel approach, whereby the team efforts are concentrated on a subset of very committed operators
Explore and decide upon the next steps for the partnership post 2020 - The strategic partnership model has shown two years of strong results. The original design of the partnership was to slow down investment in Year 3 and conclude the partnership in Year 4. However, huge potential still remains to use mobile to support DFID’s priorities as well as address wider development challenges. GSMA and DFID will meet in Autumn 2018 to explore what a future collaboration should look like and agree next steps, which will include consultation across DFID.	Completed: the business case has been approved by ministers in December 2018. The business case has been approved in July 2019 with announcement mid-July at M360 Africa.
DFID and GSMA to hold a focused session with M4D leads on (1) grant flexibility, particularly the milestone payment mechanism, and (2) routes to scale, to further understand key constraints innovators are facing and consider what can be changed for the remainder of the programme.	Ongoing: this is considered as part of the centralisation of the Innovation Fund, that will take effect in April 2020, as part of the next phase of the Partnership.
Update the Partnership logframe in-line with recommendations set in section C of this annual review, after a dedicated session between GSMA, DFID and Altai to agree specific changes.	Completed
GSMA to start the implementation of the strengthened approach for M&E, including a strong focus on user insights.	Completed
GSMA to provide ongoing progress updates on the implementation of safeguarding policies (in-line with safeguarding recommendations by DFID)	Completed and assessed as part of the PwC due diligence
GSMA to continue engaging with DFID stakeholders to share learning and potential innovation pipeline, e.g. with TRANSFORM (Unilever), Transforming Energy Access (Shell Foundation), CDC, Global Innovation Fund and country offices.	Ongoing. Our engagement can be classified as three types of engagement: / Engagement with future investors of our grantee’s portfolio, whatever private investors or other donors / Learning from partners recommended by DFID such as ACUMEN lean approach for our M&E methodologies / Inform and advise investors such as CDC as part of the Connected Society Innovation Fund.

### ANNEXES TO BE INCLUDED WITH ANNUAL REPORT
Logframe
### Attach the current version that you are reporting against.
Financial documents
### Please provide a financial report for the reporting period and attach an up-to-date full programme budget by DFID financial year (fiscal) and the audited financial statements for your organisation.
Forward work plan
### Please submit the work-plan for the upcoming year.
Asset Register
### E. Downstream Partner mapping
### Please complete Annex F and submit it with the annual report. Please ensure that the 1st
### and 2nd tier partners are included as a matter of course and include, as far down the delivery
### chain as possible, the name of any partners you engage with/fund on this project and the
### associated risks.
List of evidence per logframe indicator and per programme + M&E monitoring plan
Life stories