SP1- Annual Review Template – from April 2020

Title: Mobile for Development Strategic Partnership (incorporating M4D Utilities since 2016)
Programme Value £ (full life): 38,897,334 (1st phase) / 38,000,000 (2nd Phase)		Review date: August 2020
Programme Code: [AMP ID#] 203804	AMP start date: 4 January 2013	AMP end date: 31 March 2023

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020	2021
Overall Output Score	A	A	A+	A++	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	2016 Addendum | 2019 Business case
DevTracker Link to results framework:	Pending

A. SUMMARY AND OVERVIEW

     Description of programme

This annual review reports on the achievement of the fourth year of the first phase of the Strategic Partnership (July 2019-June 2020). It also reports on the first months of the second phase of this Partnership (September 2019-June 2020; with achievements marked as [SP2] throughout this document).
Since 2013, DFID and the GSMA Foundation have been working together under the Mobile for Development Utilities (M4D Utilities) programme to seize the opportunities of mobile technology for energy, water and sanitation. Building on the success of the M4D Utilities programme, DFID and the GSMA Foundation agreed to develop a wider strategic Partnership - the first phase of which was launched in February 2016 and mostly concluded in March 2020 with a No Cost Extension (NCE) agreed until March 2021 for some specific activities. The aim of this first phase of the Partnership was to leverage the power of mobile to improve the lives of 20 million people by 2020. DFID committed £27.6m across 4 years (April 2016 to March 2020 + NCE until March 2021) to the Strategic Partnership. The GSMA’s yearly contribution was £2.8m (£1.2m direct contribution and £1.6m in-kind contribution) for a total contribution of £11.6m over 4 years.
Building on the success of this 2016-2020 Partnership and recognising that mobile can be a cost-effective, large-scale channel for delivering a wide range of services with compelling socio-economic benefits, DFID and the GSMA Foundation agreed to scale the Partnership for a second phase (September 2019 to March 2023). This second phase was announced at the GSMA M360 Africa event in Kigali in July 2019 and formally agreed in September 2019. This new Partnership has an increased focus on scaling, innovation and inclusion to leave no-one behind, delivered through a combination of research and analysis, catalytic funding to de-risk innovation and targeted advocacy to inform national policy and industry decisions.
The two phases of the Strategic Partnership work on four strategic themes (and related programmes, see figure 1) under the Mobile for Development (M4D) portfolio, making contributions to all 17 of the United Nations Sustainable Development Goals (SDGs):
- digital inclusion
- unlocking access to essential utilities services through mobile
- supporting digital ecosystems through innovation
- digital technology as an enabler for the transition towards climate-resilient economies.

Figure 1: M4D programmes under the Partnership

Summary supporting narrative for the overall score in this review

In the fourth and final year of the first phase (NCE activities excluded), the Partnership either reached or exceeded all of its output, outcome and revised impact targets. The output and outcome targets of the second phase of the Partnership for the first year were also reached or exceeded.

Key achievements of the Partnership include:
Through its first phase, the Partnership has reached over 32m beneficiaries, twice the number of beneficiaries originally set in the business case (16m), distributed across 40 countries. 72% of these beneficiaries are women.

The value for money of the Partnership has been strong for DFID with a cost of each impacted user at £1.20, at the end of the first phase of the Partnership – as compared with £2.30 in the original business case

Crowding-in has been strong with a figure of £445.6m private investment raised by grantees on the back of DFID funding of £15.65m, hence a combined multiplier effect of 28.5:1 (see Annex J)

A strong engagement from the private sector with 148 projects launched by MNOs in 40 LMICs over the past 4 years, including partnerships with some of our 84 sub-grantees.

The Partnership pivoted some of its activities by repurposing existing funding to respond to the direct impact of the COVID-19 crisis and subsequent lockdown, summarised in the call-out box below and Annex M.

All sub-grants of the Ecosystem Accelerator and M4D Utilities have now been closed, and these programmes are transitioning to an adapted scope of work under the second phase of the Partnership.

The IPN Hub has successfully been transitioned to the industry (Beyonic Inc), marking a unique achievement given the risks associated with developing and transitioning such a live service. This transitioning marks the successful management of this platform – from inception to scale – by the GSMA: since June 2019, the Hub has increased unique transactions by 100% and unique users served by 79%.

The Partnership has strengthened its position as a thought leader on the use of mobile to accelerate socioeconomic impact for the underserved, especially women, youth and rural populations.

COVID-19 Response
As COVID-19 continues to fundamentally change the global landscape, its impact on vulnerable populations is substantial. The Strategic Partnership has responded with the following key activities to ensure that mobile technology can play its part in responding to the pandemic (no incremental funding was requested for these activities):
- Launch of a new project providing immediate response to the Covid-19 pandemic by focusing on how aggregated mobile big data analytics could support the planning and decision making of health authorities and emergency agencies in 4 LMICs. The GSMA will also work with MNOs to develop the required mobile big data analytics to deliver insights as required, while ensuring privacy and ethical principles are applied end-to-end (see output 1.1).
- Through an Emergency Response Fund available to selected GSMA Grantee Alumni, support and bolster the ability of local private sector organisations well positioned to provide support to those affected by the crisis through their continued/enhanced delivery of essential services during the pandemic, in sectors such as healthtech, edtech, food security, water or sanitation (see output 1.2).
- Documenting the role of mobile and digital technology during the pandemic in LMICs on a knowledge hub. This hub includes GSMA guidelines, blog posts or interviews on topics related to the pandemic, examples of what MNOs and other private sector partners are doing, summary of projects the GSMA is supporting, best practices, and FAQs (e.g. zero-rating, mobile money commissions, or contact tracing).
- Promotion of and participation in the content of the DFID-Unilever TRANSFORM programme’s Survive & Thrive platform: the opportunities for the GSMA include both promoting this platform to all our grantees as well as contributing towards partnership facilitation with MNOs that can either help to expand distribution or support efforts for business continuity.
- On the back of the GSMA and BMGF-funded Mobile Money programme (non-DFID funded), publication and promotion of several practical recommendations to governments and central banks on how to facilitate the role of mobile money in a COVID-19 context.

Main lessons learned

Progress from the fourth year of the Partnership has highlighted the following key lessons:

The amount and the diversity of requests received by M4D since the beginning of the COVID-19 crisis reflect the importance mobile and digital solutions is expected to play in such contexts. The programmes have been able to reorganise themselves quickly to address some of the challenges faced by LMICs, and some ad-hoc initiatives have been launched. However, the pandemic also highlighted the fact that such crises are not ‘great levellers’ but rather exacerbate inequalities; in particular, being digitally excluded becomes a much wider issue when the society and the economy you evolve in move online overnight. Once the crisis is over, we anticipate the shift to how mobile and digital technology can be leveraged to anticipate shocks (preparedness), respond to them (immediate response) and recover from them (recovery). On all three aspects, M4D will be uniquely positioned to be involved in such initiatives, either as a lead or as a partner.

Effective private sector engagement model - GSMA's model to engage the private sector (mobile operators and start-ups/ innovators) has demonstrated its ability to unlock scale for social impact. This is evidenced by the overachievement of the scale and crowding-in indicators as well as the number of projects (148) launched by MNOs in LMICs.

Cross-portfolio approach: Having the Partnership cover a wide range of topics creates a rich environment for cross-pollination: e.g. Mobile Money and M4D Utilities (IPN hub) or Connected Women and Digital Identity.

Pathways to scale: both our scale and crowding-in indicators have been exceeded by a large margin. This is a testimony to how the Partnership activities were able to drive scale using different models (see figure 2). The GSMA M4D’s internal ‘Pathways to scale’ paper (Annex J) considers how M4D projects have progressed on their scale journey: proved their value, scaled up (reach more people within a context) or scale out (replicate to new contexts).

Figure 2: how M4D influences levers of scaling in the ecosystem

Lessons learnt on innovation: the first phase of the Partnership, GSMA M4D has been able to unlock highly innovative solutions to some of the most complex challenges in development (see figure 3).

Figure 3: The Partnership’s approach of building innovation

Lessons learnt on inclusion: An estimated 22,987,888 of the first phase of the Partnership’s beneficiaries are female, largely owing to the scale of beneficiaries contributed by the Connected Women programme. The success of the programme builds on the Connected Women Commitment Initiative, which relies on the private sector (MNOs) to make commitments with set targets to increase the proportion of women in the customer base of their mobile internet and/or mobile money services. Drawing on research and work with MNOs in Africa, Asia and Latin America over the last decade, the Programme has identified 10 key recommendations (Figure 4) that MNOs can take to reach female customers and realise this opportunity. These are detailed in the latest flagship publication “Reaching 50 Million Women with Mobile: A Practical Guide”.

Figure 4: a framework for mobile network operators to reach female customers

- The DFID programme-funded post at the GSMA has proven to be very effective at building bridges between the two organisations as well as with DFID regional offices
- The new Central Insights Unit (CIU) has been instrumental to strengthen the work between GSMA and regional DFID offices. The model of engagement trialled this year has proven successful and clearly fulfils unmet needs of the regional offices (e.g. DFIDs’ Futures Workshop).

[SP2] Recommendations for the year ahead (under second phase of the Partnership)
- COVID-19: in addition to the activities currently in plan, the programmes will keep monitoring and consolidating the response of the mobile industry within the GSMA COVID-19 knowledge hub. DFID/FCDO and the GSMA will discuss any new opportunities for action where relevant, in particular as the focus shifts from immediate response to recovery and preparedness [Mar-21].
- Climate change: the GSMA will undertake a broad strategic research piece on the role and additionality of mobile to address climate change challenges in LMICs. This research will lead to a clearer definition of the role of M4D in addressing climate change, and how this role is spread between programmes [Nov-20].
- Logframe/Cleantech: Once the Cleantech programme’s scope of work is fully defined (see above), DFID/FCDO and the GSMA will agree on a revised logframe [Jun-21].
- Innovation Fund: DFID/FCDO and the GSMA will decide the sequencing, topics and overall timeline of the next Innovation Fund rounds [Sep-20].
- Connected Society coverage fund: Although there continues to be full confidence that this fund will be regarded as a success in terms of delivering innovative coverage solutions, it has proven to be both resource- and time-intensive from the team (see output section). It is therefore recommended that no further funds are implemented to deliver coverage infrastructure within the phase 2 of the partnership and that the completion of the current fund is extended until March 2022 (under the existing NCE) [Sep-21].
- Testing of the key strategic hypotheses and questions of the Partnership: DFID/FCDO and the GSMA will agree the key strategic hypotheses and questions that the M&E team will evidence during the course of the second phase of the Partnership [Sep-20].
- Analysis of the routes to scale: The GSMA will continue to collaborate with the Wheeler Institute and the London Business School to input into their science of scaling work [Mar-21].
- Ministerial engagement: DFID/FCDO will pursue senior level internal engagement to raise awareness on the contribution of digital solutions in addressing key challenges in LMICs [Mar-21].
- Scale up of the second phase of the Partnership: DFID/FCDO and the GSMA will start discussions about the scale up of the second phase of the Partnership [Mar-21].
- M4D dissemination strategy: The endline review recommended that the dissemination strategy of GSMA could be fine-tuned by using innovative formats, organising launch events and providing training. The GSMA will share this M4D dissemination strategy with DFID by [Mar-21]

An update of the actions from the 2019 PwC due diligence are provided in Annex I.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The first phase of the Strategic Partnership aimed to impact over 20 million people (by 2020, with improved access and use of life-enhancing mobile-enabled services, contributing to the achievement of the SDGs.

The theory of change that supports the first phase of the Partnership is illustrated below:

Figure 5: Theory of change of the first phase of the Partnership
The endline evaluation led by an independent third party (Altai consulting) was concluded in February 2020 and gathered evidence confirming that: (1) the overall logic model of the Strategic Partnership holds against implementation experience for outputs and outcomes, and (2) the GSMA contributed strongly to the outcomes and has the potential to achieve more. The endline evaluations’ review of the theory of change for the Strategic Partnership is included as Annex G.
In terms of change impacting the logframe throughout the lifetime of the Partnership, additional activities were added: CHOGM Digital Identity (2018, additional funding added), IPN Hub (2018, no additional funding) and COVID-19 activities (2020, as detailed in section A, no additional funding added).
[SP2] The second phase of the Partnership leverages the lessons learnt from the first phase (including external evaluation) and M4D’s approach to achieving impact. The theory of change has therefore evolved to reflect these changes (see below):

Figure 6: Theory of change of the second phase of the Partnership

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? Consider value for money

In its final year of existence (with the exception of an NCE for some specific activities), the first phase of the Partnership concludes with a high value of money for DFID (see VfM matrix in section E) showing a very high level of effectiveness:

All impact outcomes and output indicators have been achieved or exceeded. In particular, the strong crowding-in figures (additional funding raised by sub-grantees) has been impressive (2.5 times compared to the initial business case) and the number of impacted beneficiaries is twice the number of beneficiaries set in the original business case (16m). Please see below for further details on the impact and outcome targets.

The original (as set in the business case) estimated impact was up to 16 million people as a result of DFID’s £37.5 million investment, equivalent to a cost of roughly £2.67 per impacted user by 2020. As of this annual review (year 4), the programme has reached 32.8m users on the back of a revised £38.9m investment (including CHOGM additional investment), meaning that the cost of each impacted user is now £1.20, 55% less than in the original business case.

The Partnership has been very flexible, enabling new high-impact activities to be undertaken within the original business case funding. Examples include the IPN Hub, which scaled to become a sustainable industry asset, as well as activities responding to the COVID-19 outbreak.

The Partnership has attracted new donors who joined the Partnership, therefore increasing the impact of existing Partnership activities: NORAD / digital skills; BMZ / technical assistance for the grantees of the Digital Inclusion Innovation Fund; World Bank / model the effects of public policy options for mobile infrastructure deployment, leveraging M4D’s coverage maps. Other grants are expected to be signed in the coming months.
#### Impact target
The total number of beneficiaries is 32,862,289 at the end of the first phase of the Partnership, distributed across 40 countries. This figure includes a 4.98% discount to account for possible double counting across programmes. Of the total beneficiaries, 22% are ‘indirect’ beneficiaries (indirect beneficiaries are mostly innovation fund grantees reporting in the two years after grant end).

Figure 7: Geographic spread of DFID-funded projects where beneficiaries are recorded

Looking in more details at each programme of the Partnership, most of the programme either reached or exceeded its impact target (figure 8).

Figure 8: number of beneficiaries per programme, showing female (dark green) and all beneficiaries (teal) and final year targets (red lines). Number of beneficiaries per programme is shown before the cross-programme double-counting discount is taken, so totals sum to more than the total beneficiaries reported for the grant.
An estimated 72% of those beneficiaries are female, largely owing to the scale of beneficiaries contributed by the Connected Women programme. This also explains why the contribution to SDG topic areas is overwhelmingly positive in favour of SDG 5: Gender equality, although Strategic Partnership projects contribute to all 17 SDGs.

Figure 9: Contribution of beneficiaries to different SDG topic areas
Where a project is relevant to several M4D topic areas, the beneficiaries are double counted. As this data is shown at the project level, the total beneficiaries shown in this graphic exceeds the total beneficiary number.
#### Outcome targets
Regarding the partnership outcome indicators, they are all either on track or exceeded. More details in Annex O.
Outcome Indicator	Milestone	Progress	Notes
Outcome 1: Number of new services (technological innovations, services and business models) supported through the partnership	62	77 (+15 in the past reporting period)	15 new business models and 2 new technological innovations (in addition to the ones supported through the grant they received) launched by the Ecosystem Accelerator start-ups. The programme supported them through (1) funding which de-risked their existing models giving them room to iterate at a lower cost, (2) some of the partnerships with MNOs which required them to change their business models, or (3) market research / Three digital ID-related business models (economic identity and health identity services) supported through the Digital Identity programme.

Outcome Indicator	Milestone	Progress	Notes
Outcome 2: Number of changes in policy as result of programme activities or cases where GSMA is actively supporting the creation of a more enabling policy environment	22	22 (+7 in the past reporting period)	Nigeria National Broadband Plan launched in Mar-20, reflecting a number of M4D recommendations on mobile internet usage and coverage / Uganda National Development Plan elevating the role of digital and ICTs, as an outcome of the National Dialogue in this country. / Ghanaian Universal Service Fund Administrator provided land free of charge and committed to waive all import taxes and duties (Connected Society coverage fund) / Successful advocacy of the Benin, Tanzania and Zambia policymakers in regards to Digital ID matters / Supported the Tunisian government to develop an early warning system (EWS) to alert citizens at risk of major natural disasters

Outcome Indicator	Milestone	Progress	Notes
Outcome 3: Number of services (including technological innovations and business models) supported or influenced by the partnership and that are reaching early indication of scale	27	29 (+10 in the past reporting period)	Digital Inclusion: MTN Benin deployed the Mobile Internet Skills Training Toolkit (MISTT) on a national scale (see below), whilst 5 Connected Women Commitment Partners’ services demonstrated that they are reaching early indication of scale (i.e. more than 100k users) / Access to Energy, Water and Sanitation: Jazz (energy, Pakistan with 265,000 users) and KCCA (Sanitation, Uganda, with 31,280 users) reached scale / Supporting the Digital Ecosystem: two additional grantees reached scale by raising over $1 million in additional non-grant funding: GiftedMom (Cameroon) and eSewa (Nepal). In total nine Ecosystem Accelerator-funded grantees have now reached scale since the start of the Partnership

Reliance Jio (India): The Jio Phone is a low cost 4G-enabled handset. At launch (2017), it was available for a deposit of Rs 1,500 Rs (less than $25) but this has been frequently discounted to maximise affordability and uptake of the phone. Since September 2019, the deposit has been just Rs699 (less than $10), with large data plans offered at Rs 155 (less than $2) per month. By providing a low-cost 4G enabled option, the JioPhone has made internet affordable and accessible for the digitally excluded in India – the vast majority of whom are women. In doing so, Jio brought 100 million internet-deprived feature phone users (including millions of women) onto its mobile broadband platform, many of whom are getting online for the very first time. For further details, see case study (p34)

Outcome Indicator	Milestone	Progress	Notes
Outcome 4: Amount of additional £ funding mobilised for the technological innovations and business models trialled through the innovation fund	£295m	£445.6m	Access to Energy, Water and Sanitation: £261.6m, 28 times the amount of funding received from the Utilities fund / Supporting the Digital Ecosystem: The total amount of funding raised by Ecosystem Accelerator grantees is now £195 million, equal to 31 times the amount of funding received from Ecosystem Accelerator innovation fund

Figure 10: Additional funding raised by the Ecosystem Accelerator start-ups
Figure 11: Scale and performance of the Ecosystem Accelerator programme

Outcome Indicator	Milestone	Progress	Notes
Outcome 5: Number of activities GSMA has contributed to, which are likely to result in transformational impact over time	13	13 (+3 in the past reporting period)	Pakistan National Dialogue, where the government reiterated its commitment to support the growth of the digital economy and then announced a significant reduction in sales and withholding tax, up to 86%, on imported smartphones valued at USD100 or less / Advocacy to the World Bank DDP to include a focus on gender as part of their support to the Africa Moonshot initiative / Work done by MNOs during this COVID-19 pandemic has been quite transformational to the lives of the underserved, in particular in critical areas such as water, health or education (as illustrated by the many insights collected in the knowledge Hub).

Outcome Indicator	Milestone	Progress	Notes
Outcome 6: Perceived non-monetary value of GSMA M4D’s grants to raise further funding and unlock partnership with MNOs (qualitative)	Fundamental	Fundamental	Stakeholders saw GSMA’s value to raise additional funding mainly e.g. through the credibility given by the GSMA which automatically gives grantee a certain reputation in the eyes of other potential investors and MNOs or the due diligence conducted by the GSMA on grantees, which act as a “guarantee” of a project with potential for MNOs

[SP2] Although the second phase of the Partnership has relatively similar outcome targets to the first phase, two new outcome indicators were added.
Outcome Indicator	Milestone	Progress	Notes
Number of citations of programme messages and endorsement of Partnership programmes by non-MNO influential stakeholders	1	5	Includes citations from Alliance for Financial Inclusion (Connected Women) and the Responsible Financial Forum (Utilities).
Number of cases where digital players and their partners implement action plans/ new business strategies / use cases / partnerships to better reach underserved populations through digital solutions	1	1	As an outcome of the engagement between the Assistive Tech programme, Dialog Sri Lanka initiated a disability inclusion strategy and formed a strategic partnership with Petralex to offer an affordable and accessible smartphone-based hearing enhancement solution targeted at those with hearing impairments.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the sections above, the first phase of the Partnership has delivered very strong value for money. The theory of change and M4D operational model have been validated by these past 4 years and the second phase of the Partnership is likely to follow the same path. Early evidence of this includes:
- Higher than expected number of new Connected Women commitments by MNOs.
- Higher than expected interest from the private sector on the inclusion of people with disabilities, as evidenced by five MNOs already interested.
- Thought leadership of M4D insights, as evidenced by the high level of citations and endorsement of the GSMA insights in the past months.
- Engagement of local DFID offices: The Central Insights Unit has been instrumental in building stronger relationships between GSMA and the DFID local offices, enabling GSMA to be closer to DFID’s in-country challenges and needs and therefore providing additional value for money.
- Continued level of crowding in from other donors: in this incoming period, it is expected that DFAT, GIZ and Sida will add new funds to the Partnership.
## C. DETAILED OUTPUT SCORING

Output Title	The M4D team (and its partners) actively engage with operators to implement partnership activities
Output number:		1	Output Score:	A+ (moderately exceeded expectations)
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 – Number of documented commitments received from operators to take a concrete action to increase mobile access and usage (cumulative)	321	347 (overachieved)
1.2 – Number of cases with evidence of concrete actions (e.g. implementation of project) being taken by operators (cumulative)	125	148 (overachieved)
1.3 – Number of low/medium-income countries actively represented within M4D-driven activities (cumulative)	65	70 (overachieved)
1.4 – Intensity/quality of MNO engagement (qualitative)	Medium	Medium

[SP2]

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Number of measurable action plans / partnerships agreed (involving a digital player) to deliver digital solutions	12	22 (overachieved)
3.2 - Number of key stakeholders/MNOs from low/medium-income countries are consulted in the strategic decisions of Strategic Partnership (cumulative)	5	28 (overachieved)

Briefly describe the output and provide supporting narrative for the score

1.1 - Number of documented commitments received from operators to take a concrete action to increase mobile access and usage
1.2 - Number of cases with evidence of concrete actions (e.g. implementation of project) being taken by operators
Digital Inclusion
Connected Society achieved eight additional commitments, four of them leading to implemented projects. On usage especially, the programme supported a second deployment of the partnership between Ooredoo Group and Facebook in Indonesia, as well as supported MTN Benin to rollout MISTT.
The Connected Society programme worked with Orange and Vodacom in DRC to pilot active infrastructure sharing for the first time in the country. The purpose of the pilot was to test this business model as means to improve the economics of extending coverage to rural areas. The programme supported the two MNOs with the selection of areas to deploy the new sites and the implementation of required interfaces/processes between the two operators. The selection of sites was mainly informed by the analysis of the DRC Mobile Coverage Map. Coverage maps are a powerful tool to explore the availability of mobile coverage in every location, estimate the amount of people who can be reached and provide key information for the business case of expanding mobile coverage. 14 maps are now available, including 6 done this year (DRC, Benin, Sierra Leone, Burkina Faso, South Sudan and Guinea).
Looking specifically at digital/financial inclusion from a gender angle, the Connected Women Commitment Initiative reached a cumulative total of 54 Commitments from 38 operators to increase the proportion of women in their mobile money and/or mobile internet customer bases. There were 8 additional cases of concrete action taken by them this year, including launching or improving services to: support women’s safety (such as the launch of Robi Ichchedana in Bangladesh); offer affordable handsets or data packs (such as Reliance Jio’s JioPhone in India) and mobile money apps (see box below).
[SP2] In the second phase of the Partnership, the programme has launched a second phase of the Connected Women Commitment Initiative (2020 to 2023). The programme has achieved 16 commitments (+6 versus target) from 12 MNOs.

 [SP2] Now looking at digital inclusion from a disability angle, the Assistive Tech programme has secured engagement from Vodafone Ghana, Airtel Ghana and Dialog Sri Lanka to collaborate on research to better understand the mobile disability gap in Ghana and Sri Lanka and drive actions on the digital inclusion of people with disabilities. This leads to the overachievement of the target of 2 action plans/partnerships agreed (+1 versus target).
Instrumental to digital inclusion is the ability to have a digital identity. The Digital Identity programme supported MNOs to launch three Digital Identity services this year (+1 versus target): a digitally accessible health platform (“One Health”, Kenya) that leverages Safaricom’s data to create a unique and interactive health identity; an economic identity platform (Mobitel Sri Lanka) targeting fisherfolk; and an economic identity service for small business owners (particularly women) in Nigeria (9Mobile).
Access to Energy, Water and Sanitation
The M4D Utilities programme achieved 7 additional commitments this year (+5 versus target) and 8 previously made commitments were converted into actions by operators (+5 versus target). Examples of these partnerships include Orange Burkina Faso with Greenlight Planet. The programme also supported Uduma to partner with Orange Burkina Faso, in addition to Orange Mali. Airtel Madagascar and Baobab+ formed a partnership too.
Looking at the IPN Hub project, this year was extremely successful as the IPN Hub achieved a major milestone – transitioning it to a sustainable future. In addition, the platform continued its growth this year with a YoY increase of:
- Unique transactions by 100% (from 2,895,795 to 5,786,145);
- Unique MSISDNs served by 79% (from 155,028 to 277,718).

Figure 12: countries of operations of the IPN Hub as of April 2020
Supporting Digital Ecosystems
This year, the Ecosystem Accelerator achieved 8 additional commitments (+10 versus target) with all of them converted in actions by operators (+8 versus target). Examples of these partnerships include eSewa’s partnership (January 20) with Smart Cell Nepal to distribute Smart Cell SIM cards and airtime through their network of 75,483 agents across Nepal. Agrocenta and Vodafone in Ghana concluded a second partnership, where the operator provides discounted devices and packages to farmers through AgroCenta’s mobile app.

COVID-19 mitigation
In May 2020, the GSMA AI for Impact (AI4I) team kicked off the project to leverage mobile big data analytics in response to COVID-19. The team has reached out to MNOs to assess their interest and map their capabilities. In addition, the programme engaged with DFID country offices (including Nigeria, Burkina Faso, Sierra Leone etc.) Four markets have been selected so far (DRC, Pakistan, Benin, Burkina Faso) and 1 signed Letter of Intent (DRC) has been received. (counting as one action plan in the [SP2] logframe).

Climate change
[SP2] The CleanTech programme facilitated 2 new partnerships. These partnerships are a direct result of the E-waste webinar held by GSMA, which resulted in the ITU proposing MNOs to sign and commit to the Global Circular Electronics Partnership (CEP). GSMA facilitated the introductions and recommendations resulted in Safaricom and Globe Philippines’ signing on to CEP.
1.3 – Number of low/medium-income countries actively represented within M4D-driven activities (cumulative)
The cumulative total figure of 70 low/medium-income countries excludes double-counting as many programmes are active in certain countries.
1.4 – Intensity/quality of MNO’s engagement (qualitative)
During the endline evaluation conducted by Altai this year, they graded this output as ‘medium’, based on feedback from grantees, MNOs, international stakeholders and GSMA team members.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The value for money 4E’s table is detailed in section E. Regarding this output in particular:
- Connected Women and Assistive Tech has a mandate to ensure that gender and disability are taken into account in the design and delivery of the other programmes of the M4D portfolio. For example, Assistive Tech has also influenced the approach of the M4H and AgriTech (run by RED’s Agriculture team) programmes in regards to disability.
- The successful transition of the IPN Hub to the industry marks the completion of a thorough due diligence process whereby 6 proposals from industry players were received, then evaluated against strict qualification and selection criteria and eventually presented to a selection panel (comprising of DFID and GSMA senior management).
Describe any changes to this output, and any planned changes as a result of this review.
No changes to this output for the first phase of the Partnership (final year). Any amendments made for Phase 2 of the partnership will be reflected in the 2021 Annual Review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation (June 2019)	Progress
IPN Hub: The GSMA and DFID will agree on the best option to ensure financial and commercial sustainability of the IPN Hub. Options appraisal to ensure growth and sustainability of the service is currently underway and will be presented in September 2019 and implemented in the following 6-12 months	Achieved. Through a rigorous process, the transition of the IPN Hub has been successfully completed.
Analysis of the routes to scale (science of scaling) – building on the innovation fund portfolio (EA, M4D Utilities and M4H) and programmes like Connected Women. Such an analysis will collaborate with relevant partners (e.g. Wheeler Institute, London Business School) and will inform the next phase of the Partnership.	Ongoing (on track): Collaboration between the Partnership and the Wheeler Institute has started with an MoU signed in June 2020. Results from this collaboration are expected to be delivered by June 2021.

Lessons Learned this year
Digital Inclusion
- [SP2] In the first year of the programme, the Assistive Tech programme developed a flexible and bespoke suite of MNO activities depending on the maturity of their disability strategies, which helped the programme to get good traction from MNOs.
- Digital Identity is progressively maturing: taking the lessons learnt from past years, the programme now provides both regulatory support and guidance to MNOs, which helped ensure that policy barriers are identified early and suitably resolved prior to any pilot launch.

Access to Energy, Water and Sanitation
Partnership between MNOs and PAYG solar businesses: The programme activities suggest that MNOs are generally better suited to partnering with PAYG solar businesses rather than leading these businesses themselves. This is because the PAYG solar model is very complex. The level of investment to succeed is very high and would compete with MNOs’ core business.

Supporting Digital Ecosystems
The Ecosystem Accelerator programme identified three main factors encouraging partnerships between MNOs and grantees:
- Step by step Capacity Building to help start-ups to best articulate their value proposition to MNOs while MNOs gained insights on how to work with start-ups.
- Articulating the value for MNOs to ‘outsource’ innovation: Through collaboration, MNOs can build a stronger competitive advantage by leveraging unique product offerings and innovative operating business models
- Funding & Access to Mobile Operators: the funding from the programme helped start-ups to de-risk their projects This has resulted in early indicators of scale such as paying customers, product adoption. It also helped them build a better proposition and partnerships with MNOs.
COVID-19 response and recovery
There is a lack of awareness within governments of mobile data analytics and how they can be used in the COVID-19 response. Educating government stakeholders and addressing regulatory challenges is key to the project. On the other hand, there has been significant initial interest from MNOs and some government stakeholders to engage on this project, showing the strong appetite for this project in the COVID-19 context.
Recommendations for year ahead: none

Output Title	M4D Innovation Funds select, fund & support technological business model innovations
Output number:		2	Output Score:	A (met expectations)
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)	2,804	2,830 (overachieved)
2.2 Number of grantees of the Innovation Fund (disaggregated by geography)	84	84 (achieved)

[SP2]
Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of applications received through Innovation Fund rounds	0	597 (overachieved)
2.2 Number of grantees contracted through the Innovation Fund which offer digital solutions to proven problems	0	0
2.3 Percentage of grantees which have a plan for sustainability at grant close	0	0

Briefly describe the output and provide supporting narrative for the score
The last reporting period saw the launch of two innovation funds: an unplanned Fund on COVID-19 emergency response and one new Fund on Mobile Internet Adoption and Digital Inclusion. Ecosystem Accelerator, M4D Utilities and Disaster Response funds have been successfully closed.
Innovation Fund	Status	Total funding awarded	Number of grantees	Comments
Mobile Internet Coverage Fund	Ongoing	£639,264 (+£326,822 cancelled)	2 (+1 cancelled)	Despite delays due to COVID-19, Nuran Wireless (Ghana) is on track for their forecast go-live date of end of July 2020. / iSAT (Uganda) have suffered more significant setbacks due mainly to the shutdown of the MTN testing facility (closed in March). The facility has recently reopened making it realistic for the sites to go live in August / Fairwaves (Ghana) withdrew from the Fund, citing insurmountable financial and resourcing difficulties
COVID-19 Emergency Response Fund	Ongoing	£443,689	9	In response to the COVID-19 pandemic, GSMA launched a COVID-19 Emergency Response Fund in May-20. The programme received 13 expressions of interest which were brought forward to a Panel on 15th June 20 (see table 1)
Mobile Internet Adoption and Digital Inclusion Fund	Ongoing	Up to £2.5m	Up to 12-15	In April the GSMA Innovation Fund launched its first funding round, focused on Mobile Internet Adoption and Digital Inclusion in collaboration with the Connected Society and Connected Women programmes. The fund has closed with 597 applications received and has short-listed 27 (see figure 13)
Disaster Response	Closed	£1,282,150	5	The 5 grantees exceeded their impact target, reaching 105k beneficiaries (115% of the target)
Ecosystem Accelerator Rounds 2 and 3	Closed	£6,247,396	32 (+2 cancelled)	The Ecosystem Accelerator successfully closed 17 grants from Rounds 2 and 3 this year. Only two grantees – Lipamobile (Uganda) and Pacific Ads Group (PNG, DFAT-funded) - had their grant cancelled because of substantial delays to implementation. The full portfolio can be found here and in the figure 14 below.
M4D Utilities Phase 3 (2 rounds)	Closed	£3,409,143	16 (+3 cancelled)	The M4D Utilities Innovation Fund successfully closed 16 grants from phase 3 this year (see figure 15 below). 3 grants were terminated (AWCC, Simgas and Orange Burkina Faso) for different reasons whilst three others (Uduma, Practical Action and KCCA) had their grants amended (due to significant delays).

Sector	Organisation	Country	Impacted Beneficiaries	Award amount
Health-tech	Sehat Kahani	Pakistan	300,000	£50,000
	Kea Medicals	Benin	45,000	£49,710
	oDoc*	Sri Lanka	99,464	£50,000
Water	Drinkwell	Bangladesh	127,765	£49,096
	Safe Water Network*	Ghana	171,600	£50,000
	Uduma	Burkina Faso	200,000	£44,883
Sanitation	Loowatt	Madagascar	1,350	£50,000
Ed-tech	Eneza Education	Cote d’Ivoire	150,000	£50,000
Food Security	Agrocenta*	Ghana	100,000	£50,000
Total			1,195,179	£443,689

Table 1: grantees of the COVID-19 emergency response fund

Figure 13: short listed applicants of the Mobile Internet Adoption and Digital Inclusion Fund

Figure 14: geographical locations of the Ecosystem Accelerator grantees

Figure 15: Statistics of the M4D Utilities Innovation Fund (phase 3)
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The value for money 4E’s table is detailed in section E. Regarding this output in particular:
- The GSMA launched an RFP to select a new Fund Manager for the activities under the second phase of the Partnership. The RFP Process resulted in savings in negotiation of £356k (26% decrease vs initial offer).
- [SP2] Under the second phase of the Partnership, the GSMA Innovation Fund is the centralised Innovation Fund facility, enabling consistency and therefore efficiency across the portfolio.
Describe any changes to this output, and any planned changes as a result of this review.
No changes to this output for the first phase of the Partnership (final year)
[SP2] The logframe has been updated, taking into account the recommendations of the annual review, especially around potential sequencing of the Innovation Fund.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation (June 2019)	Progress
Use the Ecosystem Accelerator model throughout all relevant social-enterprise orientated innovation funds in the second phase of the Partnership (i.e. not Connected Society)	Implemented. Leveraging the lessons learnt from the Ecosystem Accelerator and model for success, the GSMA Innovation Fund now offers a centralised facility to manage all new Innovation Fund rounds under the new phase of the Partnership.
Owing to the slow development of technological innovations around coverage, it is recommended that the second round of the Connected Society fund focuses on innovative solutions to tackle the usage gap	Implemented. The first round of the GSMA Innovation Fund is focused on Mobile Internet Adoption and Digital Inclusion

Lessons Learned this year
Connected Society coverage fund: this continues to be a complex fund to manage. Owing to the number of dependencies between sub-grantees, consortium partners, suppliers and MNOs, it is clear that funds implementing infrastructure projects require longer runways for planning and implementation prior to going live.

M4D Utilities / energy portfolio: The KOPAGAS scaling grant and ultimate investment from Safaricom are a great validation for the business opportunity for MNOs in energy service models and the maturity of this sector. The programme will now shift to providing advocacy and insights.

M4D Utilities / water portfolio: the fund panel decision to focus on initiating scale for some of the previous water investments (i.e. CityTaps and Safe Water Networks) and new portfolio companies (i.e. Drinkwell), had a good pay-off, with these companies gaining traction and attracting further investment.

M4D Utilities / sanitation portfolio: the portfolio demonstrated these solutions do show promise, but the models are still difficult to scale given the significant government under-investment in sanitation infrastructure, and the financial viability challenges of fully private models. For parts of many cities, decentralised solutions will play an increasingly important role.

COVID-19 Emergency response fund: given the emergency of the COVID-19 pandemic and the relevance of many past grantees to address this emergency, the design of a more lightweight process (compared to a regular Innovation Fund) proved to be impactful. This enabled a quicker selection of grantees whilst ensuring strong compliance.

     Recommendations for the year ahead
Execute a No Cost Extension for the Connected Society Fund Round 1 through to March 2022, to ensure pilot sites are live for no less than 12 months to maximise reporting and evaluation opportunities [Sep-20]

- [SP2] Launch the second round of the GSMA Innovation Fund, dedicated to digital inclusion targeting people with disabilities [Sep-20]
- [SP2] Innovation Fund: DFID/FCDO and the GSMA will decide the sequencing, topics and overall timeline of the next Innovation Fund rounds. Topics include climate, solutions for urban poor and frontier-tech topics such as AI / digital identity solutions [Sep-20]

Output Title	The M4D team generates, disseminates and promotes research, insights and learnings
Output number:		3	Output Score:	A+ (moderately exceeded expectations)
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Usage: number of publications downloaded from the GSMA M4D website and physically distributed (content relevant to the partnership) (cumulative)	46,433	68,471 (overachieved)
3.2 Thought Leadership: Number of publications which demonstrate new insight including reports, blog posts, case studies and videos	153	176 (overachieved)
3.3 Events: # of convenings (of which # include at least 3 types of stakeholders) whose purpose is to disseminate learnings (cumulative)	213	244 (overachieved)

[SP2]

Indicator(s) – SP2	Milestone(s) for this review	Progress
1.1 Number of thought leadership pieces produced by the Partnership (disaggregated cross-programme insights)	5	5 (achieved)
1.2 Number of closed-door convenings where we strategically engage key stakeholders on national and regional levels (disaggregated by type of stakeholders)	4	10 (overachieved)
1.3 Number of cases where GSMA messages are disseminated at international high-level platforms (excluding GSMA events)	2	12

Briefly describe the output and provide supporting narrative for the score
The GSMA exceeded all output 3 targets, a result of M4D’s ability to generate new reports focused on key issues that resonated with key stakeholders as well as strong dissemination plans and marketing support. All programmes proved adept at ensuring key reports originally planned for launch during MWC20, such as the 2020 Mobile Gender Gap Report, and were well publicised despite that event’s cancellation in mid-February due to COVID-19 concerns.
Output 3.1 – Usage: number of publications' downloads from the GSMA M4D website and physical distribution (content relevant to the partnership)
The six programmes published new written insights, which have been downloaded or physically distributed a total of 25,087 times during the past reporting period. This brings the Partnership’s cumulative total to 68,471, which greatly exceeds the Year 4 cumulative target of 47,664. In addition, 15 videos were produced by the Ecosystem Accelerator, Digital Identity and Mobile for Development Utilities programmes, which were viewed online a total of 10,230 times.
Output 3.2 – Thought leadership: Number of publications which demonstrate new insight including reports, blog posts, case studies and videos (cumulative).
37 new reports and case studies (which surpassed the annual target of 28) were produced, with some highlights below. Please also note, under [SP2], the Digital Solutions for the Urban Poor report which will be instrumental in the new direction of the Utilities programme under the second phase of the Partnership.
Digital Inclusion
The Mobile Gender Gap Report 2020 showed that over half of women in low- and middle-income countries now use mobile internet, and the gender gap is narrowing.
Since publication in March 2020, it has been downloaded 1,379 times and cited by a variety of stakeholders (including Executive Director of UN Women, the Arab Women’s Enterprise Fund, and Georgetown Institute for Women’s Peace and Security). In addition, despite the cancellation of MWC 2020 and the Connected Women Seminar, there was strong coverage of the report internationally (e.g. in Forbes, CNBC Africa, The Economic Times and The Daily Jang), including a joint op-ed piece with DFID emphasising the increased importance of addressing digital inclusion for women during the current COVID-19 pandemic.

It has been already well established that mobile internet – particularly mobile broadband– has widespread macroeconomic impacts. However, the evidence is less clear on the impacts for individuals, especially those living in extreme poverty. To address this gap, the GSMA and the World Bank developed an innovative and ground-breaking study to evaluate the causal impact of mobile broadband on welfare and poverty-reduction in Nigeria, the largest economy and mobile market in Africa.
The study estimates the impacts of mobile broadband coverage on household consumption and poverty in Nigeria, in particularly using the Mobile Coverage Map developed by the GSMA.
The study finds that mobile broadband coverage had large and positive impacts on household consumption levels which increased over time, although at a decreasing rate. Mobile broadband coverage also reduces the proportion of households below the poverty line, driven by higher food and non-food consumption in rural households. These effects are mainly due to an increase in labour force participation and employment, particularly among women.

Figure 16: some insights of the “Value of PAYG Solar for Mobile Operators” report
The coronavirus (COVID-19) pandemic has magnified existing weaknesses and gaps in health systems. Developing countries have been severely affected. From under resourced health facilities to poor data and information coordination, weak health systems pose serious challenges for developing country leaders and development partners working to mitigate the impact of COVID-19 and other health issues.
The Health system strengthening tool for developing countries paper highlights tangible examples of digital health and digital solutions that are strengthening health systems across the developing world. The work on Digital Health is also being used by DFID to inform their regional COVID-19 response efforts
Output 3.3 – Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings.
Together, all programmes organised, hosted and/or spoke at 57 convenings during the reporting period. This includes GSMA events, such as m360 Africa in July 2019, as well as various external meetings hosted by key stakeholders, specifically: Seedstars, UNICEF, ID for Africa, Alliance for Financial Inclusion, GOGLA, UNESCO, the World Bank, the World Economic Forum, and the United Nations General Assembly.
Also, under [SP2] The Central Insights Unit conducted country-level engagements with DFID’s country offices (India, West Africa, Senegal, Sahel region, Rwanda), shared insights at DFIDs’ Futures workshops and also supported the Frontier Tech hub and other DFID partners in reviewing reports and applications for funding to share M4D’s thought leadership on mobile-enabled tech solutions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Please see output 1 for a VfM assessment

Describe any changes to this output, and any planned changes as a result of this review

No changes to this output.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation (June 2019)	Progress
Although GSMA insights are well adopted overall, it is doubtful that the industry stakeholders have the time to absorb all the insights produced in a year. It is proposed that, in the next phase of the Partnership, GSMA produces less but consolidated insights and concentrates on the dissemination of them	Implemented. The first version of the Partnership logframe reflects M4D’s move towards the production of more targeted insights. In addition, each insights piece has its own dissemination plan and GSMA keeps exploring new ways of dissemination though webinars, videos etc…
The GSMA will undertake the following activities under the new Partnership by July 2020: / Landscaping study on the future of Youth employment in SSA (in partnership with Mastercard Foundation) / Landscaping study on Data and AI for Development Impact (with DFAT, EPIC and Digital for Development) - pending agreement by DFAT / Landscaping study on Digital Health with the RED Health team / Increase number of coverage maps, to include a minimum of Sierra Leone and Malawi, based on demand from those country offices	The CIU concluded the landscaping study on the future of youth employment in SSA (MCF funding) and also organised a workshop in Ghana, which validated the drivers, barriers and skill gaps affecting youth employment through mobile industry in SSA. This year, the CIU aims to deep dive into 3 additional countries in East, West and Southern Africa. / The CIU has started a landscaping work on AI in the developing world to understand the current and potential use of AI in the developing markets in Africa and Asia Pacific (APAC) regions. This report will be published in Sept-20 / The CIU has published a landscaping study on digital health (see output 3.2 above). The work on Digital Health is also being used by DFID to inform their regional COVID-19 response efforts / Finally, the Connected Society programme produced an additional 6 coverage maps (see narrative in output 1). Due to persistent issues with Airtel Malawi to share their data, the coverage map is yet to be produced.

Lessons Learned this year
In the coming year, the number of new reports set to be published will drop and the number of concise, targeted case studies will increase. When detailed reports are produced, teams will ensure that engaging infographics or a video will accompany these insights along with dissemination plans to ensure that they can attract as wide an audience as possible.

The CIU’s work has been instrumental to strengthen the work of GSMA with regional DFID offices. The model of engagement trialled this year has proven successful and clearly fulfils an unmet need of regional offices (e.g. DFID’s Futures Workshop and work on Digital Health / COVID-19).

     Recommendations for the year ahead
M4D dissemination strategy: from the end line review of the Partnership undertaken by Altai Consulting, GSMA is considered best placed to fill the knowledge gap in the M4D space due to its expertise and global perspective on M4D topics. Altai Consulting recommended that the dissemination strategy of GSMA could however be fine-tuned by using innovative formats, organising launch events and providing training. This dissemination strategy will be shared by [Mar-21].

D: RISK

Overall the risk of the DFID GSMA Foundation Strategic Partnership is judged to be Moderate. The full risk matrix is attached in Annex N, with the three top risks being:

COVID-19 restrictions impact implementation of innovation fund grantees, strategic partnerships, fieldwork for research projects and dissemination of programme message: as mitigating actions, the programme have adapted their activity plans from face-to-face to virtual and leveraged in-country resources / consultant where possible to minimise travel.

The achievement of some programme goals can be dependent on regulatory environments that could delay projects: as mitigating actions, the Partnership programmes regularly engage with regulators (e.g. through National Dialogues) to build the case of the socio-economic benefits of M4D projects and influence them.

The risk profile of the Partnership is increasing given DFID’s commitment to fragile countries, leading to reputational risks for DFID: as mitigating actions, the GSMA has developed a risk assessment framework to analyse country wise risk and align the sub-grant pre award due diligence and monitoring processes with the risk.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Compared to the original business case, original logframe and original budget, the first phase of the Partnership concludes very well as, at the end of the final year of implementation:
- All output and outcome indicators have been met or exceeded
- The impact target has been exceeded by nearly 100% compared to the target number included in the original business case
As underlined in section E (risks), COVID-19 is a new important risk that could derail the delivery of the partnership in the coming reporting period. Mitigations are in place but the spread of the pandemic and its duration are important factors to monitor. The second phase of the Partnership has learnt from the first phase of the Partnership and we are confident that the other risks are well mitigated.
Summary of performance
Much like 2019, this year the GSMA has continued to prove themselves as an industry leader with a unique offering to development; close links to mobile network operators and other private sector stakeholder, the ability to be a convener between private sector and development partners, and exceptional technical expertise across a broad range of thematic areas.

DFID has, once again, found the partnership to be honest, open and based on mutually agreed impact aims. The GSMA have responded in a timely fashion to all requests and demonstrated extraordinary flexibility and proactivity in managing the impact of and response to COVID-19; both in terms of regrouping and pivoting following the cancellation of MWC 2020 – the GSMA-owned and mobile industry’s biggest event and an important opportunity to showcase M4D - and developing a strategy to not only mitigate the impact of the epidemic on our programming, but to leverage the GSMA’s position at the nexus of digital and development and the M4D programming expertise to meaningfully contribute to global response efforts. The GSMA team has also been active in its engagement with other parts of DFID, especially EPIC and our broader network of country offices via the newly established Central Insights Unit.

Their performance is seen as on-par with 2019, hence the recommendation of an A+ in this Annual Review. We have been pleased with the outputs from the first months of the extension to the partnership and look forward to another strong year in 2021.

VfM considerations
Metric	VfM Measures	Relevant examples
Economy– whether the project has bought inputs of the appropriate quality at the right price?	Procurement: The GSMA is governed by the GSMA Procurement Policy covering all purchasing process, whether as purchasers. Robust procurement process is in place, which are consistent with international good practice. Specifically, it ensures competition for all procurement over the value of £50,000 and encourages it for lower value transactions / Human resources: The GSMA has strict policies in terms of recruitment, remuneration (based on set market benchmarks) and performance appraisal. In addition, staff are generally recruited in the market / close to the market of programme focus. / Travel: Booked in advance and at the cost of economy fare only. The hotel and subsistence rates meet GSMA’s strict travel policy guidelines to ensure value for money.	The GSMA has launched an RFP to select a new Fund Manager for the activities under the second phase of the Partnership. The RFP Process resulted in savings in negotiation of £356k (26% decrease vs initial offer)
Efficiency - how well the project is converting inputs into outputs? (‘Spending well’)	Input maximisation: cross-collaboration between programmes of the partnerships allows for maximum impact / DFID Profiling: GSMA M4D activities have been able to leverage GSMA flagship events such as the Mobile 360 Africa event and high-level platforms (UNGA, WEF) to profile the Partnership outputs / Monitoring and evaluation: constant improvement of services based on user feedback, business intelligence and monitoring and evaluation feedback. / Strengthened due diligence to mitigate risks that sub-grantees of the Innovation Fund could misuse funds	DFID is able to leverage the content of the entire M4D portfolio (irrespectively of the funder). Examples include Mobile Money expertise that is leveraged in the M4D Utilities and IPN Hub activities. GSMA also supports the outcomes of the Partnership by funding policy activities. / [SP2] Under the second phase of the Partnership, the GSMA Innovation Fund is the centralised Innovation Fund facility, enabling consistency and therefore efficiency across the portfolio / GSMA profiles grantees on every GSMA platform, enabling them to network, and meet investors and MNOs / GSMA has developed a risk assessment framework to analyse country-wise risk and align the sub-grant pre award due diligence and monitoring processes with the level of risk
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’)	Achievement and overachievements of all targets as set in the agreed logframe / Crowding in of new donors, demonstrating the effectiveness and attractiveness of the Partnership to other donors	The programme has now reached 32.8m users on the back of a revised £38.9m investment, meaning that the cost of each impacted user is now £1.20, therefore 55% less than in the original business case. / The Partnership has been very flexible, enabling new high-impact activities to be undertaken within the original business case funding (e.g. IPN Hub or activities responding to the COVID-19 outbreak such as the COVID-19 Emergency Response fund, Big Data project and insights on how the mobile industry has been supporting in this pandemic period) / The Partnership has attracted new donors who joined the Partnership, therefore increasing the impact of existing Partnership activities: NORAD, BMZ, World Bank in the past reporting period. Other grants are expected to be signed in the coming months.
Equity - ensuring that research is inclusive and benefitting the target group	All programmes have a special focus on equity, with two programmes fully focused on gender and disability	72% of the first phase of the Partnership’s impacted beneficiaries are women. / Connected Women and Assistive Tech has a mandate to ensure that gender and disability are taken into account in the design and delivery of the other programmes of the M4D portfolio. For example, Connected Women has been heavily involved in the CHOGM programme. Assistive Tech has also influenced the approach of the M4H and Agritech programmes in regards to disability. / The Innovation Fund programmes have always used a gender lens when evaluating investment opportunities: (1) tracking on women involvement in the start-ups selected and (2) evaluating the impact each of the start-ups have on women as their partners, vendors or users. See blog on this topic.

Monitoring activities through the review period
As part of the Partnership, an independent consultant conducted an endline assessment, focussing especially on validating the theory of change. Full details of this endline assessment can be found in Annex G.

During the past reporting period, the Partnership conducted M&E activities, especially with some of the grantees, with very satisfactory results. Full details can be found in Annex L.

Finally, as part of the second phase of the Partnership, terms of reference were approved (see Annex H), specifying the approach taken on the Partnership level. As part of the recommendations for the year ahead, DFID/FCDO and the GSMA will agree the key strategic hypotheses and questions that the M&E team will evidence [Sep-20]

Date of last narrative financial report	April 2020
Date of last audited annual statement	June 2020

## ANNEXES TO BE INCLUDED WITH ANNUAL REPORT
1. Partnership (phase 1) logframe June 2020
2. Partnership (phase 2) logframe June 2020
3. Financials actuals and forecasts (phase 1)
4. Financials actuals and forecasts (phase 2)
5. Logframe Evidences (both phases)
6. Downstream Partner mapping
7. Altai end-line report
8. M&E Terms of Reference
9. Update of the PwC due diligence
10. Pathways to scale’ paper
11. Life stories
12. M&E report summaries
13. Summary of COVID-19 activities undertaken by the Partnership
14. Full risk matrix
15. Detailed lessons learned, outcomes and outputs for this reporting period