## Annual Review

Title: Disaster Risk Insurance
Programme Value £38.9 million		Review date: March 2025
Programme Code: 203809	AMP start date: / November 2016	AMP end date: / December 2025

Summary of Programme Performance
Year	Dec 2016	Dec 2017	Dec 2018	Dec 2019	Dec 2020	Dec 2021	March 2023	March 2024	March 2025
Overall Output Score	B	B	A	A	A	B	A	A	A+
Risk Rating	Severe	Major	Major	Major	Major	Major	Major	Major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/45411632.odt
DevTracker Link to results framework:	TBC – in process of publication

A. SUMMARY AND OVERVIEW

Description of programme

Natural hazards and climate-related disasters - including sudden-onset shocks such as earthquakes, extreme rainfall and tropical storms as well as slower-onset events such as droughts and extreme heat - are among the key risks faced by the private sector in developing countries[1]. Such catastrophic events create severe disruption, put business under financial stress and lead to the destruction of productive assets. As a result, many communities and businesses face delayed/inadequate recovery and existential crises in the wake of a disaster. That, in turn, puts at risk the income and livelihood of communities, employees, producers, suppliers and consumers, with knock-on risks of wider economic setbacks, development reversals and impacts on the most vulnerable and exposed communities.
[1] World Economic Forum Global Risks Report 2019 http://www3.weforum.org/docs/WEF_Global_Risks_Report_2019.pdf

Insurance can provide much-needed, predictable finance in the wake of a shock, helping to mitigate impacts, ensure business continuity and contingency planning and play a critical role in accelerating recovery. However, most disaster risks in developing countries are under-insured and typically levels of insurance are lowest where vulnerability is greatest.

The Disaster Risk Insurance Programme (DRI) was established by the UK (alongside Germany) to mitigate the impact of extreme weather and climate related shocks through insurance and risk transfer solutions, in low- and middle-income ODA eligible countries. It is designed to build resilience to disaster risks across the public and private sectors and with regional entities and institutions (e.g. state/provincial level governments, co-operatives etc.) and humanitarian actors in developing countries. It does this through the market development and provision of risk transfer and risk insurance products, to strengthen the protection of vulnerable and risk-exposed communities. It focuses particularly on parametric insurance solutions which are based on modelled estimates of losses and disburses automatically if an event exceeds a pre-agreed magnitude. It focuses on contexts where the availability of this sort of risk transfer capacity remains scarce and most losses from disasters remain uninsured, leaving communities, business and governments under-prepared for the impact of shocks on economic growth and prosperity.

The programme was initially set up to deliver these results through the capitalisation of a new fund (NDF, the Natural Disaster Fund) to underwrite risks in ODA-eligible countries and provide payouts following shocks; alongside the establishment of a new start-up social enterprise (Global Parametrics), a distinct entity that has managed and administered the NDF since its launch. Funding and support to this programme was initially broken down as:

Establishment of a start-up social enterprise (Global Parametrics) in 2016, to develop and distribute Financial Disaster Risk Management products to protect developing country public sector, private sector and non-state entities against natural disaster risk. Support was initially provided through direct investment from FCDO (then DFID) in the form of equity (£1.5m) and debt (a £6.4m loan). This UK support was increased by a further £1.8m loan in 2019-20 in the form of a SAFE Agreement. In terms of German support, KfW’s Climate Investment Fund has provided an additional £1.5m in equity investment and Blue Orchard provided a £1.2m loan alongside our £1.8m in 2019-20.

Seed funding (£25m from FCDO/ €34m from BMZ) in 2018 for a Natural Disaster Fund (NDF) to underwrite the risk of FDRM contracts designed and distributed by Global Parametrics, to prove concept and leverage additional underwriting capital. The initial UK funding was provided in the form of non-fiscal CDel, i.e. the full amount will enable the Fund to protect against risk but will ultimately be returnable to FCDO at the end of the programme’s life. The limited partnership agreement documenting FCDO’s participation in the NDF provides that FCDO’s commitment endures for a minimum of 20 years.

Technical Assistance provided by BMZ/KfW (EUR 3m) to support capacity building and use of FDRM products by regulators and other stakeholders in targeted low and middle-income countries.

On 6 September 2023, both the UK (FCDO) and German (BMZ through KfW) governments completed the process of selling their shares in Global Parametrics to CelsiusPro AG, a Swiss-based insurtech company that acquired the entire issued share capital and so became the sole shareholder. As part of the process of selling its shares in GP, the £1.8m loan from FCDO to GP was written off, although FCDO still retains the debt funding of £6.4m, which remains returnable. The capital committed to the NDF by both the UK and Germany also remains in place - i.e. the FCDO retains its investment of £25m of first loss equity into the NDF in 2018 and the objectives of the NDF remain.

The sale was intended to secure ongoing support from a dedicated owner that was able to leverage technical and operational expertise and synergies in a particularly specialist area, in order to put GP on a strong future footing. The acquisition combines Global Parametrics’ expertise in delivering parametric solutions for disaster risk response in developing countries, with CelsiusPro’s capabilities in data science, parametric product structuring, risk modelling, and underwriting in developed economies.

Given that this Annual Review considers the calendar year 2024, this is the first programme year that reviews NDF only. The logframe has been substantially updated to reflect this change.

Summary supporting narrative for the overall score in this review

Score: A+

This has been a strong year for the programme. Performance against both outputs exceeded expectations, with a significant scale up the in volume of the financial resources deployed through the NDF and the number of poor and vulnerable beneficiaries protected. The programme is assessed therefore to have scored an A+: outputs exceeded expectations.

This growth in deployment was driven by factors including:

- The increasing presence of the Global Parametrics team and the NDF in the parametric market place, whereby the team are now a recognised risk capacity provider who are actively approached by brokers and others for participation in market-based opportunities,
- the greater reach of the combined CelsiusPro/Global Parametrics team following the completion of the acquisition of Global Parametrics in late 2023, the size of the team and resources available have significantly increased – for example the business development team which has doubled in size and the underwriting team which analyses and prices risk transfer opportunities has more than doubled in size post-merger.
- the sustained impact of the Technical Assistance Facility (TAF) in enabling high impact risk transfer programmes to come to fruition,
- the adjustment to the Hannover Re/NDF risk sharing ratio to leverage further the NDF capital and,
- the increased activity of new providers of subsidy for premium financing.

The sale has enabled Global Parametrics to benefit from the additional climate risk products, technology and consulting services that Celsius Pro offers, deepening the resource available for it to draw on and enabling it to operate on a more regular commercial basis. The NDF has retained a focus on development impact in ODA-eligible countries and the UK and Germany have continued to guide NDF governance and direction through the Advisory Council and Development Committee. As the NDF’s only Limited Partners, the UK and Germany are the sole participants in these committees outside Global Parametrics and Celsius Pro representatives.

Further to this strong performance, there are ambitious plans in place to further expand the NDF’s impact. GP are actively exploring with relevant stakeholders how the Lloyd’s of London architecture, which is able to offer customer solutions in more than 200 countries globally, can help facilitate and increase the scale of NDF activities.

Case Study 1

Mahila Housing Trust (MHT)– an extreme heat solution for women entrepreneurs
Climate-driven extreme heat events are becoming more intense, frequent and deadly. More than 70% of the global workforce – some 2.4 billion people - are now at risk from death or injury as a result of extreme heat, and by 2050 heat waves are predicted to claim some 1.6 million lives globally.In 2019, an estimated 302 billion working hours were lost due to higher temperatures, while loss of labour caused by heat stress wiped out the equivalent of 4% of Africa’s GDP in 2022.

Global Parametrics was one of the first to recognise this risk and since 2021 has been developing and piloting a pioneering parametric solution for vulnerable women entrepreneurs living and working in slums in three cities on the extreme heat frontline in India. 80% of India’s workforce is in the informal sector, with poor women making up more than nine-tenths of that number – typically self-employed or working on a daily basis, with few regulations, rights or protections, but often with whole families dependent on their earnings.

A new excess heat insurance solution was developed with funding from NDF’s Technical Assistance Facility and offered exclusively to women’s credit co-operatives (solidarity groups of local women who come together to access financial services as a group) affiliated to MHT. Payouts are triggered by two consecutive days of high temperatures, with the threshold varying between the three cities but starting at just over 37 ˚C. A larger payout is triggered if a second, higher threshold is reached, around a degree higher than the first in each setting.

Following several years of piloting, the product was launched this year (2024) with risk capacity from the NDF underwriting the credit co-operatives, and with Humanity Insured covering much of the cost of the premiums through a ‘smart subsidy’ approach that will see their share decrease over the next three years as the women covered take on a bigger share of the premium costs themselves. As is typical with NDF transactions, Hannover Re will take 50% of the risk, doubling the impact that the NDF cover can provide and leveraging genuine private sector additionality.

26,000 direct beneficiaries and their families are now covered across the three cities – and in its first year of operation the policy has already triggered, with a swift payout of $17,000 having been released in May 2024.

Major lessons and recommendations for the year ahead

Major lessons from the past year

The NDF’s lack of a global insurance fronting solution adds costs and time in putting together transactions. Currently the NDF operates on the reinsurance level meaning they cannot legally interface directly with the business or national entity buying the insurance but only with an insurance company. This requires them to put in place a fronting insurance solution to reach the underlying beneficiaries. While a fronting insurance solution is sometimes built into the structure of a transaction there is frequently a need to identify, onboard and pay for a fronting insurer for each transaction. GP/CP are exploring options to reduce these costs.

The NDF’s Technical Assistance Fund (TAF) has played a catalytic role in developing innovative, high-impact programmes. The TAF is the primary vehicle for the establishment of ‘GP-originated’ transactions. These are a key point of difference for the NDF. Global Parametrics have made it clear that the TAF has a key role to play in covering a significant proportion of the costs relating to bringing opportunities to fruition and removing l hurdles to progress. The TAF’s role is particularly crucial for the development of insurance solutions that create protection for the poorest and most vulnerable beneficiaries in markets where institutional capacities are low.

There is a continuing need to support the wider enabling environment for parametric insurance products, particularly in building brokers’ capability in understanding these products. Educating brokers and other key business-introducing intermediaries is a key pre-requisite to growing the origination of new parametric risk transfer opportunities. GP/CP have continued to play an important role in building this market awareness. In 2024, the GP/CP team developed and launched “Parameter Pro” which is a technology platform designed to enable brokers and other key intermediaries to readily structure and determine an expected loss in respect of a series of natural catastrophes. It will be important for GP/CP to draw from others working in this area given ever-changing market and regulatory conditions.

Case Study 2

Tearfund multi-country drought protection

The humanitarian charity Tearfund is taking out cover through the NDF to protect its in-country programming and support across the four most drought-vulnerable countries where it has ongoing operations. The new initiative will cover 140,000 beneficiaries across Ethiopia, Malawi, Nepal and Pakistan - with payouts supporting drought response activities including cash transfers; improved water conservation, access and storage; water purification; and targeted support for livestock and agricultural workers.

The product is also making use of an innovative ’40-day rolling window’ to assess possible drought conditions. The window becomes active on day one of the season and considers whether the drought trigger has been met in any period of 40 consecutive days, working backwards from the most current day and rolling on a daily basis. This means drought can be identified and payouts made much earlier, enabling Tearfund to take a more anticipatory approach to impacts, rather than having to wait until the end of the season before drought can be declared.

The product was developed with funding from the NDF Technical Assistance Fund before being included as a risk transfer transaction by the main NDF, with premium financing support being provided by Humanity Insured for a period of three years. Tearfund operates in 50 countries globally, providing opportunities to scale both geographically and to also cover additional hazards including tropical cyclone, earthquake and flood.

Recommendations for the year ahead

Global Parametrics should continue to finalise ongoing efforts to significantly increase the volume of private capital leveraged alongside the NDF. Bringing new private risk capacity providers on board will increase the amount of private capital available and raise the profile of the NDF and its impact.

Global Parametrics should continue to explore ways to demonstrate and monitor its impact, particularly for poor and vulnerable beneficiaries. GP have made a concerted effort over the past few years to better capture their impact – including through the publication of an annual impact report. Given the NDF is often one step removed from the final beneficiary (as a reinsurer); it can be challenging to monitor impact at a granular, business or household level. GP should continue to explore ways, particularly for transactions it originates, to better capture impact for end beneficiaries.

Global Parametrics and the FCDO should develop an updated theory of change by December 2025 for the NDF, reflecting changes in GP’s operating model. The programme’s theory of change has not been updated since the original business case was approved and the underlying assumptions underpinning the TOC should be tested.

FCDO should continue to ensure that the core mandate of the NDF to help poor and vulnerable people from low- and middle-income mitigate the impact of extreme weather and climate related shocks is maintained regardless of any change in structure. The FCDO is represented on the Advisory Council and Development Committee. The Advisory Council is a joint body responsible for the management and oversight of the NDF. The Development Committee is responsible for ensuring that any new proposal is focused on ODA-eligible contexts and is able to demonstrate development impacts that are in line with the aims of the programme’s business. The FCDO should continue to ensure its effective oversight of the NDF is maintained through these committees.

FCDO, KFW and GP should agree whether there remains a need for a standalone ‘business plan’ or whether the strategic plan developed through the AC is sufficient.

Progress against recommendations in last year’s annual review

Recommendation	Progress
GP should now look to benefit from the further resources it can now draw on following the sale. In particular, this includes a deeper team of business development specialists, the faster risk analysis, structuring and pricing of risk transfer opportunities that the combined technology of CP Group enables in order to further grow both uptake and profitability.	Achieved – The successful integration of the GP and CelsiusPro teams during the course of the last 18 months has enabled the combined group to benefit from further resources. The group has actively recruited on the business development front, including two new senior business developers,
GP should explore potential interest from other risk capacity providers to offer risk capacity on similar terms alongside Hannover Re, further leveraging private capital – although it will be important to do this in a way that does nothing to jeopardise the existing arrangement.	Achieved - The principal focus of the GP team during the course of the past year in terms of mobilising third-party risk capacity has been through discussions with Lloyd’s regarding a potential syndicate arrangement. In addition, the risk sharing arrangements between the NDF and Hannover Re have been adjusted to further leverage the NDF capital, with Hannover Re. providing a greater share of capacity (70:30) in a number of deals.
GP should continue to explore possible engagement with Lloyd’s of London and report to the NDF Advisory Council with updates.	Achieved - the GP team has been heavily committed (working in conjunction with experienced advisory teams from Guy Carpenter) to engagement with Lloyd’s of London and has reported on progress to the Advisory Council regularly.
Last year’s Annual Review recommended that GP should set out a business plan which considers capital deployment, KPIs, risk management and returns for the NDF. While the KPI component of this recommendation has been addressed separately in 2023 and elements of this plan were discussed in detail at the NDF Stakeholders’ Meeting in November 2023, the wider business plan itself has not yet been produced. This should now be treated as an urgent priority for this year, as well as an opportunity to chart the course of the NDF post-sale.	Partially achieved - The GP team worked with the NDF Advisory Council on the development of a strategic plan for the NDF for the period from 2024-2028. This plan was ultimately signed off by the NDF Advisory Council during the course of the NDF Advisory Council meetings that took place in October 2024. / As per the recommendation above, FCDO, KFW and GP should agree whether there remains a need for a standalone ‘business plan’ or whether the strategic plan is sufficient.
Two years of accounts for the NDF are now late. Delays caused through challenges in identifying and engaging suitably specialised auditors and reporting requirements have now been addressed. It will be important, therefore, for GP to now complete this process as a matter of urgency, particularly for the 2021 accounts. Once up-to-date, future accounts should be prepared and shared with FCDO in a timely manner.	Achieved - The NDF UK and NDF Deutschland financial statements for 2021, 2022 and 2023 have now all been finalised, approved and signed. The GP team is working with UK and German auditors on the audits in respect of the financial year ended 31 December 2024. GP now has two stable firms of auditors in respect of both funds and has recently taken steps to change the fund administrators thereby greatly facilitating and speeding up the financial management and reporting processes, meaning there are now systems and advisory teams in place in order to enable the annual audit processes in respect of any financial year to be undertaken within the first few months of the immediately following year.
Logframe indicators applying to Global Parametrics will need updating or removing this year, and the GP team should work with FCDO’s programme team to ensure the indicators reflect the new KPIs agreed this year and future priorities for the programme.	Achieved – GP and FCDO have reviewed and updated the logframe indicators removing indicators applying to GP, developing indicators reflecting the KPIs and creating a new output focussed on the NDF’s development impact.

Case Study 3

Land Bank Insurance in South Africa

South Africa is perennially exposed to drought risk, exacerbated by climate change and El Nino effects. Smallholder farmers are disproportionately affected due to low levels of resilience and financial reserves to withstand losses. Agriculture accounts for around a fifth of national employment in South Africa, with an estimated 250,000 smallholder famers, of which fewer than 1 % have access to insurance; and more than 1.2 million subsistence farmers with no access to insurance at all.

NDF Technical Assistance funding to the Land Bank Insurance Company (LBIC), a subsidiary of the government-owned Land and Agricultural Bank of South Africa, was provided earlier this year to develop two parametric drought-risk insurance products to protect both crop and livestock.

In South Africa, regulatory approval for such products is provided on a case-by-case basis. To date, no general parametric insurance has ever been permitted under the regulatory framework in place. In March 2024 the regulator invited all parties interested in submitting a case for regulatory approval for such products to come forward. LBIC based its submission on the technical advice that had been provided through the NDF, drawing heavily on this to explain the proposed project, quantify benefits and cite support. This material reportedly played an instrumental role in securing the subsequent wider approval that has now been granted as a result.

The NDF-backed drought products will now be an important element of the first wave of parametric products to be rolled out in South Africa, with the regulator allowing a two year window in which to prove concept. The product will be targeted to five provinces - Eastern Cape, Limpopo, North West, KwaZulu-Natal and Mpumalanga – where 75% of smallholder farmers are based.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A key recommendation in this year’s annual review is for the FCDO and GP to update the programme’s theory of change. The TOC has not been updated since the original business case was approved and the underlying assumptions (below) underpinning the TOC should be tested.

The existing Theory of Change for the programme states that the programme has 2 primary impact channels it is trying to achieve:

to build the resilience to natural disasters of the private sector in developing countries; and

to provide, and build the market for risk transfer/insurance products and to facilitate investment in areas and sectors subject to natural disaster risk

The Theory of Change states that the programme will achieve these impacts through the following outcomes:

Increasing the number of businesses with improved resilience whether directly through using a GP product, NDF capacity or through another market actor that has been crowded in.

Lowering the cost of capital for entities covered by financial disaster risk management products.

GP initiatives, products or transaction structures are replicated by others in the market indicating the viability and development of the risk transfer market in developing countries.

NDF pay-outs support clients and end beneficiaries to better cope with the effects of climate change and other geophysical shocks.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As outlined above, a thorough update to the programme Theory of Change will be conducted this year, including an assessment of the expected outcomes and impacts.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

There is a clear continued need for this programme in closing the crisis protection gap. Climate shocks are on the rise; extreme weather events have increased five-fold in the past 50 years. In the last decade alone, 1.7 billion people have been affected by sudden, extreme climate-related disasters. The way we provide finance for these disasters no longer meets the challenges we face today. Just 2% of finance is pre-arranged and in place before disasters hit despite many shocks being predictable and modellable. This approach smooths costs over time for donors and governments, ensures that plans are in place for disaster response, and most importantly gets money into affected peoples hands more quickly – which allows them to rebuild their lives more rapidly, saving money in the longer time.

The Natural Disaster Fund can play an important role in directly providing and facilitating greater volumes of pre-arranged financing in developing countries. It can play a catalytic role in growing the market and crowding-in third party capacity. The NDF can take greater risks, underwrite smaller and potentially less profitable but scalable transactions than most capacity providers in the market. It also builds market trust in such transactions, most notably by deploying Hannover Re capacity alongside the NDF. Through GP’s efforts in expanding the market, businesses and their customers, governments and their constituents, are receiving protection from natural disasters and extreme weather events, many for the first time.

This programme continues to be well aligned with the objectives of the FCDO, particularly in supporting sustainable development, responding to humanitarian needs, helping people and businesses adapt to the effects of climate change and mobilising private finance – a need that is expected only to increase in the years to come, particularly with climate-related shocks set to grow in both frequency and intensity.

## C. DETAILED OUTPUT SCORING

Output Title	Natural Disaster Fund (NDF) UK capital is preserved, fully utilised to underwrite risk and attracts additional risk capacity
Output number:		1	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	Revised Output Indicators

Indicator(s)	Milestone(s) for this review	Progress	Score
Minimum peak deployment of NDF capital	55%	84%	A+
Private capital deployed through/alongside/in conjunction with NDF capital	US$40m	59.6	A+
Annual number of risk capacity providers (of whatever nature and type e.g. insurers, reinsurers, ILS, investors etc) mobilised to participate in risks supported by, or otherwise catalysed by (i.e. including, without limitation, through the NDF TAF), the NDF and its activities	4	4	A
NDF overall P&L profitability in respect of each financial year	Loss of GBP£0.5m	Profit of US$769,000	A++

Briefly describe the output’s activities and provide supporting narrative for the score.

This output captures Global Parametrics management of the Natural Disaster Fund including the effective deployment of NDF capacity, how it is drawing in additional risk capacity and whether the UK’s capital is being preserved.

There has been very strong performance against this output this year. Three of the output indicators exceeded their targets while one achieved its target. This output is therefore assessed to have scored an A+ – exceeded expectations.
Output 1.1

Captures the deployment of NDF risk capacity. The target for this indicator aligns with the key performance indicator (KPI) agreed between Global Parametrics and the NDF Limited Partners to monitor NDF performance and determine the allocation of GP’s performance fee.

The target for this indicator was a peak deployment of NDF capital of 55%. The peak deployment achieved during the reporting period was 84%. This indicator is therefore assessed to have exceeded expectations.

The impressive performance against this indicator was underpinned by a high level of renewals of existing risk transfer contracts during the year. This strong foundation was built upon by the NDF underwriting a range of new risks including new transactions developed by the market (e.g. PCRIC Papua New Guinea Data Co, World Food Programme Sahel drought cover) and new transactions developed by the Global Parametrics team with the benefit of financial support from the NDF Technical Assistance Facility (TAF) (e.g. Mahila Housing Trust Extreme Heat and Tearfund Multi-country drought programme).

Output 1.2

Captures how the NDF is leveraging additional private capacity. This additional capacity is primarily provided by Hannover Re. Under the terms of a $50m mutual risk sharing agreement with the NDF, Hannover Re participates in transactions of all types provided they fall within the scope of the NDF business plan and satisfy the criteria as to agreed applicable pricing multiples. As such, it participates in the vast majority of NDF transactions.

This output and target aligns with the key performance indicator (KPI) agreed between Global Parametrics and the NDF Limited Partners to monitor how the NDF is leveraging additional capacity and helps determine the allocation of GP’s performance fee. Additional private capital deployed was $59.6 million against a target of $40m. This indicator is therefore assessed to have exceeded expectations. During 2024 (including renewals), Hannover Re participated in risks with an aggregate limit of more than US$56m, with further contributions made to the UNICEF Today/Tomorrow programme and the ARC Pandemic programme for Senegal where GP/NDF played the highly catalytic role in enabling both transactions to come to fruition.
Output 1.3

Captures the number of risk capacity providers mobilised to participate in risks supported by or otherwise catalysed by the NDF. This indicator attempts to demonstrate there is an increased number of providers spreading the risk year on year and the NDF is not overly reliant on a small number of private sector providers. The target for this indicator was 4 risk capacity providers and was achieved. Providers included: Hannover Re through the risk sharing arrangements with the NDF and the separate US$50m limit of delegated authority to the GP MGA; Canopius (Lloyd’s Syndicate 4444) through a US$35m limit introduction and underwriting services agreement/cover holder delegated authority to the GP MGA; a Ghanaian reinsurer to support the Farmerline-QIC drought programme that was developed with financial support from the NDF TAF and; Munich Re as co-reinsurer to the ARC Pandemic programme for Senegal enabled by the NDF’s catalytic participation.
Output 1.4

This output captures the NDF’s profitability, demonstrating whether the NDF is being professionally managed well and whether UK capital in the NDF is being preserved. Based on previous commercial performance, the target for this indicator had been set at a loss of not more than $500,000. NDF (UK) LP has achieved a profit of US$769,000 in 2024. This is the very first time that NDF (UK) LP has generated an annual profit and, as such, represents an important milestone for the fund.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

1. The programme logframe has been updated prior to this annual review. FCDO worked with Global Parametrics to adjust the logframe outputs with three principal aims:
  1. To update the indicators post GP sale to focus solely on the NDF
  2. To align with the NDF’s own KPIs to avoid parallel reporting processes;
  3. To make sure that the indicators were capturing the NDF’s core development impact.

One of the previous outputs related to Global Parametrics will no longer be assessed. There is now one output focussed on the sustainability and growth of the NDF, and one focussed on the development impact of the NDF.

Output one is the same but with new indicators, whereas output 2 is new, capturing the development impact of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Outlined in section A above.

Output Title	NDF (UK) LP’s impact in helping to close the protection gap in ODA eligible countries
Output number:		2	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	Revised Output

Indicator(s)	Milestone(s) for this review	Progress	Score
Number of poor and vulnerable beneficiaries	24m	36.4m	A+
Percentage of NDF UK risk exposure in low-income countries relative to the total risk exposure underwritten by NDF UK during the course of the relevant calendar year	6%	23%	A++
Number of risk transfer transactions underwritten by the NDF during the course of the relevant calendar year that either: (i) flow from CP Group’s own (i.e. typically not (re)insurance broker led) origination/subsequent renewal activities (including, without limitation, through the NDF TAF); or (ii) would not reasonably have come to fruition/reached the scale that they achieved without the participation of the NDF	4	11	A++

Briefly describe the output’s activities and provide supporting narrative for the score.

This is a new output measuring the development impact of the NDF. There has been strong performance against this indicator, reflecting the significant increase in impact the NDF has delivered over the past year. All three output indicators exceeded their targets this year. This output is therefore assessed to have exceeded expectations.
Output 2.1

This output indicator captures the number of poor and vulnerable beneficiaries benefitting from risk cover as a result of NDF capacity deployment. The target for this indicator aligns with the key performance indicator (KPI) agreed between Global Parametrics and the NDF Limited Partners to monitor NDF performance and determine the allocation of GP’s performance fee. The number of poor and vulnerable beneficiaries for 2024 has been determined applying the measurement methodology approved by the NDF Advisory Council for Development KPIs.

The target for this indicator was 24m. This was significantly exceeded, with over 36m poor and vulnerable beneficiaries supported.
Output 2.2

This output captures the percentage of overall risk exposure in low-income countries as a percentage of overall risk cover. It should be noted that the NDF can only operate in ODA-eligible countries. The majority of NDF capacity has been deployed in middle-income countries, which is unsurprising given these countries are likely to have more mature domestic insurance markets. The Limited Partners do not dictate where the NDF should operate (other than it must be in ODA-eligible countries) and understand that the NDF, similarly to many private insurance companies have limited opportunity to operate in the very poorest countries. However, one of the stated objectives of the NDF is to operate in underserved and challenging markets. It is positive therefore that the NDF has exceeded the target of 6%, deploying 23% of its capacity in low income countries.

While the NDF portfolio features a wide range of transactions that focus on risks in low income countries, they are primarily, for smaller pilot schemes which are growing. The exceptions to this are the WFP drought programme (which covers only low income countries) with an NDF total notional limit of US$12m and the UNICEF programme with an NDF total notional limit of US$10m. As such, these programmes have a significant impact upon the overall low income country allocation for the NDF when calculated by reference to notional limit.
Output 2.3

This output captures the number of transactions that are either ‘GP-originated’ i.e., those that flow from their own origination/subsequent renewal activities, especially through the NDF TAF, or those market transactions that would not reasonably have come to fruition/reached the scale that they achieved without the participation of the NDF.

As above, Limited Partners do not dictate the number of GP-originated transactions as they understand this will be commercially driven. However, both GP and Limited Partners recognise the significant value addition GP can bring to the market through the development of these products and are committed to continuing to develop and originate new products and business.

The target for this indicator was 4 transactions. This was exceeded with 11 transactions developed by GP, covering around 10 million beneficiaries. This indicator therefore significantly exceeded expectations. These were:
- One Acre Zambia drought/excess moisture programme
- One Acre Malawi drought/excess moisture programme
- One Acre Rwanda drought/excess moisture programme
- One Acre Nigeria drought/excess moisture programme
- VisionFund International Multi-Country multi peril programme
- Tearfund Multi-Country drought programme
- Corp EFF Dominica and Grenada TC programme
- WILMA tropical cyclone programme for SMEs in Mexico
- Mahila Housing Trust extreme urban heat programme for cities in Gujarat
- CLIMBS weather insurance protection for the Philippines

In addition, the UNICEF Today/Tomorrow programme and the ARC Pandemic programme for Senegal were catalysed by the support and participation of the NDF.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

As outlined above, the programme logframe has been substantially updated prior to this annual review. This is a new output that attempts to capture the NDF’s development impact.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Outlined in section A above.

## D: VALUE FOR MONEY

Key cost drivers and performance

Despite selling its shares in Global Parametrics, FCDO retains an interest in the company through a £6.4m loan provided to support the establishment of Global Parametrics. This is the first Annual Review not to cover Global Parametrics itself following the sale, although reporting still captures the handling of this ongoing debt, which is paid back according to the profitability of Global Parametrics and is, therefore, intrinsically linked to the success of the NDF. The £25m provided by FCDO as seed funding to the NDF constitutes CDEL and as such will also ultimately be returnable to FCDO.

The key cost driver for the programme relates primarily to pay-outs from the NDF reaching those most in need, when they need it. Within the programme, the only actual spend we have had in 2024 is the contract that’s in place with Forvis Mazars relating to the valuation of our investment in the NDF.

All contracting was carried out in adherence to FCDO standards and procedures. Financial management involved ensuring invoices only covered agreed work carried out to a satisfactory standard in line with the contract. Financial management involves scrutinising invoices and ensuring the outputs justify the number of days claimed by the partner.

The other ongoing cost consideration is management fees paid out to Global Parametrics from the NDF for administering the fund. These are not additional costs but are transferred out to GP from the NDF itself in part against pre-agreed indicators of management performance. Key Performance Indicators were agreed with GP in 2023 that directly link these management fees to the development impact that the NDF can demonstrate, including against an agreed indicator for poor and vulnerable beneficiaries protected.

VfM performance compared to the original VfM proposition in the business case

The VfM proposition outlined in the original business case holds, namely that “the catalytic nature of FCDO’s investment is expected to leverage other investors.” In 2024 the NDF deployed $59.6m in private capital through/alongside/in conjunction with NDF capital. During the course of 2024 (including renewals), Hannover Re participated in risks with an aggregate limit of more than US$56m, with further contributions made to the UNICEF Today/Tomorrow programme and the ARC Pandemic programme for Senegal Since the last Annual Review, the risk sharing arrangements between the NDF and Hannover Re have been adjusted to further leverage the NDF capital, with Hannover Re providing a greater share of capacity (70:30) in a number of deals.

Timely payouts continue to be made and remain important but are not the sole measure of success for all NDF transactions. Ultimately, the VfM position is dependent on pay-outs reaching those most in need, when they need it, in the context of disaster preparedness and response. The nature of insurance-type arrangements typically limits the extent to which GP can stipulate how pay-outs are used, particularly when it is part of a consortium, or several levels removed from the final payout recipient. Data on gender disaggregation of beneficiaries is similarly dependent on client analysis.
Assessment of whether the programme continues to represent value for money

The DRI programme should continue from a VfM assessment as the NDF is still providing a good return. In particular, this is the second consecutive year in which the fund has demonstrated incremental growth in cover and beneficiaries, with clear scope to continue on this trajectory into 2025 and beyond. We have also seen significant payouts to beneficiaries.

E: RISK

Overview of risk management

Overall risk rating: Moderate

A detailed risk register is reviewed and updated on a regular basis, and mitigating actions are identified and actioned where required. Risks are escalated to the Head of Department and Director and Director General when deemed necessary. FCDO’s programme team sought external legal advice and worked closely with KfW and Global Parametrics to ensure that the updated Limited Partners’ Agreement and related legal framework had the proper checks and balances in place to ensure continuing developmental impact for the programme post-sale, in line with the ambitions of the original business case. That included agreement of the new Key Performance Indicators linking payment of part of the management fees to impacts including number of poor and vulnerable beneficiaries receiving protection under the NDF.

The programme is no longer a higher-than-average risk for FCDO since the sale of its share in GP, and its overall risk rating has been reduced down to moderate. All risks are within Risk Appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The only programme cost this year was for the annual valuation of GP and NDF. A procurement process took place in December 2023 for a professional advisory through a Crown Commercial Service procurement framework. Forvis Mazars LLP won the tender as a specialist local accountants and business advisory group providing audit, payroll, corporate finance, tax and banking and finance services. It was contracted to provide valuations covering 2024 and 2025, with an option for a further valuation in 2026. The first valuation report was received in March 2024, with the second annual report due in March 2025.

The NDF UK and NDF Deutschland financial statements for 2021, 2022 and 2023 have been finalised, approved and signed. The GP team is working with the respective UK and German auditors on the audits in respect to financial year ending 31 December 2024. GP has two stable firms of auditors in respect of both funds and has recently appointed a new fund administrator. These changes should allow a more standardised approach to the annual audit process.

Asset monitoring and control:  FCDO’s financial investments in the NDF and Global Parametrics are represented on FCDO’s balance sheet. Professional advice has been provided on accounting treatment for these assets.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

FCDO oversight of the NDF sits at two levels: the Advisory Council, which is attended by the FCDO’s Senior Responsible Officer; and the Development Committee, which is covered by the FCDO’s Programme Responsible Officer, both alongside equivalent representation from KfW/BMZ.

The Advisory Council is a joint body responsible for the management and oversight of the NDFs by means of the NDF UK and NDF D Master Risk Participation Agreement (MRPA). The objective of the Advisory Council is to enable NDF UK and NDF D (which are established as legally distinct limited partnerships) to operate in conjunction with each other on a number of key decisions and areas of authority relating to the administration and governance of the NDF(s) - including appointments and removals of specific personnel, review of financial statements, elements of the NDF Business Plan etc. In 2023, the Advisory Council oversaw a ‘dry run’ process of reporting against the newly-developed Key Performance Indicators designed to inform performance related payments to GP and that came in to effect from 2024.

Monitoring on decisions around utilisation of NDF capital over the course of the year is predominantly through the ad hoc meetings of the Development Committee to consider new opportunities. This committee is tasked with ensuring that any new proposal is focused on ODA-eligible contexts and is able to demonstrate development impacts that are in line with the aims of the programme’s business case and make explicit the anticipated economic and social benefits of the proposed risk transfer transaction. That includes clear reporting against the additionality that any proposed transaction provides and details of the size and structure of the transaction, as well as quantifying the number of poor and vulnerable beneficiaries reached and covering off due diligence reporting. GP senior staff, including those directly involved with developing the proposed transaction, join the committee meeting to answer questions and provide additional detail as needed before the proposal is formally considered.

FCDO continues to engage in both committees in this capacity in 2024 and beyond. In order to ensure committees deliver against their respective aims as effectively as possible, Global Parametrics have ensured associated administrative processes are delivered as effectively and promptly as possible – including ensuring that meetings are scheduled with good notice, that relevant papers are provided well in advance to ensure time for review and reflection, and that minutes and actions are circulated and agreed promptly following meetings. The GP team worked with the NDF Advisory Council on the development of a strategic plan for the NDF for the period from 2024-2028. This plan was ultimately signed off by the NDF Advisory Council during the course of meetings that took place in October 2024.

This year saw the second publication of the Annual Impact Report covering the calendar year 2023. This document set out key highlights in numbers from the reporting year, outlined the organisation’s approach to impact and how this was measured, provided a number of case studies showing portfolio highlights for the NDF and also reported on partnership successes through the course of the year.

Given the NDF is often one step removed from the final beneficiary (as a reinsurer); it can be challenging to monitor impact at a granular level. GP should continue to explore ways, particularly in transactions it originates, to better capture impact for end beneficiaries.

As stated in last year’s Annual Review, reporting could also go further in not only setting out levels of protection in place, but also in actively following up on payouts to better understand how these were used, challenges and successes, and eventual impacts. These learnings could then be fed back into future transaction design and accountability. While a resource intensive process, and one that is at least partly dependent on willingness to engage from downstream partners, increased resource and dedicated capacity within GP should make this more feasible in future years.

Evidence

The way that NDF capital is utilised to provide risk capacity means that GP may often find itself several degrees removed from the ultimate beneficiary via structuring agents and other intermediaries as well as its actual client. This creates a level of challenge in tracking delivery through to final beneficiaries, capturing the impact of that delivery, and disaggregating data on the basis of age, sex, disability, geography and other relevant variables, but one that GP should continue to work to more clearly articulate.

A key indicator for calculating impact for the programme is determining the number of people who benefit from NDF risk transfer. To that end, after an extensive consultation process with partners and stakeholders, including engagement with KfW and FCDO, the InsuResilience Investment Fund (IIF) and participation in industry working groups within the InsuResilience Global Partnership (IGP), GP has a developed methodology for capturing and quantifying poor and vulnerable beneficiaries. This methodology calculates the total number of beneficiaries protected by risk transfer services for each transaction, with the number of poor and vulnerable beneficiaries determined as a subset of this. Poor beneficiaries are classified as those with income < $3.20 per day and vulnerable beneficiaries those with income >$3.20 and <$15.per day, in line with IGP methodologies.

Total beneficiary estimates are reached through partner and client calculations for their own individual beneficiaries, adding in a household multiplier where applicable to also capture indirect beneficiaries. Where information is limited or unavailable, pre-approved third-party sources for calculating these figures are used. Wherever possible, GP gathers disaggregated data from partners, particularly with regard to gender given the heightened risks and impacts of disasters on women and girls. It then monitors progress on beneficiary figures on a quarterly and annual basis and shares this information with stakeholders and partners. It protects against double counting in annual reporting by ensuring that any renewals within the annual period covered should only be included in cumulative reporting if either covering a different geography or representing an increase in scale in an existing geography, in which case the number of original beneficiaries is subtracted from any new projection.

This methodology is robust and has been tested with a wide range of partners. The NDF should continue to push with partners to capture both beneficiaries and impact, modelling good practice in its public reporting to normalise expectation of this level of detail, including helping to ensure that those who are ultimately benefitting from this risk transfer can better understand the level of protection they should expect to receive in the event of a shock.

Learning

The primary vehicle for learning within the programme is through the Technical Assistance Facility, which provides opportunities to test and pilot innovative risk transfer approaches in developing countries. The learning and evidence generated through the TAF has been used to expand and roll out transactions in other countries, for example through GP’s engagement with One Acre Fund which has now expanded to 4 African countries. There are also instances (e.g. Mahila Trust) where learning is being generated through external review.

Global Parametrics are well plugged into the wider market, with their location in Lloyds in London giving them a particular advantage in being co-located with some of the City’s largest firms and brokerages. GP also host a well-attended market event where they showcase the work of NDF to city stakeholders.

Date of last narrative financial report	21st February 2025 – NDF Quarterly Monitoring Report	Date of last audited annual statement	February 2025