## Annual Review

Title: Disaster Risk Insurance
Programme Value £38.9 million		Review date: March 2025
Programme Code: 203809	AMP start date: / November 2016	AMP end date: / December 2038

Summary of Programme Performance
Year	Dec 2016	Dec 2017	Dec 2018	Dec 2019	Dec 2020	Dec 2021	Mar 2023	Mar 2024	Mar 2025	Mar 2026
Overall Output Score	B	B	A	A	A	B	A	A	A+	A+
Risk Rating	Severe	Major	Major	Major	Major	Major	Major	Major	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/45411632.odt
DevTracker Link to results framework:	TBC – in process of publication

A. SUMMARY AND OVERVIEW

Description of programme

Natural hazards and climate-related disasters - including sudden-onset shocks such as earthquakes, extreme rainfall and tropical storms as well as slower-onset events such as droughts and extreme heat - are among the key risks faced by the private sector in developing countries, placing a disruptive burden on the economies of ODA-eligible countries[1].
[1] World Economic Forum Global Risks Report 2019 http://www3.weforum.org/docs/WEF_Global_Risks_Report_2019.pdf

Insurance can provide much-needed, predictable finance in the wake of a shock, helping to mitigate impacts, ensure business continuity and contingency planning and play a critical role in accelerating recovery. University of Cambridge researchers found that a 1% increase in insurance penetration can cut disaster recovery times by a year. However, most disaster risks in developing countries are under-insured and typically levels of insurance are lowest where vulnerability is greatest.

1. The Disaster Risk Insurance programme (DRI) develops and underwrites risk insurance and reinsurance products designed to help businesses and other organisations in ODA eligible countries build resilience to disaster risks. Established in 2017, the programme initially had two core components:
  1. The Natural Disaster Fund (NDF), for which the FCDO provided £25m returnable seed funding in 2018. The NDF underwrites parametric insurance contracts, which payout a specific amount when pre-agreed thresholds are met (e.g. rainfall volume, wind-speed). This contrasts traditional indemnity insurance, which relates to the actual damage caused and therefore takes longer to pay.
  2. Global Parametrics Ltd (GP), a private reinsurance company, was set up to design and distribute the insurance contracts and currently manages the NDF.

On 6 September 2023, the UK (FCDO) and Germany (BMZ/KfW) sold their shares in Global Parametrics to CelsiusPro AG, which became the sole shareholder. GP began repaying the £6.4m in returnable debt in 2025,several years ahead of schedule, as the loan was originally due to be repaid between 2028 and 2034. The UK (£25m) and German (EUR 34m) capital committed to the NDF remains in place until the programme end-date when it can be returned to FCDO.

Pre-sale Annual Reviews evaluated the programme’s performance by monitoring progress of GP as well as the NDF. However, in line with the changes made to the Logframe post-sale, this document reviews the performance of the NDF only.

Summary supporting narrative for the overall score in this review

Score: A+

The programme has delivered another very strong year with performance against both outputs exceeding expectations, with a significant scale up the in volume of the financial resources deployed through the NDF and the number of poor and vulnerable beneficiaries protected. The programme is assessed therefore to have scored an A+: ‘outputs exceeded expectations’.

In 2020 HannoverRe engaged in a risk sharing agreement with the NDF by committing $50m to be leveraged by the NDF which enabled a 50/50 burden share of all transactions. This effectively doubled the volume of insurance that could be offered through the NDF. In June 2025, further progress has been made with Hannover Re doubling that commitment to US$100m, enabling an enhanced 70:30 risk‑sharing structure, which now means that for every $3 risk that the NDF underwrites, Hannover Re underwrite $7.

Pipeline development has been especially strong, with the NDF Annual Stakeholder Meetings highlighting a 24% year‑on‑year increase in transaction opportunities and substantial scaling of both homegrown and open‑market prospects. The Technical Assistance Facility (TAF) has played a critical role within this, supporting origination of 10 new projects this year.

Operationally, the NDF has grown in visibility and credibility. GP ensured the NDF was prominent at key industry and development sector events including the 2025 Parametric Insurer Conference and London Climate Action Week, helping raise awareness of its work and strengthening its standing with partners across the growing sector.

Plans are in place to expand the NDF’s impact further, with active engagements underway with at least one major commercial reinsurer, alongside other public and private institutions.
.
Case Study 1: Increasing the NDF’s impact through innovation

Frontier Markets - Scaling Gender-Sensitive Climate Insurance Solutions in India

This case study illustrates how NDF support is enabling product‑level innovation tailored to underserved groups—showcasing how gender‑sensitive parametric insurance can deliver early and tangible impact for poor and vulnerable women farmers.

Women smallholder farmers in climate‑vulnerable communities face acute climate‑related risks yet remain significantly underinsured due to affordability, land‑tenure barriers and limited access to financial services. In 2025, Frontier Markets and Global Parametrics launched the She Leads Bharat Mahila Kisaan Initiative with support from the NDF TAF. The initiative developed a gender‑sensitive parametric crop insurance product tailored to women farmers.

Surveys of more than 5,000 women during the pilot confirmed the scale of risk: 97% had experienced a major drought in the past decade. Coping strategies underscored the fragility of existing safety nets—32% relied on savings, 25% turned to NGOs or government support, and 12% reduced household meals. The new parametric product provides faster, more predictable support, helping safeguard savings, improve food security, and reduce dependence on external assistance.

By November 2025, 10,000 women farmers were registered and enrolled into the insurance scheme, providing protection to 46,000 people across four districts in Rajasthan and Uttar Pradesh, covering 3,568 acres and more than 480 villages. With NDF‑backed risk capacity, the project transitioned from a TAF‑funded pilot to a fully-fledged transaction within a year. A payout was triggered in 14 locations due to excess moisture in November 2025, demonstrating tangible early impact and the potential for expansion to additional states.

Major lessons and recommendations for the year ahead

Major lessons from the past year

The programme context has evolved and the NDF is now operating at a larger scale and working with a wider group of partners than envisaged when its legal and regulatory structure was designed. These changes have highlighted limitations in the current structure, which may constrain the NDF’s ability to scale funding and deploy risk as efficiently as required.

Grant funding to cover structuring costs can be a necessary catalyst to the development and implementation of high impact risk transfer programmes. A significant portion of the high-impact programmes which are developed and/or supported by the NDF require grant funding to cover their structuring, establishment and implementation costs. This improves affordability for beneficiaries and enables them to build familiarity with the insurance products. The NDF Technical Assistance Fund (NDF TAF) plays a crucial role in providing catalytic grant funding to develop a pipeline of high-impact risk transfer transactions.

Premium finance has played an important role in making early-stage or pilot schemes affordable for poor and vulnerable groups, however, the DRF system must now adapt to reduce reliance on ODA grants over time. In this context the NDF’s emphasis on sustainability and catalytic impact becomes ever more salient.

Continued importance of promoting and publicising the NDF, its activities and its impact. Increasing the awareness of the NDF’s activities and impact is key to scaling its risk capacity and pipeline of transactions and TAF opportunities. During 2025, NDF participated in promotional events including a high-profile event as part of the 2025 London Climate Action Week. Effectively showcasing the work of the NDF will continue to be important in order to ensure the whole sector is aware of the possibilities for mutually beneficial partnerships with the NDF.

Case Study 2: Pan-Caribbean & Central American Microinsurance Facility for The Caribbean
Catastrophe Risk Insurance Facility (CCRIF)

This case study highlights the that through partnering with the Caribbean Catastrophe Risk Insurance Facility (CCRIF), NDF has been able to influence the DRF architecture needed for scalable, multi‑country expansion of microinsurance for vulnerable households.

The Caribbean and Central America face frequent and severe climate‑related hazards—tropical storms, heavy rainfall, earthquakes, droughts, and secondary risks—that disproportionately affect low‑income and vulnerable populations. Limited access to affordable insurance leaves many exposed to financial shocks, reinforcing cycles of poverty and underscoring the need for accessible microinsurance solutions.

In June 2025, during London Climate Action Week, CCRIF—working with Global Parametrics and CelsiusPro and supported by an NDF TAF grant—launched the Pan‑Caribbean & Central American Microinsurance Facility. The initiative aims to expand access to microinsurance through a new digital administrative platform that allows multiple insurers to distribute products efficiently across the region.

The Facility’s first product, the Livelihood Protection Policy (LPP), is a parametric weather index insurance offering rapid payouts for tropical storm winds, hurricanes, and heavy rainfall. It is designed to strengthen resilience for vulnerable groups including smallholder farmers, fishers, market and food vendors, day labourers, construction and tourism workers, and micro‑business owners. Initial rollout in Belize, Grenada, Jamaica, Saint Lucia, and Trinidad & Tobago targets 33,500 policyholders in the first year.

Throughout 2025, the consortium established the foundations for scale—onboarding and training a regional insurer, developing the platform, and setting up the necessary legal arrangements for NDF risk capacity. Training, marketing, and sales activities planned for early 2026 will support continued expansion, with CCRIF aiming to grow distribution to additional countries and insurers over time.

Recommendations for the year ahead

Global Parametrics should continue to explore opportunities to significantly increase the volume of private capital leveraged alongside the NDF. Hannover Re’s increased risk-sharing demonstrates strong progress in this space, but more risk capacity will be required to be mobilised to ensure the NDF’s impact continues to grow.

Global Parametrics and the FCDO should review the legal and regulatory structure of the NDF to improve its ability to scale its risk deployment activities, with FCDO seeking external and independent advice to support this review.

An updated Theory of Change (ToC) and Logframe should be developed by Summer 2026, reflecting changes in the programme. A clear plan will be needed to sequence the ToC/Logframe updates alongside any changes to programme structure. Updates should consider how the market has changed since the business case was first written and should thus reflect the additionality that the NDF is able to offer within this current context.

Global Parametrics should work with FCDO to develop strategic partnerships to maximise reach and embed the NDF within the global Climate and Disaster Risk Finance and Insurance (CDRFI) landscape, specifically through building closer relationships with regional risk pools and MDBs. In the short to medium term GP should work with FCDO to amplify the reach of the current capital base through engagement with the wider international insurance industry to explore opportunities for crowding-in further risk sharing capacity. Risk pools and MDBs represent a key area for further growth with access to and affordability of reinsurance representing a key constraint to expansion of these organisations’ activities.
Progress against recommendations in last year’s annual review

Recommendation	Progress
Global Parametrics should continue to finalise ongoing efforts to significantly increase the volume of private capital leveraged alongside the NDF.	Achieved – This has been a key focus of the GP team and progress has been regularly reported through NDF Advisory Council meetings. / Key achievements include enhanced leverage of NDF capital through the existing Hannover Re/Kaith Re reinsurance fronting arrangements and, approved Lloyd’s coverholder status enabling Global Parametrics to deploy risk capacity on behalf of third-party Lloyd’s syndicates. / Progress has been made in risk sharing discussions with potential new private sector risk capacity providers to sit alongside the risk sharing arrangements with Hannover Re.
Global Parametrics should continue to explore ways to demonstrate and monitor its impact, particularly for poor and vulnerable beneficiaries.	Achieved –Global Parametrics has worked with the NDF Advisory Council to determine an appropriate methodology for application in the context of “macro-level” risk transfer covers with a particular focus on critical infrastructure. / GP are working more closely with downstream technical assistance and consulting partners to gather detailed information related to NDF payout usage and effectiveness. The information gathered is supporting product and policy refinement processes to enable greater impact and scale of future renewals.
Global Parametrics and the FCDO should develop an updated theory of change by December 2025 for the NDF, reflecting changes in GP’s operating model.	Not achieved – Update to the ToC was delayed and will be prioritised in 2026. As such, this remains a firm objective for both Global Parametrics and for FCDO
FCDO should continue to ensure that the core mandate of the NDF to help poor and vulnerable people from low- and middle-income mitigate the impact of extreme weather and climate related shocks is maintained regardless of any change in structure.	Achieved – The NDF has maintained its core development mandate, with the Development Committee continuing to review all NDF transactions and TAF grants for developmental impact and additionality. Oversight has been strengthened by FCDO’s recruitment of a G7 economist as PRO, providing dedicated capacity on mandate delivery. / Strategic direction also remains robust, with the NDF Advisory Council meeting regularly throughout the year, including the two‑day annual Stakeholders’ Meeting bringing together all key partners to review progress and risks. Senior representatives from FCDO, KfW and Hannover Re also contributed to a panel during London Climate Action Week, further reinforcing programme alignment and visibility.
FCDO, KFW and GP should agree whether there remains a need for a standalone ‘business plan’ or whether the strategic plan developed through the AC is sufficient.	Achieved – Global Parametrics and FCDO agree that there is no need for a comprehensive rewrite of the business plan as the multi‑year Strategic Plan developed with the NDF Advisory Council in 2024/25 now fulfils the purpose of the earlier recommendation, provided it continues to set out clear priorities for capital deployment, risk management, development impact and operational objectives. / GP will outline key strategic objectives annually to ensure the plan remains up‑to‑date and aligned with programme needs.

Case Study 3

World Food Programme Iraq – Drought Index Insurance Transaction

This case study illustrates how NDF risk capacity can make climate‑risk insurance commercially viable even in fragile, hard‑to‑insure markets by enabling the expansion of a drought product that commercial reinsurers had limited appetite to underwrite.

Iraq, one of 21 countries in the World Food Programme’s (WFP) Inclusive Risk Financing portfolio (an initiative aimed at increasing food-system resilience), faces severe climate risks—including drought, heatwaves and irregular rainfall—that significantly undermine agricultural production. With 23% of the population reliant on agriculture, increasing drought frequency poses a major threat to food security, particularly for smallholders dependent on early‑ and mid‑season rainfall.

WFP’s approach integrates cash-based transfers and digital financial services to promote financial inclusion, especially for women and youth, while supporting climate adaptation and sustainable agricultural practices. These efforts are closely coordinated with government ministries, UN agencies, and local partners to ensure broad reach and lasting impact.

Launched in 2023, the WFP’s drought insurance pilot initially covered 400 farmers across five districts. Strong demand in year two expanded coverage to 821 farmers. Facing challenges sourcing reinsurers to deploy risk capacity within the country context, WFP sought additional risk capacity from the NDF. In December 2025, an NDF-backed transaction deployed USD 415,000 in parametric drought reinsurance—supporting an underserved, fragile context where reinsurer appetite is limited.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A key recommendation in this year’s annual review is for the FCDO and GP to update the programme’s theory of change. The ToC has not been updated since the original business case was approved and the underlying assumptions (below) underpinning the ToC should be tested.

The existing ToC sets out two channels through which the programme delivers impact:

to build the resilience to natural disasters of the private sector in developing countries; and

to provide, and build the market for risk transfer/insurance products and to facilitate investment in areas and sectors subject to natural disaster risk

The ToC states the programme will achieve these impacts through the following outcomes:

Increasing the number of businesses with improved resilience whether directly through using a GP product, NDF capacity or through another market actor that has been crowded in.

Lowering the cost of capital for entities covered by financial disaster risk management products.

GP initiatives, products or transaction structures are replicated by others in the market indicating the viability and development of the risk transfer market in developing countries.

NDF pay-outs support clients and end beneficiaries to better cope with the effects of climate change and other geophysical shocks.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As outlined above, a thorough update to the programme Theory of Change will be conducted this year, including an assessment of the expected outcomes and impacts.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

There remains a strong need for this programme to help to close the climate protection gap and support the UK’s Global Financial Reform agenda aim of raising Pre-Arranged Finance (PAF) from 2% of global crisis financing towards 20% by 2035. With extreme weather events increasing five‑fold over the last 50 years and 1.7 billion people affected by climate‑related disasters in the past decade, traditional, reactive disaster‑response financing is no longer sufficient. PAF enables faster, more efficient, and more predictable support to affected people, reduces fiscal volatility for governments, and ensures preparedness before shocks occur.

The NDF is playing an increasingly important role in facilitating pre-arranged financing in developing countries. It has already crowded in much larger volumes of private capital than the FCDO’s initial investment via its partnership with Hannover Re and should continue to do so given emerging interest from other big insurers. The NDF underwrites risks and transaction sizes that commercial actors tend to under-invest in due to the uncertain returns involved in originating innovative products. Furthermore, by demonstrating that these innovative products are scalable and replicable the NDF builds market interest and confidence in deploying their capacity towards these risks.

The programme remains well aligned with FCDO priorities: supporting sustainable development, strengthening humanitarian response, enabling adaptation to climate impacts, and mobilising private finance. Given the projected increase in climate‑related shocks, the need for this programme will continue to grow, reinforcing its value within the wider portfolio.

## C. DETAILED OUTPUT SCORING

Output Title	Natural Disaster Fund (NDF) UK capital is preserved, fully utilised to underwrite risk and attracts additional risk capacity
Output number:		1	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Score
Minimum peak deployment of NDF capital	65%	74%	A+
Private capital deployed through/alongside/in conjunction with NDF capital	US$60m	US$78.3m	A+
Annual number of risk capacity providers (of whatever nature and type e.g. insurers, reinsurers, ILS, investors etc) mobilised to participate in risks supported by, or otherwise catalysed by (i.e. including, without limitation, through the NDF TAF), the NDF and its activities	6	8	A
NDF overall P&L profitability in respect of each financial year	Break-even	US$2m profit	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

This output captures Global Parametrics’ management of the NDF including the effective deployment of NDF capacity, how it is drawing in additional risk capacity and whether the UK’s capital is being preserved.

There has been strong performance against this output this year. Three of the output indicators exceeded their targets while one achieved its target. This output is therefore assessed to have scored an A+ exceeded expectations.
Output 1.1

Captures the deployment of NDF risk capacity. Progress was 74% for the indicator for peak deployment of NDF capital against the target of 65%. Strong performance was underpinned by a high renewal percentage of the previous year's business alongside entry into a number of new risks and transactions during 2025. GP have also sought to increase the proportion of risk assumed by the NDF for certain renewal transactions. The adjustment to the risk‑sharing ratio between Hannover Re and the NDF meant that the NDF could take on larger amounts of risk, allowing it to underwrite more total business and still meeting the percentage deployment target.

Although both capacity and deployment increased this year, the percentage of capacity deployed fell by 10 points compared to last year (from 84% to 74%). This is a feature of using percentage targets: even if both are growing, performance can appear weaker when leverage grows faster than deployment. When revisiting the Logframe, it may therefore be worth adopting a raw‑value deployment target—either alongside, or instead of, a percentage measure—to give a clearer view of performance.
Output 1.2

Captures how the NDF is leveraging additional private capital. This additional capacity is primarily provided by Hannover Re via the risk-sharing arrangement. Hannover Re participates in transactions of all types provided they fall within the scope of the NDF business plan and satisfy the criteria as to agreed applicable pricing multiples.

Additional private capital deployed was $78.3 million against a target of $60m, with $45m of that deployed by Hannover Re. This indicator is therefore assessed to have exceeded expectations.
Output 1.3

Captures the number of risk capacity providers mobilised to participate in risks supported by the NDF. This indicator attempts to demonstrate there is an increased number of providers spreading the risk year on year and the NDF is not overly reliant on a small number of private sector providers.

The target for this indicator was 6 risk capacity providers and that has been exceeded with 8 participants mobilised. Providers included Hannover Re alongside Lloyd’s Syndicates such as Canopius; The National Reinsurance Corporation of the Philippines; and local reinsurer in Ghana who provided the capacity for a TAF-generated transaction.

Output 1.4

This output captures the NDF’s commercial viability, demonstrating whether the NDF is being professionally managed well and whether UK capital in the NDF is being preserved. Based on previous commercial performance, the target for this indicator had been set at a Break-Even level and this was surpassed with an estimated profit (subject to audit) of US$2m in 2025. This is the second year that NDF (UK) LP has generated an annual profit.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output in 2025. The changes made post-sale for the review of 2024 have been retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Outlined in section A above.

Output Title	NDF (UK) LP’s impact in helping to close the protection gap in ODA eligible countries
Output number:		2	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Score
Number of poor and vulnerable beneficiaries	33m	34.3m	A
Percentage of NDF UK risk exposure in low-income countries relative to the total risk exposure underwritten by NDF UK during the course of the relevant calendar year	7%	29.7%	A+
Number of risk transfer transactions underwritten by the NDF during the course of the relevant calendar year that either: (i) flow from CP Group’s own (i.e. typically not (re)insurance broker led) origination/subsequent renewal activities (including, without limitation, through the NDF TAF); or (ii) would not reasonably have come to fruition/reached the scale that they achieved without the participation of the NDF	5	14	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

There has been strong performance against this indicator, reflecting the significant increase in impact the NDF has delivered over the past year. All three output indicators exceeded their targets and the output, therefore, is assessed to have exceeded expectations.
Output 2.1

This output indicator captures the number of poor and vulnerable beneficiaries benefitting from risk cover as a result of NDF capacity deployment. The target for this indicator aligns with the KPI agreed between Global Parametrics and the NDF Limited Partners to monitor NDF performance and determine the allocation of GP’s performance fee. The number of poor and vulnerable beneficiaries for 2025 has been determined applying the measurement methodology approved by the NDF Advisory Council for Development KPIs.

The target for this indicator was 33m. This was just exceeded, with over 34.3m poor and vulnerable beneficiaries supported.
Output 2.2

1. This output captures the percentage of overall risk exposure in low-income countries as a percentage of overall risk cover.
2. The NDF exceeded its 7% target by deploying nearly 30% of its risk capacity in low‑income countries. This rise, around six percentage points higher than last year, is driven not by the many small LIC pilot transactions, which together make up only a small share of total exposure, but by a few high‑value deals. Most of the 30% comes from a few transactions, including WFP Africa (US$13.3m), UNICEF (US$10m) and ARC Umbrella (US$3.2m).
Output 2.3

This output measures the number of transactions that are either ‘GP-originated’ i.e., those that flow from their own origination/subsequent renewal activities, especially through the NDF TAF, or those market transactions that would not reasonably have come to fruition/reached the scale that they achieved without the participation of the NDF.

Whilst Limited Partners do not dictate the number of GP-originated transactions as they understand this will be commercially driven, both GP and LPs recognise the significant value GP can bring to the market through the development of these products.

The target for this indicator was 5 transactions. This was exceeded with 14 transactions developed by GP, up from 11 last year. The TAF has been responsible for 10 of these 14 transactions, covering 2.6m beneficiaries. In total, homegrown transactions comprise 12% of the portfolio’s capacity (and 26% by count).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As outlined above, Logframe has not been changed since last year’s update.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Outlined in section A above

D: Value for Money

Key cost drivers and performance

Since the sale of GP, the main fixed programme cost for FCDO is the £25m non-fiscal CDEL provided in 2018 as seed funding to the NDF. However, this will ultimately be returnable to FCDO and so from a value for money perspective, if capital is preserved, programme benefits will be the primary driver of VfM.

The key risks to the NDFs £25m capital base relate is high payouts in the wake of disasters. However, these payouts also represent the value of the programme when they reach those most in need, when they need them. Given the NDF has achieved two consecutive years of profit, this indicates the portfolio is well-diversified and so payouts are cost-efficient. We are awaiting final statements for 2025 but as of December 2024 the NDF capital stood at approximately £21m. Assuming continued annual profits, the capital should be expected to be replenished to the full £25m within a number of years after which any excess profits are allocated as junior interests.

The only programme expenditure in 2025 was the contract that’s in place for the valuation of FCDOs investment in the NDF. All procurement followed FCDO standards, and financial management and invoices reflected agreed, satisfactorily delivered work.

The other cost consideration is the management fees paid to Global Parametrics for administering the NDF. These are not additional programme costs but are drawn from the NDF itself and tied to pre‑agreed performance indicators, including development impact metrics such as the number of poor and vulnerable beneficiaries protected.

VfM performance compared to the original VfM proposition in the business case

The VfM proposition outlined in the original business case holds, namely that “the catalytic nature of FCDO’s investment is expected to leverage other investors.” The NDF deployed $78.3m in private capital in conjunction with NDF capital. In June 2025, Hannover Re doubled their financial commitment to the NDF and their on-risk capital with NDF transactions totalled $53.4m by the end of the year. Hannover Re, among other prospective partners, have cited the value of innovation and origination within emerging markets as a key driver of their interest in the NDF. Thus, FCDO’s decision to replenish the TAF should be a key driver in 2026 of added value for money due to its capacity to transfer small-scale funding into new and scalable products.

Timely payouts continue to be made and remain important but are not the sole measure of success for all NDF transactions. Ultimately, the VfM position is dependent on pay-outs reaching those most in need, when they need it, in the context of disaster preparedness and response. The nature of insurance-type arrangements typically limits the extent to which GP can stipulate how pay-outs are used, particularly when it is part of a consortium, or several levels removed from the final payout recipient. Data on gender disaggregation of beneficiaries is similarly dependent on client analysis.
Assessment of whether the programme continues to represent value for money

The DRI programme still provides good value for money, with public investment continuing to crowd-in private capital and 34.3m beneficiaries benefitting from the programme without the FCDO’s initial investment having diminished. This is the third consecutive year in which the fund has demonstrated incremental growth in cover and beneficiaries, with clear scope to continue on this trajectory into 2026 and beyond. We have also seen timely payouts to beneficiaries reaching a total of US$14.9m, including US$450k to Malawi and Pakistan as part of the TAF-supported Tearfund transaction as well as $1.5m to One Acre Fund in Malawi, Zambia and Nigeria which is also a former-TAF project.

E: RISK

Overview of risk management

Overall risk rating: Moderate

A detailed risk register is reviewed and updated on a regular basis, and mitigating actions are identified and actioned where required. Risks are escalated to the Head of Department and Director and Director General when deemed necessary. FCDO’s programme team sought external legal advice and worked closely with KfW and Global Parametrics to ensure that the updated Limited Partners’ Agreement and related legal framework had the proper checks and balances in place to ensure continuing developmental impact for the programme post-sale, in line with the ambitions of the original business case. That included agreement of the new Key Performance Indicators linking payment of part of the management fees to impacts including number of poor and vulnerable beneficiaries receiving protection under the NDF.

One noteworthy risk that has become apparent is the risk that a decline in ODA volumes globally, reduces the amount spent on types of insurance provided through the NDF. Given the reliance of many low‑income consumers of insurance on premium finance, there is a risk that the reduction of these funding flows weaken the wider DRF architecture, creating a near‑term vulnerability to the system. Whilst this risk sits at the system level, the NDF programme is assessed to be relatively resilient to such reductions due to its diverse portfolio and independent pipeline for generating business. Investments in the TAF should partially mitigate these effects by more sustainably targeting the demand‑side constraints that subsidies are designed to overcome.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The only programme cost this year was for the annual valuation of GP and NDF. Following competitive procurement process in December 2023, Forvis Mazars LLP were contracted to provide valuations covering 2024 and 2025, with an option for a further valuation in 2026. Earlier this year we took up that option to extend and the last valuation report is due by April 2026.

The NDF UK and NDF Deutschland financial statements for 2024 were finalised, approved and signed off late 2025.

Asset monitoring and control:  FCDO’s financial investments in the NDF and Global Parametrics are represented on FCDO’s balance sheet. Professional advice has been provided on accounting treatment for these assets.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

FCDO oversight of the NDF sits at two levels: the Advisory Council, which is attended by the FCDO’s Senior Responsible Officer; and the Development Committee, which is covered by the FCDO’s Programme Responsible Officer, both alongside equivalent representation from KfW/BMZ. The FCDO continues to participate actively in both committees.

The Advisory Council is a joint body responsible for the management and oversight of the NDF UK and NDF De via the Master Risk Participation Agreement (MRPA), enabling both legally distinct limited partnerships to coordinate on key governance decisions, including personnel appointments, financial statement review, and elements of the NDF Business Plan. Performance‑related KPIs for GP came into effect in 2024.

The Development Committee meets as needed to review proposals for the use of NDF capital, ensuring each opportunity is ODA‑eligible and aligns with the aims set out in the programme’s business case. Projects must demonstrate clear development impact, additionality, transaction structure, and projected beneficiary reach. GP staff involved in developing each proposal attend meetings to provide detail and respond to queries.

This year saw the third publication of the Annual Impact Report covering the calendar year 2024. This document set out key highlights in numbers from the reporting year, outlined the organisation’s approach to impact and how this was measured, provided a number of case studies showing portfolio highlights for the NDF and also reported on partnership successes through the course of the year.

Evidence

Because NDF capital is deployed through multiple intermediaries, GP is often several steps removed from final beneficiaries. This makes it challenging to track delivery, assess impact, and obtain disaggregated data (age, sex, disability, geography). GP should continue strengthening how it communicates these limitations and its approach to addressing them. However, this is a challenge that GP should continue to work to more clearly articulate.

A core impact metric is the number of people benefiting from NDF‑supported risk transfer. Following extensive consultation with partners GP has developed a methodology to quantify poor and vulnerable beneficiaries. Beneficiaries are classified using InsuResilience Global Partnerships (IGP) thresholds: poor (< $3.20/day) and vulnerable (>$3.20–<$15/day).

Beneficiary estimates are based on partner‑reported figures but, where data is limited, approved third‑party sources can be used. GP collects disaggregated data when possible—particularly gender data given the heightened climate‑related risks for women and girls. Figures are monitored quarterly and annually, with safeguards to prevent double counting by excluding simple renewals unless scale or geography expands.

In 2025, supported by technical scrutiny from the Advisory Council, GP developed an update to this beneficiaries methodology which includes four calculation methodologies including a methodology for calculating the beneficiaries of critical infrastructure insurance. This extends the NDF’s beneficiary monitoring toolkit through offering a more robust appraisal across a variety of different coverage types.

Learning

The primary vehicle for learning within the programme is through the Technical Assistance Facility, which provides opportunities to test and pilot innovative risk transfer approaches in developing countries. The learning and evidence generated through the TAF has been used to expand and roll out transactions in other countries, for example through GP’s engagement with One Acre Fund which has now expanded to 4 African countries. There are also instances (e.g. Mahila Trust) where learning is being generated through external review.

Global Parametrics are well plugged into the wider market, with their location in Lloyds in London giving them a particular advantage in being co-located with some of the City’s largest firms and brokerages. GP also host a well-attended market event where they showcase the work of NDF to city stakeholders.

Date of last narrative financial report	February 2026 – NDF Quarterly Monitoring Report for Q4	Date of last audited annual statement	November 2024