 Programme Completion Review

Title: Better Health in Bangladesh (BHB) Programme
Final Programme Spend £ (full life): £65.58m	Review Date:	April – June 2025
Programme Code: 203864	Start Date: April 2018	End Date: March 2025

Summary of Programme Performance

Year	2019	2020	2021	2022	2023	2024	2025
Programme Score	A+	A	A	A+	A	A+	A+
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-1-203864/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-1-203864/documents

A. Summary and Overview

Description of the programme and what it has achieved
1. Better Health in Bangladesh (BHB) aimed to improve health outcomes for the people of Bangladesh, especially women, children, and the poor, by strengthening health systems and supporting quality improvements. BHB supported the Government of Bangladesh’s (GoB’s) 4th Health, Population and Nutrition Sector Programme (HPNSP, 2017-2024) by providing Financial Assistance (FA) through a Multi-Donor Trust Fund (MDTF), and through Technical Assistance (TA). The implementing partners of this programme were United Nations Population Fund (UNFPA), World Health Organization (WHO), Management Sciences for Health (MSH), icddr,b, DAI and their downstream partners.
2. BHB focused on improving the quality of maternal and infant care; sexual and reproductive health and rights (SRHR); climate change resilience; and governance and stewardship of medicine sales. Among other successes, BHB has proven the potential for midwife-led care in Bangladesh - an independent modelling study by Johns Hopkins University estimated that midwives deployed in eight BHB districts saved over 1,000 maternal and neonatal lives from 2019 to 2023, with the potential to save between 12,000 and 31,000 lives during from 2024 to 2030 if midwifery-led care is expanded across Bangladesh.
3. BHB adapted to significant changes over the course of delivery. The overall budget of the programme was reduced from £88m to £65.58m due to reductions in Overseas Development Assistance (ODA). As a result, direct FA to support the 4th HPNSP ended earlier than planned and was reduced from £44m to £27.6m. Total TA funding was reduced from a planned £43m to £37.4m, with £12.2m of TA reprioritised to the COVID-19 response. Finally, BHB was extended for two years to allow a responsible exit from bilateral health programming. Some of the logframe targets were revised during the amendments because of changes in the budget and reprioritisation of funds to respond to COVID-19.
4. BHB was one of the UK government’s key instruments in responding to the COVID-19 pandemic in Bangladesh. It directly supported the national response by providing testing kits, personal protective equipment (PPE), and logistics for vaccine rollout. It also contributed to health system strengthening by deploying additional midwives to maintain essential services and improving WASH facilities. Subsequently, BHB-funded Sexual and Reproductive Health and Rights (SRHR) Officers supervised the return of health service delivery to pre-pandemic levels. BHB also responded to other national emergencies, including cyclones, floods and supporting UK Emergency Medical Team (EMT) to treat the students injured during the July 2024 movement.
5. The COVID-19 pandemic, and the challenges of addressing it, had slowed down the pace of implementation of the programme. However, during COVID-19 the programme continued to keep its focus on its core objectives including SRHR and health systems strengthening. Prioritisation of key areas helped prevent further scaling back of programme activities on these areas. When the pandemic ended the programme refocused on its regular activities and was able to deliver the expected results.
6. The 4th HPNSP ended in June 2024. The GoB worked on the design of the subsequent 5th sector programme in collaboration with development partners (DPs), including FCDO. However, the new sector programme did not start in July 2024 as planned, partly because of political unrest and the fall of the previous GoB in August 2024. The Interim Government (IG) has decided to move away from a Sector-Wide Approach (SWAp) and is in the process of integrating all public sector health activities under a single revenue budget. DPs agreed with this approach but highlighted concerns about its immediate and medium-term impact. For example, there are reports of potential stock-outs of contraceptive products and vaccines, delays with disbursing remuneration of the community health workers and uncertainties with the integration of some of the DP funded programme activities.
7. BHB is expected to be the UK Government’s final bilateral health programme in the country. However, its conclusion does not signify the end of FCDO’s involvement in Bangladesh’s health sector. BHC Dhaka will maintain its collaboration with the Government of Bangladesh (GoB) through a range of initiatives, including multi-sector programmes aimed at strengthening state systems; delivery of targeted technical assistance via FCDO’s centrally managed programmes (CMP); leveraging multilaterals through UK’s global commitments; and continued advocacy for the adoption of healthcare interventions that demonstrated success under BHB.
8. In this Programme Completion Review (PCR), the programme has scored A+, i.e., moderately exceeded expectation. This is based on two outputs (combined weight of 70%) scoring A+ and one output (30% weight) scoring A. Output 4 on COVID-19 was not included in the calculation, as it was dropped in 2023. Most of the outcome indicators have also achieved or exceeded their targets. The score is consistent with the annual review scores and with the findings of the independent evaluation carried out at the end of the programme.

Major lessons learned, evidence generated and recommendations
1. Due to the country’s socioeconomic progress, conventional service delivery-focused programming is no longer critically required or likely to offer the best value for money (VfM). The challenge was to tackle donor dependency that has developed over the long history of donor-supported service delivery programmes in the country. During the last two years of the programme, BHB primarily focused on country ownership, capacity building, and institutionalisation. While there has been some progress, there are still some concerns about the sustainability of programme activities, particularly in the absence of a new GoB SWAp in the health sector.
2. BHB demonstrates the potential for small-scale targeted TA that combines high-level buy-in with local initiative. Successful examples from this programme include the piloting of a Green Hospital Initiative in a coastal district and the introduction of the Automated Drug Licensing and Renewal System (ADLRS) across the country These types of effective TAs can be continued through FCDO’s Centrally Managed Programmes (CMP) and through a bilateral cross-cutting state effectiveness and accountability programme.
3. During the final years of the programme, BHB combined its programme activities with a sustainable policy influencing agenda. For example, using a small amount of resource from the BHB programme, the British High Commission (BHC) Dhaka and UNFPA staff worked with the government to establish a safeguarding cell within the Directorate General of Nursing and Midwifery (DGNM) and provided TA for developing a comprehensive Standard Operating Procedure (SOP) on Safeguarding against Sexual Exploitation Abuse and Harassment (SEAH). While this was an example of a low-cost quick win, some of the other policy advocacy agendas will take longer to materialise and require continuous and sustained effort. For example, despite the programme’s advocacy efforts, significant efforts are still needed to reduce irrational use of antibiotics to tackle Antimicrobial Resistance (AMR).
4. FCDO commissioned an end-of-programme independent evaluation in 2024. The evaluation highlighted that the programme was relevant to GoB’s 4th HPNSP, the key interventions were effective, promoted equitable access to healthcare, and were delivered with good value for money. However, the evaluators reported concerns about the sustainability of improvements beyond donor support in the absence of a new GoB health SWAp. The evaluation recommended advocating GoB to increase domestic financing for health, integrating future TAs within national governance mechanisms, and supporting climate change and health, equity in health services and digital health. Some of these recommendations can be incorporated into BHC Dhaka’s health policy influencing agenda.
  [note] DAI Global. Evaluation of the Better Health in Bangladesh (BHB) Programme’s Technical Assistance Components. Final Evaluation Report. 2025.
5. BHB programme generated some high-quality evidence. These include three original research articles on COVID-19 led by icddr,b scientists, which were published in journals from Cambridge University Press and Nature. These studies generated important evidence on severity of infections among slum and non-slum dwellers, antibody longevity and waning following COVID-19 vaccination, and immune response to different vaccines. A modelling study on the impact of midwives was commissioned by FCDO’s South Asia Research Hub, carried out by Johns Hopkins University. The study showed that midwives deployed in eight BHB programme districts have saved more than one thousand maternal and neonatal lives during 2019-2023.
  [note] Sarker P, Haq MA, Akhtar E et al. Serosurveillance among urban slum and non-slum populations immunized with COVID-19 vaccines in Bangladesh. Epidemiol Infect. 2024;152:e14.
  [note] Haq MA, Roy AK, Ahmed R et al. Antibody longevity and waning following COVID-19 vaccination in a 1-year longitudinal cohort in Bangladesh. Scientific Reports. 2024;14(1):11467.
  [note] Akhtar E, Kuddusi RU, Talukder MT et al. Functional T cell response to COVID-19 vaccination with or without natural infection with SARS-CoV-2 in adults and children. Scientific Reports. 2025;15(1):13341.
  [note] Inagaki Y, Tam Y, Rahman M, Winch P. Impact of Skilled Midwives on Saving Maternal and Newborn Lives in Bangladesh. 2024. London: Foreign Commonwealth & Development Office. Available at: https://www.evidencefund.com/lib/M6ZF5WES
6. Recommendations:
1. BHC Dhaka to contribute to health systems strengthening and institutional capacity in health through a cross-cutting state effectiveness and accountability programme, by March 2026.
2. BHC Dhaka to update the health policy influencing agenda with a clear workplan and monitoring framework including continued advocacy for mainstreaming successful BHB interventions by the government, by December 2025.
3. BHC Dhaka to identify potential effective TA interventions that can be mobilised through CMPs and global programmes, by March 2026.

How this report was conducted
1. This PCR was carried out during April-June 2025 after the implementing partners submitted their final reports. The PCR was led by the Senior Responsible Owner (SRO) of the programme with the support from the Programme Responsible Owner (PRO) and Lead Adviser. In addition, the Science, Technology and Health Lead of the regional team provided 10% support to the PCR. Two field visits in three districts were carried out between December 2024 and March 2025, prior to drafting the PCR report.
2. The PCR team used the implementing partners’ final reports, the independent evaluation report, and the observations from the field visits as the primary source of information and evidence for this PCR. The team also reviewed the evaluation report of 4th HPNSP commissioned by GoB and the Implementation Completion and Results Report of World Bank’s Health Sector Support Project to understand the performance and impact of the MDTF. The PCR report was reviewed by the Programme Assurance Committee (PAC) of BHC Dhaka, and the final report was quality assured by the Deputy Development Director. To avoid duplication, the Annual Review of 2025 received a waiver from BHC Dhaka Deputy High Commissioner and Development Director.
3. The following rubric was used to assess the outputs scores compared to final logframe targets: <85% of target: C (substantially did not meet expectation); 85-95%: B (moderately did not meet expectation), 95-105%: A (met expectation); 105-115%: A+ (moderately exceeded expectation), >115%: A++ (substantially exceeded expectation).

Actions following approval of this report

The following actions will be completed subsequent to the approval of the PCR report:
1. Initiate sales order for processing refund of the unspent funds (£17,725 remaining balance shown in provisional report) with UNFPA after receiving the certified financial report from UNFPA, by December 2025.
2. Disburse the final payment to MSH after receiving the final financial report, by December 2025.
3. Disburse final payment to DAI following approval on the final evaluation report from FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS 2), by September 2025.
4. Initiate financial closure in FCDO’s Aid Management Platform (AMP) once all final transactions are made.
5. Publish the approved PCR report on the UK Government’s Development Tracker (DevTracker).
6. Archive the BHB programme in AMP.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£88 million	£65.58m
Timeframe	December 2017 – November 2022	April 2018 – March 2025
Outcomes	The outcome statement in the Business Case (BC) was: / The citizens of Bangladesh, especially women, children and the poor, increasingly use quality family planning, health and nutrition services, delivered by efficient and sustainable health systems.	There were two outcome statements in the final logframe: / Citizens of Bangladesh, especially women, children and the poor, increasingly utilize quality family planning, health and nutrition services. / Health, family planning, and nutrition services are delivered increasingly by effective and efficient health systems.

Overall assessment of programme outcomes, sustainability and VfM
1. The original BC had one outcome statement including both service delivery and health systems strengthening activities. In the subsequent logframes, this was split into two outcome statements. The logframe outcomes were achieved within the timeframe and budget. This is evident from the achievements in outcome indicators against targets, as shown in Table 1. The programme has also shown agility and adaptability by incorporating new strategically important areas, like climate change and health. It also responded to national emergencies like COVID-19 during 2020-21, Cyclone Amphan in 2020 and the flood in eastern Bangladesh in 2024.
2. The last two years of the programme focused on a responsible and sustainable exit from bilateral health programming. The BHC Dhaka health team and the implementing partners actively engaged with GoB during the design of the 5th HPNSP to ensure that pilot interventions that demonstrated clear impact were included in the Operational Plans (OP) of the sector programme. These included introducing District Sexual and Reproductive Health and Rights (SRHR) Officers, accreditation of model pharmacies and scaling up midwifery-led care in district and union level health facilities. However, with the Interim Government’s decision not to continue with the subsequent sector programme, introducing these interventions in government systems have become challenging and will require renewed and sustained policy engagement. This sustainability risk has also been highlighted in the independent evaluation.
3. The VfM of the programme was thoroughly assessed in the evaluation using the FCDO VfM framework. It concluded that the programme achieved strong VfM in economy, efficiency and was cost-effective. The programme achieved economy through bulk recruitment, in-house expertise and using government facilities where possible. The cost per Disability-Adjusted Life Year (DALY) averted was £99 for the overall BHB programme, which is far below Bangladesh’s per capita Gross Domestic Product (GDP) of £2,057. Interventions with a cost per DALY averted of less than three times the GDP per capita are generally considered as cost-effective. The programme generated a high return on investment with economic benefits of more than £745 million. However, the evaluation report highlighted the absence of a standardised VfM framework across the implementing partners as one of the limitations of measuring VfM of the programme, which has led to some inconsistencies in VfM reporting.
  [note] The overall burden of disease is assessed using the disability-adjusted life year (DALY), a time-based measure that combines years of life lost due to premature mortality (YLLs) and years of life lost due to time lived in states of less than full health, or years of healthy life lost due to disability (YLDs).
  [note] Marseille E et al. Thresholds for the cost–effectiveness of interventions: alternative approaches. Bulletin of the World Health Organization. 2014;93(2):118–124.
4. BHB’s core objective was to ensure that every citizen of the country, especially women, children and poor, have equitable access to quality healthcare. The programme’s persistent focus on professionalising midwifery care not only improved health outcomes of poor women and adolescents but also contributed to girls’ education and women’s empowerment. BHB also implemented SRHR interventions targeting indigenous Santal community, strengthened disability-inclusive healthcare and piloted interventions for climate-vulnerable people in coastal areas. While recognising these successes, the evaluation flagged that there are structural challenges and systemic barriers in achieving equity in healthcare in the public sector. Continued policy advocacy is required to improve government’s willingness, ownership and capacity to address this gap.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
1. The Theory of Change (ToC) of the BHB programme included policy commitments with technical, technological and financial contributions as inputs. The outputs were to increase services, strengthen health systems and improve governance and stewardship. These were expected to achieve the intended outcomes, mentioned at the beginning of this section, leading to better health and well-being of citizens of Bangladesh. There were a range of assumptions in different stages of the ToC, including ensuring efficiency, value for money, capacity, supplies and mobilisation of domestic resources.
  [note] Development Tracker. Better Health in Bangladesh: Business Case. 2018. London: Foreign, Commonwealth and Development Office. Available at: https://devtracker.fcdo.gov.uk/programme/GB-1-203864/documents
2. No changes have been made to the ToC during the entire programme period. The impact and outcome statements mentioned in the Business Case remained extant throughout the life of the programme. The only exception was splitting the original BC outcome statement into two as explained in paragraph 18. The steps and underlying assumptions for achieving the outcome and impact remained valid. However, the logframe was regularly reviewed and updated based on the recommendations of the annual reviews and business case amendments to ensure realistic milestones and consistency in reporting.
3. BHB was a large-scale bilateral health programme with significant budget support and a service delivery focus, which was appropriate when it was designed. This is no longer applicable or feasible. As Bangladesh is graduating out of Least Developed Country (LDC) status in 2026, it can now afford to self-finance its health service delivery. In this context, development partners like the FCDO can only provide targeted technical assistance and policy support to sustain the achievements made through programmes like BHB and help fulfil global commitments in health.
4. BHB has gone through some transitions over the course of the programme. It started as a service delivery focused programme with significant funding commitment to MDTF of 4th HPNSP. In 2021, through an addendum to the Business Case (BC), the contribution to MDTF was reduced by half and funds were repurposed to respond to COVID-19 pandemic and increasing focus on health systems strengthening. In 2023, through two subsequent addendums, the programme duration was extended by two years, with a focus on TA to enable smooth and sustainable transition from bilateral health programming in Bangladesh. The overall budget of the programme was also reduced from £88m to £65.58m due to Overseas Development Assistance (ODA) cuts, which was largely adjusted from the MDTF contribution to the health sector programme, resulting in proportionately lower results attribution. The ODA cut also required the programme to deprioritise all service delivery interventions.
5. As outlined in Table 1, most of the outcome indicators have either achieved or exceeded the targets. In many cases, the most recent data (e.g., percentage of newborns receiving essential newborn care) is several years old. For that reason, it is difficult to assess whether the programme has achieved the target in those indicators.
Table 1: Progress at outcome level
Outcome Indicator(s)	Target	Result
OC-1: Citizens of Bangladesh, especially women, children, and the poor, increasingly utilise quality family planning, health, and nutrition services.
1.1 Percentage of births attended by skilled providers. (RFW3.2.4); and Ratio of births in facilities by poor to rich women (RFW 3.2.5)	72% / 1:2.5	69.7% / (SVRS 2024) / 1:2 / (BDHS 2022)
1.2 Contraceptive prevalence rate (CPR) for modern methods (all women); (RFW 3.2.1)	57%	61.0% / (SVRS 2024)
1.3 Contraceptive prevalence rate (CPR) for modern methods in Sylhet and Chittagong divisions (lagging behind areas) (RFW 3.2.2)	Syl: 54%, / Ctg: 54%,	Syl: 61.3% / Ctg: 59.4% (SVRS 2024)
1.4 % of newborn received essential newborn care (RFW 3.1.1) (at least 2 postnatal signal function care within 2 days of birth)	60%	56.5% / (MICS 2019)
1.5 Percentage of TB cases remaining un-detected (RFW 3.2.8)	30%	18% / (NTP 2022)
1.6 Number of women screened for cervical cancer (UNFPA TA)	1,000,000	1,258,884 / (DHIS2)
OC-2: Health, family planning, and nutrition services are delivered increasingly by effective and efficient health systems.
2.1. Percentage of district health facilities (#40) using digital systems to manage assets. (FCDO TA; DLI-5)	100%	100% / (DHIS2)
2.2. Percentage of health facilities reporting no stock-out of essential medicines.	100%	100% / (DHIS2)
2.3. Percentage of accredited medicine shops with improved dispensing practises as per national guidelines; (FCDO TA).	90%	90% / (MSH 2023)

BDHS: Bangladesh Demographic and Health Survey; DHIS-2: District Health Information Software 2; DLI: Disbursement Linked Indicator; MICS: Multiple Indicator Cluster Surveys; NTP: National Tuberculosis Programme; RFW: Results Framework; SVRS: Sample Vital Registration System; TB: Tuberculosis
BHB provided financial assistance to the 4th HPNSP through the MDTF managed by World Bank. It had 16 Disbursement-Linked Indicators (DLI). World Bank’s implementation completion and results report included a detailed assessment on MDTF. Among 16 DLIs, seven exceeded the target by achieving more than 100% of the target, four met the target, four failed to meet the target by achieving 66%-75%, and one had no progress towards the target. DLI 7 was the most successful DLI with 382 upazila health complexes having two midwives compared to the target of 150. DLI 16 failed to meet the target as Ministry of Public Administration (MoPA) did not approve Ministry of Health and Family Welfare (MoHFW) proposal on restructuring Central Medical Supply Depot (CMSD).
[note] World Bank. Implementation Completion and Results Report: Health Sector Support Project. 2025. Available at: http://documents.worldbank.org/curated/en/099032625092529709.

## C: Detailed Output Assessment

Output Number and Title	Quality Family Planning, Health and Nutrition services are provided increasingly, especially in hard-to-reach areas.
Output Score	A+ (Moderately exceeded expectation)
Impact weighting (%)	40%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1.1 Number of childbirths attended by skilled birth attendants / [in 20 BHB districts]		15,686 / (annual)	121,624 / (cumulative)	210,759 / A++ (substantially exceeded expectation)
1.2 Number of childbirths attended by skilled birth attendants in Sylhet, Barishal and Chittagong divisions (DLI)		143,660 / (annual)	965,196 / (cumulative)	1,218,371 / A++ (substantially exceeded expectation)
1.3 Number of total FP Users (modern methods)		226,036	325,000	347,519 / A+ (moderately exceeded expectation)
1.4 Number of under five children received vitamin A supplementation, annually		350,627	425,000	420,000 / A (Met expectation)
1.5 Incidence rate of tuberculosis (TB) per 100,000 population (this indicator was dropped in 2023)		215 / (2020)	215	221 / A (Met expectation)
1.6 Number of service providers and community leaders, trained to cope with climate and other shocks; (FCDO ICF)		13,000	30,000 / (as per BC addendum)*	32,717 / A+ (moderately exceeded expectation)

FP: Family Planning; ICF: International Climate Finance. * Per 3rd BC addendum, total target of 30,000. Target shown in logframe of 49,000 does not account for revision of this target in BC addendum.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
1. Output 1 moderately exceeded expectation. A significant focus was on strengthening midwifery and capacity of health facilities to provide quality basic emergency obstetric and neonatal care (BEmONC) services. Over 300 nursing faculties received training to implement the midwifery curriculum, and 150 faculties completed their master's programme. A key achievement was the training of 1,217 healthcare providers on Life-Saving Skills in Pregnancy and Childbirth (LSPC) across 20 BHB districts, including midwives, doctors and nurses between 2019 and 2024.
2. The share of normal vaginal deliveries by midwives in BHB-supported districts increased from 54.9% in 2019 to 91% in 2024. The use of partographs (a monitoring and decision-making tool for use during the active phase of labour) increased from 50% in 2018 to 85% in 2024 in BHB-supported districts, and facility-based deliveries increased by 15%. The Safe Delivery App was adapted for Bangladesh, and 3,035 service providers received orientation on its use. Collectively, these contributed to increase quality of maternal care and childbirths by skilled birth attendants.
3. The independent evaluation indicated that BHB effectively aligned with the strategic objectives of the 4th HPNSP and was crucial in expanding access to healthcare services, particularly in underserved regions. BHB-supported scale up of midwifery services directly contributed to increasing skilled birth attendance rates, particularly in underserved regions. This intervention significantly reduced maternal and neonatal mortality and exemplified the programme’s commitment to addressing regional health disparities.
4. Johns Hopkins University carried out modelling on lives saved by midwives using the Lives Saved Tool (LiST). The study estimated that midwives deployed in eight BHB programme districts saved more than one thousand maternal and neonatal lives from 2019-23. It also estimates that midwives can save 12,000 and 31,000 maternal and neonatal lives across Bangladesh during 2024-30 if midwifery-led care is expanded.
5. Climate resilience was another focus of output 1. A pilot Green Hospital Initiative was implemented at Mongla Upazila Health Complex to reduce its environmental impact and enhance climate resilience. Learnings from this initiative are being used to develop national Standard Operating Procedures (SOPs) on climate resilient health facilities. UNFPA provided technical support for the MoHFW Comprehensive Climate Change and Health-National Adaptation Plan (CCHNAP, also known as HNAP) to integrate climate actions across the health system.
6. Capacity building in climate change resilience included the development and launch of a short course on Climate Change and Health, designed with Dhaka University. Over 70 professionals completed the course in two batches. Additionally, 274 health professionals received training on climate change and SRHR. The programme also reached over 32,000 individuals in the community improving their understanding of climate change impacts on health and how to mitigate and adapt.
7. Output 1.5, which addressed TB incidence, was phased out in 2023. The 4th HPNSP included limited TB programming, but since the end of FA to the 4th HPNSP, all UK support for TB in Bangladesh has been via The Global Fund. According to the World Health Organization’s 2024 estimates, the TB incidence rate in Bangladesh has remained stable at 221 cases per 100,000 people from 2010 to 2024.

Lessons learned through this output, and recommendations for future programming
Lesson Learned:
BHB supported midwifery-led care has demonstrated a transformative impact on maternal and newborn healthcare in Bangladesh, as highlighted by the independent evaluation.
- Integration and better coordination between Directorate General of Health Services (DGHS) and Directorate General of Family planning (DGFP) is required to avoid duplication and minimise gaps in universal health coverage.
- Climate vulnerability has a direct impact on women’s health. Addressing this requires improving knowledge and capacity of health managers and reducing shortages in the healthcare workforce.
Recommendations:
- BHC Dhaka should continue policy advocacy to strengthen midwifery-led care across the country to reduce maternal and neonatal deaths.
- BHC Dhaka to continue advocacy and explore targeted TA to integrate climate resilience measures into health planning.

Output Number and Title	Health systems strengthened to increase performance, quality and efficiency.
Output Score	A (Met expectation)
Impact weighting (%)	30%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
2.1 Number of sub-district health facilities (Upazila Health Complexes) with at least two licensed midwives (TA, DLI-07)		450	420	407 / A (Met expectation)
2.2 Number of public health facilities meeting facility readiness criteria* for delivering post-partum FP services in Sylhet and Chittagong divisions (TA, DLI-9) and 20 BHB districts. (Cumulative)		60% / (2019) / 682 / (tracked numbers since 2020)	537	515 / A (Met expectation)
2.3 Number of health facilities (MCH, DH, UHC) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer (Cumulative)		60% / (2019) / 176 / (tracked numbers since 2020)	175	180 / A (Met expectation)
2.4 Number of district hospital personnel trained on digital Asset Management System. (Discontinued since 2023)		34 / (2019 only FCDO TA) / 188 / (2020- national)	190	283 / A++ (substantially exceeded expectation)
2.5 Number of medicine dispensers trained on GPP.		11,500	14,000	14,129 / A (Met expectation)

DH: District Hospital; MCH: Medical College Hospital; UHC: Upazila Health Complex

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
1. Output 2 met expectation. The programme supported the development of various policy guidelines and tools, curricula for midwives at different levels (Diploma, Post-basic Bachelor, MSc), training guidelines, SOPs, and job descriptions to increase performance and quality. Efforts were made to safeguard nurses and midwives against SEAH, including establishing a dedicated safeguarding cell at DGNM and development of an SOP on SEAH. Regulatory support was provided to BNMC for developing frameworks such as the Nursing and Midwifery Act and a midwifery Code of Ethics.
2. District SRHR Officers conducted 535 monitoring visits to district hospitals and 906 visits to Upazila Health Complexes (UHC). SRHR Officers helped to develop postpartum haemorrhage (PPH) and eclampsia action plans, and kit boxes were distributed to district hospitals (DH) and UHCs to strengthen maternal health services. A structured training initiative was launched, equipping 230 health officials, including Civil Surgeons, Hospital Directors, and Upazila Health and Family Planning Officers (UH&FPOs) with advanced skills in managing PPH and eclampsia. As a result, 98% of UHCs and DHs in supported districts had regular supplies of life-saving commodities to ensure quality of care.
3. The DGFP Management Information System (MIS) was improved with training of 2,199 participants. Supply-chain management of family planning commodities was strengthened. The BHB programme institutionalised quality family planning services in DGHS, with 410 DGHS health facilities reporting FP service data into DHIS2. FP skills among intern and post-graduate medical professionals in public medical college hospitals was increased, with 495 interns and postgraduate doctors trained. As a result, 76 programme-supported health facilities met post-partum family planning (PPFP) service readiness criteria. The Family Planning Clinical Supervision and Quality Improvement Team (FPCS QIT) was deployed in 64 districts, and competency-based training on their digital monitoring software was provided to District Consultants.
4. Cervical cancer screening services were strengthened through an initial assessment of existing government health facilities and development of micro-plans for each of the 20 BHB-supported districts to address identified gaps and strengthened facilities' capacity to deliver quality cervical cancer screening and treatment. Regional training hubs were established in four medical college hospitals. Over 1.4 million women were screened between 2018 and 2024 in the 20 programme districts, exceeding the target of 1 million.
5. Medicine dispensers from 32 districts of Bangladesh received training on Good Pharmacy Practice (GPP), antimicrobial resistance (AMR), and COVID-19-related issues. Against the end-of-programme target of 14,000 medicine dispensers, BHB trained 14,129 medicine dispensers including 13,629 males and 500 females in three rounds. BHB specifically targeted, trained and encouraged female entrepreneurs in several districts that enabled them to run retail pharmacies. This is a good example of women empowerment in a male dominated sector in Bangladesh.
6. The independent evaluation of BHB revealed that the programme contributed to strengthening pharmaceutical governance, introducing digital reporting system, capacity building and deploying digital tools to enhance healthcare system efficiency, transparency and accountability. The programme also made significant strides in increasing access to quality healthcare and reducing health inequities by expanding the health workforce and improving service delivery in underserved regions.
Lessons learned through this output, and recommendations for future programming
Lessons learned:
- Awareness on good pharmacy practice (GPP) plays an important role in improving drug management and over-the-counter drug selling.
- Use of digital technologies in health can significantly improve system efficiency and transparency.
- Dedicated focal persons at the district level such as SRHR officers can play a critical role in improving maternal and newborn health, and SRHR outcomes through coordination, planning and capacity building at the local level.
Recommendations:
FCDO should continue their policy engagement with government counterparts to improve the country’s health systems.

Output Number and Title	Stewardship and Governance of health sector improved
Output Score	A+ (moderately exceeded expectation)
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
3.1 Number of targeted medicine shops accredited		10,000	9,000	10,335 / A+ (moderately exceeded expectation)
3.2 Number of retail medicine shops, licensed/ license renewed, by DGDA using automated licensing and renewal system. (this indicator was added later)		700	1,300	1,857 / A++ (substantially exceeded expectation)
3.3 Proportion of agreed decisions in Urban Health policy meetings implemented. (Discontinued since 2021)		80%	80%	80% / A (met expectation).
3.4 Number of policies influencing agendas on pharmacy sector and antimicrobial resistance successfully implemented with significant contributions from BHB programme. [ new indicator since 2023]		2	2	2 / A (met expectation)

DGDA: Directorate General of Drug Administration

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
1. Output 3 moderately exceeded expectation. BHB played a significant role in strengthening the regulatory capacity of the Directorate General of Drug Administration (DGDA) and Pharmacy Council of Bangladesh (PCB), promoting good pharmacy practices (GPP) among retail medicine shops, and raising awareness on AMR. The project accredited 10,335 medicine shops against the end-of-project target of 9,000 (115%)
2. The programme helped DGDA to develop and enforce a national standard for licensing medicine shops. BHB helped to develop the ADLRS. In December 2023, DGDA abandoned the manual system and made ADLRS the only system for licensing medicine shops. The system has become an instrumental tool for DGDA to streamline operations, enhance transparency, and enable more efficient regulation of medicine outlets. In addition, BHB supported DGDA in developing Pharmacy Management Software (PMS) to track medicine expiry date and ensure safe disposal.
3. As a result of FCDO’s continued advocacy, DGDA developed daily activity entries from 64 district officers of DGDA. This report is used in the Annual Performance Agreement and shared with the ministry. DGDA developed clinical trial, drug and vaccine databases and up-to-date information is currently available on the website. DGDA is currently developing an online medical device database and updating the price of medical devices. The consumers are now able to submit product related complaints and DGDA can track status of the complaint from the dashboard in the website. Technical support was provided to form a ministerial national committee and working committee at DGDA along with a Terms of Reference (ToR) for updating the essential medicine list. In addition, BHB’s technical assistance to the DGDA enabled establishment and application of the red labelling in the main and secondary packaging of antibiotics with awareness messages to limit the use of antibiotics without prescription.
4. The National Parliament of Bangladesh enacted the Drug and Cosmetics Bill 2023 on 7 September 2023. BHB carried out policy advocacy and provided TA supports to DGDA during the drafting and fine-tuning of this law. BHB TA also supported the Directorate General of Medical Education (DGME) to complete the Management Information System (MIS) and the medical academic institutes (56 public and 78 private) are using the system efficiently. The national dashboard of this MIS has significantly improved monitoring, transparency and accountability.
5. The independent evaluation of the BHB programme confirmed that the BHB’s support in developing the ADLRS (online licensing and accreditation software) has been groundbreaking. Interventions targeting pharmaceutical governance, such as developing and implementation of the ADLRS, accreditation of retail pharmacies, and promotion of Good Pharmacy Practices (GPP), ensured safer, higher-quality medicines reached the population and addressed systemic inefficiencies in drug administration.
Lessons learned through this output, and recommendations for future programming
Lessons Learned:
- Automation and use of digital technology can improve system efficiency and transparency of government systems.
- Technical assistance is more effective when coupled with diplomacy and policy influencing.
Recommendations:
- BHC Dhaka to continue their policy engagement with the Government to improve health systems governance and ensure accountability and transparency.
- FCDO to consider bilateral umbrella TA programme to ensure continued access to the policy table and contribute to institutional capacity in the health sector.

Output Number and Title	COVID-19 response strengthened in target districts
Output Score	No score since this output was dropped
Impact weighting (%)	Not applicable		Impact weighting revised since last AR?	Yes, this output was not tracked since 2023

Output Indicator		Starting Target	Final Logframe Target	Final result Achieved
4.1 Number of health facilities (MCH, DH, UHC) with functional WASH facilities (hand washing stations with soap, water supply, functional latrines)		10	10	10 / A (Met expectation)
4.2 Number of COVID-19 research/ studies contributing to policy/ programme decisions		4	3	3 / A (Met expectation)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
1. Output 4 Met expectation – not included in final programme score. BHB adapted to COVID-19 response at the onset of COVID-19 outbreak in the country in 2020 and UK was the first to support the Bangladesh Preparedness and Response Programme of the GOB. The programme responded with emergency support and system strengthening: BHB contributed to provision of 81,500 testing kits, 50,000 full sets of PPE, 35 patient monitors, 60 lab technicians and 61 data operators. 3 million masks were distributed following awareness of masking raised through training of 1,000 volunteers. The programme provided 50 medical officers and deployed 200 midwives to continue essential services, while UNFPA supported 10 facilities with functional Water, Sanitation and Hygiene (WASH) provision (hand washing stations with soap, water supply, functional latrines). The programme also trained health managers and care providers on triage guidelines in the targeted health facilities. This output was dropped in 2023 as the Covid-19 situation improved in the country.
2. The GoB successfully vaccinated a large part of its population, and the programme provided support for additional vaccinators, training, logistics and transport. FCDO supported eight vehicles and logistics for the school vaccination programme of the GoB, facilitating the administration of over 1.37 million doses to school children. BHB also supported GoB’s health systems to reach pre-COVID-19 levels of service delivery and targets; supportive supervision by district SRHR officers played an important role in this.
3. UNFPA completed two research studies on COVID-19. Findings helped to develop a framework for pandemic preparedness and response. Through BHB, icddr,b conducted Sero-prevalence of COVID-19 and assessment of protective immune responses induced by different vaccines. Three research papers were published in academic journals based on these studies.
Lessons learned through this output, and recommendations for future programming
Lessons learned:
- Bangladesh had a successful role out of COVID-19 vaccination. This was built upon many years of successful national immunisation programme in Bangladesh.
- The country needs to have a better and stronger health systems to prevent and respond to any future public health emergency including a pandemic.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case
1. The independent evaluation of BHB provided a comprehensive VFM analysis of the TA elements of the programme to feed into this PCR. A summary of the VFM analysis from the evaluation report is given below:
2. Economy: BHB achieved strong economy through various cost-saving mechanisms. UNFPA and WHO used UN procurement processes which provided inputs at significantly reduced rates – lower than local markets for selected commodities. MSH saved £1.51m from the planned procurements alone, which was reprogrammed for flexible demand driven TA. Besides this, various alternative approaches helped cost minimisation in different line items, i.e., using in-house expertise instead of hiring external consultants, shifting to virtual models for training delivery instead of in-person training, and the use of government venues resulted in cost reductions of up to 89%. However, lack of disaggregated financial data from all partners constrained full quantification of savings.
3. Efficiency: BHB demonstrated strong efficiency in translating inputs into outputs. Eight out of 12 programme outputs met or exceeded targets, including childbirths attended by skilled birth attendants (Output 1.1 at 173%), family planning uptake (Output 1.3 at 107%), and licensing of medicine shops (Output 3.2 at 102%). Digital innovations like ADLRS significantly reduced licensing times (from 15–45 days to 2–5 days) and generated £1.62 million in savings. Training of medicine dispensers improved storage compliance (from 45% to 92%), labelling, and patient counselling, reducing medicine spoilage and health risks. However, performance in Output 1.4 (Vitamin A coverage at 99%) and Output 1.6 (climate resilience training at 67%) fell short, indicating implementation challenges in multi-stakeholder activities.
4. The VFM analysis also confirms that the BHB programme has delivered meaningful efficiency gains across all outcome-level service delivery areas. The cost per BEmONC patient stands at £56 compared to BC estimation of £83, indicating a 33% efficiency gain. This reduction suggests that the intervention was implemented with greater precision, leaner inputs, and improved facility-level management. Similar efficiency gains were found in cervical cancer screening (£1.28 per unit compared to £2 in the BC), and FP service delivery (£3.9 per unit compared to £6 in the BC).
  [note] Basic Emergency Obstetric and Newborn Care (BEmONC) is a set of interventions provided at primary health care facilities to manage complications during pregnancy and childbirth, as well as newborn health emergencies. It was a crucial part of programs aimed at reducing maternal and newborn mortality.
5. Effectiveness: The programme made notable improvements in health and policy outcomes. The share of normal deliveries conducted by midwives rose from 54.9% (2019) to 91% (2024), increasing access to skilled birth attendance. Deliveries supported by skilled birth attendants increased fourfold. The programme also helped strengthen the supply chain resulting in no stock-out of essential medicines; stock-out rates dropped from 40% to 0%. At the policy level, BHB supported enactment of the Drug and Cosmetics Act 2023, development of national pharmacy accreditation guidelines, and embedding digital tools like ADLRS and Pharmacy Management Software (PMS) in government systems. The programme’s e-learning platform trained over 25,000 pharmacy professionals, enhancing long-term institutional capacity.
6. Cost-Effectiveness: The BHB has been cost-effective in most cases compared to the design estimates. The VFM analysis looked at four major interventions under the UN-TA component and confirmed high return on investment for all four.
Table 2: Summary of VfM indicators of four elements of BHB
Detail	Deaths Averted	DALYs averted	Cost per DALY averted	Economic Benefits Generated	Economic return per £1 invested
Midwifery and BEmONC services	2,277	162,407	£33	£321m	£60
Family Planning information and services	2,058	142,514	£25	£280m	£79
Implant provision	650	45,854	£30	£89.3m	£65
Cervical Cancer Screening	78	27,576	£65	£53.9m	£29

Source: Independent evaluation of BHB, DAI Global
1. Some delivery costs were slightly higher than anticipated in the BC, possibly due to inflation, enhanced quality standards, or more comprehensive costing. The cost per life saved through BEmONC is estimated at £2,329 compared to £2,079 in the BC. In the area of family planning, the cost per unsafe abortion averted is estimated at £17, which is higher than the BC estimates at £5. Given the complex and often under-recognised system costs in reducing unsafe abortion rates, especially in conservative or under-resourced contexts – this figure may still represent reasonable value. The cost per cervical cancer case averted however is £189, which is 51% lower than the £385 projected in the BC. This strongly indicates that the cervical cancer screening interventions have been delivered in a highly efficient and cost-effective manner.
2. Equity: The programme purposively factored in equity through targeting the most vulnerable groups, especially women and newborns in hard-to-reach and lagging behind divisions like Chittagong, Sylhet and Barisal and regions vulnerable to climate change. The programme significantly contributed to increasing access to family planning, SRHR, and nutrition services for the pregnant, and lactating mothers and newborns. It supported establishment of safe maternity waiting homes in Chittagong Hill Tracts districts and provided emergency referral costs and transportation services to marginalised women. It also implemented the community-based approach in climate resilient intervention for the climate vulnerable women and girls in coastal districts.
Key VfM findings at a glance
- 5,063 deaths averted and 378,351 DALYs saved across four major interventions, generating £745.75 million in economic benefits.
- Cost per DALY averted: £99 – 19 times lower than Bangladesh’s GDP per capita (£2,057), confirming strong cost-effectiveness.
- £1.62 million saved through the digitisation of medicine shop licensing via ADLRS.
- £1.51 million saved through improved procurement practices by MSH.
- Compliance with prescription-only antibiotic sales increased from 33.7% to 82.7%.
- 515 public health facilities became PPFP-ready, up from zero at baseline.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
1. The overall risk rating for the BHB programme remained ‘moderate’ throughout the life of the programme and the overall risk rating was well within the FCDO risk appetite because of the nature of the programme and GOB’s ownership for its relevance to the GoB’s health sector programme. The FCDO’s programme team maintained a comprehensive risk register with specific mitigation strategies for each partner and monitored these risks throughout the period. These were updated bi-monthly and recorded in the online risk register. UNFPA and MSH developed and maintained separate risk registers and regularly updated FCDO through quarterly reports. A total of fifteen risks were identified at the outset of the programme including safeguarding, financial and fiduciary, policy and programme delivery, strategy and context, reputational, public service delivery and operations risks. Most risks were mitigated effectively during the implementation phase with two live risks at this moment considering the current political situation and the due financial closure.
2. The BHB programme had to accommodate significant budget reductions (i.e., £22.39m) over the life of the programme. In addition, £12.2m were reprioritised for COVID-19 emergency response. The programme’s scope was reduced and adjusted multiple times based on the allocated budget. However, with two years of extension to the project timeline, the delivery risks were minimised and continuous policy engagement and discussions on FCDO’s shifting approach have been helpful to protect FCDO from any potential reputational risk.
3. There were no reported cases regarding safeguarding or fraud under the BHB programme mainly because of the nature of the delivery and because partners had extensive monitoring and systems in place. However, we regularly monitored and ensured that BHB partners adhered to the safeguarding standards in concordance with FCDO’s “zero tolerance” policy on safeguarding. Delivery partners were well aware of, and adhered to, the safeguarding principles and operational requirements for fraud management. All programme staff completed mandatory Preventing Sexual Exploitation and Abuse (PSEA) training annually, and all downstream partners were briefed and assessed on their compliance with PSEA standards. MSH and UNFPA had dedicated gender and safeguarding focal person. Moreover, FCDO provided TA to DGNM to establish a safeguarding cell with dedicated staff and hotline/email and develop standard operating procedure outlining safeguarding reporting process for the DGNM staff, midwives and nurses along with capacity building and orientation, both at education institutions and health facilities through the UNFPA TA as part of its delivery plan policy agenda. It is expected that this will significantly improve the safeguarding environment for midwives working in remote settings.
4. Internal Audit Department (IAD) report, December 2019, identified a number of risks concerning the delivery of the programme, which were addressed and mitigated over the life of the programme. Details are included in Table 3.
Table 3: Update on risks identified in Internal Audit Department (IAD) 2019 report
Risk	Update
Independent results monitoring of the programme	Implementation Monitoring and Evaluation Division (IMED), under Ministry of Planning, was given the responsibility to verify and assess the agreed DLIs. The DLI verification protocols were agreed jointly. WB scrutinised IMED verification reports and process prior to each disbursement. Funds were not released until the Bank was satisfied with the verification reports of the IMED. To help address the independence, MDTF Partners joined as members of the DLI review committee along with HQ staff of the World Bank.
VFM in procurement of technical assistance components	The programme went through number of restructuring processes, formalised through BC addendum. TA procurements were integrated in the MSH component instead the commercial agent, which provided greater VFM.
Safeguarding risk	Enhanced due diligence assessments were completed for World Bank, UNFPA and MSH in response to the audit recommendation.
Fraud risk management	Comprehensive due diligence assessments and refresh DDAs were completed for all partners and recommendations were duly acted upon. Besides all project accounts were audited by independent auditors annually.
Risk management	Addressed through DDAs, project visits, spot checks and regular meetings with the partners.

Update on Partnership Principles
The BHB programme adhered to the country-level assessment (2019) of the UK Partnership Principles, which sought reasonable commitment to poverty reduction and the SDGs, including in health. While the previously elected Government of Bangladesh prioritised poverty reduction and was highly committed to the attainment of SDG, the commitment to accountability was assessed to be low. However, the commitment to strengthening public financial management remained high on the agenda and GoB successfully improved the internal audit capacity and scaled up the digital management system for high-end medical equipment, which indicate an appetite for more transparency in public spending. At present, the Interim Government is also prioritising poverty reduction and has initiated a number of reform commissions on various areas for the overall system improvement.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]
1. Overall, the performance of World Bank, MSH, UNFPA, and their downstream partners has been satisfactory in terms of programme delivery as well as commercial and financial performance. All partners achieved the stipulated results in line with the approved revised logframe. The FCDO programme team actively supported all implementing partners to ensure smooth delivery of the programme activities through regular programme management meetings and monitoring visits. Partners updated FCDO on programmatic and financial progress through quarterly and half yearly reports. All the reports were submitted on time and were of good quality, with adequate details on programme activities and expenditures. All partners have taken necessary actions to address the recommendations from each of the annual reviews.
2. Financial Performance: BHB programme spend totals £65.58m (almost 100% utilisation) as of 31 March 2025 including £12.2m for the COVID-19 response. All BHB partners have shown a great deal of flexibility in adjusting their respective budget in line with FCDO yearly budget allocation and ODA availability, and planned activities accordingly in discussion with the FCDO programme team. They have also been proactive in managing programme risks throughout the period.
3. The BHB budget was reduced by £22.39m from the original BC value. The breakdown of the budget allocation and spent by each component is set out in the table below.
Components	Allocation as per BC	Allocation as per 1st Addendum (December 2020)	Allocation as per 2nd Addendum / (November 2021)	Allocation in the 3rd Addendum (October 2023)	Actual Spent
UN TA (UNFPA led)	£10m	£27.65m	£34.30m	£28.0m	£28.03m
NGO TA (MSH led)	£3m	£10.35m	£10.35m	£9.36m	£9.21m
TA through Supplier	£25m	£5m	£0	£0	£0
TA through NGO	£5m	£0	£0	£0	£0
Total TA	£43m	£43m	£44.65m	£37.36	£37.24
II. Monitoring Evaluation and Learning (MEL)	£1m	£1m	£1m	£0.65m	£0.74m
III. Support to GoB through World Bank	£44m	£44m	£38.5m	£27.6m	£27.60m
Total Programme	£88m	£88m	£84.15m	£65.61m	£65.58

1. FCDO processed all planned disbursements following rigorous review of the financial reports and invoices in line with the ADAMANT Principles following approvals from the Lead Adviser, PRO and SRO. All partners completed financial audits annually and recommendations were acted upon in due course. All the audits were unqualified and provided a true and fair view on the project accounts and all recommendations were acted upon by respective partner. UNFPA's last Office of Audit and Investigation Services (OASIS) audit was held in 2019. They are currently undergoing an audit for the year 2024, which will be publicly available once completed. The World Bank Group’s annual Trust Funds Single Audit report for the fiscal year ended June 2024 is also available in the Bank’s Development Partner Centre website.
  [note] UNFPA. Office of Audit and Investigation Services (OASIS): Audit and Investigation. 2019. Available at: https://www.unfpa.org/audit-and-investigation
2. Asset Monitoring and Control: UNFPA and MSH maintained all project assets as per the FCDO requirements. No assets were procured through the MDTF and UNFPA TA components during 2023. MSH procured few items, with prior approval from FCDO. FCDO conducted an asset check on MSH each year and found that they followed robust procurement process and financial management practices. FCDO transferred the ownership of the programme assets to MSH and Government counterparts following an approval on asset disposal from the Development Director. Assets purchased under UNFPA will be handed over to the government and respective implementing partners, as per the UNFPA policy and in line with the global framework arrangement. The assets will be used for the purpose of health service delivery and will be instrumental in maintaining their operational efficiency for providing SRHR services in the community. UNFPA will ensure that these assets are being used for the intended purpose.
Programme-level approach to monitoring and evaluation
1. The FCDO programme team had regular monthly/bi-monthly meetings with the TA implementing partners (UNFPA, WHO and MSH) to discuss progress and delivery challenges. They also carried out field visits to various project districts, at least once or twice per year.
2. UNFPA ensured adequate monitoring, mentoring and supportive supervision visits by the District Public Health Nurse (DPHN) and Assistant DPHN at Upazila Health Complexes (UHC) and Union Sub Centres (USCs) under the project district for midwifery services. DGFP deployed the Family Planning Clinical Supervision and Quality Improvement Team (FPCS QIT) in 64 districts with responsibility to ensure the quality of care and supportive supervision at different facilities. They initiated the digital FPCS-QIT monitoring software to establish proper recording, reporting and feedback systems. SRHR officers (hired through DGHS) were employed in each of the 20 UNFPA-supported districts to help monitor all SRHR activities, which helped build ownership and interest among central government programme managers and improved communication with local health managers.
3. FCDO conducted annual reviews to assess progress and provided recommendations for improvement, which were duly acted upon by respective partners. Additionally, an independent impact assessment was undertaken by DAI Global UK towards the end of the programme. The primary purpose of this was to evaluate the programme's technical assistance interventions, delivered by UNFPA and MSH, and inform and strengthen future health programming, policy and institutional governance of the health sector in Bangladesh.

Date of last narrative financial report	UNFPA: 30 March 2025 / MSH: 03 March 2025 / World Bank: 29 April 2025	Date of last audited annual statement	UNFPA: OAIS audit is currently ongoing and will be available by December 2025. / MSH: 29 April 2025 / World Bank TF single audit report: 23 September 2024