Evaluation of the Better Health in Bangladesh (BHB) Programme’s Technical Assistance Components

Final Evaluation Report: May 2025
Framework ECM No: ECM_4755

Submitted by DAI Global UK in partnership with Halcyon Consulting Limited and Data Management Aid (DMA).

Authors: Disha Ali, Foyzul Bari Himel, Afeef Mahmood, Hasib Reza, Charlotte Laurence, Michelle Wong

Disclaimer: The views expressed in this document do not necessarily represent the Foreign, Commonwealth & Development Office’s (FCDO) views or policies, or those of DAI.

Contents

List of Tables

List of Figures

# Acronyms and Abbreviations

ADLRS	Automated Drug Licensing and Renewal System
AMR	Antimicrobial resistance
ANC	Antenatal Care
APIR	Annual Programme Implementation Reports
BHC	British High Commission
BDHS	Bangladesh Demographic and Health Survey
BEmONC	Basic Emergency Obstetric and Newborn Care
BHB	Better Health Bangladesh
BHC	British High Commission
CCHPU	Climate Change and Health Promotion Unit
COVID-19	Coronavirus disease of 2019
CPD	Continuous Development Programme
CPR	Contraceptive Prevalence Rate
CV	Curriculum Vitae
DAC	Development Assistance Committee
DALY	Disability Adjusted Life Years
DFC	Direct Financial Cooperation
DFID	Department for International Development
DG	Director General
DGDA	Directorate General of Drug Administration
DGFP	Directorate General of Family Planning
DGFP-MIS	Directorate General of Family Planning – Management Information System
DGHS	Directorate General of Health Services
DGME	Directorate General of Medical Education
DGNM	Directorate General of Nursing and Midwifery
DH	District Hospital
DHIS	District Health Information System
DLI	Disbursement Linked Indicators
DMA	Data Management Aid
DP	Development Partner
DPC-HN	Development Partners Consortium for Health, Population and Nutrition
DPM	Doctor of Podiatric Medicine
e-LMIS	Electronic Learning Management Information Systems
e-AMS	Electronic Asset Management System
EMONC	Emergency obstetric and newborn care
EQuALS	Evaluation Quality Assurance and Learning Services
EU	European Union
FCDO	Foreign, Commonwealth and Development Office
FP	Family Planning
FPCS-QIT	Family Planning Clinical Supervision and Quality Improvement Team
FY	Financial Year
GBV	Gender Based Violence
GDP	Gross Domestic Product
GEMFA	Global Evaluation and Monitoring Framework Agreement
GESI	Gender and Social Inclusion
GGHH	Global Green Health and Healthcare
GIZ	Gesellschaft für Internationale Zusammenarbeit
GoB	Government of Bangladesh
GPP	Good Pharmacy Practice
GRE	Gender-Responsive Evaluation
HEU	Health Economics Unit
HIS-eH	Health Information System and electronic-Health
HIV	Human Immunodeficiency Virus
HMIS	Health Management Information System
HNAP	Health National Adaption Plan
HNP	Health, Nutrition and Population
HPNSP	Health, Population and Nutrition Sector Programme
HPV	Human Papillomavirus
HR	Human Resources
HRH	Human Resources for Health
HSD	Health Services Division
HSS	Health System Strengthening
ICDDR,B	International Centre for Diarrhoeal Disease Research, Bangladesh
ICF	International Climate Finance
IEET	Independent Endline Evaluation Team
IRT	Independent Review Team
IT	Information Technology
IUD	Intrauterine device
JHU	John Hopkins University
JICA	Japan International Cooperation Agency
KII	Key Informant Interview
KMSS	Khulna Mukti Seba Sangstha
LDC	Least Developed Country
LFW	Logical Framework
LSSPC	Life Saving Skills in Pregnancy and Childbirth
LiST	Lives Saved Tool
LMIS	Labour Market Management Information System
M&E	Monitoring and Evaluation
MCH	Medical College Hospital
MCRAH	Maternal, Child, Reproductive and Adolescent Health
MDTF	Multi Donor Trust Fund
MEFWD	Medical Education and Family Welfare Division
MEL	Monitoring, Evaluation and Learning
MICS	Multiple Indicator Cluster Survey
MIS	Management Information System
MLC	Midwifery-led Care
MLU	Midwifery-Led Units
MMR	Maternal Mortality Rate
MNCAH	Maternal, Newborn, Child and Adolescent Health
MNCH	Maternal, Newborn and Child Health
MOHFW	Ministry of Health and Family Welfare
MSH	Management Sciences for Health
MTaPS	Medicines, Technologies and Pharmaceutical Services
MTR	Mid Term Review
NCD	Non-Communicable Disease
NGO	Non-Governmental Organisation
NIPORT	National Institute of Population Research and Training
NMS	Nursing and Midwifery Services
NSSS	National Social Security Strategy
NVD	Normal Vaginal Delivery
ODA	Overseas Development Assistance
OECD	Organisation for Economic Co-operation and Development
OP	Operational Plan
PCB	Pharmacy Council of Bangladesh
PCR	Programme Completion Report
PHD	Partners in Health and Development
PMS	Pharmacy Management Software
PNC	Postnatal Care
PPE	Personal Protective Equipment
PPFP	Postpartum Family Planning
PRO	Programme Responsible Officer
QIT	Quality Improvement Team
RBF	Results-based Financing
RFW	Relevant Results Framework
ROD	Single-Rod Contraceptive Implant
ROI	Return on Investment
SBA	Skilled Birth Attendants
SDG	Social Development Goal
SIDA	Swedish International Development Cooperation Agency
SOP	Standard Operating Procedures
SRH	Sexual and Reproductive Health
SRHR	Sexual, Reproductive and Human Rights
SRMNCAH	Sexual, Reproductive, Maternal, Neonatal, Child and Adolescent Health
SRO	Senior Responsible Officer
STI	Sexually transmitted infections
SVRS	Sample Vital Registration System
SWAp	Sector Wide Approach
TA	Technical Assistance
TB	Tuberculosis
TBA	Traditional Birth Attendant
TAC	Technical Assistance Committee
TFR	Total Fertility Rate
TO	Technical Officer
ToC	Theory of Change
ToR	Terms of Reference
UHC	Upazila Health Complexes
UHFPO	Upazila Health and Family Planning Officer
UK	United Kingdom
UNFPA	United Nations Population Fund
US	United States
UN	United Nations
USAID	United States Agency for International Development
VfM	Value for Money
VIA	Visual Inspection by Acetic Acid
WASH	Water, Sanitation and Hygiene
WB	World Bank
WHO	World Health Organization
WISN	Workload Indicators of Staffing Needs
YLL	Years of Life Lost

# Executive summary
The £65.61 million Better Health in Bangladesh (BHB) programme (2018-2025) was a health system strengthening initiative funded by the United Kingdom’s Foreign, Commonwealth and Development Office (FCDO). The programme had four components: direct financial assistance to Government of Bangladesh’s 4th Health, Population and Nutrition Sector Programme (HPNSP) through a World Bank managed Multi-Donor Trust Fund (independently evaluated in 2024), two technical assistance (TA) components delivered by the United Nations Population Fund (UNFPA) and Management Sciences for Health (MSH) respectively and a monitoring and evaluation component. The purpose of this evaluation was to evaluate the programme's TA interventions and inform and strengthen future health programming, policy and institutional governance of the health sector in Bangladesh. The primary audiences are the British High Commission (BHC) Dhaka and the Bangladesh Ministry of Health and Family Welfare (MOHFW). It was conducted from December 2024 to March 2025.
Objectives: The evaluation took a learning approach to 1. Identify lessons from the programme's TA work; 2. Assess value for money (VfM) of the key interventions; 3. Assess if the BHB Theory of Change was implemented; 4. Identify the main factors influencing the achievement of results from interventions; 5. Inform the Programme Completion Report; and 6. Provide recommendations for future health policy and programme interventions in Bangladesh.
Design and Methodology: A mixed-methods approach triangulating qualitative and quantitative data from a range of sources including document review (45 documents); logframe and theory of change review; key informant interviews (58 interviewees of which 28 were female); secondary data analysis; field observations; case studies; value for money analysis and GESI analysis. Limitations included time constraints, potential biases in data collection, data quality and external disruptions. These were mitigated through triangulation, cross-verification and strategic planning. Data provided a robust, credible foundation for the evaluation.
###### Findings of the evaluation
Relevance: The BHB programme demonstrated strong alignment with the 4th HPNSP (2017-2024), supporting key operational plans and addressing systemic health challenges. Its focus on maternal, neonatal and child health, workforce development and pharmaceutical governance strengthened healthcare delivery and governance and contributed to HPNSP’s equitable service delivery goals. It responded to emerging health challenges, including COVID-19, shifting from direct service delivery to policy influence and ensuring sustainability through anti-microbial resistance (AMR) control, midwifery-led care and integrating climate resilience.
Effectiveness on intended logframe outcomes. Logframe indicators demonstrated acceptable progress between 2019-2024. TA contributed towards improvements in service delivery and there is evidence of effectiveness beyond logframe indicators. Implementation challenges included leadership changes within government agencies, which disrupted TA continuity, and limited follow-up mechanisms for research-based interventions, leading to underutilisation of research findings. Factors that drove effectiveness were TA’s agility in adapting to evolving health priorities, collaboration with government, a data-driven approach, leadership at all levels, engaging with communities and additional workforce for supervision, monitoring and mentoring. Systems to ensure a consistent supply of drugs and equipment played a critical role while multipronged climate change and resilience activities created a pathway to address climate change challenges. The TA model leveraged the distinct strengths of partner organisations but faced challenges in achieving sustainability. TA effectiveness would be enhanced by more integrated, complementary governance, regulatory and systems strengthening efforts, for example maximising the long-term benefits of the model pharmacy model by increasing capacity of the Directorate General of Drug Administration to monitor the capacity of pharmacies to ensure compliance with national AMR related regulations.
Sustainability. While the programme successfully influenced national health systems, there are concerns about the longevity of BHB improvements once donor support is phased out. Shifting away from the 5th HPNSP sector wide approach presents a sustainability challenge. Government commitment to retain workforce is inconsistent and there are gaps in continuous support for information technology maintenance. Without sustained investment in human resource development, gains achieved through BHB’s TA could be lost over time. The lack of on-going regulatory oversight in areas such as AMR control and pharmacy standards could potentially limit the longer-term benefits of TA. Systemic inefficiencies within government agencies have hindered the full institutionalisation of TA outcomes. The lack of a unified health information system remains a persistent issue, with multiple databases operating in silos.
Efficiency. BHB achieved strong economy through cost-saving mechanisms across procurement, consultancy, and training. TA demonstrated strong efficiency in translating inputs into outputs. Digital innovations like Automated Drug Licensing and Renewal System (ADLRS) cut licensing times and generated £1.62 million in savings. Training medicine dispensers improved compliance, labelling and patient counselling, reducing medicine spoilage and health risks. BHB was cost-effective with a cost per Disability Adjusted Life Year (DALY) averted of £99, substantially below gross domestic product (GDP) per capita.
Equity. BHB proactively included equity in its programming in a range of ways. Despite important progress in expanding midwifery services, gaps remain from an equity perspective including geographic inequalities; over-burdened staff; issues around safety and logistics for midwives in remote areas; lack of essential infrastructure and medical supplies.
###### Summary of lessons learnt
- Policy engagement is crucial to achieve impact and broad coverage.
- Effective policy implementation should be complemented with robust TA and continuous skill development at all levels to deliver results.
- Successful programmes should demonstrate visible and measurable improvements.
- Interventions across broad geographic regions enhanced impact at the population level.
- Effective programme monitoring and reporting requires integration of well-defined, measurable indicators into national databases.
- Strong government ownership is essential for long-term sustainability and to create an enabling environment for effective policy implementation.
###### Summary recommendations for BHC Dhaka with development partners and relevant government departments
1. Explore options to integrate future TA more fully within national governance structures.
2. Conduct advocacy with MOHFW to strengthen sustainable financing.
3. Support interventions to integrate climate resilience measures into health planning.
4. Continue advocacy and/or support for Social Equity in health service delivery.
5. Support strategic workforce planning to enhance Human Resources for Health.
6. Support digital health innovation scale-up to increase efficiency and accountability.
7. Strengthen programme reporting frameworks.
8. Strengthen and standardise VfM frameworks in any future programming.
# Introduction and overview
This section summarises the Better Health in Bangladesh (BHB) programme's design and objectives, describes the programme’s context and evolution during implementation, and provides an overview of the programme’s Theory of Change (ToC). The £65.61 million BHB programme (2018-25) was a health system strengthening initiative funded by the United Kingdom (UK) Foreign, Commonwealth and Development Office (FCDO). The programme supported pro-poor policy reform and service delivery through financial assistance, technical assistance and capacity building to support the Government of Bangladesh (GoB) to achieve a more resilient, efficient, sustainable, and equitable health system. The programme’s intended outcome was for Bangladesh citizens, especially women, children and the poor, to increasingly utilise quality family planning, nutrition, and health services.
This evaluation was commissioned by the British High Commission (BHC) Dhaka and conducted by DAI Global UK from December 2024 to March 2025.
BHB was delivered through four complementary components. These include:
1. Results-based financial assistance to Bangladesh’s national Health, Population and Nutrition Sector Programme (HPNSP) (£27.6m) through a Multi Donor Trust Fund (MDTF) managed by the World Bank (WB). This component ended in 2024 and was evaluated separately in 2024 as part of the overall endline evaluation of 4th HPNSP.
  [note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished. Key findings included strong progress on child health, skilled birth attendance, post natal care, health workforce expansion and digital tools (e.g. DHIS2 and electronic Management Information Systems). It noted positive innovations including Community Eye Centres, midwifery-led care and postpartum family planning (PPFP). Challenges included gaps in governance and stewardship, urban primary health care (PHC) access, unmet maternal/neonatal health targets, procurement delays and data integration issues.
2. Technical Assistance (TA) through United Nations (UN) agencies (£28.0m), led by the United Nations Population Fund (UNFPA). Support focused on strengthening Sexual and Reproductive Health and Rights (SRHR) through interventions in 20 pilot districts across Bangladesh and strengthening health workforce capacity, data management, and governance systems at the central level.
3. TA through Non-Government Organisation (NGO) (£9.2m), delivered by and Management Sciences for Health (MSH) to improve the stewardship, governance, and regulation of the health sector. This entailed registering and licensing pharmacies, addressing antimicrobial resistance (AMR), and supporting drug regulation reforms through initiatives like the Automated Drug Licensing and Renewal System (ADLRS) and Pharmacy Management Software (PMS).
4. Monitoring, Evaluation and Learning (MEL) component (£0.75m) to generate evidence and carry out evaluations.

This evaluation addressed the two TA components and is intended to inform and strengthen future health programming, policy, and institutional governance of the health sector in Bangladesh.
## Intervention logic
The BHB Theory of Change (ToC) captures its intervention logic, setting out how effective delivery of all four components will result in more effective health systems and increased use of quality health services (see figure 1 below). The core rationale underpinning the BHB ToC is that if there is increased access to quality health services, strengthened health systems, and enhanced governance through improved policy frameworks, financing models, and regulatory mechanisms, then Bangladeshi citizens – particularly women, children, and vulnerable populations – will increasingly utilise quality family planning (FP), nutrition, and health services.

Figure 1: Theory of Change (ToC) of Better Health in Bangladesh (BHB) programme
## Policy context and pro-poor focus
BHB aligned with various national and global policy commitments to reduce health disparities for marginalised populations, particularly women, children and those living in poverty. Key policy frameworks include the Social Development Goals (SDGs) (especially SDG 3 and SDG 5), the 4th HPNSP, the National Strategy for Maternal Health (2021–2030), the National Social Security Strategy (NSSS) of Bangladesh (2015), the Universal Health Coverage Framework and BHC Dhaka’s strategic priorities in Bangladesh. The programme also focused on gender-sensitive service delivery (e.g. midwifery-led care), reducing out-of-pocket health expenditures by supporting governance reforms and financial risk protection mechanisms, targeting poverty-prone and hard-to-reach areas of Barishal, Sylhet and Chattogram divisions and focusing on ethnic minorities and other disadvantaged people (e.g. Santal community). In addition to strengthening the GoB’s health system with targeted interventions aligned with the 4th HPNSP, the programme contributed to developing the 5th HPNSP​ through TA and policy engagement. The programme included support to the Ministry of Health and Family Welfare (MOHFW) to advance Universal Health Coverage and address key health challenges, including maternal and child health, non-communicable diseases (NCDs), and anti-microbial resistance (AMR).
## Broader country context and health sector development
Over the past two decades, Bangladesh has seen considerable economic growth and achieved lower-middle-income status according to the WB country income classification. Ensuring equitable access to healthcare remains a challenge due to persistent socio-economic disparities. Health financing remains limited, with less than 1% of Gross Domestic Product (GDP) allocated to the sector (the recommended health expenditure is generally around 5% of GDP for lower-middle-income countries), and 69% of expenditures covered out-of-pocket, which restricts access for vulnerable populations. Systemic inefficiencies, such as under-utilised budgets and delayed disbursements, hinder resource utilisation. The health workforce is below World Health Organisation (WHO)-recommended standards in terms of availability, accessibility, acceptability and quality. There are geographic disparities in health service quality and access.
[note] MOHFW, 2024. Feasibility Study of 5th HPNSP. Ministry of Health and Family Welfare. Dhaka, Bangladesh
[note] Health Economics Unit (HEU), 2023. Bangladesh National Health Accounts 1997–2020. Health Economics Unit, Ministry of Health and Family Welfare.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
The health system faces a triple burden of ongoing communicable diseases, rising NCDs and overall poor maternal and child health outcomes (due to inadequate pre- and post-natal care, child marriage and associated health risks, gender-based violence, malnutrition, infectious diseases, and child labour, among other determinants). As one of the world's most climate-vulnerable nations, Bangladesh frequently faces natural disasters like floods and cyclones, which disrupt health services and exacerbate disease outbreaks.
The MOHFW oversees the health sector and is divided into the Health Services Division (HSD) and the Medical Education and Family Welfare Division (MEFWD). The MOHFW delivers a substantial portion of its public health services through the HPNSPs. The 4th HPNSP was due to end in 2024, and the 5th HPNSP (2024 to 2029) is under development – with support from the BHB programme. While these initiatives aim to achieve Universal Health Coverage and align with the SDGs, governance issues, such as overlapping mandates and limited accountability mechanisms, hinder effective implementation.
National health sector priorities to address challenges within the health system and improve shock responsiveness include strengthening domestic resource mobilisation, improving the efficiency of health expenditure and building capacity for long-term health system resilience.
## Evolution: adapting to changing priorities in the national and global context
BHB has evolved over time in response to changing circumstances. Figure 2 below show’s BHB’s evolution over time. Initially the programme prioritised expanding essential health services and improving health system resilience (largely through the financial assistance component). However, COVID-19 temporarily shifted focus towards pandemic response and emergency support. More recently, the programme reduced its emphasis on direct service delivery and transitioned towards supporting policies, regulatory reforms and providing targeted TA.

Figure 2: BHB evolution over time
Programme establishment and early implementation (2018-2019). BHB was originally structured to improve health outcomes by expanding service delivery, focusing on maternal, newborn, child and adolescent health (MNCAH), family planning and nutrition services. Through financial assistance provided via the World Bank-managed MDTF, the programme worked to improve service provision in low-performing regions such as Sylhet and Chittagong. The programme also focused on strengthening procurement and financial management systems, human resources in health and digitalisation of health governance. This approach aligned with Bangladesh’s Vision 2021, which sought to improve healthcare access, and its commitment to achieving the SDGs.
Adaptations in response to the COVID-19 pandemic (2020-2022). The outbreak of COVID-19 in early 2020 necessitated a substantial shift in programme priorities. The pandemic put immense pressure on Bangladesh’s health system, affecting service delivery and disrupting ongoing health initiatives. BHB was restructured to provide immediate support to the national COVID-19 response. Funds (£12.2m) were redirected from the financial support component to procure essential medical supplies, strengthen infection prevention and control measures and support large-scale vaccination efforts. BHB also played a role in maintaining essential MNCAH services when routine healthcare utilisation had declined due to movement restrictions and public apprehension.
During the COVID-19 pandemic, progress continued in key programme areas, for example, deploying midwives across sub-district health facilities improved access to skilled birth attendants. Efforts to digitise pharmacy licensing and strengthen AMR control facilitated the introduction of new regulatory frameworks aimed at improving the quality of healthcare provision. These measures helped support continued functioning of Bangladesh’s health system despite the pandemic.
Transitioning to a policy support and TA model (2022-2024). As Bangladesh prepares to graduate from Least Developed Country (LDC) status in 2026, international assistance is shifting from direct service delivery models towards policy support, regulatory strengthening and targeted TA. In line with this transition, BHB underwent structural changes, placing greater emphasis on supporting health governance, facilitating policy reform and institutional capacity-building. The focus was on embedding reforms within national frameworks to ensure sustainability. Key initiatives in the programme’s later phase included TA to develop the 5th HPNSP, introducing legislative reforms such as the Drug and Cosmetic Act 2023 and scaling up digital solutions in health governance. BHB also provided capacity-building for health professionals and policymakers to address emerging environmental health challenges.
In 2023, reductions to overall UK ODA funding as a result of the COVID-19 pandemic necessitated budget adjustments, which in turn required a careful realignment of priorities including a greater prioritisation of TA relative to direct financial assistance. Key changes were summarised in an addendum to the Business Case and included:
[note] FCDO, 2023. Addendum to Business Case. BC addendum
- Financial assistance to the 4th HPNSP through WB MDTF: FCDO originally committed a total of £38.5m. Total disbursement was £27.6m as of 31 August 2023. It was proposed there would be no further disbursement so the total budget for this component was therefore reduced by £10.9m to £27.6m
- TA through UNFPA: The original budget was £34.3m and, as of the end of August 2023, total disbursement was £26.95m. It was agreed that two further payments would be made of £0.45m in Financial Year (FY) 23/24 and £0.6m in FY 24/25, which would bring the total budget to £28m, an overall reduction of £6.3m. The timeline for this component was also extended by one year until 31 December 2024.
- TA through NGO (MSH): Original allocation £10.35m. As of the end of August 2023, the total disbursement was £8.41m. Two further disbursements of £0.55m (FY23/24) and £0.4m (FY24/25) were proposed, making the total budget for this component £9.36m, an overall reduction of £0.99m.

With the programme scheduled to conclude in March 2025, the period from 2024-2025 focused on ensuring the sustainability of the reforms introduced under BHB. Key priorities included:
- Developing an exit strategy for on-going TA, particularly for midwifery services, pharmacy governance and AMR control.
- Documenting key lessons from transitioning from a service delivery model to a policy-based approach to inform future health sector interventions in Bangladesh.

# Purpose and scope of the evaluation
## Purpose
The primary purpose of this evaluation was to evaluate the programme's TA interventions and inform and strengthen future health programming, policy and institutional governance of the health sector in Bangladesh. Key lessons learnt from the programme were also documented. The review also served to inform BHC Dhaka’s learning and will feed directly into the BHB Programme Completion Report (PCR) – an important tool to ensure accountability for UK aid funding – and inform the design of subsequent UK support to the health sector. Therefore, the purpose was to inform the design of future TA interventions rather than address global evidence gaps more widely. The primary audience is, accordingly, BHC Dhaka and the Bangladesh MOHFW.
## Objectives
As set out in the Terms of Reference (ToR) Annex 1: Terms of Reference, the objectives of this evaluation were to:
- Identify lessons from the programme's TA work, including TA's contribution, relevance, effectiveness, and sustainability.
- Assess value for money (VfM) of the key interventions.
- Assess if the BHB ToC has been implemented and if the key assumptions have changed during the programme cycle.
- Identify the main factors influencing the achievement of the results from BHB interventions.
- Inform the PCR.
- Provide recommendations for future health policy and programme interventions in Bangladesh.
## Evaluation scope
The evaluation's scope was to assess the relevance, effectiveness, equity, sustainability, and efficiency of the TA provided from the start of the programme implementation in 2019 to the end of 2024. The scope was laid out in the ToR, which was developed by BHC Dhaka with inputs from the Evaluation Quality and Learning Service (EQuALS). During inception, the evaluation team reviewed the ToR and confirmed no substantial changes to the scope were needed.
This evaluation was limited to the second and third components of BHB, comprising of the TA provided through UNFPA and MSH, looking at how this contributed to the overall pathway of change. As set out in the ToR and agreed with EQuALS, coherence and impact were beyond the scope of this evaluation, which was realistic given the time and funding constraints.
The Financial Assistance to the MDTF (the pooled fund mechanism of the 4th HPNSP led by the WB) had effectively finished in August 2023. An independent endline evaluation of the 4th HPNSP was conducted by the MOHFW and findings accepted by both the Government and Development Partners. Relevant elements from this end evaluation have been referenced in this report. The WB's Implementation Completion Report, currently in draft, was also reviewed and its findings used where applicable.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
The endline evaluation of Bangladesh’s 4th HPNSP (2017–2024), funded by GoB with support from development partners, assessed programmatic and financial progress, identifying achievements, challenges and lessons to inform the upcoming 5th HPNSP. Using mixed methods, document reviews, key informant interviews, field visits, and stakeholder consultations, the evaluation found notable successes in reducing under-5 mortality, improving skilled birth attendance, and postnatal care, with innovations and expansion of midwife-led care expanding digital health tools, increasing health worker availability, and strengthened financial management and supply chains, despite major disruptions from the COVID-19 pandemic and the demands arising in relation to Forcibly Displaced Myanmar Nationals (FDMNs).
The evaluation noted on-going challenges, including gaps in governance and stewardship, unmet maternal and newborn health targets, weak urban primary health care (PHC), procurement delays, data integration gaps, and high out-of-pocket expenses. The evaluation recommended approving the 5th HPNSP, strengthening governance and sector wide coordination, improving human resources, enhancing financial and procurement systems, building robust health data architecture (including private-sector integration and legal frameworks), improving referral mechanisms, and expanding good practices. For development partners, the evaluation called for coordinated TA, greater financial transparency for off-budget projects, and sustained support for governance and system reforms to ensure long-term sector resilience and progress toward Universal Health Coverage and the SDGs by 2030. The evaluation report has not been published yet. FCDO shared the report with the team.
Both UNFPA and MSH provided TA to support national-level system strengthening. In addition, both provided TA to districts that were low-performing in terms of health systems and had relatively high levels of need. MSH provided TA to enhance the Directorate General of Drug Administration (DGDA) capacity and its regulatory functions in 32 selected districts, of which 20 were also supported with TA by UNFPA. Annex 2: BHB programme coverage has a table of the administrative divisions (also known as Upazilas) and districts covered by UNFPA and MSH support, with a map showing the different divisions.
Cross-cutting issues like gender, poverty, capacity building and governance are integral to the programme and were part of the evaluation – notably through Evaluation Question (EQ) 5.1 which directly addresses equity. The BHB programme prioritised gender equity and poverty to improve health outcomes for underserved populations, especially women and children in disadvantaged regions. The evaluation assessed how these considerations are embedded in the programme's TA interventions and their impact on outcomes. Key areas include: (1) the midwife deployment and capacity-building and their role in improving maternal and newborn care services; (2) efforts to enhance sexual and reproductive health rights (SRHR), particularly in reducing disparities in service delivery for women and adolescent girls in vulnerable communities; and (3) gender-sensitive governance reforms, such as workforce policies and practices that support female health professionals. Data were gathered from secondary documents and key informant interviews (KIIs).
The evaluation also examined how the programme addressed the needs of economically disadvantaged populations by targeting interventions in high-poverty regions, supporting equitable resource allocation, enhancing access to essential health services for low-income groups and strengthening financial protection mechanisms. Poverty-focused analyses used secondary data on regional disparities and stakeholder discussions, notably those with government officials.
The evaluation focused on two TA components, service delivery and governance, to improve health systems, rather than the entire programme. While issues like human rights and environmental sustainability are crucial cross-cutting themes in development, they were not primary drivers in the TA. Due to a tight timeline and budget, the evaluation aligned with the programme’s original objectives, concentrating on measurable system and governance improvements, rather than broader systemic issues.
The evaluation took place between December 2024 and March 2025. As the evaluation was commissioned to inform BHC-Dhaka learning and feed into the PCR and design of subsequent support to the health sector, the findings are time critical. Due to issues around budget reorganisation and procurement processes (a separate budget for evaluation was cut as part of budget reallocations due to COVID-19), activities had to completed by the end of March 2025 to meet FCDO’s financial year deadline. The potential risk of this timeline was mitigated through a strong local team that combined considerable technical experience in the proposed methods and access to key stakeholder networks.
## Use, influence and dissemination
The primary audience is MOHFW, BHC Dhaka and UK FCDO more widely. The secondary audiences include UNFPA, MSH, development partners, donors and other stakeholders working toward achieving Universal Health Coverage by 2030, as the report could provide insights for informing future health programming and policy development. A Use and Influence Plan that sets out our approach for disseminating the findings and lessons from this evaluation was developed during the inception phase and is presented in Annex 3: Use and influence plan. The plan details the key outcomes expected from stakeholder engagement with findings, and the tailored dissemination methods designed to promote this engagement. Specific activities include an internal event, external event, publication of a two-page summary and targeted distribution of the full report.
As planned, the evaluation team shared preliminary findings and lessons with BHC Dhaka to receive initial feedback, then shared the draft report, incorporating feedback into the final report. A dissemination event was held on 20th March 2025 to share findings and recommendations with a wider range of key stakeholders (BHC Dhaka, MOHFW, UNFPA, MSH, WHO). In line with FCDO policy, the two-page executive summary will be made publicly available on-line.
The evaluation findings are already being used to inform the PCR – the lead PCR reviewer attended the meeting to share the findings and recommendations. The findings will also inform the UK’s future health programming and policy influencing priorities in health in Bangladesh. BHC Dhaka intends to use the findings to engage with the government of Bangladesh and other development partners regarding future interventions. BHC Dhaka is the Co-Chair of Bangladesh's Development Partners Consortium for Health, Population and Nutrition (DPC-HPN) and is therefore strategically well-placed to continue to monitor the impact of this evaluation on wider health systems in Bangladesh.
# Evaluation approach
This section summarises our evaluation design. It covers our evaluation questions, overall approach, data collection and analysis methods, management approach, and key evaluation limitations and mitigating strategies.
## Evaluation overview
The primary purpose of evaluating the BHB programme is learning that can inform and strengthen future health programming, policy and institutional governance of the health sector in Bangladesh. The evaluation adopted a utilisation-focused and mixed-methods design, comprised of quantitative analysis of available and relevant secondary data, qualitative data collection through Key Informant Interviews (KIIs) and visits to the districts of Bagerhat and Gaibandha. The major deliverable of the evaluation is this final evaluation report, accompanied by a 2-page summary of the finalised evaluation report for publication on the FCDO website.
## Evaluation questions
The evaluation was guided by a set of evaluation questions (EQs) that were derived from the original ToR and refined during the inception phase (particularly for the VfM relevant questions), based on discussions with BHC Dhaka. The evaluation questions below are the original evaluation questions presented in the ToR and were developed to assess the relevance, effectiveness, efficiency, equity and sustainability of the programme. The proposed evaluation questions relate to the Organisation for Economic Co-operation and Development's (OECD) Development Assistance Committee (DAC) Evaluation Criteria on relevance, effectiveness, sustainability, and efficiency. The full evaluation framework, with expanded evaluation questions, data sources, and analytical methods used for each question, can be found in Annex 4: Evaluation framework and questions.
1. Relevance:
1.1 To what extent has the TA responded to the priorities and policies of the HPNSP (2017-2024)
1.2 What are the recommendations for improvement to help inform BHC Dhaka’s next health programme in Bangladesh (if any)?
2. Effectiveness:
2.1 To what extent did the TA achieve the intended outcomes (as set out in the logframe and ToC)?
2.2 What were the key factors contributing to the successful achievements?
2.3 Was TA the most appropriate intervention or would others have been more appropriate?
3. Sustainability:
3.1 What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?
3.2 What evidence is there that the benefits of the TA will be sustained?
4. Efficiency:
4.1 How effective were the various TA interventions compared to the cost of the respective TA?
4.2 Did the programme achieve good VfM?
5. Equity:
5.1 How has the programme addressed aspects of gender equality, equity, poverty and inclusion?
## Methods
The methods summarised in Table 1 below followed the plans presented in the Inception Report and are described in more detail in Annex 5: Methods. The evaluation team applied a mixed-methods approach, ensuring a comprehensive analysis of purpose, application, and outputs. The team conducted document review, key informant interviews (KIIs), secondary quantitative data analysis and field observations, logframe and TOC review, case studies and VfM analysis. The document review and KIIs provided the bulk of the information and most of the EQs were answered using this data. Quantitative secondary data analysis was used to answer EQ 2.1 (extent to which the programme achieved the intended outputs) and EQ 4.2 (VfM analysis) and to triangulate findings from the qualitative analysis. Field observations enriched the evaluation by offering contextual insights into programme implementation and on-the-ground realities. While the tight timeline constrained comprehensive pre-testing of tools, the team ensured that first draft interview guides were assessed after initial interviews and open-ended questions streamlined for ease of use. Annex 6: Interview guide and checklists.
Methods	Summary description
Document review	A document review of 45 reports, documents and project write-ups was the main approach to understanding programme context, activities and coverage and was the major data source to address the EQs. Programme documents were provided by BHC Dhaka and programme partners, augmented by peer-reviewed literature on costings for the VfM analysis. The list of documents reviewed is included in Annex 7: Document review matrix.
Logframe and ToC Review	The evaluation team reviewed the ToC and logframe. While the ToC provided a useful high-level overview of the programme as a whole, the team based their analysis of how the programme aimed to achieve change – its expected change pathways – on the logframe. This offered a more structured and operational framework to assess these intended pathways (Annex 13: Logframe 2018-2024, Annex 8: Understanding the relationship between BHB outputs and outcomes). The team conducted a comprehensive review of progress against expected outputs and outcomes – including revisions, changes to milestones, and the integration of emerging priorities Annex 14: Reasons for revisions of logframe indicators as reported in 2024 logframe). Interviews with BHC Dhaka, UNFPA, and MSH shed light on how the logframe was used in practice and revealed any gaps between planned and actual implementation.
Key Informant Interviews (KIIs)	KIIs were the main method to collect qualitative data. KIIs captured the experiences and perspectives of those closely involved with the programme. Interviews were conducted individually or in groups, based on informant preference. Semi-structured interview guides with open-ended questions were tailored to different informant groups. Interviews were conducted in person or remotely using interviewees preferred language (Bangla or English). / As per the Inception Report, the evaluation team used a purposive sampling approach. The team focused on engaging stakeholders and key informants from relevant organisations and sectors with expert knowledge and close involvement in the programme's key components. Initial interviews with the FCDO and programme partners’ staff (UNFPA and MSH) helped identify appropriate stakeholders. Snowball sampling was utilised to enable informants to suggest other relevant stakeholders for interviews but no further external or independent stakeholders emerged through this process. / A total of 58 key informants were interviewed (Annex 9: Key informants interviewed). While efforts were made to ensure gender balance in the selection of key informants, respondents were primarily identified based on their official roles, institutional affiliations, and expertise relevant to the BHB programme. Overall, there was a relatively even balance between genders overall at 30 men and 28 women. However, there was an observable difference between gender balance at central/Dhaka level and field level. This is reflective of the reality that many field level health workers, particularly midwives, are female while more senior management roles are more often occupied by males.
Secondary Data Analysis (Quantitative)	To track programmatic trends over time and complement KII findings, the evaluation team, including the VfM expert, conducted secondary data analysis. Quantitative analyses mainly used the most current logframe data that was provided by FCDO and approved for their annual review. Logframe data is populated by different data sources (DHS, District Health Information System 2 (DHIS2) and programme data). The team additionally received programme data from UNFPA, but identified some inconsistencies and data quality issues. Cross-verification of sources such as programme data and logframe data yielded some inconsistencies. As a result, the team decided to mainly use logframe data. While the inconsistencies were relatively minor, because it was not possible to cross-verify with actual DHIS2 data the team agreed not to use programme data extensively but use it only to provide additional insights to complement data from other sources. MSH-related data was extracted from the programme completion report. / Quantitative data was mainly applied for descriptive and trend analysis. Quantitative data (such as increase in the number of deliveries, cervical cancer screening, pharmacy staff trained, pharmacy licensing etc.) was also used to verify qualitative data from KIIs.
Field observations	Field observation sites were selected purposively after discussions with FCDO. Emphasis was given to visit south of the country (Bagerhat) and north (Gaibandha) and to visit specific areas; Green Health Initiative in Mongla and Sampara Upazila Health Complexes (UHC) for Santal population (Annex 2: BHB programme coverage). The Green Health Initiative also informed one of the case studies. Field observations included district hospitals, UHCs, a maternal health facility and a Nursing and Midwifery Training Institute in Bagerhat and pharmacies. The team conducted KIIs with administrators, doctors, nurses and midwives. In Mongla Upazila in Bagerhat district, the team visited a BHB-funded UHC that transitioned into a Green Health Initiative. In Gaibandha, the team visited a Sampara UHC serving Santal populations (indigenous population), where midwives from the community had been trained with BHB funding.
Case studies	During discussion with the key respondents from FCDO, UNFPA, Directorate General of Health Services (DGHS) and Directorate General of Nursing and Midwifery (DGNM), the team identified two noteworthy cases: the Green Health Initiative and Midwifery-Led Care (MLC). The evaluation conducted case studies for these two initiatives, taking data from document review, field observations and discussions with the respective health managers and service providers. (Annex 10: Case study: Green Healthcare Initiative at Mongla Upazila Health Complex Annex 11: Case study: Midwifery-led care (MLC) model under the BHB programme)
Value for Money	VfM assessment was conducted using FCDO’s four-pillar VfM framework, evaluating the programme’s performance in terms of economy, efficiency, effectiveness, and cost-effectiveness. The assessment relied on programme reports, logframe, financial and procurement data, and service delivery data. Analysis included application of the Lives Saved Tool (LiST) to estimate maternal and neonatal deaths averted; Disability-Adjusted Life Years (DALYs) approach to estimate health benefits; Cost-effectiveness thresholds based on Bangladesh’s GDP per capita (US$2,057). / Annex 12: Value for Money assessment provides a detailed description of methods used. The methodology acknowledges that not all outcomes can be solely attributed to the programme. Services like Basic Emergency Obstetric and Newborn Care (BEmONC) rely on broader health system inputs not funded by the project. A financial contribution-based attribution approach was used to estimate the programme's share in observed impacts – such as deaths averted and economic benefits. The VfM expert conducted his own assessment, but collaborated closely with the team. The team leader attended interviews for the VfM assessment with the VfM expert.

Table 1: Summary of the methods used in this evaluation
## Data analysis
Triangulation enhanced the validity and reliability of findings by integrating data from document reviews, field observations, KIIs and secondary quantitative analysis. This ensured a comprehensive evaluation by cross-verifying evidence from multiple sources.
Qualitative analysis
Qualitative data from KIIs and field observations was analysed using thematic analysis to address key evaluation questions. After translation and transcription, codes were generated using Atlas.ti software and themes identified within the evaluation framework. Insights and perspectives gathered through KIIs were verified and supplemented with information from document reviews and quantitative analyses whenever feasible. Transcribed summaries of KIIs were disaggregated by type of respondents (Government, TAs, district and sub-district level officials, service providers).
The document review followed the same thematic framework, ensuring alignment with qualitative findings. It provided valuable context by examining programme details, published data (secondary sources) and historical progress and challenges. The findings were integrated with qualitative insights from KIIs to develop a holistic understanding of the programme’s impact. Additionally, documents were examined for quantitative data to support and corroborate qualitative evidence. The evaluation team also explored (mainly from the document review) how the interventions included gender, socio-economic (hard-to-reach, marginalised population), and location (urban/ rural areas) dimensions.
Quantitative analysis
The team analysed quantitative data from secondary sources to assess the programme achievements over time. Quantitative analysis was not the main approach to addressing the evaluation questions but was intended to support and triangulate the findings of key informants’ interviews as well as to inform the VfM assessment. The team mainly applied logframe data that was shared by FCDO and approved in FCDO’s Annual Review. Analysis focused on simple descriptive and trend analysis; no statistical testing or advanced analysis on correlation was performed. The evaluation team and the VfM expert worked from the same data sources to ensure consistency. The analysis and data visualization were conducted using Excel.
Logframe data was the main source of data used for quantitative analysis, which is populated using various data sources including routine programme data, DHIS2, and Bangladesh Demographic and Health Survey (BDHS) and Sample Vital Registration System (SVRS) data. The logframe is conceived as a living document to help drive programme performance and was revised several times during implementation. The team used FCDO’s most recent logframe for analysis, which was reviewed and approved for the final BHB Annual Review. This version is attached as Annex 13: Logframe 2018-2024. A table summarising the reasons for changes to indicators over time is provided in Annex 14: Reasons for revisions of logframe indicators as reported in 2024 logframe.
In addition to logframe data, the team received additional programme data directly from UNFPA in Excel format, which was applied to explore additional indicators beyond those available in the logframe. During the data review, the team identified some quality issues with programme data. To understand and address these, the team leader communicated frequently with the UNFPA data focal point to clarify inconsistencies and better understand the challenges in data collection and reporting. Programme data from facilities is reported by health facility staff (nurses, midwives, etc.), which was a steep learning curve for them, especially in the early years of the programme. After discussion, the team agreed programme data provided insights into important activities such as midwives’ service delivery that were not fully reflected in the logframe indicators and thereby offered useful contextual understanding. However, as a result of the limitations identified, the team agreed to use programme data to only a limited extent to triangulate findings from qualitative data.
Strength of evidence
Annex 15: Ranking strength of evidence analyses the strength of evidence for each research question. Overall, evidence strength was rated as STRONG or MODERATE to STRONG. The interviews with key stakeholders, including BHC Dhaka, helped understand the programme, provided relevant background information and essential documents, refined the evaluation questions, and identified some key informants. Subsequent interviews with the stakeholders, including MOHFW, UNFPA, MSH, WHO, DGHS, DGNM and Directorate General of Family Planning (DGFP), facilitated in-depth understanding of achievements, challenges, key issues, and building emerging insights. The desk review contributed valuable context by examining programme details, accessing published data (secondary sources) and assessing historical progress and challenges. Field observations, guided by a comprehensive checklist and KIIs with service providers further validated and enriched the findings from the above KIIs, desk reviews and quantitative data. Together, data from these different sources provided a robust and credible foundation for the evaluation.
## Limitations and mitigation strategies
This evaluation adopted a learning-focused approach, relying primarily on qualitative data, document reviews, and descriptive analysis of secondary data. Rather than aiming to establish a direct causal link between FCDO funding and the TA outcomes, the evaluation examined plausible contributions aligned with the evaluation questions while capturing lessons learned. Table 2 below sets out the limitations and the evaluation team’s mitigation strategies.
Limitations	Mitigation strategies
Potential positive bias. While the team engaged a diverse range of respondents, all were affiliated or familiar with the programme, which may have introduced a positive bias.	The team cross-verified opinions expressed in KIIs with quantitative data and published reports and evaluations.
Recall bias. Some respondents struggled to recall specific details, particularly for activities or events that occurred several years ago leading to omission of critical insights or remembering only selective occurrences.	The team cross-verified information through document reviews and multiple interviews with stakeholders to triangulate findings.
Prearranged field observations. Due to time constraints, the team visited only two districts, with site selection facilitated by UNFPA. These visits were purposive and based on logistical convenience for the evaluation team and implementing partners. This may have caused the following biases
Non-random selection of field sites. The facilities visited may not have been fully representative of overall programme performance. It is possible that better-performing sites were chosen to showcase positive results.	The team acknowledged this limitation and counterbalanced it by engaging with a wide range of respondents and complementing with broader programme data.
Observer bias. Health facility staff were aware of the visit in advance. The presence of the evaluation team may have influenced the responses of stakeholders, particularly during field observations. Health facility staff and programme implementers might have presented a more positive picture of programme activities while downplaying challenges.	Independent, informal and where possible private conversations with providers and staff, ensuring candid perspectives. Though some level of preparedness was expected, respondents eventually felt comfortable sharing their views, including concerns regarding programme sustainability.
Generic responses from high-level officials. Some key informants, particularly high-level government officials, provided broad responses rather than specific insights.	Targeted cues and probing questions to guide informants toward more detailed and relevant answers. When responses remained high-level, the team cross-referenced information with programme documents and data to ensure accuracy and depth.
Quality and accuracy of quantitative data. Data quality, with (relatively minor) inconsistencies across sources and multiple datasets reported different values for the same indicator, potentially undermining the reliability of analysis and comparability / Programme data were provided by UNFPA, primarily reported from districts. Until 2022, many indicators were tracked using Google Sheets, posing a learning curve for field personnel (e.g., midwives and nurses). The team identified some data discrepancies between programme data and logframe data (Source: MOHFW DHIS2).	The team used mainly logframe data for quantitative analysis as logframe data are reviewed and approved by FCDO for their annual reviews. Quantitative data was used to complement qualitative analysis, which was the main source of data for this evaluation. The evaluation team identified some inconsistencies across the programme datasets shared by UNFPA. Where discrepancies occurred, data points considered unreliable were excluded from analysis. The team primarily relied on logframe data as the most consistent and structured source. / While the programme datasets had some quality limitations, including gaps and inconsistencies, the team found them sufficiently robust in key areas to offer complementary value to the logframe data and key informant interviews (KIIs). / Following internal review and discussion, the team agreed to use the programme data selectively and cautiously, drawing on it to provide additional insight where appropriate and where it could be triangulated with other sources.
Most of the data for VfM analysis was derived from programme data. Absence of a standard VfM framework across partners led to inconsistent VfM reporting. Gaps in financial data hindered granular analysis of cost drivers in the current VfM analysis.	Working closely with UNFPA led to some clarification. Despite the absence of a standard VfM framework and gaps in partner-level financial data, the VfM assessment adopted a conservative and pragmatic approach to ensure credibility. Where granular cost data were missing, the analysis focused only on well-documented and verifiable savings to avoid speculative estimations. / Where quantification was not possible, the evaluation team presented international experiences to show a possible range of outcomes. This approach allowed the assessment to generate a credible VfM narrative, while acknowledging that certain system-level and TA benefits remain partially unquantifiable. / Due to non-availability of granular data, the team were not able to analyse cost drivers.
Quantifying long-term benefits. BHB programme heavily contributed toward policy and systems strengthening, the benefits of which are often intangible. This caused difficulty in quantifying long-term benefits of TA, policy, and systems strengthening in VfM analysis.	To address this limitation, the assessment focused on interventions where measurable outcomes could be reasonably linked to the programme's contributions, such as digital system uptake, midwifery deployment, and improved regulatory compliance. For broader policy and system-level changes, a narrative-based approach was used, supported by qualitative evidence (e.g. enactment of the Drug and Cosmetics Act 2023, institutionalisation of digital tools like ADLRS and PMS). This ensured that while not all benefits could be monetised or fully attributed, the VfM analysis still recognised the foundational role of BHB’s TA in enabling sustainable, system-wide improvements.
Capturing the complexity of the BHB programme. Given BHB’s extensive scope, it was not feasible to capture all nuances within the limited timeframe.	To ensure comprehensive coverage, the team conducted document reviews, engaged a diverse set of stakeholders (snowball methods helped) and triangulated findings across multiple sources. While some finer details may not have been captured, the evaluation provides a well-rounded analysis of the TAs' contributions.
Evaluation did not reach or gather insights from primary service recipients, such as women who received delivery services at health centres, those screened for cervical cancer, or individuals who purchased medicines from pharmacies. Direct perspectives from end-users, could have provided critical insights into their experiences, satisfaction, barriers to access, and the overall effectiveness and/or quality of the interventions. This gap limits the evaluation’s ability to fully understand key demand-side factors influencing service utilisation and health outcomes.	Due to the time constraints and the considerable challenges in getting appropriate ethics approval, it was not feasible to reach primary service recipients. At the inception phase, it was decided not to include service recipients and that the EQs could be responded to through the proposed methods.

Table 2: Limitations and mitigation strategies
Managing risk
A risk matrix for the evaluation is included in Annex 16: Risk description and mitigation. The tight timeline (March 31, 2025) was identified from the start as a risk. Mitigation strategies ensured the evaluation team executed the proposed activities as planned. Time constraints put extreme pressure on the team, which, though impacting minimally on core research and analysis, constrained time for review and revisions.
## Governance and management
Governance
The evaluation was overseen by a BHC Dhaka programme team, specifically the BHB Programme Responsible Owner (PRO) and Senior Responsible Owner (SRO). This team was responsible for approving evaluation outputs and commenting on draft reports, alongside EQuALs quality assurance reviews. The PRO is responsible for leading the evaluation management response and implementing agreed recommendations. The team could work freely to derive and present findings and recommendations without interference. No conflicts of interest were identified among team members.
Team structure
Figure 3 below sets out the team structure, governance and management arrangements.
DAI UK office support:
Project Director: Cathy Shaw
Project Manager/Research Assistant: Michelle Wong
Evaluation Quality Assurance: Charlotte Maugham/Charlotte Laurence
Project Accountant: Zia Ur Rahman

Halcyon office support
VfM Quality Assurance: Rob Wood
DMA: In-country research delivery, management and data analysis

Figure 3: BHB Evaluation Team organogram
Team Leader: Dr. Disha Ali (DAI consultant and US-Bangladeshi citizen based in the US, though located in Bangladesh for the duration of the evaluation) was responsible for overall assignment deliverables; planning and coordinating the inputs from team members. She was the core team’s primary point of communication with the clients and led delivery of the final evaluation report and final dissemination products.
Evaluation Technical Lead: Foyzul Bari Himel (Halcyon consultant based in Bangladesh) conducted stakeholder consultations; field observations; coordinated and led other in-country researchers; provided advice on the MEL approach; technical support to develop tools; drafts and finalise reports.
Data Analyst: Hasib Reza (DMA employee based in Bangladesh) supported the coordination of interviews, organised the findings from KIIs/coding, organised secondary data, conducted data analysis, and ensured data validity and reliability.
Value for Money Expert (VfM): Afeef Mahood (Halcyon consultant based in Pakistan) led the Value for Money (VfM) analysis, which assessed the cost-effectiveness and efficiency of TA interventions and their alignment with budgeted outcomes, working especially closely with the Team Leader and the Data Analyst to assess financial metrics and cost indicators. After his analysis was completed, the team worked together to incorporate his findings and recommendations into the main report.
Project Manager/Research Assistant. Michelle Wong (DAI UK office) was responsible for overall project management, supporting evaluation activities and data analysis, and assisting with copy editing and formatting deliverables.
## Ethics and safeguarding
The evaluation adhered to FCDO’s ethical standards, which served as the guiding framework for obtaining informed consent, conducting interviews, maintaining informant confidentiality, ensuring data protection and disseminating findings to relevant stakeholders so that they benefited from the evaluation process.
[note] DFID ethical guidance for research, evaluation and monitoring activities
The evaluation design and implementation, particularly discussions and interactions with KIIs, adhered to Bangladesh's socio-economic, cultural, and political context. No community members were interviewed (only health sector employees at different levels or business owners), so there was no need for formal approval from an ethical review board.
Given that the on-site evaluation team is of Bangladeshi background, language and cultural barriers are naturally mitigated. However, the team recognises the hierarchical dynamics that may exist between urban-based evaluators and respondents from provincial areas. Evaluators remained mindful of these dynamics and ensured all respondents – regardless of position or background – were treated with respect, openness and appreciation for their work and responsibilities.
Safeguarding measures were implemented to ensure the principle of ‘do no harm’ was delivered throughout and to address potential power imbalances. Interviewees were interviewed online or in their organisation’s offices. In scenarios requiring heightened sensitivity, for example when interviewing young midwives in maternity-related hospital settings (e.g. antenatal clinics), interviews were conducted by the female Team Lead alone. Facility administrators or management staff who could influence, intimidate, or inhibit respondents were not allowed to participate in sensitive interviews.
As part of the ‘do-no-harm' policy of ethical considerations, the evaluation team did not disclose the names of the pharmacies and drug stores participating in the evaluation to respect their wish to remain anonymous and avoid revealing potentially commercially sensitive information about their business.
Informed consent was obtained verbally before initiating interviews. To protect participant confidentiality, audio recordings and transcriptions were securely stored in a Microsoft (MS) SharePoint folder, with restricted access limited to team members directly involved in data collection and analysis.
# Evaluation findings
This section presents our evaluation findings relating to the EQs for relevance, effectiveness, sustainability, efficiency and equity. Each sub-section summarises findings to individual questions in table form, before providing a deeper analysis. The strength of evidence to support findings to questions is also provided, though a fuller description is presented in Annex 15: Ranking strength of evidence. EQ 1.2 is a specific request for recommendations, which are therefore presented in the recommendation section rather than described here.
## Relevance
#### EQ 1.1: To what extent has the TA responded to the priorities and policies of the HPNSP (2017-2024)?
Strength of evidence: STRONG
Table 3 below summarises key findings, followed by a more detailed narrative analysis.
EQ 1.1: To what extent has the TA responded to the priorities and policies of the HPNSP (2017-2024)?
BHB TA aligned effectively with national health priorities. The BHB programme aligned with the strategic objectives of the GoB’s 4th HPNSP (2017–2024), strengthening healthcare governance, addressing inequities, and advancing Universal Health Coverage through targeted TA. / TA contributed to expanded access to healthcare services, particularly in underserved regions. Interventions included scaling up midwifery services, strengthening pharmaceutical governance and deploying digital tools to enhance healthcare system efficiency and transparency. / TA demonstrated flexibility in responding to evolving health challenges, particularly during the COVID-19 pandemic and floods. / TA contributed to strengthened health systems, through regulatory improvements, digital health strategy development, supply chain management enhancements, and accreditation of retail pharmacies. BHB’s support in developing the ADLRS (online licensing and accreditation software) has been groundbreaking.

Table 3: Summary of EQ 1.1 findings on relevance
BHB TA aligned effectively with national health priorities.
The design of the BHB programme represents a deliberate and strategic effort to address systemic health challenges in alignment with the government of Bangladesh's (GoB) priorities and policies. Specifically, the programme demonstrated strong alignment with the priorities and policies of the 4th HPNSP (2017-24), effectively addressing systemic health challenges and strengthening healthcare governance. By integrating targeted TA into the overall national programme, BHB contributed to expanding skilled birth attendance, improving pharmaceutical governance, and enhancing digital health solutions. Its responsiveness to emerging health sector needs, including COVID-19 pandemic response and climate-focused initiatives, further underscores its adaptability and relevance to the 4th HPNSP.
TA contributed to expanded access to healthcare services, particularly in under-served regions.
BHB’s direct support to the 4th HNSP indicates its relevance to stronger healthcare governance, addressing service delivery inequities, and advancing Universal Health Coverage. By integrating targeted TA, the programme has effectively supported the government’s broader health policy objectives.
Its focus on MNCAH, capacity building and governance reform demonstrates a comprehensive approach to addressing key challenges in the health system. For instance, the programme’s initiative to scale up midwifery services directly contributed to increasing skilled birth attendance rates, particularly in underserved regions where access to such care was previously limited.
By expanding the health workforce and improving service delivery in underserved regions, the programme made considerable strides in increasing access to quality healthcare. Integrating digital tools such as DHIS2 and ADLRS enhanced the efficiency and transparency of health system operations, aligning with HPNSP’s goal of systemic strengthening. This finding is supported by the 4th HPNSP evaluation, which highlighted that efforts to update drug laws, strengthen staff capacity, and establish Model Pharmacies and Model Medicine Shops were aimed at promoting rational drug use and improving service quality. Moreover, the programme’s targeted efforts to reduce regional disparities ensured that the benefits of a strengthened health system were equitably distributed, addressing the HPNSP’s emphasis on reducing health inequities.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
Interventions targeted to pharmaceutical governance, such as developing and implementing the ADLRS, accreditation of retail pharmacies and promotion of Good Pharmacy Practices (GPP), ensured safer, higher-quality medicines reached the population and addressed systemic inefficiencies in drug administration. Such efforts aligned with HPNSP’s goals of improving system efficiency, transparency, and accountability.
The 27 TA interventions under the BHB programme as part of the flexible TA modality were critical in facilitating implementation of key HPNSP operational plans. Workforce development was a cornerstone of this effort. Deployment and training of midwives addressed critical gaps in MNCAH service delivery. These initiatives directly supported the operational goals of increasing skilled birth attendance and reducing maternal and neonatal mortality rates, particularly in regions with historically poor health indicators. Additionally, TA to the DGDA strengthened pharmaceutical governance, a priority area within the HPNSP. By improving the regulatory environment for medicines and tackling issues such as AMR, the programme advanced the operational plans related to drug safety and public health.
TA demonstrated flexibility in responding to evolving health challenges
A hallmark of the BHB programme’s design was its ability to adapt to evolving health priorities in Bangladesh. During the COVID-19 pandemic, the programme’s TA shifted focus to support emergency response efforts. This included vaccine deployment, strengthening infection prevention protocols and building healthcare capacity in highly affected areas. The rapid reorientation of activities during the pandemic illustrates the programme’s agility in addressing emerging challenges while remaining aligned with broader health objectives.
Beyond the pandemic, the programme addressed longer-term issues by integrating global health priorities such as the intersection of climate change and health. This approach ensured that Bangladesh’s health system was responsive to immediate crises and prepared to tackle future challenges. By embedding flexibility into its design, the programme demonstrated an understanding of the dynamic nature of health policy and need for adaptive strategies.
TA contributed to strengthened health systems
The design of the BHB programme was intentionally responsive to the specific needs of local health systems, particularly in underserved and high-need areas. According to the 4th HPNSP evaluation, one of the most impactful interventions was the deployment of midwives to remote Upazilas, ensuring that women in these regions had access to skilled birth attendants.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
The programme also scaled up cervical cancer screening services in low-performing regions, providing early detection and treatment opportunities for women who previously lacked access to such care. This improved health outcomes and built trust in the healthcare system among marginalised populations. Moreover, the accreditation of retail pharmacies and the training of medicine dispensers ensured the availability of safe and effective medicines, further strengthening the quality of care in underserved areas.
Efforts to enhance supply chain mechanisms were another critical aspect of the programme’s design. By ensuring the timely delivery of essential medicines and reducing stockouts in remote regions, the TAs improved the reliability of healthcare services. The focus on strengthening health information systems, particularly at the local level, empowered regional health governance structures to allocate resources more effectively and prioritise interventions based on real-time evidence. This holistic approach addressed immediate needs and systemic weaknesses, creating a more equitable health system. Annex 17: Matrix showing relevance with priorities of BHB with 4th HPNSP shows examples of activities aligned with 4th HPNSP’s key strategies that BHB supported.
#### EQ 1.2: What are the recommendations for improvement to help inform the next FCDO’s programme in health (if any)?
Strength of evidence: STRONG
See Recommendations

Effectiveness
#### EQ 2.1: To what extent did the technical assistance achieve the intended outcomes (as set out in the logframe and ToC)?
Strength of evidence: MODERATE TO STRONG
Table 4 below summarises key findings, followed by a more detailed narrative analysis.
EQ 2.1: To what extent did the TA achieve the intended outcomes (as set out in the logframe and ToC)?
Logframe indicators demonstrated acceptable progress between 2018-2024. According to 2024 data, skilled birth attendance and use of modern family planning exceeded targets, demonstrating progress in maternal and child health. / Analysis of programme (service delivery) data demonstrated that BHB TA contributed towards improvements in service delivery. This included full digital health management implementation, no essential medicine stock-outs and increased midwife availability: / Increased proportion of deliveries conducted by midwives (54% in 2019 to 91% in 2024). / About 1.4 million women screened for cervical cancer over the life of the project, though the number declined in 2024 from 2023. / More than 14,000 dispensers were trained over the programme’s duration, with all 10,000 targeted medicine shops receiving accreditation. / There is evidence of effectiveness beyond the logframe indicators. These include: / Policy advancements and regulatory reforms. / Health system strengthening. / Cross-sectoral collaboration and partnerships. / Training and mentorship of faculty members for midwives advanced midwifery autonomy. / Model pharmacy approach had an effect beyond project pharmacies. / Flexible TA was responsive to MOHFW’s evolving needs enabling them to adapt to changing contexts. / Despite the successes of BHB’s flexible TA, several challenges were identified in coordination and implementation. Frequent leadership changes within government agencies disrupted TA continuity. Limited follow-up mechanisms for research-based interventions led to underutilisation of research findings in policy formulation.

Table 4: Summary of EQ 2.1 findings on effectiveness
Logframe output indicators demonstrated acceptable progress between 2019-2024
The evaluation team assessed the effectiveness of the BHB programme by examining its success in achieving planned outputs and outcomes. This included a review of logframe indicators, see Annex 13: Logframe 2018-2024 and Annex 18: Achievement against outcome and output indicators of logframe in 2024
Impact indicators: While impact indicators were not critically analysed, the team reviewed the indicators reported from BDHS and SVRS data. Table 5 below shows achievement against BHB impact indicators. The findings indicate a steady decline in the Maternal Mortality Ratio (MMR), with a larger reduction in 2023. However, the Total Fertility Rate (TFR) showed a rising trend and remained off target. Neonatal mortality rate and prevalence of under-5 stunting met the targets.
Indicator		2019	2020	2021	2022	2023	2024
Maternal mortality ratio (MMR) per 100,000 live births	Target	174	174	160	160	160	160
	Achieved	165	163	163	163	156 (SVRS)	136 (SVRS- 2023)
Total Fertility rate (TFR; per woman)	Target	2.3	2.3	2.1	2	2	2
	Achieved	2.04	2.04	2.04	2.04	2.15 (SVRS)	2.17 (SVRS- 2023)
Neonatal mortality rate (NMR; per 1000 live births)	Target	25	24	24	24	20	20
	Achieved	30	26	26	26	20 (BDHS)	20 (BDHS)
Prevalence of stunting among children under 5 years of age;	Target		32%			28%	24%
	Achieved		31%	28%		24% (BDHS)	24% (BDHS)

Table 5: BHB Impact Indicators
Source: Logframe indicators from Annual Review 2024

Outcomes and output indicators:
Figures 4 and 5 below illustrate the percentage achievement of outcome and output indicators, which shows mainly cumulative achievement over the period of BHB programme’s life. These same figures are also presented in the VfM evaluation under ‘efficiency’ and ‘effectiveness’ in Annex 12: Value for Money assessment. The indicators mostly met or exceeded targets at the end of the programme period, as shown in Annex 18: Achievement against outcome and output indicators of logframe in 2024. While outcome indicators reflect the programme's overall direction at the national level, they are not exclusive to BHB districts. Broader political, developmental, and socio-economic contexts are likely to influence them. In contrast, output indicators are more directly linked to programme implementation, providing more direct measures of effectiveness in meeting maternal and delivery care targets and good pharmacy practices. An analysis of the linkage between outcome and output indicators is presented in Annex 8: Understanding the relationship between BHB outputs and outcomes.

Figure 4: Effectiveness according to Output Indicators in 2024
Source: Logframe indicators from Annual Review 2024
Output 1.1: Number of childbirths attended by skilled birth attendants [in 20 BHB districts]; Output 1.2: Number of childbirths attended by skilled birth attendants in Sylhet, Barishal and Chittagong divisions; Output 1.3: Number of total Family Planning (FP) Users (modern methods); Output 1.4: Number of under five children received vitamin-A supplementation, annually; Output 1.6: Number of service providers and community leaders trained to cope with climate and other shocks; Output 2.1: Number of sub-district health facilities (Upazila Health Complexes (UHCs)) with at least two licensed midwives; Output 2.2: Number of public health facilities meeting facility readiness criteria for delivering post-partum FP services in Sylhet and Chittagong divisions and 20 BHB districts; Output 2.3: Number of health facilities (Medical College Hospitals (MCH), District Hospitals (DH), UHCs) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer; Output 2.5: Number of medicine dispensers trained on GPP; Output 3.1: Number of targeted medicine shops accredited; Output 3.2: Number of retail medicine shops, licensed/ license renewed, by DGDA using automated licensing and renewal system .

Figure 5: Effectiveness according to Outcome Indicators in 2024
Source: Logframe indicators from Annual Review 2024
Outcome 1.1: Percentage of births attended by skilled providers and ratio of births in facilities by poor to rich women; Outcome 1.2: Contraceptive Prevalence Rate (CPR) for modern methods (all women); Outcome 1.3: CPR for modern methods in Sylhet and Chittagong divisions (lagging behind areas); Outcome 1.4: % of newborns received essential newborn care (at least 2 postnatal signal function care within 2 days of birth); Outcome 1.5: Percentage of tuberculosis (TB) cases remaining un-detected; Outcome 1.6: Number of women screened for cervical cancer; Outcome 2.1: Percentage of district health facilities (#40) using digital systems to manage assets; Outcome 2.2: Percentage of health facilities reporting no stock-out of essential medicines; Outcome 2.3: Percentage of accredited medicine shops with improved dispensing practises as per national guidelines (Source: Unpublished study. “Assessing Good Pharmacy Practices in private medicine shops in selected districts of Bangladesh” by Dr. Iqbal Anwar, Consultant, BHB-MSH.)
Effectiveness of UNFPA TA on midwifery training and deployment
Midwifery training, deployment and deliveries: Programme data provided further insights on midwives trained and deployed in addition to progress towards logframe indicators. BHB worked with development partners such as the Swedish International Development Cooperation Agency (SIDA) at the policy level to create posts and deploy midwives. In addition to deployment, BHB supported continuous professional development for midwives through mentoring, ensuring they remained updated on evidence-based maternal care practices. DGNM was supposed to recruit four midwives to all UHCs in Bangladesh, which included both BHB and non-BHB districts. However, according to some key informants, many of these positions were not filled. This finding is supported by the 4th HPNSP evaluation report, which noted the vacancy rate for midwives was 28%.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
Figure 6 below presents logframe output indicator 1.1: “Number of childbirths attended by skilled birth attendants” (SBAs). While the team could infer from logframe indicator data, KIIs and document review that the BHB programme contributed to the overall trend of increasing skilled birth attendance, it was not possible to directly attribute specific increases to BHB interventions. The evaluation team consulted UNFPA to clarify the data sources (DHIS2 and programme data) and the discrepancies between logframe and programme data on this particular indicator. UNFPA explained the differences between the logframe indicator and programme data on the number of deliveries as follows. The logframe indicator includes all deliveries, including those conducted in community (household) settings by skilled birth attendants (not by midwives). While not all community-based births are reported at nearby health facilities, some are reflected in this indicator. Additionally, this indicator applies an assumption of attributing 10% of all reported deliveries attended by SBAs in the 20 BHB districts to BHB.
Due to the difference between the logframe indicator and number of reported deliveries at health facilities in the programme data, the evaluation team did not include the programme reported number to avoid confusion. It is also important to note that verifying data accuracy or assessing the quality of DHIS2 and programme data was beyond the scope of this evaluation, as noted in the quantitative analysis and limitations sections. Through iterative communications with UNFPA, the team understood that reporting processes at UHCs, particularly by midwives and nurses, involved a learning curve. Initially, data were reported using Google Sheets before transitioning to a formal database system. Taking these factors into account, the evaluation team judged the programme data, while not without limitations, to be sufficiently robust for reporting where appropriate.

Figure 6 Deliveries attended by SBA under the BHB programme
*There was no target in 2024
Source: Logframe data [MOHFW DHIS2]
Figure 7 below demonstrates a rising proportion of normal deliveries conducted by midwives in BHB-supported districts from 54.9% in 2019 to 91% in 2024, indicating their growing involvement in supporting overall delivery care. This trend indicates increased involvement of midwives in normal deliveries at UHCs due to BHB’s midwife-led care programme which ensured presence of midwives, enhanced their capacities and possibly increased communities’ confidence and trust in midwife-led care.

Figure 7: Proportion of normal deliveries conducted by midwives out of total normal deliveries at the UHCs in 20 districts
Source: Programme data.
Figure 8 below presents an average number of normal deliveries per district per year comparing BHB and non-BHB districts based on programme data. Midwife-led deliveries have increased over the years in both BHB and non-BHB districts. The difference in the average number of normal deliveries conducted by BHB and non-BHB districts may not seem major when considered yearly, but between 2019 and 2024, the number of normal deliveries increased by 64% in non-BHB districts but by 105% in BHB districts.
While the difference in the increase of normal deliveries between BHB and non-BHB districts is worth noting, simple trend analysis alone is insufficient to demonstrate that BHB’s deployment of midwives was the sole factor driving this trend. The rise in normal deliveries across both BHB and non-BHB districts may in part reflect the broader effects of national midwifery policies, training, and advocacy efforts where BHB played an important role at the national level. KIIs with major stakeholders, including DGNM, field-level personnel, and midwives, along with document reviews, emphasised that BHB’s contributions, particularly in midwife capacity strengthening through training and mentoring, and community awareness were critical to build trust in midwives and were likely to have supported the observed increase in skilled births. These activities align with the inputs and processes outlined in the programme’s ToC, including midwife recruitment and deployment, focused training, strengthened management information systems (MIS), and enhanced supervision and monitoring. The 4th HPNSP evaluation also found that the midwife-led care approach had a positive effect on increasing skilled births. However, limitations such as data quality issues, the absence of advanced quantitative analysis, and the lack of critical insights from non-BHB areas constrain the evaluation’s ability to draw a definitive causal connection between BHB’s contributions and the observed trends
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished

Figure 8: Average number of normal deliveries per district by BHB vs. non-BHB districts (2018-2024)
Source: Programme data.

Cervical cancer screening: The BHB project, through financial and technical support, strengthened cervical cancer screening services nationwide, particularly in 20 target districts. At the national level, BHB provided coordination support to DGHS and the National Cervical and Breast Cancer Training Centre in Bangabandhu Sheikh Mujib Medical University. BHB deployed about 20 midwife field trainers to mentor and support government midwives and nurses in conducting screening and following up with patients who screened positive. A total of 379 healthcare providers, including doctors, midwives, nurses, and managers, were trained in cervical cancer-related clinical skills, including screening using Visual Inspection by Acetic Acid (VIA), between 2019 and 2024.
Figure 9 below presents the total number of women screened for cervical cancer mainly in 20 BHB districts (15% and 10% of cases from other districts were also included in the total for 2023 and 2024 as per the logframe data). About 1.46 million women were screened for cervical cancer in 20 BHB programme (2018-2024), exceeding the target every year and the cumulative target of 1,000,000. The years 2022 and 2023 demonstrated high performance. This might be due to targeted campaigns aiming to raise awareness and uptake of the services. The programme did not set any target for 2024, but the number of women screened declined substantially from 2023 to 2024 (more than 100,000).
[note] This total includes an additional 67,474 who women were screened in 2018, thus slightly higher than what is reported in the final logframe Annex 13: Logframe 2018-2024.

Figure 9: Total number of women screened for cervical cancer showing achievement against target (2019-2024)
*There was no target for 2024.
Source: Logframe data (Outcome indicator 1.6). Note: the data include 20 target districts and additional screenings
Figure 10 below compares BHB and non-BHB districts in terms of the average number of women screened per year per district based on programme data. Between 2019 and 2023, the average annual number of women screened for cervical cancer increased in BHB and non-BHB districts, mainly in BHB districts. The average number of women screened per district in BHB districts increased from 7,616 in 2019 to 16,199 screenings until 2023, demonstrating effective implementation and sustained improvement. Non-BHB districts (N=44) also experienced a steady increase. The increase in cervical cancer screening across BHB and non-BHB locations over the years reflects broader national improvements, possibly due to a combination of factors such as the availability of trained nurses and midwives, policies and frameworks focusing on the issues, and community mobilisations toward awareness increase.
However, the average number of women screened fell in BHB districts in 2023 and 2024 and non-BHB in 2024. During the team’s visits to the field, health facility staff cited shortages of VIA reagents, lack of referral of eligible women from other departments for screening, insufficient number of trained staff, and an overworked workforce as the major challenges in meeting targets, which may have led to the decline observed in 2024.

Figure 10: Average number of women screened for cervical cancer (BHB vs non-BHB districts) 2019-2024
Source: Programme data.

Post-partum family planning interventions: Under the BHB programme, midwives received specialized training to counsel and provide postpartum FP services after delivery. Output Indicator 1.3, related to modern family planning use, consistently exceeded its target throughout the programme's duration, as shown in Figure 11 below. The 2019 target is exactly what was achieved according to the logframe indicator. The evaluation team used this data with the assumption that there may be a minor calculation error while reporting. This number is close to what was reported in 2018 (135,794).
Between 2020 and 2023, the indicator surpassed its targets, demonstrating strong performance and high utilisation of family planning services. The programme did not assign any target for this indicator in 2024, but the number of family planning users remained high compared to the start of the programme.

Figure 11: Number of family planning users of modern methods (2019-2024): planned vs. achieved
*No target set for 2024
Source: Logframe data (Output indicator 1.3)

Governance reforms on the pharmaceutical sector: Through MSH’s targeted technical assistance to DGDA and the Pharmacy Council of Bangladesh (PCB), the BHB programme has strengthened governance, pharmacy licensing, GPP, and mitigation of AMR. The DGDA was a critical partner in implementing reforms to improve pharmaceutical regulation, policy development, and enforcement mechanisms.
Figure 12 below demonstrates targets and achievements in medical shop accreditation. According to the logframe, the programme started with a low target and increased the cumulative target each year. MSH met or exceeded its targets every year, and in 2024, it exceeded its target (103.5%), demonstrating that the pharmacies in programme areas complied with national GPP standards. Cumulatively, 10,345 retail medicine shops were accredited between 2020-2024, exceeding the target of 10,000.
The introduction of the digital accreditation process, streamlining, licensing, monitoring, and compliance enforcement have contributed to this achievement and ensured greater accountability in medicine dispensing, reducing unauthorised antibiotic sales.

Figure 12: Accreditation of medical shops: year-wise target and acheivement against targets 2020-2024
Source: MSH PCR and logframe data
Pharmacy licensing, ADLRS and Pharmacy Management Software (PMS): The MSH TA’s major contribution towards regulatory oversight was the digital transformation of pharmacy licensing and management. One major activity from BHB was establishing the ADLRS – an automated system that helps pharmacies to obtain or renew their licenses much more efficiently, avoiding the previous cumbersome manual process that took up to 45 days. This process used to incur unofficial costs. With ADLRS, licensing can be completed online within 2-5 days, eliminating middlemen and reducing costs by 92% according to MSH’s PCR. Table 6 below presents key achievements in training and digital transformation under the MSH programme. Since its implementation in 2021, ADLRS has issued 1,857 licenses, surpassing the target of 550.
MSH developed and promoted PMS designed to help medicine dispensers track medicine inventory, expiry dates, and antibiotic sales. The system is integrated with WHO's AWaRe (Access, Watch, Reserve) classification to regulate antibiotic distribution. By the end of 2024, 1,312 pharmacies adopted PMS, exceeding the 900-shop target. PMS is particularly important for AMR mitigation and rational drug use. MSH introduced red labelling for antibiotics to curb over-counter antibiotic sales, trained pharmacy professionals on AMR risks and rational prescribing, and raised public awareness campaigns, including social media outreach, community events, and digital content. Table 6 below shows the key achievements in terms of training and licensing of retail medicine shops and pharmacies.
Digital transformation/ Training	Target	Achievement (2024)
New or renewal of licence through ADLRS*	550	1,857
Number of retail medicine shops managing medicines using the PMS*	900	1,312
Number of medicine dispensers trained in good pharmacy practice*	14000	14,129
E-learning platform for professionals enrolled		25,408 (89% completed)

Table 6: Key training and digital transformation achievements by MSH
*Cumulative targets and achievements Source: MSH-PCR
Training of medicine dispensers: Training medicine dispensers and pharmacy owners was important to strengthen pharmaceutical practices. Under the programme, 14,129 dispensers were trained on GPP, AMR, and COVID-19-related issues, slightly exceeding the 14,000 target. The e-learning platform, with 25,408 enrolments and 22,492 completions (89%), provided a sustainable model for continued professional education. An independent study examined training outcomes and found that trained dispensers outperformed non-trained counterparts in:
[note] Frontiers. 2023 Assessment of the impact of good pharmacy practices training among drug dispensers in Bangladesh. Vol 14. Frontiers | Assessment of the impact of good pharmacy practices training among drug dispensers in Bangladesh
- Labelling medicines properly (63.2% vs. 53.4%, p = 0.038).
- Counselling customers on medicine use (39.1% vs. 28.6%, p = 0.021).
- Using room thermometers to maintain proper medicine storage (56.8% vs. 26.8%, p < 0.001).

Achievements beyond the logframe
In addition to logframe targets, the BHB project contributed to broader systemic improvements that fortified Bangladesh’s health system and enabling environment. While not captured by formal indicators, these achievements have been instrumental in creating sustainable, long-term health benefits. Through strategic policy engagement, capacity-building and innovation, BHB helped lay stronger foundations for healthcare delivery – ensuring that the project's contributions endures well beyond its implementation period.
Policy advancements and regulatory reforms: A key BHB success was its contribution to national health policy and regulatory improvements. The project worked closely with government stakeholders to develop and implement new standards and guidelines that strengthened the health system. For example, BHB supported the DGDA in establishing an accreditation model for retail pharmacies and medicine shops – an initiative that led to Bangladesh’s first national standards for these outlets​. This regulatory reform was groundbreaking in a country with over 150,000 licensed medicine shops (as many unlicensed) serving as first points of care​. It improved the quality of pharmaceutical services by instituting licensing criteria, training for drug dispensers and oversight mechanisms, enhancing patient safety and curbing the misuse of medicines.
BHB supported developing and refining critical national strategies, such as revising the Health Workforce Strategy reviewing the Health Care Financing Strategy and formulating the Digital Health Strategy, that provided a more coherent policy framework for improving service delivery.
Health system strengthening: Rather than delivering one-off services, the project invested in building the skills, systems and accountability needed for a resilient health system. BHB provided TA and mentorship to government health departments at national and district levels, bolstering their ability to plan, manage and evaluate health services​. This included training health managers and administrators and improving health information systems for better data-driven decision-making.
In terms of human resources, the project worked on empowering health workers through improved training curricula, mentorship, and supervision. By organising capacity-building workshops, high-level advocacy events, and tailored training courses, BHB fostered enhanced data-driven decision-making, streamlined health information systems, and improved clinical practices.
Cross-sectoral collaboration and partnerships: BHB’s achievements extended beyond the boundaries of the health sector by forging innovative partnerships and collaborative efforts across sectors. The project brought together a diverse set of partners – including government agencies, international organisations, private sector entities, and local institutions – to tackle health challenges holistically. This multi-actor partnership was evident in how BHB addressed issues like AMR and climate-related health risks. For instance, in tackling antibiotic misuse (a driver of AMR), the project worked with the health ministry and drug regulators and engaged private pharmacy owners and professional associations e.g. Bangladesh Chemist Druggist Samity, to ensure broad buy-in for the new accreditation system.
To address the health effects of climate change, BHB collaborated with environmental and disaster-management stakeholders to integrate climate resilience into health planning​. This meant that health facility plans and community health initiatives increasingly took into account disaster preparedness, clean water and sanitation – areas where coordination with other sectors is crucial. BHB also partnered with national research institutions and NGOs (such as icddr,b and others) to generate evidence and community engagement for health interventions.
Training and mentorship of faculty members for midwives advanced midwifery autonomy: BHB’s structured mentorship programme enhanced the competency and confidence of newly graduated midwives by providing hands-on training in the Thana, Upazila, and district hospitals under the supervision of medical doctors. The MLC model, implemented by UNFPA in the BHB programme, represents a foundational approach to strengthening maternal healthcare by advancing midwifery autonomy through structured mentorship and professional development (see Annex 11: Case study: Midwifery-led care (MLC) model under the BHB programme). Midwives have received training in life-saving skills (LSS), EmONC and neonatal resuscitation to enhance clinical competencies. The Life-Saving Skills in Pregnancy and Childbirth programmme, conducted in collaboration with the Obstetrical and Gynaecological Society of Bangladesh, has trained 1,217 healthcare professionals, including midwives, nurses and doctors, between 2019 and 2024​. A major milestone was the introduction of Objective Structured Clinical Assessment training for over 300 midwifery faculty members, strengthening their skills and competency evaluation mechanisms. Additionally, 1,000 midwives completed a three-month internship, and 300 received competency-based training on sexual and reproductive health (SRH)​.
Model pharmacy approach had an effect beyond programme pharmacies: The training initiative for model pharmacies has enhanced service quality and improved adherence to safe dispensing practices nationwide. The BHB programme enabled the Model Pharmacies to improve the environment within their respective pharmacies/medicine shops (e.g. temperature control with air conditioning and refrigerator, use of trained pharmacists (even if C Grade), use of labels, etc.). This practice was utilised by other pharmacies that did not have the model pharmacy accreditation. That means these practices have become standards or norms in the pharmacy business, and clients expect these to be minimum standards. During the team's visits to the pharmacies, many of the pharmacies had the ‘Model Pharmacy’ logo from DGDA. During discussions, the drug dispensers highlighted the issues of AMR, prescribing the full course of antibiotics, temperature control, etc.
Flexible TA was responsive to MOHFW’s evolving needs enabling them to adapt to changing contexts. Under MSH, the BHB programme also supported the MOHFW to implement the 4th HPNSP, assisting 31 operational plans and extending support to develop the 5th HPNSP. A total of 27 TA interventions were provided by MSH under this component. TA was designed to respond dynamically to MOHFW’s evolving needs, ensuring that support could respond to changing contexts. For example, support was provided to conduct the Bangladesh Adolescent Health and Well-being Survey, which was not originally included in the BHB programme design, but was provided because the Operational Plan did not have a budgetary allocation for this. As senior personnel from MSH noted: all flexible TA interventions were approved based on their perceived importance at the time of selection.
According to the key respondents, the flexibility in TA options has allowed for targeted interventions, by-passing the typical bureaucratic hurdles and ensuring on-time deployment of TA experts. A Planning Wing senior official of MOHFW mentioned that the programme facilitated short-term expert recruitment, overcoming bureaucratic hurdles that typically delay government hiring processes. The flexibility in drafting ToRs and engaging experts allowed MOHFW to conduct sectoral assessments, workshops and programme reviews efficiently.
Despite the successes of BHB’s flexible TA, several challenges were identified in coordination and implementation.
Frequent leadership changes within government agencies disrupted TA continuity, as indicated by one of the senior personnel from MSH: The effectiveness of these TAs was sometimes hindered by leadership transitions within MOHFW, leading to discontinuities in implementation.
Limited follow-up mechanisms for research-based interventions led to underutilisation of research findings in policy formulation, as indicated by one of the senior officials from Planning Wing of MOHFW: some of the [line directors] conducted important research with the TA funding, but we do not know what the results are or following activities or use of those researches. Another senior official from MOHFW indicated that: although the initiative brought various donor-supported TA initiatives under a common platform, allowing for more coordinated and effective resource utilisation, however, aligning DP [development partner] priorities with government objectives remained a challenge, impacting the seamless execution of TA interventions. This implies a stronger governance mechanism is necessary to ensure that donor-supported TA efforts complement national priorities rather than operate in parallel.
#### EQ 2.2. What were the key factors contributing to the successful achievements?
Strength of evidence: STRONG
Table 7 below summarises key findings, followed by a more detailed narrative analysis.
EQ 2.2: What were the key factors contributing to the successful achievements?
Agility in adapting to GoB’s evolving health priorities and changing contextual needs. Despite financial constraints, BHB strategically reprioritised activities to maintain core objectives, swiftly redirected resources during emergencies and aligned with shifting government policies to transition from service delivery to policy influence, ensuring sustained relevance in the evolving health sector. / Close collaboration with key MOHFW agencies to drive policy reforms, identify priorities and advocate for change. Regular coordination through frequent interactions, strategic placements of project officers at the respective offices of the Directorates and securing an observer role in the TA Committee (TAC) of HSD’s Planning Wing, facilitating active participation in decision-making and TA monitoring. / A data-driven approach integrating monitoring, learning and documentation systems enhanced programme effectiveness. Through integration with MOHFW’s health information systems, including DHIS2, DGFP-MIS and e-Learning Management Information Systems (e-LMIS), BHB enabled real-time data collection, analysis and evidence-based decision-making for continuous improvement. / BHB leadership at all levels and among all partners and commitment from the government and DG levels to establish strategic oversight, aligning efforts with national health goals. / Engaging with local communities increased awareness and demand for health services. Interventions focused on maternal and reproductive health, family planning and disease prevention. / Additional workforce for service delivery, supervision, monitoring and mentoring was instrumental in quality service delivery (e.g. SRHR officers, midwives, etc.). / Ensuring a consistent supply of drugs, equipment and logistics played a critical role. The e-LMIS was a major contributing factor to track drug availability and prevent stockouts of essential, life-saving supplies. / Multipronged climate change and resilience activities create a pathway to equip the country to address climate change challenges. Activities undertaken by UNFPA from advocacy at policy, academic and community levels to implementation is a novel approach for Bangladesh and provided a pathway to equip the country to address the growing climate related health challenges.

Table 7: Summary of EQ 2.2 findings on effectiveness
Agility in adapting to GoB’s evolving health priorities and changing contextual needs.
The BHB programme demonstrated flexibility and adaptability, allowing it to remain responsive to the evolving needs of the 4th HPNSP and the broader health sector landscape. The programme continuously adjusted its focus and implementation strategies to address emerging challenges, shifting policy priorities and external shocks such as the COVID-19 pandemic. This adaptability was evident in its ability to realign financial resources, modify TA approaches and integrate digital solutions to support the uninterrupted delivery of essential health services.
One of BHB's strengths was its ability to pivot in response to national health priorities and sectoral constraints. As the GoB’s health agenda evolved, BHB adapted its TA to support new and urgent needs, such as strengthening governance structures, enhancing regulatory frameworks, and improving human resource management. When financial constraints and budget reductions affected the programme, it strategically reprioritised activities without compromising its core objectives, ensuring that essential services remained a priority.
The COVID-19 pandemic further tested the programme’s resilience. BHB redirected resources to support emergency response efforts, adjusting its implementation model to expand remote training, support digital health initiatives and strengthen data-driven decision-making. This proactive adaptation enabled it to maintain momentum in critical areas such as maternal and newborn health, while contributing to pandemic mitigation efforts.
Beyond crisis response, BHB’s adaptability was reflected in its engagement with multiple stakeholders to harmonise interventions with sector-wide reforms. The programme aligned with shifting government policies, including transitioning from supporting service delivery to TA and policy influence. This helped to ensure its relevance as the health sector’s needs evolved. The ability to navigate policy shifts, funding reallocations and institutional reforms helped to solidify BHB’s role as an enabler of sustainable health sector improvements in Bangladesh.
Close collaboration with key MOHFW agencies to drive policy reforms, identify priorities and advocate for change
To ensure strong coordination, the programme had regular interactions with key MOHFW agencies and in many instances stationed UNFPA, WHO and MSH project officers within them. These officers worked very closely with the counterpart officials of these agencies and supported policy reforms, regulatory improvements, and health system strengthening efforts, ensuring that TA was tailored to evolving government needs. MSH was made an observer at the TAC of the Planning Wing of HSD, MOHFW, which ensured programme participation in TA decision-making and coordination meetings throughout the 4th HPNSP. The programme also engaged in policy dialogues and high-level coordination platforms, allowing for direct engagement with senior government officials and DPs. This close coordination with MOHFW helped to institutionalise BHB’s contributions within national structures, supporting smooth implementation and long-term sustainability.
A data-driven approach integrating monitoring, learning and documentation systems enhanced programme effectiveness.
BHB made data-driven monitoring, learning, and documentation a core strategy to achieve its objectives. By establishing robust data collection systems, real-time performance tracking and structured evaluation mechanisms, BHB enabled evidence-based decision-making that continuously refined and improved programme implementation. A key aspect of this approach was BHB’s integration with the MOHFW’s health information systems, particularly the DHIS2, DGFP-MIS, e-LMIS and other digital monitoring platforms of DGHS and DGFP. By leveraging these systems, the programme facilitated timely data collection, analysis and reporting, allowing policymakers and implementers to track progress, identify gaps and make informed adjustments. Regular joint review meetings, performance assessments and feedback loops ensured that programme activities aligned with sector priorities. BHB also institutionalised learning through structured documentation and dissemination of best practices. Annual reviews, case studies and reports captured lessons learned, challenges and innovations, providing a roadmap for continuous improvement. This iterative learning process was reinforced through knowledge-sharing sessions, stakeholder workshops, and policy/knowledge briefs, ensuring that implementation insights informed both ongoing and future health sector strategies. By integrating data-driven decision-making, adaptive learning and systematic documentation, BHB improved programme effectiveness and enabled responsive interventions.
BHB leadership at all levels and among all partners
BHB leadership at all levels and among all partners helped to drive progress, especially commitment from the government and DG levels to establish strategic oversight and align efforts with national health goals. For example, the Director General of DGDA led the ADLRS automation, streamlining regulatory processes. Additionally, Bangladesh Midwifery Society leadership trained midwives in leadership and governance, strengthening maternal healthcare services. Continuous monitoring and evaluation ensured accountability and sustainability. Strong leadership from the Additional Secretary of the Planning Wing of MOHFW enabled the TAC to approve and monitor health initiatives, which ensured efficient implementation. Moreover, WHO-supported policy workshops providing guidance to the government to track SDG health indicators and improve national healthcare strategies.
Leadership and commitment were also cited as key drivers at the district and sub-district levels. Staff interviewed at districts and UHCs consistently highlighted their authorities’ leadership and dedication toward serving their communities as their motivation to improve services. One district-level administrator and leader stated: We can’t deny our responsibility if a pregnant woman comes with labour pain at 3:00 AM. She has the right to access services whenever she comes, and it is our duty at the management level to provide such services.
Engaging with local communities increased awareness and demand for health services
Engaging and collaborating with local communities increased awareness and demand for healthcare services, particularly in maternal and reproductive health, family planning and disease prevention. Community engagement efforts, including meetings, forums and dialogues, were critical to informing the public about available health services, such as midwifery care, cervical cancer screening and adolescent health programs. When midwives were deployed at district hospitals and UHCs, some health facilities actively promoted their presence and services within the community. One health facility administrator highlighted their strategy to engage midwives in field activities, stating: It was our strategy to engage midwives in various field activities. For example, when [Maternal and Perinatal Death Surveillance and Response] programmes were done at the community level as a social autopsy, it helped establish trust for midwives within the community.
Similarly, awareness initiatives on antibiotic misuse and the importance of safe medicine were crucial in supporting AMR policies under HPNSP to promote GPP. Community discussion events, rallies with folk songs and road shows were all included in raising community awareness. Television spots were produced and broadcast to encourage medicine shop owners to upgrade their outlets. AMR awareness interventions were disseminated through social media, newspapers, YouTube and public health expert discussions. One stakeholder noted: The bad effects of the misuse of antibiotics and the need for safe medicine were advertised in the electronic media that educated both pharmacies and the general public. These awareness campaigns helped reinforce responsible antibiotic use and adherence to national AMR policies, ultimately contributing to safer healthcare practices across communities.
Additional workforce for service delivery, supervision, monitoring and mentoring
Deployment of additional workforce for supervision, monitoring and mentoring was instrumental in improving service quality. For example, UNFPA deployed SRHR Officers across 20 districts in Bangladesh who worked at the district and Upazila health level to improve SRHR services, including identifying service gaps, ensuring the availability of life-saving drugs and equipment and providing mentorship to healthcare providers that enhanced SRHR service quality. Similarly, the Family Planning Clinical Supervision and Quality Improvement Team (FPCS-QIT) was deployed in 64 districts to ensure quality of care and supportive supervision at various healthcare facilities, establishing a digital monitoring system to establish proper recording, reporting and feedback mechanisms, that enhanced the effectiveness of family planning services.
Ensuring a consistent supply of drugs, equipment and logistics played a critical role
The availability of life-saving maternal and neonatal care drugs, logistics support force caesarean-section services, emergency stabilisation kits (postpartum haemorrhage-eclampsia and Family Planning kits) and delivery kits enhanced facility readiness for maternal and neonatal emergencies, supporting safe and hygienic childbirth in healthcare facilities. For cervical cancer screening, logistics and supplies, including VIA screening equipment and colposcopy, were ensured, and service delivery and utilisation in the BHB districts were encouraged. Regular monitoring and supervision by SRHR Officers, district health managers and FPCS-QIT teams ensured proper stock management, reduced supply gaps and improved coordination among healthcare facilities. The e-LMIS was a major factor in tracking drug availability and preventing stockouts of essential, life-saving supplies.
Multipronged climate change and resilience activities create a pathway to equip the country to address climate change challenges
UNFPA’s climate change and resilience activities, from advocacy at policy, academic, and community levels to implementation, is a novel approach for Bangladesh that provides a pathway to equip the country to address the growing climate-related health challenges. UNFPA provided technical support to integrate climate change considerations into the Health National Adaptation Plan (HNAP) and advocated for including climate resilience measures in the 5th Health Sector Plan. At the academic level, UNFPA collaborated with the Government's Climate Change and Health Promotion Unit (CCHPU) and the Department of Disaster Science and Climate Resilience at the University of Dhaka, launching a course for diverse professionals. At the district level, targeted interventions were implemented in Bagerhat and Bhola, two climate-vulnerable districts, to strengthen community health resilience with targeted health care professional training. (See Annex 10: Case study: Green Healthcare Initiative at Mongla Upazila Health Complex).
#### EQ 2.3: Was TA the most appropriate intervention, or would others have been more appropriate?
Strength of evidence: STRONG
Table 8 below summarises key findings, followed by a more detailed narrative analysis.
EQ 2.3: Was TA the most appropriate intervention or would others have been more appropriate?
The TA model successfully leveraged the distinct strengths of its partner organisations. / Despite these successes, TA faced major challenges in achieving long-term sustainability and systemic integration. TA alone could not address deeper institutional inefficiencies, which require policy-level reforms. Another major challenge was the lack of supporting infrastructure and resources to maximise the benefits of TA (for example continuation of cervical cancer screening, continuation of ADLRS, PMS and other pharmaceutical-governance IT system). / Given these challenges, TA effectiveness would have been enhanced by complementary governance, regulatory and systems strengthening efforts. A more comprehensive approach that linked TA with complementary policy reforms, infrastructure development and longer-term financial commitments (for example to provide cervical cancer screening) is likely to have been more effective in achieving lasting improvements in Bangladesh’s healthcare system.

Table 8: Summary of EQ 2.3 findings on effectiveness
The TA model successfully leveraged the distinct strengths of its partner organisations
The two TAs through UNFPA (with support from WHO and other organisations) and MSH played a critical role in strengthening the country’s healthcare system. TA led by UNFPA significantly contributed to the professionalisation of midwifery in Bangladesh. Through TA, UNFPA established skill labs, improved midwifery curricula and trained midwives, significantly raising the quality of midwifery services in Bangladesh. Mentorship programmes and UNFPA training initiatives helped midwives gain practical knowledge and confidence in managing maternal health complications. TA led by WHO played a critical role in health governance, policy development and regulatory reforms through initiatives such as health workforce planning, digital health systems and AMR strategies. MSH’s contributions to improving pharmacy regulations and drug administration were notable, such as introducing the ADLRS, streamlining pharmacy operations, and reducing corruption by eliminating intermediaries. WHO's leadership in health reform and governance proved invaluable and as a seasoned international NGO, MSH served as a robust implementing partner.
Despite these successes, TA faced significant challenges in achieving long-term sustainability and systemic integration
TA faced significant challenges, particularly in achieving long-term sustainability and systemic integration. Several structural barriers prevented TA from lasting impact, raising questions about whether other interventions would have been more appropriate. Many midwives and healthcare professionals trained and deployed under TA left their positions once the project funding ended, leading to gaps in service continuity. Due to the delay in the 5th HPNSP, MOHFW and its agencies cannot continue several good initiatives of the BHB programme, meaning the long-term benefits of these TAs are quite uncertain.
While the TAs enhanced technical capacity, this could not overcome deeply rooted governance challenges. Frequent leadership changes within the regulatory and implementing agencies led to inconsistencies in implementing TA-led reforms. Similarly, bureaucratic delays in health sector governance limited the effectiveness of TA in strengthening hospital and health service management. TA primarily focused on training and regulatory improvements. TA alone could not address deeper institutional inefficiencies, which require policy-level reforms.
The effectiveness of TA to strengthen governance and regulatory frameworks was hindered by bureaucratic inefficiencies. According to the key informants, a system-wide institutional reform, including reducing bureaucratic delays, improving coordination between the two major service delivery directorates of MOHFW (i.e. DGHS and DGFP), appropriate human resources (HR) management and strengthening accountability mechanisms, would have enhanced the impact of TA.
The budgetary allocation to health remains low in Bangladesh. As per the BHB Annual Review Report of 2023, the budgetary allocation is only 4.3 percent of the budget, which is low even considering the same in the neighbouring countries. Without increased domestic investment, TA-driven improvements are difficult to sustain beyond the donor funding period. A retired senior official of MOHFW clearly articulated this – donor funding is for a particular period and focusing on the particular cause. If the Government does not invest its funding, then the good deeds of the donor-funded projects would not sustain for a long time.
Another major challenge was the lack of supporting infrastructure and resources to maximise the benefits of TA-driven training. During the initial phases of the BHB programme (before the modality was changed from a service delivery programme to a TA programme), there had been direct support to regions that were lagging behind in terms of supplies and commodities. Without complementary investments in hospital infrastructure, medical equipment and essential supplies (from either government or donors) healthcare facilities remained under-equipped to implement knowledge and skills gained through TA. Many health facilities lacked the necessary infrastructure and supplies to implement improvements effectively. Direct investments in hospital facilities, medical equipment, and essential pharmaceuticals (whether by government or donors) would have helped to ensure that TA-led workforce training translated into more sustainable service improvements.
Given the challenges, TA effectiveness would have been enhanced by complementary governance, regulatory and systems strengthening efforts
A more comprehensive approach that linked TA with a broader programme of policy reforms, infrastructure development and longer-term financial commitments is likely to have been more effective in achieving lasting improvements in Bangladesh’s healthcare system. For example, maximising the long-term benefits of the successful model pharmacy model through complementary investments to increase DGDA’s capacity to monitor pharmacies and ensure compliance with national AMR related regulations.
## Sustainability
#### EQ 3.1: What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?
Strength of evidence: STRONG
Table 9 below summarises key findings, followed by a more detailed narrative analysis.
EQ 3.1: What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?
Governance and institutional reforms. Clear, long-term health policies, decentralised decision-making to Upazila health administrations and enhanced inter-ministerial coordination for better integration of health, finance and local government. / Strengthened Human Resources for Health (HRH) systems to sustain service quality. Long-term workforce planning, transition midwife and pharmacist roles to permanent government positions and institutionalise Continuous Professional Development (CPD). / Strengthened pharmaceutical and regulatory systems: Effective regulatory enforcement is critical to improve pharmacy standards, AMR control and drug administration. / Sustainable health financing and budget allocation. The BHB programme demonstrated how external funding can drive change, but gains must be maintained through domestic financing. Spending should be linked to measurable health outcomes.

Table 9: Summary of EQ 3.1 findings on sustainability
Governance and institutional reforms
The effectiveness of Bangladesh’s health system is hindered by fragmented governance, frequent leadership changes and inefficient coordination among key stakeholders. To improve system resilience beyond the BHB programme, governance reforms should focus on:
Clear and stable policy frameworks: Lack of continuity in policy implementation, like the uncertainty surrounding the 5th HPNSP, has threatened the sustainability of several key interventions. Institutionalising a clear, long-term strategic plan will help ensure that health sector reforms are less dependent on political cycles or donor priorities.
Decentralised decision-making: Decision-making authority should be devolved to local health administrations to ensure timely responses to service delivery challenges. A strengthened Upazila Health System with increased budgetary and human resource management autonomy can improve operational efficiency.
Inter-ministerial coordination: The health sector's effectiveness is linked to multiple ministries, including finance, local government, and education. A structured coordination mechanism must be established to integrate efforts across sectors.
Strengthened Human Resources for Health (HRH) systems to sustain service quality
A well-trained, motivated and equitably distributed health workforce is essential for improving service delivery.
Long-term workforce planning: Strategic workforce planning should be embedded within MOHFW to align recruitment, training and deployment with actual service delivery needs.
Retention and career progression mechanisms: Ensuring career development pathways for midwives, pharmacists and other healthcare professionals is crucial to prevent staff attrition. The transition of midwife positions from project-based funding to permanent government positions must be replicated for other cadres.
Mandatory CPD: CPD should be institutionalised to maintain clinical and technical competencies. Regular refresher training and accreditation requirements should be enforced.
Strengthened Pharmaceutical and Regulatory Systems
Effective regulatory enforcement is critical to improve pharmacy standards, AMR control and drug administration.
Stronger regulatory oversight: The DGDA must be strengthened with financial and human resources to maintain GPP and AMR control.
Legislative reforms: The Drug and Cosmetic Act 2023 introduced key regulatory provisions, but effective enforcement mechanisms must be in place to prevent the resurgence of counterfeit medicines and unauthorised drug sales.
Digital prescription systems: To combat antibiotic misuse, a national digital prescription system should be established to track and monitor prescribed antibiotics.
Sustainable health financing and budget allocation.
The BHB programme demonstrated how external funding can drive change, but gains must be maintained through domestic financing. Sustainable health interventions require long-term financial planning and efficient resource allocation. Options to consider include the following points.
Increased government allocation to health: Currently, the GoB allocates only around 4.3% of its national budget to health, compared to the regional average of 7%. Without increased domestic financing, continued progress is unlikely.
Establishment of a health sector sustainability fund: A dedicated fund, sourced from domestic revenue, private sector contributions and international partnerships, could support critical interventions, including maternal and newborn health, AMR control and health information systems.
Results-Based Financing (RBF) models: Performance-based funding mechanisms could be introduced to ensure that government spending is linked to measurable health outcomes.

#### EQ 3.2: What evidence is there that the benefits of the technical assistance will be sustained?
Strength of evidence: STRONG
Table 10 below summarises key findings, followed by a more detailed narrative analysis.
EQ 3.2: What evidence is there that the benefits of the TA will be sustained?
While the programme successfully influenced national health systems, there are concerns about the longevity of BHB improvements once donor support is phased out. The sustainability of the benefits derived from the TA provided under the BHB programme is contingent on institutional integration, workforce retention, financial commitments and regulatory oversight. / Shifting away from the 5th HPNSP sector wide approach presents a sustainability challenge. The biggest concern for the sustainability of the TA components is associated with the MOHFW decision to shift away from the planned sector wide approach (SWAp) in Bangladesh towards a project-based approach. / Inconsistent GoB commitment to retain workforce. The programme has made notable efforts to embed its key interventions within the government framework. However, some of the positions created by DGFP are under the Operational Plan budget of 5th HPNSP. With the uncertainty of the next SWAp, personnel recruitment in these positions is also uncertain. / Gap in continuous support for IT maintenance. Digitising health services, such as the ADLRS, introduced under BHB, has improved efficiency in pharmacy regulation. However, challenges remain regarding the continuity of digital health solutions. / Commitment to retaining quality beyond the programme. Without sustained investment in human resource development, gains achieved through BHB’s TA could be lost over time. / Lack of regulatory oversight in areas such as AMR control and pharmacy standards. Regulatory challenges remain critical to sustainability. The enforcement of GPP has been a priority under BHB, but compliance weakened after the programme reduced its direct involvement. / Lack of centralised health information systems. Systemic inefficiencies within government agencies have hindered the full institutionalisation of TA outcomes. The lack of a unified health information system remains a persistent issue, with multiple databases operating in silos.

Table 10: Summary of EQ 3.2 findings on sustainability
While the programme successfully influenced national health systems, there are concerns about the longevity of BHB improvements once donor support is phased out
As described above, while the programme successfully influenced national health systems, strengthened service delivery and introduced critical policy changes, concerns remain regarding the longevity of these improvements once donor support is phased out. The sustainability of the benefits derived from the TA provided under the BHB programme is contingent on institutional integration, workforce retention, financial commitments and regulatory oversight.
Shifting away from the 5th HPNSP sector wide approach presents a sustainability challenge
The biggest concern for the sustainability of the TA components is associated with the MOHFW decision to shift away from the planned sector wide approach (SWAp) in Bangladesh towards a project-based approach. During implementation of the 4th HPNSP it was assumed the country would have a follow-up health sector SWAp from 2024 to 2029, to be known as the 5th HPNSP. As a strategy to ensure sustainability, several components of the BHB programme, particularly the service provision and systems strengthening components, were embedded into draft Operational Plans for the 5th HPNSP. The intention was that they would start immediately after closure of 4th HPNSP, i.e. from July 2024.
Though the Planning Commission held a series of review meetings of the proposed 5th HPNSP Programme Implementation Plan, shortly afterwards a major political leadership change took place. The new leadership of MOHFW decided to change the implementation modality away from a 5th HPNSP. Instead, MOHFW will implement projects. The design of these projects has not yet been completed, and it is not clear whether interventions included in the planned 5th HPNSP Operating Plans will be included. This has resulted in uncertainty around whether some of the good practices of the BHB programme will be continued.
Inconsistent GoB commitment to retain workforce
The programme has made notable efforts to embed its key interventions within the government framework. UNFPA-supported midwifery integration into Bangladesh’s health system is one such example. A senior official from DGNM noted that UNFPA/BHB’s advocacy led to the institutionalisation of midwifery positions and improved health governance. BHB programme advocacy resulted in the creation of additional midwives’ positions in DGNM (e.g. in DH and MCHs) under the revenue budget. This budgetary provision ensures that MOHFW will continue these positions in the future. However, the sustainability of these efforts depends on continued government commitment to workforce retention and career progression for midwives.
Gaps in continuous support for IT maintenance
Similarly, digitising health services, such as the ADLRS, introduced under BHB, has improved efficiency in pharmacy regulation. However, challenges remain regarding the continuity of digital health solutions. An official from DGDA highlighted: We must make sure that ADLRS will continue to be functional. The upgradation of the software should also be thought of​. Without consistent government investment in IT infrastructure and training, these systems risk becoming obsolete. It should be noted that DGDA does not have a regular budget to maintain its IT infrastructure. The Directorate does not even have its own IT personnel. Continuation of ADLRS was included in the Strengthening Drug Administration and Management Operational Plan under 5th HPNSP. Again, with the uncertainty of the 5th HPNSP, it is unclear how the Directorate will maintain this system.
Commitment to retaining quality beyond the programme
Without sustained investment in human resource development, gains achieved through BHB’s TA could be lost over time. A persistent theme across stakeholder interviews was the challenge of retaining trained personnel once donor funding ceases. This was especially evident in the midwifery profession, where although the introduction of midwives into healthcare facilities has been transformative, there remains a gap in ensuring that these professionals have the necessary support to continue providing quality care. One midwifery professional stated: We don’t lack resources, but we lack the skills and competencies to optimise their utilisation. Similarly, BHB’s TA in the pharmacy sector led to significant advancements in GPP, yet adherence rates declined when external oversight was reduced. As reported by one pharmacist: After you [TA from BHB] left, no one followed up, so we stopped maintaining the standard practices​. This highlights the need for a structured, government-led mechanism to ensure continuity in quality assurance.
Several stakeholders emphasised the importance of refresher training for health professionals as part of a more systematic approach to continuous professional development. A senior health manager stressed: Sustainability can only be ensured when the service is continuously provided after training.
Lack of regulatory oversight in areas such as AMR control and pharmacy standards
Regulatory challenges remain critical to sustainability. Enforcement of GPP was a priority under BHB, but compliance weakened after the programme reduced its direct involvement. The pharmacy sector saw early improvements in antibiotic regulation, but without sustained enforcement previous issues began to resurface. As an official from DGDA noted: People now have consciousness about fake medicines, duplicate medicines and unauthorised medicine​. However, without stronger enforcement from DGDA, these improvements may not be sustained.
Lack of centralised health information systems
Systemic inefficiencies within government agencies have hindered the full institutionalisation of TA outcomes. The lack of a unified health information system remains a persistent issue, with multiple databases operating in silos. The absence of a centralised health data system limits the government’s ability to track progress and make evidence-based policy decisions.
## Efficiency
Efficiency evaluation questions 4.1 and 4.2 are summarised in this section and presented in more detail in Annex 12: Value for Money assessment.
#### EQ 4.1: How effective were the various TA interventions compared to the cost of respective TA
Strength of evidence: MODERATE TO STRONG
Table 11 below summarises key findings, followed by a more detailed narrative analysis.
EQ 4.1: How effective were the various TA interventions compared to the cost of respective TA
BHB achieved strong economy through cost-saving mechanisms across procurement, consultancy and training. UN-based procurement platforms (UNFPA and WHO) provided inputs at significantly reduced rates. MSH’s procurement strategies delivered £1.51 million in savings. Consultant costs were reduced through in-house expertise. Training expenditures were minimised by shifting to government-led and virtual models, resulting in reductions of up to 89%. Direct Financial Cooperation (DFC) agreements further streamlined fund disbursements. However, lack of disaggregated financial data from all partners constrained full quantification of savings. / BHB demonstrated strong efficiency in translating inputs into outputs. Eight out of 11 programme outputs met or exceeded targets. Digital innovations like ADLRS cut licensing times and generated £1.62 million in savings. Training medicine dispensers improved storage compliance, labelling, patient counselling, reducing medicine spoilage and health risks. However, performance in Output 1.4 (Vitamin A coverage at 99%) and Output 1.6 (climate resilience training at 67%) fell short, indicating implementation challenges in multi-stakeholder activities. / The programme effectively contributed to notable health and policy outcomes. The share of normal deliveries conducted by midwives rose from 54.9% (2019) to 91% (2024), increasing access to skilled birth attendance. Deliveries supported by skilled birth attendants increased fourfold. Stock-out rates for essential medicines dropped from 40% to 0%, signalling strengthened supply chains. BHB also supported enactment of the Drug and Cosmetics Act 2023, development of national pharmacy accreditation guidelines, and embedding digital tools like ADLRS and PMS in government systems. / BHB was cost-effective with a cost per DALY averted of £99, substantially below Bangladesh’s GDP per capita. / VfM reporting challenges and caveats: Absence of a standard VfM framework across partners led to inconsistent VfM reporting. Gaps in financial data hindered granular analysis of cost drivers. There is an inherent difficulty in quantifying long-term benefits of TA, policy, and systems strengthening. There was some variation in performance across outputs, with some areas (e.g., Output 1.4 and 1.6) underachieving.

Table 11: Summary on EQ 4.1 findings on efficiency
The VfM assessment evaluated the programme’s financial efficiency, operational effectiveness, and overall contribution to improving maternal and reproductive health, digital health systems, and policy governance. Annex 12: Value for Money assessment. The assessment follows FCDO’s VfM framework, and analysed economy, efficiency, effectiveness and cost-effectiveness to determine how well programme resources were utilised to achieve the greatest possible health outcomes.
BHB achieved strong economy through cost-saving mechanisms across procurement, consultancy and training
UN-based procurement platforms (UNFPA and WHO) provided inputs at significantly reduced rates – lower than local markets for selected commodities – though precise savings could not always be disaggregated. MSH’s strategic procurement alone delivered £1.51 million in savings. Consultant costs were reduced through in-house expertise, and training expenditures were minimised by shifting to government-led and virtual models, resulting in reductions of up to 89%. Direct Financial Cooperation (DFC) agreements further streamlined fund disbursements, enhancing cost control. However, lack of disaggregated financial data from all partners constrained full quantification of savings.
[note] Calculations by author based on data reported in Programme Completion Report by MSH. These savings are estimated based on actual procurement price less budgeted amount.
BHB demonstrated strong efficiency in translating inputs into outputs
Eight out of 11 programme outputs met or exceeded targets, including childbirths attended by skilled birth attendants (Output 1.1 at 173%), family planning uptake (Output 1.3 at 107%), and licensing of medicine shops (Output 3.2 at 102%). Digital innovations like ADLRS cut licensing times (from 15–45 days to 2–5 days) and generated £1.62 million in savings. Training of medicine dispensers improved storage compliance (from 45% to 92%), labelling, and patient counselling, reducing medicine spoilage and health risks. However, performance in Output 1.4 (Vitamin A coverage at 99%) and Output 1.6 (climate resilience training at 67%) fell short, indicating implementation challenges in multi-stakeholder activities.
[note] Automation savings calculated by author based on time and cost reductions estimated per licensing application, multiplied by the volume of applications processed through the system (as detailed in ADLRS implementation reports).
The programme effectively contributed to notable health and policy outcomes
The share of normal deliveries conducted by midwives rose from 54.9% (2019) to 91% (2024), increasing access to skilled birth attendance. Deliveries supported by skilled birth attendants increased fourfold. Stock-out rates for essential medicines dropped from 40% to 0%, signalling strengthened supply chains. BHB also supported enactment of the Drug and Cosmetics Act 2023, development of national pharmacy accreditation guidelines, and embedding digital tools like ADLRS and Pharmacy Management Software (PMS) in government systems.
The programme’s e-learning platform trained over 25,000 pharmacy professionals, enhancing long-term institutional capacity.
BHB was highly cost-effective, with a cost per DALY averted of £99, substantially below Bangladesh’s GDP per capita.
- Midwifery and Basic Emergency Obstetric and Newborn Care (BEmONC): 2,277 deaths averted, 162,407 DALYs saved, and £321 million in benefits; £32.7 per DALY averted; £60 return per £1 invested.
- Family Planning: 2,058 deaths averted, 142,514 DALYs saved; £25 per DALY averted, with an ROI of £78 per £1 invested.
- Implant Provision: 650 deaths averted, 45,854 DALYs saved; £30 per DALY.
- Cervical Cancer Screening: 78 deaths averted, 27,576 DALYs saved; £65 per DALY, and £29 return per £1 invested.
VfM reporting challenges and caveats
Absence of a standard VfM framework across partners led to inconsistent VfM reporting, while gaps in financial data hindered granular analysis of cost drivers. There is an inherent difficulty in quantifying long-term benefits of TA, policy, and systems strengthening. There was some variation in performance across outputs, with some areas (e.g., Output 1.4 and 1.6) underachieving.
#### EQ 4.2: Did the programme achieve VfM?
Strength of evidence: MODERATE TO STRONG
Table 12 below summarises key findings, followed by a more detailed narrative analysis.
EQ 4.2: Did the programme achieve VfM?
The BHB programme provided strong value for money across all four VfM pillars (economy, efficiency, effectiveness, and cost-effectiveness). It effectively minimised costs, efficiently converted resources into outputs, achieved substantial health improvements, and delivered high cost-effectiveness relative to investment. / The low cost per DALY averted (£99), combined with the economic benefits exceeding £745 million, illustrates a high return on investment. While data limitations and implementation gaps existed, they do not detract from the programme’s overall VfM performance. BHB demonstrated that well-structured TA, aligned with national systems, can generate significant, lasting impact when paired with smart resource use.

Table 12: Summary on EQ 4.2 findings on efficiency
The BHB programme provided strong value for money across all four VfM pillars
BHB successfully optimised financial resources to generate meaningful and sustainable health impacts, reinforcing its high return on investment. Based on the assessment of VfM (Annex 12: Value for Money assessment) the BHB programme provided strong value for money across all four pillars. It effectively minimised costs, efficiently converted resources into outputs, achieved substantial health improvements, and delivered high cost-effectiveness relative to investment. The low cost per DALY averted (£58) compared to Bangladesh’s GDP per capita confirms that the programme was highly cost-effective. While some inefficiencies and data limitations exist, they do not significantly undermine the programme’s overall VfM rating. Overall, performance against impact and outcome level cost indicators compared well to Business Case estimates.
[note] Observed variances between the Business Case, VfM assessment, and Annual Review 2024 estimates can be attributed to methodological, temporal, and contextual factors. Business Case estimates were based on ex-ante projections made at the design stage, often using global or regional benchmarks, hypothetical coverage levels, and assumed impact pathways. These estimates tend to be conservative or aspirational and may not fully reflect on-ground realities or implementation nuances. The VfM assessment is an ex-post analysis conducted using actual implementation data, refined costing inputs, and updated assumptions around coverage, service delivery effectiveness, and attribution of outcomes. This tends to produce more accurate and sometimes more favourable cost-effectiveness metrics, as seen in the lower cost per life saved and cost per case averted in the VfM assessment. The Annual Review 2024, on the other hand, reflects a snapshot of just one year of implementation and is likely influenced by annual variations in expenditure patterns, service uptake, and external factors (e.g., supply chain issues, delayed disbursements, or seasonal demand shifts). Since it is not a cumulative analysis like the VfM assessment, it may present a skewed picture – especially if the denominator (e.g., lives saved or cases averted in one year) is low relative to the annual cost base. Moreover, Annual Reviews may apply a different attribution logic or be more conservative in crediting outcomes directly to programme interventions, which could further inflate the cost per outcome.
Outcome level cost indicators: The VfM assessment identified substantial efficiency gains in the delivery of key health interventions under the BHB programme. Comparative analysis of outcome-level cost indicators shows that actual implementation costs for services such as BEmONC and cervical cancer screening are significantly lower than those projected in the original Business Case. VfM analysis involved a comparative analysis of outcome-level cost indicators across three benchmarks: (i) the original estimates provided in the Business Case, (ii) the latest VfM findings based on implementation data, and (iii) the most recent cost figures reported in the Annual Review 2024. These benchmarks help to demonstrate the programme’s cost-efficiency pillar by illustrating the extent to which service delivery has achieved value relative to initial projections. Three outcome-level indicators are examined: cost per patient for BEmONC, cost per cervical cancer screening, and cost per FP adopter.
The cost per BEmONC patient serves as a strong marker of implementation efficiency. The Business Case estimated this at £83 per patient. The VfM analysis, however, shows a reduced cost of £56 per patient, indicating a 33% efficiency gain. This reduction suggests that the intervention was implemented with greater precision, leaner inputs, and improved facility-level management. Contributing factors may include targeted resource allocation to high-burden facilities, integrated training models for midwives and obstetric staff, and more cost-efficient procurement of equipment and supplies. In contrast, the Annual Review 2024 reports a cost of £50.1 per patient – a figure that remains 40% lower than the Business Case and slightly lower than this VfM assessment.
The cost per cervical cancer screening further reinforces the programme’s cost-efficiency. The Business Case projected a unit cost of £2, based on Visual Inspection by Acetic Acid (VIA) as the primary screening modality. This VfM assessment reveals a lower cost of £1.28 per screening, reflecting efficient programme rollout, effective provider training, and integration of services within existing reproductive health platforms. The Annual Review 2024 figure stands at £1.33, which is slightly higher than the VfM estimate but still well below the original projection.
The third indicator, cost per FP service provided, adds further nuance to the outcome-level cost-efficiency analysis. The Business Case placed this cost at £6, while this VfM analysis estimates it at £3.9, showing a 34% reduction. This likely results from streamlined service delivery, improved commodity distribution, and scaled-up community-based FP promotion. The Annual Review 2024 reports a lower figure of £2.5, which remains appreciably more efficient than the Business Case estimate.
Taken together, this analysis confirms that the BHB programme has delivered meaningful efficiency gains across all outcome-level service delivery areas. The VfM estimates consistently fall below the original Business Case projections and remain competitive against the 2024 Annual Review. These trends reflect improvements in operational efficiency, better use of TA, and programmatic learning over time. Analysed in combination, these perspectives present a compelling narrative of cost-effective health service delivery under the BHB programme.
Impact level cost indicators: A comparison of impact-level cost-effectiveness indicators across the Business Case, the VfM assessment, and the Annual Review 2024 provides a clear picture of how the BHB programme has performed in terms of delivering VfM. Three key indicators are analysed: cost per life saved through BEmONC, cost per unsafe abortion averted through FP services, and cost per cervical cancer case averted through screening interventions. These indicators represent critical areas of maternal, reproductive, and preventive health, and demonstrate how efficiently the programme translates investments into high-impact outcomes.
The cost per life saved through BEmONC is estimated at £2,329 in this VfM assessment, compared to £2,079 in the Business Case, and £3,213 in the Annual Review 2024. While the VfM estimate is slightly higher than the Business Case projection, it is still 27% lower than the Annual Review figure. This suggests that delivery costs are somewhat higher than initially anticipated – possibly due to inflation, enhanced quality standards, or more comprehensive costing. Nevertheless, the BHB programme has still achieved better effectiveness than reflected in the broader Annual Review costing. The VfM estimate likely benefits from a tighter attribution of results and a more direct mapping of costs to lives saved.
In the area of FP, the cost per unsafe abortion averted is estimated at £17 in this VfM assessment, compared to just £5 in the Business Case. While this is more than triple the initial projection, the lack of an Annual Review comparator limits direct interpretation. Given the complex and often under-recognised system costs in reducing unsafe abortion rates, especially in conservative or under-resourced contexts – this figure may still represent reasonable value, albeit less efficient than originally projected.
The cost per cervical cancer case averted tells a different story. Here, the VfM estimate of £189 is 51% lower than the £385 projected in the Business Case, and over 90% lower than the £2,221 reported in the Annual Review 2024. This strongly indicates that the cervical cancer screening interventions have been delivered in a highly efficient and cost-effective manner. The large gap between the VfM and Annual Review figures may reflect differing assumptions about attribution and data modelling for long-term cancer prevention impact.
Overall, this VfM assessment shows mixed results across the three impact level indicators – exceeding expectations for cervical cancer screening, moderately exceeding Annual Review efficiency for BEmONC, and underperforming against the Business Case estimate in FP-related impact. These variations reflect a combination of methodological differences, data improvements, and contextual realities in programme implementation. Nonetheless, the results collectively underscore that the BHB programme has delivered significant health outcomes at a generally reasonable and in some cases highly favourable cost, particularly when compared to broader costing benchmarks used in the Annual Review.
Key VfM findings at a glance
- 5,063 deaths averted and 378,351 DALYs saved across four major interventions, generating £745.75 million in economic benefits.
- Cost per DALY averted: £99 – 19 times lower than Bangladesh’s GDP per capita (£2,057), confirming strong cost-effectiveness.
- £1.62 million saved through the digitisation of medicine shop licensing via ADLRS.
- £1.51 million saved through improved procurement practices by MSH.
- Compliance with prescription-only antibiotic sales increased from 33.7% to 82.7%.
- 515 public health facilities became PPFP-ready, up from zero at baseline.
## Equity
#### EQ 5.1: How has the programme addressed gender equality, equity, poverty and inclusion aspects?
Strength of evidence: STRONG
Table 13 below summarises key findings, followed by a more detailed narrative analysis.
EQ 5.1: How has the programme addressed aspects of gender equality, equity, poverty, and inclusion?
BHB proactively included equity in its programming. The programme’s core objective is to ensure that all citizens, particularly women, the poor and marginalised communities, have equitable access to quality healthcare services. / Expansion of midwifery-led maternal healthcare. One of the BHB’s most significant achievements has been scaling up midwifery services across Bangladesh to ensure access to safe delivery covering urban and rural areas. While the BHB programme worked in 20 specific districts, TAs involvement and contribution in the policy and frameworks at the national level with the Planning Wing of HSD, MOHFW and the two large service-providing directorates DGHS and DGFP aimed to ensure equitable services across the country. Remaining gaps from an equity perspective include geographic inequalities; over-burdened staff; safety and logistics for midwives in remote areas; lack of essential infrastructure and medical supplies. / Gender-inclusive targeted interventions: Cervical cancer screening. The BHB programme significantly advanced gender-inclusive healthcare by expanding cervical cancer screening, with over 900,000 women screened, leading to improved early detection and reduced mortality. / Targeted interventions for indigenous and marginalised populations. Recognising the disparities in healthcare access among indigenous communities, the BHB programme implemented region-specific health initiatives such as the Santal Health Programme in Gaibandha and the Khagrachari Maternal and Child Health Initiative. These interventions have resulted in births by skilled attendants in these communities. / Expanding healthcare access for populations living in hard-to-reach areas. With BHB support, access to healthcare services for underserved and geographically isolated populations of districts like Gaibandha and Kurigram has significantly improved. However, major challenges remain in ensuring consistent, accessible, safe maternal and reproductive healthcare. / Emergency response and climate-resilient healthcare services. During the 2024 floods, the BHB programme responded by mobilising 50 mobile SRH outreach camps, providing life-saving maternal and reproductive healthcare to over 7,140 women and girls. / Equity in drug dispensing services. BHB has strengthened efforts to ensure socio-economic and geographic equity in drug dispensing services in Bangladesh through expanded access to accredited model pharmacies and medicine shops across all eight divisions, including hard-to-reach and underserved areas. However, major gaps remain and there is a risk of regression. / Addressing Gender-based Violence (GBV). The BHB programme supported initiatives to strengthen GBV response services in healthcare facilities, ensuring survivors had access to medical, psychological and legal support, though implementation is inconsistent.

Table 13: Summary of EQ 5.1 findings on equity
The evaluation investigated the programme’s effectiveness in addressing gender equality, poverty and social inclusion, with a particular focus on how it has targeted the most vulnerable populations and reduced disparities in access to healthcare services. The team examined how the programme navigated structural barriers to ensure equitable healthcare access for marginalised populations, particularly rural women, indigenous communities, persons with disabilities and the urban poor.
BHB proactively included equity in its programming
The BHB programme’s core objective is to ensure that all citizens, particularly women, the poor and marginalised communities, have equitable access to quality healthcare services.. Equity in healthcare is therefore a fundamental pillar of the BHB programme. Despite Bangladesh’s progress in improving health indicators, deep inequities persist. The healthcare system remains urban-centric, disproportionately benefiting wealthier populations, while rural communities – particularly those in climate-vulnerable and indigenous regions – struggle with inadequate service availability.. Furthermore, socioeconomic constraints and cultural norms continue to limit women’s access to healthcare, particularly for reproductive and maternal health services.
[note] Outcome 1 of the original logframe of BHB programme, 2019
[note] World Health Organization. (2020). Bangladesh country cooperation strategy 2020–2025. WHO Regional Office for South-East Asia. https://www.who.int/publications/i/item/9789290209478
[note] WHO. 2015. Bangladesh Health System Review. Health Systems in Transition. Vol. 5 No. 3 2015. Asia Pacific Observatory on Public Health Systems and Policies
Expansion of midwifery-led maternal healthcare
One of the most significant achievements of the BHB programme has been the scaling up of midwifery services across Bangladesh, ensuring access to safe delivery in urban and rural areas. While the BHB programme worked in 20 districts, its involvement and contribution in the policy and frameworks at the national level (with Planning Wing of HSD, MOHFW and the two large service providing directorates, i.e. DGHS and DGFP) aimed at ensuring equitable services across the country.
TA advocated and facilitated DGNM to deploy 2,557 registered midwives in over 400 UHCs, improving access to skilled birth attendants, particularly in rural and underserved areas. As a result of the deployment, midwives conducted 85% of normal vaginal deliveries in these public sub-district level health facilities. Since there was no position of midwives in the organisational structure of DGHS at district hospitals (DH), BHB deployed 48 midwives in eight DHs. The deployment of midwives in these facilities has improved antenatal, postnatal, and delivery services, as mentioned by all the service providers who interacted with them during this evaluation. A senior official from DGNM shared: In UHCs, about 82% of normal deliveries are now conducted by midwives…previously, the Nurses used to conduct some normal deliveries, but mostly these were done at home.
[note] FCDO. 2023. Annual Review of BHB Programme 2023.
[note] FCDO. 2024. Annual Review of BHB Programme 2024.
Despite significant progress in midwifery expansion, gaps remain from equity perspectives:
Geographic inequities remain a critical concern: Districts such as the Chittagong Hill Tracts and parts of Barisal continue to experience shortages of midwives, limiting access to skilled maternal healthcare.
[note] HSD, 2024. HRH Datasheet, 2023. Human Resources Wing, Health Services Division, Ministry of Health and Family Welfare
Overburdened staff and job insecurity: Workload and insecure jobs (trained midwives not absorbed in the government system) threaten overall services, especially to marginalised communities.
Safety and logistics for midwives in remote areas: Despite these improvements, significant barriers remain in ensuring safety and logistics support to the midwives, which in turn, has major consequences on ensuring care effectiveness. For example, geographical isolation and poor infrastructure in Char areas continue to be major obstacles, preventing placement of midwives in those sub-centres and discouraging mothers from reaching health facilities in time for deliveries.
Lack of essential infrastructure and medical supplies at the health facilities limited midwives' ability to provide quality care: A midwife noted: We don’t have delivery sets. We already reported to our supervisors about the shortage of medical equipment. There is a lack of support facilities at union-level health centres, which hinders the deployment of midwives at those levels. A midwifery expert from DGNM mentioned: It would have been helpful if midwives had been stationed at union facilities as per the original plan. But there are no accommodation facilities there. Security is also a concern. Some union facilities do not even have basic utilities. So midwives are now stationed at UHCs.
Gender-inclusive targeted interventions: cervical cancer screening
The BHB programme significantly advanced gender-inclusive healthcare by expanding cervical cancer screening, with over 900,000 women screened using VIA, leading to improved early detection and reduced mortality. It also strengthened sexually transmitted infections (STI) services by formulating the National STI Strategy (2019-2027) and updating management guidelines to enhance equitable access for vulnerable populations. Additionally, the programme ensured life-saving maternal emergency drugs were available in 98% of Upazila health complexes and district hospitals. Furthermore, BHB played a key role in gender-inclusive policy reforms, supporting the Bangladesh Nursing and Midwifery Council in implementing workforce protection policies to safeguard female healthcare professionals from workplace harassment and discrimination, fostering a more equitable health sector.
While the cervical cancer screening was an important initiative, the lack of resources of MOHFW, both human and financial, has created a significant threat for the sustainability of this intervention. The funding for the reagents of the screening was provided from the BHB programme. Later, MOHFW included the funding in the planned 5th HPNSP. However, since this sector programme has not yet been initiated, the service provision is highly constrained, since the DHS have limited budget or human resources to continue it. A senior manager from the MNCAH programme of DGHS mentioned: Cervical cancer screening has increased access for women in remote areas, but workforce shortages persist. Currently, some of the nurses are trained for this service – however, there is a shortage of nurses and these trained nurses are often involved in other services. We do not have a budget to train more people on this service. Another manager from DGHS indicated: We included the budget for reagents of cervical cancer screening and training in the MNCH Operational Plan of 5th HPNSP. But the Operational Plan has not yet been approved – so we do not have the budget. Social stigma also persists in enabling women’s access to STI services. A UNFPA official noted: While access has improved, social stigma still discourages many women, particularly adolescents and unmarried women, from seeking STI treatment.
Targeted interventions for indigenous and marginalised populations
Recognising the disparities in healthcare access among indigenous communities, the BHB programme implemented region-specific health initiatives such as the Santal Health Programme in Gaibandha and the Khagrachari Maternal and Child Health Initiative. Over 562 normal vaginal deliveries, 6,935 antenatal care visits and 5,937 family planning consultations were conducted in Gaibandha district, an area with flatland ethnic minorities like Santals, benefiting 4582 women, including 79 from the Santal Community. The Khagrachari Maternal and Child Health Services initiative facilitated 1,738 safe deliveries in maternity waiting homes and 10,647 normal vaginal deliveries in government facilities. By providing financial and transportation support to women in remote areas like hill tracts districts of Khagrachari, the programme successfully increased facility-based deliveries, contributing to improved maternal and neonatal outcomes.
[note] UNFPA FCDO Maternal Health Report, document shared by FCDO, year unknown
[note] FCDO. 2022. Annual Review of BHB Programme 2022.
While targeted health interventions have benefited indigenous populations, language and cultural barriers remain unaddressed. Indigenous women continue to report lower antenatal and postnatal care utilisation rates due to a lack of culturally competent healthcare providers and materials in indigenous languages. A community health worker pointed out: We don’t have enough indigenous-language health materials and many providers lack training on culturally competent care. The future programmes may consider greater investments in culturally tailored service delivery models to ensure increased access to services for the indigenous population.
At the time of the evaluation team’s field visit to the union sub-centre in one of the northern districts, three BHB-supported midwives provided services to their community, fostering trust and comfort among mothers seeking care. Their presence has also inspired others in the community to consider midwifery as a career path. However, the midwives currently posted at the health centre are supported by the BHB programme, which created job insecurity as the project ended. Without government support, health centres like this risk losing their trained midwives. As one midwife noted: After completing our studies, we returned home during COVID. When offered jobs at this facility, we eagerly accepted. It was our first job, and what made it even more special was serving our community. As Santals, working for our people gives us a sense of purpose and we are still here.
Expanding healthcare access for populations living in hard-to-reach areas
With BHB support, access to healthcare services for the underserved and geographically isolated populations in the island chars of districts like Gaibandha and Kurigram has significantly improved. However, major challenges remain in ensuring consistent, accessible and safe maternal and reproductive healthcare. BHB provided critical logistics and technical support to the midwives placed in district hospitals, Mother and Child Welfare Centres (MCWC) and UHCs, equipping these facilities to provide delivery and FP services. The government deployed midwives to these centres, aiming to encourage more mothers from char communities to seek facility-based care and support. BHB has brought some services closer to char households. Within the char areas, UNFPA has played a crucial role by supporting three dedicated union sub-centres, while surrounding health facilities including Family Welfare Centres have also received essential equipment and TA.
[note] In Bangladesh, Island chars refer to isolated landmasses formed within river channels (e.g., in rivers like Padma, Teesta, Jamuna and Brahmaputra). Island chars are completely surrounded by water, making transportation difficult and limiting access to essential services such as schools, healthcare and disaster relief.
Strengthening disability-inclusive healthcare services
The programme took proactive steps to integrate disability inclusion in healthcare services by developing Standard Operating Procedures (SOPs) for disability-inclusive family planning and SRH services. This SOP ensured that healthcare providers were equipped with the necessary guidelines to offer accessible and inclusive reproductive health services for persons with disabilities. However, implementation challenges persist. A health manager mentioned: The SOPs exist, but many health facilities lack accessible infrastructure and trained staff to serve persons with disabilities effectively. Stakeholders emphasised that without a national monitoring system, it is difficult to track the utilisation of healthcare services by persons with disabilities. A UNFPA official noted: There is no comprehensive tracking system to monitor how many persons with disabilities access SRH services, making it hard to design targeted interventions. The absence of disability-disaggregated data limits evidence-based policy formulation and resource allocation.
Emergency response and climate-resilient healthcare services
During the 2024 floods, the BHB programme responded effectively by mobilising 50 mobile SRH outreach camps, providing life-saving maternal and reproductive healthcare to over 7,140 women and girls. This effort was instrumental in ensuring that climate-vulnerable populations continued to receive essential health services despite environmental disruptions. Additionally, the Climate Change and Public Health Certificate Programme facilitated fieldwork in flood-prone districts, building capacity for long-term climate health resilience.
[note] FCDO. 2024. Annual Review of BHB Programme 2024.
Equity in drug dispensing services
Efforts to ensure socio-economic and geographic equity in drug dispensing services were strengthened by BHB through expanded access to accredited model pharmacies and medicine shops across all eight divisions, including hard-to-reach and underserved areas. This initiative prioritised equitable training opportunities, with over 14,000 medicine dispensers receiving professional development, including those from rural, haor, coastal and flood-prone regions. By leveraging digital learning platforms, such as the BHB e-Learning system, pharmacy professionals – regardless of location, gender, or financial status – could access continuous education, leading to an 89% course completion rate between 2021 and 2024.
Gender-inclusive training initiatives ensure that women – especially those facing mobility and societal constraints – can actively engage in the health sector. To enhance women’s participation in the pharmacy workforce, the project trained 500 female medicine dispensers and provided free, flexible e-Learning opportunities to enable women to pursue professional development without barriers related to travel or family responsibilities. Additionally, digital solutions like ADLRS and PMS facilitated licensing, accreditation and safe medicine disposal, reducing bureaucratic barriers, particularly for pharmacy owners in remote areas. Collectively, these initiatives enhanced equitable access to high-quality pharmaceutical services, bridging disparities in healthcare access between urban and rural communities. However, equity gaps remain, as set out below.
Lack of gender-disaggregated reporting: Reporting on training was not disaggregated by gender, leaving gaps in understanding how many women participated as trainers or enrolled in or completed courses through the online platform.
Low female representation in training and workforce participation: Despite the project's efforts to recruit and train female pharmacy professionals, actual numbers indicate a significant gender gap. Of 14,129 trained medicine dispensers, only 500 were women (~3.5%). However, the socio-cultural context and the business environment in Bangladesh are significant barriers for women to work as medicine dispensers, and addressing these issues was not within the purview of the BHB programme.
Addressing Gender-based Violence (GBV)
A critical component of equity in healthcare is ensuring protection against GBV. The BHB programme supported initiatives to strengthen GBV response services in healthcare facilities, ensuring survivors had access to medical, psychological and legal support. Additionally, TA was provided to integrate GBV screening protocols within reproductive health services, particularly in rural and marginalised communities where reporting mechanisms are weak.
Service implementation, however, seemed to be inconsistent. A senior health official noted: Midwives and nurses received training to identify and manage GBV cases, but implementation remains inconsistent across districts. Another district hospital manager noted: Some facilities have well-functioning referral pathways for GBV survivors, while others lack the necessary coordination with legal and psychosocial support services. There is a pressing need for stronger enforcement mechanisms, standardised protocols and survivor-centred support services to ensure the long-term effectiveness of these interventions.
# Conclusions
This section starts with an overview of the conclusions that emerge from the evaluation and challenges that remain, particularly regarding the sustainability of TA interventions. It then summarises conclusions by evaluation question area: relevance, effectiveness, sustainability, efficiency and equity, and links them to recommendations which are set out more fully in the following chapter. The team note that findings are in-line with and support the findings from the independent evaluation of the 4th HPNSP.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
Overview
The BHB Programme has helped to lay a strong foundation for a more equitable healthcare system in Bangladesh. The programme’s contributions in midwifery expansion, cervical cancer screening and disability-inclusive healthcare serve as valuable blueprints for future health reforms. With continued commitment from policymakers, stronger government integration and sustainable financing, progress supported by BHB can be scaled and institutionalised to ensure lasting impact (see: Recommendations). Multiple factors integral the TA design and implementation contributed to this achievement.
- From the outset, the programme aimed to be adaptable and responsive to needs.
- BHB strategically collaborated with the government by coordinating with different agencies, including flexible funding to support the MOHFW’s immediate needs.
- Interventions focused on strengthening, mentoring and transferring updated skills.
- Leadership and commitment at all levels played a crucial role, along with community engagement.
- Innovative approaches such as the Green Health Initiative and the course on climate and resilience at Dhaka University are testament to BHB’s commitment to piloting innovation and addressing disasters caused or exacerbated by climate change.
- Strong alignment with government systems allowed for integration of digital tools and sustained reforms, which improved policy uptake and service delivery.
- Smart resource use through cost-saving procurement, virtual training, and in-house TA delivery enhanced efficiency without compromising quality.
- High implementation efficiency was achieved, with key outputs exceeding targets (e.g., skilled birth attendance, FP uptake, medicine shop licensing).
- Emphasis on scalable, evidence-based interventions led to high returns on investment and system-wide improvements (e.g., midwifery deployment FP services and enabling environment, PPFP facility readiness, AMR compliance).
Despite these achievements, significant challenges and gaps persist in the healthcare system.
Many health facilities, particularly at the sub-district level, lack basic amenities such as delivery sets, adequate logistics, infrastructure, and safety. This shortfall makes it difficult to assign midwives to these centres as per initial HPNSP plans. Reliance on external funding for critical initiatives like cervical cancer screening raises concerns about sustainability, especially as government budget constraints have already disrupted service provision. While some midwifery positions under the DGNM have been institutionalised, others under the DGFP remain vulnerable due to inadequate budget allocations. The absence of IT personnel and maintenance funding for the ADLRS threatens the continuity of pharmacy licensing and regulation processes. Bangladesh is particularly vulnerable to the impact of climate change, which will put more pressure on health systems, especially in communities that are already under-served and hard-to-reach.
Relevance: The BHB programme strongly aligned with the country’s 4th HPNSP and corresponds to its strategies. For example, strategic support from UNFPA aligned with the country's priorities, reflected in the programme’s emphasis on maternal and newborn health and its initiative to scale up midwifery services. This directly contributed to increasing skilled birth attendance rates, especially in underserved regions as reported. TA demonstrated flexibility in responding to evolving health challenges, particularly during the COVID-19 pandemic and floods. The programme contributed to institutional capacity building through regulatory improvements, digital health strategy development, supply chain management enhancements, and accreditation of retail pharmacies. BHB’s support in developing the ADLRS (online licensing and accreditation software) has been groundbreaking.
However, it was noted that government departments did not always have the capacity to fully benefit from technical support. Specifically, limited follow-up mechanisms for research-based TA interventions led to underutilisation of research findings in policy formulation. Integrating TA better within national governance structures and providing more opportunities to co-design interventions might help to reduce this disconnect, and would help to ensure greater institutional ownership and accountability
Recommendation 1: Explore options to integrate future TA more fully within national governance structures
Effectiveness: The programme demonstrated adaptability and effectiveness in delivering targeted support to the MOHFW and its agencies, despite challenges including financial constraints, shifting development priorities and the COVID-19 pandemic. By embedding flexibility into its operational framework, BHB effectively positioned itself to respond to both immediate needs and long-term sectoral changes, ensuring its contribution extended beyond the duration of the programme. Its ability to adapt, recalibrate and sustain progress in a dynamic environment underscores its role as a resilient and responsive initiative within Bangladesh’s healthcare landscape.
The TA components supported systemic reforms, enhancing governance structures and building institutional capacity. The combined effects of BHB’s contributions to policy influence, midwifery-led care, mentorship and strengthening digital reporting systems have improved maternal and newborn service deliveries at the district level and below, including increased institutional normal deliveries and increased cervical cancer screening as reported in programme MIS and logframe. Similarly, enacting the Drug and Cosmetic Act 2023 was a key step towards safer medicine dispensing practices, addressing AMR and establishing a transparent and efficient system aligned with the HPNSP’s goals of improving system efficiency, transparency and accountability. Findings are well documented in the reports highlighting capacity strengthening of drug dispensers, pharmacy licensing and accreditation and AMR awareness-raising. Achievements beyond the logframe included policy advancements and regulatory reforms, health system strengthening and cross-sectoral collaboration and partnerships on key issues such as AMR and climate resilience. However, lack of enforcement of regulations, constrained government resources and shifting priorities potentially undermine the sustainability of these improvements. In addition, issues with consistency of programme reporting highlighted a need to strengthen and standardise programme reporting frameworks.
- Recommendation 1: Explore options to integrate future TA more fully within national governance structures.
- Recommendation 2: Conduct advocacy with MOHFW to strengthen sustainable financing.
- Recommendation 3: Support interventions to integrate climate resilience measures into health planning.
- Recommendation 4: Support strategic workforce planning to enhance Human Resources for Health.
- Recommendation 5: Support digital health innovation scale-up to increase efficiency and accountability.
- Recommendation 6: Support digital health innovation scale-up to increase efficiency and accountability.
- Recommendation 7: Strengthen programme reporting frameworks.
Sustainability: A major threat to the long-term sustainability of the achievements gained through the BHB are shifting government priorities and the uncertainty surrounding the approval of the 5th HPNSP. Delays in approval and a move away from a SWAp risk the continuity of key BHB-supported interventions, particularly in expanding the midwifery workforce, digital health systems and good pharmacy practices. To ensure continuity, agencies under MOHFW that worked in BHB programme must take decisive steps to safeguard the gains achieved through the programme, particularly by integrating successful interventions into long-term government policies and financial planning mechanisms.
It will be important to strengthen institutional ownership, secure independent funding streams and establish regulatory mechanisms for on-going oversight. Without these commitments, the impact of BHB’s TA risks being eroded, undermining the programme’s long-term contribution to Bangladesh’s health sector.
- Recommendation 1: Explore options to integrate future TA more fully within national governance structures.
- Recommendation 2: Conduct advocacy with MOHFW to strengthen sustainable financing.
Efficiency: Overall, BHB delivered high-impact, low-cost interventions and stands out as a strong VfM model for TA-driven health system strengthening as demonstrated in Annex 12: Value for Money assessment. The programme demonstrated strong VfM across all core pillars, i.e. economy, efficiency, effectiveness, and cost-effectiveness. It effectively utilised financial resources to deliver measurable health improvements, strengthen systems, and introduce sustainable digital innovations. Strategic procurement practices, such as leveraging UN mechanisms and transitioning to government-led training, resulted in significant cost savings. The programme showed high efficiency, with key outputs exceeding targets and automation of drug licensing generating £1.62 million in savings. Effectiveness was evident in substantial improvements in maternal and neonatal health outcomes, reduction in stock-outs, and policy contributions like the Drug and Cosmetics Act 2023.
Cost-effectiveness was particularly strong, with a cost per DALY averted of £99, which is 19 times lower than Bangladesh’s GDP per capita and exceeds WHO benchmarks. Interventions in BEmONC, family planning, and cervical cancer screening collectively [attributable to BHB] averted over 5,000 deaths and 378,000 DALYs, generating £745.75 million in economic benefits. Unit costs for key services remained consistently below Business Case estimates, confirming greater efficiency than anticipated. As above, some issues with consistency of programme reporting highlighted a need to strengthen and standardise programme reporting frameworks.
- Recommendation 7: Strengthen programme reporting frameworks.
- Recommendation 8: Strengthen and standardise VfM frameworks in any future programming.
Equity: The BHB Programme successfully embedded equity as a core principle in its healthcare interventions, demonstrating a commitment to reducing health disparities for Bangladesh’s most vulnerable populations. The programme’s targeted initiatives, from midwifery expansion to gender-inclusive policies and indigenous healthcare interventions, have undoubtedly bridged critical gaps in service delivery. The programme to train pharmacists and drug dispensers through an online platform reached all eight divisions and provided opportunities for those (urban/rural, hard-to-reach areas, gender) to participate in training and capacity building.
However, a closer examination of structural challenges reveals that while progress has been made, systemic barriers still hinder full equity in healthcare access. Without a robust government-led equity framework to sustain the programme’s interventions, the risk of regression remains high. Furthermore, reliance on external funding and project-based deployment models creates a precarious healthcare landscape where essential services for underserved and marginalised population remain vulnerable to discontinuation.
Addressing these sustainability concerns requires a policy shift toward full government integration, budgetary allocation and long-term workforce strategies. Moreover, while impactful, the programme’s approach to equity has not fully addressed deep-rooted socio-cultural and geographical barriers. Gender, disability, and Indigenous healthcare access remain constrained by prevailing stigma, infrastructural limitations, and workforce shortages. To truly achieve equity, the healthcare system must move beyond service provision and toward systemic transformation that includes inclusive policymaking, intersectional equity strategies, and institutional accountability.
Recommendation 4: Continue advocacy and/or support for Social Equity in health service delivery.

# Recommendations
To sustain the long-term benefits of BHB’s TA, the MOHFW must integrate successful interventions into national policies and financing frameworks, ensuring independent funding mechanisms, stronger regulatory enforcement, continuous workforce development and a unified health information system. Given Bangladesh’s climate vulnerability, climate resilience should be integrated into planning, alongside inclusive, gender-sensitive approaches that prioritise marginalised populations. Without these commitments, the progress achieved under BHB risks eroding, limiting its lasting impact on the country’s healthcare system.
Based on the conclusions above, this section sets out key recommendations for Bangladesh’s health sector, with specific recommendations for BHC Dhaka, who commissioned this evaluation, as they plan their next phase of support to the health sector. Effectively, these recommendations answer evaluation question 1.2 What are the recommendations for improvement to help inform the next FCDO’s programme in health (if any)? Recommendations were developed by the team, drawing on the evaluation findings including observations and recommendations from key informants – who were all specifically prompted to provide recommendations for future programming.
To ensure recommendations are pragmatic and actionable, the evaluation team have geared them towards BHC Dhaka – who are expected to use findings to influence change among key stakeholders.
1. Explore options to integrate future support more fully within national governance structures.
The evaluation found that TA played a vital role in strengthening midwifery services, pharmaceutical governance and AMR control. However, in some cases weak institutional integration and bureaucratic inefficiencies hindered the long-term impact of reforms. Options to explore to reduce this risk in the future may include the following:
- Future programmes should be co-designed with government counterparts, with a clear transition strategy that includes funding commitments and institutional ownership.
- If, as seems likely, MOHFW goes forward with a project-based approach for service delivery in the 5th HPNSP rather than the previous sector-wide approach, BHC Dhaka could consider supporting the DGHS and DGFP as they develop Development Project Proposals. This would help to ensure that key service delivery interventions supported by BHB (e.g. midwifery-led care model, cervical cancer screening and other maternal health interventions) are incorporated into these projects.
- BHC Dhaka should collaborate with partners to advocate for increased resource allocation and institutional capacity development of key directorates like DGDA to continue pharmaceutical governance and AMR control interventions initiated by the BHB programme.
- Work with the planning wings of both HSD and MEFWD to ensure that coordination mechanisms introduced during the four previous SWAp programmes are continued, to ensure better coordination between the two divisions and among the directorates (local consultative group platforms, Task Groups, etc.).
Priority: HIGH
Responsibility: BHC Dhaka and partners (UNFPA, WHO or other UN Agencies) in future Bangladesh health programmes in collaboration with HSD and MEFWD planning wings.
2. Conduct advocacy with MOHFW to strengthen sustainable financing
In line with findings and recommendations from the independent evaluation of the 4th HPNSP, this evaluation found that one of the critical challenges observed in the BHB programme was the limited fiscal space for health. Bangladesh allocates less than 1% of GDP to the sector. This financial constraint has led to insufficient domestic investment, high out-of-pocket expenditures and difficulties sustaining TA-driven improvements beyond donor support.
- BHC Dhaka should advocate for increased public health financing, including domestic resource mobilisation strategies.
- BHC Dhaka should explore co-financing arrangements with the MOHFW and development partners to embed long-term financial sustainability into health programmes.
Priority: HIGH
Responsibility: BHC Dhaka, in collaboration with development partners.
3. Support interventions to integrate climate resilience measures into health planning.
Bangladesh remains one of the world’s most climate-vulnerable countries. Future health programmes should therefore integrate climate resilience measures into health planning. This may include:
- Embedding climate resilience strategies into MOHFW’s policy frameworks, ensuring that health facilities in flood-prone and cyclone-affected areas have disaster preparedness and emergency response plans.
- Supporting Green Health Initiatives by piloting solar-powered health facilities, improving water, sanitation and hygiene (WASH) infrastructure and incorporating climate-adaptive technologies in healthcare service delivery.
- Enhancing climate-sensitive disease surveillance to track emerging health risks linked to climate change, such as vector-borne diseases.
Priority: HIGH
Responsibility: BHC Dhaka and its partners in the future health programme in Bangladesh (e.g. UNFPA, WHO or other UN Agencies) in collaboration with the CCHPU of MOHFW.
4. Continuous advocacy and/or support for Social Equity in health service delivery.
To address the persistent geographical disparity in service delivery and socio-economic inequity, subsequent health sector programmes of BHC Dhaka may consider the following:
- Advocacy and support to strengthen pro-poor healthcare financing mechanisms, such as voucher schemes or health insurance models, to reduce out-of-pocket expenditures for marginalised populations.
- Support expansion of community engagement initiatives to ensure inclusive service delivery for ethnic minorities, rural populations and other vulnerable groups.
- Support roll-out of financial incentives and scholarships for women from disadvantaged communities and underserved areas to pursue careers in midwifery and community health work professions.
- Advocacy to government to recruit and train more healthcare workers from indigenous communities, to support culturally appropriate care and help overcome language barriers.
- Translate health education materials and service guidelines into indigenous languages to increase awareness and improve health-seeking behaviour.
- Conduct advocacy for targeted resource allocation for health services in ethnic minority regions through ring-fenced budget allocations in national health plans.
- Advocacy for disability-friendly infrastructure in all public health facilities. To encompass training for healthcare providers on disability-inclusive service delivery and specialised maternal and child healthcare for women with disabilities. Targeted disability screening and rehabilitation programmes at district and Upazila health facilities to ensure early diagnosis and intervention. Strengthen referral pathways for persons with disabilities to access specialised medical and rehabilitation services at tertiary-level hospitals.
Priority: HIGH
Responsibility: BHC Dhaka and its partners in the future health programme in Bangladesh (e.g. UNFPA, WHO or other UN Agencies) in collaboration with the CCHPU of MOHFW.
5. Support strategic workforce planning to enhance Human Resources for Health.
BHB made significant progress in professionalising midwifery services and strengthening human resources in the health sector. However, workforce retention, deployment gaps and bureaucratic delays in HR recruitment remained key barriers. To address these challenges, and enhance HRH, future BHC Dhaka programmes should consider the following options:
- Support to HR policy reforms that institutionalise midwifery-led care models and expand employment opportunities for midwives, nurses and pharmacists within MOHFW structures.
- Integrate Workload Indicators of Staffing Need (WISN) into MOHFW’s HR planning to strengthen workforce planning and forecasting systems
- Support efforts to expand mentorship and professional development programmes for midwives, pharmacists and community health workers to enhance staff retention and service quality.
Priority: MEDIUM
Responsibility: BHC Dhaka and its partners in future health programme in Bangladesh (UNFPA, WHO or other UN Agencies) in collaboration with HR Wings of HSD and MEFWD.
6. Support the scale up of Digital Health Innovations to increase efficiency and accountability.
The BHB programme introduced digital health initiatives such as DHIS2-based health information systems and pharmacy management software. However, digitalisation efforts remained fragmented with varying levels of adoption across districts. Future health programmes should:
- Expand electronic health records systems and strengthen interoperability between digital health platforms to improve data-driven decision-making.
- Support the institutionalisation of digital tools, such as electronic licensing systems for pharmacies, midwifery training e-platforms and telemedicine services to improve health sector efficiency.
- Support strengthening digitisation efforts, such as expanding the ADLRS and enhancing electronic supply chain tracking mechanisms.
Priority: MEDIUM
Responsibility: BHC Dhaka and its partners in future health programme in Bangladesh (e.g. UNFPA, WHO or other UN Agencies) in collaboration with the MIS of DGHS and DGFP.
7. Strengthen programme reporting frameworks.
Future programming would be strengthened by clearer linkages between outputs to outcomes to track progress more easily. This recommendation is based on the review of output and outcome indicators, which found that refining certain indicators would have enhanced their effectiveness to more accurately capture programmatic success without creating an undue reporting burden. (See Annex 8: Understanding the relationship between BHB outputs and outcomes.)
Align indicator definitions and data collection methods
- Harmonise facility-based output indicators with population-level outcome indicators for improved alignment and interpretation.
- To the extent feasible, introduce more targeted output indicators that directly reflect programme activities.
- Expand facility-level tracking for outcomes currently lacking corresponding outputs (e.g., newborn care, essential medicine stock-outs).
Enhance periodic review and validation
- Consider mid-term assessments to evaluate whether output indicators effectively contribute to expected outcomes and adaptive learning.
- Use mixed-methods approaches, combining routine data (DHIS2, programme data) with household surveys (BDHS, Multiple Indicator Cluster Survey (MICS)), observations, and independent studies to triangulate findings.
Consider systemic and contextual factors
- Acknowledge that outcome improvements require multi-sectoral efforts beyond direct programmatic outputs.
- Incorporate process indicators to monitor whether activities are implemented as planned, ensuring a clear linkage between inputs, outputs, and outcomes for a more comprehensive assessment.
Priority: MEDIUM
Responsibility: BHC Dhaka and its partners in future health programme in Bangladesh (UNFPA, WHO or other UN Agencies).
8: Strengthen and standardise VfM frameworks in any future programming
This recommendation is based on based on issues identified in the VfM analysis Annex 12: Value for Money assessment.
- Establish a standardised and adaptive VfM framework and strategy from the outset to ensure all partners align on methods and indicators. The framework should allow for adaptive tracking – reviewing and revising VfM indicators during implementation to reflect operational realities.
- Integrate VfM thinking into programme design, budgeting, and resource allocation. VfM principles, such as cost-efficiency, delivery modality analysis, and marginal cost – should inform the full programme cycle, from design to budgeting and reallocation.
- VfM findings should actively shape resource distribution and prioritisation, rather than serving as post-hoc assessments.
- Require cost reporting at intervention level. Mandate all implementing partners to report financial data at the output or intervention level. This will enable deeper analysis of cost-effectiveness, efficiency, and value drivers.
- Provide specific VfM guidance for TA components, including dedicated guidance and templates to assess VfM in TA-heavy programmes, particularly focusing on indirect outcomes such as policy influence and capacity strengthening.
- Build VfM capacity across stakeholders, strengthening capacity through early training or induction modules for programme staff and partners. This will improve the rigour and consistency of VfM planning, analysis and use throughout the programme.
Priority: MEDIUM
Responsibility: BHC Dhaka and its partners in future health programme in Bangladesh (UNFPA, WHO or other UN Agencies).

# Lessons learned
Lessons learned were presented at a dissemination event held on 20th March 2025 to share findings and recommendations with a wider range of key stakeholders (BHC Dhaka, MOHFW, UNFPA, MSH, WHO). The full report will be shared with FCDO and project partners. Draft findings have already been shared with the person leading the BHB PCR. Lessons learned have also have been summarised in the Executive Summary, which will be available on-line. Key lessons emerging from this evaluation are as follows.
Engagement at the policy level: Policy engagement is crucial to achieve significant impact and broad coverage. BHB’s success is largely attributed to its strategic role in government-level coordination, advocacy for policy reforms and fostering strong partnerships with key stakeholders.
High-quality TA through strategic partnerships: Collaborations with expert organisations, such as those shown in the BHB programme (UNFPA, WHO, and MSH), ensured access to the latest knowledge and best practices. Effective policy implementation should be complemented with robust technical support and continuous skill development at all levels to deliver results. Continuous training and mentorship for knowledge and skill transfer are essential for sustainability and long-term ownership.
Tangible and impact-driven interventions: Successful programmes should be able to demonstrate visible improvements. For example, midwifery training and mentoring have led to increased adoption of skilled birth attendants. Similarly, strengthening pharmacy certification and accreditation systems through online platforms has resulted in measurable achievements in service quality and accessibility.
Scaling interventions for maximum impact and equity: Implementing programmes/ interventions at scale across broader geographic regions enhances impact at the population level. A wide-reaching approach ensures equity by including diverse socio-economic and marginalised populations, promoting more inclusive healthcare access.
Robust monitoring and reporting systems: Effective programme monitoring and reporting require integration of well-defined, measurable indicators into national databases. Systematic tracking of programme performance with a strong feedback mechanism for continuous improvement helps drive progress. Indicators must be carefully selected to generate meaningful and actionable insights, balancing efficiency with effectiveness. While output-level monitoring is essential to track immediate progress, robust outcome indicators are critical to assess interventions' long-term impact on health outcomes and policy effectiveness.
Government ownership: Health interventions supported through TA require strong ownership from the government for long term sustainability. BHB had mixed ownership experiences from MOHFW, which resulted in different outcomes. For example, DGHS, DGFP, and DGNM owned midwifery-led care, which resulted in the deployment of midwives from the revenue budget of health facilities. The outcome was increased skilled birth attendance, in both BHB and non-BHB districts. On the other hand, while DGDA has appreciated systems like ADLRS and PMS, frequent leadership changes have not allowed the directorate to take full ownership of these systems. Hence, these remained dependent on external funding till the end of the programme.
Enabling regulatory environment: TA interventions designed to change systems should be backed by an appropriate regulatory environment, including the introduction and/or enforcement of appropriate regulatory actions. For example, while model pharmacy initiatives were initiated, weak enforcement of relevant regulatory actions to prevent antibiotic selling without prescription reduced commercial incentives for model pharmacies.
Focusing solely on low-performing districts does not automatically ensure equitable healthcare access: While BHB successfully targeted underperforming regions, it did not fully address the unique barriers faced by women, indigenous communities and persons with disabilities. Future programmes should incorporate intersectional analyses to design interventions that address these challenges, ensuring no vulnerable groups are left behind.
Prioritise leadership development: TA programmes must prioritise leadership development within government institutions. Many government officials trained under BHB were later transferred to non-health roles, resulting in a loss of institutional knowledge. Future programmes should incorporate leadership development, mentorship and succession planning to retain expertise within the health sector.
Regulatory reforms require political buy-in and stakeholder engagement. The passage of the Drug and Cosmetics Act 2023 faced resistance from influential pharmaceutical industry stakeholders, delaying its implementation. Future programmes should proactively engage policymakers, industry leaders, and civil society early to foster consensus and minimise resistance to change.

# Annex 1: Terms of Reference

TERMS OF REFERENCE
Evaluation of technical assistances provided by Better Health in Bangladesh (BHB) Programme
1. Introduction

Better Health in Bangladesh (2018-2025) is a £65.61 million UK bilateral health programme that provides technical assistance to support the implementation of the 4th Health, Population and Nutrition Sector Programme (HPNSP, 2017-2024) of the Government of Bangladesh (GoB). Additionally, it will support the design and roll out of the 5th health sector programme. Key programme documents, such as the Business Case, Logframe and Annual Reviews can be accessed on DevTracker.1
The programme is being delivered through the following components:
• Financial assistance to the HPNSP (£27.6m) through a Multi Donor Trust Fund
(MDTF) managed by the World Bank.
•	Technical Assistance (TA) through United Nations (UN) agencies (28.0m), led by United Nations Population Fund (UNFPA) working on Sexual and Reproductive Health and Rights (SRHR) interventions in 20 pilot districts across Bangladesh and at the central policy level.2
•	Technical assistance through NGO (£9.36), delivered by Management Sciences for Health (MSH) to improve the stewardship, governance and regulation of the health sector, specifically registration and licensing of pharmacies. The TA to Health Population and Nutrition Programme is also being provided by this component.3
•	A Monitoring, Evaluation and Learning (MEL) component (£0.75m) to generate evidence and carry out evaluations.

The intended impact of the programme is for all citizens of Bangladesh to enjoy good health and well-being. There two outcomes that will contribute towards the impact are:
•	citizens of Bangladesh, especially women, children and the poor, increasingly utilise quality family planning, health and nutrition services; and
•	health, family planning and nutrition services are delivered increasingly by effective and efficient health systems.

A Theory of Change of the programme is included in Annex A.

1 See: https://devtracker.fcdo.gov.uk/programme/GB-1-203864/documents
2 Further information on the UNFPA led TA is available at Better Health in Bangladesh: Health Systems Strengthening Technical Assistance | UNFPA Administrative Agent
3 Further information on the MSH led TA is available here: https://msh.org/projects/bhb/
.

BHB is aligned with British High Commission (BHC) Dhaka’s Business Country Plan (BCP) Goal 3 on Women Girls and Global Health. The goal is: Combined UK development support and diplomatic lobbying contributes to improving systems, policies and practices in Bangladesh that educates and empowers its people, especially women and girls, to protect their rights, fulfil their potential and live a healthy life. To achieve this goal, BHB is addressing priority areas including i) Women and Girls (W&G) by improving SRHR services, piloting up cervical cancer screening and empowering midwives and ii) Global Health by health systems strengthening (HSS), addressing climate change and health and tackling antimicrobial resistance (AMR).
BHB adopted the shift in FCDO’s operating model in Bangladesh, focusing on targeted TA alongside British High Commission (BHC) Dhaka’s engagement in policy influencing. BHB is supporting GoB in achieving a sustainable, inclusive and resilient health system capable of delivering Universal Health Coverage, as Bangladesh prepares to graduate from United Nations (UN) Least Developed Country (LDC) status in 2026. Further details of the programme including the business case, logframe, annual reviews are available at: https://devtracker.fcdo.gov.uk/programme/GB-1-203864/documents.
The 4th HPNSP was extended another two years to June 2024. An independent impact evaluation has been commissioned by the World Bank Bangladesh to evaluate the sector programme.

2. Purpose, scope and objectives
Purpose
The primary purpose of this evaluation is to evaluate the technical assistance interventions of the programme and inform and strengthen future health programming, policy and institutional governance of the health sector in Bangladesh. This should document the key lessons learnt from the programme.

Scope
The scope of the evaluation is to assess the relevance, effectiveness, equity, sustainability and efficiency of the technical assistance provided over the entire course of programme
implementation (2018-24). Coherence and impact are not covered in this evaluation because of
insufficient time availability and funding. It is not intended to cover all areas of delivery, just the technical assistance components. The Financial Assistance to MDTF is not within the scope of this evaluation as a separate evaluation has been commissioned for that. The MEL component will also not be covered under this evaluation.
The content and depth of the evaluation will be guided by the indicative evaluation questions, to be further developed by the evaluation team against the OECD DAC criteria. The evaluation team should submit an evaluation matrix as part of the Inception Report
Some of the cross-cutting issues like gender, poverty, capacity building, governance are already covered in the programme and will be part of the focus of the evaluation. Some of the other cross-cutting like human rights, HIV/AIDS, environment and power relations are not within the scope of this work.
The geographical coverage of the programme varies by interventions. The UN TA covers some of the national level health systems related activities and also providing targeted TA in selected
20 low performing districts. The NGO TA supports health sector programme activities, provides technical assistance to strengthen capacity of Directorate General of Drug Administration (DGDA) and regularity functions of DGDA in selected 32 districts.
Objectives
The objectives of this evaluation are to:
- Identify lessons from the programme's technical assistance work, including on the contribution TA has made and, on its relevance, effectiveness and sustainability;
- Assess value for money (VfM) of the key interventions;
- Assess if the BHB ToC has been implemented and if the key assumptions have changed during the programme cycle.
- Identify the main factors that are influencing the achievement of the results from BHB
interventions.
- Inform the programme completion report (PCR) of the programme;
- Provide recommendations for future health policy and programme interventions in
Bangladesh.

3. Evaluation Questions
The evaluation questions proposed relate to Organisation for Economic Co-operation and Development's (OECD) Development Assistance Committee (DAC) Evaluation Criteria on relevance, effectiveness, sustainability and efficiency:
Relevance
- To what extent has the technical assistance responded to the priorities and policies of the HPNSP (2017-2024)
- What are the recommendations for improvement to help inform the 5th health sector?
Effectiveness
- To what extent did the technical assistance achieve the intended outcomes (as set out in the logframe and theory of change)? What were the key factors contributing to the successful achievements?
- Was Technical Assistance the most appropriate intervention or would others have been more appropriate?
Sustainabilit

What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?
What evidence is there that the benefits of the technical assistance will be sustained?
Efficiency
- How effective was the various technical assistance interventions compared to the cost of respective technical assistance?
- Did the programme achieve good value for money (VfM)?
Equity
How the programme addressed gender equality, equity, poverty and inclusion aspects?

Evaluation team will be responsible to include other relevant questions during the inception phase of the programme in consultation with BHB Dhaka and implementing partners.

4. Methodology
It is expected that the evaluator will use a process and mixed methods approach to collect data and information from a range of sources and informants, specifically:
- Process evaluation to analyse if the technical assistance is being implemented as intended, if the design is working and identify any gaps, what is working, what is not working and why.
- Mixed methods (quantitative and qualitative) evaluation to investigate what changes have been made as a result of the technical assistance, the scale of the change and the extent to which these changes can be attributed to the technical assistance provided.

The evaluator will be expected to pay attention to triangulating the data and information collected to form an assessment and provide recommendations based on findings. This is essential to ensure an evidence-based and credible evaluation, with robust analysis. The evaluation findings should be disaggregated by age, sex and geography, where possible. The evaluators may consider collecting secondary data on comparison groups from existing routine data sources like DHIS-2, Sample Vital Registration Systems (SVRS) etc.
The above methodology is suggested based on the nature of the programme, data sources, budget and timeline. However, the evaluators may propose alternative methodologies and that can be finalised during the inception phase.
The safeguarding and ethical requirements are included in Annex B and Annex C respectively

5. Risks
The potential risks for implementing this evaluation are:
- Limitations and data quality issue of secondary data from routine sources
- Political instability and related uncertainty on availability and access to the stakeholders
- Tight timelines
The evaluator will be responsible for developing a risk matrix with mitigation strategy during the inception phase of the evaluation.
6. Data Sources
Secondary documents review
- Programme documents and datasets from partners (quantitative and qualitative data) including the business case, annual reviews, partner reports.
- Government policies, plans (Programme Implementation Plan, Operational Plan, monitoring and management plan of 4th HPNSP, government health policy, health strategy of MOHFW) and World Bank’s independent impact evaluation of the 4th HPNSP.
- FCDO funded study by John Hopkins Bloomberg School of Public Health on Impact of Skilled Midwives on Saving Maternal and Newborn Lives in Bangladesh.
- FCDO funded study by Brown University on cervical cancer screening in Kurigram, Bangladesh.
- FCDO funded study by ICDDR,B on factors for retention of Grade A pharmacists for model pharmacies and suitability of Grade B dispensers as ‘Pharmacist in Charge’ in model pharmacies in Bangladesh.
- FCDO funded study by ICDDR,B on assessing Good Pharmacy Practice (GPP) among pharmacy technicians in model pharmacy and model medicine shops in selected districts in Bangladesh.
- FCDO funded trial study by ICDDR,B on the introduction of pre-conception care through the public health system to improve maternal health and family planning service utilisation among young women in rural Bangladesh.
- Analysis of programme monitoring data, Health Management Information Systems (HMIS), Sample Vital Registration System (SVRS) and other secondary sources.
- Desk review of available secondary data (documents and literature) related to the programme interventions.
Primary data collection
- The evaluator will be expected to conduct stakeholder consultations through structured and semi-structured interviews and focus group discussions. The key stakeholders to be interviewed include: FCDO staff involved in the programme; implementing partners UNFPA and MSH; government officials, downstream partners, development partners such as the World Bank, beneficiaries, civil society. The evaluator will undertake field visits to project sites and conduct on-site observation of the results achieved by the programme. Implementing partners (UNFPA and MSH) will facilitate access to beneficiary informants during the planning stage and in the field and assist introductions to relevant authorities. FCDO will make introductions to stakeholders at the Ministry of Health and Family Welfare (MOHFW) and other relevant departments.
- The evaluator may also consider carrying out Focus Group Discussions with programme beneficiaries.
It should be noted that all data and metadata are owned by FCDO. The evaluator should ensure that in the initial design and methodology, the datasets to be collected are comprehensively documented. FCDO will have unlimited access to the material produced by the evaluator (as stated in the FCDO’s general conditions of contract). This gives FCDO the right to request all underlying data (quantitative and qualitative), anonymised and in a suitable, accessible format.
7. Timeframe, Deliverables and Budget
The work is expected to be finalised within 4-5 months and should be completed by March 2025 to coincide with programme completion end date. The evaluation findings will be used in the PCR of the programme which is due in June 2025. The evaluation is expected to start from mid- October 2024. The indicative timeline for when the deliverables should be completed are shown in the table below.
Evaluation Deliverable	Estimated Timeline	Responsibilities
Initial meeting with Evaluation	Within a week of the contract signing	BHC Dhaka, Evaluator
team
Inception Report	Within 4 weeks of contract signing	Evaluator,	BHC	Dhaka,
Quality Assured		EQUALS
Use and Influence Plan	Within 6 weeks of contract signing	Evaluator
Draft Report	Within 16 weeks of contract / signing	Evaluator,	BHC	Dhaka,
Quality Assured		EQUALS
Final Report	Within 20 weeks of contract / signing	Evaluator, BHC Dhaka
Published
Dissemination of the findings from	Within 20 weeks of contract signing	Evaluator
the final report
FCDO Management Response	Within 4 weeks of the report being / published	BHC Dhaka

Further details of some of the deliverables are listed below.
Inception Report should include: evaluation objectives, questions, methodology, workplan, evaluation use and influence plan
Draft and Final report should include: Executive Summary of key findings and recommendations (2 pages maximum), descriptive analysis of health institution and governance context and the appropriateness of the BHB interventions, assessment of the programme achievements against key outcomes and VfM. Key lessons learnt, recommendations for BHC Dhaka to use for future programmes and ongoing influence work. Full datasets collected.
- Dissemination of the evaluation findings with keys stakeholders. The evaluators will be responsible for organising this event with approximately 30-40 participants.
- A 2-page summary of the finalised evaluation report for publication on the FCDO’s website.
The total budget for this evaluation is£100,000 including the cost for the dissemination event. The Level of Efforts (LoE) should include at least 150 days of international and national team members inputs. The timelines for the deliverables will be agreed by FCDO in consultation with the evaluator.
The proposal should include a total budget, inclusive of all applicable taxes. The budget allocation per deliverable and per team member should be outlined. DAI is requested to maximise quality deliverables and the best value for money for FCDO from this exercise.
Use and Influence Plan
It is intended that the findings from the evaluation will be used to help inform decisions on the influencing strategy in BHC Dhaka on health system strengthening and capacity building. The supplier will be expected to produce a dissemination plan on how the findings will be shared with recipients and how the recommendations will be shared with recipients. The plan should include stakeholder mapping, timelines for evaluation outputs and dissemination, tailored
stakeholder engagement. This will be required as part of the Inception Report.
Quality and Payment by Results
The evaluator should quality assure all deliverables before submitting to BHC Dhaka. The evaluation reports will be subject to further targeted quality assurance by BHC Dhaka and the FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS). This will provide assurance that quality expectations of the evaluation outputs have been met and EQUALS feedback should be incorporated into the final draft, which will be a requirement before payment of each deliverable. The deliverables should adhere to the FCDO branding requirements (Annex D).
Payments will be made on a milestone basis with each deliverable being subject to a quality threshold as defined above for each milestone to be fully completed.
8. Recipient
The primary recipient for the evaluation is the BHC Dhaka, Other recipients are Ministry of Health and Family Welfare of Government of Bangladesh, BHB implementing partners and other development partners. The assessment will be used by BHC Dhaka to inform future interventions (programmatic, policy and diplomacy) and to determine approach for working with the interim government to inform policy dialogue.
The findings and recommendations will be used to provide a better understanding of the areas that FCDO has had maximum impact and can influence the state to make further improvements. Something around providing value for money. The evaluation findings will be shared with the Country Board of BHC Dhaka. The Deputy High Commissioner and Development Director and Deputy Development Director of BHC Dhaka will use the findings of the evaluation to make an informed decision on the future health programming in Bangladesh. This process is likely to take place during July – December 2025.
9. Governance and Management
The evaluation will be overseen by the BHB programme team, specifically the BHB Programme Responsible Owner (PRO) and Senior Responsible Owner (SRO) with evaluation advice provided by Statistics and Results Adviser. The BHC Dhaka team will be responsible for approving all evaluation outputs and commenting on draft reports, alongside the quality assurance reviews from EQUALS. The PRO has the additional responsibility for leading on the production of the evaluation management response and implementation of the agreed recommendations.
The evaluation will be fully independent. The implementing partners will not have any direct influence on the evaluation to minimise potential conflict of interest. However, they will be supporting the evaluators in provision of programme documentation, datasets and access to government officials and beneficiaries.
Within BHC Dhaka, the main points of contact will be:
- Technical aspects: Lead Adviser
- Delivery aspects: Programme Responsible Owner (PRO)
- Logistics: Programme Officer
The evaluator will be responsible for recruiting and deploying all the experts as necessary to conduct and manage the evaluation. The proposal should clearly set out anticipated roles and responsibilities, leadership and points of contact. It is important that the proposal provides information on how quality will be assured for the evaluation and who will be responsible for this
It is equally important that all draft outputs are produced and delivered to a high standard. The evaluator will be responsible for finalising methodology and data collection tools in consultation with FCDO. These should be included in the Inception Report including evaluation matrix and evaluation timelines.
The evaluator will provide regular updates to BHC Dhaka on progress of the evaluation. BHC Dhaka health team members will have bi-weekly calls/ meetings with the evaluation team.
10. Evaluator requirements
We would expect the evaluator team to have the following skills set:
- Academic qualification: The team members should have post-graduate or graduate qualifications in public health, health economics and or other relevant discipline.
- Extensive and proven experience of carrying out research studies and evaluations especially in the public health area.
- Sound knowledge about the health systems of Bangladesh as well as about the 4th
- HPNSP of MOHFW and the sector wide approach as a whole.
- Extensive experience and expertise on information/data collection to use appropriate methods and methodologies from different stakeholders, beneficiaries, implementers including MOHFW and its relevant directorates such as DGHS, DGDA, DGME, DGFP.
- Excellent oral and written communication skills in English.
- The team should have a balance of international and national members including health systems expert and economist.
A gender balance is preferred within the evaluator team. The evaluator will be responsible for all logistical arrangements and for all duty of care for all travel within the contract.
11. Requirements for the bid
The interested bidders are requested to submit:
- Technical proposal: not more than 5 pages, including organisational profile, relevant experiences, proposed approach and timeline
- CVs of the relevant proposed personnel: 2 pages maximum per person (counted outside the 5 pages above)
- Budget including number of days, fee rate, days, reimbursable expenses and overhead
Annex A: Theory of change
Theory of change of Better Health in Bangladesh (BHB) programme

Annex B: Safeguarding
FCDO maintains a zero-tolerance approach to sexual exploitation and abuse within Supplier organisations, which includes their downstream supply chains. We expect FCDO partners to follow our lead and robustly consider environmental and social safeguards through their own processes. The capacity of our partners to do this and their effective performance will be a key risk assessment factor in programme delivery and monitoring and evaluation.
The Supplier will have responsibility for assessing safeguarding policies and practices of consortium members and downstream partners. Supplier(s) will comply with all FCDO safeguarding policies and will be required to demonstrate that they have robust approaches in place to reduce the risk of bullying, harassment and exploitation and to manage instances if they take place.
FCDO requires assurances regarding protection from violence, exploitation and abuse through involvement, directly or indirectly, with FCDO suppliers and programmes. This includes sexual exploitation and abuse but should also be understood as all forms of physical or emotional violence or abuse and financial exploitation.
The Supplier must demonstrate a sound understanding of the ethics of working in this area and applying these principles throughout the lifetime of the programme to avoid doing harm to beneficiaries. In particular, the delivery of interventions including research and programme evaluations should recognise and mitigate the risk of negative consequences for women, children and other vulnerable groups. The supplier will be required to include a statement that they have a duty of care to informants, other programme stakeholders, and their own staff and that they will comply with the ethical principles in all programme activities. Their adherence to this duty of care, including reporting and addressing incidences, should be included in both regular and annual reporting to FCDO.
A commitment to the ethical design and delivery of evaluations, including the duty of care to informants, other programme stakeholders and their own staff, must be demonstrated.
The Supplier will be requested to conduct an Environmental and Safeguarding Risk Assessment during the Inception phase, to consider the potential positive and negative environmental impacts of programme activities (for example related to use of reusable materials in training).
Annex C: Ethical principles and standards
Suppliers are required to refer to ethical guidelines available at https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation- and-monitoring-activities.
Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.
Annex D: UK International Development Branding
The successful Supplier will be responsible for ensuring full adherence with the guidance on when and how to use UK International Development branding on all elements of the Programme. Full guidance on how and when to use the UKAid logo and branding can be found at https://www.gov.uk/government/publications/official-development-assistance-oda-funded- programmes-branding-guidance
Annex E: Schedule of Processing, Personal Data and Data Subjects
This schedule must be completed by the Parties in collaboration with each other before the processing of Personal Data under the Contract. Any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and / Processor for each Category of Data / Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this Call-down Contract. / 1) The Parties acknowledge that Clause 33.2 and 33.4 (Section 2 of the contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 33.3 in respect of the following Personal Data: / • [to be determined]
Subject matter of the processing
Duration of the processing
Nature and purposes / of / the / processing

Type of Personal Data [and Special
Categories of Personal Data]
Plan for return and destruction of the	(UNLESS requirement under EU or European member state law to preserve that type of data)
data once processing complete

# Annex 2: BHB programme coverage
The table below shows the 32 districts that received BHB TA directly. MSH provided TA to all the districts, while UNFPA provided TA to 20. The first column shows the administrative divisions covered by BHB TA. The second column shows which districts were covered within each division. The third column shows which TA provider(s) provided support.
Division	District	TA Component
Barisal	Barisal	MSH, UNFPA
	Bhola	MSH, UNFPA
	Jhalokathi	MSH
	Patuakhali	MSH, UNFPA
	Pirojpur	MSH, UNFPA
Chatagram	Bandarban	MSH, UNFPA
	Brahmanbaria	MSH
	Chatagram	MSH, UNFPA
	Cox’s Bazar	MSH, UNFPA
	Cumilla	MSH
	Noakhali	MSH, UNFPA
Dhaka	Dhaka	MSH, UNFPA
	Faridpur	MSH
	Gazipur	MSH, UNFPA
	Kishoreganj	MSH
	Manikganj	MSH, UNFPA
	Narayanganj	MSH
	Narsingdi	MSH, UNFPA
Khulna	Jashore	MSH
	Khulna	MSH, UNFPA
	Satkhira	MSH, UNFPA
Mymensingh	Jamalpur	MSH, UNFPA
	Mymensingh	MSH
	Netrokona	MSH, UNFPA
Rajshahi	Bogura	MSH, UNFPA
	Naogaon	MSH
	Pabna	MSH
	Rajshahi	MSH
Rangpur	Dinajpur	MSH
	Kurigram	MSH, UNFPA
	Nilphamari	MSH, UNFPA
Sylhet	Sylhet	MSH, UNFPA

The map below shows the administrative divisions that received support from the two BHB TA components (MSH and UNFPA)

Bangladesh administrative divisions directly supported with TA funded by BHB (UNFPA and MSH)

# Annex 3: Use and influence plan
This Use and Influence Plan outlines the strategy for disseminating the findings and lessons from this evaluation of Technical Assistance (TA) components of the Better Health in Bangladesh (BHB) programme to maximise its impact on strengthening Bangladesh’s health system. The two-page executive summary will be publicly available on-line. The evaluation report itself will be a critical resource for informing future health programming and policy development, particularly for FCDO and the Ministry of Health and Family Welfare (MOHFW) in Bangladesh. Additionally, it provides valuable insights for development partners, donors and other stakeholders working toward achieving Universal Health Coverage by 2030.
The plan is structured to ensure that all relevant audience, both primary and secondary, are engaged in a way that aligns with their roles and responsibilities within Bangladesh’s health sector. Primary audiences include those decision-makers directly responsible for designing and implementing programmes, while secondary audiences include partners and stakeholders whose contributions influence the health system.
Opportunities to engage stakeholders in the design of this evaluation were limited, primarily because the evaluation only covers part of the BHB programme. The Results-Based support component has already been evaluated and engaging largely the same stakeholders for a second round of evaluation would be duplicative and unrealistic within the evaluation’s tight timeframe. However, preliminary results were shared with the key stakeholders who participated in interviews for their verification and vetting (maybe in the form of a remote presentation) as well as general interest and information on the evaluation’s findings.
The table below provides a detailed breakdown of the key audiences, the outcomes expected from their engagement with findings and the tailored dissemination methods designed to achieve these outcomes. The schedule took into account Eid, when many key informants will be on leave. Following this, a schedule of dissemination activities highlights the planned efforts to share and apply the findings effectively. This approach ensures that the evaluation's insights are leveraged to drive evidence-based decision-making and foster collaboration among all stakeholders.

Audience	Rationale for engagement	Expected outcomes	Dissemination/ influencing
British High Commission (BHC) Dhaka / (primary audience)	Insights from the evaluation will directly inform their strategic planning and future programmes.	Decisions on shape of the next FCDO health programme (if any) in Bangladesh are directly informed by eval findings. / Wider efforts to support Bangladesh's health system and achieve Universal Health Coverage by 2030 are directly informed by evaluation findings.	Direct sharing of comprehensive report and two-page summary. / Internal presentation to BHC Dhaka detailing findings and recommendations.
MOHFW (primary audience)	Key government body responsible for health policy and programme implementation in Bangladesh. Currently considering a transition from Sector Wide Approach (SWAp) to a programmatic approach.	Ministry’s transition plan is directly informed by evaluation lessons learnt. / Specific transition interventions in areas like Sexual and Reproductive Health (SRH), Maternal, Newborn, Child and Adolescent Health (MNCAH), Drug Administration, Anti-microbial Resistance (AMR) and Health Workforce Planning are directly informed by eval lessons learned.	Direct sharing of the final report and summary. / External dissemination event – focusing on lessons learnt. / Engagement with BHC Dhaka around findings and recommendations. (Note: this sits outside the evaluation team’s sphere of control)
BHB partners (secondary audience)	Partners such as World Bank (WB), World Health Organisation (WHO), United Nations Population Fund (UNFPA) and Management Sciences for Health (MSH) work closely with MOHFW and play a crucial role in implementing health programmes. Alignment with evaluation findings will ensure consistency and efficiency in programme design and delivery.	Partners demonstrate interest in evaluation findings/lessons and consider aligning future programming. / Convening together around the discussion of the eval findings promotes enhanced collaboration/alignment.	Invitations to the external dissemination event. / Access to the full report and summary.
Donors and TA partners (secondary audience)	Donors and technical assistance partners provide funding and expertise for health initiatives. / Sharing findings encourage alignment of their contributions with evidence-based priorities for the health sector.	Partners demonstrate interest in evaluation findings/lessons and consider aligning future programming. / Increased understanding of efficient and impactful use of resources.	Invitations to the external dissemination event. / Access to the full report and summary.
Broader stakeholder community (secondary audience)	Researchers, policy advocates and other actors interested in Bangladesh’s health system. Disseminating the findings can promote evidence-based decision-making.	Raise awareness of evaluation findings among a wider audience. / Encourage evidence-based decision-making across the health sector.	Making final report and summary publicly accessible.

Use and influence plan.

Activity	Audience	Purpose	Timing
Internal and External Presentation	FCDO and key stakeholders	Share findings, recommendations and limitations to inform FCDO’s decision-making.	Second week of March
External Dissemination Event	Wider stakeholders: MOHFW, BHB Partners, Donors, TA	Present actionable lessons and foster collaboration among stakeholders.	Third week of March
Comprehensive Report Distribution	FCDO, MOHFW, BHB Partners	Provide a detailed account of evaluation findings for integration into policy and programs.	After report finalisation
2-Page Summary Publication	Broader Stakeholder Community	Increase accessibility and awareness of key findings and lessons from the evaluation.	After report finalisation
Follow-Up engagements (FCDO responsible)	FCDO, MOHFW, BHB Partners	Provide clarification and support for applying evaluation findings.	As needed post-dissemination

Dissemination Activities Schedule

# Annex 4: Evaluation framework and questions
Evaluation Questions / (Original Questions)	Data Sources	Data Collection Methods	Analysis Methods
RELEVANCE
To what extent has the technical assistance (TA) responded to the priorities and policies of the Health, Population and Nutrition Sector Programme (HPNSP) (2017-2024)?	Strategic Investment Plan and Programme Implementation Plan of 4th HPNSP (2017-2024) / End Evaluation Report of 4th HPNSP / Programme documents of BHB / Key respondents from MOHFW and its relevant agencies (Directorates General of Drug Administration (DGDA), Family Planning (DGFP), Health Services (DGHS) and Nursing and Midwifery (DGNM)); Key respondents from FCDO, United Nations Population Fund (UNFPA) and Management Sciences for Health (MSH)	Document review / Key informant interviews (KIIs)	Thematic Analysis

What are the recommendations for improvement to help inform the next FCDO’s programme in health (if any)?	Annual Reviews of Better Health in Bangladesh (BHB) / Business Case / PCRs submitted by UNFPA and MSH / End Evaluation of 4th HPNSP	Document Review / KIIs	Thematic Analysis

EFFECTIVENESS
To what extent did the technical assistance achieve the intended outcomes (as set out in the logframe and theory of change)?	BDHS, 2024 / Routine data from DHIS2 / Programme Completion Reports of UNFPA and MSH / Annual Reports of UNFPA and MSH / Independent study reports	Extract available indicators (outcome indicators) / Analysis of programme data (output indicators)	Trend analysis (change over time

What were the key factors contributing to the successful achievements?	Key respondents from MOHFW and its agencies (DGHS, DGFP, DGNM and DGDA); key respondents from UNFPA and MSH; Beneficiaries and service providers at health facilities and pharmacies	KIIs	Thematic Analysis
Was Technical Assistance the most appropriate intervention, or would others have been more appropriate?	Business Cases; Key respondents from FCDO, UNFPA and MSH	Document review / KIIs	Comparative Case Study Analysis

SUSTAINABILITY
What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?	End Evaluation of 4th HPNSP / Annual reports of BHB / Key respondents from MOHFW and its agencies (DGHS, DGFP, DGNM and DGDA) / Pharmacists and other workers from Model Pharmacies and Drug Dispensaries	Document Review / KIIs / IDIs	Thematic Analysis

What evidence is there that the benefits of the technical assistance will be sustained?	End Evaluation of 4th HPNSP / Annual reviews of BHB / Key respondents from MOHFW and its agencies (DGHS, DGFP, DGNM and DGDA) / Pharmacists and other workers from Model Pharmacies and Drug Dispensaries	Document Review / KIIs / IDIs	Thematic Analysis

EFFICIENCY
How effective were the various technical assistance interventions compared to the cost of respective technical assistance?	Financial documents	Document Review	Cost-effectiveness analysis.
Did the programme achieve good value for money (VfM)?**	Logframe data, annual reviews of BHB, completion reports from implementing partners. / Financial and procurement data: Available cost reports and procurement records. / Health outcome data: Indicators from service delivery data (e.g., maternal and neonatal health, facility readiness, contraceptive uptake). / Economic and modelling tools: / Lives Saved Tool (LiST) for estimating maternal and neonatal deaths averted. / Marie Stopes International (MSI) Impact 2 Model for contraceptive impact assessment. / Disability-Adjusted Life Years (DALYs) approach to estimate health benefits. / Cost-effectiveness thresholds based on Bangladesh’s GDP per capita (£2,057).	Document reviews / KIIs	VfM analysis
EQUITY
How did the programme address gender equality, equity, poverty and inclusion aspects?	Annual Reports of BHB Program / Programme Completion Reports of UNFPA and MSH / Key respondents from FCDO, UNFPA and MSH / Key respondents from the agencies (DGHS, DGFP and DGNM) / Beneficiaries	Document Review / KIIs / IDIs	Gender Equality and Social Inclusion (GESI) Analysis. / Limited form of GESI focusing on programme’s inclusion of marginalised population.

# Annex 5: Methods
Methods largely followed the plans presented in the Inception Report, with the exception that during the evaluation, the decision was made to include two case studies. Methods are summarised in the main report. The team applied a mixed-methods approach to address the evaluation questions, to ensure a comprehensive analysis of purpose, application, and outputs of the Better Health in Bangladesh (BHB) programme’s technical assistance (TA) components. The team conducted a document review, key informant interviews (KIIs), analysis of secondary quantitative data, field observations, Gender and Social Inclusion (GESI) analysis, value for money (VfM) analysis and case studies. Field observations further enriched the evaluation by offering contextual insights into programme implementation and on-the-ground realities.
Document Review
The core team conducted a document review, which was a central approach to understanding the programme’s context, activities, and coverage. The reviewed documents are set out in Annex 7: Document review matrix and range from informal descriptions of activities to formal reports, mainly developed by the TA providers, and Annual Reviews of the programme commissioned by FCDO. Key documents of Ministry of Health and Family Welfare (MOHFW), including the Strategic Investment Plan and Programme Implementation Plan and relevant Operational Plans of 4th Health, Population and Nutrition Sector Programme (HPNSP) were also included in the analysis.
Logframe and Theory of Change review
As part of the document review, the evaluation team reviewed the Theiry of Change (ToC) and logframe. While the ToC provided a useful high-level overview of the programme as a whole, the team based their analysis of how the programme aimed to achieve change – its expected change pathways – on the logframe. This offered a more structured and operational framework to assess these intended pathways. The evaluation team assessed the programme logframe, tracking changes from 2018 to 2024. The team also reviewed the logframe’s adaptability by assessing revisions, milestone modifications, and emerging priorities. The team focused the change pathway line of enquiry on the logframe rather than the ToC, as the latter was intentionally broad and offered limited utility for testing change pathways. In so doing, the team explored relationships between the output indicators and outcome indicators including measurement, data sources, and how the output indicators contributed toward the outcome indicators. See Annex 8: Understanding the relationship between BHB outputs and outcomes. The team also reviewed the ToC, examining whether processes, output, outcomes and impact aligned broadly with the programme interventions. Because of time and resource constraints, it was not feasible to review the logframe or ToC with stakeholders.
Key Informant Interviews (KIIs)
KII sampling strategy: A structured selection approach was used to ensure that the evaluation team engaged the most relevant and knowledgeable individuals, aligning with the evaluation’s objectives and information needs. Informants were purposively selected to ensure the inclusion of key stakeholders with relevant expertise and institutional affiliations. The Evaluation Technical Lead developed an initial list of key informants, drawing on the desk review of project documents and his knowledge of the BHB programme acquired through his participation in the evaluation of the 4th HPNSP. This initial list was then shared with FCDO who recommended additional respondents, thereby broadening the range of sectors included in the interviews. During the evaluation, additional respondents were identified through snowball sampling, primarily identified and facilitated by BHB implementing partners including United Nationals Population Fund (UNFPA) and Management Sciences for Health (MSH). This allowed key informants to suggest further participants.
The key informants included officials from the MOHFW, representatives from agencies under the Director General at both the central (Dhaka) and decentralized levels (district and subdistrict), as well as implementing partners such as UNFPA, World Health Organisation (WHO), and MSH. Other relevant stakeholders were also engaged in the study. A detailed breakdown of key respondents by category is provided in Annex 9: Key informants interviewed.
The list of key respondents was finalized and agreed upon with FCDO during the inception phase. Given the complexity, large scale, and multi-year scope of the BHB programme, which was deeply embedded within the government health systems, there were no truly external individuals who were both independent and sufficiently knowledgeable to serve as key informants. While the Government of Bangladesh played a critical partnership role, its agencies (Directorate General of Health Services (DGHS), the Directorate General of Drug Administration (DGDA), and the Directorate General of Family Planning (DGFP), and Directorate General of Nursing and Midwifery (DGNM)) were not direct implementers. Implementation was led by UNFPA and MSH. Other development partners were involved only in their own projects under the broader 4th HPNSP and did not have detailed insight into the specific BHB components, making them unsuitable as key informants.
Selection of respondents was gender-blind as respondents were identified based on their official roles, institutional affiliations, and expertise relevant to the BHB programme. In total 58 key informants were interviewed (30 male and 28 female). It was noted that at senior government levels, such as the DGHS, DGFP, DGDA, the majority of key informants were male. Conversely, respondents from the DGNM were all female. At the field level, the evaluation team communicated with both service providers and health managers. At the service provider level, due to the predominant system of Bangladesh, most service providers (nurses and midwives) were female. Among representatives from international organizations, UNFPA and WHO respondents were predominantly female, while MSH had a more gender-diverse representation.
KIIs were a key method to collect primary qualitative data. The KIIs aimed to capture the experiences and perspectives of those closely involved with the programme. Interviews were conducted individually or in groups, based on the informant’s preference. Semi-structured interview guides with open-ended questions, tailored to different informant groups, were used. Annex 6: Interview guide and checklists. While the initial interview guides are broadly generic, they were fine-tuned and adjusted to suit the specific category of respondents. Instead of pre-testing, after initial interviews the guide was edited for clarity.
The respondents for the KIIs comprised of TAs and government level stakeholders (UNFPA and WHO, MSH, DG, service providers) and were inherently limited in number. Each type of key informant offered unique perspectives and insights into the BHB programme. Interviewees were contacted directly by the team to arrange appointments and there was a very high acceptance rate. The process was driven by the Evaluation Technical Lead who is well connected in Bangladesh through his long experience in the country’s health sector which facilitated rapid contact, with support from other team members. The VfM expert made his own appointments, though most meetings of the meetings he scheduled were also attended by the Team Leader.
The team made every effort to accommodate interviews, including meeting a recently-retired senior health official at his house because he was unable to travel. Interviews were conducted in person or remotely, primarily in Bangla, except for two joint interviews with UNFPA and WHO where international staff participated which were conducted in English. With respondents’ verbal consent, interviews were recorded, transcribed and later deleted. Follow-up questions were asked if needed through further communication with the informants.
Secondary Data Analysis (Quantitative)
Logframe data: For this evaluation, the evaluation team focused on outcome- and output-level indicators from the logframe. The logframe includes key impact indicators, such as the Maternal Mortality Ratio (MMR) and Total Fertility Rate (TFR), which are sourced from national datasets like the Sample Vital Registration System (SVRS) (published annually) and the Bangladesh Demographic and Health Survey (BDHS) (conducted every 3 to 5 years). These indicators provide insights into the country’s progress toward achieving Sustainable Development Goals (SDGs).
While the BHB programme contributed to improvements in these impact indicators, this evaluation does not seek to attribute causality or quantify BHB’s direct impact on them. However, recognizing BHB’s contributions, the evaluation team reported on the status of these indicators based on logframe data.
The team also received additional programme data directly from UNFPA. During review, the team identified some quality issues with this data. To address these the team lead was in regular communication with the UNFPA data focal point to clarify inconsistencies and better understand challenges in data collection and reporting. It became clear that the facility-level staff, including nurses and midwives, were going through a steep learning curve on how to report. Initially, data were submitted through Google Docs before moving to an online portal, which impacted the consistency and quality of the data. The team could not verify the programme data against DHIS2 data. As a result, after careful discussion the team decided to mainly use logframe data and use programme data in a limited capacity to provide additional insights into the findings.
The analysis focused on BHB-supported districts. However, where applicable, the team assessed changes over the programme’s lifespan and compared findings between BHB and non-BHB districts to provide a broader context for the programme’s influence.
Field observations
The team visited two BHB districts – Bagerhat and Gaibandha. The sites were selected purposively after discussing with FCDO. Emphasis was given to visit south of the country (Bagerhat) and north (Gaibandha) and to visit specific areas; Green Health Initiative in Mongla and Sampara UHC for Santal population.
Visits included district hospitals, Upazila Health Complexes (UHCs) and a Nursing and Midwifery Training Institute in Bagerhat. In these locations, the team conducted KIIs with administrators, doctors, nurses and midwives. Of the 58 KIIs conducted, 22 were interviewed in the field (14 female). See Annex 9: Key informants interviewed.
In Mongla, during the visit to the BHB-funded UHC that transitioned into a Green Health Initiative, the team reviewed and assessed the transformation and discussed its implementation with administrators, service providers and partner representatives from the NGOs supporting the initiatives – Partners in Health and Development and Khulna Mukti Seba Sangstha. Key informants shared their insights and views on BHB’s role in this novel initiative in the context of Bangladesh. Annex 10: Case study: Green Healthcare Initiative at Mongla Upazila Health Complex.
In Gaibandha, the team visited a Sampara UHC serving Santal populations (indigenous population), where midwives from the community had been trained with BHB funding and currently deployed. The team listened to the insights of how training of women as midwives and subsequently engaging them in the service motivated the local community toward midwifery. Annex 11: Case study: Midwifery-led care (MLC) model under the BHB programme. The team also identified some of the challenges and limitations in terms of sustainability of the approach adopted by BHB.
Additionally, the team observed pharmacies and drug stores in Gaibandha and Jessore. A total of 20 pharmacies (10 per district) were visited. MSH provided a list of the model pharmacies in these areas, but the pharmacies were not pre-warned about the visits by MSH. The visit included both pharmacies/medicine shops that were identified as models by MSH and also others that were not under the MSH programme. The team used a check list during observation (see Annex 6: Interview guide and checklists.).  As part of the process of completing the observation checklist, the team talked to people present in the drug store at that time, who may or may not have been a pharmacist. These discussions were not KIIs or in-depth interviews but were conducted to gather additional information to fill out the observation checklists.
Gender Equality and Social Inclusion (GESI)
To address the equity-related evaluation questions, the evaluation team primarily relied on qualitative methods, using secondary data from the document review to explore how interventions considered gender, socio-economic status (e.g., marginalized and hard-to-reach populations), and geographic location (urban vs. rural). Due to the unavailability of reliable and updated disaggregated quantitative data from secondary sources and limited time period of the evaluation, there were limited possibilities for disaggregated data analysis. The evaluation team did, however, disaggregate Key Informants by gender. Due to the nature of the programme being evaluated, Key Informants were selected based on their professional role. Differences in the distribution of gender at different professional levels therefore directly reflect this.
It is important to note, however that the intervention areas predominantly focused on upazila health facilities, which, the endline evaluation of 4th HPNSP of MOHFW mentioned, serve primarily women from middle-to-lower income groups and from rural areas. The endline evaluation acknowledged the pro-poor nature of the midwifery service provision from the public health facilities and indicated is as a best practice to uphold equity in the Bangladesh Context.
[note] Independent Endline Evaluation Team (IEET). 2024. Endline Evaluation of 4th HPNSP. Unpublished
The UNFPA-led TA component of the BHB programme was inherently pro-women and pro-rural, given its emphasis on midwifery and reproductive health, which naturally involved female service providers and service recipients. For the MSH programme, which focused on training of pharmacy staff and improving good pharmacy practices, the team reviewed the PCR to see if gender segregated indicators are presented in the report. No further in-depth analysis was done on the MSH programme.
Case-studies
While case studies were not originally included in the methodology, the idea to present the UNFPA-supported Midwifery-Led Care (MLC) model and Green Health Initiative (GHI) as case studies emerged organically during the evaluation process. The Evaluation Lead and Team Lead identified these two initiatives as noteworthy during discussions with key stakeholders including FCDO, UNFPA, DGHS, and DGNM.
The selection was based on their significance within the programme’s broader objectives. MLC was a foundational component of the midwifery intervention that was implemented in all the UHCs in Bangladesh. GHI was an innovative, collaborative pilot between the Ministry’s Climate Change and Health Promotion Unit and Dhaka University, implemented at a single Upazila Health Centre. The case studies were not designed to be comparative but to present two distinct and illustrative strategies within the BHB programme. These two approaches stood out during the interviews and document reviews as having sufficient depth and relevance for case study treatment. See Annex 10: Case study: Green Healthcare Initiative at Mongla Upazila Health Complex and Annex 11: Case study: Midwifery-led care (MLC) model under the BHB programme.
Initially, the MLC case study came from reviewing the end evaluation report of the 4th HPNSP of MOHFW, as it was designated as one of the best practices of the sector programme. KIIs with DGNM officials, health facility managers, midwives, and staff from the midwifery institute further informed the case study. Field visits helped to contextualize the mentorship component, a key element of MLC implementation. The GHI case study was based on interviews with key informants at the Climate Change and Health Promotion Unit and Dhaka University, and relevant programme staff and facility personnel at the UHC.
Case studies were developed collaboratively by the evaluation team with input from all team members. Stakeholders were not directly involved in co-producing the case studies but contributed insights through interviews.
Value for Money (VfM)
Value for Money analysis was led by an expert VfM Expert who worked closely with the evaluation team and communicated regularly with the Team Lead, who also facilitated further liaison and communications between the VfM expert and UNFPA, WHO, and MSH.
The VfM Expert set up virtual meetings with different teams and the Team Lead participated in most of the calls to understand and facilitate the documents, data, and other relevant information needs. While using quantitative data, the team consulted and used the same data source where applicable (mainly the final logframe data shared by FCDO).
In this evaluation of BHB programme, the VfM was conducted using the four-pillar VfM framework, evaluating the programme’s performance in terms of economy, efficiency, effectiveness, and cost-effectiveness (detailed methodology is included in Annex 12: Value for Money assessment).
- Economy: whether inputs (e.g., medical supplies, training, and technical assistance) were procured at the lowest cost without compromising quality.
- Efficiency: how well inputs were converted into outputs, analysing training completion rates, TA delivery timeliness, digital innovations, and stock-out reductions.
- Effectiveness: to what extent the programme achieved intended outcomes, focusing on maternal and neonatal health improvements, cervical cancers screened, stock-out reductions, service deliveries.
- Cost-effectiveness: Used Disability-Adjusted Life Years (DALYs) averted monetising health benefits using Bangladesh’s Gross Domestic Product (GDP) per capita for key interventions (e.g., midwifery services, family planning, cervical cancer screening).

The VfM assessment relied on the following sources and tools:
- Programme reports: logframe, annual reviews, and completion reports from implementing partners.
- Financial and procurement data: Available cost reports and procurement records.
- Health outcome data: Indicators from service delivery data (e.g., maternal and neonatal health, facility readiness, contraceptive uptake).
- Economic and modelling tools such as Lives Saved Tool (LiST) for estimating maternal and neonatal deaths averted; DALYs approach to estimate health benefits; cost-effectiveness thresholds based on Bangladesh’s GDP per capita (£2,057).

The methodology applied recognises that not all outcomes can be fully attributed to the programme alone. For example, the provision of Basic Emergency Obstetric and Newborn Care (BEmONC) services depends on a combination of programme inputs and resources provided by the broader health system, such as existing infrastructure, human resources, and operational funding, which were not directly financed by the project. Therefore, to estimate the programme’s attributable contribution to observed outcomes, the team agreed a financial contribution-based attribution approach. Attribution was applied to all impacts estimated [e.g. deaths averted, economic benefits generated etc].
Ethical Considerations
The evaluation adhered to FCDO’s ethical standards. which served as the guiding framework for obtaining informed consent, conducting interviews, maintaining verbal informant confidentiality, ensuring data protection, and planning for the timely dissemination of findings to relevant stakeholders. The evaluation team made sure that the design and implementation of the evaluation, particularly the discussions and interactions with the key informants, adhered to the socio-economic, cultural and political context of Bangladesh.
[note] DFID ethical guidance for research, evaluation and monitoring activities
Safeguarding measures were implemented to prevent harm and address potential power imbalances. Separate interviews with potentially more vulnerable key informants such as younger midwives or junior staff at health centres were considered as a precautionary measure but were not considered feasible. As part of the ‘do-no-harm’ policy of the ethical considerations, the evaluation team did not disclose the names of the pharmacies and drug stores that participated in the evaluation to respect their wish to remain anonymous and avoid revealing potentially commercially sensitive information about their business.
Informed consent was obtained verbally before initiating interviews. At the start of each discussion, key informants were given an overview of the evaluation’s objectives and scope to ensure they had accurate information before consenting to participate. This included obtaining consent for audio recording of the interviews. To protect participant confidentiality, audio recordings and transcriptions were securely stored in a Microsoft (MS) SharePoint folder, with restricted access limited to team members directly involved in data collection and analysis. This ensured compliance with ethical standards while safeguarding sensitive information. The evaluation team used quotes and insights from the KIIs, however, to preserve anonymity they did not provide names, or locations that might indirectly identify any individual.
Data Analysis
A triangulation approach was used to enhance the validity and reliability of the findings by integrating information from document reviews, field observations, KIIs, and secondary quantitative analysis. This approach ensured a comprehensive evaluation by cross-verifying evidence from multiple sources.
Qualitative Analysis. Qualitative data from KIIs were analysed using thematic analysis to address key evaluation questions. After translation and transcription, codes were generated using Atlas.ti software, and themes were identified within the evaluation framework. Insights and perspectives gathered through KIIs were verified and supplemented with information from document reviews and quantitative analyses whenever feasible. Transcribed summaries of KIIs were disaggregated by type of respondents (government, TAs, district and sub-district level officials, service providers). The document review followed the same thematic framework, ensuring alignment with qualitative findings. It provided valuable context by examining programme details, published data (secondary sources), and historical progress and challenges. Findings were integrated with qualitative insights from KIIs to develop a holistic understanding of programme impact. Additionally, documents were examined for quantitative data to support and corroborate qualitative evidence.
[note] https://atlasti.com/
Quantitative Analysis. The team analysed quantitative data from secondary sources to assess the program’s achievements over time. The primary data was the programme’s logframe, which was populated using a range of data sources including routine programme data, DHIS2, BDHS, and the SVRS. Most analysis, including descriptive and trend analysis, was conducted using Excel. No statistical testing or advanced analysis on correlation was performed.
The logframe evolved over the course of the program. The team used the latest versions shared by FCDO approved for annual review to finalise analysis. A summary of the logframe changes and their rationale is included in Annex 14: Reasons for revisions of logframe indicators as reported in 2024 logframe.
The team received additional programme data directly from UNFPA. The team observed data quality issues and inconsistencies with some of the logframe indicators. After reviewing the data and clarifying some inconsistencies in the data sets with UNFPA, the team decided that the programme data still holds value, but only used the data in a limited capacity. The team and the VfM expert worked from the same data sources to ensure consistency.

# Annex 6: Interview guide and checklists
A) Interview guide for respondents from MOHFW, DGHS, DGFP, DGNM, DGDA and PCB
Section 1: Context and alignment (for all respondents)
1. In what ways did the TA activities align with the strategic priorities of the 4th HPNSP? (Probing Areas: Specific policies or strategic objectives supported by the TAs; Evidence of alignment with operational plans (e.g., SRHR, AMR, midwifery services); Examples of activities that contributed directly to HPNSP priorities).
2. How did the TAs adapt to evolving health sector priorities? (Probing Areas: Emerging health challenges (e.g., AMR, digital health systems); Inclusion of underserved regions and vulnerable groups in TA interventions).
Section 2: Impact of UNFPA TA on SRHR (for respondents from DGHS, DGFP and DGNM)
1. How has the TA influenced SRHR service delivery at the district and national levels? (Probing Areas: Success in scaling up interventions like cervical cancer screening; Impact of SRHR initiatives in underperforming districts; Challenges in service delivery and how they were addressed).
2. What changes have midwifery services brought to maternal and neonatal health outcomes? (Probing Areas: Availability and distribution of trained midwives; Integration of midwifery services into existing health systems; Feedback from beneficiaries on midwifery services).
3. How have TA activities addressed gender equity and access barriers? (Probing Areas: Inclusion of women, adolescents and marginalised groups; Strategies used to reduce disparities in SRHR access).
Section 3: Impact of MSH TA on health system governance (For respondents from HIS-eH, DGFP MIS, DGDA and PCB)
1. What has been the TA’s impact on improving pharmacy practices and governance? (Probing Areas: Implementation of Good Pharmacy Practice (GPP) guidelines; Progress in automating drug licensing and renewal systems; Role of the DGDA in sustaining these improvements).
2. How has the TA supported AMR policy development and implementation? (Probing Areas: Progress in enacting AMR-specific policies; Coordination between stakeholders (DGDA, DGHS, etc.) on AMR initiatives; Impact of AMR interventions on pharmacy practices and public health).
3. How effective has the TA been in strengthening health information systems? (Probing Areas: Success stories in digitising data collection and analysis; Usage of digital tools by policymakers for planning and decision-making; Challenges in scaling and sustaining digital health initiatives).
Section 4: Lessons Learned and Sustainability (For all respondents)
1. What mechanisms have been established to sustain the benefits of these TAs? (Probing Areas: Capacity-building initiatives within directorates; Institutional ownership and funding commitments; Plans to scale successful interventions nationwide).
2. What are the key lessons from these TAs for future health programming? (Probing Areas: Examples of interventions that worked well and why; Areas where adjustments are needed for greater impact; Recommendations for designing the 5th HPNSP).
Section 5: Coordination and implementation challenges (For all respondents)
1. How well did coordination work between the TAs and government directorates? (Probing Areas: Communication and alignment across agencies (MOHFW, DGHS, DGDA, etc.); Effectiveness of partnerships with UNFPA and MSH; Suggestions for improving coordination mechanisms).
2. What challenges did the TAs face in implementation and how were they resolved? (Probing Areas: Bureaucratic delays; Resource constraints (financial, human, technical); Political or external factors influencing programme execution).
Section 6: Recommendations for policy and programme design (For all respondents)
1. What policy changes would help strengthen future TA initiatives? (Probing Areas: Specific areas needing regulatory updates or reforms; Suggestions for enhancing government readiness and capacity).
2. How can the design and delivery of TAs be improved? (Probing Areas: Adjustments needed for better alignment with health system needs; Strategies to ensure equity and efficiency in TA delivery).

B) Interview guide for respondents from MSH
Section 1: Programme relevance
1. How well were MSH’s TA activities aligned with the goals and priorities of the 4th HPNSP? (Probing Areas: Specific operational plans or strategic objectives supported by MSH-led TA; Contribution to governance and regulatory reforms in the health sector; Adaptation to emerging health system needs (e.g., AMR, pharmacy regulation)).
2. How were the TA’s focus areas identified and prioritised? (Probing Areas: Process for selecting governance, regulation and pharmacy system improvements; Engagement with MOHFW, DGDA and other directorates in identifying key needs; Adjustments made to maintain relevance during implementation).
Section 2: Governance and regulatory improvements
1. What were the key achievements in improving pharmacy practices and governance? (Probing Areas: Implementation and uptake of Good Pharmacy Practices (GPP) guidelines; Automation of drug licensing and renewal systems; Support for enacting the Drug and Cosmetic Act 2023).
2. How did MSH support AMR-related policy and system improvements? (Probing Areas: Development and operationalisation of AMR policies; Engagement with DGDA, DGHS and other stakeholders on AMR initiatives; Challenges faced in building a multisectoral approach to AMR).
3. How has the TA contributed to building the capacity of government institutions? (Probing Areas: Training, workshops and resources provided to strengthen regulatory capacity; Examples of institutional ownership and leadership in sustaining improvements; Support for data-driven decision-making in governance and regulation).
Section 3: Health Systems strengthening
1. What progress has been made in strengthening health information systems? (Probing Areas:
2. Implementation of digital tools for health data collection and analysis; Use of digital systems for policy development and regulation; Challenges in ensuring the adoption and scalability of digital systems).
3. How has MSH contributed to strategic frameworks and policy development in the health sector? (Probing Areas: Specific policies or strategies influenced by MSH-led TA; Mechanisms for integrating governance reforms into broader health policies; Impact of these contributions on achieving HPNSP objectives).
Section 4: Coordination and collaboration
1. How effective was the collaboration with MOHFW and directorates like DGDA and DGHS? (Probing Areas: Mechanisms used to ensure alignment with government priorities; Level of government ownership and participation in TA activities; Challenges in navigating bureaucratic processes or ensuring buy-in)
2. How did MSH coordinate with other development partners involved in the health sector? (Probing Areas: Collaboration with UNFPA, WHO and other stakeholders; Examples of joint initiatives or complementary activities; Challenges and successes in ensuring synergy between interventions).
Section 5: Sustainability and long-term impact
1. What measures have been put in place to sustain the benefits of MSH-led TA? (Probing Areas: Institutionalisation of governance and regulatory reforms; Continued use of digital systems and AMR policies post-TA; Risks to sustainability and strategies to address them).
2. How has the TA ensured that capacity built within government institutions is retained? (Probing Areas: Training and mentorship programmes for government staff; Knowledge transfer mechanisms for continued implementation of reforms; Challenges in ensuring long-term capacity retention).
Section 6: Monitoring, Learning and Adaptation
1. How were MSH’s interventions monitored and evaluated for effectiveness? (Probing Areas: Indicators tracked and lessons learned; Use of evaluation findings to refine activities during implementation; Examples of course corrections based on monitoring data).
2. How did MSH adapt its approach to changes in the health system or external environment? (Probing Areas: Adjustments made in response to policy shifts or health sector challenges; Flexibility in addressing unexpected barriers or leveraging new opportunities).
Section 7: Recommendations and future directions
1. What are the key lessons learned from the implementation of MSH-led TA? (Probing Areas: Successful strategies for governance and regulatory improvements; Areas requiring more focus or different approaches; Recommendations for designing the 5th HPNSP and future TAs).
2. What are MSH’s priorities for future involvement in Bangladesh’s health sector? (Probing Areas: Opportunities for continued engagement in health system governance; Potential for innovation in AMR, pharmacy regulation and digital health; Recommendations for fostering sustainable partnerships with the government).
C) Interview guide for respondents from UNFPA
Section 1: Programme relevance
1. How well were UNFPA’s TA activities aligned with the priorities of the 4th HPNSP? (Probing Areas: Specific operational plans or strategic objectives supported; Adaptation to emerging health sector needs, including SRHR and underserved populations; Evidence of contributions to gender equity and Universal Health Coverage).
2. How was the scope of TA determined and how responsive was it to government needs? (Probing Areas: Processes for identifying priority areas for intervention; Feedback mechanisms with MOHFW and other stakeholders; Adjustments made during implementation to meet evolving demands).
Section 2: Impact on SRHR services
1. What changes did the TA bring to SRHR services in pilot districts and nationally? (Probing Areas: Success in scaling up interventions such as cervical cancer screening; Expansion of access to contraceptive services and family planning; Support for reducing maternal and neonatal mortality rates).
2. What has been the impact of midwifery-focused interventions on maternal and neonatal health outcomes? (Probing Areas: Recruitment, training and deployment of midwives; Challenges in midwife retention and integration into the health system; Feedback from health facilities and beneficiaries on midwife services).
3. How has UNFPA ensured that TA activities address gender disparities in access to health services? (Probing Areas: Strategies used to target marginalised and vulnerable populations (e.g., rural women, adolescents); Measures to enhance male involvement in SRHR; Results achieved in reducing gender-based disparities).
Section 3: Coordination and implementation
1. How effective was the collaboration with MOHFW and its directorates (e.g., DGHS, DGFP)? (Probing Areas: Mechanisms for ensuring coordination and alignment; Challenges in navigating government processes or bureaucratic hurdles; Lessons learned for improving collaboration in future programming).
2. What challenges did UNFPA face in implementing TA activities and how were these addressed? (Probing Areas: Barriers in capacity-building efforts or scaling interventions; Issues related to funding, logistics, or workforce availability; Political or external factors influencing programme delivery).
Section 4: Monitoring, Learning and Adaptation
1. How were TA activities monitored and evaluated to ensure effectiveness? (Probing Areas: Indicators tracked and results achieved; Use of data for decision-making and course correction; Examples of adaptations based on monitoring and evaluation (M&E) findings).
2. How has UNFPA contributed to knowledge sharing and capacity building among stakeholders? (Probing Areas: Training sessions, workshops, or knowledge products developed; Sharing of global best practices in SRHR with local stakeholders; Integration of lessons learned into future programming).
Section 5: Sustainability and long-term impact
1. How has the TA strengthened institutional capacities within MOHFW and other local entities? (Probing Areas: Capacity development in SRHR, health governance and data management; Evidence of increased local ownership of interventions; Sustainability plans for midwifery services and other TA outcomes).
2. What measures have been taken to ensure the sustainability of TA-supported improvements? (Probing Areas: Institutionalisation of new policies, practices, or services; Funding commitments or resource mobilisation by the government; Risks to sustainability and strategies to mitigate them).
Section 6: Recommendations and future directions
1. What key lessons have been learned from the implementation of the UNFPA-led TA? (Probing Areas: Examples of successes and areas for improvement; Insights for designing the 5th HPNSP and future Tas; Recommendations for integrating SRHR into broader health systems).
2. What are UNFPA’s priorities for future health sector support in Bangladesh? (Probing Areas: Potential areas of focus under the 5th HPNSP; Opportunities for innovation in SRHR and health systems strengthening; Strategies to enhance collaboration with government and development partners).

FIELD VISIT CHECKLISTS
Illustrative checklist for visits of healthcare facilities (Upazila Health Complex)
- Is the Upazila Health Complex well-maintained and clean?
- Does the facility have proper signage for easy navigation (e.g., for maternity services, family planning, immunisation)?
- Are there functional health management information systems (HMIS) for tracking patient records, service delivery and health outcomes?
- Are skilled birth attendants available during childbirth?
- Is the facility equipped for basic emergency obstetric and newborn care?
- Are midwives deployed and fully trained at the facility? How many midwives are present and licensed?
- Is the facility providing comprehensive maternal care, including antenatal care and postnatal care?
- Are there systems in place for preventing and managing complications like postpartum haemorrhage (PPH)?
- Is the facility conducting cervical cancer screenings for women (e.g., using Human Papillomavirus testing)?
- Are necessary equipment and supplies available for safe deliveries and newborn care?
- Are family planning services available, including modern contraceptive methods (e.g., implants, IUDs, oral contraceptives and injectables)?
- Is there counselling available for family planning and reproductive health, particularly targeting adolescents and young women?
- Are there specific services tailored for women and girls, including safe spaces and services for survivors of gender-based violence (GBV)?
- Are there visible materials (posters, pamphlets) promoting SRHR awareness and services?
- Is family planning information and counselling offered to all women seeking reproductive health services?
- Are contraceptives available for a wide range of methods and are they stocked regularly to prevent shortages?
- Are service providers trained to offer informed choices regarding family planning methods, including addressing myths and misconceptions?
- Are contraceptive use rates being tracked at the facility level?
- Is there a system in place to follow up with women who receive family planning services, ensuring they have the support they need for continued use?
- Are there dedicated services for adolescents and young people, including sexual and reproductive health (SRH) education, family planning and gender-based violence (GBV) prevention?
- Is the facility promoting the availability of youth-friendly spaces and services for counselling, family planning and HIV/STI prevention?
- Are there outreach programmes for youth, including education on puberty, menstrual health and sexual rights?
- Is there a dedicated service or referral system for survivors of gender-based violence?
- Are service providers trained in handling cases of GBV, including providing appropriate support, counselling and medical care?
- Is there a referral system in place for victims of GBV to access legal, psychological and medical assistance?

KII checklist for health facility staff (e.g. Midwives, nurses, Obs/Gyn and medical officers)
1. Could you briefly describe your role at this health facility? (Probing Areas: Your primary responsibilities (e.g., maternal care, family planning, general health services); How long you’ve been working here and your experience with midwifery or nursing).
2. Have you received any training or support through the BHB programme? If yes, please elaborate. (Probing Areas: Type of training (e.g., midwifery skills, AMR awareness, use of digital tools); Who provided the training (e.g., UNFPA, MSH); Impact of the training on your daily work and patient care).
3. Have you observed any changes or improvements in the services provided at this facility due to the programme interventions and/or the trainings they provided? (Probing Areas: Specific services (e.g., maternal and neonatal care, family planning, SRHR); Availability of essential supplies and equipment; Changes in patient outcomes or satisfaction levels)
4. How have midwifery services been integrated into this facility’s operations? (for midwives) (Probing Areas: Your role as a midwife and key challenges you face; Collaboration with other staff (nurses, doctors, administrators); Feedback from patients on midwifery care).
5. Have you noticed any changes in gender equity or access to healthcare services? (Probing Areas: Barriers faced by women or marginalised groups in accessing care; Measures taken to address these barriers (e.g., community outreach, free services); Success stories or remaining gaps in gender-inclusive healthcare).
6. Have you been trained or involved in using digital health systems (e.g., data collection, patient records)? (Probing Areas: Specific tools or systems used at this facility (e.g., e-MIS, DHIS-2); Benefits and challenges of using these tools; Impact on decision-making, patient care, or facility management)
7. What role do you play in data collection or reporting at this facility? (Probing Areas: How often you input or review data; Challenges in maintaining accurate and timely records; Use of data for improving patient care or facility operations).
8. What challenges do you face in providing quality healthcare at this facility? (Probing Areas: Shortages of supplies, staff, or training; Coordination with other staff or external stakeholders; Specific challenges related to maternal and neonatal care or pharmacy practices).
9. Do you feel adequately supported in providing your services to the service recipients? (Probing Areas: Availability of mentorship, supervision and refresher training; Accessibility of essential resources (e.g., medicines, equipment, staffing).
10. What has been the most significant change in patient care due to the BHB programme? (Probing Areas: Improvements in maternal and neonatal health outcomes; Increased patient trust or satisfaction with services; Examples of cases where the programme made a noticeable difference).
11. Do you think the improvements introduced by the programme can be sustained in the long term? (Probing Areas: Institutional or community support for sustaining changes; Risks or challenges in maintaining the improvements after the programme ends).
12. What would you recommend to improve the support provided to healthcare workers under this programme? (Probing Areas: Specific areas for more training, resources, or mentorship; Ideas for better integrating midwifery or digital systems into facilities).
13. What additional support or initiatives do you think are needed to strengthen healthcare at your facility? (Probing Areas: Priorities for future programmes or policy changes; Areas for further innovation or scaling of successful interventions).

Illustrative Checklist for Model Pharmacies/Drug Retail Outlets
- Is the retail medicine shop clean and well-organised?
- Are there clear signage and labels indicating services provided (e.g., prescription filling, consultation)?
- Are all required licenses (e.g., DGDA registration) visible and up-to-date?
- Are the pharmacy staff trained in GPP, including the safe dispensing of medications and patient counselling? Have pharmacy staff received training on AMR and COVID-19-related issues?
- Are there visible educational materials on GPP and antimicrobial resistance (AMR) in the pharmacy?
- Has the pharmacy been accredited by the DGDA? If yes, is there visible evidence of this accreditation?
- Is the pharmacy actively using the Pharmacy Management Software (PMS) to track expiration dates and manage inventory?
- Is there evidence that the pharmacy promotes awareness about antimicrobial resistance (AMR) to customers?
- Are antibiotics sold with clear guidance on usage, risks and the importance of adhering to the prescribed treatment duration?
- Are there any public awareness campaigns about AMR visible in the pharmacy (e.g., posters, pamphlets)?

KII Checklist for Pharmacists or Drug Retailers at Pharmacy/Drug Stores
1. Could you describe your role in this pharmacy and your primary responsibilities? (Probing Areas: Length of time in the role and experience in pharmacy practice; Types of services provided (e.g., dispensing, advice, health product sales).
2. Have you received any training or capacity-building support related to pharmacy practices through the BHB programme? (Probing Areas: Type and provider of training (e.g., MSH, DGDA); Topics covered (e.g., AMR, Good Pharmacy Practices [GPP]); Impact of the training on your knowledge and daily practices).
3. Are you aware of the GPP guidelines introduced under the BHB programme? If yes, how have these influenced your practices? (Probing Areas: Specific practices adopted (e.g., record-keeping, patient advice); Challenges in implementing GPP in your pharmacy; Perceptions of GPP’s impact on service quality and customer trust).
4. Have there been any changes in licensing or regulatory requirements for this pharmacy in recent years? (Probing Areas: Experience with the drug licensing and renewal process; Use of automated systems for licensing (if applicable); Feedback on the efficiency and transparency of regulatory changes; Availability and Quality of Medicines).
5. Has the availability or quality of medicines improved due to the programme’s interventions? (Probing Areas: Access to essential medicines, especially antibiotics; Any observed reductions in counterfeit or substandard medicines; Challenges in maintaining a consistent supply).
6. Are you aware of antimicrobial resistance (AMR) and its importance in healthcare? How did you learn about it? (Probing Areas: Sources of information (e.g., training, public health campaigns); Understanding of AMR and its implications for pharmacy practice).
7. How have your practices changed in response to AMR policies or training under the programme? (Probing Areas: Advice provided to customers on antibiotic use; Efforts to limit over-the-counter sales of antibiotics; Challenges in educating customers about responsible antibiotic use).
8. Are you using any digital tools or systems introduced under the programme for pharmacy operations or reporting? (Probing Areas: Experience with automated licensing or reporting systems; Benefits and challenges of using these tools; Suggestions for improving digital integration in pharmacies).
9. Do you contribute data (e.g., sales, inventory) to government or regulatory bodies? If yes, how is this process managed? (Probing Areas: Frequency and method of data sharing; Perceived usefulness of the data for improving pharmacy operations or public health outcomes).
10. What challenges do you face in running this pharmacy effectively? (Probing Areas: Issues with medicine supply chains or regulatory compliance; Knowledge gaps among pharmacy workers or customers; Financial or logistical barriers to improving services).
11. What have been the most noticeable changes in pharmacy practices or customer experiences due to the BHB programme? (Probing Areas: Improvements in service quality, medicine availability, or customer trust; Success stories or examples of positive changes in your community).
12. Do you think the improvements introduced by the programme can be sustained in the long term? (Probing Areas: Institutional support for sustaining changes; Risks or barriers to maintaining progress, such as funding or enforcement gaps).
13. What could be improved in the support provided to pharmacists under this programme? (Probing Areas: Areas needing more focus, such as training, resources, or regulatory support; Ideas for better engagement with pharmacy workers or the community)
14. What additional support or initiatives are needed to strengthen pharmacy practices in your area? (Probing Areas: Recommendations for scaling successful interventions; Suggestions for addressing unmet needs in pharmacy governance or operations).

# Annex 7: Document review matrix
Title	Organisations / Authors	Year	Overarching Content	Purpose
Better Health in Bangladesh (BHB) programme Business Case (BC) / DevTracker Programme GB-1-203864 Documents	FCDO	2018	Rationale for BHB programme in Bangladesh	BHB programme overview / Theory of Change (ToC)
Addendum to the Business Case. BC addendum	FCDO	2023	Rationale for proposed budget and programming changes.	BHB programme overview
BHB Annual Reviews / DevTracker Programme GB-1-203864 Documents	FCDO	2019, 2021, 2022, 2023, 2024	Progress, changes in ToC, recommendations	Indicator status / Context of programme performance / Value for Money (VfM) calculation
Endline Evaluation of 4th Health, Population and Nutrition Sector Programme (HPNSP) (Unpublished)	Independent Endline Evaluation Team (IEET).	2024	Overall progress of the 4th HPNSP, unfinished agenda and way forward	Status of the some of the Impact and outcome level indicators of BHB / Context of the HNP sector of Bangladesh, the progress and challenges
Mid Term Report of 4th HPNSP	Independent Review Team (IRT)	2020	Progress of 4th HPNSP till midterm	Same as above
Programme Completion Report (PCR)	Management Sciences for Health (MSH)	2024	Progress and status of MSH Technical Assistance (TA) under BHB	Programme activities and performance of MSH TA

Title	Organisations / Authors	Year	Overarching Content	Purpose
Frontiers | Assessment of the impact of good pharmacy practices training among drug dispensers in Bangladesh	Ali Sunjida Binta et al. Frontiers, Vol. 14.	2023	Good Pharmacy Practice (GPP) indicators status related to trained pharmacy technicians	Programme’s performance (MSH)
Impact of Skilled Midwives Report	John Hopkins University/ FCDO	2024	Study on maternal and neonatal lives saved by scaling up midwifery	Programme performance United Nationals Population Fund (UNFPA) / VfM Calculation
Annual Report of WHO and UNFPA to FCDO	UNFPA and World Health Organisation (WHO)	2024	Annual status update of UNFPA TA	Programme activities and performance
Programme Implementation Plan and Revised Programme Implementation Plan of 4th HPNSP	MOHFW	2017 and 2022	Overall programme design of 4th HPNSP	Context of the BHB programme, macro level issues and targets
Short documentaries provided by FCDO	FCDO	2024	MSH and UNFPA’s activities, context and performance presented in short videos	Programme activities, performances / Service providers, beneficiaries perspectives
Bangladesh Demographic and Health Survey (BDHS), 2022	National Institute of Population Research and Training (NIPORT) and ICF	2023	Progress of country against key goals in health sector	Status of the some of the Impact and outcome level indicators of BHB
Feasibility Study of 5th HPNSP. Ministry of Health and Family Welfare (MOHFW). Dhaka, Bangladesh	MOHFW	2024	Feasibility study	Context of sector of Bangladesh, the progress and challenges; Recommendations
Study on Training Costs – Public vs NGO Training Mechanisms in Pakistan	Asia Pacific Journal of Rural Development	2021		Cost benchmarks for VfM Analysis.
Adding It Up: The Costs and Benefits of Investing in Sexual and Reproductive Health	Guttmacher Institute.	2020		Cost Benchmarks for VfM Analysis.
Comparative Analysis of UN Procurement Mechanisms – Kyrgyzstan, Tajikistan, Uzbekistan, BACKUP project, GIZ.	Gesellschaft für Internationale Zusammenarbeit(GIZ)	2021		Cost Benchmarks for VfM Analysis.
Supply Catalogue and Procurement Reference Data	UNICEF	2024	Supply Catalogue and Procurement Reference Data	Cost Benchmarks for VfM Analysis.
Contraceptive Price Indicator	UNFPA	2023	Comparative price indicator data	Cost Benchmarks for VfM Analysis.
Value for money assessment: Institutionalize infection prevention control, strengthen oxygen infrastructure, supplies and revitalise essential MNCAH services to combat COVID-19 in the selected hospitals of eight districts in Bangladesh	UNICEF	2021	VfM assessment for Maternal, Newborn, Child and Adolescent Health (MNCAH) system strengthening in Bangladesh	VfM Analysis.
Assessing Good Pharmacy Practices in Private Medicine Shops in selected Districts of Bangladesh	Dr. Iqbal Anwar	2023	Assessing the GPP status of private medicine shops where trained pharmacy technicians were working	Relevance, Effectiveness
Political Economy Analysis of the Health Sector in Bangladesh	DM Watch	2021	Politics of policymaking and implementation of health in Bangladesh	Context of HNP sector of Bangladesh, policy context; country context
Bangladesh country case study for COVID-19 strategic joint Evaluation	Unknown	2023	COVID-19 Knowledge, Attitudes, Practices & Needs and impact in country.	Evolution of BHB programme
Bangladesh country cooperation strategy 2020–2025	WHO	2020	Description of WHO planned interventions in Bangladesh	Equity
DFID ethical guidance for research, evaluation and monitoring activities	UK Department for International Development (DFID)	2019	Ethical guidance for research, evaluation and monitoring activities	Evaluation Methodology
Safe abortion: technical and policy guidance for health systems	WHO	2012	Laws and policies on abortion; women’s health and human rights	Equity/VfM
The health and economic impact of scaling cervical cancer prevention in 50 low- and lower-middle-income countries / https://obgyn.onlinelibrary.wiley.com/doi/10.1002/ijgo.12184	Campos et al. International Journal of Gynaecology & Obstetrics Vol 138, Issue S1	2017	Health impact, financial costs, and cost-effectiveness of scaling-up coverage of Human Papillomavirus (HPV) vaccination and cervical cancer screening	Equity/VfM
Bangladesh National Health Accounts 1997- 2020	HEU, MOHFW	2021	Results of Bangladesh National Health Accounts 1997-2020	Broader country context
Bangladesh Health System Review. Health Systems in Transition	WHO	2015	Description of health system and policy initiatives in Bangladesh	Broader country context; Equity
Total documents reviewed		35
The following project write ups, which did not contain information such as year of publication, were also shared by FCDO and read by the evaluation team
Introduction brochure of BHB Programme	FCDO	Unknown	Overview of the BHB programme and its components	BHB programme overview; ToC
Midwifery Education and Services (Supported by FCDO/DFID)	FCDO	Unknown	Overview of the midwifery education component of BHB	BHB programme overview; Effectiveness; Equity
MSH BHB	MSH	Unknown	Overview of the MSH TA Component of the BHB Programme	BHB programme overview;
Cervical Cancer	UNFPA	Unknown	Brief description cervical Cancer, COVID-19 and climate change component of UNFPA TA	BHB programme overview; Effectiveness; Equity
DGFP Activities by FCDO Fund	UNFPA	Unknown	Overview of the UNFPA activities with Directorate General for Family Planning (DGFP) under BHB Programme	BHB programme overview; Effectiveness; Equity
Maternal Health	UNFPA	Unknown	Overview of the maternal health interventions in BHB programme	BHB programme overview; Effectiveness; Equity
Creating Female Pharmacists to Ensure Quality SRHR Information, Counselling, and Referral Services	Unknown	Unknown	Intervention update and results of training female pharmacists on sexual and reproductive health rights (SRHR)	Equity
Empowering Resilience: UK Government's Partnership with UNFPA in Eastern Bangladesh Flood Response: A Brief Summary	UNFPA	Unknown	Overview of BHB programme support during flood	BHB programme overview;
Increased access to STI management services	UNFPA	Unknown	Overview of the sexually transmitted infections (STI) service interventions in BHB programme	BHB programme overview; Effectiveness
Strengthening Health Systems in Bangladesh: WHO’s Collaborative Efforts	WHO	Unknown	Overview of the WHO part of UNFPA TA Component of the BHB Programme	BHB programme overview; Effectiveness
Total project write-ups:		10
Total reviewed		45

# Annex 8: Understanding the relationship between BHB outputs and outcomes
As part of the evaluation, the team explored how output indicators contribute to outcome indicators. Output indicators are designed to reflect programme performance, while outcome indicators measure progress at the population level. Though outputs can influence outcomes, their impact is often indirect and affected by various external factors.
Assessing contribution
Differences in measurement and scope: Output indicators capture direct service provision within programme areas, while outcome indicators assess broader population-level trends influenced by multiple determinants. For example, Output Indicator 1.1 (Number of childbirths attended by skilled birth attendants in 20 Better Health in Bangladesh (BHB) programme districts) captures programme activities at the facility level and is reported through the District Health Information System 2 (DHIS2) system. Outcome Indicator 1.1 (Percentage of births attended by skilled providers) is a population-level measure derived from household surveys (Bangladesh Demographic and Health Survey (BDHS), Multiple Indicator Cluster Survey (MICS)), conducted every 3–5 years.
Some BHB indicators currently categorised as outputs may function more as intermediate outcomes. For example, the number of births attended by skilled providers includes both facility and community-based deliveries, making it a broader measure than a direct programmatic output.
Causality and External Influences: While outputs contribute to outcomes, the relationship is rarely linear. Several external factors mediate the impact of output on outcomes, such as:
- Health system constraints (e.g., workforce shortages, supply chain issues)
- Socioeconomic disparities affecting healthcare access
- Regional differences in service utilization
For example, an increase in facility-based deliveries in intervention districts does not necessarily lead to a rise in the national skilled birth attendance rate if health-seeking behaviours, access to care, and other externalities remain inconsistent.
Gaps in Output Indicators for Certain Outcomes: Some outcome indicators lack corresponding output-level measures, making it difficult to track direct programme contributions. For example:
Outcome Indicator 1.4 (Percentage of newborns receiving essential newborn care) lacks a facility-based output indicator. Introducing a measure such as ‘Number of newborns receiving essential care within 48 hours of birth at health facilities’ would enhance monitoring.
Stock-out of essential medicines can be tracked as both an output and outcome. Disaggregated facility level stock availability (output) is an important programmatic indicator with related outcome measure showing proportion of overall health facilities with available stock.
The table below shows the relationship between selected outcome and output indicators, with observations including areas for improvement in the future.
Table: Relationship between selected outcome and output indicators
Outcome Indicators	Output Indicators	Observation/ Comments
1.1: Percentage of births attended by skilled providers. [Source: BDHS]	1.1 Number of childbirths attended by skilled birth attendants [in 20 BHB districts]. [Source: DHIS2]	Output is at the service provision level, and outcome is at the population level, measuring the same outcome. / Output indicator could be more specific to programme’s activities and disaggregated by sub-district levels.
1.2: Contraceptive prevalence rate (CPR) for modern methods. [Source: BDHS]	1.3: Number of total FP Users (modern methods). [Source: DHIS2]	As above.
1.4: Percentage of newborn received essential newborn care. [Source: MICS]		An output indicator at facility level could be added.
	1.6: Number of service providers and community leaders, trained to cope with climate and other shocks.	Relevant indicator for FCDO. Since it is a new initiative, the outcome level indicator is not a priority.
1.6: Number of women screened for cervical cancer. [DHIS2]	2.3: Number of health facilities (MCH, DH, UHC) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer. [Source; Programme data]	This output indicator is a contributing factor to outcome (1.6). Determinants may include health systems and socio-economic level factors. / Indicator can further be disaggregated by the type of health facility.
	2.1 Number of sub-district health facilities (Upazila Health Complexes - UHC) with at least two licensed midwives. [Source: MOHFW report]	This output indicator can be transformed into an outcome level indicator if collected through DHIS2.
2.2 Percentage of health facilities reporting no stock-out of essential medicines. [Source: DHIS2]		Appropriate as both outcome and output indicators and can be measured regularly as this is a DHIS2 indicator. / At the output level, disaggregation by health facility level may be considered.
2.3: Percentage of accredited medicine shops with improved dispensing practices as per national guidelines. [Source: Independent studies]	2.5: Number of medicine dispensers trained on Good Pharmaceutical Practice (GPP). [Source: Programme data] / 3.1: Number of targeted medicine shops accredited. [Source: MOHFW verification report] / 3.2: Number of retail medicine shops, licensed/ license renewed, by Directorate General of Drug Administration (DGDA) using automated licensing and renewal system.	Appropriate as an output indicator. Indicators 2.5, 3.1 and 3.2 all contribute toward outcome 2.3.

Conclusion
Output indicators are essential to measure programme performance, but their impact on outcomes depends on their specificity and alignment with broader programme goals. Under BHB, refining certain indicators could enhance their effectiveness to more accurately capture programmatic success.
While output indicators facilitate immediate decision-making and adaptive management, outcome indicators must be carefully designed to account for systemic influences and socio-economic conditions. Strengthening the specificity of output indicators and improving their alignment with outcome measures will enhance the evaluation of long-term effectiveness and sustainability.
Recommendations to strengthen future reporting frameworks
  1. Align indicator definitions and data collection methods
- Harmonise facility-based output indicators with population-level outcome indicators for improved alignment and interpretation.
- To the extent it is feasible, introduce more targeted output indicators that directly reflect programme activities.
- Expand facility-level tracking for outcomes currently lacking corresponding outputs (e.g., newborn care, essential medicine stock-outs).

  1. Enhance periodic review and validation
- Consider mid-term assessments to evaluate whether output indicators effectively contribute to expected outcomes and adaptive learning.
- Use mixed-methods approaches, combining routine data (DHIS2, programme data) with household surveys (BDHS, MICS), observations, and independent studies to triangulate findings.

  1. Consider systemic and contextual factors
- Acknowledge that outcome improvements require multi-sectoral efforts beyond direct programmatic outputs.
- Incorporate process indicators to monitor whether activities are implemented as planned, ensuring a clear linkage between inputs, outputs, and outcomes for a more comprehensive assessment.
# Annex 9: Key informants interviewed
Name and Role		Organisation	Gender
Dhaka Level			Male	Female
1	Ashadul Islam, Former Senior Secretary, HSD	MOHFW	M
2	Mr. Helal Uddin, Former Addl. Secretary, HSD	MOHFW	M
3	Prof. Iqbal Kabir, Director and Coordinator, CCHPU, HSD	MOHFW	M
4	Dr. Rashid Zaman, Health Advisor and SRO, BHB	FCDO	M
5	Dr. Shafiqul Islam, Health Advisor	FCDO	M
6	Fawzia Nasrin, Programme Manager	FCDO		F
7	Dr. Abu Sayed Mohammad Hasan, SRHR Specialist	UNFPA	M
8	Joy Kemp, International Midwifery Specialist	UNFPA		F
9	Dr. Animesh Biswas, Technical Officer	UNFPA	M
10	Pronita Raha, Programme Analyst-Midwifery	UNFPA		F
11	Md. Amirul Islam, Consultant- Management Information Systems	UNFPA	M
12	Dr.Quazi Mamun Hossain, TO-HMIS&LMIS	UNFPA	M
13	Dr. Rokhsana Yasmin, PTO-HIV, STI, hepatitis G virus	UNFPA		F
14	Dr.Mohammad Azad Rahman, TO-FP &MNH	UNFPA	M
15	Nabila Purno, Programme Analyst, SRHR	UNFPA		F
16	Farida Begum, National Consultant - Midwifery	UNFPA		F
17	Dr. Mohammad Sabbir Haider, VfM Consultant	UNFPA	M
18	Md. Alauddin Abu Tuhid	UNFPA	M
19	Sangay Wangmo, Team Leader - HS	WHO		F
20	Mohammad Touhidul Islam, National Professional Officer - HF	WHO	M
21	Md Nuruzzaman, National Professional Officer -Human Resources for Health	WHO	M
22	Ngawang Dema, Technical Officer-ED&M	WHO		F
23	Tasmia Islam, National Professional Officer – Health Information Systems	WHO		F
24	Dr. Abul Kalam Azad, Former Project Director (BHB)	MSH	M
25	Raian Amzad, Former Senior Technical Advisor	MSH		F
26	Abdul Gaffer Mondol, Principal Technical Advisor	MSH	M
27	Mominur Rahman, Former Technical Advisor	MSH	M
28	Dr. Moazzem Hossain Tarafder, PM (Acting), MNCAH	DGHS	M
29	Dr. Mostafa Mahmud, DPM (EOC), MNCAH	DGHS	M
30	Dr. Farida Akhter, National Consultant, MNCAH	DGHS		F
31	Md.Aziulla, Asst Director	DGDA	M
32	Dr. Md Rafiqul Islam Talukder, Line Director, Clinical Contraceptive Services Delivery Programme	DGFP	M
33	Momtaz Begum, Deputy Director (Midwifery)	DGNM		F
34	Khama Rani Baroi, Asst. Director (Midwifery)	DGNM		F
35	Most. Rabeya Basri, Focal Person (Midwifery)	DGNM		F
36	Dr. Md Zillur Rahman, Chairman, Department of Disaster Science and Climate Change	University of Dhaka	M
	Sub-total Dhaka level		22	14
Field Level
37	Dr Asim Kumar Samaddar, Superintendent, Bagerhat 250 Bed Hospital	DGHS	M
38	Dr Dalia Halder, Senior Gyn. Consultant, Bagerhat 250 bed Hospital	DGHS		F
39	Maksuda Akter, Senior Staff Nurse, Bagerhat 250 Bed Hospital	DGNM		F
40	Rahima Khatun , Principal, Bagerhat Nursing Institute	DGNM		F
41	Mst. Selina Khatun , Nursing Instructore (Midwifery), Bagerhat Nursing Institute	DGNM		F
42	Dr. Md. Shahin, UHFPO, Mongla	DGHS	M
43	Tariqul Islam, Local Coordinator	KMSS	M
44	Laboni Akter Sadia, Waste Management Supervisor	DGHS		F
45	Dr. As Saba Sakib, Technical Co Ordinator, Green Healthcare Initiative	PHD	M
46	Sraboni Mondol, Midwife, Mongla UHC	DGNM		F
47	Tania Khatun, Labor-in-Charge, Mongla UHC	DGNM		F
48	Ayesha Khatun, Midwife, Mongla UHC	DGNM		F
49	Md. Tarikul Islam Deputy Director-Family Planning, Gaibandha	DGFP	M
50	Dr Marula Akter Jahan, Asst. Director - Family Planning, Gaibandha	DGFP		F
51	Dr. Tahera Akter Moni (Senior Consultant, Gynaecology), Gaibandha District Hospital	DGHS		F
52	Dr. Md. Atiqur Rahman Khan, Medical Officer, Gaibandha MCWC	DGFP	M
53	Dr. Mubin, Medical Officer, Gaibandha District Hospital	DGHS	M
54	Dr. Rezwan, Medical Officer, Gaibandha District Hospital	DGHS	M
55	Most. Kulsum Khatun, Senior Staff Nurse, Gaibandha District Hospital	DGNM		F
56	Silvia Mardı, Midwife	LAMB		F
57	Nipa Soren, Midwife	LAMB		F
58	Adury Hasnat, Community Health Worker	DGFP		F
	Sub-total (22)		8	14
	Total (58)		30	28

# Annex 10: Case study: Green Healthcare Initiative at Mongla Upazila Health Complex
Introduction: The Green Healthcare Initiative at Mongla Upazila Health Complex is a pioneering initiative aimed at transforming Mongla Health Complex into Bangladesh’s first Green Health Center. This initiative, originally part of the FCDO-funded Climate Resilience Program, evolved into a structured model integrating sustainability, waste management, renewable energy and climate resilience into healthcare services.
Programme development and objectives: Mongla, classified as a climate disaster-prone area, was selected for this initiative under the Climate Change and Health Promotion Unit of the Ministry of Health and Family Welfare. The goal was to develop a green hospital model, aligning with Global Green Health and Healthcare (GGHH) standards, which focus on ten interconnected goals to help hospitals and healthcare institutions reduce their environmental footprint while promoting public health. These are leadership, chemicals management, waste management, energy consumption, water, transportation, food, pharmaceuticals, buildings and purchasing. These ten components guide hospitals in achieving environmental sustainability, cost savings and improved public health outcomes. This effort is called ‘initiative’; as the process is yet to embrace all components of GGHH, especially, green building code. As one key informant noted: We are still calling this a green hospital initiative rather than green hospital. The infrastructure should maintain green building code. These things can’t be done without the help of the ministry.
[note] https://greenhospitals.org/
Key interventions included:
- Rainwater harvesting: 140,000-liter storage system, installed by BRAC, to address water scarcity.
- Carbon footprint reduction: assessment and reduction of emissions from hospital kitchens, waste disposal and medical equipment.
- Sustainable waste management: segregation of sharp waste (2-5%), contaminated waste (15%) and general waste (80%) at the source, supported by a dedicated waste supervisor.
- Plastic and medical waste recycling: use of plastic crushers to repurpose waste into income-generating resources for hospital cleaners.
- Green procurement policies: adoption of digital thermometers instead of mercury-based ones, glass water mugs instead of single-use plastic and paperless administration.
- Energy-efficient cooking practices: transitioning from wood-burning stoves to Bondhu Chula and electric stoves to reduce carbon emissions.
- Sustainable transport: encouraging staff to share transport, minimising individual carbon footprints.
Implementation and community engagement: A Green Hospital Team of eleven members, including administrators, doctors, cleaners and chefs, was formed to oversee sustainability efforts. Community engagement played a vital role in ensuring long-term success, with awareness sessions held in six unions, targeting local leaders, community clinic staff and rural medical practitioners.
The team presented a vision that aligns with GGHH: We have a concept called ‘From Waste to Resource’. We are trying to make this our tagline. We tried to ensure no illegal use of plastic in medical equipment. We are trying to reduce plastic disposal. We discussed with pharmacists on how to reduce plastic pharmaceutical waste. We tried to train them regarding this matter. We wanted to ensure that we have no mercury pollution. We tried to add greenery in the open spaces of the hospital compound.
To enhance hygiene and sustainability practices, the hospital took a range of steps:
- Installation of plastic-free waste bins in patient wards and trained staff on proper waste disposal.
- Eliminating mercury pollution by replacing hazardous materials in medical equipment.
- Planting 1,200 trees, with a 10-year sustainability goal to reduce carbon emissions and improve air quality.
- Ensuring waste separation and processing, significantly reducing hospital waste volume by 75%.
Challenges and sustainability concerns: Despite notable achievements, several challenges hinder the initiative’s long-term sustainability. These include:
- Funding uncertainties: the project relies heavily on development partner support, with no confirmed government budget allocation.
- Human resource shortages: the hospital, formally a 50-bed facility, regularly accommodates 80+ patients with only six doctors instead of the required 28 and an insufficient number of nurses and support staff.
- Energy supply issues: frequent power outages, particularly during disasters, make it difficult to maintain continuous electricity in labour and emergency rooms.
A team member stated: the power generation should come from a renewable source. In recent times this area was affected by cyclone Remal. During that time the electricity was cut off for 48 hours. But we need continuous electricity supply in the labour rooms and emergency rooms through renewable energy.
- Limited infrastructure support: future hospitals must follow green building codes to ensure sustainability, as isolated interventions at Mongla alone cannot transform the national healthcare system.
- Lack of formal government integration: without government policies mandating sustainable hospital practices, the initiative may not scale nationwide.
Policy recommendations for future expansion: To ensure the sustainability of the Green Healthcare Initiative, the following steps are recommended:
1. Government Policy Integration: Ministry of Health and Family Welfare should formally adopt green healthcare standards in national health policies and hospital construction guidelines.
2. Sustainable Funding Models: long-term funding commitments are needed for waste management, renewable energy integration and community engagement programmes.
3. Expansion of Green Healthcare Models: other Upazila Health Complexes and district hospitals should adopt similar sustainability measures, guided by Mongla’s success.
4. Institutional Capacity Building: medical training curricula should include climate resilience and sustainable healthcare management to equip future healthcare leaders.
5. Strengthened Community Ownership: patients and local communities should be actively engaged in waste management and hospital cleanliness to sustain behavioural change.
6. Renewable Energy Integration: solar power should be adopted to maintain emergency electricity supply, ensuring at least 48 hours of backup power in disaster situations.
Conclusion: The Green Healthcare Initiative at Mongla Upazila Health Complex has demonstrated that sustainability and climate resilience can be successfully integrated into healthcare systems. While it serves as a model for environmentally conscious healthcare in Bangladesh, its long-term impact depends on sustained funding, policy integration and national-level commitment. If scaled effectively, this initiative can lead to healthier, more sustainable hospitals across the country, reducing carbon emissions, improving patient well-being and enhancing healthcare resilience against climate change.

# Annex 11: Case study: Midwifery-led care (MLC) model under the BHB programme
Background: Bangladesh has made significant progress in maternal and neonatal health, yet challenges persist, particularly in reducing maternal and neonatal mortality rates in rural and underserved areas. To address these challenges, the United National Population Fund (UNFPA), under the Better Health Bangladesh (BHB) programme, introduced the Midwifery-Led Care (MLC) model. This model aimed to enhance the role of midwives in delivering high-quality maternal and newborn healthcare services while integrating them into the national healthcare system.
Implementation of the MLC model: The MLC model was launched with a focus on strengthening midwifery services in Bangladesh through policy advocacy, capacity building and facility-based interventions. The key components included:
1. Establishment of Midwifery-Led Units (MLUs): UNFPA supported the establishment of MLUs in selected district hospitals and Upazila Health Complexes (UHCs). These units provided a dedicated space for midwives to deliver respectful maternity care to women.
2. Training and capacity building: Midwives were trained in evidence-based practices, emergency obstetric care and interpersonal skills to ensure culturally appropriate and high-quality care.
3. Integration into the health system: The model emphasised the formal recognition of midwives within the public health sector, promoting their inclusion in national health policies and service delivery frameworks.
4. Community engagement: Awareness campaigns were conducted to improve community perceptions of midwifery services, particularly in rural areas where traditional birth attendants (TBAs) were more commonly utilised.
5. Collaboration with stakeholders: UNFPA worked closely with the Ministry of Health and Family Welfare (MOHFW), nursing and midwifery councils, professional associations and academic institutions to scale up midwifery-led care across the country.
Key outcomes and impact:
- Improved maternal health outcomes: Facilities with MLUs reported a reduction in maternal and neonatal complications, with an increase in facility-based deliveries.
- Enhanced midwifery workforce: Over 3,000 midwives were trained and deployed across healthcare facilities, ensuring skilled attendance at births.
- Increased community trust: Positive shifts in public perception led to greater utilisation of midwifery services, reducing reliance on unskilled birth attendants.
- Policy recognition: The model contributed to policy advocacy efforts that led to the institutionalisation of midwifery-led services in national maternal health policies.
Challenges and lessons learned:
- Workforce integration: Despite progress, midwives faced challenges in gaining full autonomy within the hierarchical healthcare system.
- Sustainability concerns: The reliance on donor funding posed a risk to the long-term sustainability of the model.
- Cultural barriers: Deep-rooted socio-cultural preferences for traditional birth practices required ongoing community engagement efforts.
Sustainability and future directions: To ensure long-term sustainability, the MLC model needs to be integrated into the core service delivery network of MOHFW. Future efforts should focus on:
- Strengthening midwifery leadership roles within health governance structures.
- Expanding MLUs to more healthcare facilities.
- Enhancing financial sustainability through government investment in midwifery education and employment.
- Promoting digital health solutions to improve midwifery service delivery in remote areas.
Conclusion: The Midwifery-Led Care (MLC) model under the BHB programme has demonstrated a transformative impact on maternal and newborn healthcare in Bangladesh. By institutionalising midwifery-led services, strengthening capacity and advocating for policy reforms, UNFPA has laid the foundation for sustainable and equitable maternal healthcare. Continued investment in midwifery is essential for achieving Bangladesh’s long-term maternal and neonatal health goals.

# Annex 12: Value for Money assessment
Executive Summary
This Value for Money (VfM) assessment evaluated the Better Health in Bangladesh (BHB) programme’s financial efficiency, operational effectiveness, and overall contribution to improving maternal and reproductive health, digital health systems, and policy governance. The assessment follows FCDO’s VfM framework, and analyses economy, efficiency, effectiveness and cost-effectiveness to determine how well programme resources were utilised to achieve the greatest possible health outcomes. Key VfM findings include:
- 5,063 deaths averted and 378,351 Disability Adjusted Life Years (DALYs) saved across four major interventions, generating £745.75 million in economic benefits.
- Cost per DALY averted: £99 – 19 times lower than Bangladesh’s Gross Domestic Product (GDP) per capita (£2,057), confirming strong cost-effectiveness.
- £1.62 million saved through the digitisation of medicine shop licensing via Automated Drug Licensing and Renewal System (ADLRS).
- £1.51 million saved through improved procurement practices by Management Sciences for Health (MSH).
- Compliance with prescription-only antibiotic sales increased from 33.7% to 82.7%.
- 515 public health facilities became Postpartum Family Planning (PPFP)-ready, up from zero at baseline.
Economy: BHB achieved strong economy through cost-saving mechanisms across procurement, consultancy, and training. UN-based procurement platforms (United Nationals Population Fund (UNFPA) and World Health Organisation (WHO)) provided inputs at significantly reduced rates – lower than local markets for selected commodities – though precise savings could not always be disaggregated. MSH’s strategic procurement alone delivered £1.51 million in savings. Consultant costs were reduced through in-house expertise, and training expenditures were minimised by shifting to government-led and virtual models, resulting in reductions of up to 89%. Direct Financial Cooperation (DFC) agreements further streamlined fund disbursements, enhancing cost control. However, lack of disaggregated financial data from all partners constrained full quantification of savings.
Efficiency: BHB demonstrated strong efficiency in translating inputs into outputs. Eight out of 11 programme outputs met or exceeded targets, including childbirths attended by skilled birth attendants (SBAs) (Output 1.1 at 173%), family planning uptake (Output 1.3 at 107%), and licensing of medicine shops (Output 3.2 at 102%). Digital innovations like ADLRS cut licensing times (from 15–45 days to 2–5 days) and generated £1.62 million in savings. Training of medicine dispensers improved storage compliance (from 45% to 92%), labelling, and patient counselling, reducing medicine spoilage and health risks. However, performance in Output 1.4 (Vitamin A coverage at 99%) and Output 1.6 (climate resilience training at 67%) fell short, indicating implementation challenges in multi-stakeholder activities.
Effectiveness: The programme led to notable health and policy outcomes. The share of normal deliveries conducted by midwives rose from 54.9% (2019) to 91% (2024), increasing access to SBAs. Deliveries supported by SBAs increased fourfold. Stock-out rates for essential medicines dropped from 40% to 0%, signalling strengthened supply chains. BHB also supported enactment of the Drug and Cosmetics Act 2023, development of national pharmacy accreditation guidelines, and embedding digital tools like ADLRS and Pharmacy Management Software (PMS) in government systems.
The programme’s e-learning platform trained over 25,000 pharmacy professionals, enhancing long-term institutional capacity.
Cost-effectiveness: BHB is highly cost-effective, with a cost per DALY averted of £99, substantially below Bangladesh’s GDP per capita.
- Midwifery and Basic Emergency Obstetric and Newborn Care (BEmONC): 2,277 deaths averted, 162,407 DALYs saved, and £321 million in benefits; £32.7 per DALY averted; £60 return per £1 invested.
- Family Planning: 2,058 deaths averted, 142,514 DALYs saved; £25 per DALY averted, with a Return on Investment (ROI) of £78 per £1 invested.
- Implant Provision: 650 deaths averted, 45,854 DALYs saved; £30 per DALY.
- Cervical Cancer Screening: 78 deaths averted, 27,576 DALYs saved; £65 per DALY, and £29 return per £1 invested.
Outcome and Impact cost indicators: The evaluation of outcome- and impact-level cost indicators shows that the BHB programme has achieved strong VfM, with several interventions delivered more efficiently than projected. At the outcome level, the cost per BEmONC patient was reduced from £83 (Business Case) to £56 (VfM Assessment), cervical cancer screening from £2 to £1.28, and family planning services from £6 to £3.90. At the impact level, the cost per life saved through BEmONC was £2,329 (VfM Assessment) versus £2,079 (Business Case) and £3,213 (Annual Review); unsafe abortion averted cost £17 (VfM Assessment) compared to £5 (Business Case); and cervical cancer case averted cost £189 (VfM Assessment), significantly lower than £385 (Business Case) and £2,221 (Annual Review). These results demonstrate consistent efficiency gains, especially in cervical cancer prevention and maternal health, underscoring the programme’s ability to deliver impactful services at comparatively low unit costs.

Challenges and caveats
- Absence of a standard VfM framework across partners led to inconsistent VfM reporting.
- Gaps in financial data hindered granular analysis of cost drivers.
- Difficulty in quantifying long-term benefits of TA, policy, and systems strengthening.
- Variation in performance across outputs, with some areas (e.g., Output 1.4 and 1.6) underachieving.

Recommendations for future programmes
- Develop a standardised VfM framework and strategy from inception, with clear guidance on metrics, attribution, and reporting.
- Mandate intervention-level cost reporting across partners to enable deeper VfM analysis.
- Integrate VfM indicators into routine monitoring tools (dashboards, quarterly reviews).
- Build VfM capacity among implementing partners and FCDO teams, through training or induction modules.
- Develop specific guidance for analysing and evaluating VfM in TA-heavy programmes, including use of proxy indicators (e.g., DALYs averted, cost per output).
- Encourage use of VfM findings to inform resource allocation and programme design.
- Institutionalise VfM documentation standards in implementing partner reporting formats.
- Promote regular VfM reflection sessions among stakeholders to understand progress and adjust strategies.

Was BHB value for money?
Based on the VfM assessment, the BHB programme provided strong value for money across all four pillars. It effectively minimised costs, efficiently converted resources into outputs, achieved substantial health improvements, and delivered high cost-effectiveness relative to investment. The low cost per DALY averted (£99), combined with the economic benefits exceeding £745 million, illustrates a high return on investment. While data limitations and implementation gaps existed, they do not detract from the programme’s overall VfM performance. BHB demonstrated that well-structured TA, aligned with national systems, can generate significant, lasting impact when paired with smart resource use.
Notes for readers
This section of the document presents some important clarifications, assumptions and limitations which need to be kept in mind while reading this assessment and drawing conclusions.
1. Scope of the evaluation. While this VfM analysis is embedded within the broader programme evaluation, it applies a specific VfM lens using FCDO’s 4Es framework. It does not cover all OECD-DAC evaluation criteria, such as relevance and sustainability, nor does it aim to provide full causal attribution. The analysis is intended to complement the BHB evaluation by focusing on how efficiently and effectively resources were used to achieve outcomes.
2. Non-availability of comprehensive financial data. Due to gaps in financial data availability, some aspects of programme expenditure could not be fully analysed. This affects the ability to understand VfM at a more granular level. For example, the evaluation team were not able to analyse the main cost drivers of the programme.
3. Closure of MSH implemented part of the project and lack of staff availability. With the closure of the project, MSH staff were unavailable for discussions, limiting insights into operational challenges and decision-making processes.
4. Absence of a VfM framework. No standardised VfM framework was developed for the programme, making it difficult to systematically track and measure VfM across all interventions.
5. Different understanding of VfM among implementing partners. From the reports available, it appears that each implementing partner interpreted VfM differently, leading to inconsistencies in how VfM was analysed and reported.
6. Limited VfM reporting. Most annual reports lacked detailed VfM analysis, often stating adherence to VfM principles without providing evidence of actual cost savings or efficiency gains.
7. Lack of standardisation and coherence in VfM reporting. VfM reporting varied between implementing partners, with no coherent approach to tracking financial efficiency, cost-effectiveness, and impact measurement.
8. Challenges in quantifying long-term system-level benefits. While policy and governance improvements are crucial for sustainability, their impact is difficult to measure in economic terms. Many technical assistance (TA) interventions lead to benefits that manifest over time, making it hard to directly attribute outcomes to the programme.
9. Variability in output achievement. While many outputs exceeded expectations, some key interventions (e.g., Output 1.4 and 1.6) underperformed, suggesting the need for a deeper analysis of implementation challenges which was not possible in the given scope.
10. Interpreting VfM judgement ratings. To ensure consistency in interpreting findings, each VfM pillar (Economy, Efficiency, Effectiveness, Cost-effectiveness) includes a judgement matrix summarising performance. Judgement ratings were derived based on the strength of evidence and degree of achievement against key VfM indicators:
- Strong: Evidence consistently demonstrates high VfM across all indicators, with quantifiable results and minimal gaps.
- Moderate to strong: Most VfM indicators were met and evidence is robust, but one or two limitations exist (e.g., lack of disaggregated data or a few outputs falling short).
- Moderate: Evidence shows partial VfM performance; either mixed results across indicators or limitations in evidence base.
Attribution methodology. It is important to recognise that not all outcomes can be fully attributed to the programme alone. For example, the provision of BEmONC services depends on a combination of programme inputs and resources provided by the broader health system, such as existing infrastructure, human resources, and operational funding, which were not directly financed by the project.

To estimate the programme’s attributable contribution to observed outcomes, the evaluation team adopted a financial contribution-based attribution approach. This method involves comparing the relative financial inputs of the programme with those made by the Government of Bangladesh (GoB) in similar areas of service delivery. Specifically, the team identified four major GoB operational plans that closely align with the thematic focus of the programme [Maternal, Child, Reproductive and Adolescent Health, Nursery and Midwifery Education Services, Maternal, Neonatal and Child Health, and Family Planning Field Service Delivery]. By calculating the average annual public sector investment in these plans and proportionally allocating it across all districts, the team derived an estimate of government co-investment in the programme's 20 target districts.
The ratio of GoB investment in these districts to the FCDO investment was used as a proxy for attributing the share of outcomes to the programme. This yielded an attribution factor of 40%, which has been applied consistently across relevant outcome estimates.
While this approach does not offer exact causal attribution, it provides a pragmatic, transparent, and evidence-informed estimation technique. It recognises the joint contribution of both domestic systems and external programme support and is particularly suited for complex system-strengthening interventions where outcomes are co-produced.
This method is commonly referred to as a proportional financial attribution or investment share-based attribution and is widely accepted in development evaluations when direct causal attribution is not feasible.

Introduction
VfM explained: VfM can be approached from multiple perspectives. At its core, it reflects the relationship between the cost of services and the outcomes achieved through their delivery. The modern understanding of VfM has evolved to incorporate a broader framework known as the ‘5Es’ – namely: (i) economy, (ii) efficiency, (iii) effectiveness, (iv) equity, and (v) cost-effectiveness, as outlined in Box VfM 1. Together, these components aim to optimise not just individual aspects but the entirety of the service delivery process, striking a balance between inputs, outputs, outcomes, and equitable access.
A common misconception is that VfM revolves solely around cutting costs or prioritising cheaper alternatives. However, VfM is much more nuanced. It focuses on maximising outcomes in the most cost-effective way. While minimising costs is part of the equation, it is equally important to understand the drivers behind these costs and ensure they align with the intended results.
The UK Foreign Commonwealth & Development Office (FCDO) highlights this more comprehensive understanding in its guidance on VfM. It stresses that simply reducing costs without considering quality, effectiveness, or equity can undermine impact. The 5Es framework shifts the focus from expenditure to the outcomes achieved through the investment. It encourages decision-makers to maintain a careful balance between financial prudence and quality outcomes to achieve their objectives effectively.
Box VfM 1: The 5Es of VfM
Economy: Are we procuring inputs of the appropriate quality at the best possible price?
Efficiency: How well are we converting inputs into outputs? (this reflects ‘spending well’)
Effectiveness: Are the outputs achieving the intended results? (this reflects ‘spending wisely’)
Equity: How fairly are the benefits distributed? Are we reaching marginalised or vulnerable groups? (this reflects ‘spending fairly’)
Cost-effectiveness: What is the long-term impact of the intervention, particularly on poverty reduction, compared to the resources invested?
Source: DFID’s approach to VfM – Smart Guide, DFID updated 2020.

Achieving VfM requires a clear understanding of how resources generate impact, which is achieved through the results chain (see Figure 1 in the main report). The results chain depicts the stages from inputs (such as funds, human resources, and materials) to activities, outputs, outcomes, and, ultimately, impact. Each component of the 5Es aligns with a different point along this chain, helping to ensure that costs are optimised, and meaningful results are delivered.

Input
Process
Output
Outcome
Impact
Economy
Efficiency
Effectiveness
Cost-Effectiveness
Equity
Human resource, materials, capital items.
e.g.
Staff, consultants, venue costs, survey costs, procuring medicines etc.
The methods by which inputs are used.
e.g.
Process of staff hiring, procurement of services, design of trainings etc.
Delivery of results - more direct control.
e.g.
Number of medicine dispensers trained on GPP.
Less control on outcomes as compared to outputs.
e.g.
Contraceptive prevalence rate (CPR) for all modern methods.
Long-term transformational change
e.g.
All citizens of Bangladesh enjoy good health and well-being.

Figure VfM 1: Results Chain – contextualised to BHB

Source: Adapted from FCDO’s approach to VfM – Smart Guide, FCDO updated 2020.

The economy, efficiency, effectiveness, and equity components serve as intermediary steps that support the cost-effectiveness of interventions. For example, ensuring efficiency in the conversion of inputs to outputs and focusing on equity in the distribution of benefits both contribute to maximising cost-effectiveness. Ultimately, cost-effectiveness reflects the highest level of VfM, as it ensures that the resources expended have the greatest possible impact on improving people’s lives.

Methodology: Better Health in Bangladesh Programme VfM
VfM of the BHB programme was conducted using FCDO’s VfM framework, and as outlined in the evaluation Inception Report, the evaluation team evaluated the programme’s performance in terms of economy, efficiency, effectiveness, and cost-effectiveness. Given the TA-heavy nature of the programme, the methodology incorporated both quantitative and qualitative approaches to understand VfM comprehensively.
Data sources
The VfM assessment relied on the following sources:
- Programme reports: Logframe, annual reviews, and completion reports from implementing partners.
- Financial and procurement data: Available cost reports and procurement records.
- Health outcome data: Indicators from service delivery data (e.g., maternal and neonatal health, facility readiness, contraceptive uptake).
- Economic and modelling tools:
  - Lives Saved Tool (LiST) for estimating maternal and neonatal deaths averted.
  - Marie Stopes International (MSI) Impact 2 Model for contraceptive impact assessment.
  - DALYs approach to estimate health benefits.
  - Cost-effectiveness thresholds based on Bangladesh’s GDP per capita (£2,057).

VfM approach
Economy: Analysed whether inputs (e.g., medical supplies, training, and technical assistance) were procured at the lowest cost without compromising quality. Key indicators included cost savings through bulk procurement, strategic hiring practices, and financial efficiency in programme operations.
Efficiency: Evaluated how well inputs were converted into outputs, analysing training completion rates, TA delivery timeliness, digital innovations (e.g., ADLRS), and stock-out reductions. Performance was analysed against programme targets to identify bottlenecks and efficiency gains.
Effectiveness: Measured the extent to which the programme achieved intended outcomes, focusing on maternal and neonatal health improvements, stock-out reductions, TA contribution to policy and system strengthening, and service delivery expansion.
Cost-effectiveness: Used DALYs averted as the primary metric, monetising health benefits using Bangladesh’s GDP per capita. Specific interventions (e.g., midwifery services, family planning, cervical cancer screening) were selected where measurable health gains could be attributed to the programme.
Despite data gaps and limitations, the VfM analysis used a conservative approach, ensuring that only well-documented cost savings and health outcomes were included in the VfM calculation. Further, the evaluation team applied 40% attribution. Please refer to Note to Readers section for details. Where precise cost-effectiveness estimates were not feasible, proxy indicators and external benchmarks were used to contextualise findings. The results provide a credible, evidence-based VfM narrative, while acknowledging areas where improved reporting and standardisation could strengthen future VfM in programme delivery as well as future VfM evaluations.
[note] Please refer to note to the readers section at the start of this assessment for details.
About this assessment: This assessment supports the overall evaluation of the BHB programme carried out, which uses the OECD-DAC pillars of (Relevance, Effectiveness, Sustainability, Efficiency, Equity). This component of the overall evaluation assesses the VfM of the BHB programme, focusing on four key VfM pillars: Economy, Efficiency, Effectiveness, and Cost-Effectiveness. The assessment looks at how well the programme utilised financial resources to achieve its intended health and system-strengthening outcomes, particularly in maternal and reproductive health, digital health innovation, and policy reform. By applying a structured judgment framework, this assessment provides an evidence-based analysis of whether BHB optimally converted inputs into health and economic benefits, ensuring its contributions to Bangladesh’s health sector were efficient, impactful and cost-effective.
Economy: were inputs procured at the right cost for the right quality?
‘Economy’ in the context of BHB: In the context of the BHB programme, economy refers to ensuring that financial resources are used optimally to procure inputs such as medical supplies, personnel, training, and infrastructure at the lowest possible cost without compromising quality. Given the scale and complexity of this programme, economic efficiency was a key priority, particularly in the areas of bulk procurement, strategic hiring practices, training expenditures, and financial disbursements. The programme was implemented in a dynamic and evolving context, requiring constant adaptation to emerging needs such as the COVID-19 response.
A key focus of this analysis is to evaluate whether the programme effectively managed its procurement and operational costs, ensuring that the funding from FCDO was utilised in a cost-efficient manner. This requires examining whether bulk procurement strategies, financial management systems, and human resource deployment led to tangible cost savings. Several documented saving mechanisms and efficiency measures highlight the programme’s ability to maximise resources while delivering essential health services to vulnerable populations.
Cost-saving measures and financial efficiency
UNFPA and WHO: Both UNFPA and WHO used bulk procurement mechanisms, particularly through UNFPA’s global supply chain, to ensure competitive pricing. However, no specific percentage of cost reduction has been explicitly documented in the available reports. Instead, the reports mention that consolidating orders and negotiating with global suppliers contributed to cost containment. For instance, medical supplies, including personal protective equipment (PPE) and essential drugs, were procured at globally negotiated rates, which likely resulted in savings compared to local procurement.
However, without direct figures, the exact cost savings remain unquantified, although various studies do indicate cost reductions when using UN-based global procurement mechanisms. A VfM report in Bangladesh, for example, found that procurement through UNICEF systems led to a reduction in costs by approximately 25%. Another report comparing the use of UN platforms for procuring medicines in Kyrgyzstan, Tajikistan, Uzbekistan found that procurement using international platforms will result in 38% reduced prices in comparison to using country mechanisms.. Table VfM 1 below compares UN procurement prices and local market prices in India and Bangladesh for selected contraceptives and drugs.
[note] UNICEF 2021. Value for money assessment: Institutionalize infection prevention control, strengthen oxygen infrastructure, supplies and revitalise essential MNCAH services to combat COVID-19 in the selected hospitals of eight districts in Bangladesh.
[note] GIZ 2019. BACKUP project.

Product	UN procurement price (USD)	Local market price (USD)	Percentage difference	Source
Male Condom (per piece)	0.03	0.40	93%	UNFPA Contraceptive Price Indicator 2023 India market data 2022
Ceftriaxone 1g Injectable Antibiotic	0.868	2.00	57%	UNICEF price 2024 and Bangladesh market price 2024.

Table VfM 1: Comparisons of UN procurement prices versus local procurement prices
Source: GIZ 2019. BACKUP project.
The available data suggests that the procurement through UN-based mechanisms yields significant cost savings due to bulk purchasing, global supplier negotiations, and streamlined logistics. While precise savings for the programme remain unquantified due to data limitations, evidence from other countries demonstrates that similar procurement approaches have led to substantial cost reductions – ranging from 25% to 38% – compared to local procurement.
The price comparisons further reinforce this argument, showing that UN procurement prices for essential commodities are markedly lower than local market prices. For example, as shown in Table VfM 1, male condoms procured through the UN system cost only USD 0.03 per piece compared to USD 0.40 in local markets (a 93% reduction), Copper IUDs (T380A) were 72% cheaper, and Ceftriaxone 1g injectable antibiotic was 57% lower in price. These indicative trends highlight the financial efficiency of UN-based procurement systems and their potential to optimise resource utilisation while ensuring broader access to critical health supplies.
Another significant cost-saving measure was reducing consultant expenditures by utilising internal staff for TA and communications instead of hiring external consultants. UNFPA played a pivotal role in ensuring that in-house expertise was maximised, thereby avoiding consultant fees where possible. Similarly, WHO leveraged its regional and headquarters technical expertise to provide guidance and oversight without additional direct hiring costs.
[note] While specific cost comparisons were not available, the evaluation draws on general assumptions based on established organisational norms. In-house staff are typically considered more cost-effective for delivering TA, as they do not require separate contracting, daily fees, or additional administrative costs. This assumption is consistent with VfM literature and commonly observed practices in UN-implemented programmes.
[note] These finding have been reported by UNFPA and WHO in the annual reports, as well as in discussions that the evaluation team held with respective staff members. However, there is no data available to quantify these claims.
The programme also realised savings in training and capacity-building initiatives by shifting from NGO-led training models to government-facilitated training programmes. For midwifery education, training relied increasingly on government faculty rather than third-party mentors, which not only reduced costs but also ensured long-term sustainability. Additionally, by integrating existing government training infrastructure, the programme reduced the need to rent external training facilities, leading to further cost savings.. A study conducted in Pakistan comparing the unit costs of training health workers through government systems versus private sector NGOs found that training through the private sector was nearly twice as expensive as training conducted using public sector arrangements.
[note] The annual reports do not quantify the exact financial impact of these measures.
[note] Cost per trainee per day for training community health workers was estimated be USD 23 [trained by private sector NGOs] and USD 11 [trained through public sector].
Financial efficiency was further demonstrated through direct financial transfers to the government. A significant portion of funds were allocated through Direct Financial Cooperation (DFC) agreements, which streamlined transactions and reduced overhead costs. While specific VfM data on cost savings through DFC agreements was not available, this approach is generally recognised for reducing administrative layers and improving fund flow efficiency in donor-financed programmes.. Additionally, the programme adhered to government-set pre-negotiated per diem and travel cost rates, which helped ensure consistency and cost control in expenditure management.
[note] WHO Results Report. 2020. Mid-Term Review: highlights those improvements in financial practices and oversight – including through mechanisms like DFC grants – are part of a broader effort to enhance efficiency and internal financial control frameworks. It emphasises that such grants can streamline operations and improve accountability.
Although the evaluation team could not quantify exact savings due to the lack of cost disaggregation from implementing partners, the use of DFCs is aligned with best practices for enhancing financial efficiency, as it reduces reliance on intermediary channels and facilitates timely disbursement of funds with lower transaction overheads.

MSH: MSH has demonstrated improved reporting on savings achieved through an efficient procurement mechanism. By implementing good procurement practices and effective negotiations, the project successfully reduced costs. It is estimated that these measures resulted in total savings of £1.51 million., reflecting strategic vendor negotiations, bulk purchasing efficiencies, and competitive bidding processes. This proactive approach to cost management ensured optimal resource utilisation and enhanced financial accountability within the project.
[note] Calculations by author based on data reported in Programme Completion Report by MSH. These savings are estimated based on actual procurement price less budgeted amount.
A review of specific procurements indicates that, in instances, the winning bids were lower than the budgeted estimates, and additional negotiations with bidders secured further discounts, maximising cost savings. Figure VfM 2 below illustrates the reduction in costs at two key stages: first, the difference between the budgeted amount and the bid amount, and second, the further reduction achieved through negotiations, leading to the final contract value.
Figure VfM 2: Cost savings achieved through good procurement practices

Source: Project completion report for BHB, MSH 2024.

Source: Programme Completion Report for BHB, MSH 2024.
In a few instances, the project also eliminated consultant costs by leveraging in-house expertise. Instead of hiring external consultants for the pre-assessment of retail medicine shops, the MSH team conducted the assessment themselves, resulting in a 21% cost saving (£23,266)​. Similarly, training activities were transitioned from physical to virtual modes, leading to a 55% reduction (£39,102) in the cost of training medicine dispensers​. A particularly significant saving came from ADLRS training, where shifting to virtual training saved £1,000,300 (89%), minimising logistical and venue costs​.
Comparison of fee rates: A key aspect of financial efficiency in development programmes is the cost of TA – this is more relevant for the BHB components implemented by UNFPA/WHO and MSH. BHB relied on a combination of international and national experts to provide policy guidance, health systems strengthening, and implementation support. Understanding how TA costs compare across different hiring modalities, is essential to evaluating VfM. However, there is limited information in this regard to do comprehensive comparisons.
[note] WHO did not provide this information. UNFPA provided average rates for local and international consultants, for MSH the team used the rates as were documented in the final report ‘assessing value for money of the technical assistance packages of the Better Health in Bangladesh programme’, May 2021, HEART.
Figure VfM 3 below presents the minimum and maximum daily consultancy rates achieved by the project through UNFPA and MSH, highlighting significant differences between the two. UNFPA's rates range from £36 to £400, suggesting a broader fee structure that accommodates both lower-cost and higher-end consultants. In contrast, MSH's rates range from £100 to £750, indicating a generally higher baseline and a less economical upper limit.
[note] It is important to note that higher daily rates may reflect efforts to attract niche or high-calibre consultants in competitive markets and therefore do not necessarily represent inefficiency. Fee comparisons must be interpreted alongside the quality of expertise and outputs delivered. A singular focus on reducing costs risks undermining VfM if it compromises quality or effectiveness.

Figure VfM 3: Comparison of TA rates [figures in £]
Source: UNFPA = reported by programme; MSH = report on ‘assessing value for money of the technical assistance packages of the BHB programme’, May 2021, HEART; Benchmark = web search.

Overall, BHB remains highly competitive within FCDO’s range of similar projects and fee rates, offering a flexible fee structure that accommodates a wide range of consultancy expertise. Compared to the benchmark projects, BHB’s rates are compatible..
[note] Our analysis is limited to comparison of rates only – the team were not able to review the quality of consultants that were hired.
Judgement matrix - Economy: The BHB programme demonstrated strong cost economy (evidence consistently demonstrates high VfM across all indicators, with quantifiable results and minimal gaps) in procurement, consultant cost minimisation, and training expenditure reductions. The use of UN-based procurement yielded significant savings, as evidenced by comparative data from other countries, though direct savings figures for BHB remain unquantified due to a lack of data. MSH effectively leveraged competitive procurement, securing £1.51 million in savings. Consultant costs were reduced through internal expertise, and training cost efficiency was enhanced by shifting to government-led and virtual models.
Overall, BHB performed moderately to strongly (most VfM indicators were met and evidence is robust, but one or two limitations exist) on the economy pillar, with notable cost-saving measures. The lack of precise quantification in some areas (e.g., UNFPA/WHO procurement savings) prevents a full ‘strong’ rating, but the programme effectively optimised resource use within its operational constraints. Further details are provided in Table VfM 2 below.

Criteria	Evidence from Analysis	Judgment
Cost-effectiveness of procurement	UNFPA and WHO utilised bulk procurement via global supply chains, resulting in cost containment, though exact savings were not quantified. Evidence from other countries shows reductions of 25%-38%.	Moderate to strong – Procurement was efficient, but lack of direct quantification for BHB limits strong judgment.
Use of competitive pricing mechanisms	MSH saved £1.51 million through strategic vendor negotiations and bulk purchasing. Procurement savings were documented in bidding processes.	Strong – Demonstrated savings through competitive procurement.
Minimisation of consultant costs	UNFPA and WHO leveraged internal expertise to reduce external consultant costs. MSH achieved 21% cost savings by using in-house staff for assessments.	Strong – Clear savings from in-house expertise utilisation.
Training and capacity-building cost efficiency	Training shifted from NGO-led to government-led models, reducing costs and improving sustainability. Virtual training led to a 55%-89% cost reduction.	Strong – Effective cost reduction strategies were applied.
Financial disbursement efficiency	DFC agreements streamlined fund disbursement, reducing overhead costs. Pre-negotiated per diems ensured controlled expenditure.	Moderate to strong – Good financial efficiency, but direct cost savings figures were limited.
Technical Assistance (TA) cost competitiveness	UNFPA’s TA rates ranged from £36 to £400, while MSH's rates were £100 to £750. BHB’s rates remained competitive with FCDO benchmarks.	Moderate to strong – Competitive rates, though MSH’s upper range was higher than UNFPA

Table VfM 2: Economy judgement matrix
Efficiency: how well were inputs converted into outputs?
Introduction to efficiency in context of BHB: Efficiency in BHB relates to how well the programme converted resources into outputs, ensuring that planned interventions were delivered promptly and cost-effectively. The programme required strong coordination between various implementing partners to maximise impact while minimising delays, wastage, and duplication of efforts. This section evaluates whether the programme achieved optimal operational performance, resource utilisation, and service delivery.
A primary factor in efficiency is the timely deployment of health personnel and training activities and the effective implementation of digital health solutions such as DHIS2. Another key component is reducing administrative inefficiencies and improving collaboration between UNFPA, WHO, MSH, and government agencies. Additionally, the efficiency of TA delivery, procurement mechanisms, and financial disbursement processes significantly determine overall efficiency.

Outputs achievement – from an efficiency perspective: This analysis examines the percentage achievement of outputs in the BHB programme against planned targets, providing insights into whether the programme has efficiently translated inputs into results. By analysing variations in performance across different outputs, it is possible to identify areas of efficiency, potential inefficiencies, and opportunities for improvement in resource allocation and execution. Figure VfM 4 below shows the achievement of output targets set under the BHB programme. Results indicate a strong level of efficiency across most outputs, with several exceeding their planned targets. Notably, Output 1.1 (173%), Output 1.2 (126%), and Output 1.3 (107%) reflect high levels of output generation, demonstrating effective resource utilisation. Output 1.4 (99%) performed just below target, still indicating reasonable efficiency. However, Output 1.6 (67%) remains a key underperformer, significantly below target. This shortfall reflects the complexity of the activities under this output, which involved multi-stakeholder coordination, government approvals, and slower-than-anticipated uptake at subnational levels. These challenges highlight the need for better risk anticipation and more flexible planning in future phases.
Output 2-related indicators (Outputs 2.1 to 2.5) show consistent performance, with all outputs falling within a narrow range of 97% to 103%. This close alignment with targets reflects stable implementation and efficient use of resources, with minimal over- or under-utilisation.
Output 3-related indicators (Outputs 3.1 and 3.2) slightly exceeded their targets at 103% and 102%, respectively. While this suggests marginal overachievement, the alignment remains within acceptable bounds and reflects the system's ability to deliver efficiently.
[note] For the purpose of this evaluation, an ‘acceptable range’ refers to outputs that achieve between 90% and 110% of their planned targets. Minor deviations within this range are generally considered normal in implementation and do not indicate significant inefficiency or resource misallocation. This threshold aligns with common international evaluation practices, where a ±10% variance is typically accepted as an indicator of effective delivery, acknowledging the inherent uncertainties and operational flexibilities in development programme implementation (e.g., OECD-DAC evaluation standards and World Bank performance frameworks).

Figure VfM 4: Percentage achievement of targets by output in the BHB Programme - 2024
Source: Compiled from the BHB Logframe and MSH programme completion report.

Output 1.1: Number of childbirths attended by SBAs [in 20 BHB districts]; Output 1.2: Number of childbirths attended by SBAs in Sylhet, Barishal and Chittagong divisions; Output 1.3: Number of total Family Planning (FP) Users (modern methods); Output 1.4: Number of under five children received vitamin-A supplementation, annually; Output 1.6: Number of service providers and community leaders, trained to cope with climate and other shocks; Output 2.1: Number of sub-district health facilities (UHCs) with at least two licensed midwives; Output 2.2: Number of public health facilities meeting facility readiness criteria for delivering post-partum FP services in Sylhet and Chittagong divisions and 20 BHB districts; Output 2.3: Number of health facilities (Medical College Hospitals (MCH), District Hospitals (DH), UHCs) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer; Output 2.5: Number of medicine dispensers trained on Good Pharmaceutical Practice (GPP); Output 3.1: Number of targeted medicine shops accredited; Output 3.2: Number of retail medicine shops, licensed/ license renewed, by Directorate General of Drug Administration (DGDA) using automated licensing and renewal system.

Efficiency in the delivery of demand-driven TA by MSH: The demand-driven TA component was critical in supporting the Ministry of Health and Family Welfare (MOHFW) in implementing the 4th Health, Population, and Nutrition Sector Programme (HPNSP). Efficiency in TA delivery was analysed based on the timeliness of procurement and approval of TA reports, which are key indicators of how well resources were mobilised and utilised to meet programme needs.
While TA delivery does not lend itself easily to quantitative metrics, the indicators used here, i.e. (i) timeliness of procurement and (ii) acceptance of deliverables; are widely recognised proxies for efficiency in demand-driven TA models, particularly in complex institutional environments.
One of the core efficiency indicators was the percentage of TA procured within the stipulated timeframe following approval by the Technical Assistance Committee (TAC). The annual target was 80%, ensuring that most TA procurement processes were completed efficiently within the agreed timeframes. The programme achieved 100% timeliness in 2019, 88% in 2020, and 100% again in 2021, 2022, 2023, and 2024. The minor shortfall in 2020 (88%) may have been due to external factors, such as COVID-19-related disruptions, but the quick recovery to full compliance in subsequent years demonstrates strong process efficiency and adaptability.
Another indicator of efficiency was the proportion of TA reports that were accepted and endorsed by the respective government units receiving the support – such as MOHFW’s directorates (e.g., Directorate General of Health Services (DGHS)), its internal divisions or 'wings' (e.g., Planning Wing, Administration Wing), and affiliated government bodies or implementing entities (such as the DGDA or National Institute of Population Research and Training).
The programme achieved 100% approval across all years, indicating that TA outputs were delivered to the expected quality standards and required no major rework or revisions. This eliminated inefficiencies related to delays, repeated consultations, or non-utilisation of TA outputs, ensuring that the assistance provided was actionable and directly useful to government agencies.
While it is theoretically possible that reports could be approved without scrutiny, in the context of this programme, TA outputs were reviewed through formal multi-level government channels that regularly request revisions. The 100% endorsement rate reflects both the demand-led nature of TA and the delivery of outputs that met technical and operational standards required for institutional uptake.
Quantitative and qualitative efficiency markers: One way of understanding the programme's efficiency is through quantitative and qualitative indicators, reflecting the programme’s ability to maximise impact while minimising resource use. The BHB annual reviews and programme reports highlight significant efficiency gains in health service delivery, digital health implementation, and workforce deployment. These indicators show how well TA and programme interventions were implemented to strengthen the health system.

Summary of key efficiency gain: quantitative and qualitative efficiency markers
Digital transformation of licensing (ADLRS): reduced costs by £1.6 million; cut processing time by 90%. / Training of medicine dispensers: improved correct medicine storage from 45% to 92%. / AMR compliance: prescription-only antibiotic sales rose from 33.7% (2022) to 82.7% (2024). / Facility readiness for PPFP services: expanded from 0 to 515 facilities.

Box 2: Summary of key efficiency gain: quantitative and qualitative efficiency markers
Source: programme documents

A few examples showcasing this are discussed below.
How training medicine dispensers made healthcare more efficient in the target districts: A study conducted in early 2022 evaluated how training medicine dispensers improved efficiency in pharmaceutical service delivery. It compared trained and non-trained dispensers. The findings revealed significant improvements among trained dispensers, enhancing efficiency in safely and accurately dispensing medicines. One of the most notable efficiency gains was in medicine storage, where 92% of trained dispensers adhered to correct temperature guidelines, compared to only 45% of untrained dispensers. This improvement reduced medicine spoilage, ensuring more medications remained effective for longer. Similarly, the training led to better labelling practices, with 95% of trained dispensers correctly labelling medicines, compared to 80% of those without training.
[note] Frontiers. 2023 Assessment of the impact of good pharmacy practices training among drug dispensers in Bangladesh. Vol 14. Frontiers | Assessment of the impact of good pharmacy practices training among drug dispensers in Bangladesh
Another key efficiency improvement was in patient counselling. Among trained dispensers, 99% provided clear instructions on medicine usage, significantly higher than the 92% among untrained dispensers. This meant that more patients received accurate information on how to take their medicines, leading to fewer mistakes, better treatment adherence, and reduced pressure on healthcare facilities due to preventable medication errors. This training programme made medicine dispensing faster, more accurate, and safer, reducing medication errors and the need for patients to revisit pharmacies due to confusion. Additionally, ensuring medicines are stored properly and labelled correctly reduces waste and maximises the impact of available resources.
Efficiency gains in combating Antimicrobial Resistance (AMR) through improved dispensing practices: In Bangladesh, one of the key contributors to AMR is the unregulated sale of antibiotics without valid prescriptions, often due to lack of enforcement and limited awareness among medicine dispensers. The BHB programme addressed this issue through targeted training of medicine dispensers, significantly improving adherence to GPP and reducing the indiscriminate sale of antibiotics.
From an efficiency standpoint, the results of this intervention are notable. In 2022, only 33.7% of dispensers refrained from selling antibiotics without a valid prescription, leading to continued misuse and accelerating AMR. However, by 2024, following widespread training and reinforcement of regulations, this figure jumped to 82.7%, demonstrating a nearly 2.5-fold improvement in compliance. This shift directly reduces unnecessary antibiotic use, ensuring that these medicines remain effective for those who truly need them.
Adherence to prescription-only antibiotic sales under the programme has enhanced healthcare efficiency by reducing unnecessary antibiotic use, lowering healthcare costs, and improving treatment outcomes. With compliance rising, fewer antibiotics are misused, slowing AMR's progression and preserving essential medicines' effectiveness. This shift reduces hospital admissions and the need for stronger, costlier treatments, ultimately easing the financial burden on patients and the healthcare system.
Enhancing efficiency through automation – introduction of ADLRS: DGDA requested that BHB support the automation of existing medicine shop licensing mechanisms by introducing an online licensing system. This was requested to replace an inefficient system whereby obtaining or renewing a medicine shop license was slow, costly, and bureaucratic. Applicants had to make multiple visits to the DGDA offices, often relying on middlemen, leading to delays of 15 to 45 days and extra expenses of up to Bangladeshi Taka (BDT) 38,000 beyond the official fee.
With support from BHB, by December 2023, DGDA completely transitioned from the manual system, making ADLRS the sole licensing platform for medicine shops in Bangladesh. As of 14 December 2024, the system had processed 5,996 applications, with 1,857 successfully approved and the remaining in different stages of review. The introduction of ADLRS resulted in significant efficiency improvements:
- Reduced processing time: Applicants previously waited 15 to 45 days for a new license; with ADLRS, a fully completed application is processed in 2 to 5 days.
- Cost savings for clients: By eliminating intermediaries, clients now only pay the official government fee of BDT 3,000, reducing total costs by up to 92%.
- Simplified renewal process: Previously, renewing a license took 10 to 20 days and cost up to BDT 7,000. Now, it takes a few minutes and costs just BDT 2,000.
- Reduced bureaucratic burden: DGDA staff spend less time on manual paperwork, allowing them to focus on regulatory oversight instead of administrative tasks.
The impact of ADLRS on the efficiency of licensing processes is reflected in the following savings. As shown in Table VfM 3 below. Automation savings were based on time and cost reductions estimated per licensing application, multiplied by the volume of applications processed through the system (as detailed in ADLRS implementation reports).
[note] These calculations are based on the assumption that if a manual system was still in place to process 5,996 applications received as of 14th December 2024, MSH PCR.

Details	Savings
Savings from reduced cost of processing licenses [issuance and renewal]	£556,985
Time cost saving due to reduced processing time [issuance and renewal]	£1,064,954
Total	£1,621,939

Table VfM 3: Summary of efficiency gains for ADLRS
Source: Calculations carried out as part of this VfM assessment

These figures highlight the major financial and time efficiency improvements achieved by moving from a manual to a digital system. The ADLRS has made the licensing process faster, more transparent, and cost-effective, benefiting the government and medicine shop owners by reducing processing delays and eliminating unnecessary costs.
Accelerating access: Strengthening facility readiness for PPFP services: Over the project period, the number of public health facilities meeting facility readiness criteria for PPFP services increased from 0 at the baseline to 515 reporting facility readiness for providing PPFP services. This achievement represents a significant efficiency gain, ensuring wider access to PPFP services without requiring major new infrastructure investments. With more facilities equipped to provide quality FP services, women now have greater access to counselling and contraceptive options, reducing unintended pregnancies and maternal health risks. Data on PPFP use in the 20 BHB districts shows an increase of more than 3.5 times between 2019 and 2024.
Judgement matrix – Efficiency: The BHB programme demonstrated strong efficiency (evidence consistently demonstrates high VfM across all indicators, with quantifiable results and minimal gaps), particularly in training interventions, digital health implementation, TA delivery, and the expansion of service delivery. Many key outputs exceeded their targets – most notably Output 1.1 (173%), Output 1.2 (126%), and Output 1.3 (107%), indicating effective resource utilisation. TA procurement was consistently completed on time, except for a minor delay in 2020 (88%) due to COVID-19 disruptions, with all TA reports endorsed without requiring major revisions. Training medicine dispensers led to substantial efficiency gains in medicine storage, labelling, and counselling, while the ADLRS system significantly enhanced the efficiency of medicine shop licensing, resulting in time and cost savings of over £1.5 million.
A few areas, such as Output 1.4 (99%) and Output 1.6 (67%), showed relatively lower achievement (evidence shows partial VfM performance; either mixed results across indicators or limitations in evidence base), suggesting some implementation bottlenecks. However, these were outweighed by strong performance in digital transformation, health workforce optimisation, and demand-driven TA delivery.
Overall, the BHB programme performed strongly on the efficiency pillar, demonstrating the effective conversion of inputs into outputs while optimising costs, time, and human resources. Table VfM 4 provides further details.
Criteria	Evidence from Analysis	Judgment
Achievement of planned outputs	Several outputs exceeded targets (e.g., Output 1.1 at 173%, Output 1.2 at 126%, Output 1.3 at 107%). Output 1.4 performed close to target (99%), while Output 1.6 (67%) lagged behind. This suggests strong overall achievement with some implementation bottlenecks in selected areas.	Moderate to strong – High overall output achievement, but some implementation bottlenecks.
Timeliness of TA procurement and delivery	100% of TA procurement was completed within agreed timeframes in most years (except 2020, which was 88% due to COVID-19). All TA reports were approved without major revisions.	Strong – TA was procured and delivered efficiently with minimal delays.
Efficiency in training and capacity building	Trained medicine dispensers improved efficiency: 92% adhered to correct storage vs. 45% untrained, 95% labelled correctly vs. 80% untrained, and 99% provided accurate counselling vs. 92% untrained.	Strong – Training enhanced workforce efficiency and reduced errors in service delivery.
Efficiency in digital interventions	The introduction of ADLRS reduced license processing time from 15-45 days to 2-5 days, cut applicants' costs by 92%, and saved over £1.5 million in time and financial efficiency.	Strong – Digital transformation significantly increased efficiency in public service delivery.
Health service delivery efficiency	Facility readiness for postpartum FP services increased from zero to 515 facilities, tripling PPFP usage over five years.	Strong – Optimised existing infrastructure to expand service coverage efficiently.
Efficiency in reducing AMR risks	Trained dispensers improved compliance with prescription-only antibiotic sales from 33.7% (2022) to 82.7% (2024), reducing unnecessary antibiotic use.	Strong – Addressed a critical public health issue with targeted, efficient intervention.

Table VfM 4: Efficiency judgement matrix
Effectiveness: to what extent did the programme achieve its intended results?
Effectiveness in the BHB context measures the extent to which the programme successfully achieved its planned outputs and outcomes. As this is a TA-heavy programme, effectiveness cannot be understood solely on direct service delivery figures. Still, it must also consider policy influence, system strengthening, and long-term sustainability of interventions.
The programme aimed to improve maternal and reproductive health, strengthen national and subnational health systems, and enhance digital health and health governance. This section evaluates key indicators, such as improvements in maternal and neonatal health outcomes, health service utilisation, digital health adoption, and policy impact.
Outcomes achievement – from an effectiveness perspective: Figure VfM 5 below illustrates the achievement of outcome indicators against planned targets, providing insights into the effectiveness of the programme’s implementation. It categorises performance into two key outcome areas, with multiple sub-indicators reflecting progress. The programme has been largely effective in achieving its intended outcomes, with most indicators meeting or exceeding their targets. Outcome 1 demonstrates mixed performance. While some indicators such as Outcome 1.3 (111%) and Outcome 1.5 (100%) either exceeded or met their targets, others – including Outcome 1.1 (97%), Outcome 1.2 (96%), and Outcome 1.4 (94%), fell slightly short. These shortfalls, however, remain within the generally acceptable performance range and do not suggest major implementation failures. Outcome 1.6 stands out with a significant overachievement at 146%, which may reflect efficiency gains and system-level scalability. In contrast, Outcome 2 reflects consistent and balanced delivery. Both Outcome 2.1 and Outcome 2.2 achieved 100% of their targets, indicating precise and well-aligned implementation. Outcome 2.3 exceeded expectations at 113%, suggesting positive performance without raising concerns about disproportionate resource use. The overall results point to strong programme effectiveness.
[note] For the purpose of this evaluation, an ‘acceptable range’ refers to outputs that achieve between 90% and 110% of their planned targets. Minor deviations within this range are generally considered normal in implementation and do not indicate significant inefficiency or resource misallocation. This threshold aligns with common international evaluation practices, where a ±10% variance is typically accepted as an indicator of effective delivery, acknowledging the inherent uncertainties and operational flexibilities in development programme implementation (e.g., OECD-DAC evaluation standards and World Bank performance frameworks).

Figure VfM 5: Percentage achievement of targets by outcomes in the BHB Programme - 2024
Source: Compiled from logframe and programme reports.

Outcome 1.1: Percentage of births attended by skilled providers and Ratio of births in facilities by poor to rich women; Outcome 1.2: Contraceptives Prevalence Rate (CPR) for modern methods (all women); Outcome 1.3: CPR for modern methods in Sylhet and Chittagong divisions (lagging behind areas); Outcome 1.4: % of newborn received essential newborn care (at least 2 postnatal signal function care within 2 days of birth); Outcome 1.5: Percentage of tuberculosis (TB) cases remaining un-detected; Outcome 1.6: Number of women screened for cervical cancer; Outcome 2.1: Percentage of district health facilities (#40) using digital systems to manage assets; Outcome 2.2: Percentage of health facilities reporting no stock-out of essential medicines; Outcome 2.3: Percentage of accredited medicine shops with improved dispensing practises as per national guidelines.

Maternal and neonatal health outcomes:
A primary objective of the programme was to reduce maternal and neonatal mortality and improve access to SBAs. The following indicators demonstrate the programme’s contributions towards this.
Midwifery Training and Deployment: Over 400 midwives were deployed, significantly improving access to SBAs, particularly in rural and underserved areas. In addition to deployment, the programme supported continuous professional development for midwives, ensuring they remained updated on evidence-based maternal care practices. Figure VfM 6 below shows the increasing role of midwives in conducting normal deliveries in the BHB districts.

Figure VfM 6: Share of normal vaginal deliveries by midwifes in BHB districts
Source: Data analysed using programme data.

Significant progress in strengthening maternal health services can be seen by the increasing proportion of normal vaginal deliveries conducted by midwives in BHB-supported districts, rising from 54.9% in 2019 to 91% in 2024. From an effectiveness perspective, this trend indicates improved access to midwives, enhanced capacity and confidence among midwives, and a positive shift toward midwife-led maternal care. The trend contributes to more equitable and cost-effective maternal healthcare delivery, particularly in underserved settings.

Deliveries by SBAs: The number of deliveries attended by SBAs supported by the BHB programme has shown a clear upward trend over the years, reflecting its effectiveness in improving maternal and newborn health services. Number of deliveries dropped from 2018 (20,888) to 2019 (11,956), but the number has increased significantly overall from 2019 to 2024, despite a temporary decline in 2023, reaching 49,577 in 2024, as seen in Figure VfM 7. This growth indicates that the programme has successfully expanded access to SBA, which is critical for reducing maternal and neonatal mortality and ensuring safer childbirth practices.
Figure VfM 7: Deliveries by SBAs under the BHB programme
Source: Logframe data [MOHFW HMIS]
The recovery in 2024 may reflect corrective actions taken by implementing partners, such as intensified supervision and training reinforcement, though other factors could also have contributed to the observed pattern. The ability to rebound effectively reflects the programme's resilience and adaptability in responding to challenges. From an effectiveness standpoint, the overall trajectory demonstrates that the BHB initiative has successfully contributed to increasing institutional births, a key indicator of improved maternal health outcomes.
[note] This interpretation is drawn from qualitative interviews and internal progress reports, but is not supported by conclusive causal evidence.
Health system and TA related effectiveness
Stock-out reduction of essential medicines: The increase in health facilities reporting no stock-outs of essential medicines from 60% to 100% reflects a significant improvement in supply chain management and service delivery effectiveness. This suggests stronger procurement planning, better logistics management, and enhanced stock monitoring systems, ensuring consistent availability of life-saving medications. The uninterrupted supply likely improved treatment adherence reduced patient referrals due to medicine shortages, and strengthened public trust in health facilities. Additionally, achieving 100% availability indicates effective policy interventions, better financing mechanisms, and improved coordination between national and district-level supply chains.
TA support implication: BHBs TA supported Bangladesh’s 5th HPNSP. The BHB e-Learning platform, which trained 25,408 pharmacy professionals across 33 courses, was another highly effective intervention, ensuring long-term capacity building in pharmaceutical management.
A key policy outcome of the programme was its contribution to enacting the Drug and Cosmetics Act 2023, which enhanced regulatory oversight and stricter safety standards for pharmaceutical products in Bangladesh. BHB also supported the development of national guidelines for pharmacy accreditation and medicine shop licensing, ensuring that DGDA had a standardised framework to sustain accreditation processes beyond the project’s lifecycle.
Capacity building and sustainability of interventions: One of the programme’s strongest effectiveness outcomes was its emphasis on sustainability and long-term capacity building. By embedding digital tools like ADLRS and Pharmacy Management Software (PMS) within DGDA and Pharmacy Council of Bangladesh (PCB), BHB ensured that government institutions could independently manage pharmaceutical regulation post-programme. Similarly, the BHB e-learning platform, which trained thousands of pharmacy professionals, will continue to serve as a capacity-building resource for future pharmacists and medicine dispensers.
BHB also played a crucial role in institutionalising regulatory practices within DGDA and PCB, enabling these agencies to continue pharmacy accreditation, licensing, and quality assurance without external support. The programme’s successful handover of digital platforms, training curricula, and policy frameworks to national agencies further reinforces its long-term sustainability.
Judgement matrix – Effectiveness: The BHB programme demonstrated strong effectiveness (evidence consistently demonstrates high VfM across all indicators, with quantifiable results and minimal gaps), achieving most planned outcomes and exceeding targets in several key areas. Maternal health improvements were particularly notable, with midwife-led deliveries increasing from 54.9% in 2019 to 91% in 2024, and deliveries attended by SBAs rising from 11,956 to 49,577 over the same period. These trends reflect enhanced access to skilled care and a strengthened maternal health system. Additionally, the reduction of essential medicine stock-outs to 100% underscores the programme’s effectiveness in improving supply chain management and ensuring continuous service delivery.
From a TA and policy reform perspective, BHB contributed to significant achievements, including support to the Drug and Cosmetics Act 2023, development of national pharmacy accreditation guidelines, and the rollout of a scalable e-learning platform that trained over 25,000 pharmacy professionals. The successful handover and institutional embedding of digital tools such as ADLRS and PMS further reinforces the programme’s sustainability and long-term impact.
Overall, the BHB programme performed strongly on the effectiveness pillar, delivering measurable health system improvements, contributing to key policy reforms, and ensuring institutional capacity for sustained progress. Table VfM 5 provides further details.
Criteria	Evidence from Analysis	Judgment
Achievement of planned outcomes	Outcome 1 showed mixed but acceptable performance: Outcome 1.3 (111%) and 1.5 (100%) met/exceeded targets; 1.1 (97%), 1.2 (96%), and 1.4 (94%) slightly below target. Outcome 1.6 notably overachieved (146%). Outcome 2 indicators met or exceeded targets (e.g., 2.3 at 113%).	Strong – Most outcomes met or exceeded targets, with minor shortfalls.
Maternal and Neonatal Health Impact	Midwife-led deliveries increased from 54.9% (2019) to 91% (2024). SBA-supported deliveries rose from 20,888 (2018) to 49,577 (2024), reflecting improved access to skilled birth attendance.	Strong – Significant improvements in access to skilled birth attendance.
Health system strengthening – Medicine stock-outs	Facilities reporting no stock-outs of essential medicines increased from 60% to 100%.	Strong – Demonstrates effective supply chain and procurement improvements.
Technical Assistance (TA) effectiveness	100% TA reports were approved across all years. Supported Bangladesh’s 5th HPNSP, including key contributions to the Drug and Cosmetics Act 2023.	Strong – TA was timely, relevant, and contributed to policy reform.
Digital health and sustainability impact	BHB’s e-learning platform trained 25,408 pharmacy professionals across 33 courses. ADLRS and PMS systems embedded in national institutions, ensuring continuity post-programme.	Strong – Ensured long-term impact through institutional digital integration.
Policy and regulatory effectiveness	Contributed to national pharmacy accreditation guidelines, improving medicine shop licensing and regulatory oversight.	Strong – Strengthened governance frameworks for pharmaceutical regulation.

Table VfM 5: Effectiveness judgement matrix
Cost-effectiveness: were the programme resources used to achieve the greatest possible impact?
Introduction to cost-effectiveness: Cost-effectiveness in the BHB programme aims to understand whether the financial resources invested resulted in optimal health outcomes, particularly in maternal and reproductive health (including family planning), digital health strengthening, and overall health system improvements. Given that this is a TA-heavy programme, cost-effectiveness must be evaluated based on direct service delivery outcomes and long-term system-level benefits, such as policy influence, capacity building, and technology adoption. The analysis examines whether the programme's financial inputs generated the best possible health returns, ensuring that resources were allocated efficiently to maximise impact.
Interventions on cost-effectiveness: Evaluating the cost-effectiveness of this programme presents inherent challenges due to the diverse range of interventions supported through TA. Unlike direct service delivery programmes, where cost-effectiveness can be more precisely quantified, the impact of TA-driven interventions often materialises indirectly by strengthening health systems, improving policies, and enhancing workforce capacity. Given these complexities, a full-scale cost-effectiveness evaluation of every intervention under BHB is not feasible.
To reasonably approximate the programme’s cost-effectiveness, the evaluation team selected key interventions where measurable health outcomes – such as lives saved, and disability-adjusted life years (DALYs) averted – can serve as proxies for the broader impact of TA support. Specifically, the team focused on four key areas: (i) the BEmONC services [including the midwifery Programme], which contributed to improved maternal and neonatal health outcomes; (ii) FP component; (iii) procurement and distribution of contraceptive implants, which enhanced access to long-acting FP methods; and (iv) the cervical cancer screening programme, which improved early detection and treatment coverage.
[note] Enhanced capacity to increase supply of family planning information and services (Including IPAS).
Increased facility readiness to provide BEmONC services [including midwifery programme]: Using service data on healthcare provision in 20 BHB districts through the midwifery programme, the team estimated the number of potential maternal and neonatal deaths averted due to FCDO’s intervention. LiST was used to model these impacts, incorporating Bangladesh-specific data to estimate the number of lives saved. The team kept all other parameters constant in the LiST and incorporated impact only relevant to SBA service provision.
[note] LiST is a modelling tool that allows users to estimate the impact of coverage change on mortality in low- and middle-income countries. It calculates the number of deaths averted under various scenarios, providing planners and decision-makers with an evidence-based approach for setting targets. The team used LiST version 6.37.
As part of our evaluation of the programme’s impact, the team estimated that increased facility readiness to provide BEmONC services, including the roll-out of the midwifery programme – contributed to averting approximately 434 maternal deaths and 5,258 neonatal deaths. These estimates reflect the broader health system improvements supported by the programme. However, it is important to recognise that not all outcomes can be fully attributed to the programme alone. The provision of BEmONC services depends on a combination of programme inputs and resources provided by the broader health system, such as existing infrastructure, human resources, and operational funding, which were not directly financed by the project.
To account for this shared responsibility, the team applied an attribution factor of 40% to the estimated deaths averted. This adjustment acknowledges that while the programme played a significant enabling role, it was not the sole contributor to the observed outcomes. The adjusted, programme-attributable figures therefore stand at, (i) 174 maternal deaths averted (40% of 434); and (ii) 2,103 neonatal deaths averted (40% of 5,258). Additionally, the team estimated the potential DALYs averted because of these interventions, which are presented in Figure VfM 8 below.
[note] Please refer to note to the readers section (k) point for further details on attribution estimation.

Figure VfM 8: Maternal and neonatal DALYs averted
Source: Calculations carried out as part of the VfM assessment based on deaths averted data estimated using LiST.

It is estimated that a total of 162,407 DALYs have been averted over the project’s duration. By valuing these DALYs using Bangladesh’s GDP per capita, the estimated benefits generated amount to £321.2 million over the project implementation period. The intervention can be classified as highly cost-effective as the cost per DALY averted is estimated to be £32.7 – which is almost 59 times lower compared to the GDP per capita of Bangladesh. For each £1 invested in this intervention, the team estimate a return of £60.
[note] The DALYs averted per maternal and neonatal death were estimated using the Years of Life Lost (YLL) component of the DALY formula, as disability (YLD) is minimal in these cases. For maternal deaths, YLL was calculated based on an average age at death of 30 years and a life expectancy of ~75 years, resulting in 39–51 DALYs averted per maternal death. For neonatal deaths, assuming a life expectancy of 74–76 years, YLL was nearly equal to total life expectancy, leading to 74–76 DALYs averted per neonatal death. Estimates were contextualised using Bangladesh-specific life expectancy data. The team used the lower bound estimates i.e. 1 maternal death = 39 DALYs and 1 neonatal death = 74 DALYs.
[note] The Human Capital Approach was used to monetise the health benefits of preventing maternal and neonatal deaths by assigning an economic value to each DALY averted. This method assumes that one DALY represents one lost year of full health and productivity, and the economic value of that lost year can be approximated using Bangladesh’s GDP per capita for the corresponding year. The total benefit of preventing a death was calculated by multiplying the estimated DALYs averted per maternal or neonatal death by the GDP per capita for that year.
Enhanced capacity to increase supply of family planning information and services (Including IPAS): The cost-effectiveness analysis of the BHB programme's support to enhance the supply of FP information and services demonstrates significant health and economic returns. The analysis was based on service delivery data from BHB-supported facilities in target districts, with a focus on four high-impact modern contraceptive methods: injectables, implants, intrauterine devices (IUDs), and female sterilisation. The table below shows the number of FP services provided by method.
Methods	2019	2020	2021	2022	2023	2024	Total
Injectable	253,777	199,808	201,201	222,418	364,818	185,893	1,427,915
IUD	40,614	10,796	29,620	30,104	28,645	25,268	165,047
Implant	116,988	28,089	88,055	96,387	92,318	101,571	523,408
Female sterilisation	36,759	30,909	22,718	23,018	22,095	17,782	153,281

Table VfM 6: Number of FP services provided in BHB districts
Source: Programme data.
Health outcomes were estimated using the Maria Stopes International (MSI) Impact 2 (version 6) tool, which projected the number of maternal and child deaths averted as well as unsafe abortions prevented as a result of the services provided. In parallel, DALYs averted were estimated using DALY averted factors already estimated in this study and detailed in the BEmONC section [1 maternal death = 39 DALYs averted; 1 neonatal death = 74 DALYs averted] and their economic value was monetised using the human capital approach.
Details	2019	2020	2021	2022	2023	2024	Total
Total Deaths averted (a)	204	244	342	368	453	447	2,058
Maternal deaths averted	33	38	50	50	57	52	279
Child deaths averted	171	207	292	318	396	395	1,779
Unsafe abortions averted (a)	19,844	24,010	33,945	36,971	46,015	45,919	206,706
Total DALYS averted (b)	13,942	16,763	23,550	25,487	31,519	31,252	142,514
Maternal DALYs averted	1,306	1,475	1,936	1,946	2,220	2,014	10,899
Child DALYs averted	12,636	15,288	21,614	23,541	29,299	29,238	131,615
Benefits estimation: Monetised DALYS – £ million(c)	£23.3	£29.4	£42.5	£56.2	£64.1	£64.3	£279.7

Table VfM 7: Impact estimates for provision of FP services [40% attribution applied]
Note:
(a) source of these deaths is the MSI impact 2 (version 6) tool.
(b) using deaths averted and applying the DALY factor as estimated before.
(c) DALYs were monetised using GDP per capita of Bangladesh
The results reveal a highly cost-effective intervention. The cost per DALY averted was estimated at just £25 – substantially lower (77 times lower in comparison to the GDP per-capita of Bangladesh) than typical cost-effectiveness thresholds used by global health bodies such as WHO. The cost per new FP adopter was calculated at £3.9, which compares favourably with international benchmarks. A study by the Guttmacher Institute estimates the average cost per additional user of modern contraception in low- and middle-income countries ranges between US$7 and US$31 (approx. £5.5–£24) depending on the method mix and service delivery context. Likewise, the cost per unsafe abortion averted was £17, which is considerably lower than the estimated cost of treating complications from unsafe abortions. WHO estimates that the average cost of post-abortion care in low-income countries can range from £55 to £78 per case, underscoring the preventative and cost-saving nature of FP services. Notably, the return on investment was estimated at £78 for every £1 invested.
[note] Guttmacher Institute. 2017. Adding It Up: The Costs and Benefits of Investing in Sexual and Reproductive Health 2017
[note] WHO. 2012. Safe abortion: technical and policy guidance for health systems.
Overall, the analysis strongly supports the conclusion that the BHB programme’s family planning interventions deliver excellent value for money. The low unit costs, combined with significant health and economic returns, present a strong case for continued investment and potential scale-up in similar underserved contexts.
Procurement and distribution of Single-Rod Contraceptive Implant [ROD]: BHB supported the procurement of single rod implants, an FP method that provides 5 years of protection following insertion. FCDO, through BHB, provided 200,000 RODs through UNFPA. Using the MSI Impact 2 (version 6) tool, the team estimated the impact of providing 200,000 RODs in Bangladesh over the project’s duration. The model was configured with Bangladesh-specific data to ensure accuracy. Table VfM 8 below presents the key impact figures, assuming 40% attribution of results to the BHB programme. This attribution assumption was applied to reflect that while BHB supported procurement and distribution of implants, other elements of service delivery, such as insertion, counselling, and follow-ups, were supported by the government health system. As such, attributing the full health impact to BHB would likely overstate its contribution.
Table VfM 8 below presents an analysis of the benefits derived from deaths averted, DALYs averted, and estimated economic gains in £ million. A total of 650 deaths and 45,854 DALYs were averted. The estimated economic benefits totalled £89.3 million over the project life. The intervention can be classified as highly cost-effective as the cost per DALY averted is estimated to be £30 – which is almost 65 times lower compared to the GDP per capita of Bangladesh. For each £1 invested in this intervention, the team estimate a return of £65.
Details	2020	2021	2022	2023	2024	Total
Total Deaths averted (a)	167	146	128	112	97	650
Maternal deaths averted	21	16	12	8	6	63
Child deaths averted	146	130	116	103	92	586
Total DALYS averted (b)	11,611	10,239	9,028	7,960	7,017	45,854
Maternal DALYs averted	822	627	464	330	219	2,461
Child DALYs averted	10,789	9,612	8,564	7,630	6,798	43,393
Benefits estimation: Monetised DALYS – £ million (c)	£20.4	£18.5	£19.9	£16.2	£14.4	£89.3

Table VfM 8: Impact estimates for provision of ROD implants
Note:
(a) source of these deaths is the MSI impact 2 (version 6) tool.
(b) using deaths averted and applying the DALY factor as estimated before.
(c) DALYs were monetised using GDP per capita of Bangladesh

Improved cervical cancer screening, diagnosis and treatment services: BHB through UNFPA supported the cervical cancer screening programme in 20 project districts. The efforts focus on increasing screening and diagnosis while improving data management and referral mechanisms. Table VfM 9 below presents the total number of women screened and diagnosed positive for cervical cancer.
Details	2019	2020	2021	2022	2023	2024	Total
Women screened	126,031	142,359	155,143	348,825	368,227	251,660	1,392,245
Women positive	5,147	4,422	6,255	8,118	7,925	5,922	37,789

Table VfM 9: Number of women screened and tested positive for cervical cancer
Source: Programme data.
Between 2019 and 2024, the project provided screening services to over 1.3 million women, identifying 37,789 positive cases, resulting in a positivity rate of approximately 2.5%. The team used service provision data to estimate the number of potential deaths averted due to the intervention. This data on deaths averted was then used to estimate the DALYs averted as a result. Table VfM 10 below summarises the year-wise deaths and DALYs averted with the monetised value of DALYs.
[note] Our approach to estimating deaths averted due to cervical cancer screening follows a standard epidemiological method based on baseline mortality rates, screening coverage, test sensitivity, and treatment effectiveness. First, the team estimate the expected cervical cancer deaths without screening by applying the baseline mortality rate (per 100,000 women) to the total population of women of reproductive age. Next, determine the mortality reduction factor, calculated as the product of screening coverage, test sensitivity, and treatment effectiveness, which represents the proportion of cases that screening and subsequent treatment prevent from progressing to fatal stages. Using this factor, the team estimate deaths with screening by adjusting the baseline mortality figures. Finally, the difference between deaths without screening and deaths with screening gives the estimated deaths averted due to the screening programme. This method assumes that early detection and timely treatment effectively reduce cervical cancer mortality.
Details	2019	2020	2021	2022	2023	2024	Total
Number of deaths averted	7	8	9	20	21	14	78
Number of DALYs averted	3,670	3,199	4,463	5,991	5,886	4,367	27,576
Monetised DALYs – £ million	£6.1	£5.6	£8.0	£13.2	£12.0	£9.0	£53.9

Table VfM 10: Number of potential deaths and DALYs averted as a result of cervical cancer screening
Source: Calculations carried out as part of the VfM assessment

Table VfM 10 presents the estimated impact of cervical cancer screening in terms of deaths averted, DALYs averted, and the monetised value of DALYs from 2019 to 2024. Over this period, a total of 78 deaths were prevented, and 27,576 DALYs were averted, highlighting the significant health benefits of the screening programme. The monetised value of these averted DALYs amounts to £53.9 million, showcasing the economic benefit of reducing the disease burden through early detection and intervention.
[note] The team used the Human Capital Approach to value DALYs (as also explained in footnote 24). The Human Capital Approach was used to monetise the health benefits of preventing maternal and neonatal deaths by assigning an economic value to each DALY averted. This method assumes that one DALY represents one lost year of full health and productivity, and the economic value of that lost year can be approximated using Bangladesh’s GDP per capita for the corresponding year. The total benefit of preventing a death was calculated by multiplying the estimated DALYs averted per maternal or neonatal death by the GDP per capita for that year.
According to financial reports, the implementation of the cervical cancer screening programme across 20 BHB districts amounted to a total cost of £1.78 million. The cost per DALY averted is estimated at £65, positioning the intervention as highly cost-effective when benchmarked against Bangladesh’s GDP per capita (£2,057). This means that the cost per DALY averted is approximately 30 times lower than the country’s GDP per capita, reinforcing the programme's efficiency in delivering significant health benefits at a relatively low cost.
[note] To understand the cost-effectiveness, the team applied the recommendations of the Commission on Macroeconomics & Health and the WHO. According to these guidelines: (i) Very cost-effective: Cost per DALY is less than GDP per capita of the country; (ii) Cost-effective: Cost per DALY is between 1- and 3-times GDP per capita of the country; and (iii) Not cost-effective: Cost per DALY exceeds 3 times GDP per capita of the country.
Additionally, the programme demonstrates a high economic return, with an estimated £29 generated for every £1 invested, highlighting its substantial financial and social impact. The cost per woman screened stands at £1.3, reflecting the affordability of expanding screening efforts and further supporting the case for scaling up the initiative to enhance cervical cancer prevention and early detection.
A study conducted in lower- and middle-income countries found that a comprehensive cervical cancer screening programme had a cost per DALY averted of £51, slightly lower than the BHB estimate of £65. However, the cost per woman screened for BHB was lower (£1.3) than in the lower- and middle-income countries (£6.6) reported by the study.
[note] https://obgyn.onlinelibrary.wiley.com/doi/10.1002/ijgo.12184
Programme level cost-effectiveness: Evaluating the cost-effectiveness of a TA programme presents inherent challenges, as the impact of many interventions remains indirect, diffuse, or difficult to quantify. Unlike service delivery programmes, where outcomes such as lives saved or diseases averted can be directly attributed to specific interventions, TA programmes often function by strengthening systems, improving policies, and enhancing capacities, changes that manifest overtime and through complex pathways.
The team adopted a selective approach to overcome this challenge and provide a meaningful cost-effectiveness analysis. Rather than attempting to capture the full breadth of benefits, the team focused on key interventions where the impact can be tracked, quantified, and, where possible, monetised. These interventions were chosen [discussed in the previous section] based on the availability of reliable data and the feasibility of drawing a direct link between programme activities and measurable health or economic outcomes.
After estimating the benefits of these selected interventions, the team aggregated them to form a conservative estimate of the programme’s contribution. This total estimated benefit was then compared against the total cost of the BHB programme to derive an indicative measure of cost-effectiveness.
It is important to emphasise that this approach inevitably underestimates the true benefits of the programme. Many systemic improvements facilitated by the BHB programme – such as enhanced governance, better financial management, improved data utilisation, and strengthened workforce capacities, have long-term benefits that are difficult to capture in immediate cost-effectiveness calculations. Additionally, the programme’s contribution to policy and institutional strengthening creates enabling conditions for improved service delivery and health outcomes that extend far beyond the interventions funded directly.
Despite this inherent understatement of benefits, the cost-effectiveness analysis still serves a valuable purpose. It provides a tangible narrative on how the programme’s investments translate into measurable health and economic gains, offering a clear perspective on the value generated by the resources deployed. Furthermore, by using conservative estimates, the analysis ensures credibility and robustness, avoiding overly optimistic projections that could undermine the analysis.
The table below combines the deaths averted, DALYs averted, and benefits generated by implementing BHB in 20 target districts.
Details	Deaths averted	DALYs averted	Economic benefits generated - / £ million
Increased facility readiness to provide BEmONC services [including midwifery programme]	2,277	162,407	£321.17
Enhanced capacity to increase supply of family planning information and services (Including IPAS)	2,058	142,514	£279.67
Procurement and distribution of implants [ROD]	650	45,854	£89.34
Improved cervical cancer screening, diagnosis and treatment services	78	27,576	£53.94
Cost and time savings from implementation of ADLRS	n/a	n/a	£1.62
Total	5,063	378,351	£745.75

Table VfM 11: Summary of deaths and DALYs averted, and benefits generated
Source: Calculations carried out as part of the VfM assessment

The cost per DALY averted is estimated to be £99, making the BHB programme highly cost-effective based on WHO’s cost-effectiveness criteria. Cost per DALY averted is 19 times lower than Bangladesh’s GDP per capita, reinforcing the programme’s strong value for money.
Comparison of VfM impact and outcome level cost indicators with the Business Case estimates
[note] The observed variances between the Business Case, VfM evaluation, and Annual Review 2024 estimates can be attributed to several methodological, temporal, and contextual factors. First, it is important to note that the Business Case estimates were based on ex-ante projections made at the design stage, often using global or regional benchmarks, hypothetical coverage levels, and assumed impact pathways. These estimates tend to be conservative or aspirational and may not fully reflect on-ground realities or implementation nuances. In contrast, the VfM evaluation is an ex-post analysis conducted using actual implementation data, refined costing inputs, and updated assumptions around coverage, service delivery effectiveness, and attribution of outcomes. This tends to produce more accurate and sometimes more favourable cost-effectiveness metrics, as seen in the lower cost per life saved and cost per case averted in the VfM evaluation. The Annual Review 2024, on the other hand, reflects a snapshot of just one year of implementation and is likely influenced by annual variations in expenditure patterns, service uptake, and external factors (e.g., supply chain issues, delayed disbursements, or seasonal demand shifts). Since it is not a cumulative analysis like the VfM evaluation, it may present a skewed picture – especially if the denominator (e.g., lives saved, or cases averted in one year) is low relative to the annual cost base. Moreover, the Annual Review may apply a different attribution logic or be more conservative in crediting outcomes directly to programme interventions, which could further inflate the cost per outcome.
Outcome level cost indicators: A key part of the VfM analysis for the BHB programme involves a comparative analysis of outcome-level cost indicators across three benchmarks: (i) the original estimates provided in the Business Case, (ii) the latest VfM findings based on implementation data, and (iii) the most recent cost figures reported in the Annual Review 2024. These benchmarks help to demonstrate the cost-efficiency pillar of the programme by illustrating the extent to which service delivery has achieved value relative to initial projections. Three outcome-level indicators are examined: cost per patient for BEmONC, cost per cervical cancer screening, and cost per FP adopter.
The cost per BEmONC patient serves as a strong marker of implementation efficiency. The Business Case estimated this at £83 per patient. The VfM analysis, however, shows a reduced cost of £56 per patient, indicating a 33% efficiency gain. This reduction suggests that the intervention was implemented with greater precision, leaner inputs, and improved facility-level management. Contributing factors may include targeted resource allocation to high-burden facilities, integrated training models for midwives and obstetric staff, and more cost-efficient procurement of equipment and supplies. In contrast, the Annual Review 2024 reports a cost of £50.1 per patient – a figure that remains 40% lower than the Business Case and slightly lower than this VfM assessment.
The cost per cervical cancer screening further reinforces the programme’s cost-efficiency. The Business Case projected a unit cost of £2, based on VIA as the primary screening modality. This VfM assessment reveals a lower cost of £1.28 per screening, reflecting efficient programme rollout, effective provider training, and integration of services within existing reproductive health platforms. The Annual Review 2024 figure stands at £1.33, which is slightly higher than the VfM estimate but still well below the original projection.
The third indicator, cost per FP service provided, adds further nuance to the outcome-level cost-efficiency analysis. The Business Case placed this cost at £6, while this VfM analysis estimates it at £3.9, showing a 34% reduction. This likely results from streamlined service delivery, improved commodity distribution, and scaled-up community-based FP promotion. The Annual Review 2024 reports a lower figure of £2.5, which remains appreciably more efficient than the Business Case estimate.
Taken together, this analysis confirms that the BHB programme has delivered meaningful efficiency gains across all outcome-level service delivery areas. The VfM estimates consistently fall below the original Business Case projections and remain competitive against the Annual Review 2024. These trends reflect improvements in operational efficiency, better use of technical assistance, and programmatic learning over time. When analysed in combination, these perspectives present a compelling narrative of cost-effective health service delivery under the BHB programme.
Impact level cost indicators: A comparison of impact-level cost-effectiveness indicators across the Business Case, the VfM assessment, and the Annual Review 2024 provides a clear picture of how the BHB programme has performed in terms of delivering VfM. Three key indicators are analysed: cost per life saved through BEmONC, cost per unsafe abortion averted through family planning services, and cost per cervical cancer case averted through screening interventions. These indicators represent critical areas of maternal, reproductive, and preventive health, and demonstrate how efficiently the programme translates investments into high-impact outcomes.
The cost per life saved through BEmONC is estimated at £2,329 in this VfM assessment, compared to £2,079 in the Business Case, and £3,213 in the Annual Review 2024. While the VfM estimate is slightly higher than the Business Case projection, it is still 27% lower than the Annual Review figure. This suggests that although delivery costs are somewhat higher than initially anticipated – possibly due to inflation, enhanced quality standards, or more comprehensive costing. The BHB programme has still achieved better effectiveness than reflected in the broader Annual Review costing. The VfM estimate likely benefits from a tighter attribution of results and a more direct mapping of costs to lives saved.
In the area of family planning, the cost per unsafe abortion averted is estimated at £17 in this VfM evaluation, compared to just £5 in the Business Case. While this is more than triple the initial projection, the lack of an Annual Review comparator limits direct interpretation. Given the complex and often under-recognised system costs in reducing unsafe abortion rates, especially in conservative or under-resourced contexts – this figure may still represent reasonable value, albeit less efficient than originally projected.
The cost per cervical cancer case averted tells a different story. Here, the VfM estimate of £189 is 51% lower than the £385 projected in the Business Case, and over 90% lower than the £2,221 reported in the Annual Review 2024. This strongly indicates that the cervical cancer screening interventions have been delivered in a highly efficient and cost-effective manner. The large gap between the VfM and Annual Review figures may reflect differing assumptions about attribution and data modelling for long-term cancer prevention impact.
Overall, this VfM assessment shows mixed results across the three indicators – exceeding expectations for cervical cancer screening, moderately exceeding Annual Review efficiency for BEmONC, and underperforming against the Business Case estimate in family planning-related impact. These variations reflect a combination of methodological differences, data improvements, and contextual realities in programme implementation. Nonetheless, the results collectively underscore that the BHB programme has delivered significant health outcomes at a generally reasonable and in some cases highly favourable cost, particularly when compared to broader costing benchmarks used in the Annual Review.
Judgement matrix – Cost-effectiveness: The BHB programme is highly cost-effective, with a cost per DALY averted of £99, which is 19 times lower than the WHO-recommended threshold based on Bangladesh’s GDP per capita (£2,057). Four major interventions - midwifery/BEmONC services, broader FP (including IPAS), contraceptive implants, and cervical cancer screening - collectively averted 5,063 deaths and 378,351 DALYs, generating an estimated £745.75 million in economic benefits. Specifically, the midwifery programme yielded £321.17 million in benefits, FP interventions delivered £279.67 million, implant provision added £89.34 million, and cervical cancer screening contributed £53.94 million.
In addition, the digital transformation enabled by ADLRS resulted in £1.62 million in time and cost savings by streamlining medicine shop licensing, further underscoring the economic efficiency of digital health investments. While some long-term benefits of TA-driven system reforms are not monetised, their role in improving service readiness, regulatory frameworks, and digital infrastructure is expected to produce lasting impact.
Overall, the BHB programme performed strongly on cost-effectiveness (evidence consistently demonstrates high VfM across all indicators, with quantifiable results and minimal gaps), delivering substantial health and economic returns for resources invested. Further details are provided in Table VfM 12 below.
Criteria	Evidence from Analysis	Judgment
Health outcomes achieved per cost unit – BEmONC / midwifery	BEmONC support averted 2,277 deaths and 162,407 DALYs, generating £321.17 million in economic benefits. Cost per DALY averted was £32.7 – 59x lower than GDP per capita.	Strong – Clear evidence of significant health outcomes relative to investment.
Cost-effectiveness of broader FP interventions (incl. IPAS)	Implementation of FP interventions under BHB averted 2,058 deaths, 142,514 DALYs, and prevented 206,706 unsafe abortions, generating £279.67 million in economic benefits. Cost per DALY averted: £25. ROI: £78 per £1 invested.	Strong – Demonstrated high returns from a relatively low-cost intervention.
Cost-effectiveness of contraceptive implants	Procurement of 200,000 implants averted 650 deaths, 45,854 DALYs, and yielded £89.34 million in economic benefits. Cost per DALY averted: £30. ROI: £65 per £1 invested.	Strong – High-impact, long-acting intervention at low unit cost.
Cervical cancer screening impact	Screened 1.39 million women, averted 78 deaths, 27,576 DALYs, and generated £53.94 million in economic value. Cost per DALY averted: £65 – 30x lower than GDP per capita.	Strong – Highly cost-effective preventive health intervention.
Cost-effectiveness of digital health transformation (ADLRS)	The ADLRS system saved £1.62 million by reducing licensing delays and costs. Broader digital benefits not monetised but likely substantial.	Moderate to strong – Significant cost savings, though less direct health impact.
Overall programme cost-effectiveness	Across all interventions: 5,063 deaths averted, 378,351 DALYs, £745.75 million in benefits. Cost per DALY averted: £99, which is 19x lower than GDP per capita.	Strong – BHB demonstrates high cost-effectiveness based on WHO criteria.

Table VfM 12: Effectiveness judgement matrix
Conclusion and recommendations
The BHB programme demonstrates strong VfM across the key pillars of economy, efficiency, effectiveness, and cost-effectiveness. The programme effectively utilised financial resources to achieve substantial health improvements, strengthen health systems, and introduce digital solutions, ensuring long-term sustainability. The evidence indicates that BHB delivered measurable health outcomes at a relatively low cost and contributed to policy and regulatory enhancements, which will have a lasting impact beyond the programme’s duration.
From an economic perspective, the programme achieved significant cost savings through bulk procurement of medical supplies via UN mechanisms, leveraging global pricing advantages. The shift from NGO-led to government-led training models further reduced costs, making the training component more sustainable. MSH alone secured £1.51 million in savings through competitive procurement.
In terms of efficiency, the programme effectively converted inputs into outputs, with key interventions such as training, TA delivery, and digital licensing far exceeding expectations. Outputs like 1.1 (173%), 1.2 (126%), and 1.3 (107%) surpassed targets, and ADLRS automation resulted in £1.62 million in time and financial savings. Training medicine dispensers improved medicine storage, counselling, and adherence to safe dispensing practices, directly reducing wastage and enhancing pharmacy-level care. While Output 1.6 (67%) lagged behind, the overall trend reflects efficient implementation and strong coordination.
The programme also demonstrated strong effectiveness, particularly in improving maternal and neonatal health. The share of midwife-led deliveries increased from 54.9% in 2019 to 91% in 2024, while skilled birth attendant-supported deliveries rose from 11,956 to 49,577. The programme also played a key role in reducing stock-outs of essential medicines, ensuring uninterrupted service delivery in health facilities. Furthermore, its support for policy development, such as enacting the Drug and Cosmetics Act 2023, highlights its role in shaping Bangladesh’s health governance landscape.
From a cost-effectiveness standpoint, the BHB programme is highly cost-effective and meets WHO criteria. The cost per DALY averted is estimated at £99, which is 19 times lower than Bangladesh’s GDP per capita – exceeding WHO benchmarks. Specific interventions like BEmONC, FP services, implants, and cervical cancer screening collectively averted over 5,000 deaths and 378,000 DALYs, generating £745.75 million in economic benefits. Returns on investment were high – up to £78 per £1 invested in FP interventions, with consistently low cost per DALY averted across the board.
Importantly, outcome-level cost indicators confirm delivery was more efficient than originally projected. The cost per BEmONC patient was £56 (vs. £83 in the Business Case), and the cost per FP service provided was £3.9 (vs. £6 projected). The cost per cervical cancer screening was £1.28, below both the Business Case and global benchmarks.
At the impact level, BHB’s cost per life saved through BEmONC was £2,329, slightly higher than the Business Case but 27% lower than the Annual Review 2024 figure. The cost per unsafe abortion averted was £17, reflecting more realistic implementation costs. Cervical cancer screening stood out with a cost per case averted of £189, significantly below both Business Case (£385) and Annual Review (£2,221) estimates.
Taken together, these results confirm that BHB delivered high-value services at a lower unit cost than expected and converted investments into substantial health outcomes and systemic improvements. The programme offers strong evidence of VfM and provides a replicable model for TA-driven health system strengthening in other contexts.
Recommendations to further enhance VfM in future programmes
The following recommendations should be considered to further enhance VfM in future programmes:
1. Develop a standardised VfM framework: Future programmes should establish a clear VfM framework from the outset, ensuring that all implementing partners follow a consistent methodology for measuring and reporting VfM. The framework should be accompanied by a VfM strategy clearly stating how VfM will be understood and evaluated for different project components.
2. Institutionalise VfM thinking in programme design and budgeting: VfM considerations (e.g., cost per output, marginal cost, delivery modality efficiency) should inform programme design, annual work planning, and budget formulation – not just be retrofitted into evaluations.
3. Adopt adaptive VfM tracking mechanisms: Since some VfM pillars evolve during implementation, programmes should review VfM indicators and data collection plans mid-course and revise them to reflect operational realities.
4. Mandate intervention-level cost reporting across partners: Future VfM evaluations should require output or intervention line cost reporting. This will allow deeper analysis of cost-effectiveness drivers and support more granular VfM tracking.
5. Integrate VfM metrics into routine programme monitoring tools: Cost-efficiency and cost-effectiveness indicators should be embedded into quarterly progress reviews and results dashboards, enabling real-time adaptive management rather than post-hoc analysis only.
6. Develop guidance on measuring VfM in TA-heavy programmes: Future programmes should include specific guidance or templates to understand VfM in technical assistance components, including ways to measure the indirect impact of TA on policy, systems, and institutional capacity.
7. Strengthen VfM capacity among programme staff and partners: Given limited VfM expertise within implementing agencies and donor teams, targeted training sessions or VfM induction modules should be considered early in the programme. This will improve consistency and quality of VfM planning, reporting, and analysis throughout implementation.
8. Promote periodic VfM reflection sessions among stakeholders: Structured VfM reflection meetings (e.g., during mid-year reviews) can help partners interpret VfM findings collectively, identify course corrections, and maintain VfM as a management tool rather than an evaluative afterthought.
9. Establish minimum VfM documentation standards for partner reports: All implementing partners should be guided to document VfM in a more structured way, e.g., including quantified examples of cost savings, unit cost benchmarks, or comparative efficiency across delivery modes (NGO vs. government-led, virtual vs. physical).
10. Ensure coherence in VfM reporting: Implementing partners should agree on a unified approach to VfM reporting, ensuring that financial efficiency, cost-effectiveness, and impact measures are consistently documented.
11. Financial reporting: Future VfM evaluations should mandate cost reporting at intervention level across all partners to allow deeper analysis of efficiency and cost-effectiveness drivers.
12. Use VfM findings to inform resource allocation and budgeting decisions: Programme management teams should use VfM findings (e.g., under/over-performing outputs, unit costs, cost-effectiveness ratios) as inputs in future budgeting, reallocation, and prioritisation decisions, rather than treating VfM analysis as a compliance exercise.
13. Encourage use of proxy indicators when precise data is unavailable: Where direct cost or benefit data is not feasible, programmes should systematically use credible proxy indicators (e.g., staff time saved, client cost savings, DALYs averted) to maintain VfM rigour without overcomplicating reporting.
Overall, the BHB programme offers strong value for money, achieving substantial health outcomes at a relatively low cost while strengthening policy frameworks and health governance. The programme’s cost per DALY averted is well below international benchmarks, reinforcing its high cost-effectiveness. However, inconsistencies in VfM understanding, lack of a standardised VfM framework, and limited financial data affected the ability to conduct a more comprehensive evaluation. Addressing these gaps in future programmes will ensure more robust and transparent VfM analysis, further strengthening accountability and impact measurement.

# Annex 13: Logframe 2018-2024
PROJECT NAME	DRAFT LOGICAL FRAMEWORK: BETTER HEALTH IN BANGLADESH, April 2018- March 2025					Dated:original 17.Dec 2017 Updated 22.July.2019 Minor adjustment Apr 2020 Updated Nov 2020 Further updated Nov 2021 Final update in Oct 2022 Latest update in Oct 2023
IMPACT	Impact Indicator 1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
All citizens of Bangladesh enjoy good health and well-being;	Maternal mortality ratio (MMR) per 100,000 live births (HPNSDP RFW GI3)	Planned	196	176	174	174	160	160	160	160	160
		Achieved		176	165	163	163	163	156 (SVRS2022)	136 (SVRS- 2023)
		Source:	BMMHCS 2016	Bangladesh Maternal Mortality & Health surveys (BMMS); Maternal Mortality Estimation Inter-agency Group (MMIEG) of WHO, UNICEF, UNFPA and The World Bank;
	Impact Indicator 2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Total Fertility rate (TFR; per woman)	Planned	2.3	2.3	2.3	2.3	2.1	2	2	2	2
		Achieved		2.3	2.04	2.04	2.04	2.04	2.3	2.17
		Source	BDHS2014	BDHS 2017	SVRS 2019	SVRS 2020	SVRS 2020	SVRS 2020	BDHS 2022	SVRS 2023
	Impact Indicator 3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Neonatal mortality rate (NMR; per 1000 live births) (RFW GI2)	Planned	28	25	25	24	24	24	20	20	20
		Achieved		30	30	26	26	26	20	20
		Source	BDHS 2014	BDHS 2017	BDHS 2017	MICS 2019	MICS 2019	BDHS 2021	BDHS 2022	BDHS 2022
	Impact Indicator 4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Prevalence of stunting among children under 5 years of age; (RFW GI5)	Planned	36.10%	35%		32%			28%	24%	24%
		Achieved		31%		31%	28%		24%	24%
		Source	BDHS2014	BDHS 2017			MICS 2019	BDHS 2022	BDHS 2022	BDHS 2022
	Impact Indicator 5		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Universal Health Coverage Index Bangladesh	Planned			45	50	55	57	55	56	56
		Achieved			48	52	52	52	49
		Source		WHO Universal Health Coverage Report: https://www.who.int/data/gho/indicator-metadata-registry/imr-details/4834
OUTCOME-1	Outcome Indicator 1.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
Citizens of Bangladesh, especially women, children and the poor, increasingly utilise quality family planning, health and nutrition services.	Percentage of births attended by skilled providers. (RFW3.2.4); and Ratio of births in facilities by poor to rich women (RFW 3.2.5)	Planned	42.1% 1 poor/ 4.7 rich women	48% 1 poor per 4 rich women	50% 1 poor per 4 rich women	52%	53%	54% 1 poor/ 3 rich women	65% 1 poor/ 2.5 rich women	72% 1 poor/ 2 rich women	72% 1 poor/ 2 rich women	GoB will remain committed to achieving SDG-3 and relevant targets through increasing coverage of priority services and reaching the poor and enhancing its operational efficiency. Trained providers will be available in the health facilitties. Supply of medicines and FP logistics will remain uninterrupted. Citizens will be aware, value public health services and utilise them increasingly. Accredited shops will follow improved dispensing practices. Widespread or pervasive natural disasters unusually stretching the health systems, will not occur.
		Achieved		53.1% 1 poor/ 3 rich women	53% 1:3	53% 1:3	53% 1:4	50% 1:3	70% 1:2	70% 1:2
		Source:	BDHS2014	BDHS 2017	BDHS 2017	BDHS 2017	BDHS 2017	MICS 2019	BDHS 2022	BDHS 2022
	Outcome Indicator 1.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Contraceptive prevalence rate (CPR) for modern methods (all women); (RFW 3.2.1)	Planned	42.7%	43.0%	50.0%	54.0%	55.0%	56.0%	56.0%	57.0%	57%
		Achieved		52.0%	52.0%	52.0%	52.0%	54.7%	54.7%	54.7%
		Source:	BDHS2014	BDHS 2017	BDHS 2017	BDHS 2017	BDHS 2017	BDHS 2022	BDHS 2022	BDHS 2022
	Outcome Indicator 1.3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Contraceptive prevalence rate (CPR) for modern methods in Sylhet and Chittagong divisions (lagging behind areas) (RFW 3.2.2)	Planned	Syl: 40.9%, Ctg: 47.2%,	Syl: 42%, Ctg: 48%,		Syl: 49%, Ctg: 50%,	Syl: 49%, Ctg: 50%,	Syl: 48%, Ctg: 48%,	Syl: 54%, Ctg: 54%,	Syl: 54%, Ctg: 54%,	Syl: 54%, Ctg: 54%,
		Achieved		Syl: 45%, Ctg: 45%,	Sylt:53.1% Chtg: 51.9%	Sylt:46.1% Chtg: 53.9%	Sylt:46.1% Chtg: 53.9%	51.3% (sylhet); 52.6% (Ctg)	Syl: 64.9%, Ctg: 60.9%,	61.3% (Sylhet) 59.4%(Ctg)
		Source:	BDHS2014	BDHS 2017	MICS2019	SVRS 2019		SVRS 2020	SVRS 2022	SVRS 2023
	Outcome Indicator 1.4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	% of newborn received essential newborn care (RFW 3.1.1) (at least 2 postnatal signal function care within 2 days of birth)	Planned	6.1%	7.0%			12.0%	12.0%	56.5%	60.0%	60%
		Achieved		91.2%	56.5%	56.5%	56.5%	56.5%	56.5%	56.5%
		Source:	BDHS 2014	BDHS 2017	MICS 2019	MICS 2019	MICS 2019	(MICS 2019)	(MICS 2019)	(MICS 2019)
	Outcome Indicator 1.5		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Percentage of TB cases remaining un-detected (RFW 3.2.8)	Planned	47%	45%	38%	33%	31%	31%	31%	30%	30%
		Achieved		39%	33%	33%	33.0%	33%	31%
		Source	BDHS2014	National TB Programme MIS, MOHFW					NTP 2023
	Outcome Indicator 1.6		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Number of women screened for cervical cancer (UNFPA TA)	Planned		50,000	100,000	130,000	150,000	220,000	350,000	0	1,000,000
		Achieved		67,474	126,031	142,359	155,143	348,825	368227 [264446 in 20 target districst and additional 103781 screenings (15% of all screening done in other districts n=691878) due to overall national technical support].	251,660 [200,835 in 18 target districst and 50,825 from other districts based on 10% contribution of the total number screened (508250). Note: Sunamganj, Noakhali and Dhaka have been supported by Sida in 2024.]	1,459,719
		Source:	BDHS2014	UNFPA BHB TA Reports					DHIS2	DHIS2		Assumptions
OUTCOME-2	Outcome Indicator 2.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assigned government officials will continue to use the digital app.
Health, family planning, and nutrition services are delivered increasingly by effective and efficient health systems.	Percentage of district health facilities (#40) using digital systems to manage assets. (FCDO TA; DLI-5)	Planned	2%	5%	15%	25%	100%	100%	100%	100%	100%
		Achieved		6%	20.3%	100%	100%	100%	100%
		Source:	MOHFW report	HPNSP Implementation reports, MOHFW					DHIS2
	Outcome Indicator 2.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
	Percentage of health facilities reporting no stock-out of essential medicines.	Planned		50%	63%	65%	67%	69%	100%	100%	100%
		Achieved		60%	67%	67%	67%	100%	100%
		Source:	MOHFW report	HPNSP Implementation reports, MOHFW					DHIS2			Assumptions
	Outcome Indicator 2.3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	*Oversight of the accredited medicine shops will continue. *DGDA visits and accreditation will inspire and stimulate the pharmacists to remain compliant to GPP.
	Percentage of accredited medicine shops with improved dispensing practises as per national guidelines; (FCDO TA)	Planned	0%	n/a	n/a	15%	20%	25%	80%	90%	90%
		Achieved				26.8		61.80%	90%
		Source: Project report					Independent study
	Outcome Indicator 2.4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
	Percentage of targeted government health facilities (40) practicing infection prevention and control (COVID related) - THIS ACTIVITY IS DISCONTINUED SINCE COVID-19 SITUATION IMPROVED.	Planned				20%	50%	60%	70%			The facility based IPC committees will remain functional beyond the project.
		Achieved				20%	60%	60% (UNFPA Project Reports)8 district hospitals and 16 UHCs are practicing IPC
		Source	source: Pproject reports (UNFPA)
	Outcome Indicator 2.5		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
	Percentage of COVAX targeted population as a proportion of the total population vaccinated against C-19 - THIS ACTIVITY IS DISCONTINUED SINCE COVID-19 SITUATION IMPROVED.	Planned					60%	65%	70%	70%		Target population will continue to register for COVID vaccination. Those registered will get both the doses of vaccine. Supply of vaccine will remain steady.
		Achieved
		Source	HMIS, MOHFW reports
INPUTS (£)	FCDO (£)		Govt (£)		Other DPs (£)	Total (£)
	88m (attribution 2%)		8bn		1bn	11.1bn
INPUTS (HR)	FCDO (FTE): 1.8m
OUTPUT 1	Output Indicator 1.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
Quality Family Planning, Health and Nutrition services are provided increasingly, especially in hard-to-reach areas.	Number of childbirths attended by skilled birth attendants [in 20 BHB districts]	Planned		12,144	12,672	12,693	14,116	25,000	45,000	0	121,624	Skilled human resources are available and deployed throughout the country. Supply of necessary logistics remains adequate. People's practices with regards to health, hygiene and population control continue to improve year by year
		Achieved		20,888	11,956	18,291	28,823	42,146	39,078	49,577	210,759
		Source		HMIS MOHFW
	Output Indicator 1.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Number of childbirths attended by skilled birth attendants in Sylhet, Barishal and Chittagong divisions (DLI)	Planned	106,673	117,340	129,074	129,074	136,819	143,660	150,843	158,385	965,196
		Achieved		119,963	129,726	157,153	180,119	297,428	307,796	303,302	1,218,371
		Source:		WB and MOHFW reports (DHIS2 2022 results)
	Output Indicator 1.3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (peak) (Dec 2024)
	Number of total FP Users (modern methods)	Planned	135276	135574	137578	137578	139641	141736	325000	0	325,000
		Achieved		135794	137578	275,905	201,549	320,001	347,519	334,115	347,519
		Source:	FPMIS, MOHFW	FPMIS, MOHFW and TA project data
	Output Indicator 1.4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (peak) (Dec 2024)
	Number of under five children received vitamin-A supplementation, annually	Planned	353610	357,146	375003	375003	380628	384435	425000	0	425,000
		Achieved		374,000	380005	387180	383,640	420,000	396,000	281,445	420,000
		Source:		HMIS- NNS reports MOHFW
	Output Indicator 1.5		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Incidence rate of tuberculosis (TB) per 100,000 population. THIS ACTIVITY IS DISCONTINUED SINCE THIS IS SUPPORTED BY GLOBAL FUNDS	Planned	225		222		218			215
		Achieved			221
		Source	Programme Implementation Report, HPNSP, MOHFW Global Tuberculosis Report, WHO, 2019
IMPACT WEIGHTING (%) 40%	Output Indicator 1.6		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
	Number of service providers and community leaders, trained to cope with climate and other shocks; (FCDO ICF)	Planned		0		6,000	10,000	13000	8,000	12000	49,000
		Achieved				5864	4223	0	8,564	14,066	32,717
		Source		Programme reports (UNFPA TA)					RISK RATING: High
INPUTS (£)	FCDO (£)		Govt (£)	5.3 bn
	35 million
INPUTS (HR)	FCDO (FTEs): 35%
OUTPUT 2	Output Indicator 2.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
Health systems strengthened to increase performance, quality and efficiency.	Number of sub-district health facilities (Upazila Health Complexes) with at least two licensed midwives ( TA, DLI-07)	Planned	0	80	350	380	400	420	420	420	420	New posts for Midwives will be created as per plan. Recruitment and deployment plan for midwives will be implemented as planned; Funds will be released on time and as planned.
		Achieved		349	326	342	404	407	407	407
		Source: Annual Programme Implementation Report (APIR), MoHFW
	Output Indicator 2.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Number of public health facilities meeting facility readiness criteria* for delivering post-partum FP services in Sylhet and Chittagong divisions (TA, DLI-9 ) and 20 BHB districts. (Cumulative)	Planned	0	65	132	295	390	537	515	515	537
		Achieved		65	133	165	488	515	515	515
		Source:	BHFS 2009	Bangladesh Health Facility Survey (BHFS) every 2yrs; UNFPA TA report
	Output Indicator 2.3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Eligible women will value screening for cervical cancer and will participate.
	Number of health facilities (MCH, DH, UHC) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer (Cumulative)	Planned		60	80	88	132	170	175	175	175
		Achieved		73	85	159	159	160	180	180
		Source:	BHFS 2009			UNFPA report 2021
	Output Indicator 2.4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Number of district hospital personnel trained on digital Asset Management System. THIS ACTIVITY IS DISCONTINUED AS NO DIRECT INTERVENTION IS PROVIDED FROM BHB.	Planned	1	16	36	108	164	188	190	190		MOHFW will continue prioritising modernisation of the health systems.
		Achieved		20	51	283
		Source	*APIR and DLI verification reports, MOHFW
IMPACT WEIGHTING (30%)	Output Indicator 2.5		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Eligible dispensers will give time for attending the training. COVID-19 pandemic will not hamper progress of implementation.
	Number of medicine dispensers trained on GPP	Planned	0		5,500		3,000	3,000	2,500	0	14,000
		Achieved			5,598	-	4,649	2,557	-		12,804
		Source	Project Report, MSH					RISK RATING: Moderate
INPUTS (£)	FCDO		Govt (£)		Other (£)	Total (£)		FCDO SHARE (%)
	20 million		2.6 bn
INPUTS (HR)	FCDO (FTEs): 45%
OUTPUT 3	Output Indicator 3.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
Stewardship and Governance of health sector improved	Number of targeted medicine shops accredited	Planned	0					5360	0	9000	9,000	Medicine shop owners and sellers will be interested to know about correct dispensing practices.
		Achieved					6735	0
		Source	*APIR and DLI verification reports, MOHFW
	Output Indicator 3.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	MOHFW will continue to priortise strengthening regulatory functions in health.
	Number of retail medicine shops, licensed/ license renewed, by DGDA using automated licensing and renewal system.	Planned				20	280	400	500	100	1,300
		Achieved				22	162	499	647		1,330
		Source: Project report
	Output Indicator 3.3		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
	Proportion of agreed decisions in Urban Health policy meetings implemented. THIS ACTIVITY IS DISCONTINUED AS NO DIRECT INTERVENTION IS PROVIDED FROM BHB.	Planned		n/a	n/a	60%	70%	80%
		Achieved				80%
		Source: MoHW meeting minutes and performance reports					RISK RATING
IMPACT WEIGHTING (30%)	Output Indicator 3.4		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)	Assumptions
	Number of policy influencing agendas on pharmacy sector and antimicrobial resistance successfully implemented with significant contributions from BHB programme.	Planned					1	1	2	BHB programme personnel will work closely with DGDA and other partners to implement policy influencing agendas.
		Achieved					1
		Agenda 1: Policy influencing to include Good Pharmacy Practice (GPP) in the Operation Plan of DGDA under 5th Health Sector Programme Agenda 2: Mainstreaming and operationalising automation of drug licensing and renewal system at DGDA					RISK RATING: Moderate
INPUTS (£)	FCDO (£)		Govt (£)		Other (£)	Total (£)		FCDO SHARE (%)				High
	10.5 million		0.9 bn
INPUTS (HR)	FCDO (FTEs): 20%
OUTPUT 4	Output Indicator 4.1		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
COVID-19 response strenthened in target districts	Number of health facilities (MCH, DH, UHC) with functional WASH facilities (hand washing stations with soap, water supply, functional latrines) - THIS ACTIVITY IS DISCONTINUED SINCE COVID-19 SITUATION IMPROVED.	Planned				2	6	10	10	10
		Achieved				1	6
		Source:	Source: Project report
IMPACT WEIGHTING (%)	Output Indicator 4.2		Baseline	Milestone 1 (Dec 2018)	Milestone 2 (Dec 2019)	Milestone 3 (Dec 2020)	Milestone 4 (Dec 2021)	Milestone 5 (Dec 2022)	Milestone 6 (Dec 2023)	Milestone 7 (Dec 2024)	Target (Dec 2024)
12%	Number of COVID-19 research/ studies contributing to policy/ programme decisions - THIS ACTIVITY IS DISCONTINUED SINCE COVID-19 SITUATION IMPROVED.	Planned				1	2	3	4	4
		Achieved				1	2
		Source: Project report
[note] Unpublished study. “Assessing Good Pharmacy Practices in private medicine shops in selected districts of Bangladesh” by Dr. Iqbal Anwar, Consultant, BHB-MSH)

# Annex 14: Reasons for revisions of logframe indicators as reported in 2024 logframe

Indicator Number	Indicator description
		Revisions (2019-2024)
Outcome Indicator 1.1	Percentage of births attended by skilled providers. (RFW3.2.4); and Ratio of births in facilities by poor to rich women (RFW 3.2.5)	Targets for 2023 and 2024 have been revised and increased from 56% to 65% (2023) and to 72% (2024), making the target ambitious.
Outcome Indicator 1.2	Contraceptive prevalence rate (CPR) for modern methods (all women); (RFW 3.2.1)	mCPR was wrongly reported for all methods CPR since 2019. Corrected replacing SVRS data with BDHS data.
Outcome Indicator 1.3	Contraceptive prevalence rate (CPR) for modern methods in Sylhet and Chittagong divisions (lagging behind areas) (RFW 3.2.2)	No change.
Outcome Indicator 1.4	% of newborn received essential newborn care (RFW 3.1.1) (at least 2 postnatal signal function care within 2 days of birth)	Results reported were not consistent, and used different sources in different years, i.e. BDHS and MICS. Targets have been revised to ensure consistency using the MICS 2019 data. BDHS data records only non-institutional newborn care, which does not provide the log-frame indicator data. UNICEF conducted MICS in 2024, but the data have not been published yet.
Outcome indicator 1.5	Percentage of TB cases remaining un-detected (RFW 3.2.8)	Targets added for 2023 and 2024. However, the National TB Programme MIS did not report for 2024.
Outcome Indicator 1.6	Number of women screened for cervical cancer (UNFPA TA)	Target increased from 270k to 350k based on the previous year's performance in 2023. No separate target for last year due to the reduction of fund and no specific support for this intervention.
Outcome Indicator 2.1	Percentage of district health facilities (#40) using digital systems to manage assets. (FCDO TA; Disbursement linked Indicator 5 (DLI-5))	The programme had exceeded the target of 100% by 2020, and there were no plans to increase the number of district. The milestones for 2021 and 2022 have been adjusted to 100%,and the achievement has been corrected to 100% for 2021.
Outcome Indicator 2.2	Percentage of health facilities reporting no stock-out of essential medicines	Target increased from 70% to 100% as all 20 BHB districts continued to report no stockout.
Outcome Indicator 2.3	Percentage of accredited medicine shops with improved dispensing practices as per national guidelines; (FCDO TA)	Target for 2023 increased from 30% to 80% in line with Business Case (BC). And 2024 target is set at 90%.
Outcome Indicators 2.4 and 2.5	COVID-19-related indicators	Discontinued as the programme activities are not focusing on Covid-19.
Output Indicator 1.1	Number of childbirths attended by skilled birth attendants [in 20 BHB districts]	Target in 2023 increased from 28,000 to 45,000 based on last year's performance. No target for 2024 due to lack of budget.
Output Indicator 1.2	Number of childbirths attended by skilled birth attendants in Sylhet, Barishal and Chittagong divisions (DLI)	No change.
Output Indicator 1.3	Number of total FP Users (modern methods)	Target in 2023 increased from 144,570 to 325,000 based on previous year’s performance. No target for 2024 due to lack of budget allocation.
Output Indicator 1.4	Number of under five children received vitamin-A supplementation, annually	Target increased from 388,279 to 425,000 based on previous year's performance. No target for 2024 due to lack of budget allocation.
Output Indicator 1.5	Incidence rate of tuberculosis (TB) per 100,000 population	Discontinued as this is being carried out through the Global Fund.
Output Indicator 1.6	Number of service providers and community leaders, trained to cope with climate and other shocks; (FCDO ICF)	Targets for 2023 and 2024 have been revised from 15000 to 8000 and 12,000, respectively, in discussion with CCHPU.
Output Indicator 2.1	Number of sub-district health facilities (Upazila Health Complexes) with at least two licensed midwives ( TA, DLI-07)	No Change.
Output Indicator 2.2	Number of public health facilities meeting facility readiness criteria* for delivering post-partum FP services in Sylhet and Chittagong divisions (TA, DLI-9 ) and 20 BHB districts (Cumulative)	Target reduced from 682 to 515 as no additional facilities would be covered because of the funding reduction.
Output Indicator 2.3	Number of health facilities (MCH, DH, UHC) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer (Cumulative)	No change.
Output Indicator 2.4	Number of district hospital personnel trained on digital Asset Management System	Discontinued after 2020 as no specific digital asset management activity has been carried out under the BHB programme.
Output Indicator 2.5	Number of medicine dispensers trained on GPP	Replaced previous indicator 'Number of medicine dispensers trained on GPP and COVID-19 related issues' by dropping C-19. Additional targets added for 2023 increasing total programme target from 11,500 to 14,000.
Output Indicator 3.1	Number of targeted medicine shops accredited	Included in 2022 and yearly milestones as cumulative figure. Yearly targets revised based on the previous year’s achievements. No target in 2023 for preparatory work for next round of accreditation. Targets revised in 2024 from 12,000 to 9,000 in Business case addendum.
Output Indicator 3.2	Number of retail medicine shops, licensed/ license renewed, by DGDA using automated licensing and renewal system	Target in 2023 reduced from 700 to 500 to be more realistic and to factor in the budget reduction. Target is 100 for 2024 because of budget reduction.
Output Indicator 3.3	Proportion of agreed decisions in Urban Health policy meetings implemented	Discontinued after 2020 as there is no direct intervention from BHB.
Output Indicator 3.4	A number of policy-influencing agendas on the pharmacy sector and antimicrobial resistance were successfully implemented with significant contributions from the BHB programme.	New indicator on policy added in 2023.
Output Indicators 4.1 and 4.2	COVID-19 related indicators	Discontinued after 2021 as COVID-19 situation improved.

# Annex 15: Ranking strength of evidence

1. Strong: Evidence drawn from several high-quality data sources.
2. Moderate to strong: Evidence drawn from few, high-quality data sources OR triangulated from several lower-quality data sources.
3. Moderate: Evidence drawn from few lower-quality data sources.
4. Low: Evidence drawn from single source OR incomplete or unreliable data.
Although there were four possible strength categories, only the top two were applicable.
Evaluation Question	Strength of evidence	Ranking of strength of evidence
RELEVANCE / 1.1 To what extent has the technical assistance responded to the priorities and policies of the HPNSP (2017-2024)?	This EQ was responded to by taking evidence from the country's highest level of policy documents. Evidence was also drawn from the endline evaluation of 4th HPNSP, which was approved by the MOHFW and agreed upon by all the Development Partners supporting 4th HPNSP.	Strong: Evidence drawn from several high-quality data sources
1.2 What are the recommendations for improvement to help inform the next FCDO’s programme in health (if any)?	Recommendations were based on discussions with high-level stakeholders, including senior-level officials of MOHFW, the Directorates, and the partners. / Additionally, effectiveness data demonstrated strengths and gaps in the outputs.	Strong: Evidence drawn from several high-quality data sources
EFFECTIVENESS / 2.1 To what extent did the technical assistance achieve the intended outcomes (as set out in the logframe and theory of change)?	Evidence for this EQ included the approved Annual Reviews of BHB and the documents prepared by the partners, which can all be categorised as high-quality sources. Some of the evidence was drawn from the DHIS2, DGFP MIS, and data from health facilities, which might have some quality issues.	Moderate to strong: Evidence drawn from few high-quality data sources OR triangulated from several lower-quality data sources
2.2 What were the key factors contributing to the successful achievements?	Evidence was generated from KIIs with the stakeholders directly associated with implementing the BHB project.	Strong: Evidence drawn from several high-quality data sources
2.3 Was Technical Assistance the most appropriate intervention, or would others have been more appropriate?	Evidence was generated from synthesising the document review and KIIs.	Strong: Evidence was drawn from several high-quality data sources.
SUSTAINABILITY / 3.1 What systems are needed to improve the effectiveness and efficiency of health systems that will continue beyond the life of the programme?	Evidence was generated from MOHFW’s own/approved documents and KIIs with the stakeholders directly associated with implementing the BHB project.	Strong: Evidence drawn from several high-quality data sources
3.2 What evidence is there that the benefits of the technical assistance will be sustained?	Evidence was generated from MOHFW’s own/approved documents and KIIs with the stakeholders directly associated with implementing the BHB project.	Strong: Evidence drawn from several high-quality data sources
EFFICIENCY / 4.1 How effective were the various technical assistance interventions compared to the cost of respective technical assistance?	Evidence generated from the approved logframe, annual reviews, available financial reports, programme data, annual programme reports, and economic modeling tool.	Moderate to strong: Evidence drawn from few high-quality data sources OR triangulated from several lower-quality data sources
4.2 Did the programme achieve good value for money (VfM)	Evidence generated from the approved logframe, annual reviews, available financial reports, programme data, annual programme reports, and economic modeling tool.	Moderate to strong: Evidence drawn from few high-quality data sources OR triangulated from several lower-quality data sources
EQUITY / 5.1 How did the programme address aspects of gender equality, equity, poverty, and inclusion?	Evidence generated from approved documents of the BHB project and from KIIs with the stakeholders directly associated with the implementation of the BHB project.	Strong: Evidence drawn from several high-quality data sources

# Annex 16: Risk description and mitigation

Key:
Risk/impact	Risk/Potential Impact
High potential risk/impact
Medium potential risk/impact
Lower potential risk/impact

Anticipated risks/ challenges	Potential impact	Situation during assignment	Mitigation strategies taken
Constrained timeline: due to Foreign Commonwealth & Development Office (FCDO) contractual requirement/budget constraint that all activities for the Better Health in Bangladesh (BHB) programme are completed and invoiced before March 31 2025.		The team worked against a tight timeline.	The team was selected based on their significant combined operational and technical experience in Bangladesh and with BHB stakeholders in particular. / The Evaluation Technical Lead was involved in the end evaluation of 4th Health, Population and Nutrition Sector Programme (HPNSP), which helped to orient the team and saved time on reviewing background documents. / The team met internally and with FCDO on a weekly basis, to review progress and work together to mitigate against potential delays.
Identifying and scheduling Key Informant Interviews (KIIs): The major source of information in the evaluation will be key informant interviews. / Many of the key stakeholders listed for the interview are government officials. Identifying the right respondents, reaching them, and securing interviews in a timely fashion can be challenging.		Identifying KIIs was not an issue. However, it was a challenge initially to schedule interviews with government officials. / The team missed one key informant from the planning wing who has been transferred to another ministry and was engaged other official activities. After two attempts, the team aborted the plan to interview the official.	The Technical Evaluation Lead, due to his vast experience and personal contacts, could reach to some of the senior members of Ministry of Health and Family Welfare (MOHFW) and arranged appointments. / The team worked according to the schedule of the key informants convenience, sometimes conducting interviews on weekends or after work hours. / Team replaced the key informant by another member suggested by FCDO and partners.
Unavailability of key informants: Many government officials during BHB period have been transferred to other departments or retired. Current officials in those positions may not have clear idea about the activities done under BHB programme. Most of the project staff of BHB programme managed by Management Sciences for Health (MSH) have been shifted to other projects or other organisations.		MSH programme has ended and staff have moved on, it was difficult to reach the key informants. / Accessing to data for VfM	The evaluation lead managed to connect with one of the seniormost members of MSH team and conducted the interview in the early stage of evaluation. With help of this key informant, the team managed to identify other MSH members. The team took advantage of the Portfolio Director from the US in the country toward the end of February and conducted a short interview. / The team managed interviews with the VfM experts from United Nationals Population Fund (UNFPA) and could gather required data from those KIIs
Quality of secondary quantitative data: Quantitative data relies on secondary sources, such as reviews, reports, and programme information systems, which may result in variability in quality and completeness.		The team did not have easy access to District Health Information System 2 (DHIS2) and programme data. The team eventually got data from the UNFPA. The programme data, mainly reported between 2019-2021 has quality issues.	To ensure data quality, utilised published and reported data that meet established quality standards / The team utilised the data, clarified confusions with UNFPA and reported where quality seemed to be compromised. / Triangulation of information helped to validate the qualitative data.
Access to Data and Information for Value for Monay (VfM) and Economic Analysis: Conducting the VfM and economic analysis, led by the health economist, requires access to multiple reports and detailed financial information, which may be challenging to obtain due to data availability, accessibility, or confidentiality constraints.		Access to data was initially a challenge, but was eventually shared to enable a sound assessment of VfM.	The assessment used a conservative approach to ensure only well-documented cost savings and health outcomes were included in VfM calculation. Where precise cost-effectiveness estimates were not feasible, proxy indicators and external benchmarks were used to contextualise findings. This provided a credible, evidence-based VfM narrative, while acknowledging areas where improved reporting and standardisation could strengthen future VfM in programme delivery and future VfM assessments
Political instability: Bangladesh has recently undergone significant political shifts, creating an environment of uncertainty. These changes may impact various aspects of the work, including access to key informants and the feasibility of conducting field visits. The evolving political situation could lead to disruptions in communication, travel restrictions, or heightened security concerns, potentially delaying project timelines or affecting the reliability of data collection.		Political unrest was not an issue during the evaluation period and the team was able to work in a rather politically calmer atmosphere. / However, the global situation arising from the collapse of USAID unsettled and unnerved many of the evaluation team members as most of them had been engaged in other USAID projects.	After absorbing the initial shock, diverting some time to manage demand from other USAID funded project, the team was able to focus and allocate dedicated time to the evaluation.
Equity: Unavailability of appropriate data to include gender and other equity aspects in the analysis.		KIIs and field observation gave opportunities to address equity, especially to examine BHB’s inclusion of marginalised populations. However, the team could not get quantitative data to apply equity lens (poverty or urban/rural)	The team applied qualitative analysis from findings of KIIs for gender and inclusion analysis.
Breadth of the work: Broad research questions may pose challenges in gathering sufficient and relevant evidence, increasing the risk that the findings may not fully align with the expectations and needs of FCDO.		All the questions have been addressed.	During the inception and implementation phases, the team worked closely with the FCDO team to understand priority needs and refine the evaluation focus and methodology accordingly.

# Annex 17: Matrix showing relevance with priorities of Better Health in Bangladesh (BHB) programme with 4th Health, Population and Nutrition Sector Programme (HPNSP)

This table shows the two main technical assistance (TA) partners (United Nationals Population Fund (UNFPA) and Management Sciences for Health (MSH)), as well as the World Health Organisation (WHO), who provided some TA funded by BHB
Strategic Objectives and Priorities of 4th HPNSP	Relevant activities in BHB
	UNFPA	WHO	MSH
Strategic Objective 1: To strengthen governance and stewardship of the public and private health sectors / Programme Strategies in which BHB Contributed: / Strengthen the regulatory functions and stewardship role of Ministry of Health and Family Welfare (MOHFW) including the agencies under it. / Strengthen oversight on medical education, drug administration, hospital management, clinic and laboratory services, etc. to ensure quality service delivery.		Assisted the Directorate General of Drug Administration (DGDA) in finalising antimicrobial stewardship (AMR) guidelines. / Supported the Directorate General of Medical Education (DGME) in developing an online teachers’ evaluation system and integrated teaching criteria for selected medical colleges	Created a national accreditation guideline for model pharmacies and medicine shops. / Supported DGDA in the accreditation of 10,345 medicine shops as model pharmacies and model medicine shops. / Supported the enactment of the Drug and Cosmetic Law in Bangladesh
Strategic Objective 2: To undertake institutional development for improved performance at all levels of the system / Programme Strategies in which BHB Contributed: / Continue to strengthen various support systems and institutions of the Health, Nutrition and Population (HNP) sector based on the current needs. / Adopting new technologies to strengthen surveillance, data quality and information systems. / Develop appropriate technologies, care services and infrastructure to accommodate the needs of older persons and other special needs groups. / Strengthen monitoring and evaluation (M&E) activities at all stages of supervision by MOHFW and the agencies under it, including private sector M&E activities.	Supported the deployment of 401 midwives and advocated for creating additional midwifery posts to address healthcare gaps. / Worked on safeguarding policies and guidelines for Directorate General of Nursing and Midwifery (DGNM) to ensure safety and equity in midwifery practices. / Established maternity waiting homes for ethnic minorities in Khagrachari district, providing antenatal care (ANC)/ postnatal care (PNC) services, food, and transportation support. / Deployed the Family Planning Clinical Supervision and Quality Improvement Team (FPCS-QIT) in all 64 districts, introducing a digital monitoring software.	Conducted workshops and awareness campaigns on good pharmacy practices (GPP) and rational prescribing of antibiotics. / Assisted in developing Bangladesh's digital health strategy and architecture blueprint.	Developed the Automated Drug Licensing and Renewal System (ADLRS) for DGDA, which streamlined licensing processes. / Procured need-based TA support on behalf of TA Committee for strengthening various support systems and institutions of the HNP sector / Developed and maintained an electronic asset management system (eAMS) for hospitals at the district and Upazila levels. / Designed and implemented a Pharmacy Management Software (PMS) to manage inventory, track expired medicines, and enhance transparency in medicine shops. / Provided dashboards for tracking family planning and post-abortion care services at various health facilities.
Strategic Objective 4: To strengthen the capacity of the MOHFW's core health systems (Financial Management, Procurement, Infrastructure development) / Programme Strategies in which BHB Contributed: / Expanding the supply chain management portal to capture the total government procurement plans. / Improving warehousing of medicines and vaccines, including automated mechanisms with proper storage conditions and environmental control.	Ensured the continuous supply of contraceptives in health facilities, achieving zero stock-outs. / Supplied lifesaving kits (postpartum haemorrhage and eclampsia kits) to target facilities and ensured the availability of essential Emergency Obstetric and Newborn Care (EmONC) drugs.	Assisted Directorate General of Health Services (DGHS) in implementing an electronic supply chain management system for essential medicines, covering 131 health facilities.
Strategic Objective 5: To establish a high-quality health workforce available to all through public and private health service providers. / Programme Strategies in which BHB Contributed: / Strengthen medical education, nursing, and midwifery education and services by deploying qualified doctors/nurses to public health and Family Planning (FP) service delivery points, medical colleges, and nursing colleges and institutions. / Strengthen the institutions/regulatory bodies that produce, recruit, and train quality medical technologists, health assistants, family welfare assistants/visitors, etc.	Conducted training on Life Saving Skills in Pregnancy and Childbirth (LSSPC) for healthcare providers. / Collaborated with the DGNM to strengthen midwifery education and certification. / Strengthened pre-service midwifery education by updating curricula and training on innovative teaching methodologies. / Supported DGME in training medical interns and postgraduate students on family planning skills as part of their education in medical colleges.	Trained DGME staff to use the MIS effectively and ensured the system upgrades for continued functionality. / Supported the BNMC in developing specialised curricula and training tools, such as logbooks and checklists for nursing interns. / Conducted workshops on health-related SDG indicators for government officials and stakeholders. / Developed best practice guidelines for nurses working in Upazila health complexes (UHCs) to improve service delivery standards.	Trained 14,000 medicine dispensers on GPP. / Developed and maintained the BHB e-Learning platform for healthcare professionals. / Provided training to DGME staff on using the MIS and ensured regular upgrades to maintain its functionality.
Strategic Objective 6: To improve health measurement and accountability mechanisms and build a robust evidence-base for decision making / Programme Strategies in which BHB Contributed: / Digitising the entire routine health information system of the HNP sector to build a robust evidence-base for decision making. / Strengthening the M&E capacity of the MOHFW planning Wing, Branch, the Planning Units of DGHS, DGFP, and DGME and others through capacity training, logistics, and TA. / Carrying out appropriate studies/research and strategic advocacy to prioritise information management and evidence-based decision making in the HNP sector, avoiding duplication.		Facilitated AMC data submission to WHO’s GLASS AMC platform. / Supported the DGME in: designing a comprehensive MIS, including a facility registry, human resource system, student portals, and inventory management tools. / Supported DGME in addressing health workforce gaps by conducting situational assessments and developing workload standards for health professionals. / Monitored readiness and quality of Basic Emergency Obstetric and Newborn Care (BEmONC) services in district hospitals and Upazila health facilities. / Facilitated the adoption of data-driven systems to monitor contraceptive use and maternal health services effectively.	Supported DGME’s efforts to improve oversight of medical education through the comprehensive MIS (Facility registry and human resource management; an international students’ application system; Student information portals and medical dormitory management systems.). / Ensured alignment of DGME’s MIS with national health goals, enhancing data-driven decision-making. / Procured need-based TA support on behalf of TA Committee for different research/studies and evidence generation
Strategic Objective 7: To improve equitable access to and utilisation of quality health, nutrition and family planning services / Programme Strategies in which BHB Contributed: / Exploring various innovative approaches for improving service delivery, particularly hard-to-reach areas. / Ensuring Skilled Birth Attendants (SBAs) at birth; maternal care, family planning, newborn care, adolescent care, etc. and accelerating initiatives in low-performing and hard-to-reach areas. / Accelerating initiatives in hard-to-reach areas and strengthening FP activities by delivering regional packages in low-performing divisions/pockets.	Provided TA support to ensure BEmONC and postpartum family planning services in UPCs across target districts. / Organised screening camps in underserved areas to detect and manage cervical cancer early. / Delivered sexual and reproductive health rights (SRHR) services to the indigenous Santal community in Gaibandha district, including ANC, PNC, referrals, and community education sessions. / Promoted postpartum family planning and implemented Robson’s classification to categorise deliveries in model districts. / Developed Standard Operating Procedures (SOPs) and an action plan for disability-inclusive FP and SRHR.
Strategic Objective 8: To promote healthy lifestyle choices and a healthy environment / Programme Strategies in which BHB Contributed: / Developing a comprehensive lifestyle and environment strategy in collaboration with relevant ministries, departments, private entities and other stakeholders. / Developing public health programmes related to preventing communicable diseases and emerging diseases like COVID-19.	Supported the development of the Health National Adaptation Plan (HNAP) to address climate change and health resilience. / Advocated for including climate change activities in the operational plans of the 5th HPNSP. / Conducted climate change training for health professionals in Bagerhat and Bhola. / Facilitated introduction of a course on climate change in health at Dhaka University	Conducted awareness campaigns and workshops on GPP and rational antibiotic use.	Organised AMR awareness campaigns, including educational materials and social media outreach. / Trained 14,000 medicine dispensers on COVID-19 protocols.

# Annex 18: Achievement against outcome and output indicators of logframe in 2024

Indicator Number	Indicator description	2024
		Target	Achievement
Outcome Indicator 1.1	Percentage of births attended by skilled providers. and Ratio of births in facilities by poor to rich women	72.0%	70.0%
Outcome Indicator 1.2	Contraceptive prevalence rate (CPR) for modern methods (all women);	57.0%	54.7%
Outcome Indicator 1.3	CPR for modern methods in Sylhet and Chittagong divisions (lagging behind areas)	Sylhet: 54%; Chattogram: 54%,	Sylhet: 61.3%; Chattogram: 59.4%
Outcome Indicator 1.4	% of newborn received essential newborn care (at least 2 postnatal signal function care within 2 days of birth)	60.0%	56.5%
Outcome indicator 1.5	Percentage of tuberculosis (TB) cases remaining un-detected	31% (2023)	31%
Outcome Indicator 1.6	Number of women screened for cervical cancer (United Nationals Population Fund (UNFPA) technical assistance (TA))	No target for 2024 / 350,000 (2023)	251,660
Outcome Indicator 2.1	Percentage of district health facilities (#40) using digital systems to manage assets. (Foreign Commonwealth and Development Office (FCDO) TA; Disbursement Linkd Indicator 5 (DLI-5))	100.0% (2023)	100.0%
Outcome Indicator 2.2	Percentage of health facilities reporting no stock-out of essential medicines.	100.0% (2023)	100.0%
Outcome Indicator 2.3	Percentage of accredited medicine shops with improved dispensing practices as per national guidelines; (FCDO TA)	80.0% (2023)	90.0%
Output Indicator 1.1	Number of childbirths attended by skilled birth attendants [in 20 Better Health inf Bangladesh (BHB) districts] / *10% of the reported numbers are included in the logframe as attribution of BHB.	No target for 2024 / 45,000 (2023) / 121,624 / (Cumulative in 2024)	49,577 / 210,759 / Cumulative in 2024)
Output Indicator 1.2	Number of childbirths attended by skilled birth attendants in Sylhet, Barishal and Chittagong divisions (DLI)	158,385 / 965,196 (Cumulative in 2024)	303,302 / 1,218,371 (Cumulative in 2024)
Output Indicator 1.3	Number of total family planning (FP) Users (modern methods)	No target for 2024 / 325,000 (2023)	334,115 (peak)
Output Indicator 1.4	Number of under five children received vitamin-A supplementation, annually	No target for 2024 / 425,000 (2023)	281,445 (Vitamin A this year. 10% discounted for NGO contribution. FCDO contribution is 2%=281,445)
Output Indicator 1.6	Number of service providers and community leaders, trained to cope with climate and other shocks; (FCDO International Climate Finance (ICF))	12,000 / 49,000 (Cumulative in 2024)	14,066 / 32,717 (Cumulative in 2024)
Output Indicator 2.1	Number of sub-district health facilities (Upazila Health Complexes (UHCs) with at least two licensed midwives (TA, DLI-07)	420	407
Output Indicator 2.2	Number of public health facilities meeting facility readiness criteria* for delivering post-partum FP services in Sylhet and Chittagong divisions (TA, DLI-9 ) and 20 BHB districts. (Cumulative)	515	515
Output Indicator 2.3	Number of health facilities (Medical Colleage Hospitals (MCH), District Hospitals (DH), UHC) strengthened (trained personnel, instrument and reagent available) for screening women for cervical cancer (Cumulative)	175	180
Outcome Indicator 2.4	Number of district hospital personnel trained on digital Asset Management System. THIS ACTIVITY DISCONTINUED AS NO DIRECT INTERVENTION IS PROVIDED FROM BHB.
Output Indicator 2.5	Number of medicine dispensers trained on Good Pharmaceutical Practices (GPP)	3000 (2022) / 14,000(Cumulative in 2024)	2,552 (2022) / 12,804 (Cumulative in 2024)
Output Indicator 3.1	Number of targeted medicine shops accredited	5360 (2022)	6735
Output Indicator 3.2	Number of retail medicine shops, licensed/ license renewed, by Directorate General of Drug Administration (DGDA) using automated licensing and renewal system.	500 (2023) / 1300 (Cumulative in 2024)	647 / 1330 (Cumulative in 2024)
Output Indicator 3.4	A number of policy-influencing agendas on the pharmacy sector and antimicrobial resistance were successfully implemented with significant contributions from the BHB programme.	1 (2023) / 2 (Cumulative in 2024)	1 (2023)