## Annual Review Template

Title: Capacity for Economic Research and Policy-making in Africa (CERPA)
Programme Value £ (full life): 22.3million		Review date: September 2025
Programme Code: 204153	AMP start date: March 2015	AMP end date: March 2026

Summary of Programme Performance
Year	2016 / Mar	2016 / Oct	2017	2018	2018	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A	A	A	A	B	A	A
Risk Rating	Minor	Minor	Minor	Minor	Minor	Minor	Minor	Minor	Mod-erate	Mod-erate	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/5350736.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005667.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Capacity for Economic Research and Policy-making in Africa (CERPA) programme aims to help establish a core of quality economic policy-makers and researchers across Africa, to improve economic policy-making across the continent. This is necessary to drive inclusive growth and poverty reduction. CERPA supports African economists to undertake PhD and MSc training in economics as well as supporting early years and more senior African researchers through competitive research grants to produce policy relevant findings on topical priorities for African economic development.

CERPA is in its second phase of support to the African Economic Research Consortium (AERC), covering 2020-25, having granted an £8m extension in 2020. Phase 1 of the CERPA programme (2015-20) worked with the AERC and the Partnership for Economic Policy (PEP) up to the value of £14.3m. Phase 2 is focused exclusively on supporting the AERC. The AERC links with existing universities across sub-Saharan Africa, providing opportunities to upgrade the quality of economics MSc and PhD programmes through activities such as additional summer schools and online training. It also runs a research programme to build the capacity of early career researchers and provides opportunities for African policy-makers to engage with the latest economic development research relevant to the continent. The FCDO has a representative on the Board to help steer the AERC through the plan.

The AERC’s 5-year strategic plan ended in March 2025. Following an independent review of its structure and activities in 2024, and with permission from the AERC and its Board, the FCDO decided to continue funding its representative on the Board (independent senior economist academic) for a year beyond the end of the 5-year strategic plan to support the transition to the new strategic plan. The CERPA programme was therefore extended by one year and a Programme Completion Review will be carried out after the programme ends in March 2026.

Summary supporting narrative for the overall score in this review

This review covers the period April 2024 to March 2025, the final year of AERC’s 5-year strategic plan. Delivery highlights include a higher than anticipated volume of papers published as a result of the research programme and excellent reach during events for policy-makers. However, the graduate training programme log frame output scores a B, with fewer participating universities, fewer students involved in the joint electives courses and less representation of students from fragile and post-conflict states than envisaged at the beginning of the 5-year strategic plan, though stopping new sponsorships during the year due to the upcoming AERC reforms played a part. Regarding sustainability, while the AERC has built up affiliations with more regional organisations than anticipated, it has faltered with regards to national think tanks, African governments and central banks. Overall, programme performance scored an A (met expectation).

The AERC is working to a strategic plan with targets and milestones set around five years ago. Multiple funders use a common reporting framework which is also used by the AERC Board to assess performance. Therefore, the milestones and targets are not adjusted from year to year to take account of realities at the time. Furthermore, the version of the log frame used by the FCDO uses only a selection of the indicators so the FCDO log frame is not as coherent as if it were developed for the programme as a whole. The global funding climate has changed in the last five years so the expectations at the start around attracting funding towards the current 5-year strategic plan have not come to fruition, leading to areas of underperformance.

Major lessons and recommendations for the year ahead

FCDO funding to the AERC for its strategic plan has now come to an end. Many of the areas of underperformance highlighted in this review will be addressed as a result of the reforms arising from the independent review carried out in 2024, as the AERC moves into its new strategic plan. A recommendation in previous annual reviews was to document examples of where the AERC’s work has led to policy change. This will become more important than ever given the recent changes to the aid donor funding landscape.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The diagram below sets out the theory of change for the AERC.

The 2020-25 programme worked through the African Economic Research Consortium (AERC) which is a leading African-led capacity-building and research organisation based in Nairobi. Since its inception in 1988, the AERC has specialised in building capacity in African economic training, research, and policy by working collaboratively with universities, students, policy-makers and researchers from across the African continent. The AERC graduates are sought after to take up prominent positions in both government and research settings. Many hold prominent policy positions (Ministers of Finance and Central Bank Governors, for example) and are actively contributing to economic decision-making across Africa. For example, by the end of the year under review, PhD alumni were employed in universities (196), central banks and national ministries/bodies (62) and think tanks / research institutes (14).
The AERC has three main approaches. The first is supporting MSc and PhD students from across the continent to upgrade the quality of their degrees through supplemental learning. The AERC also provides institutional support to participating universities’ economics and agricultural and applied economics departments, helping them upgrade the quality of degrees they offer. The second is to support research activities involving junior African researchers in partnership with more experienced researchers from the continent or from other continents. Lastly, the AERC has significant convening power to bring together high-level policy-makers from across the continent to discuss research findings on particular policy issues. The AERC has strong links into African policy-making processes through its alumni network and its policy-making links. The AERC works on the capacity to undertake research, the capacity to use research and the research/policy interface.
Annually, the AERC supports around 300 MSc and 20 PhD economics students, as well as supporting substantial research activities and policy events. Despite the AERC reaching out to potential new funders throughout the 5-year strategic plan, it has proved challenging to mobilise new funds. African governments and institutions have continued to provide financial support for the AERC, remaining at 5% of funding over the past year.

An independent review of the AERC was commissioned by the AERC Board, carried out by senior academics in the first half of 2024. The AERC reached its 36th year in 2024 and much has changed in the sub-Saharan African research landscape during that time. The review sought to investigate whether the AERC needed to restructure to address current and emerging challenges in the region. The AERC developed proposals in response to the review which were accepted by the Board. However, funding challenges among international donors, including the FCDO, has meant that the AERC is having to rethink its funding model. By the time of writing this annual review, a new strategic plan had not yet been finalised.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

At outcome level, performance has been mixed and overall is off-track. 1,549 alumni have been engaged in policy formulation and research within policy-making institutions against the target of 1,440. 200 articles have been published in internationally-refereed journals since the beginning of the 5-year strategic plan (some of which came out of research carried out during the previous strategic plan) against a target of 176. 85% of graduates in economics and agricultural economics are working as teaching faculties, researchers, policy analysts and policy-makers in universities, government institutions and policy research institutes, meeting the target. However, by the end of March 2025, only four policies had been informed by AERC research against a milestone of five. This is an important outcome to track, not least because it demonstrates impact on policy to potential funders. The four examples are:

- Research and facilitation of an inter-ministerial policy dialogue through the USAID-funded Promoting Results and Outcomes through Policy and Economic Levers (PROPEL) Health project which informed the development of legislative instruments for health financing reforms in Kenya and influenced the decision of the Government of Kenya to change the ‘Universal Healthcare Fund’ to the ‘Primary Healthcare Fund’.
- A policy paper on tax reform in relation to alcoholic products provided the blueprint for the Government of Kenya Finance Bill 2024. The Bill proposed that taxation be based on alcoholic content rather than volume.
- A policy paper on tax reform in relation to value added tax informed the Government of Kenya Finance Bill 2024 by proposing to increase the mandatory VAT registration threshold from KES 5 million to KES 8 million.
- The project on "COVID-19 Impact on Poverty and Mitigation Measures, Debt Sustainability, and Agri-food Policies for Better Nutrition Outcomes," informed a decision by the Government of Kenya to implement three new social assistance programmes to help cushion vulnerable Kenyans against the negative economic effects of COVID-19: i) The multi-agency COVID-19 cash transfer; ii) The National Council for Persons with Disabilities (NCPWD) cash transfer; and iii) The Kazi Mtaani National Hygiene Programme (an urban public works programme).
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This review covers the final year of the AERC’s 5-year strategic plan which ended in March 2025. A no-cost extension of one year was granted for the CERPA programme to enable the FCDO’s independent representative on the AERC Board to continue on the Board for a further year, until March 2026. This would enable her to use her expertise and institutional knowledge to support the AERC as it transitions to an organisational and governance structure that can deliver on the reforms recommended by the independent reviewers in 2024, which the FCDO endorses. A Programme Completion Review for the CERPA programme will be carried out in spring 2026.

CERPA is well aligned with the FCDO development principles. The FCDO/DFID has partnered with the AERC for a number of years because capacity development takes time. The AERC is a Kenyan organisation with staff from across the African continent and one of the outputs of the 5-year strategic plan was for the AERC to reduce its reliance on donor funders.

## C. DETAILED OUTPUT SCORING

Output Title	Improved synergy between collaborative and thematic research
Output number:		1	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of collaborative research projects done by the 5 AERC thematic research groups (Cumulative) / Number of thematic research papers generated from the broader themes of collaborative research projects (Cumulative)	6 / L[1] 18 / M 20 / H 22	Moderately exceeded expectation / 7 / 23 / (achievement last year was 19)
1.2. Improved incentive for thematic and collaborative research, to be measured by: / Number of early career researchers (ER) conducting thematic research (Cumulative) / Number of senior researchers (SR) participating in AERC research (Cumulative)	L 5,190 / M 5,270 / H 5,340 / L 650 / M 680 / H 720	Moderately did not meet expectation / 4,781 / (51 more than last year) / 693 / (2 more than last year)
1.3. Improved due diligence and quality assurance by AERC, to be measured by: / Percent of research proposals out of the total peer reviewed and presented that proceed to interim report	85%	Met expectation / 85%
[1] The log frame for this programme assigns targets for high, medium and low scenarios for programme performance. These are calibrated such that the medium scenario is in line with programme expectations for the reporting period, the high scenario moderately above expectations, and the low scenario moderately below expectations. This establishes clear thresholds for assessing programme performance, providing clarity for both FCDO and implementing partners on how performance will be assessed.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output considers the research aspect of the AERC’s capacity-building activities:
- The thematic research programme is for early career African researchers who are, or were recently, involved in the Collaborative PhD Programme (CPP). The researchers are given support with conceptualising, framing and designing their research, using a framework of learning-by-doing, peer review, mentoring and networking. An important element is the week-long biannual research workshops. The research is organised around five broad themes or research groupings: Poverty, labour markets and income distribution; Macroeconomic policy and growth; Finance and resource mobilisation; Production, trade and economic integration; and Agriculture, climate change and natural resource management. Cross-cutting issues include gender, governance and institutions analysis.
- The collaborative research model provides a mechanism for collaboration between established international researchers and the AERC’s network of senior African scholars. Young researchers under the thematic research programme are also encouraged to collaborate in the research. The four research themes, closely linked to Africa’s policy agendas, are: Sources and spread of growth opportunities and distribution of benefits; natural resource management, climate change and economic development nexus; regional integration and strategic trade relations; and financial sector development.
On balance an A score is awarded for this output. The collaborative research produced a good number of papers and involved more than the anticipated number of senior African researchers. The number of early career researchers participating in thematic research did not meet expectation, though there was a higher proposal success rate than in previous years, meeting expectation.

1.1 One additional collaborative research project was started during the year, taking the total to seven projects across the AERC thematic research groups. Four additional research papers were published under the “Agricultural Policy Analysis for Nutrition Outcomes” project.

Efforts have been made to ensure that the collaborative research project steering committees have at least 50% representation of women. Affirmative action to ensure that at least 30% of research group members are women who have active roles has resulted in a growth from 0% to 30% of women participating in collaborative research. These efforts have also led to an increase in the cumulative number of thematic research papers produced and co-authored by women (282 from a baseline of 200 in 2019/20).

1.2 In April 2024, authors of new proposals attended a 5-day proposal-writing workshop in an effort to improve the quality of thematic research at entry. Intensive support was given to female researchers from fragile and post-conflict contexts. The bi-annual research workshops held in June and December 2024 had 154 researchers presenting their proposals, interim reports, and final reports.

To strengthen technical capacity of researchers, two workshops were organised during the reporting period. In the Autumn of 2024, 45 researchers from 19 countries, of which 58% were women, participated and benefitted from the training on ‘Research Methods and Proposal Writing Skills’. Additionally, a technical workshop on ‘Advanced Econometrics Including Bayesian, AI and Machine Learning Techniques and Application’ was run for 41 researchers from 21 countries, 68% of whom were women.

The 60th plenary session was held virtually in June 2024 on the theme “Youth, Demographic Dividend, Migration, and Economic Opportunities in African Economies”. The 61st Biannual Plenary Session in December 2024 focused on the theme “The Financial Technology (FinTech) Revolution in Africa”. The plenary sought to inspire young African researchers by exposing them to emerging topical and policy-relevant issues.

1.3 Out of 27 new proposals presented across the two biannual research workshops, 23 were approved to proceed to interim report.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to the log frame during the past year, owing to the fact that it draws directly from the AERC’s common reporting framework which is used by the AERC Board to assess performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As the AERC’s strategic plan 2020-2025, which underlies FCDO’s core funding contribution, has finished, there are no recommendations.
Output Title	Improved quality and delivery of university-graduate level economics curriculum
Output number:		2		Output Score:		B
Impact weighting (%):		25		Weighting revised since last AR?		N
Indicator(s)			Milestone(s) for this review		Progress
2.1. Number of CMAP, CMAAE and CPP[2] universities with capacity to offer graduate level / teaching in economics and agricultural economics (cumulative)			35		Moderately did not meet expectation / 32
2.2 Number of Masters and PhD students registered for online JFE/SFSE[3] (annually)			L 270 / M 300 / H 350		Substantially did not meet expectation / 265 (CMAP 105; CMAAE 125; CPP 35)
2.3 Enhanced participation of under-represented countries, groups and institutions, including post-conflict and fragile states in economic policy research and training To be measured by: / Percent of AERC sponsored students from fragile and post-conflict countries graduating with PhD degrees. / Percent of AERC sponsored Masters and PhD graduates who are women			80% / MA (45%) PhD (30%) / (average over last 10 years)		Moderately did not meet expectation / 67% / Met expectation (see explanation in text below) / MA 36% PhD 26%
2.4 Economists with competencies to conduct economic policy research and graduate training in sub-Saharan Africa produced To be measured by: / Number of CMAP, CMAAE and CPP alumni produced since inception of the programmes / (cumulative) / (Note all numbers are for medium targets. Low is (-2%) on each category. High is (+2%) on each category)			CMAP 3897 / CMAAE 1345 / CPP 357		Moderately did not meet expectation / CMAP 3917 / CMAAE 1366 / CPP 319
[2] CMAP - Collaborative Masters Programme, CMAAE - Collaborative Masters Agricultural Economics, CPP - Collaborative PhD Programme
[3] JFE - Joint Facility for Electives – summer schools organised by the AERC for the CMAP students and CPP students. SFSE - Shared Facility for Specialisation and Electives – summer school organised by the AERC for the CMAAE students.

Briefly describe the output’s activities and provide supporting narrative for the score.

The aim of this log frame output is to measure the level of support the AERC gives to universities in terms of upgrading their economics training. Partner universities are assessed by the AERC and graded and this informs what courses they can provide and whether they can receive visiting students from other participating universities (see Annex A).

At the end of year 3 of the strategic plan this output scored a C and last year it scored a B. This year, on balance, the output scores a B (moderately did not meet expectation). Efforts to encourage female participation in the Masters and graduate programme are paying off, though this is hidden by the log frame indicator which is an average over the past 10 years. After the independent review reported in summer 2024, the AERC decided that, due to major changes required to the graduated training programme, it would not take on any new Masters and PhD candidates. This has given little opportunity for the programme to improve on diversity and catch up on other indicators.

2.1 No further universities have been added in the past year. The AERC reforms will result in a move away from supporting Masters courses as a core activity, due to there being far more universities offering economics courses in sub-Saharan Africa than previously, so there was little incentive to extend the network of universities over the past year. Furthermore, the winding down of the Masters programme with a reduction in scholarships meant that potential participating universities could not reach economies of scale in teaching core courses that would enable them to join the network.

2.2 The Joint Facility for Electives (JFE) for Masters and PhDs was held between July and November 2024. Students from nine universities attended the Masters JFE, 37% of them women. Students from ten universities attended the agricultural economics course, 44% of whom were women. Students from 11 universities attended the PhD JFE, 17% of which were women, representing a substantial drop from almost half of attendees last year. With dwindling support for scholarships, some universities have been unable to mount their programmes due to students needing to self-sponsor.

The number of female visiting lecturers teaching at the electives courses has increased since virtual learning was introduced during the Covid-19 pandemic. A total of 10 women were appointed to teach various elective courses in 2024 compared to only 4 in 2019.

2.3 This indicator considers scholarships since the beginning of the CMAP and PhD programmes (around 10 years). The Bridge programme sought to support female, francophone and lusophone candidates and those from fragile and post-conflict states to access the Masters and PhD programmes. This was stopped in 2018 due to budgetary constraints and funding for new scholarships declined, leading to lower enrolment of students from fragile and post-conflict states.

Regarding female participation, the AERC has taken affirmative action beyond the Bridge programme. The training programme introduced quotas for participating universities for the proportion of support to be allocated to qualified women. The proportion of scholarships awarded to female students enrolled in CMAP, CMAAE and CPP was 60%, 49% and 57%, respectively, over the current strategic plan period, compared to 59%, 44% and 37% over the period 2015-2019. However, over the last two years of the strategic plan there was less budget for scholarships as the AERC reviewed the effectiveness and relevance of the training programmes. The scholarship allocation reduced from US$1.1m in FY22/23 to US$124k by FY24/25.

There exist significant disparities between male and female students completing their PhDs. While 33% of AERC-sponsored PhD students are female, only 26% of those who have graduated are women. The completion rate for women is 55% compared to men at 77%. Reasons for withdrawal from the programme include poor academic performance in coursework, medical issues or death, and challenges with funding support after the 4-year sponsorship has ended, with PhD students taking an average of 5-6 years to complete their PhDs. Female students may experience greater challenges in striking a balance between taking care of their families and their studies.

2.4 Overall, 5,602 students have completed their studies under AERC Masters and PhD programmes compared to a target of 5,999. When broken down according to course, there are fewer PhD alumni than anticipated. The AERC attributes this to the challenges of PhD students balancing their studies with part-time jobs due to scholarships being provided for four years but PhDs often taking 5 or 6 years to complete, and supervision challenges in some universities meaning that PhD completion is delayed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to the log frame during the past year, owing to the fact that it draws directly from the AERC’s common reporting framework which is used by the AERC Board to assess performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As this annual review covers the year to the end of the 5-year strategic plan, there are no recommendations. An independent review, the recommendations of which the FCDO supports and which the AERC is responding to fully, will fundamentally change the AERC’s training offer.

Output Title	Improved institutional performance and sustainability
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of empirical policy research papers produced by policy analysts and researchers of institutions of government, national think tanks and research institutes technically equipped through research mentorship and specialised technical training	92	Substantially exceeded expectation / 165 (120 more than last year)
3.2 Improved collaboration with / economic policy decision-making / institutions To be measured by: / Affiliation of AERC with national, regional and international organisations (Confirms formal recognition of AERC's leadership position as a research and capacity building institution in SSA)	National Think Tanks (20) / Central Banks (19) / African Governments (4) / Regional Institutions (4)	Moderately did not meet expectation / 13 / 12 / 1 / 12
3.3 Diversified financial resource / base supporting AERC activities. To be measured by: / Funding concentration-reliance ratio, which measures funding share of 5 largest funders (gives awareness of the risk of reliance on few funders)	75%	Met expectation (see explanation in text below) / 83%
3.4 Improved organisation support system To be measured by: / Percent of technical staff (Directors and Managers) retained over the entire duration of the strategic plan / Programme efficiency ratio calculated as programme expenses divided by total expenses (Measures how much of an organisation's expenses are being spent on programmes versus overhead costs)	75% / 75%	Substantially did not meet expectation / 43% / Moderately exceeded expectation / 82%

Briefly describe the output’s activities and provide supporting narrative for the score.

This indicator looks at institutional issues related to the AERC including engagement with policy-makers, finance and management. On balance, this output scores an A.

3.1 The working papers and research papers published during the year by the collaborative research and thematic research projects can be found at Annex B. The high number of papers published in the past year reflects a fast-tracking process used to increase the number of publications before the end of the 5-year strategic plan.

3.2 Progress with affiliations has been made over the past year as the AERC pivots towards the reform agenda. The AERC has affiliated with one additional national think tank (Economic Association of Malawi) and four additional regional institutions (Alliance for Green Revolution in Africa, African Development Bank, International Food Policy Research Institute, United Nations Environment Programme). The AERC has also had promising engagement with institutions such as the African Import-Export Bank and Trade and Development Bank. More proactive engagement with central banks has also been a feature of the past year, and is beginning to bear fruit for the next strategic plan with some banks making contributions to core funding.

3.3 The top 5 funders were FCDO, Swedish International Development Cooperation Agency, Gates Foundation, World Bank and Danida. The funding reliance ratio has increased, due to some funders backloading their funding into the final year of the strategic plan due to funding pressures in previous years. This was outwith the AERC’s control.

3.4 The first indicator considers the proportion of staff retained throughout the 5-year strategic plan. During the past year the Chief Finance Officer left the AERC and a new one was appointed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to the log frame during the past year, owing to the fact that it draws directly from the AERC’s common reporting framework which is used by the AERC Board to assess performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

At a previous annual review, we considered it essential for the AERC to consider ways to diversify its funding base amidst the financial challenges facing potential funders which were likely to continue into the medium-term. Over the past year, donor funding challenges have become even more acute. The AERC has revised the plan due to the current donor funding landscape and has been working hard over the past year to consider how to resource its next strategic plan.

Output Title	Greater influence on economic policy
Output number:		4	Output Score:	A++
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Improved proactive policy engagement and / outreach (cumulative) / To be measured by: / Number of policy-makers participating in AERC events such as senior policy seminars	3,514	Substantially exceeded expectation / 4,235
4.2. Enhanced platforms for / cooperation and information sharing / To be measured by: Number of impactful / information sharing tools developed (cumulative)	8	Substantially exceeded expectation / 16 (7 more than last year)

Briefly describe the output’s activities and provide supporting narrative for the score.

The AERC has substantially exceeded expectation on both of its indicators around influence on economic policy. Its outreach to policy has been broad, across both policy-makers and practitioners and in a number of areas relating to economic development. The tools it has developed will put it in good stead for the upcoming reforms as the AERC aims to use its network more.

4.1 Despite not holding a senior policy seminar over the past year due to financial constraints, AERC continued to make use of opportunities to run or engage with smaller-scale policy events leading to a 684 increase in policy-makers reached since the previous year. Events included:
- a knowledge event at the African Development Bank annual general meeting allowing the AERC to influence high-level discussions on harnessing Africa’s demographic dividend and skilled labour for sustainable growth.
- an AERC-organised IMF Task Force roundtable under the theme “IMF 2030: Advancing Global Financial Architecture Reforms for Climate Prosperity,” as a side event of the G20 / Finance in Common Summits (FICS) conference in South Africa. The roundtable convened government and other relevant stakeholders (e.g. central bank officials) to explore pathways for IMF reforms aligned with aspirations for a climate-resilient future.
- a roundtable discussion during the Centre for Global Finance-Overseas Development Institute-AERC Conference in London, bringing together researchers, policy-makers and practitioners to discuss issues surrounding the China-Africa economic interactions through the lens of China’s infrastructure investment.
- various policy dialogue events in Burkina Faso, Ethiopia, Kenya, Madagascar, Nigeria and Senegal, to engage policy makers on the key policy issues that emerged from the country case studies during the implementation of the Human Capital Development Project.
- a “Policy Analysis for Sustainable and Healthy Foods in African Retail Markets” project workshop with 30 policy-makers, academics and farmers in Ethiopia
- a “Propelling Outcomes through Policy and Economic Levers” Health project policy dialogue on strengthening primary healthcare financing in: Botswana with 18 participants from the Ministry of Health, Ministry of Finance and National Health Promotion Agency; Zambia with 26 participants from the Ministry of Health, Ministry of Finance and National Planning as well as Ministry of Local Government and Rural Development
- a Digital Financial Services for the Poor regional policy forum in Tanzania with 23 attendees.
4.2 Tools include:
- a new Statistical Data Feature that provides detailed insights into the popularity of research outputs
- an application and network monitoring tool
- an alumni repository for sharing information is now available but only accessible by registered members
- whistle blower platform
- human resource recruitment platform.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to the log frame during the past year, owing to the fact that it draws directly from the AERC’s common reporting framework which is used by the AERC Board to assess performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Given that FCDO funding to the AERC has ended and the AERC is making great efforts to pivot in the direction of the independent reviewer’s recommendations, which the FCDO supports, there are no recommendations.
## D: VALUE FOR MONEY

Key cost drivers and performance
As reported in the yearly audit, the AERC’s expenditure by theme was on research projects at 49% of the total expenditure, communications at 12%, the CMAAE at 11%, the PhD programme at 10% and Masters programme at 3%. General Administration costs were recorded at 15%, which is around half of the previous year’s reported amount. The FCDO’s contribution to the AERC’s total revenues for this audit period was 43%[4]. Had the FCDO contribution been evenly distributed across the 5 years of the strategic plan, it would have amounted to around £1.6m per year, 18% of AERC’s income.
[4] Budget constraints at the FCDO meant that in earlier years the funding provided was less than anticipated and it was backloaded into the final year of the strategic plan.

VfM performance compared to the original VfM proposition in the business case

VFM indicators in the business case identified the need for the following processes to be followed when awarding research contracts:
1. Use a competition for award of research contract
2. Bids to be assessed against specific criteria
3. Robust M&E system incorporated in design of project including quarterly and annual monitoring
4. Bidders to articulate detailed plans for project delivery in bid document
5. Peer review mechanism to be built into procurement and project implementation.
These are still relevant and used and fit within the Economy, Efficiency, Effectiveness and Equity framework that FCDO is currently using.

Economy – The AERC uses a competitive process to procure research, considering costs as one of the assessment criteria. The AERC has established remuneration rates for researchers that take into account country indices. Projects are required to report according to the monitoring and evaluation system. Staff rates are benchmarked and set appropriately for an international organisation and country living costs using UN standards. The move to delivering training online has lowered the unit costs of graduate training. MSc and PhD training is conducted within the continent of Africa helping to keep costs down compared to international travel and associated costs.

Effectiveness and Efficiency –The business case noted the VFM gains in delivering high quality MSc and PhD training in Africa as opposed to funding in more developed countries. The institutional work that the AERC does with universities across the continent intends to help raise the general standard of university education over time, and the independent review found that this has happened. In addition to the cheaper cost of running training in Africa, there are benefits through networking across the continent, with the majority of graduates staying and working on the continent. The AERC graduates go on to take influential policy-making positions within the continent helping to further support the VfM rationale as the capacity for economic policy-making on the continent is gradually being enhanced.

In previous years, the FCDO allocated up to £300k per year above core funding to the AERC as a quality incentive. This was to encourage publication in order to drive the quality of the research undertaken. The AERC submitted four papers each year and one example of impact, which are assessed by the FCDO in relation to the Research Excellence Framework (http://www.ref.ac.uk/). The REF scoring is as follows: 1* Recognised nationally; 2* Recognised internationally; 3* Internationally excellent; 4* World-leading. REF 1* would mean a £50k payment; REF 2* £150k; REF 3* £250k and REF 4* £300k. There was no performance tranche funding available in the reporting period.

By March 2025, the total of AERC collaborative research framework and country studies published in international publications was 393 against a target of 371 and a baseline at the beginning of the 5-year strategic plan of 270, and 320 articles from thematic and graduate research against a target of 318 and a baseline of 243. In total, therefore, 200 articles have been published since the beginning of the 5-year strategic plan. Some of these articles originated in research projects from the previous strategic plan due to publishing time lags. A list of articles is provided at Annex B.

Equity – As part of its gender mainstreaming work, the AERC conducted a regional workshop on gender in economics in May 2024. Furthermore, gender mainstreaming workshops and retooling seminars on integrating gender and feminist lens into the country case studies were carried out in various projects. The AERC in partnership with the Nordic Consulting Group (NCG), appointed by the Swedish International Development Agency (SIDA), undertook a gender survey to better understand the barriers that female Masters and PhD students, female faculty members and female researchers face as women at various stages of their academic and research careers. Four separate online questionnaires were sent out in November 2024 to around 1,000 female Masters students, 75 female PhD students, 600 female thematic and collaborative researchers and 220 (80 male and 140 female) teaching faculty members. The findings from the survey have confirmed that the affirmative actions by the AERC ensuring space and funding for female Masters and PhD students, capacity-building efforts targeting women, and research opportunities, have enabled many women to succeed in their pursuit of an academic or other professional career. The survey findings led to a recommendation to combine the affirmative actions with a more explicit and deliberate gender-responsive approach that involves in-depth discussions with participating universities on how to actively counter gender discrimination and better integrate gender perspectives in curricula, courses, lectures and research activities.

Virtual meetings and training have increased the reach of both the policy outreach and graduate training programme. However, key challenges cited by those involved in the graduate training include: power outages and internet connectivity challenges affecting both students and lecturers; class attendance and level of commitment of students being lower compared to face-to-face teaching; lack of experience and proficiency of several lecturers in online delivery of courses and IT related technical skills and; scheduling of classes due to students being spread across different time zones.

Assessment of whether the programme continues to represent value for money

FCDO funding to the AERC for its 5-year strategic plan (2020-25) ended in March 2025. However, the CERPA programme has been extended for a year to enable the FCDO’s Board member (independent academic) to support the AERC as it transitions to its new strategic plan, given huge reforms to the structure and activities of the organisation recommended by the independent review in 2024. The AERC will need some time to transition to a new organisational and governance structure. It has not yet shared a funding proposal for its new strategic plan. The FCDO’s Board member has been on the AERC Board for a number of years, latterly on the Board’s Executive Committee, playing a key role in commissioning the independent review of the AERC and working with the Board to respond to the recommendations and support the AERC’s Executive Director to develop robust plans for the future. Using underspend to keep the FCDO’s Board member on the AERC Board will enable her to use her expertise, institutional knowledge and willingness to challenge to add value over the coming year.

E: RISK

Overview of risk management

At the last annual review the risk level was moderate due to funding challenges, changes in senior leadership and research quality. Updates on the key risks are given below according to the FCDO risk categories. FCDO funding to the AERC ceased when the strategic plan finished at the end of March 2025. Over the coming year, the FCDO Board member will continue to serve on the AERC Board, which the FCDO considers to be low-risk. The overall programme risk level in FY25/26 is therefore minor. This is within Research and Evidence Directorate’s risk appetite.

Strategy and Context (Receptive) – Over the past year the AERC made changes to some of its activities in light of the independent review, such as stopping new post-graduate training scholarships, ahead of much larger changes in its next strategic plan. This has had limited impact on progress against some log frame indicators but value for money should be considered given that the AERC will use reserves to honour existing scholarships into 2026.

Policy and Programme Delivery (Receptive) – On research quality, there was no monetary incentive from the FCDO in the final year of the strategic plan, which in previous years had rewarded publication of high-quality research, so the FCDO has not assessed quality over the past year. However, the AERC continued to take steps to improve research quality throughout its work, such as through introducing a research methods and computer applications course as a mandatory elective common course for all PhD students, running technical workshops on research methods and proposal writing for women and those from fragile and post-conflict countries and training on advanced econometrics including Bayesian, artificial intelligence and machine-learning techniques.

Public Service Delivery and Operations (Cautious) – On the risk of reduction in funding from other donors, the AERC has maintained its core funding base throughout the strategic plan. Latterly it has been thinking creatively about funding AERC activities in the next strategic plan, given the changing donor funding landscape.

People (Cautious) – The IT unit has developed policies and procedures which include data privacy and data classification policies. They have been training AERC staff on these topics in an effort to build up knowledge and understanding across the organisation.

Safeguarding (Cautious) – Safeguarding concerns are being managed and, to make reporting of safeguarding issues easier, AERC has developed a whistle blower platform, which is easy to find on the organisation’s website.

Financial and Fiduciary (Cautious) - To mitigate the risk of financial or other fraud, which would result in major reputational implications, the AERC has governance oversight by a Board Executive Committee (with external representatives including the FCDO Board representative), and regular financial and systems audits are carried out.

Reputational (Cautious) – The AERC continues to be a well-respected organisation across the African continent.

Climate and environmental risk is low. There have been fewer policy events over the past year and hybrid delivery of some events has meant less travel impact on the environment by attendees. The AERC’s research contributes to a better understanding of climate change. For example, a policy brief on Integrating Climate Change in Debt Sustainability Analyses for Low-Income Countries provides actionable insights to improve the IMF/World Bank Debt Sustainability Framework for Low-Income Countries to guide climate-related decision-making in LICs. Some of the recommendations were drawn from an AERC technical paper on the impact of climate-related investments on fiscal and debt sustainability across Africa.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

FCDO does not earmark funds with the AERC, meaning that its resources can be used to fund core activities and plug gaps. During the period the AERC worked with the FCDO to align activities to the expected budget allocation. The AERC presents finance activities fully at each Board meeting to ask the Board for guidance and approval.

During the period the AERC continued to provide the FCDO with regular financial updates in line with the agreement, and these are clear and well presented.

The AERC’s finances were audited by Deloitte and the report was produced in August 2025, with the audit confirming the “financial statements present fairly, in all material respects, the financial position”. The main concern noted in the report is the decline in reduced funding from donors because of global funding modalities and of grants coming to an end. The AERC is aware of the issues and plans to ensure robust engagement with its current donor pool and others to ensure opportunities for funding are identified.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The AERC submits quarterly reports to the FCDO showing progress against the log frame and financial expenditure by quarter against the budget. The AERC also publishes an annual report on its website. Both types of report were used as the basis for this annual review.

The FCDO has an independent representative on the AERC Board who influences and takes part in the Board discussions and oversight. The Board representative provides feedback to the FCDO on the Board meetings, which is used to support this review.

The FCDO has commissioned an evaluation of its economic development research portfolio. CERPA is one of the programmes under evaluation, particularly in view of its role in developing the capacity of economists in Africa. The evaluation will be completed in early 2027.

Evidence

In early 2024 the Board commissioned an independent review to consider implementation of the current 5-year strategic plan, and the objectives, programmes, structure, and capabilities of the AERC and its network. The review was carried out by two senior academics and reported in the summer of 2024. The Executive Director made proposals to the Board in the autumn on the future of the AERC in response to the review’s recommendations. The huge changes in the donor funding landscape, particularly since early 2025, has caused the AERC to rethink its activities and funding model, which has delayed the development of its new strategic plan. The AERC responded to some of the evidence arising from the independent review during the final year of the FY2020-25 strategic plan, such as stopping new scholarships.

Learning

The main learning process for the AERC over the past year has been as a result of the independent review, responding to the recommendations by developing plans for the future of the AERC along with learning how to navigate a changing aid donor landscape in order to ensure its plans are funded.

The AERC has identified several opportunities for the future, through the independent review and its own learning:
- using e-learning platforms, the collaborative training model can further be expanded to include partnerships with universities across the globe that offer frontier online courses within the repertoire of AERC training courses. These can be made available to students and faculty within the AERC network. This would enhance quality and improve the overall sustainability of the training programme through cost efficiency.
- webinar series conducted in partnership with international research institutions and universities have provided opportunities to offer methodological training on applied quantitative analysis and impact evaluation to a diverse range of participants globally
- countries across sub-Saharan Africa have significantly benefited from the pool of highly trained economists produced by the AERC. This provides an opportunity to the AERC to partner with African governments as it did with the Government of Kenya to develop country specific capacity building projects for economic policy analysis.
- a few projects under targeted funding support have helped in meeting part of the AERC’s administrative costs, thus providing some organisational and programme sustainability.
- re-engineering of economics training in Africa by twinning African universities with their peers in the global North, to bridge the expanding gap in the quality of doctoral training in economics. A twinned doctoral programme would provide the much-needed structured co-teaching and co-supervision, exposing African students and faculties to different scientific environments and methodologies, cultivating advanced research proficiency, and generating a broader network of academic peers and mentors.
- reforming the research programme by merging thematic and collaborative research streams to create a single work programme focusing on a few big research projects with broad topical themes aimed at answering priority research questions of policy relevance to Africa’s economic transformation.

Date of last narrative financial report	30 April 2025	Date of last audited annual statement	September 2025

Annex A – AERC participating universities and categorisation

Collaborative Masters Programme (CMAP)

Category A Universities do not offer the Collaborative Masters Programme but instead their students apply for MA studies in either the Category B or Category C universities. Even though category A universities may offer Masters programmes, they are not accredited as CMAP. Before the Covid pandemic, students were not able to join the Joint Facility for Electives (JFE) taught elective courses over a three-month period run by the AERC but when the courses became online they were opened up to category A students.

Category B Universities are deemed to have adequate capacity to offer core courses (Macroeconomics, Microeconomics and Quantitative Methods) and supervise theses. Students in Category B universities attend the JFE courses whether online or in person.
Category C Universities have capacity to offer a menu of core and elective courses as well as supervise theses. These universities therefore do not send students to the JFE because they independently teach the elective courses.
Category C / University of Addis Ababa, Ethiopia / University of Dar es Salaam, Tanzania / University of Ghana, Legon / University of Nairobi, Kenya	Category A / Kwame Nkurumah University of Science & Tech, Ghana / University of Sierra Leone / Egerton University, Kenya / Moi University, Kenya / Kenyatta University, Kenya / University of Eswatini / National University of Lesotho / University of Zambia / Eduardo Mondlane University, Mozambique / University of Liberia / University of Rwanda / University of Burundi / University of Gambia / University of Buea, Cameroon / University of Juba
Category B / University of Botswana / University of Malawi / University of Zimbabwe / University of Cape Coast, Ghana / University of Mauritius / Makerere University, Uganda / University of Namibia

Collaborative PhD Programme (CPP)

The Collaborative PhD Programme (CPP) combines coursework and thesis, which is punctuated by periodic thesis research workshops that bring all the students from the participating universities together, to enhance quality of theses produced by the students. For purposes of implementing the programme, the continent is subdivided into four regions, Southern Africa, Eastern Africa, Anglophone West Africa and Francophone Africa.

Host-degree awarding universities have been assigned the responsibility of teaching courses in core fields. Non-Host Degree Awarding Universities do not teach core courses. Instead, they admit and send their students to the regional host universities to take core courses during the first year of studies. Upon completing core courses at the regional host-degree awarding university all students take elective courses at the JFE.

Host-Degree Awarding Universities	Non-Host Degree Awarding Universities
University of Cape Town, South Africa / University of Dar es Salaam, Tanzania / University of Ibadan, Nigeria / University of Yaoundé II, Cameroon / University of Felix Houphouet-Boigny in Côte d’Ivoire	University of Witwatersrand, South Africa / University of Nairobi, Kenya / University of Benin, Nigeria / University of Abomey-Calavi, Benin / University Cheikh Anta Diop, Dakar / University of Pretoria, South Africa

Collaborative Masters in Agricultural and Applied Economics programme (CMAAE)

The CMAAE is a full-time course with the first two semesters comprising core courses taught at the accredited university (category B) offering the degree. Upon successful completion of the core courses, all students assemble at the Shared Facility for Specialization and Electives (SFSE) – virtual since the Covid 19 pandemic - to study elective courses and engage in thesis development in the third semester. The students then return to their host universities to complete their thesis research and graduate.
Category A (Non-Accredited)	Category B (Accredited)
Botswana University of Agriculture and Natural Resources / Eduardo Mondlane University, Mozambique / Jomo Kenyatta University of Agriculture and Technology, Kenya / Moi University, Kenya / University of Juba, South Sudan / University of Rwanda / University of Zambia	Egerton University, Kenya / Haramaya University, Ethiopia / Lilongwe University of Agriculture and Natural Resources (LUANAR), Malawi / Makerere University, Uganda / Sokoine University of Agriculture, Tanzania / University of Nairobi, Kenya / University of Pretoria, South Africa / University of Zimbabwe / Stellenbosch University, South Africa / University of Eswatini

Annex B - Research outputs

Working papers and research papers published in the year under review

Adekunle W and Oluwaseyi V (2024) Analysing the Determinants of Healthcare Insurance Uptake in Nigeria Working paper

Adem JM and Weldesilassie AB (2025) Rethinking Public Investment in Education in Africa: The Labor Market Response of Public Investment in Education in Ethiopia Working paper

Akem FA (2025) Implications of Financial Inclusion for Poverty in Cameroon: A Gendered Analysis Research paper 564

Ariu A (2025) Trade in Business Services’ Booms: The Case of Ghana Working paper

Atata SN, Tanankem B, Efobi V and Orkoh E (2024) Technology, Production and Food Consumption in Rural Nigeria Research paper 554

Bambe B and Apeti AE (2025) Inflation Targeting and Inflation Performance in Africa: Evidence Using a Synthetic Control Approach Research paper 560

Baroki RL and Mariam AB (2024) Maternal Education, Domestic violence and Childhood Malaria in the Democratic Republic of the Congo Research paper 557

Barro L, Tiendrebeogo A, Nana I and Ky L (2024) Maternal Education, Economic Empowerment, and Infant Mortality in Burkina Faso Working paper

Bazie P and Siri A (2024) Foreign Direct Investment Inflows and Human Capital Development, Apparent Links and the Effect of Transmission Mechanism: Evidence from Burkina Faso Working paper

Bessan E and Ayedoun C (2025) The role of ICTs in bilateral trade in sub-Saharan Africa: A gravity model analysis Research paper 563

Bizoza S and Irakoze G (2024) Exploring the Mobile Money in the Financial Inclusion Landscape in Burundi: Impacts in Gender and Location Perspectives Working paper

Botha R, Kamninga TM and Tuyisenge M (2024) Access to Digital Financial Services and Women Empowerment: Evidence from Rural Rwanda Working paper

Chakraborty KS and Villa KM (2024) Rainfall, Human Capital and Labour Market Outcomes: Evidence from Rural South Africa Working paper

Chari A (2025) Association between malaria prophylaxis stock-outs, and birth and maternal outcomes in Zimbabwe Research paper 568

Daniel L Mwighusa D and Diyamett B (2025) Digital Financial Services through Mobile Phones: Status and Challenges Faced by Rural Women in Tanzania Working paper

de Melo J and Solleder JM (2024) Approximating the First order Effects of AfCFTA Tariff Reductions on CO2 Emissions Working paper

Diagne S, Sylla FN and Henovi KC (2024) Effectiveness of the Universal Health Coverage Scheme in Senegal Working paper

Diallo MA, Diallo S and Sika MMC (2024) Return Migration and Labour Market Integration in Senegal Working paper

Dube B Nyika T and Pasara MT (2024) GVCPs in Zimbabwe’s Critical Sectors in the Face of Environmental Pollution and Climate Change: The Case of Agriculture and Mining Sectors Working paper

Eigbiremolen GO and Orji A (2024) Credit Constraints in Higher Education Attendance: Longitudinal Evidence from Ethiopia Working paper

Ewura-Adwoa Ewusie E and Annim SK (2025) Over-Indebtedness: measurement, determinants and effect on living standards Research paper 569

Fontana M (2025) Gender Responsive Macroeconomic Policy Options for Africa: Egypt and Kenya as Illustrations Working paper

Gafa D, Hodey L and Senadza B (2024) Examining Poverty Dynamics in Ghana: Evidence from Longitudinal and Repeated Cross-Sectional Data Working paper

Garang JA (2025) Impediments to the Evolution of Mobile Money and Financial Inclusion in South Sudan Working paper

Giovanis E and Ozdamar O (2024) Coping Strategies and Inequalities during the COVID-19 Pandemic Period: Evidence from Kenya Working paper

Hag MG (2024) Sudanese External Debt: Sustainability Analysis and Prospects for Solutions Research paper 556

Hussien AA, Gebrehiwot A and Abdi AI (2024) The Old and the New Economics of Financial Inclusion Leveraging Enhanced SDR Allocations to Finance Resilient Economic Recovery in Ethiopia Working paper

Kanina J, Mugure J, Nato J, Fisker P and Urzaingui DG (2025) Assessing the Impact of Personal Income Tax Reform in Kenya with Administrative Data: Behavioral Responses and Distributional Implications Working paper

Kinuthia BK (2024) Factors that Influence Global Value Chains: Evidence from the Manufacturing Sector in Kenya Working paper

Kiriga B, Nato J, Remcho N and Eldrup M (2025) Understanding the Public Revenue System in Kenya: An Overview of the Tax System Working paper

Kiringai J, Mutuku C, Muchiri B, Basescu S and Remcho N (2025) A Comprehensive Analysis of the Kenyan VAT System Working paper

Kodongo O (2024) The Fintech Ecosystem and Financial Inclusion: Evidence from Kenya Working paper

Koudjom E, Ngoko EH, Limazie MS and Mafang L (2024) Choice of the Type of School and Outcomes for Youth in the Labour Market in Togo Working paper

Kweka J and Sooi F (2024) Assessing the Drivers of Firm Participation in Global Value Chains: Empirical Evidence from Tanzania Working paper

Lemma TT and Mlilo M (2024) Digital Finance and Gender Gap in Enterprise Performance: Evidence from Kenya Working paper

Lioniel M, Dumas TA, Bertin MJ and Gnilane, DMN (2024) The Effectiveness of Work Linked Vocational Training Programmes in Senegal Working paper

Macharia KK (2024) Technical Efficiency in the Services Sector of selected SubSaharan African Countries Research paper 555

Malah-Kuete FY and Avom D (2024) Assessing the Role of Innovation in Cameroonian Firms’ Participation in Global Value Chains Working paper

Malot K, Mutuku C, Otindo C, Rand J, Shibia A and Sørensen BB (2025) Economic Complexity and Industrial Policy in Kenya Working paper

Mbara G (2024) Income Inequality and Growth: Calibration and Simulation for the Kenyan Economy Working paper

Montfaucon AF (2025) The Role of Trade Policies in Innovation: The Case of Malawi Research paper 561

Montfaucon AF and Majune SK (2025) Greening Trade through Global Value Chains in Africa Working paper

Munyengera GK (2024) Development of the Digital Financial Ecosystem in Rwanda: Drivers, Lessons and Way Forward Working paper

Munyegera GK (2024) Gender, Digital Financial Services and Financial Inclusion: Empirical Evidence
from Rwanda Working paper

Munyengera GK (2024) Disability, Digital Financial Services and Financial Inclusion: Evidence from Rwanda Working paper

Musabanganji E (2025) Welfare in Rural Rwanda Research paper 562

Musiliu AA (2024) Precolonial Centralization, Koranic Education and School Participation in Nigeria Working paper

Musyoka MP (2025) Effects of Russian-Ukraine War (RUW) on Gender and Food Security in Kenya Working paper

Mwighusa D and Diyamett B (2024) Digital Innovation Ecosystem Development for Financial Inclusion and Market Access: The Case of Tanzania Working paper

Ndayikeza MA, Ndoricimpa A and Nyamweru JC (2024) Mobile Money Usage: A Comparative Analysis of Burundi with other East African Countries Working paper

Ndoricimpa A, Nyamweru JC and Ndayikza MA (2024) Determinants of Mobile Money Adoption and Use in Burundi Working paper

Ndoye LM and Atchade TB (2024) The Impact of Women’s Participation in the Labour Market on the Academic Performance of Children in Senegal Working paper

Ndubuisi and Owusu S (2025) Firm Volatility in an Era of Global Value Chain: The Role of Product Quality Working paper

Ndzinisa P (2025) The impact of financial development on the effectiveness of monetary policy in South Africa Research paper 567

Ngepah N (2024) Asymmetric Response of Poverty to Growth and Inequality in South Africa: Implications for Current and Future Shocks Working paper

Ngigi S, Njoka J, Kamau P, Oleche M and Muriithi M (2024) The Impact of Free Primary Education Policy on Human Capital Development in Kenya: Wins and Losses Working paper

Niass D (2024) Does Natural Resources Endowment Affect Export Diversification in Africa? A Cross-Country Analysis Research paper 558

Njikam O (2024) Job Impacts of Global Value Chains: Firm-Level Evidence from Cameroon Working paper

Njikam O and Elomo TZ (2025) Multinational Enterprises and Quality of Jobs In Cameroon: Does The Mode Of Entry Matter? Research paper 566

Nyabaro V, Ogolla M, Ngugi R and Onsomu E (2024) Do Social Assistance Interventions Foster School Enrolment? A Case of School Feeding Programmes in Kenya Working paper

Oguso A, Ochieng’ J, Remcho N, Eldrup M and Chemnyongoi H (2025) Reforming Excise Taxation on Alcohol Products in Kenya Working paper

Oguso A, Ochieng’ J, Remcho N, Eldrup M and Chemnyongoi H (2025) Reforming Excise Taxation on Tobacco Products in Kenya Working paper

Ogwang A, Kahunde R and Makika MD (2024) Drivers of the Gender Gap in use of Digital Financial Services: Evidence from Uganda Working paper

Okello JA (2024) Can Mobile Money-Induced Cost Reduction Spur More Remittances to Uganda? Would the Resultant Large Remittances Affect Monetary Policy Effectiveness? Working paper

Okot N and Kasekende E (2024) Digital Finance Policy and its Impact on Financial Inclusion in Uganda Working paper

Okot N, Shinyekwa IMB, Bulime ENW and Luwedde J (2025) The Monetary Economics of e-Money and Policy Implications: Evidence from Uganda Working paper

Oleche M, Muriithi M, Kamau P, Njoka J and Ngigi S (2024) Impact of COVID-19 Pandemic on School Attendance in Kenya Working paper

Omanyo D, Chemnyongoi H and Ngugi R (2024) Leveraging Special Drawing Rights (SDRs) for Sustaining Economic Recovery in Kenya Working paper

Omotayo AO and Ogunniyi AI (2024) COVID-19 Pandemic, Poverty and Health Outcomes in South Africa: Do Social Protection Programmes Protect? Working paper

Omotoso KO, Adewole OG and Gbadegesin TF (2024) Differential Impact of the COVID-19 Pandemic on Education in Nigeria: Implications for Policy Review Working paper

Onsomu CB, Macharia J and Mwangi S (2024) Nexus between Non-Cognitive and Cognitive Skills and their Joint effect on Labour Market Outcomes: Evidence from Youths aged 15–25 years in Kenya Working paper

Onsomu LK and Ng’eno, H (2024) Importance of Investing in the First 1,000 Days of Life: Evidence and Policy Options Working paper

Onyango DW, Macharia KK, Ngui D and Maloi L (2025) Gendered Differences in Household Cooking Coping Strategies for the Russia-Ukraine War in Kenya Working paper

Osabuohien ES, Karakara AA and Edafe OD (2024) Global Value Chain Participation of Firms in West Africa: Empirical Insights from Ghana and Nigeria Working paper

Osoro J, Bundi D and Kiplangat J (2024) Behavioural Biases in Financial Access and Usage Divide: The Kenyan Case Working paper

Quartey, PA, Afful-Mensah R, and Afful-Mensah GA (2024) Reforms for Special Drawing Rights (SDRs) Financing in Ghana’s Economic Recovery Working paper

Rakotonirainy M, Ramiandrisoa O and Razakamanana M (2024) School Canteen Programme and School Performance in Madagascar Working paper

Razakamanana MV, Rakotonirainy M and Ramiandrisoa TO (2024) Healthcare Behaviour During a Health Crisis: The Case of Covid-19 in Madagascar Working paper

Sekumbo K and Manda NRC (2024) Who is More Likely to Pay the Tax on Mobile Money Withdrawals? Working paper

Shimeles A and Gallagher K (2024) Africa’s Chronic Liquidity Challenges and the Role of SDR Allocations Working paper

Shinyekwa IMB, Mpuuga D, Nattabi AK and Bulime EWN (2024) Leveraging Digital Services and Market Development for Financial Inclusion Working paper

Siri A and Combary O (2024) Human Capital Development and Household Income Growth in Burkina Faso: Using the Decomposition Method to Understand the Relationship Between the Two Working paper

Sitati M, Murebu R, Ngugi R and Onsomu E (2024) Impact of Teacher Qualification and Experience on Early Grade Achievement in Kenya Working paper

Sylla FN and Diagne A (2024) The Monetary Economics of E-Money in East Africa Reallocations of Special Drawing Rights and Financing of the Economic Recovery in Senegal Working paper

Taiwo S and Olofin S (2024) Foreign Direct Investments and Human Capital Development in Nigeria: A Firm-Level Analysis of Manufacturing and Information and Communication Technology Industries Working paper

Tamba CL and Murithi IK (2024) Promoting Gender Inclusion in Digital Financial Services: Evidence on Policies and Socio-Economic Factors in Kenya Working paper

Tesfaye W (2024) The Distributional Impacts of Public Expenditure in Ethiopia: A Gender-Lens Analysis Research paper 559

Wamalwa P, Tiriongo S and Mulindi H (2024) Bank Competition, Digital Finance, and Gender Differences in Financial Inclusion in East Africa Working paper

Yaya A (2025) Resilience to terms of trade shocks in Sub-Saharan Africa: the role of fiscal Policy and exchange rate regime Research paper 565

Yelwa M and Anyanwu SO (2024) Child Development and Family Human Capital Investment Decisions in Nigeria: A Study of Selected States in the Six Geo-Political Zones Working paper

Yeshineh AK and Woldeyes FB (2024) The Economy-Wide Impact of Harnessing Human Capital Development: A Dynamic Computable General Equilibrium Model Analysis Working paper

Zgovu E and Morrissey O (2024) Potential for Africa Continental Free Trade Area to Increase East African Community Exports to Africa Working paper

Journal articles from beginning of 5-year strategic plan up to March 2025

Abodi MA, Obare GA, Kariuki IM and Tejada Moral M (2021) Supply and demand responsiveness to maize price changes in Kenya: An application of error correction autoregressive distributed lag approach. Cogent Food & Agriculture, 7(1). https://doi.org/10.1080/23311932.2021.1957318
Ahmed MH (2022) Impact of irrigation on farm household diet quality: Evidence from Ethiopia. Irrigation and Drainage Volume 71(4):1089-1106 https://doi.org/10.1002/ird.2702
Ajefu JB and Abiona O (2020) The Mitigating Impact of Land Tenure Security on Drought-Induced Food Insecurity: Evidence from Rural Malawi. Food Policy, Available online 10 June 2020, 101911. https://www.sciencedirect.com/science/article/abs/pii/S0306919220301159
Ajefu JB and Falecia Massacky, F (2023) Mobile money, child labour and school enrolment, Telecommunication Policy, https://doi.org/10.1016/j.telpol.2023.102648

Ali E, Bataka H, Wonyra KO, Awade NE and Braly NN (2024) Global value chains participation and environmental pollution in developing countries: Does digitalization matter? Journal of International Development, pp. 451-478. https://doi.org/10.1002/jid.3823

Amidu M (2020) Bank Competition in Africa: Do Institutional Quality and Cross-border Banking Matter? Journal of African Business, 23(2), 326–360. https://doi.org/10.1080/15228916.2020.1838833

Amutabi C and Wambugu A (2020) Determinants of labor productivity among SMEs and large-sized private service firms in Kenya. Journal of African Business. https://doi.org/10.1080/15228916.2020.1838833
Asante A, Man N and Wiseman V (2020) Evaluating Equity in Health Financing Using Benefit Incidence Analysis: A Framework for Accounting for Quality of Care. Appl Health Econ Health Policy 18, 759–766 (2020). https://doi.org/10.1007/s40258-020-00597-2
Asante, A., Wasike, W.S.K.and Ataguba, JE (2020) Health Financing in Sub-Saharan Africa: From Analytical Frameworks to Empirical Evaluation. Appl Health Econ Health Policy 18, 743–746 (2020). https://doi.org/10.1007/s40258-020-00618-0
Assouto AB and Houngbeme DJL (2023) Access to credit and agricultural productivity: Evidence from maize producers in Benin, Cogent Economics & Finance, 11:1, 2196856, DOI: 10.1080/23322039.2023.2196856

Ataguba JE, Ichoku HE, Nwosu CO et al. (2020) An Alternative Approach to Decomposing the Redistributive Effect of Health Financing Between and Within Groups Using the Gini Index: The Case of Out-of-Pocket Payments in Nigeria. Appl Health Econ Health Policy 18, 747–757 (2020). https://doi.org/10.1007/s40258-019-00520-4
Atim C, Arthur E, Achala DM et al. (2020) An Assessment of Domestic Financing for Reproductive, Maternal, Neonatal and Child Health in Sub-Saharan Africa: Potential Gains and Fiscal Space. Appl Health Econ Health Policy 18, 789–799 (2020). https://doi.org/10.1007/s40258-019-00508-0
Atinkut AB, Freyer B and Bingen J (Sept 2022) Women in Agriculture: Pathways of Pesticide Exposure, Potential Health Risks and vulnerability in sub-Saharan Africa. Environmental Science Europe, 34, 89. https://doi.org/10.1186/s12302-022-00638-8
Atta-Aidoo J, Matthew EC, Saleh AO and Bizoza S (2023) A gendered Analysis of the Effect of Financial Inclusion on Household Welfare in Burundi. Review of Development Economics, 1–21. https://doi.org/10.1111/rode.13046

Awoa P, Oyono JC, Atangana BN, Atanga DO and Zeh IP (2022) Natural resource and entrepreneurship: Economic freedom matters Dec 2022, Resources Policy, Volume 79. https://www.sciencedirect.com/science/article/abs/pii/S0301420722005578
Ayadi MF and Lawanson AO (2020) The Changing Pattern of Healthcare Financing in Sub-Saharan Africa: Implications for Health Outcomes - AJHE 9(2): 32-50 http://doi.org/10.35202/AJHE.2020.923250
Babyenda P, Kabubo-Mariara J and Odhiambo, S (2024) Adaptation to climate variability and household welfare outcomes in Uganda, Climate Services, Volume 36 https://doi.org/10.1016/j.cliser.2024.100523

Balde MS (2020) Soins Prénatals et Accouchement Assisté en Guinée. European Scientific Journal, Available online Vol 16 No 16 (2020). https://doi.org/10.19044/esj.2020.v16n16p21

Banga K and Balchin N (2022) Linking Southern Africa to South Africa's exports: new opportunities for regional value chains. Linking Southern Africa to South Africa's exports: New opportunities for regional value chains - Banga - The World Economy - Wiley Online Library
Bayale N and Kouassi BK (2022) The Devil is in the Details: On the Robust Determinants of Development Aid in G5 Sahel Countries. Comparative Economic Studies https://doi.org/10.1057/s41294-021-00182-z

Bessan E and Ayédoun C (2022) Mis-invoicing in Benin's International Trade: An Analysis from Mirror Statistics. Journal of Economics, Finance and Management Studies 11(5): 3307-3333, Nov 2022. https://doi.org/10.47191/jefms/v5-i11-18
Bodjongo M (2023) « Mobile money et adoption du commerce électronique par les entreprises au Cameroun », European Review of Service Economics and Management, n° 15, 2023 – 1, p. 53-95

Bodjongo MJM (2020) Regulations of noise pollution emitted by revival churches and the well-being of neighboring populations in Cameroon. Environmental Economics, Volume 11, Issue 1, 2020. http://dx.doi.org/10.21511/ee.11(1).2020.08

Bodjongo MJM and Abenelang SM (2022) Analyse comparative de l’encadrement du commerce électronique : cas de six états Africains. Revue internationale de droit économique 2022/1 t.XXXVI | pages 75 à 101. https://www.cairn.info/revue-internationale-de-droit-economique-2022-1-page-75.htm
Byiers B and Woolfrey S (2022) Nigeria and the AfCFTA as a Two-level game, Nigeria and the AfCFTA as a two‐level game - Byiers - The World Economy - Wiley Online Library
Chama-Chiliba CM, Hangoma P, Chansa C and Mulenga MC (2021) Effects of Performance Based Financing on Facility Autonomy and Accountability: Evidence from Zambia, Health Policy https://doi.org/10.1016/j.hpopen.2021.100061

Chegere MJ and Kauky MS (2022) Agriculture commercialisation, household dietary diversity and nutrition in Tanzania, Food Policy, August 2022, https://doi.org/10.1016/j.foodpol.2022.102341 .
Chegere, MJ and Mrosso TL (2022) "Climate Variability, Temporal Migration, and Household Welfare among Agricultural Households in Tanzania" Sustainability 14, no. 22: 14701. https://doi.org/10.3390/su142214701
Cheruto PL (2024) Impact of Forced Relocation and Community Integration on Household Well-being of Urban Refugees in Kenya, International Journal of Advanced Multidisciplinary Research and Studies Volume 4, Issue 4 https://doi.org/10.62225/2583049X.2024.4.4.3157

Chuku C, Simpasa A and Ekpo A (2022) Catalyzing Regional Integration in Africa: The Role of Infrastructure. Catalysing regional integration in Africa: The role of infrastructure - Chuku - The World Economy - Wiley Online Library

Coulibayl D SS (2021) A study of the factors affecting mobile money penetration rates in the West African Economic and Monetary Union (WAEMU) compared with East Africa. Financial Innovation 7, 25 (2021). https://doi.org/10.1186/s40854-021-00238-0

Coulibaly D and Gnimassoun B (2023) Emigration and External Imbalances in Sub-Saharan Africa: Do Migrants’ Skills Matter? Journal of African Economies, Vol 33 Issue 3, June 2024 https://academic.oup.com/jae/article-abstract/33/3/322/7143638?redirectedFrom=fulltext

Coulibaly SS (2021) A study of the factors affecting mobile money penetration rates in the West African Economic and Monetary Union (WAEMU) compared with East Africa. Financ Innov 7, 25 (2021). https://doi.org/10.1186/s40854-021-00238-0
De Groote H and Omondi LB (2023) Varietal turn-over and their effect on yield and food security – Evidence from 20 years of household surveys in Kenya, Global Food Security Volume 36 https://doi.org/10.1016/j.gfs.2023.100676

Dedehouanou SEA and Kane A (2021) Spillover Effect of Official Development Assistance on Sectoral Economic Growth in West African Economic and Monetary Union Countries, International Journal of Economics and Financial Issues, Vol 11, No 3 https://econjournals.com/index.php/ijefi/article/view/11299/pdf
Dedewanou FA, Rolande CB and Tossou K (2021) Remittances and agricultural productivity in Burkina Faso, Agricultural and Applied Economics Association, https://doi.org/10.1002/aepp.13188

Degroote S, Ridde V and De Allegri M (2020) Health Insurance in Sub-Saharan Africa: A Scoping Review of the Methods Used to Evaluate its Impact. Appl Health Econ Health Policy 18, 825–840 (2020). https://doi.org/10.1007/s40258-019-00499-y
de Melo J and Olarreaga M (Editors) (2023) Special Issue: Supply Chain Trade in Africa: Retrospect and Prospect. The World Economy, Volume 46, Issue 11 pp3183-3418
https://onlinelibrary.wiley.com/toc/14679701/2023/46/11

Papers Published Under the Special Issue
- de Melo J and Olarreaga M, Introduction to symposium supply chain trade in Africa: Retrospect and prospect https://doi.org/10.1111/twec.13504
- Shepherd B, Regional integration and services in African value chains: Retrospect and prospect. https://doi.org/10.1111/twec.13502
- Hoekman B and Marco Sanfilippo M, Trade and value chain participation: Domestic firms FDI spillovers in Africa, https://doi.org/10.1111/twec.13505
- Mensah EB and Biesebroek JV, Integration of African countries in regional and global value chains: Static and dynamic patterns, https://doi.org/10.1111/twec.13503
- Ebeke CH, Surges in participation in global value chains: Drivers and macroeconomic impacts in sub-Saharan Africa, https://doi.org/10.1111/twec.13500
- de Melo J and Solleder J-M, The landscape of CO2 emissions across Africa: A comparative perspective, https://doi.org/10.1111/twec.13498
- Cariolle J and da Piedade C, Digital connectedness and exports upgrading: Is sub-Saharan Africa catching up? https://doi.org/10.1111/twec.13501
- Coulibaly R, Moreno H, Suwa-Eisenmann A and Traore N, African firms in global value chains: What can we learn from firm-level data in Cameroon and Côte d'Ivoire? https://doi.org/10.1111/twec.13506
- Montfaucon AF, Nigatu NS and Majune SK. An analysis of value chain trade in Africa, https://doi.org/10.1111/twec.13507
Ariu A and Ogliari L, Services' trade in Africa: Structure and growth, https://doi.org/10.1111/twec.13499

Diallo SM and Seck A (2023) Air Pollution in Urban Africa: Understanding Attitudes and Economic Valuation in the Case of Dakar, Senegal. Sustainability 15, 1494. https://doi.org/10.3390/su15021494

Dogo ARI (2024) Impact de l'intégration financière régionale sur le commerce intra régional des produits manufacturés dans la zone CEDEAO, African Development Review Volume 36, Issue 2
https://doi.org/10.1111/1467-8268.12746

Dotse SQ, Larbi I, Limantol AM, Asare-Nuamah P, Frimpong LK, Alhassan ARM, Sarpong S, Angmor E and Ayisi-Addo AK (2023) Rainfall Projections from Coupled Model Intercomparison Project Phase 6 in the Volta River Basin: Implications on Achieving Sustainable Development. Sustainability, 15, 1472. https://doi.org/10.3390/su15021472
Edeh HC (2022) Exploring dynamics in catastrophic health care expenditure in Nigeria. Health Economics Review 12, 22 https://doi.org/10.1186/s13561-022-00366-y
Edewor SE, Kollie GB and Olaoye IJ (2023) Conditions Driving Youth Employment in Key Sectors of the Nigerian Economy. Sustainability. 2023, 15, 6096. https://doi.org/ 10.3390/su15076096
Edo S and Osadolor, N (2025) Emergence of global value chains as key driver behind industrial development: evidence from participating African countries, Foresight 27(3) pp491–506

Eregha B (2020) Exchange Rate Regimes and Foreign Direct Investment Flow in West African Monetary Zone (WAMZ). International Economic Journal. Volume 34, 2020 - Issue 1
Eregha PB (2021) Asymmetric response of cpi inflation to exchange rates in oil-dependent developing economy: the case of Nigeria. Economic Change and Restructuring https://doi.org/10.1007/s10644-021-09339-3

Fiorini M, Hoekman B and Quinn D (2022) Services Trade Policy and Industry Performance in African Economies. Services trade policy and industry performance in African economies - Fiorini - The World Economy - Wiley Online Library
Fowowe B (2023) Financial Inclusion, Gender Gaps and Agricultural Productivity in Mali. Review of Development Economics, July 27, 2023 ,1–40. https://doi.org/10.1111/rode.13034

Francois, JN (2022) Habits, Rule of thumb Consumption and Useful Public Consumption in Sub-Sahara Africa: Theory and New Evidence. Journal of Africa Economies, 2022, 1-29. doi: 10.1093/jae/ejac024
Gathiaka JK (2022) Does inequality in landownership contribute to inequality in education attainment? Empirical evidence from Kenya. Tanzanian Economic Review https://doi.org/10.56279/ter.v12i2.119
Gathiaka JK and Muriithi MK (2020) Empirical Analysis of Livelihood Strategies and Food Insecurity in Turkana County, Kenya. Tanzania Economic Review Volume 10, No.1 (2020), p139-162. http://ter.udsm.ac.tz/

Gathiaka, JK (2023) Does inequality in landownership contribute to inequality in education attainment? Empirical evidence from Kenya Tanzanian Economic Review Vol 12:2 https://www.ajol.info/index.php/ter/article/view/277316 https://doi.org/10.56279/ter.v12i2.119 4

Gbangoula SAH and Akono ZC (2022) “Maternal Education and Child Health Production: Case of the Central African Republic”, Global Journal of Management and Business Research, 22(B3), pp. 1–13. https://journalofbusiness.org/index.php/GJMBR/article/view/102231
Henn SJ and Robinson JA (2022) Africa's Latent Assets. Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i9–i32, https://doi.org/10.1093/jae/ejac034
Honda A and Obse A (2020) Payment Arrangements for Private Healthcare Purchasing Under Publicly Funded Systems in Low- and Middle-Income Countries: Issues and Implications. Appl Health Econ Health Policy 18, 811–823 (2020). https://doi.org/10.1007/s40258-019-00550-y
Houngue V, Nonvide GMA and Yildiz F (2020) Estimation and determinants of efficiency among rice farmers in Benin. Cogent Food & Agriculture, 6(1). https://doi.org/10.1080/23311932.2020.1819004

Ichwara JM, Kiriti-Ng’ang’a TW and Wambugu A (2023) Changes in Gender Differences in Household Poverty in Kenya. Cogent Economics & Finance, 11(1). https://doi.org/10.1080/23322039.2023.2191455
Ilboudo PG and Siri A (2023) Effects of the free healthcare policy on maternal and child health in Burkina Faso: a nationwide evaluation using interrupted time-series analysis. Health Econ Rev. 2023 May 5;13(1):27. doi: 10.1186/s13561-023-00443-w. PMID: 37145306; PMCID: PMC10161454’

Issoufou Dogo AR et Ngoa Tabi H (2022) Sophistication des exportations et Commerce intra régional dans la Communauté Economique des Etats de l’Afrique de l’Ouest (CEDEAO). Revue Française d’Economie et de Gestion. 3, 12 (déc. 2022). https://www.revuefreg.fr/index.php/home/article/view/927
Jacobs E, Bertone MP, Toonen J et al. (2020) Performance-Based Financing, Basic Packages of Health Services and User-Fee Exemption Mechanisms: An Analysis of Health-Financing Policy Integration in Three Fragile and Conflict-Affected Settings. Appl Health Econ Health Policy 18, 801–810 (2020). https://doi.org/10.1007/s40258-020-00567-8
Kabubo-Mariara J, Machio PM, Njoroge MM and Chemengich M (2023) Links Between Firm Registration and Performance: Does it Pay to Register? World Development, 169 https://doi.org/10.1016/j.worlddev.2023.106314

Kauky MS (2024) Role of Agricultural Extension Services (AES) on Farm Productivity and Household Food Security in Tanzania, The African Review 10.1163/1821889x-bja10105

Kebede SW, Maruta AA and Geda NR (2024) Are Effects of COVID-19 Understated? Gender-Based Implications on Income, Coping Strategies and Time Allocation in Ethiopia. Advances in Social Sciences Research Journal, 11(2), 505–519. https://doi.org/10.14738/assrj.112.16563

Kendo S and Tchakounte J (2021) Impact of asset size on performance and outreach using panel quantile regression with non-additive fixed effects. Empirical Economics https://doi.org/10.1007/s00181-021-02057-9

Kilimani N, Buyinza F and Guloba M (2022) Crop commercialization and nutrient intake among farming households in Uganda 113 (2022) 102328 https://doi.org/10.1016/j.foodpol.2022.102328
Kiplagat I and Mugo M and Oleche MO (2021) "Provider Process Quality of Healthcare and its Determinants in Kenya," African Journal of Economic Review, African Journal of Economic Review, vol. 9(4), September. DOI: 10.22004/ag.econ.315815
Kosimbei GK, Omolo JO, Rono GJ, Musyoka PK and Onono PA (2023) Coping Mechanisms to Income Loss by Girls and Women During COVID-19: Evidence from Selected Informal Settlements in Kenya. Advances in Social Sciences Research Journal, 10(2). 447-464. https://doi.org/10.14738/assrj.102.13937

Kouandou A and Zeh IP (2024) Insuring consumption against Shocks: The role of informal savings in Nigeria, Food Policy Volume 129 https://doi.org/10.1016/j.foodpol.2024.102737

Macharia KK, Gathiaka GK and Ngui D (2021) Energy efficiency in the Kenyan manufacturing sector, Energy Policy https://doi.org/10.1016/j.enpol.2021.112715
Macharia KK, Ngui D and Gathiaka JK (2022). Effects of energy Efficiency on Firm Productivity in Kenya’s Manufacturing Sector. Journal of Sustainable Development Vol.15 (3): 90 -107. 10.5539/jsd.v15n3p90
Majune SK, Türkcan K and Moyi E (2023). How the African Continental Free Trade Area impacts firms’ export survival: Some lessons from Kenya, The Journal of International Trade & Economic Development 33(4) pp574–597 https://doi.org/10.1080/09638199.2023.2201363
https://orcid.org/0000-0002-6875-3581
Makate C and Makate M (2022) Do Rainfall Shocks Prompt Commercial Input Purchases Amongst Smallholder Farmers in Diverse Regions and Environments in Malawi? Sustainability 2022, 14, 14904. https://doi.org/10.3390/ su142214904

Makate M and Makate C (2023) Leaving No Women Behind: Evaluating the Impact of the COVID-19 Pandemic on Livelihood Outcomes in Kenya and Ethiopia. International Journal of Environmental Research and Public Health, 20, 5048. https://doi.org/10.3390/ijerph20065048

Maket I, Kanó IS and Vas Z (2024) Quality of urban infrastructural service accessibility and human well-being in Sub-Saharan Africa, World Development Sustainability Volume 4 https://doi.org/10.1016/j.wds.2024.100155

Maket I, Kanó IS and Vas Z (2024) Urban agglomeration and regional economic performance connectedness: Thin ice in developing regions, Research in Globalization Volume 8 https://doi.org/10.1016/j.resglo.2024.100211

Mamba E and Balaki A (2023) Deep regional trade agreement as a driver for global value chains in Africa: the case of ECOWAS region, Economic Change and Restructuring. https://doi.org/10.1007/s10644-023-09503-x
Mamba E and Balaki A (2021) Effects of trade policies on external trade performances of ECOWAS countries (1996-2017). Economics of Transition and Institutional Change. https://doi.org/10.1111/ecot.12303
Manda S (2023) COVID-19, Livelihoods and Gender: Material, Relational and Subjective Realities in Rural Zambia, World Development Perspectives 32 https://www.sciencedirect.com/science/article/pii/S2452292923000632

Manja LP and Badjie IA (2023) Does household welfare change with finance access? The case of women and the youth in The Gambia, Review of Development Economics https://doi.org/10.1111/rode.13053

Mathonnat J, Audibert M and Belem S (2020) Analyzing the Financial Sustainability of User Fee Removal Policies: A Rapid First Assessment Methodology with a Practical Application for Burkina Faso. Appl Health Econ Health Policy 18, 767–780 (2020). https://doi.org/10.1007/s40258-019-00506-2

McKay A, Ogunkola O and Semboja HH (2022) Rethinking regional integration in Africa for inclusive and sustainable development: Introduction to the special issue. Rethinking regional integration in Africa for inclusive and sustainable development: Introduction to the special issue - McKay - The World Economy - Wiley Online Library
Melesse MB (2021) The effect of women’s nutrition knowledge and empowerment on child nutrition outcomes in rural Ethiopia, Agricultural Economics 1–17. https://doi.org/10.1111/agec.12668

Montcho M, Ahoyo CC, Aboh AB, Houndonougbo FM, Babatounde S and Sinsin B (2023) food security efforts toward climate variability and change in Benin,  International Journal of Biological and Chemical Sciences, Vol. 17 No. 7 (2023). https://www.ajol.info/index.php/ijbcs/article/view/265425

Moshoeshoe R (2023) "Long-Term Effects of Primary Education Expansion on Educational Achievement: Evidence from Lesotho," Annals of Economics and Statistics, GENES, issue 149, pages 3-38.

Mothobi O and Kebotsamang K (2024) The impact of network coverage on adoption of Fintech and financial inclusion in sub-Saharan Africa. Economic Structures 13, 5 (Jan 2024). https://doi.org/10.1186/s40008-023-00326-7

Mudiriza G and Edwards L (2021) "The persistence of apartheid regional wage disparities in South Africa [Long-run effects of forced resettlement: evidence from Apartheid South Africa," Journal of Economic Geography, Oxford University Press, vol. 21(6), pages 807-839.
Mugo MG (2023). The impact of health insurance enrolment on health outcomes in Kenya. Health Econ Rev 13, 42 (2023). https://doi.org/10.1186/s13561-023-00454-7

Mukong AK, Nanziri LE and Papadamous S (2021) Social networks and technology adoption: evidence from mobile money in Uganda. Cogent Economics & Finance. https://doi.org/10.1080/23322039.202 1.1913857
Mulbah FFB, Olumeh DE, Mantey V and Ipara BO (2023) Impact of Financial Inclusion on Household Welfare in Liberia: A Gendered Perspective. Review of Development Economics, 1–21. https://doi.org/10.1111/rode.13057

Muriu P (2021) Does the Quality of Institutions Matter for Financial Inclusion? Cross Country Evidence. International Journal of Economics and Finance 13. 27 https://doi.org/10.5539/ijef.v13n7p27

Muriu PW (2022) Bank Provisioning Behavior, Ownership Structure and Financial Crisis: Evidence from a Developing Economy. African Development Finance Journal. November Vol 4 No.2, 2022 PP 1-25. http://journals.uonbi.ac.ke/index.php/adfj
Mutyaba JL, Ngigi MW and Ayuya OI (Feb 2024) Determinants of knowledge, attitude and perception towards cage fish farming technologies among smallholder farmers in Uganda. Cogent Food & Agriculture, 10(1). https://doi.org/10.1080/23311932.2024.2313252

Mwabu G (2022) Time, health service utilisation and health status in Africa: Evidence from six countries, South African Journal of Economics. 2022;1–13. (June 2022). https://onlinelibrary.wiley.com/doi/full/10.1111/saje.12320
Mwangi I, Gathiaka J and Kimuyu P (2023) Impact of Energy Sector Reforms on Electricity Penetration in Kenya Relative to Other Reforming Developing Countries. International Journal of Economics, 7(2), 61–71. https://doi.org/10.47604/ijecon.1822
Naila DL, Nandonde FA and Makindara J (2025) Measuring the uptake of process innovation by SMEs in food industry: a resource-based view perspective, Journal of Sustainable Business and Innovation https://doi.org/10.1108/IJSBI-08-2024-0040

Namulondo R and Bashaasha B (2023) Labour-saving technologies mitigate the effect of women’s agriculture time-use constraints on stunting in rural Uganda, African Journal of Agricultural and Resource Economics Volume 17, Number 3 (2022), pp 255–268. https://doi.org/10.53936/afjare.2022.17(3).18

Ndicu S, Barasa L and Ngui D (May 2023) Impact of firm-level innovation on productivity of manufacturing and service firms in Sub-Saharan Africa. Innovation and Development, 1–22. https://doi.org/10.1080/2157930X.2023.2210435

Ndicu S, Ngui D and Barasa L (2024) Technological Catch-Up, Innovation, and Productivity Analysis of National Innovation Systems in Developing Countries in Africa 2010–2018. Journal of the Knowledge Economy 15, 7941–7967. https://doi.org/10.1007/s13132-023-01327-4

Ndiene M (2023) Changements Climatiques En Afrique Subsaharienne: Une Approche
Multidisciplinaire Sur L’utilisation Des Energies Renouvelables, The West African Economic Review, Volume 11, No. 1. Sept-Dec 2023.

Ndoricimpa A (2021) Tax reforms, civil conflicts and tax revenue performance in Burundi, Scientific African, Volume 13 https://doi.org/10.1016/j.sciaf.2021.e00927

Ndoricimpa A (2023) "Illicit capital movement through trade misinvoicing in Burundi: a disaggregated approach," Journal of Money Laundering Control, Emerald Group Publishing Limited, vol. 27(3), pages 532-547, May
Ndoricimpa A and Ndayikeza MA (2023) Economic Costs of Civil Conflicts: The Case of Burundi, Defence and Peace Economics, DOI: 10.1080/10242694.2023.2232971

Ndung’u N, Odhiambo S and Shimeles A (2023) COVID-19 and Public Finance in Africa: Challenges and Opportunities, Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i3–i8, https://doi.org/10.1093/jae/ejac056

Papers Published Under the JAE Supplement
- Henn SJ and Robinson JA (2023) Africa's Latent Assets. Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i9–i32, https://doi.org/10.1093/jae/ejac034
- Robinson JA (2023) Tax Aversion and the Social Contract in Africa . Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i33–i56, https://doi.org/10.1093/jae/ejac035
- Okunogbe O and Santoro F (2023) Increasing Tax Collection in African Countries: The Role of Information Technology. Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i57–i83, https://doi.org/10.1093/jae/ejac036
Nembot AM and Baye FM (2021) "Éducation et choix professionnels des femmes mariées : le cas du Cameroun," Revue d’économie du développement, De Boeck Université, vol. 29(3), pages 49-78.
Ngepah N and Mwiinga RC (2022) "The Impact of Climate Change on Gender Inequality in the Labour Market: A Case Study of South Africa" Sustainability 14, no. 20: 13131. https://doi.org/10.3390/su142013131
Ngui D, Ndung’u N and Shimeles A (Editors) (2023) Poverty, Growth, Inequality, Redistribution, and Social Inclusion before and after the COVID-19 Pandemic in Africa. Journal of African Economies, Volume 32, Issue Supplement 2, April 2023. Oxford University Press. https://academic.oup.com/jae/issue/32/Supplement_2

Papers Published Under the JAE Supplement
- Thorbecke E (Introduction), The Interrelationships Among Growth, Inequality and Poverty in Africa. Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii81–ii86, https://doi.org/10.1093/jae/ejac055
- Fofana I, Chitiga-Mabugu M, Ramos and Mabugu RE, Is Africa on Track to Ending Poverty by 2030? Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii87–ii98, https://doi.org/10.1093/jae/ejac043
- Ebeke CH, Intergenerational Mobility and the Growth–Inequality–Poverty Nexus in Africa Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii99–ii112, https://doi.org/10.1093/jae/ejac044
- Epo BN, Baye FM, Mwabu G, Etyang MN, Gachanja PM. The Nexus between Poverty, Inequality and Growth: A Case Study of Cameroon and Kenya , Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii113–ii146, https://doi.org/10.1093/jae/ejac045
- Fields GS. The Growth–Employment–Poverty Nexus in Africa, Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii147–ii163, https://doi.org/10.1093/jae/ejac046
- Fosu AK. Progress on Poverty in Africa: The Importance of Growth and Inequality, Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii164–ii182, https://doi.org/10.1093/jae/ejac047
- Kamgnia BD and  Ahouré AAE. Alleviating Poverty in Sub-Saharan Africa: The Role of Inclusive Business Models Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii183–ii201, https://doi.org/10.1093/jae/ejac048
- Lustig N, Jellema J and Pabon VM. Are Budget Neutral Income Floors Fiscally Viable in Sub-Saharan Africa? Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii202–ii227, https://doi.org/10.1093/jae/ejac049
- Morsy H, Shimeles A and Nabassaga T. Structural Change and Inequality in Africa .Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii228–ii245, https://doi.org/10.1093/jae/ejac050
- Ngugi RW, Munga BO, Kirii PP and Onsomu EN. Does the Poverty Level Minimum Basket Adequately Inform the Scope of Governments' Poverty Reduction Strategies? Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii246–ii272, https://doi.org/10.1093/jae/ejac051
- David A, Diallo Y and Nilsson B. Informality and Inequality: The African Case Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii273–ii295, https://doi.org/10.1093/jae/ejac052
- Niño-Zarazúa M, Scaturro F, Jordá V, and Tarp F. Income Inequality and Redistribution in Sub-Saharan Africa Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii296–ii319, https://doi.org/10.1093/jae/ejac053
- Shaffer P. Typology Construction for Comparative Country Case Study Analysis of Patterns of Growth in Sub-Saharan Africa. Journal of African Economies, Volume 32, Issue Supplement_2, April 2023, Pages ii320–ii338, https://doi.org/10.1093/jae/ejac054

Nkegbe PK and Mumin YA (2022) Impact of community development initiatives and access to community markets on household food security and nutrition in Ghana. Food Policy 113 (2022) 102282. https://doi.org/10.1016/j.foodpol.2022.102282
Nyagwachia AO, Chelwa G and van Walbeek C (2020) The effect of tobacco- and alcohol-control policies on household spending patterns in Kenya: An approach using matched difference in differences, Social Science and Medicine, Vol 256.
Odongo MT, Misati RN, Kamau AW and Ngoka KN (2022) Climate Change and Inflation in Eastern and Southern Africa. Sustainability 2022, 14, 14764. https://doi.org/10.3390/ su142214764
Okumu B and Muchapondwa E (2020) Determinants of successful collective management of forest resources: Evidence from Kenyan Community Forest Associations. Forest Policy and Economics Volume 113, April 2020, 102122. https://journals.sagepub.com/eprint/4A6PHYSIXGIWUGJMYDBH/full
Okunogbe O and Santoro F (2023) Increasing Tax Collection in African Countries: The Role of Information Technology. Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i57–i83, https://doi.org/10.1093/jae/ejac036
Okyere CY and Usman MA (2021) The impact of irrigated agriculture on child nutrition outcomes in southern Ghana, Water Resources and Economics, Volume 33, Jan 2021, 100174, ISSN 2212-4284, https://doi.org/10.1016/j.wre.2020.100174.
Olakojo SA and Ogunkola EO (2020) Implications of Isolationist Policies on Regional Integration in Africa. Iranian Economic Review. doi: 10.22059/ier.2020.76530
Olasehinde N, Osakede UA and Adedeji AA (2023) "Effect of user fees on healthcare accessibility and waiting time in Nigeria", International Journal of Health Governance, Vol. 28 No. 2, pp. 179-193. https://doi.org/10.1108/IJHG-07-2022-0062

Omotayo AO and Ogunniyi AI (2024) COVID-19 induced shocks and its implications for human capital development, International Journal for Equity in Health, https://doi.org/10.1186/s12939-024-02119-1

Ongono P, Tandrayen-Ragoobur V and Gong J (2022) Infrastructure and Intra-Regional Trade in Africa. Infrastructure and intra‐regional trade in Africa - Tandrayen‐Ragoobur - The World Economy - Wiley Online Library
Ongudi S, Thiam D, Miranda MJ and Abdoul S (2024) The direct and indirect effects of cash transfer program on the consumption of nutrients: Evidence from Kenya, Agricultural Economics Vol 55 Issue 3 https://doi.org/10.1111/agec.12827

Onye K and Umoh OJ (2023) Fiscal Policy and Monetary Integration in the ECOWAS, The Review of Black Political Economy, https://doi.org/10.1177/00346446221094867

Orji A and Nwosu EO (2023) "Analysis of gender wage gap and the Nigerian labour market: a new empirical evidence," International Journal of Manpower, Emerald Group Publishing Limited, vol. 45(5), pages 926-957, December.

Osei V and Ogunkola EO (2022) "Asymmetric Effects of Fiscal Deficit Financing and Inflation Dynamics in Ghana," Journal of Sustainable Development, Canadian Center of Science and Education, vol. 15(2), pages 1-27. https://doi.org/10.5539/jsd.v15n2p27
Osei V and Ogunkola EO (2022) Regime Effects of Fiscal Deficit Financing and Inflation Dynamics in Ghana. Theoretical Economics Letters, 12, 258-286. https://doi.org/10.4236/tel.2022.121015, Available at SSRN: https://ssrn.com/abstract=4955799 or http://dx.doi.org/10.2139/ssrn.4955799
Phiri, AT, Charimbu M, Edewor SE and Gaveta E (2022) "Sustainable Scaling of Climate-Smart Agricultural Technologies and Practices in Sub-Saharan Africa: The Case of Kenya, Malawi, and Nigeria" Sustainability 14, no. 22: 14709. https://doi.org/10.3390/su142214709
Picone G, Kimou JC and Kanga D (2023) Medical emergencies and farm productivity in Côte d'Ivoire, Review of Development Economics, https://doi.org/10.1111/rode.12987

Pkaremba LC, Oleche MO and Owiti E (2023) Analysis of contraceptive use among homeless women in Kenya – a case of Nairobi County. Cogent Economics & Finance, 11(2). https://doi.org/10.1080/23322039.2023.2235118

Razakamanana MV, Andrianatoandro VT and Ramiandrisoa TO (2023) Do public health expenditures affect maternal and child health in Madagascar? Health Econ Rev 13, 47 (2023). https://doi.org/10.1186/s13561-023-00462-7
Roberts S, Simbanegavi, W and Vilakazi T (2022) Cementing regional integration or building walls? Competition, cartels and regional integration in the cement industry in Africa. Cementing regional integration or building walls? Competition, cartels and regional integration in the cement industry in Africa - Roberts - The World Economy - Wiley Online Library
Robinson JA (2023) Tax Aversion and the Social Contract in Africa. Journal of African Economies, Volume 32, Issue Supplement_1, March 2023, Pages i33–i56, https://doi.org/10.1093/jae/ejac035
Sawadogo B (2022) Drought Impacts on the Crop Sector and Adaptation Options in Burkina Faso: A Gender-Focused Computable General Equilibrium Analysis. Sustainability 2022, 14, 15637. https://doi.org/10.3390/ su142315637
Seck A and Alassane F (2020) Regional Integration and Growth Spillovers: Is Africa an Economic Space? Journal of African Trade Vol. 7(1-2); December (2020), pp. 37–44 DOI: https://doi.org/10.2991/jat.k.200724.001; https://www.atlantis-press.com/journals/jat
Ssewanyana S and Kasirye I (2020) Estimating Catastrophic Health Expenditures from Household Surveys: Evidence from Living Standard Measurement Surveys (LSMS)-Integrated Surveys on Agriculture (ISA) from Sub-Saharan Africa. Appl Health Econ Health Policy 18, 781–788 (2020). https://doi.org/10.1007/s40258-020-00609-1
Takam HN and Nanfosso RT (2024) Importance of official development assistance in improving the economic cycles of Economic and Monetary Community of Central Africa countries SN Business and Economics Volume 4, article number 76
Teklewold H (2023) Understanding Gender Differences on the Choices of a Portfolio of Climate-Smart Agricultural Practices in Sub-Saharan Africa, World Development Perspectives, Volume 29 https://doi.org/10.1016/j.wdp.2023.100486

Tesfaye, W (2022) Crop diversification and child malnutrition in rural Ethiopia: Impacts and Pathways. Food Policy 113 (2022) 102336, https://doi.org/10.1016/j.foodpol.2022.102336
Thorbecke E and Ouyang Y (2022) ‘Towards a Virtuous Spiral between Poverty Reduction and Growth in SSA’, World Development, 152:105776. https://doi.org/10.1016/j.worlddev.2021.105776
Tidjani A and Ibrahim M (2020) An exploratory analysis of financial inclusion in Chad. The European Journal of Applied Economics. 17. 34 - 53. 10.5937/EJAE17-27027.
Tione SE, Nampanzira D, Nalule G, Kashongwe O, and Katengeza SP (2022) "Anthropogenic Land Use Change and Adoption of Climate Smart Agriculture in Sub-Saharan Africa" Sustainability 14, no. 22: 14729. https://doi.org/10.3390/su142214729
Tossou, JU (2022) Effect of Landownership by Women on Household Food Security in Benin, International Journal of Food and Agricultural Economics Vol 10 (3) 247-263.
Tsambou AD et Kamga BF (2021) Adoption d’innovations et productivité des entreprises en Afrique subsaharienne francophone : cas du Cameroun, de la Côte d’Ivoire et du Sénégal, Revue d'économie industrielle [En ligne], 173 | 1er trimestre 2021, mis en ligne le 03 janvier 2024, consulté le 14 juin 2021. URL : http://journals.openedition.org/rei/9920 ; DOI : https://doi.org/ 10.4000/rei.9920
Tsambou AD, Diallo TM, Kamga and BF Asongu SA (2024) Impact of employment support programs on the quality of youth employment: Evidence from Senegal's internship program, Sustainable Development Journal, https://doi.org/10.1002/sd.2913

Tumwine GN, Lokina RB and Matovu JM (2020) The Effect of Climate Change on Agricultural Crop Returns in Uganda. Journal of Economics and Behavioral Studies (ISSN: 2220-6140). Vol. 11, No. 4, pp. 71-87. https://ojs.amhinternational.com/index.php/jebs/article/view/2922

Turkson E, Oduro AD, Baffourŧ PT and Quartey P (2022) Regional Integration and Non-Tariff Barriers to Intra Sub-Saharan Africa (SSA) Trade. Regional integration and non‐tariff barriers to Intra‐Sub‐Saharan Africa trade - Turkson - The World Economy - Wiley Online Library
Usman MA and Haile MG (2022) Market access, household dietary diversity and food security: Evidence from Eastern Africa, Food Policy, Volume 113, 2022, https://doi.org/10.1016/j.foodpol.2022.102374
Wandeda D, Masai W and Nyandemo SM (2021) Government Expenditure and Economic Growth in Sub-Saharan Africa, Journal of Economics and Public Finance, Vol 7, No 4 https://doi.org/10.22158/jepf.v7n4p14

Wandeda D, Masai W and Nyandemo SM (2021) Institutional quality and economic growth: evidence from Sub-Saharan Africa countries, African Journal of Economic Review, Vol. 9 No. 4 https://www.ajol.info/index.php/ajer/article/view/214283

Wandeda D, Masai W, Nyandemo SM (2021) Government Expenditure and Economic Growth in Sub-Saharan Africa.  Journal of Economics and Public Finance, Vol 7, No 4 (2021) ,  https://doi.org/10.22158/jepf.v7n4p14
Wandeda, DO, Masai W, and Nyandemo SM (2021) The Efficiency of Public Spending in Sub-Saharan Africa. European Scientific Journal 17(19), 173. https://doi.org/10.19044/esj.2021.v17n19p173

Were M and Odongo M (2022. Competitiveness and diversification of services exports in sub-Saharan Africa. Competitiveness and diversification of services exports in sub‐Saharan Africa - Were - The World Economy - Wiley Online Library
Wirba EL, Tingum EN, Baye FM (2023). The cost of keeping up with the Joneses: Relative deprivation and food spending in Cameroon, Journal of International Development, pp. 415-434. https://doi.org/10.1002/jid.3822

Woldu GT and Szakálné Kanó I (2023) Fiscal multipliers and structural economic characteristics: Evidence from countries in sub-Saharan Africa. The World Economy, 00, 1–26. https://doi.org/10.1111/twec.13405
Yimer A (2022) When does FDI makes a difference for growth? A Comparative analysis of resource-rich and resource scarce African Countries. International Finance, October (2022) https://doi.org/10.1111/infi.12423
Yitbarek E and Tesfaye W (2022) Climate-Smart Agriculture, Non-Farm Employment and Welfare: Exploring Impacts and Options for Scaling Up. Sustainability 2022, 14, 15981. https://doi.org/10.3390/ su142315981
Yuni D and Attama M (2022) How does the central bank recapitalization policy affect competition in commercial banks of Sub-Saharan Africa? Banks and Bank Systems. 17. 98-112. 10.21511/bbs.17(2).2022.09.

Books

Ngui, D, Shimeles A, Ndung’u N, Cracknell D and Greenacre J (Editors) (2023) Digital Financial Inclusion and Market Development in East African Community (EAC) Economies. African Economic Research Consortium, Nairobi, Kenya. https://publication.aercafricalibrary.org/items/ed42bf1a-7f1a-405c-b207-1f4b1c970b7e
- Financial Inclusion, Interoperability and Market Development in the East African Community David Cracknell Pg. 11
- Bridge Contracts in Africa: A Case Study of Orange Mali by Jonathan Greenacre Pg. 57
- Digital Financial Services and Implications of Financial Literacy on Gender and Over-Indebtedness: The Case of Kenya by Anne Kamau, Roseline Misati, Kethi Ngoka, Maureen Odongo and Maureen Were Pg. 85
- The Old and the New Economics of Financial Inclusion by Peter Knaack Pg 117
- Financial Technology in Tanzania: Assessment of Growth Drivers by Deogratias Philip Macha and Nangi Mosses Massawe Pg. 141
- The Monetary Economics of E-Money in East Africa by Isaac Mbiti and David N. Weil Pg. 191
- Expanding Digital Financial Services in the East African Community with a Gender Lens by Flora Myamba Pg. 223

Ndemo B, Ndung’u N, Odhiambo S and Shimeles A (Editors) (2023) Data Governance and Policy in Africa https://link.springer.com/book/10.1007/978-3-031-24498-8

- Ndemo B, Ndung’u N, Odhiambo S and Shimeles A, Introduction, Pages 1-8, https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_1?pdf=chapter%20toc
- Ndemo B and Thegeya A, A Prototype Data Governance Framework for Africa, Pages 9-29, https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_2?pdf=chapter%20toc
- Chege ZM, and Wanjohi PM, A Value Chain Approach to Data Production, Use, and Governance for Sound Policymaking in Africa, Pages 31-70 https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_3?pdf=chapter%20toc
- Babalola O, Data Protection Legal Regime and Data Governance in Africa: An Overview, Pages 71-96 https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_4?pdf=chapter%20toc
- Hlomani H and Ncube CB, Data Regulation in Africa: Free Flow of Data, Open Data Regimes and Cybersecurity, Pages 97-130, https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_5?pdf=chapter%20toc
- Ndemo B and Mkalama B, Digitalisation and Financial Data Governance in Africa: Challenges and Opportunities, Pages 131-153 https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_6?pdf=chapter%20toc
- Marivate V, More Than Just a Policy: Day-to-Day Effects of Data Governance on the Data Scientist, Pages 155-177 https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_7?pdf=chapter%20toc
- Thegeya A, The Economics of Blockchain Within Africa, Pages 179-202 https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_8?pdf=chapter%20toc
- Ndemo B, Ndung’u N, Odhiambo S, Omolo M and Shimeles A, Conclusion, Pages 203-208, https://link.springer.com/content/pdf/10.1007/978-3-031-24498-8_9?pdf=chapter%20toc