## Annual Review Template 2025

Title: ESRC-FCDO Joint Research Fund on Raising Learning Outcomes (RLO)
Programme Value £ (full life): £15m (+£5m ESRC)		Review date: September 2025
Programme Code: 204324	AMP start date: 10 Jan 2014	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A+	A+	A	A+	A	A	A	A	A	A	A
Risk Rating	Medium	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/4221301.odt
DevTracker Link to results framework:	54104351.xlsx (live.com) (will update once latest logframe is on DT)

A. SUMMARY AND OVERVIEW
Description of programme
The Raising Learning Outcomes (RLO) programme is a £20 million joint-funded programme between the FCDO (£15m) and the Economic and Social Research Council (ESRC) (£5m) running from 2014 to 2026. RLO is a portfolio of research, delivered through competitive research grants, generating evidence to support policymakers and practitioners in low- and middle-income countries (LMICs) to improve learning outcomes and education quality.
RLO awarded 31 main research grants (Annex A) through three research calls from 2014 to 2017. A further 16 ‘Follow-on Fund’ grants were awarded between 2017 and 2022; only one of these 16 grants is still active. This grant was awarded a time extension over the past reporting year. During the reporting period, two grants have ended and are at reconciliation stage, with the remaining 13 grants already closed.
A Business Case Addendum (BCA) to allow for a second Phase of RLO was approved in 2024. This BCA did not commit any new additional FCDO funds. It reduced the previously approved FCDO ceiling for the second phase from £12m to £10m, which would have brought the total envelope of FCDO funding for RLO to £25m across the entire programme lifetime from 2014 to December 2032. This BCA was a major recommendation in the 2024 Annual Review and followed a long-planned extension to this successful programme. The second phase of RLO was initially agreed in 2019 but was subject to rolling delays due to the COVID-19 pandemic and ODA reductions. On 25 February 2025 the UK Prime Minister took the difficult decision to gradually reduce the UK’s Official Development Assistance (ODA) to 0.3% of GNI by 2027, and to reinvest these funds into defence to meet the profound challenges undermining UK security and prosperity. The UK government has said that it remains fully committed to playing a globally significant role in humanitarian aid and development, and to spending 0.7% of GNI on ODA when the fiscal circumstances allow. Consequently, activities to initiate RLO Phase 2 have been paused.
The Memorandum of Understanding (MoU) for Phase 1 of RLO was due to expire on 31st March 2025 and has been provided a time extension of one year (31st March 2026). This allows ESRC to continue with outstanding Phase 1 activities, including management of the final grant and to support key communications activities, including on the impact of RLO, for additional evidence uptake. This annual review (AR) is therefore light touch to reflect minimal activity during the reporting period, June 2024 – June 2025.
[note] The logframe for this period runs to March 2024 as time is needed for ESRC to collect and synthesis reporting data from across all grantholders. The programme annual report is submitted by ESRC to FCDO at the end of June.
Summary supporting narrative for the overall score in this review
The overall score of ‘A’ reflects the programme meeting expectations. Section C of this AR shows how the overall judgement of expectations having been met comes from a mix of some targets being exceeded and others being marginally missed.
As mentioned above, a BCA was developed and approved for the delivery of Phase 2 but initiation of Phase 2 has been paused due to further ODA reductions. There were limited activities this year, reflecting that RLO Phase 1 is coming to a close. The annual RLO grantholder workshop took place in this reporting period (detailed in Annex B). ESRC commissioned the Institute of Development Studies (IDS) to design and deliver an in-person event in Nairobi in November 2024. The workshop focused on network-building, gender inclusion, equitable partnerships, and effective communication, with strong Global South representation. The grantholders workshop marked a successful return to in-person engagement, following the virtual networking events held under Covid-19, and provided an important opportunity to revisit the studies and identify synergies between the key findings.
Additionally, ESRC and FCDO implemented an interim communications plan to promote RLO research. This additional workstream was not originally envisioned in the programme design but has been critical to address the dissemination and communication of RLO following the end of the Impact Initiative in June 2021 and the closure of the dedicated synthesis support facility since 2019. In this reporting period, RLO commissioned four short impact films, co-produced three blogs and a selection of infographics with IDS (further details can be found in Annex E) to highlight RLO’s influence on learning outcomes and international development. These efforts have sustained the visibility of the studies, supporting grantholders’ dissemination. Such activities will also inform future funding strategies, with a dedicated impact and synthesis facility planned under Phase 2 of RLO.
Overall, the programme continues to yield qualitative examples of how RLO grants are contributing towards the programme’s intended outcomes and impact (see section B).
Major lessons and recommendations for the year ahead
The recommendations from the previous AR were mostly focused on Phase 2. These were advanced in the reporting period, but not all were completed due to the ODA announcement. Progress against recommendations include: (i) a time-only business case addendum was completed and approved in September 2024; (ii) an MoU for the design and delivery of Phase 2 was in final draft format and ready to be signed but was paused due to the ODA announcement; (iii) the Call for Proposals for Phase 2 was in final draft format with some minor adjustments still required ahead of launching, but paused due to the ODA announcement; and (iv) a Value for Money (VfM) framework was developed and approved jointly by FCDO and ESRC – this is partially in use for the purposes of this report.
Recommendation 1: FCDO and ESRC should review the recommendations from last year's AR again in the Autumn 2025, once funding decisions on the future of RLO Phase 2 have been made by FCDO and ESRC.
Recommendation 2: The programme should continue to strengthen networks and activities between researchers and practitioners, leveraging existing events and conferences such as the UK Forum for International Education and Training (UKFIET) and Comparative and International Education Society (CIES), as well as ongoing FCDO research programmes including the What Works Hub for Global Education, so that the community of practice remains active beyond the end of the programme.
Recommendation 3: If Phase 2 is no longer considered viable following ODA decisions in Autumn 2025, ESRC and FCDO should work together to deliver an exit strategy that supports evidence uptake. This should consider how to encourage grantholders to further disseminate their research, including through policy dialogues or briefings; academic conferences; technical working groups; and online and/or print media.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The theory of change developed from the business case has remained relevant for this phase for the RLO programme (Annex C) and there have been no changes to the theory of change or outcome and impact indicators this reporting period. The intended impact of RLO is that policy and programme decisions to improve the efficiency, effectiveness, and equity of education systems to deliver learning outcomes at scale in developing countries are demonstrably informed by the programme-generated evidence base. This is supported by three outcomes which are discussed below.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Outcome 1: A community of practice is established and supported to produce high-quality, policy-relevant evidence on how learning outcomes can be raised within education systems in low-income countries.

Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 1.1: Number of scheme-funded researchers (PIs/CoIs) reporting examples of benefits linked to programme-funded activities designed to support the production of high quality research on raising learning outcomes within developing country education systems.	70% (21 of 30) grants reporting benefits of programme-funded activities to support research synthesis and cohort building.	Target achieved. 73% (22 of 30).
Outcome indicator 1.2: Number of scheme-funded researchers (PIs/CoIs) reporting examples of benefits linked to programme-funded activities designed to build their capacity to respond to demand for knowledge from policy actors.	85% (25 of 30) grants reporting benefits of programme-funded activities to build capacity to respond to demand for knowledge from policy actors.	Target not met. / Attendees of the RLO grantholder event reported benefits, but only 73% (22 of 30) main grants were represented.
Outcome indicator 1.3: Number of activities delivered to build connections and foster new relationships, within the thematic area of raising learning outcomes.	RLO grantholder event delivered within 2024, with grantholders reporting progress in initiating new connections and/or building new partnerships as a result of the event.	Target achieved. New connections and partnerships were formed at the RLO grantholder event held in Nairobi in November.

Outcome indicator 1.1: To advance the community of practice under RLO, this year ESRC and FCDO hosted a grantholders workshop to share insights from the research generated, identify synergies, learn from different partnerships and build capacity for evidence uptake. 73% (22 of 30) of the main grants were represented at the 2024 RLO grantholder event. Each of the 43 participants provided examples of personal highlights and beneficial takeaways. For example, participants reported positively on the capacity building aspect of the event, including knowledge learnt on the importance of disability inclusiveness in research and thinking more proactively about equitable partnerships in future research design. More details are captured in Section C.
Outcome indicator 1.2: Representatives from 22 different main grants (73%) attended the 2024 grantholder event, and so the target for this indicator was not met. Not all grantholders were able to attend the event, and several grantholders reported limited capacity for impact and dissemination activities following the end of their grants. Nonetheless, the overall attendance and engagement at the grantholder's event was exceptional, particularly considering the significant time that has passed since the grants were awarded to most participants and the limited activity in the interim.
Outcome indicator 1.3: Although the community of practice for RLO is already strong, a number of new connections were made at the grantholder event. Qualitative examples provided by grantholders demonstrated that new connections and partnerships were formed during the event (Annex E). For example, participants outlined concrete plans to strengthen international research partnerships, with specific commitments to establishing Africa and India collaboration and growing SSA partners in Malawi, Ghana, Lesotho. There was particular emphasis on South-South collaboration, with plans for collaborating with south-based universities to have comparative study in Evidence Centred Design (ESD). New connections were also demonstrated in the communications activities held following the event, which featured co-authored blogs from colleagues that had not previously worked together.
Outcome 2: Evidence generated through the programme adds to and informs the body of research knowledge relevant to how education systems can raise learning outcomes in developing countries.
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 2.1: Number of programme-funded outputs cited in academic journal articles, books and book chapters.	At least 85% programme-funded outputs published by March 2025 are reported as cited in academic journal articles, books and book chapters.	Target achieved. / 168 of 196 (86%) outputs published by March 2025 were cited in academic journals, books and book chapters by March 2025.

Outcome indicator 2.1: As of March 2025, a total of 196 unique outputs have been recorded against RLO grants. 168 of the 196 outputs (86%) published have been cited in academic journals, books and book chapters, slightly exceeding the target. A small proportion (27 outputs) remained uncited as of April 2025, however, 67% (18) of the uncited outputs were published within the last 3 years and so could reasonably be assumed to receive citation in future. Several studies continue to receive a very high number of citations demonstrating the continued relevance of these studies. For example, Professor Elaine Unterhalter’s article ‘The many meanings of quality education: Politics of targets and indicators in SDG 4’ (Unterhalter, E., Global Policy, 2019) has had 299 citations recorded in Google Scholar at the time of writing, 82 more than the same time last year.
Outcome 3: Evidence generated through the programme contributes to debates amongst policymakers and practitioners on education systems and how they can deliver learning at scale
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 3.1: Number of programme-funded outputs cited in non-academic publications.	At least 25% programme funded outputs published by March 2025 are reported as cited in non-academic publications	Target not achieved. / 29 of 196 (15%) outputs published by March 2025 were reported by grantholders to have been cited in non-academic publications by March 2025.

Outcome indicator 3.1: This year, the indicator is reported as not met. It is worth acknowledging the challenges in reliably reporting against this indicator – it is manually reported by academics (rather than through a more systematic and reliable tool like Overton), and non-academic products often do not cite their sources, although they may be influenced by and even in some instances directly draw from key arguments made in specific studies. Nonetheless, some of the non-academic citations that were recorded in this reporting period are notable. For example, Melanie Ehren contributed to the 2024 UNESCO Global Education Monitoring Report (GEMR) as an expert panel member, reviewing the system leadership chapter and full report, and integrating insights from RLO projects.
Outcome 4: Evidence generated through the programme contributes to change in policy or practice affecting the ability of education systems to deliver learning outcomes at scale in developing countries.
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 4.1: Examples of policy or practice change and influence.	At least 2 new examples of influence on, or change in, policy or practice	1 - target partially met.

Outcome indicator 4.1: One new example (see box below) was provided in this reporting year of a grant's contribution towards a change in policy or practice, meaning that this indicator was partially met.
Impact Story: Research changes teacher practice in India / Professor Caroline Dyer’s research on attendance and accountability relations to reduce drop out among disadvantaged learners has informed new ways of working for teachers in Rajasthan. As part of the research project, Professor Dyer and her team provided training to partner organisation Vidya Bhawan on how to investigate patterns of attendance in 23 of the government schools it collaborates with through the Shiksa Sambal project. Staff at Vidya Bhawan have since adopted the project’s methodology as part of the organisation's standard professional practice, using this approach to communicate findings and provide tailored support to the teachers and principals. Vidya Bhawan have also cascaded the RLO project training, running a workshop for the principals and senior staff of the Vidya Bhawan educational institutions, where participants employed SWOT (Strengths, Weaknesses, Opportunities, and Threats) analysis to identify knowledge gaps and avenues for organisational and school development.

Several other grantholders reported activities and outcomes which are well placed to achieve future policy influence and/or practice change. For example, Dirgha Ghimire and project team members from the University of Michigan and the Institute for Social and Environmental Research continued engaging with policymakers and stakeholders in Nepal. Over the past year, they held meetings with the Bharatpur Metropolitan Education Section, Chitwan Kachari, and the Nepal Planning Commission to share research findings and discuss practical steps to improve educational access and equity. In addition, Professor Jenny Aker reported that research findings from two RLO projects have been shared with policymakers at two events in March 2025: as part of a presentation on educational evidence in Benin and as part of a visit focused on strategic planning for Ivory Coast's five-year plan.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
The independent programme evaluation for Phase 1 of RLO concluded that the programme had produced a rich and diverse research portfolio, noting that the commissioning process ensured research quality and uptake. As detailed above, the programme continues to demonstrate impact in policy, practice and academic thought – in several cases, this impact is being achieved up to 5 years after grants have closed, demonstrating the long-term contribution of the RLO research in shaping the education sector.

From the start of the programme, RLO has provided an important contribution to the Education Gender Inclusion and Research (EGIR) team portfolio for its geographic breadth, focus on raising learning outcomes and emphasis on localisation of research. The latter emphasis particularly aligns with the Foreign Secretary David Lammy’s priority to refresh the UK’s development approach, moving from ‘paternalism’ to ‘partnership’. RLO has achieved a high number of research grants in partnership with or led by Global South scholars, and the programme’s approach to Southern partnerships has been influential in also shaping UK Research and Innovation’s (UKRI) approach to international development research. Building on the ESRC-FCDO RLO partnership, UKRI have continued to ensure the inclusion of equitable partnerships in the development of future funding opportunities within international development. The delivery partnership with ESRC has also consistently represented good value for money for FCDO.

Together, this strongly suggests the programme should continue. Nonetheless, the future possibility of a Phase 2 of the programme beyond March 2026 remains uncertain at the time of this AR due to the UK government ODA reductions announced in February 2025.

C. DETAILED OUTPUT SCORING

Shaded boxes in tables throughout this section show indicators that have been closed. ESRC and FCDO have agreed that these would remain included in ARs to illustrate the RLO programme’s significant delivery beyond the expectations that were set out at the start of the programme is not obscured from the record.
Output Title	A portfolio of high quality, policy-relevant research on what works to deliver learning outcomes through effective, equitable education systems in low-income countries is delivered.
Output number:		1	Output Score:	A
Impact weighting (%):		60%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.1: Number and quality profile of research awarded funding through independent assessment of scientific quality and policy relevance.	Target (March 2021): At least 27 research grants awarded which meet scheme scientific quality and policy relevance requirements.	Target exceeded and indicator closed in 2021. 31 research grants have been awarded16.
Output indicator 1.2: Number of research grants operating in line with contract terms and conditions, measured by compliance with grant annual progress reporting and Researchfish validation requirements.	Target (March 2025): At least 95% research grants will have submitted annual progress reports and completed Researchfish validation as required.	Target not met. 11 of 15 expected grantholders (73%) submitted an annual progress report. 13 out of 15 active or completed research grants (87%) submitted their required reports through Researchfish.
Output indicator 1.3: Number of research grants completed to approved timescales, measured by end of award reports received.	Target (March 2023): At least 95% research grants expected to have submitted end of award reports in approved timescales.	Target met and indicator closed in 2023. 28/28 (100%) of completed research grants have submitted end of award reports.
Output indicator 1.4: Number of scheme-funded journal articles, books, or book chapters reported as published or accepted for publication.	Target (March 2025): At least 180 journal articles, books or book chapters reported by RLO research grants.	Target exceeded. (21 in the AR period).196 journal articles, books or book chapters.
Output indicator 1.5: Number journal articles and book chapters synthesising methodologies and findings from research grants.	Target (March 2025): At least 12 articles/papers completed by March 2025 that synthesise findings across RLO grants.	Target not met.11 academic outputs completed.

Briefly describe the output’s activities and provide supporting narrative for the score:
This output scored an A based on one indicator exceeding, and two indicators being marginally not met.
Indicator 1.4 on research generation exceeded the target for this period, with 21 outputs comprising 17 journal articles, three book chapters and one book reported by grantholders. The articles published in journals this reporting year focused on education, development, economics, political sociology and women’s studies. Of these, 12 articles (70%) were available as open access in their final published form. Meanwhile, contributions made to the three books focused on: language, cognition, and communication in multilingualism; generative linguistics; and achieving equitable education. Grantholder Melanie Walker also edited a book on how transformative learning spaces can be created through different participatory methodologies and with different stakeholders.  This brings the total cumulative number of studies published under RLO phase 1 to 196.
[note] https://doi.org/10.1007/978-3-031-45806-4
Indicator 1.2 was marginally not met although 13 out of 15 active or completed research grants (87%) submitted their required reports through Researchfish, which is ESRC’s system for tracking research progress and outcomes. Grant holders have previously feedback that they have limited resources and time to continue to report on grants once the projects have closed which explains the difficulty in meeting the target.
[note] Researchfish validation refers to the process used by UK research funders—especially UKRI (UK Research and Innovation)—to ensure that researchers accurately report the outcomes, outputs, and impacts of their funded projects through the Researchfish system.
Similarly, indicator 1.5 was marginally not met. 11 rather than 12 academic outputs across RLO grants have been completed during the lifetime of the programme but no new journal articles or book chapters synthesising findings were published this year. This is not unexpected given the closure of the RLO synthesis function in 2019 and the fact that any new academic outputs would have had to have been initiated by grantees, most of whom funding has long since ended.
Describe any changes to this output during the past year, and any planned changes as a result of this review:
There were no changes to this output during the past year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
There were no recommendations for this output in the previous AR.
In the case that RLO Phase 2 is able to proceed, FCDO and ESRC should initiate and carry out a research call for new studies. Accordingly, the teams should set new targets for Output indicator 1.1 on the number and quality profile of research awarded funding through independent assessment of scientific quality and policy relevance.
However, in the case of potential programme closure, then no further targets would be set and the programme completion report should be completed by July 2026.

Output Title	Research funded through the programme draws on diverse disciplines and methodologies, appropriately addresses core cross-cutting issues, and actively involves non-academic stakeholders.
Output number:		2	Output Score:	N/A
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2.1: Number of research grants which involve more than one academic discipline, as defined by RCUK (now UKRI).	Target (March 2021): At least 15 of 30 (50%) research grants are classified to more than one academic discipline at proposal stage.	Target exceeded and closed in late 2021. / 19 of 30 (63%) contracted grants reported more than one discipline at the proposal stage.
Output indicator 2.2: Number of research grants that include a mixture of quantitative and qualitative methodological research designs and/or methods.	Target (March 2021): At least 15 of 30 (50%) research grants are classified as mixing quantitative and qualitative approaches at proposal stage.	Target exceeded and closed in late 2021. 23 of the 30 (77%) contracted grants were classified as mixing quantitative and qualitative approaches at proposal stage.
Output indicator 2.3: Number of research grants that report undertaking gender analysis or disaggregating by gender or other structural inequalities	Target (March 2021): At least 21 of 30 (70%) research grants reporting to date report they will undertake gender analysis or disaggregate data by gender or other structural inequalities.	Target exceeded and closed in late 2021. 27 of 30 (90%) research grants reported the undertaking of gender analysis in 2019.
Output indicator 2.4: Number of research grants involving non-academic organisations as co-Is, project partners or advisory board members.	Target (March 2021): At least 25 of 30 (85%) research grants include non-academic stakeholders as Co-Is, project partners or advisory board members in their proposals.	Target exceeded and closed in late 2021. 26 of the 30 (87%) contracted grants include non-academic stakeholders as Co-Is, project partners or advisory board members in their proposals.
Output indicator 2.5: Qualitative examples provided against Output Indicators 2.1 - 2.4.	Target (March 2023): At least 2 examples for each indicator 2.1 - 2.4.	Target met and closed in March 2023. 2 qualitative examples provided for 2022-23 against each indicator 2.1-2.4 above.

Briefly describe the output’s activities and provide supporting narrative for the score:
There are no active indicators against this output. As all main grants have now ended, and this indicator is completed. The weighting of this output has remained at 0%.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
In the previous AR, we noted that FCDO’s programme team were working closely with ESRC and the Institute of Development Studies to ensure that the agenda for the grantholder event included multiple sessions to support knowledge exchange, including a World Café (informal opportunity to share and discuss lessons learned) and learning labs (to facilitate sharing of latest discoveries and thinking on ways of working). This was achieved successfully and is considered completed, as discussed in more detail under output 4.4.
Output Title	Programme funding is accessible to Southern researchers, and supports individual and institutional capacity to design, conduct and disseminate high quality social science research on learning outcomes and education systems.
Output number:		3	Output Score:	N/A
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 3.1: Proportion of proposals and number of research awards funded which include PIs or Co-Is based at Southern Institutions.	Target (March 2021): At least 40% of proposals and 12 of 27 (45%) research grants awarded involve Southern PIs and Co-Is.	Target exceeded and closed in 2021. 56% of proposals and 16 of 30 (53%) research grants awarded involve Southern PIs or Co-Is.
Output indicator 3.2: Proportion of research funding awarded that is allocated to Southern institutions.	Target (March 2021): At least 35% of research funding awarded is allocated to Southern institutions.	Target exceeded and closed in 2021. 41% of funding awarded is going to Southern institutions.
Output indicator 3.3: Number of grants reporting undertaking capacity building activities benefiting Southern researchers, by type of activity.	Target (March 2022): At least 10 of 30 (30%) research grants reporting to date report undertaking capacity building activities benefiting Southern researchers.	Target exceeded and closed in 2021. 27 of the 30 live and completed grants (90%) reported capacity building activities benefitting Southern researchers in 2019.
Output indicator 3.4: Qualitative examples provided of Southern and non-Southern capacity-development	Target (March 2023): At least 2 examples for Southern and at least 2 examples for non-Southern capacity-development.	Target met and closed in 2023. At least 2 qualitative examples provided in the 2022-23 Annual Report of capacity-development activities benefitting Southern and non-Southern researchers and practitioners.

Briefly describe the output’s activities and provide supporting narrative for the score:
There are no active indicators against this output. As all main grants have ended, this indicator is completed. The weighting of this output remains at 0%. There were no recommendations against this output in the previous AR.
Output Title	Research findings are accessibly communicated and synthesised for broad audiences including potential policy and practice research users with an interest in raising learning outcomes in education systems in low-income countries
Output number:		4	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 4.1: Number of conference/working papers produced, and workshops/ lectures conducted by scheme-funded research grants.	Target (March 2025): At least 430 conference/ working papers or seminar/lectures reported.	Target exceeded. 472 (42 in this AR period) conference abstracts, working papers, workshops, talks and lectures have been reported by grantholders to date.
Output indicator 4.2: Number of outputs targeting non-academic audiences reported by research grants, by type.	Target (March 2025): At least 170 non-academic outputs reported.	Target exceeded. 177 (17 in this AR period) non-academic outputs reported to date.
Output indicator 4.3: Number of outputs produced at programme level which make learning from more than one RLO grant accessible to potential research users, by type.	Target (March 2025): 22 outputs produced at programme level which combine learning from more than one RLO grant for research user audiences. / .	Target achieved. 22 outputs produced which combine learning from more than one RLO grant for research users.
Output indicator 4.4: Number of research grants taking part in events and activities organised at a programme level which are designed to facilitate knowledge exchange: i) with potential research users; and ii) between grantees to develop common messages and a sense of cohort building.	Target (March 2025): Researchers from at least 25 RLO grants have taken part in programme-level activities designed to facilitate knowledge exchange opportunities with potential research users and/or grantees.	Target not achieved. Researchers from 22 main RLO grants attended the grantholder event in 2024 which included varied opportunities for knowledge exchange.

Briefly describe the output’s activities and provide supporting narrative for the score:
Overall, this output scored on ‘A’ based on mixed results of exceeding two targets, achieving one and missing another.
The number of conference papers and talks exceeded expectations, with 42 reported this period (Annex D), bringing the cumulative total to 472 (indicator 4.1). Researchers presented their work at several influential international events. Examples include: the System Dynamics Society conference in Norway where researchers shared insights on dynamic systems thinking; the Africa Gender Statistics Forum in Botswana where findings were presented to staff from national statistical offices representing 27 African countries; and at the Comparative and International Education Society (CIES) conference in Miami, a workshop explored the benefits and challenges of using mixed research methods in low-income settings like Honduras, drawing on experiences from multiple research projects.

The definition of non-academic outputs under indicator 4.2 is aligned with that used on other ESRC-FCDO projects. This includes technical reports, guides/manuals and policy briefing reports. One example in this reporting period includes two policy briefs that were developed to accompany academic papers produced for the project led by Andres Sandoval-Hernandez (Call 4 FoF; ES/X014118/1; UK). The briefs condensed complex empirical findings into concise, actionable insights tailored to the needs of policymakers, school leaders and educational planners. They were disseminated through institutional networks, with particular emphasis on reaching education departments and practitioners in the Global South. The RLO programme has excelled beyond the expectations that were set out at the start of the RLO programme in terms of non-academic outputs.
A target was set for 4.3 indicator for 2024-25 to reflect plans to commission a supplier to deliver a standalone grantholder event in 2024 and to co-create a number of impact-focused outputs to synthesise learning from across the RLO programme of grants. Towards meeting the total target of 22 synthesis products, IDS and RLO grantholders co-produced three blog pieces and accompanying infographics which reflected the learning of grantholders from across the cohort, key findings from multiple studies and provide important insights for policy and practice.
Against indicator 4.4, IDS delivered a grantholder event in Nairobi in November 2024, with sessions designed to facilitate knowledge exchange and create foundations for future collaboration. Representatives from 22 main grants attended the event, including 14 follow-on grants were represented at the event (in total 78% of 46 RLO grants). The event received overwhelmingly positive feedback, the workshop fostered renewed connections, direct engagement with funders, and sparked ideas for future collaborations. It prioritised knowledge exchange, equitable partnerships, and inclusive participation—featuring strong representation from the Global South and accessibility measures such as sign language interpretation and childcare support. However, fewer grantees were able to attend the event than anticipated so this target was marginally not met.
Describe any changes to this output during the past year, and any planned changes as a result of this review:
There have been no changes to this output during the past year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
There were no recommendations for this output in the previous AR.
In regard to lessons learnt, although output 4.1 exceeded its target, with many grantholders continuing to present RLO research findings at cross disciplinary international conferences, several closed grant holders again flagged challenges in doing so. In progress reports, grantees note that they have limited capacity and resources for impact and engagement activities beyond the life of their RLO grant and that this restricts their ability to present findings at events and conferences. The number of talks, presentations and conference abstracts reported for RLO grants will most likely reduce year-on-year as nearly all grants are now closed.
Lessons learnt from the grantholder’s workshop focus on accessibility and inclusion. These were cited during and after the event as a distinct benefit, not only by those who were directly supported but also by many other participants. Feedback from participants indicated that such positive practices had allowed for richer discussion across the breadth of the cohort. The workshop was particularly positive in its inclusive approach, notably through the active participation of deaf researchers and the provision of sign language interpretation throughout the event. As a result, inclusion featured prominently in the key takeaways recorded at the end of the event, including commitments to implement disability inclusiveness in research and to think proactively about inclusion in future research design.

D. VALUE FOR MONEY
The RLO business case stipulates that the programme Value for Money (VfM) should be assessed by considering the programmes’ research outputs, engagement, influence, dissemination, and use of resources for programme and administrative costs. In the reporting period, based on the recommendation from last year’s AR, FCDO and ESRC have worked to develop a VfM framework that considers each of the five E’s of economy, efficiency, effectiveness, equity and cost-effectiveness. It was agreed that this year a light touch assessment would be made, and the full VfM framework would be assessed under Phase 2 of RLO, if it goes ahead.
Economy assessment is excellent: RLO has demonstrated strong economic value for FCDO. ESRC is responsible for delivery of the programme on behalf of both FCDO and ESRC as joint funders and implements a range of safeguards to ensure VfM throughout the application, review and grant contracting and management process. The key costs drivers for the overall programme are as follows: 81% towards the grants; 10% grantholder workshop and related follow up activities; 5% evaluation activities and 4% overall administration costs for staffing and services required to administer the scheme. These costs are all within the expected amounts outlined in the business case and MoU with ESRC.
Indicators	Judgement	Evidence
% of budget spent on programme administration	Excellent	ESRC have not charged an administration fee since the end of FY 2021/22, although they continue to provide the staffing and services required to administer and oversee the scheme. This demonstrates excellent economic value for FCDO for the services provided, and reflects the strong partnership between ESRC and FCDO.

Efficiency assessment is good: The efficiency and catalytic nature of the RLO grant model is demonstrated through the additional leveraged resources secured by grantees beyond the core funding provided. This also demonstrates the value of the RLO research.

Indicators	Judgement	Evidence
Additional funding leveraged through RLO	Good	To monitor efficiency, grantholders are asked to report on any linked or additional funding acquired over the course of each reporting year which has been catalysed by RLO project work. 8 RLO grants (2 active in 2024-25) formally reported contributions, in cash and in kind, from partner organisations, in addition to the funding requested from the scheme. A total of £913,699 in contributions by partner organisations has been included in the contracted RLO grants over the lifetime of the programme. Additionally, this year, RLO grantholders reported several new and follow-on funding awards catalysed by their RLO project work, demonstrating the research’s continued influence and relevance across diverse global contexts.
[note] This number covers Calls 1 – 3 (including the Call 1 FoF), and tranches 1-4 of the Call 4 Follow-on Fund.

Effectiveness assessment is good: RLO demonstrates good effectiveness, particularly in academic and community-building outcomes. However, examples of policy influence and practice change have dwindled as time since grant closure has elapsed.

Indicators	Judgement	Evidence
Combined assessment of logframe outcome indicators	Good	Outcome 1 is judged to be good as this outcome exceeded two of three indicators and partially met the third. / Outcome 2 is judged to be excellent, with 86% of outputs cited in academic literature, exceeding the target. / Outcome 3 is fair as 15% of outputs were cited in non-academic publications, which is below the 25% target. However, qualitative examples (e.g., UNESCO GEMR contributions) show influence. / Outcome 4 is poor as only one new example of policy/practice change was reported, partially meeting the target.

Equity assessment is good: RLO continue to actively promote gender inclusion, disability inclusion and partnership equity throughout programme events and ongoing communications.

Indicators	Judgement	Evidence
% of funding allocated to Global South institutions	Good	The open calls for proposals through the RLO programme resulted in diverse researchers and research institutions being awarded grants - 41% of grants went directly to researchers and institutions in the Global South. / Continued engagement with grantees has focused on strengthening and deepening equitable partnerships, including through knowledge exchange and collaboration. The 2024 grantholders workshop held in Nairobi had a strong focus on partnership equity with excellent Southern representation. Post-event communications also featured the voices of Global South scholars.

Cost-Effectiveness is good: RLO-funded research continues to influence policy and practice by informing national education strategies and supporting evidence-based planning across the Global South.

Indicators	Judgement	Evidence
Programme outputs that have a significant policy or practice change influenced by RLO-funded research	Good	RLO-funded research has led to significant policy and practice changes through outputs such as policy briefs, technical guides, and engagement tools. Previous impacts have included shaping global gender equality frameworks used by UNESCO; informing strategic planning in countries like the Ivory Coast; influencing multi-lingual education policies and practices in India; changing community attitudes towards disability inclusion in early childhood in Malawi, among other educational reforms in low- and lower-middle-income countries. / One impact story was captured in this reporting period: the staff at the organisation, Vidya Bhawan, after training from Caroline Dyer’s research team, used the project’s methods to study school attendance in 23 government schools, influencing both teacher awareness and the organisation’s professional practices.

Assessment of whether the programme continues to represent value for money.
RLO has continued to demonstrate good value for money during this reporting period. The programme is underpinned by robust financial safeguards at every stage, from application and assessment to grant management and reporting. All costs are carefully scrutinised, and institutions must meet UKRI’s due diligence standards. Beyond its core funding, the programme has been able to leverage significant additional investment from international funders and partners, demonstrating its efficiency, value and broader impact. FCDO’s partnership with ESRC on RLO has also had wider impacts on the way UKRI advances its international development research, with a much stronger focus in its guidance and selection process on prioritising equitable partnerships and Global South scholars. This demonstrates the added value of FCDO’s investment in RLO which continues to impact the research funding landscape, in addition to direct policy-relevant research on education in a range of low and lower-middle income countries. These contributions not only extend the reach of RLO-funded research but also reinforce its role in shaping global development agendas, ensuring continued return on public investment.
E: RISK

Risks are discussed on a quarterly basis and escalated as necessary. The main programme risks identified during this reporting period are discussed below. The overall programme risk rating is Minor, reflecting that Phase 1 has limited ongoing activities. All risks identified are within FCDO’s risk appetite.
Reputational: Moderate: There is a potential reputational risk for both FCDO and ESRC as the launch of Phase 2 was announced at the grantholders’ workshop in November 2024 but has not since been launched due to the decisions to reduce ODA. This uncertainty could undermine confidence in both organisations as trusted funders and, in turn, has a direct impact on the planned future delivery objectives of the programme. FCDO and ESRC are working together to mitigate this risk through highlighting the programme’s achievements over the last decade and reaffirming our continued commitment to the programme’s goals.
Public Service Delivery & Operations and Policy and Programme Delivery: Moderate. Uncertainty about plans for the extension of the programme until 2032 under Phase 2 affected FCDO and ESRC’s ability to launch Phase 2 ahead of the Phase 1 MoU expiring. This consequently also impacted ESRC’s ability to plan for future spend, as ESRC is a research council that sits under UKRI which is a publicly funded body. In this reporting period we agreed to support additional delivery and funding allocation through Phase 2 as we developed a BCA which was approved and signed; this has now not been taking forward as a result of the ODA cuts. The delivery risk was mitigated temporarily through signing the MoU to extend the programme until March 2026 to allow for the reconciliation of the grants and for the complete closure of all activities for Phase 1.
People: Minor: Although there have been recent changes in personnel, communication between teams has remained strong. The programme benefits from a flexible and well-supported team structure therefore this risk is considered low.
Safeguarding: Minor: The programme remains vigilant due to geopolitical sensitivities across countries where RLO research is conducted. ESRC and FCDO have implemented joint measures to ensure safeguarding compliance, including mandatory reporting and guidance for researchers.
Strategy and Context: Minor: Context related risks included potential unrest and other disruptions at the country and local level where research is taking place, potentially affecting live grant activities. ESRC and FCDO actively monitor operational contexts to ensure ongoing compliance with relevant policies, standards, and safety considerations throughout the lifecycle of their live grants.
Financial and Fiduciary: Minor: Despite budget uncertainty due to reductions in UK ODA spending, existing financial commitments are secure. Controls include regular budget reviews, financial assurance checks, and transparent reporting mechanisms. The risk is actively managed and rated as minor.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

FCDO monitors ESRC’s delivery of RLO through scheduled fortnightly meetings between both programme teams where they discuss the programme’s status and progress, as well as finances and risks. Narrative and finance reports have been received on time each quarter. The costs associated with grants and awards are detailed in these quarterly financial reports and are cross-examined by FCDO before payments are authorised.
The programme budget and forecasts are managed by ESRC. The total RLO programme value of £20m is made up of an overall allocation of £15m from FCDO (75% contribution) and £5m from ESRC (25% contribution). Forecast expenditure for the financial year (FY) 2024-25 was £400,471, whereas actual expenditure for the period was £323,498 which led to a variance of £76,973 (19%) between the forecast and what was spent. Key reasons for the variance include:
[note] The financial data used for this reporting period covers 31 March 2024 - 31 March 2025. Forecast figures for this period are those provided by ESRC in June 2024.
Grantholders’ workshop: Budgeted costs for the grantholders' workshop were increased to include VAT, but this increase was ultimately partially off-set by Travel and Subsistence costs for the event being lower than expected.

Uptake, impact and evaluation activities: There is an underspend on uptake, impact and evaluation activities. FCDO and ESRC have provisionally agreed that this could be used in Phase 2, if the fiscal situation allows.
The programme as a whole currently has a budget underspend of £817,000. A portion of this had been provisionally allocated to the Networking activity, which was scoped out in 2023, but this has been delayed indefinitely whilst plans for Phase 2 have been put on pause.
All communication on finances between FCDO and ESRC have been well managed and all major decisions regarding the RLO budget continue to be made in partnership between the two funders. ESRC continues to provide support to grantholders wherever possible to ensure the effective delivery of projects.
Key programme management activities in this reporting period included the approval of the BCA which reduces the previously approved FCDO ceiling from £12m to £10m and extends the programme to 2032; and drafting a new MoU for the Phase 2 which was then put on hold and replaced with an MoU extension for Phase 1.

G: MONITORING, EVIDENCE AND LEARNING

The AR is FCDO’s primary mechanism to measure progress against logframe indicators over the previous 12 months. FCDO also internally evaluates RLO’s status, as well as FCDO’s and ESRC’s management of the programme, in internal midyear reviews. These meetings are used as opportunities to escalate and seek advice on any emerging or longstanding issues with the programme. Additionally, during this period, FCDO programme team participated in the grantholders workshop which formed part of our ongoing monitoring and oversight responsibilities, giving us the opportunity to observe the progress of funded research first-hand. This enabled FCDO to have direct conversations with RLO researchers and supported the team to assess the relevance, quality, and potential policy impact of the research being undertaken.
Throughout the year, FCDO programme staff regularly meet with the partner to discuss progress. RLO uses existing ESRC mechanisms to monitor and evaluate funded research. Funded RLO projects are required to produce an annual progress report using a template developed specifically for ESRC-FCDO's collaborative programmes. Progress reports allow active grants to report on activities, both completed and planned, and to raise any issues in grant management which can be followed up by ESRC. A shortened report focussing on impact is requested from closed grants for up to five years from the grant’s end date.  The annual report submitted by ESRC has been to a high quality. ESRC continues to manage the programme well, and to respond in a timely way to ad hoc information requests received throughout the year.
The programme evaluation took place from June 2021 to April 2022; the final report was appended to the 2021-22 AR. Findings and recommendations from the programme evaluation were intended to inform the development of Phase 2. ESRC and FCDO are continuing to work together to confirm our strategy for these findings and recommendations now that Phase 2 is currently on hold. FCDO have also taken on board a number of the recommendations in other research programmes run in the Education, Gender and Inclusion portfolio.
[note] https://www.ukri.org/wp-content/uploads/2022/08/ESRC-020822-RLOFinalReport.pdf
Date of last narrative financial report	March 2025 (Q4 workbook)	Date of last audited annual statement	July 2025 / UKRI Annual Report 2024-25

Annexes

Annex A – RLO Research Grants
Annex B – Grantholder’s Workshop
Annex C - RLO Theory of Change
Annex D – Publication outputs reported this period
Annex E– Communication Activities

Annex A– RLO research grants

Call	Grant Reference	Project Title	PI Name	Research Organisation	Country/countries of focus	Current grant status	Start date	Final End Date
Call 1	ES/M004996/1 ES/M004996/2	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	Rebecca Thornton	University of Illinois at Urbana Champaign	Uganda	Closed	01/05/2015	31/12/2015 30/04/2020
Call 1	ES/M005011/1	Constructing a Global Framework for Analysis of Social Exclusion From and Within Learning Systems	Parul Bakhshi	Washington University in St Louis	Afghanistan; India; Dafur; Sierra Leone; Morocco; Tunisia	Closed	01/05/2015	30/04/2016
Call 1	ES/M004740/1	Toward the Development of a Rigorous and Practical Classroom Observation Tool: The Uganda secondary school project	Edward Seidman	New York University	Uganda	Closed	30/04/2015	30/06/2016
Call 1	ES/M004732/1	Promoting Children's Learning Outcomes in Conflict-Affected Countries: Generating, Communicating, and Incorporating Evidence for Impact	John Aber	New York University	Democratic Republic of Congo; Bukavu; South Kivu	Closed	06/04/2015	05/07/2016
Call 1	ES/M005186/1	Literacy development with deaf communities using sign language, peer tuition, and learner-generated online content: sustainable educational innovation	Ulrike Zeshan	University of Central Lancashire	India; Ghana; Uganda	Closed	01/06/2015	31/07/2016
Call 1	ES/M005380/1	Implementing cross-age peer tutoring in the teaching of reading in Kenya	Frank Hardman	University of York	Kenya	Closed	01/06/2015	01/10/2016
Call 1	ES/M005240/1	Transforming the Pedagogy of STEM Subjects	Vanessa Kind	Durham University	Ethiopia	Closed	01/06/2015	30/11/2018
Call 1	ES/M005445/1	Learning outcomes and teacher effectiveness for children facing multiple disadvantages, including those with disabilities: India and Pakistan	Pauline Rose	University of Cambridge	India; Pakistan	Closed	01/07/2015	31/12/2018
Call 1	ES/M005453/1	Improving curriculum and teaching methods to influence policy and increase the quality of ECDE provision for children with disabilities in Malawi.	Paul Lynch	University of Glasgow (formerly at University of Birmingham)	Malawi	Closed	01/06/2015	28/02/2019
Call 1	ES/M005496/1	Pedagogies for Critical Thinking: Innovation and Outcomes in African Higher Education	Tristan McCowan	University College London	Kenya; Ghana; Botswana	Closed	01/04/2015	31/03/2019
Call 1	ES/M004864/1	Examining Effective Teaching in Rural Honduran Secondary Schools	Erin Murphy-Graham	Regents of the Uni California Berkeley	Honduras	Closed	01/07/2015	28/06/2019
Call 2	ES/N010388/1	Improving school governance and learning outcomes at scale: A randomized evaluation of the Madhya Pradesh School Quality Assessment program	Karthik Muralidharan	Institute for Financial Management & Res, India	India	Closed	01/03/2016	31/08/2018
Call 2	ES/N01023X/1	Succeeding Against the Odds: Understanding resilience and exceptionalism in high-functioning township and rural primary schools in South Africa	Servaas van der Berg	Stellenbosch University	South Africa	Closed	19/05/2016	18/11/2018
Call 2	ES/N010205/1	Facilitating Innovative Growth of Low Cost Private Schools: Experimental Evidence from Pakistan	Asim Khwaja	Harvard University	Pakistan	Closed	01/03/2016	28/02/2019
Call 2	ES/N010515/1	AFLA - Assessment for Learning in Africa: Improving Pedagogy and Assessment for Numeracy in Foundation Years.	Therese N. Hopfenbeck	University of Oxford	South Africa; Tanzania	Closed	01/04/2016	30/06/2019
Call 2	ES/N01037X/1	Education systems, aspiration and learning in remote rural settings	Nicola Ansell	Brunel University London	India; Laos; Lesotho	Closed	01/09/2016	30/08/2019
Call 2	ES/N010345/1	Multilingualism and Multiliteracy: Raising learning outcomes in challenging contexts in primary schools across India	Ianthi Maria Tsimpli	University of Cambridge	India	Closed	01/05/2016	31/07/2020
Call 2	ES/N010221/1	Investing in our Future: The Early Childhood Intervention and Parental Involvement in Bangladesh	Asadul Islam	Monash University	Bangladesh	Closed	15/05/2016	14/03/2021
Call 2	ES/N010094/1	Inclusive higher education learning outcomes for rural and township youth: developing a multi-dimensional capabilities-based higher education index	Melanie Walker	University of the Free State	South Africa	Closing	01/09/2016	30/06/2021
Call 3	ES/P006043/1	Partnership Schools for Liberia: Impact on Accountability Mechanisms and Education Outcomes	Justin Sandefur	Innovations for Poverty Action Went through Due Diligence)	Liberia	Closed	16/01/2018	30/06/2020
Call 3	ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	University College London	Malawi; South Africa	Closed	22/01/2018	21/05/2021
Call 3	ES/P005551/1	Improving Learning: Developing Measures of Accountability and Evaluating their Association with Students' Gains in Achievement in Nepal	Dirgha Ghimire	University of Michigan	Nepal	Closed	01/10/2017	30/09/2021
Call 3	ES/P005489/1 ES/P005489/2	Organizational Perspectives on Accountability and Learning (OPAL): School Management Models and the Social Impact of Schooling in Mumbai and Kathmandu	Robin Shields	University of Bristol	India	Closed	02/10/2017	31/10/2019 15/09/2021
Call 3	ES/P005802/1	Making the elementary schooling system in India work for disadvantaged learners: a cross-scalar comparative study of accountability relations	Caroline Dyer	University of Leeds	India	Closed	01/05/2018	30/04/2021
Call 3	ES/P005594/1	Technology, Monitoring and Teacher Support in Niger	Jenny Aker	Tufts University Due Diligence authorised 11/10/2017	Niger	Closed	01/01/2018	31/03/2022
Call 3	ES/P005810/1	Disadvantage and Participation Accountability Processes: Theory and Evidence from School Development and Management Committees in Karnataka, India	Sayantan Ghosal	University of Glasgow	India	Closed	01/03/2018	28/02/2023
Call 3	ES/P005349/1	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	Ricardo Sabates	University of Cambridge	India	Closed	08/01/2018	06/03/2023
Call 3	ES/P005888/1 ES/P005888/2	Accountability, capacity and trust to improve learning outcomes in South Africa; a systems approach	Melanie Ehren	Vrije Universiteit Amsterdam	South Africa	Closed	01/09/2017	01/02/2019 31/07/2022
Call 3	ES/P005799/1	Strengthening schools accountability mechanisms through participation: Addressing education quality and equity in Afghanistan and Pakistan	Jean-Francois Trani	Washington University in St Louis	Afghanistan; Pakistan	Closed	01/01/2018	31/10/2022
Fo F Call 1	ES/P008607/1	Promoting Children's Learning Outcomes in Conflict-Affected Countries: Evidence for Action in Niger	John Aber	New York University	Niger	Closed	01/07/2017	31/12/2019
Fo F Call 1	ES/P008623/1	Peer to Peer Deaf Multiliteracies: research into a sustainable approach to education of Deaf children and young adults in the Global South	Ulrike Zeshan	University of Central Lancashire	India; Ghana; Uganda; Nepal; Rwanda	Closed	01/07/2017	31/12/2020
Fo F Call 4 T1	ES/T000422/1	Application of the Teacher Instructional Practices and Processes System (TIPPS) observation tool in Rural Honduran Secondary Schools	Erin Murphy-Graham	Regents of the Uni California Berkeley	Honduras	Closed	01/08/2019	31/03/2023
Fo F Call 4 T1	ES/T000406/1	Teacher Instructional Practices and Processes System (TIPPS): Cultural extension and testing as a feedback tool to improve pedagogical practices	Edward Seidman	New York University	Honduras	Closed	08/08/2019	30/03/2023
Fo F Call 4 T1	ES/T000392/1	Education Marketplace Platform	Asim Khwaja	Harvard University	Pakistan	Closed	01/06/2019	31/03/2022
Fo F Call 4 T2	ES/T008199/1	South-South collaboration in realising the impacts of Peer-to-Peer Deaf Multiliteracies research in India, Uganda, and Nepal	Ulrike Zeshan	University of Central Lancashire	India, Ghana, Uganda	Closed	01/11/2019	30/06/2021
Fo F Call 4 T2	ES/T008164/1	The Management of Teachers in Primary Schools: Using Phone Calls for Oversight	Jenny Aker	Tufts University	Niger	Closed	03/01/2020	31/03/2022
Fo F Call 4 T2	ES/T007583/1	Reading and socio-emotional skills in challenging school contexts: Evidence from South African primary schools	Servaas van der Berg	Stellenbosch University	South Africa	Closed	17/02/2020	16/02/2022
Fo F Call 4 T3	ES/V001132/1	Solid Foundations, Mother-Tongue Literacy, and the Transition to Adolescence	Rebecca Thornton	Uni of Illinois at Urbana Champaign	Uganda	Closed	28/09/2020	27/09/2022
Fo F Call 4 T3	ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	University College London	Malawi, South Africa	Closed	01/03/2022	31/07/2023
Fo F Call 4 T3	ES/V001140/1	Organizational Perspectives on Accountability and Learning: Cases Highlighting Innovative Practice (OPAL-CHIP)	Robin Shields	University of Bristol	India	Closed	01/01/2021	31/05/2022
Fo F Call 4 T3	ES/V001094/1	Building capacity for critical thinking enhancement in African Higher Education	Tristan McCowan	University College London	Kenya, Botswana, Ghana	Closed	01/01/2021	31/12/2022
Fo F Call 4 T3	ES/V001116/1	Equipping Lesotho's primary school teachers for educating and motivating rural children	Nicola Ansell	Brunel University London	India, Loas, Lesotho	Closed	22/04/2021	21/04/2023
FoF Call 4 T4	ES/X014088/1	Improving learning outcomes in Afghanistan and Pakistan in the midst of COVID-19 through Community based system dynamics and project-based learning	Jean-Francois Trani	Washington University in St Louis	Afghanistan, Pakistan	Active - closing	27/10/2022	26/10/2024
FoF Call 4 T4	ES/X013871/1	Interrupted Learning, Fragile Attendance and 'Out of School' Children in India (ILFA)	Caroline Dyer	University of Leeds	India	Closed	09/02/2023	07/05/2024
FoF Call 4 T4	ES/X014037/1	Supplementing measures of social accountability and enhancing understanding of accountability and students' achievement during the COVID-19 pandemic	Dirgha Ghimire	University of Michigan	Nepal	Closed	01/02/2023	31/01/2024
FoF Call 4 T4	ES/X014118/1	Promoting academic resilience in Nepal, South Africa, and India: A closer look at the role of contextual, student and school-based factors	Andres Sandoval Hernandez	University of Bath	India, South Africa, Nepal	Active - closing	14/04/2023	13/04/2025
FoF Call 4 T4	ES/X013987/1	Teacher accountability to improve learning outcomes; synthesis of 4 RLO-studies	Melanie Ehren	Free (VU) University of Amsterdam	Afghanistan, Honduras, India, Nepal, Pakistan, South Africa	Active	01/04/2023	08/01/2026

Annex B – RLO Grantholder Event
An annual workshop has historically been designed to bring RLO grantholders together, to share learning and explore opportunities for further collaboration. From 2019-2021 the COVID-19 pandemic prevented a programme-led physical meeting of RLO grantholders, replaced instead with a variety of online networking and knowledge exchange events. This included the replacement of a large in-person end of programme workshop, planned to take place in Ethiopia in 2020, by a series of virtual webinars. It was intended that an in-person workshop would be held once travel restrictions had lifted, and to align with the planned launch of a second phase of the RLO programme.
[note] See 2020-21 Annual Report for further details of virtual events.

Mindful of the significant value placed on the workshop by grantholders and the risk of losing the momentum and goodwill previously established within the RLO cohort, in 2023 it was agreed that an independent supplier would be commissioned to develop and facilitate a grantholder event in the following year. In late 2023 ESRC oversaw a competitive procurement process which resulted in the appointment of the Institute of Development Studies (IDS) as delivery partner for the event.
[note] The annual workshop was highlighted by the 2022 programme evaluation as greatly valued by grantholders as an opportunity to meet up, discuss, learn about each other’s research and exchange ideas.

The agenda for the event was designed to address stated objectives around network and relationship-building within the cohort, knowledge exchange (including on gender inclusion and partnership equity), effective communication of findings to non-academic audiences, and ensuring strong representation and leadership within the event from Southern researchers and research partners. The content and format of the event was shaped by the findings of a needs assessment survey conducted in advance by IDS, to ensure participants fed into the session priorities. A steering group of a small sub-set of grantholders was also convened, to help shape and actively co-create elements of the workshop agenda and sessions.

The grantholder event was held on 11-13 November in Nairobi, Kenya, with representatives from ESRC and FCDO in attendance. Each project within the RLO portfolio was invited to nominate two participants, with guidance specifying the inclusion of research colleagues and partners from the Global South, in order to promote Southern participation and leadership. Thirty-six grants (78% of all grants including follow-on projects) were represented at the event, with forty-three participants from twelve different countries (18 participants from the Global South and 25 from the Global North). A further six individuals had planned to attend the event but were prevented from doing so due to unforeseeable circumstances including flight cancellation and visa issues.

Accessibility and inclusion were integral to the design of the event, with provision of sign language interpretation, ad hoc French interpretation and childcare support. The final agenda incorporated multi-modal sessions and group activities (including using games and prompts), subtitles on all presentations and clear principles of engagement for all. This proved successful, allowing two deaf participants to actively contribute throughout all sessions, supported by three sign language interpreters. The emphasis on accessibility and inclusion was cited during and after the event as a distinct benefit, not only by those who were directly supported but also by many other participants. Feedback from participants indicated that such positive practices had allowed for richer discussion across the breadth of the cohort. Inclusion also featured prominently in the key takeaways recorded at the end of the event, including commitments to implement disability inclusiveness in research and to think proactively about inclusion in future research design.

IDS also produced an internal report for ESRC and FCDO after the event to provide an overview of the design and planning process and event delivery, reflect on what worked well, capture lessons learned and provide recommendations for future similar events. The findings of the IDS report will be shared with any future impact and synthesis support facility involved in planning RLO grantholder events, and more broadly with FCDO and ESRC colleagues seeking to undertake similar activities.

As part of the annual reporting process, ESRC also asked grantholders to comment on any specific benefits (to themselves or their colleagues) of attending the event. Feedback was overwhelmingly positive, with many participants citing knowledge exchange (on research outcomes, tools and methods), reconnection and relationship-building across the cohort, and having time to directly engage with the funders as particularly beneficial for ongoing activities and planning future work. Several grantholders referred to specific discussions from the event about potential future collaborations across different research projects, including an edited volume on accountability, and co-submission for further research funding. See Outcome Indicators 1.1 and 1.2 below for more on the benefits of attendance reported by participants.

Agenda for the workshop:
Day 1 focused on reflective and interactive activities. Grantholders explored emerging themes through sessions like “The Tree of RLO” and an interactive poster showcase, engage in collaborative learning with “Knowledge Quest Cards,” and ended the day with a celebration spotlight and forward-looking wrap-up.
Day 2 and Day 3 shifted focus to partnerships, impact, and future research. Day 2 highlighted the role of research in policy and education through storytelling, partnership planning, and a panel on the global education crisis, followed by networking. Day 3 focused on forward planning with sessions on future research priorities, inclusive and transformative themes, and a closing session to capture the collective journey.

Annex C– RLO theory of change
Annex D: Publication outputs reported in this AR period
Award Reference	Article Title	PI	Publication	DOI
ES/M004996/2	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	Rebecca Thorton	Program Scale-up and Sustainability	N/A
ES/M004996/2	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	Rebecca Thornton	Teacher Effectiveness in Africa: Longitudinal and Causal Estimates	N/A
ES/M004996/2	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	Rebecca Thornton	A Meta-Analysis of Heterogeneity in Education Program Impacts	N/A
ES/M004996/2	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	Rebecca Thornton	Reading for Life: Lasting Impacts of a Literacy Intervention in Uganda	N/A
ES/P008623/1	Peer to Peer Deaf Multiliteracies: research into a sustainable approach to education of Deaf children and young adults in the Global South	Ulrike Zeshan	Social Justice through Pedagogies of Multiliteracies	https://doi.org/10.4324/9781003438847
ES/N010345/1	Multilingualism and Multiliteracy: Raising learning outcomes in challenging contexts in primary schools across India	Ianthi Maria Tsimpli	Current Perspectives on Generative SLA - Processing, Influence, and Interfaces - Selected proceedings of the 16th Generative Approaches to Second Language Acquisition Conference	http://dx.doi.org/10.1075/lald.70.15tsi
ES/N010345/1	Multilingualism and Multiliteracy: Raising learning outcomes in challenging contexts in primary schools across India	Ianthi Maria Tsimpli	Effects of Mother Tongue Education and Multilingualism on Reading Skills in the Regional Language and English in India	https://gresis.osc.int//doi/10.60692/hwj8j-tqm06
ES/N01037X/1	Education systems, aspiration and learning in remote rural settings	Nicola Ansell	Rethinking Rural Schooling in Laos From a Deficit Perspective to Patchworked Mobilities, the State, and the Trope of Remoteness	http://dx.doi.org/10.54195/jps.16767
ES/N010094/1	Inclusive higher education learning outcomes for rural and township youth: developing a multi-dimensional capabilities-based higher education index	Melanie Walker	A Reparative Lens for Exploring Youth Aspirations in South African Universities	http://dx.doi.org/10.1080/19452829.2024.2401015
ES/N010345/1	Multilingualism and Multiliteracy: Raising learning outcomes in challenging contexts in primary schools across India	Ianthi Maria Tsimpli	Effects of Mother Tongue Education and Multilingualism on Reading Skills in the Regional Language and English in India	https://gresis.osc.int//doi/10.60692/qs1jh-28315
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Indonesia Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Indonesia-brief-final.2-with-logos-1.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Kenya Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Kenya-Spotlight-Brief_final.3-with-logos.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Sustainability, gender equality and girls' education: Reflections from approaches to MEL (Monitoring, Evaluation and Learning) in Girls' Education Challenge projects in Kenya'	https://www.gendereddata.org/wp-content/uploads/2024/05/AGEE-2024-GEC-Sustainability-working-paper_May-2024_final.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Soft power in complicated and complex education systems: Gender, education and global governance in organisational responses to SDG 4	http://dx.doi.org/10.1007/s11159-024-10098-2
ES/P005349/1	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	Ricardo Sabates	Improving children's foundational learning through community-school participation: Experimental evidence from rural India	http://dx.doi.org/10.1016/j.labeco.2024.102615
ES/P005551/1	Improving Learning: Developing Measures of Accountability and Evaluating their Association with Students' Gains in Achievement in Nepal	Dirgha Ghimire	The relevance of governance, external monitoring, and instructional quality to public-private school differences in student achievement in the Western Chitwan Valley of Nepal: An exploratory analysis	http://dx.doi.org/10.1016/j.ijedudev.2024.103076
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Counting for change in gender and education	https://www.gpekix.org/blog/counting-change-gender-and-education
ES/P005594/1	Technology, Monitoring and Teacher Support in Niger	Jenny Carson Aker	Experimental Evidence on Supporting Teacher Effort and Student Learning using Simple Technologies	nan
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	How To Run a participatory dashboard workshop using the AGEE (Accountability for Gender Equality in Education) Framework	https://www.gendereddata.org/wp-content/uploads/2024/07/How-to-do-an-AGEE-workshop.final_.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	AGEE Dashboards March 2025	https://www.gendereddata.org/dashboards/march-2025-dashboards/
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Technical note to accompany the AGEE Spotlight Briefs	https://www.gendereddata.org/wp-content/uploads/2024/11/Technical-notes-to-accompany-the-AGEE-Spotlight-Briefs.3.pdf
ES/P005349/1	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	Ricardo Sabates	Reflexive approaches to sampling, survey design and implementation: some practical examples from rural India	https://www.repository.cam.ac.uk/handle/1810/375745
ES/P005349/1	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	Ricardo Sabates	Reflexive approaches to sampling, survey design and implementation: some practical examples from rural India	http://dx.doi.org/10.1080/1743727x.2024.2432282
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Malawi Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Malawi-brief-final.5-with-logos.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Gender, and education systems: some reflections on conceptual limits and possibilities from researching Nigerian teacher education	https://www.gendereddata.org/wp-content/uploads/2024/10/Unterhalter-and-North-2024-Working-Paper-3.pdf
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Technical note to accompany the March 2025 AGEE Dashboards	https://www.gendereddata.org/wp-content/uploads/2025/03/Technical-notes-to-accompany-the-AGEE-March-2025-Dashboards.1.pdf
ES/P005799/1	STRENGTHENING SCHOOLS ACCOUNTABILITY MECHANISMS THROUGH PARTICIPATION: ADDRESSING EDUCATION QUALITY AND EQUITY IN AFGHANISTAN AND PAKISTAN	Jean-Francois Trani	What is inclusion? Children perspective on education at primary schools in rural Afghanistan	http://dx.doi.org/10.1177/17454999241292414
ES/P005349/1	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	Ricardo Sabates	Improving children's foundational learning through community-school participation: Experimental evidence from rural India	https://www.repository.cam.ac.uk/handle/1810/373084
ES/P005675/1	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Elaine Unterhalter	Does women's education improve the sex ratio at birth? Gender, agency and sex-selective abortion in South and East Asia: a critical literature review	http://dx.doi.org/10.1016/j.wsif.2024.103050
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Indonesia Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Indonesia-brief-final.2-with-logos-1.pdf
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Kenya Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Kenya-Spotlight-Brief_final.3-with-logos.pdf
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Sustainability, gender equality and girls' education: Reflections from approaches to MEL (Monitoring, Evaluation and Learning) in Girls' Education Challenge projects in Kenya'	https://www.gendereddata.org/wp-content/uploads/2024/05/AGEE-2024-GEC-Sustainability-working-paper_May-2024_final.pdf
ES/T008199/1	South-South collaboration in realising the impacts of Peer-to-Peer Deaf Multiliteracies research in India, Uganda, and Nepal	Ulrike Zeshan	Social Justice through Pedagogies of Multiliteracies	https://doi.org/10.4324/9781003438847
ES/V001132/1	Solid Foundations, Mother-Tongue Literacy, and the Transition to Adolescence	Rebecca Thornton	Program Scale-up and Sustainability	N/A
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Soft power in complicated and complex education systems: Gender, education and global governance in organisational responses to SDG 4	http://dx.doi.org/10.1007/s11159-024-10098-2
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Counting for change in gender and education	https://www.gpekix.org/blog/counting-change-gender-and-education
ES/X013987/1	Teacher accountability to improve learning outcomes; synthesis of 4 RLO-studies	Melanie Ehren	What is inclusion? Children perspective on education at primary schools in rural Afghanistan	http://dx.doi.org/10.1177/17454999241292414
ES/X014088/1	Improving learning outcomes in Afghanistan and Pakistan in the midst of COVID-19 through Community based system dynamics and project-based learning	Jean-Francois Trani	A child-centred care approach to the learning process: Lessons learned from a participatory intervention in primary schools in Afghanistan and Pakistan	N/A
ES/T008164/1	The Management of Teachers in Primary Schools: Using Phone Calls for Oversight	Jenny Carson Aker	Experimental Evidence on Supporting Teacher Effort and Student Learning using Simple Technologies	N/A
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	How To Run a participatory dashboard workshop using the AGEE (Accountability for Gender Equality in Education) Framework	https://www.gendereddata.org/wp-content/uploads/2024/07/How-to-do-an-AGEE-workshop.final_.pdf
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	AGEE Dashboards March 2025	https://www.gendereddata.org/dashboards/march-2025-dashboards/
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Technical note to accompany the AGEE Spotlight Briefs	https://www.gendereddata.org/wp-content/uploads/2024/11/Technical-notes-to-accompany-the-AGEE-Spotlight-Briefs.3.pdf
ES/V001132/1	Solid Foundations, Mother-Tongue Literacy, and the Transition to Adolescence	Rebecca Thornton	Teacher Effectiveness in Africa: Longitudinal and Causal Estimates	N/A
ES/V001132/1	Solid Foundations, Mother-Tongue Literacy, and the Transition to Adolescence	Rebecca Thornton	A Meta-Analysis of Heterogeneity in Education Program Impacts	N/A
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Malawi Spotlight Brief	https://www.gendereddata.org/wp-content/uploads/2025/01/Malawi-brief-final.5-with-logos.pdf
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Technical note to accompany the March 2025 AGEE Dashboards	https://www.gendereddata.org/wp-content/uploads/2025/03/Technical-notes-to-accompany-the-AGEE-March-2025-Dashboards.1.pdf
ES/X013987/1	Teacher accountability to improve learning outcomes; synthesis of 4 RLO-studies	Melanie Ehren	From experience to actions for justice: learners' views on epistemic, environmental and transitional justice in Nepal, Peru and Uganda	http://dx.doi.org/10.1332/27523349y2024d000000011
ES/V001132/1	Solid Foundations, Mother-Tongue Literacy, and the Transition to Adolescence	Rebecca Thornton	Reading for Life: Lasting Impacts of a Literacy Intervention in Uganda	N/A
ES/V001086/1	Accountability for Gender Equality in Education - Statistical Expansion	Elaine Unterhalter	Does women's education improve the sex ratio at birth? Gender, agency and sex-selective abortion in South and East Asia: a critical literature review	http://dx.doi.org/10.1016/j.wsif.2024.103050
ES/X013987/1	Teacher accountability to improve learning outcomes; synthesis of 4 RLO-studies	Melanie Ehren	Global governance of education: The Sustainable Development Goals as a product and mechanism?	http://dx.doi.org/10.1007/s11159-024-10108-3

Annex E: Communication activities
The Impact Initiative for International Development Research, commissioned to increase the uptake and impact of RLO funded research, came to an end in June 2021 following a short time-only extension to its contract. As described previously, a dedicated synthesis support facility has not been in place since March 2019, following the end of the PRL and the unsuccessful Synthesis Initiative call held later that year. A dedicated facility to deliver combined support for impact and synthesis will be commissioned to support any second phase of the RLO programme.

In the absence of a dedicated support facility, ESRC and FCDO developed an interim light-touch communications plan to expand awareness of RLO research and to amplify dissemination efforts of RLO grantholders. Plans have been refined in line with the ongoing advice and experience of the UKRI Communications and ESRC Engagement teams. Planned and completed activities for this reporting year include:
Four short impact films to promote specific examples of impact and influence catalysed and achieved by RLO projects over the last decade. It is intended that the films will be used:
  - by grantholders to promote their findings, leverage further funding and engage with academics, policymakers and other stakeholders.
  - By ESRC and FCDO for future comms work around featured grants and any potential future second phase of the programme.
  - By ESRC and FCDO as evidence of the value of supporting ODA/international development/education research, for internal case-building for future funding.
Drawing on experience of work to commission impact films for the ESRC Celebrating Impact Prize, ESRC led a procurement process in late 2024 to secure a supplier to produce the RLO films. Following a competitive process, Cass Productions were awarded the contract. RLO grantholders were invited to submit expressions of interest to participate in the activity, with four projects ultimately selected. These projects provide compelling examples of the conceptual and instrumental impact which has been delivered through the RLO programme across a breadth of countries in the Global South. The filming and production process began in February 2025; it is anticipated that all four films will be completed by July 2025.
Once finalised the films will be added to the UKRI for researcher YouTube account and ESRC RLO webpage. Links will also be forwarded to film participants, to be shared with colleagues and stakeholders. Project Leads have agreed to produce LinkedIn articles to promote the films, which will in turn be promoted by the ESRC LinkedIn account. The films will also be highlighted in the ESRC LinkedIn newsletter (9k+ subscribers) and the UKRI Headlines and Highlights newsletter (25k+ subscribers). Two films (first and second) were uploaded onto YouTube in early August.
Costs for this activity will be met through the RLO budget line for uptake, impact and evaluation activities.
1. Blog pieces and accompanying infographics were co-produced by IDS and RLO grantholders following the RLO grantholder event held in November 2024 (see below for details of the event). The three blog pieces focussed on:
  1. Summary highlights from the Panel discussion at the grantholder event, including key observations on disability and inclusion, how to promote learning, teacher development, the empowerment of communities and parents, and future priorities. Published November 2024.
  2. Equitable research partnerships – reflecting on challenges in the promotion of more equitable research for global change. Published March 2025.
  3. Disability and inclusion – presenting five critical strategies uncovered by RLO research, which offer an approach to inclusive, equitable and effective educational systems. Published April 2025 (to coincide with the Global Disability Summit).
All three blog pieces and associated infographics were promoted by IDS via LinkedIn and shared with participants of the grantholder event.
An article for publication on Medium[1] highlighting the specific ways in which RLO research is helping to improve learning outcomes for children in the Global South and, more broadly, to increase public understanding of the value of international development research. Publication of this article has been delayed in order to include links to the outputs arising from the grantholder event and forthcoming impact films.

More generally, over the course of the year RLO grantholders continued to be encouraged to make use of the ESRC Impact Toolkit and to share details of their plans to promote RLO project work and outcomes, tagging ESRC and UKRI on any social media activity, so that ESRC, UKRI and FCDO Communications colleagues can amplify promotional material.