# Annual Review 2024/25

Title: Strategic Partnership on Agriculture and Food Systems for Nutrition
Programme Value £ (full life): £35 million (originally £20 million; business case addendum approved on 20 March 2020)		Review date: 6 March 2025
Programme Code: 204420	AMP start date: / 13 January 2015	AMP end date: 31 March 2026 (previously 30 June 2024; extended with the business case addendum approved on 20 March 2020, NCE approved in Dec 2024)

Summary of Programme Performance

Year	2015	2016	2017	2018	2019	2020	2021	22/23	23/24	24/25
Overall Output Score	A	A	A	A	A	A	A	A	A	A
Risk Rating	Minor	Minor	Minor	Minor	Minor	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-204420
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204420

A. SUMMARY AND OVERVIEW

Undernutrition remains one of the world’s greatest human and economic development challenges, exacerbated by Covid, climate change and conflict. It is projected that almost 600 million people will be chronically undernourished in 2030. About 2.4 billion people – were moderately or severely food insecure in 2022, of which about 900 million were severely food insecure. Worldwide, food insecurity disproportionately affects women and people living in rural areas. More than 2.8 billion people in the world were unable to afford a healthy diet in 2022. (SOFI, 2024)

At the other end of the spectrum, overweight and obesity is an increasing global problem leading to significant increases in the global burden of disease from many non-communicable diseases including cardiovascular disease, type II diabetes and cancer (FAO 2013). Every year around the world, over 420,000 people die, and some 600 million people fall ill after eating contaminated food. Foodborne hazards are known to cause over 200 acute and chronic diseases. In addition to these health effects, undernutrition costs Africa and Asia 11% of GDP year on year and reduces people’s lifetime earnings by 10% on average.

Agriculture and food systems – defined as the production, marketing, transformation and purchase of food, and the consumer practices, resources and institutions involved in these processes – play an integral role in multiple nutritional outcomes. Agriculture plays a key role not only in the production of food but also in income generation at the household and national level. However, agriculture also carries risks to nutrition and health outcomes, for example, through zoonotic, foodborne and other agriculture-related diseases, through the impact of agriculture on women’s workloads and time for childcare and feeding, and through the impact of agriculture on major environmental determinants of health including climate, groundwater availability, air quality and biodiversity.
[note] Global Panel, 2015
[note] GF and DFID, 2016 – Agriculture for Improved Nutrition: A Future Research Agenda

The gender dimension of undernutrition is a critical part of the problem and a strong entry point for solutions. Women that are undernourished give birth to children that are more likely to be stunted by the age of 5. There is also a considerable gap between genders in agriculture productivity and agriculture income. Tackling gender inequality is essential to break this inter-generational cycle of undernutrition.

This programme is a large-scale strategic research partnership between FCDO and the Gates Foundation (GF) on agriculture and food systems for nutrition, aimed at:
1. improving the impact of agricultural interventions on the food and nutrition security of the poor;
2. improving food safety and reducing the burden of foodborne disease in low- and middle-income countries (LMICs); and
3. facilitating healthier, safer, more nutritious food choices among low-income consumers in LMICs, in the context of climate change and rapidly changing global food systems.

The programme focuses on improving the food and nutrition security of children under 5 years old and pregnant and breast-feeding mothers – nutritionally vulnerable groups among whom undernutrition rates remain stubbornly high in many LMICs. The programme has been jointly designed, funded and directed by FCDO and GF. In addition to co-funding, GF provides significant technical and grant management expertise, and manages the individual projects which comprise the portfolio on behalf of both funders, without charging any management fee or overhead to FCDO. FCDO and GF have established a strong partnership in food systems research through this programme, which is supported by a highly effective, technically expert, and collaborative team at GF.

Current active grants in this business case:

Output 1	Budget	Dates	Geography	Lead partner
Indian Food Systems for Improved Nutrition (INFUSION)	GF: $4,999,105 / FCDO: $2,800,000	Nov 2022 – Nov 2027	India (with wider research applications for LMICs)	University of Sheffield
Innovative solutions to address food loss and increase access (Nutrisave)	GF: $2,182,048 / FCDO: $1,000,000	Nov 2022 – Nov 2025 (NCE expected)	Kenya	Technoserve
Output 2	Budget	Dates
All projects under this output are now closed, however lessons are included under Output 2 below, and a new food safety grant is in development, which will be reported under this output in the next annual review.
Output 3	Budget	Dates
Five projects were closed before the last annual review and are no longer included in this output. This output continues to report on Food Prices for Nutrition and the new More Milk Phase 2 that was launched in this period.
Food Prices for Nutrition	GF: $2,299,527 / FCDO: $1,568,000	Oct 2020 – Aug 2025	Global with country focus in Ethiopia, Ghana, Malawi, Bangladesh, Nigeria, Pakistan, Tanzania	Tufts University
More Milk Phase 2	GF: $3,902,935 / FCDO: $1,500,000	Sep 2024 – Aug 2028	Kenya	International Livestock Research Institute

Summary supporting narrative for the overall score in this review

This programme has received an overall ‘A’ grading for this reporting period. The portfolio continues to deliver relevant and quality research results and demonstrates the value of strategic partnership between FCDO and GF. The programme is delivering a significant body of evidence, particularly on the three priority areas – 1) action research to improve access and affordability of healthy diets, 2) reducing the burden of food borne disease, and 3) generating data and evidence to inform policies. Given the evolving portfolio, outputs have been updated and adjusted accordingly. All outputs have scored ‘A’ and have or are on track to deliver milestones and outcomes.

The outputs in this annual review reflect results in this reporting period, rather than cumulative over the lifespan of the programme. Although this annual review focuses on achievements in this last year, the programme PCR will synthesise the full body of evidence and related impacts generated over the lifetime of the project.

Progress throughout the duration of the programme

The intended outcomes of this programme in the Business Case is for FCDO and GF to deliver a body of evidence that would inform actions to deliver equitable access to safe, nutritious, and affordable diets year-round, looking across the entire food chain—from how food is produced to how it is stored, processed, purchased, and consumed. This work looks to diversify and promote efficiencies across food systems to reduce losses, enhance resilience, improve safety and generate demand for nutritious foods. Specifically, it sets out to improve:
- The availability of enhanced evidence bases on agricultural intervention and policies on health and nutrition outcomes.
- The adoption of tools and technologies as a result of programmes developed under new FCDO and GF co-investments under this programme.

To date this programme has contributed to generating:
- New evidence on the drivers of food choices among poor and low-income consumers in Africa and South Asia (programme now completed, previously reported under output 1).
  - Key findings: available here and here.
- New evidence and testing of interventions to tackle foodborne disease in low- and middle-income contexts to ensure food safety (now completed, reported under output 2 in the 23/24 Annual Review).
  - Key findings: In 2024, FCDO and GF commissioned a synthesis of this portfolio which will be available ahead of the PCR. Results have been disseminated with the technical community through publications and conferences (e.g. ANH Academy Week).
- Impact assessments of agriculture and nutrition policies and interventions, generating rigorous, policy-relevant evidence through high quality trial and study designs (mostly now completed, previously reported under output 3).
  - Key findings: Results and findings have been reported in previous annual reviews. Actions informed by two of these projects (Food Prices for Nutrition and More Milk) are being taken up and scaled drawing on our successful investments to date. FCDO and GF will synthesise the closed projects in this portfolio ahead of the PCR. Results have been disseminated with the technical community through publications and conferences (e.g. ANH Academy Week).

Progress in this reporting period (24/25)
The business case built in agility to invest in new research areas in response to ongoing portfolio reviews with GF. The programme has continuously evolved to build on the evidence generated in these three portfolios in close collaboration with GF. The remaining grants that will be funded in this programme and reported against in the final annual reviews are building on the lessons and knowledge generated from the closed portfolios. The active programmes under this programme are now:
- Output 1 - Intervention research and scaling:
  - Despite some delays, INFUSION (Output 1.1) has made good progress and will launch its first market pilot for nutritious foods in March 2025.
  - Although it was also delayed in its first year, Nutrisave (Output 1.2) has progressed well in this reporting period by generating and synthesising research on fruit and vegetable supply and demand for low-income consumers, and the project is now ready to start piloting interventions in 2025 to increase access and affordability of healthy foods for poor communities.
- Output 2 – Food safety: Now that the portfolio of six research projects have closed (in the last reporting period), this reporting period focused on commissioning lessons learned from this portfolio and using this evidence to develop a new research agenda on food safety in Ethiopia. The new proposed project will build on the successful body of evidence generated by this co-funded portfolio with a focus on Ethiopia.
- Output 3 – Scaling impact of nutritious food systems data and interventions: This output is now made up of two active grants where small research projects have now scaled to generate impact, with engagement from other partners.
  - Food Prices for Nutrition (Output 3.1) has demonstrated significant impact as the key metric on the Cost and Affordability of Healthy Diet (CoAHD) metric generated by the project has transformed the way policymakers understand how many people can access a healthy diet around the world. The metric is now embedded in the global flagship FAO SOFI report and increasingly taken up by LMIC governments (see highlight example below).
  - This year also saw the development and launch of Phase 2 of the More Milk project to improve the availability and accessibility of safe, affordable and quality milk to consumers in Kenya. By FCDO and GF demonstrating the viability of interventions that support this outcome in Phase 1, the Kenya Dairy Board has now come on board for Phase 2 to take these to interventions to scale and ensure they can continue sustainably through government support. This is a strong example of impact where donors can use project research funding to demonstrate the case and viability of interventions that can then be scaled, institutionalised and sustained by policymakers.

Key lessons and highlights from this reporting period include:
- Development of a food safety surveillance system in Ethiopia: A new investment is being developed on food safety surveillance in Ethiopia, building on the portfolio of food safety investments under Output 2 (all now closed) and in response to the Government of Ethiopia’s (GoE) commitment to food safety. The portfolio revealed the health and economic impacts of foodborne diseases in Ethiopia, as well as the challenges and opportunities for improving food safety in the country. The research was presented at a conference in Addis Ababa in October 2023. During the conference, the Ethiopian National Steering Committee for One Health launched the One Health National Food Safety Technical Working Group to exchange information on food safety in the country and discuss the evidence that informs decisions to improve food safety. The new project will directly contribute to these ambitions by working with key stakeholders, including the GoE to test and scale surveillance of foodborne disease burdens.
- Cost and Affordability of a Healthy Diet (CoAHD) and associated metrics have had rapid and significant uptake and become a standard way of summarising global food prices, which allows countries and global policymakers to understand and address drivers of nutrition insecurity. The importance of this metric is demonstrated by its adoption by the FAO and the World Bank as a key food security metric. In early 2024, Nigeria became the first country to formally adopt the metric in national food price monitoring– other countries are set to follow. This is a key step for countries to understand and tackle the barriers to affordability of healthy diets. In August 2024, the Cost of a Healthy Diet in Nigeria was leveraged to raise the minimum wage, to more than double what it had been. The project is now working with other national governments to build on this momentum.
- Engaging Kenya Dairy Board to scale More Milk interventions: The transition to Phase 2 with collaboration from the Kenya Dairy Board is a strong example of how donors can use project research funding to demonstrate the case and viability of interventions that can then be scaled, institutionalised and sustained by policymakers.

[To reflect this evolving portfolio, the weighting of the outputs was adjusted in this reporting period:
- Output 1: 20% to 30%
- Output 2: 30%
- Output 3: 50% to 40%]

Recommendations for the year ahead: Recommendations are included under each output.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change for this programme is presented visually on page 19 of the business case (2015). The theory of change is supplemented by detailed results frameworks, developed by co-funded grantees. Compared to nutrition-specific interventions, there is a dearth of evidence around the impact of agricultural policies and programmes on nutritional outcomes. Evidence is needed to guide policymakers and practitioners on cost-effective and scalable interventions with positive impacts for the food and nutrition security of the poor. The investments in this portfolio represent a portfolio of high-quality research investments which are contributing to filling these critical evidence gaps in nutrition-sensitive agriculture research. Grantees submit annual progress reports against these results frameworks to GF. There has been no material change to the assumptions underpinning the programme’s theory of change during the reporting period.

Gender: This programme is compliant with the 2014 Gender Equality Act. The funded research prioritises the food and nutrition security of pregnant and breastfeeding mothers, and also investigates gendered dimensions of agriculture and nutrition, including women’s workloads and time for childcare and child feeding. The programme also considers broader gender impacts, such as female empowerment, for example through the integration into the More Milk study of the intervention on women-in-business empowerment, as this trial represents a unique opportunity to assess the effect of a training intervention on women's empowerment in an entrepreneur population operating in informal markets. The GF team have gender specialists within the team who support in integrating gender into the design of new grants. The INFUSION and More Milk 2 projects also have strong gender components.

Climate: Nutrition is intricately linked with climate change. Climate change can impact the nutritional value of the crops themselves, can reduce availability, and raise prices. This can have particular impacts on low-income consumers and consumers who already have limited access to diverse diets. On the flipside, food systems and choices can impact on emissions. It is therefore critical to support nutritious food systems where everyone can have an adequate, healthy diet with nutritious foods that are widely available, affordable, safe and demanded, and that the food system is resilient to economic and environmental volatility and does not contribute to environmental pressure and climate change. This programme contributes towards this goal, building adaptation and resilience in targeted groups.

Progress towards expected outcomes and impact, and justification to continue
FCDO and GF have a longstanding partnership and portfolio of co-investments in strengthening the evidence on agriculture and nutrition stemming back to 2011. This has enabled a rapid evolution of the evidence base from a situation where there was little evidence of what agricultural interventions could be used to improve nutrition to a considerable body of work in this area, and emerging work on how the broader food system shapes nutritious healthy diets.

This programme has made an important contribution to this agenda, the collaboration and co-investments under this programme demonstrate strong evidence of impact. The projects have been instrumental in driving a rapid shift and exponential growth in the evidence – and its quality – over the last decade. This has contributed to a greater understanding of what works to increase the affordability and availability of safe and nutritious diets. The scale of the challenge has grown, compounded by increasingly complex trade-offs between economic, social, environmental and health/nutrition outcomes. The programme has adapted to build on the evidence generated, and to respond to this evolving context. This annual review highlights the new projects that FCDO is now funding with GF on key research questions and to test new interventions.

The programme should continue as the upcoming year will focus on continuing to build the pipeline of co-funded work with the Gates Foundation, particularly on affordability and food safety. This will link closely to the new 400196 business case: “Nutritious Food Systems: equitable science partnership to strengthen nutrition for women and girls” and we will draw out lessons and evidence across these two programmes. The projects supported through this programme continue to represent strong value for money for FCDO and are aligned with FCDO priorities. This programme specifically delivers against all three components of FCDO’s commitment to mainstreaming nutrition across its ODA portfolio in line with N4G Tokyo 2021 commitments.

## C. DETAILED OUTPUT SCORING

Output Title	Intervention research and scaling to increase consumption of nutritious foods in Africa and South Asia
Output number:		1	Output Score:	A
Impact weighting:		30%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
INFUSION project	On track with milestones in the joint results tracker	Met: Milestones for this reporting period: / Novel data and understanding of local food environments – Met / Novel spatiotemporal data and classification of markets – Met / Evidence on coexisting hotspots of multidimensional food market accessibility – Met / Evidence on inequalities in market access – Ongoing / Proposal for implementation of health markets (Didi Haats) – Met / Proposal for Nutrition Security Fund – Met (but likely to be updated in 2025)
NutriSave project	On track with milestones in the joint results tracker	Met: Milestones for this reporting period: / New solutions identified, ready for prototyping and testing – Met (with stage gate planned for March 25) / Assess existing solutions to inform selection (literature review and primary data) – Met / Tomate value chains business case developed and validated – Met

This output scores an A: These two projects are testing interventions to increase the consumption of nutrient-dense foods in India and Kenya in order to inform policy and programmes in other LMICs. Nutrisave remains agile as the research and testing phase informs the future of the project. Infusion has made strong progress, but several external factors have delayed their timelines (see below). Both of these projects will need close oversight in the coming months to ensure they stay on track. Stage gate meetings are planned for both projects in March 2025. There were no changes to this output in this reporting period, other than the weighting increasing from 20 to 30%.

Indian Food Systems for Improved Nutrition (INFUSION): A Policy Support Research Facility
Brief description: This research programme will generate evidence for market-level interventions that increase the consumption of more nutritious diets. This unique research project, delivered through a science and policy partnership with the Government of India, will inform decision-making and wider applications in India and other LMICs.
Progress update: The project is currently ~6 months behind schedule, partly due to impact of the elections, and indicating a significant delay in achieving the set milestones.
Key highlights: Major completed activities and notable achievements in the last year include:
- Good progress in Workstream 1, which is focused on market level and household/consumer level data collection. High frequency price monitoring for nutrient dense foods has been underway since July 2024 in 250 markets and is on track for completion by July 2025. This research will now be used to inform the design of interventions.
- Signing of the MOU with Jeevika (Gov of Bihar) following many months of discussions and modifications. This was achieved following a strong business case that was a continuation of a robust co-design process. This has been particularly evident in the Didi Haat workstream as demonstrated by pilot co-development with Jeevika and a design firm leading a co-design process with the local community to incorporate their views and ensure ownership of the intervention. The first Didi Haat (women-run market for nutritious foods) is expected to be launched in March 2025: https://patnapress.com/women-led-didi-haat-to-open-in-nalandas-telhara-designed-by-uk-institutes/

Despite this progress, challenges remain that the team will need to address in the next few months:
- The Nutrition Security Fund workstream faces significant changes in scope due to both the sunsetting of the fund and a lack of interest on the original NSF design by Jeevika. Alternative options are being explored and will be presented to FCDO and GF in March 2025.
- Similarly, the proposed work in Odisha has not progressed due to the focus on the Bihar components. Discussions with the team and recent reporting suggests that the scope might change. This will be discussed and a workplan agreed in the stage gate meeting in March 2025.

Given these challenges, the stage gate meeting in March 2025 will be a crucial milestone for FCDO and the GF to engage with the whole INFUSION team and agree the workplan for the next reporting period. We will continue to closely monitor progress during our monthly meetings.

Innovative solutions to address food loss and increase access (NutriSave)
Brief description: NutriSave will work to decrease fruit and vegetable loss and waste through innovative solutions that aim to improve nutrition for low-income consumers, particularly women, in Kenya.
Progress update:
- At the conclusion of Year 1, four solution concepts were presented at the stage gate meeting to discuss whether to proceed with piloting. Juice with a higher percentage of mango pulp concept was deprioritised due to concerns about nutrition while the African leafy vegetable blended flour was deprioritised due to little or no commercial viability results. A digital B2B marketplace concept was pushed into Year 2 for further assessment while the concept linking markets and processors for nutritious tomato paste was advanced to a higher fidelity prototype to test its viability assumptions further and get learnings from African tomato-producing countries.
- In Year 1, NutriSave initiated a Human-Centered Design (HCD) process to address food loss and waste challenges. Through comprehensive value chain analyses, the team systematically identified and explored potential interventions to enhance fruit and vegetable accessibility. This strategic approach laid the groundwork for targeted solution development.
- Building on this foundation, in 2024 (Year 2), NutriSave leveraged evidence-based research to identify interventions that reduce food loss and waste and increase access and consumption of fruits and vegetables. In addition, the team conducted extensive landscaping for solutions, carefully identifying potential partners with business models aligned to NutriSave’s objective. These solutions will be presented during a stage gate meeting in March 2025 for selection and progressing to piloting. Finally, they validated the tomato business case which will progress into 2025.

Key highlights:
- Literature review: NutriSave conducted a literature review to identify interventions that address food loss and waste for fruits and vegetables while improving access for low-income consumers (LICs). The research encompassed both demand and supply aspects.
- Primary research explored specific questions: On the demand side, they investigated low-income consumers' F&V prioritisation, effects of seasonal and distribution variations on decision-making, and willingness to pay for redirected F&V. Supply-side research examined supply chain inefficiencies and potential intervention points, viable alternative market channels for reaching low-income communities, and supply actors' willingness to include redirected F&V in operations.
- Intervention testing: Through these studies, NutriSave aimed to understand and identify demand and supply-side barriers and levers of F&V access, choice and consumption patterns among low-income consumers in urban, rural and peri-urban Kenya. The research sought to generate contextual learning through design, testing, and evaluation of potential project interventions that address F&V loss and waste while improving F&V access and consumption. The research identified 27 unique interventions requiring further assessment/prototyping decisions. These have now been prioritised and shortlisted and in the next 6 months, the NutriSave team will apply a Human-Centred Design (HCD) Framework to rapidly test up to five prioritised interventions. This process will involve strategic collaboration with at least five private sector partners who possess the necessary expertise, skills, and motivation to pilot and potentially scale these interventions.

Recommendations for the year ahead
- FCDO and GF to use the INFUSION stage gate meeting to agree a workplan and review the scope of the project given the changing external environment. [Timing: By April 2025]
- FCDO and GF to use the Nutrisave stage gate meeting to review the proposed pilot interventions and agree which ones to take forward in 2025. [Timing: By April 2025]

Output Title	Testing of interventions to tackle foodborne disease in low- and middle-income contexts
Output number:		2	Output Score:	A
Impact weighting:		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of new research grants on food safety	On track with milestones in the joint results tracker	Met: / 6 grants completed / lessons learned commissioned / work underway to design new research in Ethiopia to deliver a food safety surveillance system to understand the burden of foodborne disease and support response
Number of peer-reviewed publications on food safety in high quality journals	On track with milestones in the joint results tracker	Met: / 42+ papers published to date, and some still in the pipeline for publication.

This output scores an A. Output 2 was a portfolio of six research grants generating new evidence in an area identified as a major evidence gap.. GF and FCDO invested in filling a major evidence gap on the impacts of foodborne disease and feasible approaches to increase food safety in LMICs. These projects are now completed and lessons from this portfolio are informing future research agendas on food safety. Findings from a number of the projects have been taken up to inform policy - for example, this work has led to the development of compulsory Ethiopian standards for four dairy products, and the inclusion of milk safety and hygiene in the Ministry of Agriculture’s National Dairy Development Strategy 2022-2023. In addition, One Health Advisory Groups were set up in multiple countries as a result of this work, and, in Ethiopia, risk-ranking and prioritisation exercises were undertaken to inform the design of intervention food safety strategies.
[note] The aims, focus countries and status updates of each of all rounds of food safety studies can be found in Annex B.

Currently, FCDO and GF are co-developing a proposal for a food safety surveillance system in Ethiopia. Foodborne Disease (FBD) surveillance systems are foundational for detecting, responding to, and preventing FBDs, building on the findings of this evidence case. They allow public health and food systems actors to rapidly detect and control outbreaks, identify high-risk foods and pathogens, monitor trends in burden of FBDs, and inform prevention efforts by understanding the causes and sources of contamination. Modified transmission and contamination pathways due to climate change necessitate enhanced monitoring and diagnostic capacities in order to improve preparedness and response. This work is being developed in Ethiopia in part because of the Government of Ethiopia’s endorsement of a 5-year Food Safety Master Plan in May 2024, which includes a strategic objective dedicated to strengthening monitoring, surveillance and emergency preparedness response systems for food safety hazards, risks and FBD. Ethiopia is one of the first African countries to develop such a comprehensive food safety plan and our ambition to support a sustainable surveillance system supports current government momentum to address the issue of food safety.

Although the previous grants were closed before the last annual review, below are some examples of findings and lessons that should inform the future research agenda. The investments aimed to achieve a diverse range of objectives to strengthen food safety through three key project activities:
1. Gathering data to document incidence, size and scale of foodborne disease.
2. Testing interventions to understand critical points along the value chain for preventing and controlling food contamination.
3. Policy-level engagement to build and strengthen food safety systems.
This was achieved through:
- Quantitative assessments: dynamic modelling, population-based surveys and time series studies were conducted to understand the burden of FBD and transmission by specific pathogens on poultry, dairy, and vegetable value chains. Furthermore, secondary sources like health surveillance data, national databases and literature reviewed were done to assess and leverage available data.
- Qualitative assessments: interviews, assessments and focus groups were conducted to better understand and analyse food and dairy value chains.
Key lessons learned that will inform the new grant include:
- Research-policy nexus needs to be considered from project inception and strengthened throughout: For example, while the MoreMilk project did not achieve its project objective of reducing milk contamination, it successfully got the Kenya Dairy Board to come on board to scale interventions for milk handling in Phase 2 based on the feedback from the scheme (See Output 3.2 for more detail).
  - A new project developing a surveillance system will crucially need to engage with the government and key stakeholders to ensure sustainability and scalability.
- Building and strengthening in-country capacity contributes to sustainability of project objectives.
  - A new project should be led by a local partner to ensure we draw on local expertise and build capacity that can sustain a system beyond the lifetime of the grant.
- Supply and demand approaches are crucial for tackling food safety challenges. For example, supply chain delays and disruptions , and insufficient consumer awareness of microbiological hazards can increase FBD risks.
  - A new project should ensure that responses and interventions consider both supply and demand challenges.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
These projects are now closed. FCDO and GF are working together to explore the design of follow-on work, building on the success in Ethiopia for driving food safety improvements and surveillance.

Recommendations for the year ahead

FCDO and GF should continue to work together to develop the new project proposal in Ethiopia to improve surveillance and response to foodborne diseases, in order to begin implementation in the upcoming reporting period. [Timing: By June 2025]

Output Title	Scaling impact of nutritious food systems data and interventions
Output number:		3	Output Score:	A
Impact weighting:		40%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
Food Prices for Nutrition project	On track with milestones in the joint results tracker	Met : Progress against each project objective detailed below.
More Milk 2 project	On track with milestones in the joint results tracker	N/A: / Project successfully launched in January 2025:Progress will be reported in the next annual review. Key updates provided below.

This output scores an A. Food Prices for Nutrition continues to demonstrate significant impact with key metrics now embedded in the global flagship FAO SOFI report and increasingly taken up by LMIC governments, and will continue beyond this reporting period, with discussions ongoing about a future phase. This year also saw the development and launch of Phase 2 of the More Milk project, which will focus on scaling and sustaining the interventions tested in Phase 1, now with collaboration from the Kenya Dairy Board.

Changes to this output in this reporting period include:
- Output indicators updated to reflect the closure of five projects in the last reporting period, and the addition of the new More Milk Phase 2 project
- Changed weighting from 50 to 40%

Food Prices for Nutrition (FPN)
Brief description: Food Prices for Nutrition provides spatial and temporal evidence on the costs of a healthy diet and market price fluctuations of key food products globally and will work with governments in sub-Saharan Africa and South Asia to analyse the impact of potential policy and programme actions on the affordability of a nutritious diet.
Progress update: The project has made good progress in this reporting period. As we move towards the end of the project, FCDO and the Foundation have started discussions on follow-on activities at the end of the current grant. The aim is for the global metrics to be sustainably institutionalised and for FCDO and GF to provide some continued support to countries to estimate and publish the cost of a healthy diet and start estimating affordability.

Objective 1: Support use of the metrics
- The Tufts team released an updated software toolkit (now version 7.0) based on work with national user groups to provide instruction to country users on the collection and analysis of their own food price data, with added new features for food matching, data visualisation and analysis of results.
- The World Bank also developed a new online E-course on the collection and analysis of food price data for healthy diets: Food Prices for Nutrition: Cost and Affordability of a Healthy Diet and other Indicators
- Significant stakeholder engagement, culminating in the project holding a stakeholder and multi-country workshop in October 2024. This brought together representatives of 6 country governments, FAO, and the World Bank to share country experiences in data collection, food matching, and diet cost calculation and discuss a vision for sustaining project activities in the long-run.
- Demand continues to grow for the metrics. During this workshop, demand from Grenada led to new work being funded by FAO. A key question for the coming months will be to ensure that technical assistance to existing and new countries can be provided past the end of the project.

Objective 2: Build a global system for monitoring food prices for nutrition
FAO and the World Bank jointly released updated global monitoring results for the Cost and Affordability of a Healthy Diet (CoAHD), based on new price data and a new method to compute affordability. Results are now published in the joint FAO, IFAD, UNICEF, WFP and WHO flagship report on the State of Food Security and Nutrition in the World, as well as the World Bank’s Food Prices for Nutrition DataHub. The global estimates are increasingly embedded in these processes, but this work will need to be institutionalised in order to be sustained once the project ends. This will be a focus for the project team over the coming months.
- Nigeria became the first country to release a regular monthly bulletin tracking the Cost of a Healthy Diet (CoHD), using the same data collected for their consumer price index. Each month’s bulletin received significant attention in national media and informed a variety of policy debates, including negotiations and passage of the country’s new national minimum wage law in August 2024. Blog post here: https://www.anh-academy.org/community/blogs/nigeria-minimum-wage-increase-influenced-by-cost-of-a-healthy-diet.
- Ethiopia is now the second country to start publishing its bulletins. The project will be working closely with the partners in Ethiopia to track interest and dissemination.

Objective 3: Extend the original methods with new applications
- More work is needed to estimate affordability at a country level. No country government is yet calculating the affordability of a healthy diet, as this involves bringing in an entirely new data set on national incomes, expenditures or wages. Nigeria is now contemplating how to take this next step.
- IFPRI continues to drive progress in the modelling of policy and programme impacts using least cost diet analysis.

Objective 4: Actively disseminate data and results on food prices, diet costs, & affordability
- Publications and dissemination: The project published 10 papers in the last reporting period, as well as multiple working papers, policy briefs and blog posts.
- FPN collaborators continued to publish studies demonstrating the validity and usefulness of new food price indexes. To disseminate findings and improve methods, project staff shared new work at seven meetings and conferences, and published eight peer-reviewed journal articles, two blog posts, and one book chapter.
- The project held a stakeholder and multi-country workshop in October 2024. This brought together representatives of 6 country governments, FAO, and the World Bank to share country experiences in data collection, food matching, and diet cost calculation and discuss a vision for sustaining project activities in the long-run.

to estimate and publish the cost of a healthy diet and start estimating affordability. More Milk (Phase 2)
Brief description: The aim of the project is to improve the availability and accessibility of safe, affordable and quality milk to consumers in Kenya. This will be done through the implementation of a certification scheme to help small milk businesses operating in the informal sector transition gradually into competitive businesses, compliant with dairy regulations and able to offer a safe and affordable milk product to their customers. Expected outcomes:
- To improve the safety of the unpacked milk sold in the markets.
- To increase the number of small dairy businesses selling pasteurised milk or sourcing milk from pasteurised sources and having Kenya Dairy Board permits and county licenses to sell dairy products.
- To increase the daily volumes of milk sold by vendors participating in the scheme and their dairy revenues.
- To strengthen gender equity in the vendor node of the informal dairy sector.
Progress update: The grant agreement was signed in September 2024. The project was then launched in Nairobi in January 2025. The first progress report will be submitted in November 2025.
Key highlights: Despite the fact that this project is new, some key highlights include:
- Evolution of the project into Phase 2: This second phase of More Milk builds on the successes of Phase 1. This new phase was jointly developed by ILRI and the Kenya Dairy Board. The alignment with government of Kenya objectives for its dairy sector in this new phase can be attributed to the work achieved in Phase 1. Phase 2 will now focus on sustainably scaling the interventions researched in Phase 1, in a way that is aligned to the government’s priorities.
- Launch of Phase 2: The project was launched in January 2025, with significant positive media coverage. Participation included local and national government, farmer cooperatives, donors, NGOs and informal sector representatives (including trainers from Phase 1).
- Planning and next steps: The team will now focus on designing the compliance criteria for vendors in a way that ensures compliance but is also achievable. They will do this through rigorous consultation.
New opportunities: An exciting development has been the exploration of new technologies that could improve food safety, for example portable pasteurisers and instant chillers. The project is exploring opportunities to scale these technologies.

Recommendations for the year ahead
- FCDO and GF should commission synthesis of the closed grants as final results and publications are produced, in order to inform future investments and the PCR. [Timing: By March 2026]
- FCDO and GF should focus on agreeing follow-on activities to the Food Prices for Nutrition programme, particularly related to estimating affordability. [Timing: By June 2025]
- FCDO and GF should engage closely with More Milk 2 as the project kicks off and support the direction of activities. [Timing: In the next reporting period]

D: VALUE FOR MONEY

For all projects within this portfolio, FCDO funding is channelled through the Gates Foundation to grantees. This funding arrangement is governed by the Gates Foundation-FCDO Collaboration Framework (2016-2026). The Gates Foundation directly manages all grantees in the portfolio. the Gates Foundation issues grant agreements on behalf of both the Gates Foundation and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. This represents significant value for money for FCDO, as it leverages the technical and programmatic capacity of the Foundation, as well as project co-investments.

FCDO and the Gates Foundation are large funders of agricultural research for development globally. By working in partnership, the two funders can target joint resources and expertise to address the most pressing needs in global agriculture and food systems. FCDO is able to harness the Gates Foundation’s capacity and expertise in nutritious food systems. Our collaboration has led to significant growth in the nature and quality of the evidence base & science capability in the last decade.

The Gates Foundation covers the significant administrative and overhead costs of running these projects, without charging any management fee or overhead to FCDO. From an economy of inputs perspective, this partnership represents extremely high value for money. FCDO co-funds and steers the direction of a broad portfolio of R&D projects with strong potential for development impact, while maintaining very low transaction costs of managing the research.

Since May 2018, FCDO has seconded a staff member into the Gates Foundation to coordinate and support the partnership, with a new secondee taking over the role in March 2021 until June 2025. This role has significantly strengthened the efficiency, effectiveness and success of the partnership and discussions are ongoing about renewing this role beyond 2025.

VfM performance compared to the original VfM proposition in the business case

	5 Es		Summary of performance
Economy		GF manages the grant portfolio directly and does not charge any management fee or overhead to FCDO. This is a key component of this programme’s VFM proposition. Additionally, as noted in the Summary section of this Annual Review, FCDO’s £35m contribution to this programme is expected to leverage up to $29m in GF co-funding (over $20m leveraged to date) over the lifetime of the programme. This is in addition to the significant in-kind contribution made by GF through their management of the procurement process and handling all grant management.
Efficiency		The partnership between FCDO and GF has become increasingly efficient, in part because the two funders have now been working together on research in the agriculture sector for a number of years. The establishment of the FCDO secondment significantly strengthened the partnership between the two funders and facilitated closer involvement from FCDO. The FCDO secondee will continue to build on this work.
Effectiveness		Overall, the programme is producing highly relevant research outputs, both in terms of global public goods as well as responding to FCDO priorities. FCDO and GF are continuing to work closely together to ensure that dissemination and communication of research outputs is effective and achieves the programme’s goals. We also work together to build the pipeline for future collaboration.
Equity		The funded research prioritises the food and nutrition security of vulnerable groups including women and girls, and also investigates gendered dimensions of agriculture and nutrition, including women’s workloads and time for childcare and child feeding.
	Cost effectiveness		This programme represented strong value for money over the reporting period, with co-funding from GF, and a significant in-kind contribution through their direct handling of all the grants and procurement, on behalf of both funders. By harnessing GF’s considerable technical expertise and grant management capacity, FCDO is able to co-fund a diverse portfolio of highly relevant research projects, which it would struggle to identify and manage through any other delivery route. There is significant value for money in this type of collaboration between two of the major funders of research in the agriculture for nutrition space.

Assessment of whether the programme continues to represent value for money
The programme continues to represent good value for money for FCDO and GF. Despite some delays, this remains an important portfolio of global public goods research addressing evidence gaps in neglected areas of food systems and public health research in LMICs. The portfolio is delivering significant advances in the evidence base around nutritious food systems. As noted above, this programme directly delivers against FCDO’s commitments on nutrition spending and mainstreaming.

E: RISK

Overall, the risk rating remains moderate:

Risk category	Gross risk description	Mitigation strategy	Residual risk rating	Risk rating changed since last Annual Review?	Likely trajectory of risk severity (to Mar 26)
Delivery	Slowing pipeline of co-funded work, due to FCDO and GF budget uncertainty.	The FCDO programme team is working closely with GF to design new work, including on food safety surveillance.	Moderate	No
Context	Strategy could change within FCDO or GF, affecting the priority given to working in this partnership.	The GF Nutrition and the FCDO Agriculture Research team continue to collaborate on strategy for upcoming investments. This risk continue to be moderate due to budget reductions for this portfolio within GF. FCDO and GF are working closely together to mitigate this risk by designing a joint research agenda that optimises on both organisations’ current priorities.	Moderate	Yes
Delivery	While this grant portfolio is producing high quality research outputs, there is a risk that there will be ineffective/insufficient translation of those outputs into accessible, policy-relevant evidence syntheses and dissemination activities.	FCDO and GF continue to prioritise synthesis and research uptake. This includes disseminating published work and sharing through learning events.	Minor	Yes
Safeguarding	There is a risk that the research projects funded do not give due consideration to gender issues and ethical concerns.	FCDO’s safeguarding standards and requirements are incorporated in the grant terms of all GF/FCDO co-funded grants. For commissioned studies employing RCT approaches, FCDO and GF have worked to ensure best practice trial management, including ethical considerations and trial registration.	Minor	No
Fiduciary	GF supports the oversight of the grant management. Risk that this is not done in alignment with FCDO’s compliance and assurance requirements.	FCDO is updating the due diligence and is confident that GF has robust due diligence, whistleblowing, fraud and corruption policies and procedures. There have been no fraud concerns to date with this grant portfolio. The FCDO also has a secondee in place who supports GF with the grant management and who has close oversight of the projects.	Minor	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

For all projects within this portfolio, FCDO funding is channelled through GF to grantees. This funding arrangement is governed by the GF-FCDO Collaboration Framework (2016-2026). GF directly manages all grantees in the portfolio. GF issues grant agreements on behalf of both GF and FCDO, manages the reporting and payment schedules, and shares progress reports, financial reports and annual audited statements received from grantees with FCDO. The grant agreements between GF and grantees include all of FCDO’s core requirements – including, for example, the requirement for an annual audited statement from co-funded grantees – and has been reviewed and approved by FCDO’s assurance teams. FCDO is currently refreshing its due diligence assessment and operational guidelines, which will be completed by June 2025.

Progress reports, financial reports and annual audited statements have been submitted on time (per GF reporting schedules) by all grantees during the reporting period. FCDO SRO/Lead Adviser approval of grantees progress reports and their annual audited statement is required before payment is released. Payment is then made in US Dollars to GF for onward transmission to the grantees. Throughout the reporting period, FCDO engaged closely with GF Programme Officers to track progress on the grants, particularly through the FCDO secondee role.

Monitoring
GF maintains regular contact with FCDO on grantee progress and emerging issues. Additionally, the FCDO seconded staff member to GF from March 2021 continues to coordinate and support the partnership. This role is now supported by a FCDO Programme Manager. Both roles are strengthening the efficiency, effectiveness, and success of the FCDO-GF partnership.

Compliance with FCDO requirements
- Legal compliance: A new Gates Foundation Due Diligence assessment is currently being completed, however FCDO is confident that this programme complies with all relevant UK laws, regulations and guidance. The programme also meets the ODA definition of aid, in that the principal objective is to promote the economic development and welfare of ODA-eligible countries.
- Gender Equality: This programme is compliant with the 2014 Gender Equality Act. The portfolio of research projects works to deliver new agricultural technologies and research products which will increase agricultural productivity and improve both men and women smallholders’ resilience to climate change, diseases and pests in sub-Saharan Africa and South Asia. Gender issues are considered at the design stage of each grant.
- Due diligence and safeguarding: As mentioned, the Gates Foundation Due Diligence Assessment is in progress in Q1 2025. The assessment will include a review of Gates Foundation safeguarding policies and practices and how these are cascaded to grantees. For this programme, CDO’s safeguarding standards and requirements are incorporated in the grant terms of all GF/FCDO co-funded grants. For commissioned studies employing RCT approaches, FCDO and GF have worked to ensure best practice trial management, including ethical considerations and trial registration.
- IATI: The portfolio’s compliance with the International Aid Transparency Initiative (IATI) is under review as part of the Due Diligence process.
- Asset and risk registers: Assets and risks are reviewed in the progress reports and the annual reviews. Both of these processes will be reviewed through the Due Diligence process and updated if needed.
Environmental compliance: The objectives of this programme are in line with the Paris Agreement, and the programme contributes annual reports on two of the International Climate Finance Key Performance Indicators. Approaches to environmental impact assessment are being documented as part of the Due Diligence assessment.
Branding: Grantees acknowledge FCDO funding in written and verbal communications about the project.

Approach to the Annual Review
This Review was conducted by the SRO and Lead Adviser. The Review draws on annual reports from grantees to GF, additional supplementary information provided by GF, and discussions with GF Programme Officers.

Key Documentation:
- Programme logframe + project results frameworks, submitted to GF
- Programme business case
- Progress reports from all grants, submitted to GF

Date of last narrative financial report	Grantees each submit financial reports and audited accounts at different points during the year, depending on the reporting schedule in their grant agreement with GF. All audited accounts requirements are up to date.
Date of last audited annual statement